## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-373
MQ-4C Triton Unmanned Aircraft System (MQ-4C Triton)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 14
Low Rate Initial Production 24
Foreign Military Sales 25
Nuclear Costs 25
Unit Cost 26
Cost Variance 29
Contracts 32
Deliveries and Expenditures 36
Operating and Support Cost 37

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
MQ-4C Triton Unmanned Aircraft System (MQ-4C Triton)
DoD Component
Navy
Responsible Office
Mr. Sean Burke 47561 Ranch Road
Bldg 4023
Naval Air Station Patuxent River, MD 20670
sean.burke@navy.mil
Phone: | 301-757-5821
Fax: | 301-757-9459
DSN Phone: | 301-757-5821
DSN Fax: | 757-9459
Date Assigned: | December 18, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 7, 2009
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated July 7, 2014

## Table 6
Mission and Description
The MQ-4C Triton Unmanned Aircraft System (MQ-4C Triton) is an integrated System of Systems and a force multiplier for the Joint Force and Fleet Commander, enhancing battlespace awareness and shortening the sensor-to-shooter kill chain. The system provides multiple-sensor, persistent maritime and littoral Intelligence, Surveillance and Reconnaissance data collection and dissemination as well as an airborne communications relay capability to Combatant Commanders, Expeditionary Strike Group Commanders, Carrier Strike Group Commanders, and other designated U.S. and Joint Commanders. The addition of a de-icing capability over the baseline Global Hawk provides operators with the capability to transition through icing conditions. The mission sensors installed on the MQ-4C Triton provide 360 degree radar and Electro
-Optical/Infrared coverage. Additional functionality that optimizes the system for maritime search operations includes an Automatic Identification System and an Electronic Support Measures system. The MQ-4C Triton is a tactical, land-based, forward deployed platform that will operate from five operational sites (orbits) worldwide. It will provide surveillance when no other naval forces are present and will support operations in the littorals. Furthermore, the asset will respond to theater level operational or national strategic taskings.

## Table 7
Executive Summary
During this reporting period, the MQ-4C Triton program initiated sensor flight testing and completed development of Integrated Functional Capability (IFC) 2 software. The program marked the first use of the Main Operating Base Mission Control System installed at the test hangar at Naval Air Station Patuxent River, Maryland. The system completed the first phase of anechoic chamber testing and wrapped up the year with conduct of an Operational Assessment, which consisted of six planned flight events (totaling approximately 60 flight hours, in addition to ground and simulator events) at Patuxent River, MD. IFC 3 software, which will serve as the build for Operational Evaluation and for IOC, is now installed at the MQ- 4C Triton Systems Center at the Northrop Grumman Facility in Rancho Bernardo, CA, and will undergo a full year of integration and test in CY 2016. The MQ-4C Triton FMS team implemented an FMS technical services case with the German Federal Ministry of Defense to support the collaborative development of an Airworthiness Qualification Plan.
Milestone C preparations are underway in support of a FY 2016 LRIP decision. An Executive Production Readiness Review was conducted June 23-24, 2015. Production of the System Demonstration Test Article aircraft continued in 2015. An Advanced Acquisition Contract was awarded February 26, 2015 for long lead material in support of LRIP Lot 1.
The program is expected to be fully resourced within the FYDP at Milestone C. Funding associated with phased modifications to update sensor and system performance, including upgrades to the MQ-4C Triton’s Multiple Intelligence (Multi-INT) capabilities in support of the Chief of Naval Operations N2/N6 Intelligence, Surveillance, Reconnaissance and Targeting transition plan continues to be omitted from this report. Multi-INT funding will be reflected in the Milestone C APB and subsequent SAR. A separate PE was established for Multi-INT development to satisfy Congressional direction for increased transparency of MQ-4C Triton’s modernization funding.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | Apr 2008 | Apr 2008 | Apr 2008 | Apr 2008
System Requirements Review (SRR) | Jan 2009 | Jan 2009 | Jul 2009 | Jan 2009
Preliminary Design Review (PDR) | Jan 2010 | Jan 2010 | Jul 2010 | Feb 2010
Critical Design Review (CDR) | Jan 2011 | Jan 2011 | Jul 2011 | Feb 2011
Milestone C | May 2013 | Dec 2015 | Jun 2016 | May 2016
Operational Evaluation (OPEVAL) Start | Jan 2015 | Aug 2017 | Feb 2018 | Jan 2018
Full Rate Production (FRP) | Dec 2015 | Mar 2018 | Sep 2018 | Sep 2018
IOC | Dec 2015 | Apr 2018 | Oct 2018 | Sep 2018
Change Explanations
(Ch-1) The current estimate updates for Milestone C, OPEVAL, FRP, and IOC are a reflection of adjustments made to align with the latest program profile: Milestone C updated from December 2015 to May 2016, OPEVAL updated from August 2017 to January 2018, FRP updated from March 2018 to September 2018, and IOC updated from April 2018 to September 2018.

## Table 10
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Persistent multi-sensor maritime ISR at mission radius
On station 24 hrs a day / 7 days a week for 30 consecutive days with an ETOS of >=95% | On station 24 hrs a day / 7 days a week for 30 consecutive days with an ETOS of >=95% | On station 24 hrs a day for 7 consecutive days with ETOS of >=80% | TBD | On station 24 hrs a day / 7 days a week for 7 consecutive days with an ETOS of >=88% at a mission radius of 2,000 nm
Level of Interoperability 1-5
BLOS and LOS from MOB/ FOB (Land Based) MCS | BLOS and LOS from MOB/ FOB (Land Based) MCS | BLOS and LOS from the MOB (Land Based) MCS | BLOS and LOS from MOB (Land Based) MCS (LOI 4 and 5) | BLOS and LOS from MOB (Land Based) MCS
UA Mission Radius
>=3,000 nm | >=3,000 nm | >=2,000 nm | TBD | >=2,000 nm
Level Of Interoperability 2 Capability
LOS/BLOS multi-ISR payload reception to Maritime Forces | LOS/BLOS multi- ISR payload reception to Maritime Forces | LOS, ISR payload sensor data reception to Maritime Forces afloat (CVN, LHA/LHD) | TBD | LOS, ISR payload sensor data reception to Maritime Forces afloat (CVN, LHA/LHD)
Net Ready
IAW CJCSI 6212.01D | IAW CJCSI 6212.01D | IAW CJCSI 6212.01D | TBD | IAW CJCSI 6212.01D
Operational Availability
>=0.9 | >=0.9 | >=0.7 at IOT&E >=0.8 at IOC plus two years | TBD | >=0.86
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Development Document (CDD) dated May 21, 2007.
Change Explanations
None

## Table 11
Acronyms and Abbreviations
BLOS - Beyond Line of Sight
CJCSI - Chairman of the Joint Chiefs of Staff Instruction CVN - Aircraft Carrier Nuclear
ETOS - Effective Time On Station FOB - Forward Operating Base hrs - hours
IAW - In Accordance With
IOT&E - Initial Operational Test & Evaluation
ISR - Intelligence, Surveillance, and Reconnaissance LHA - Amphibious Assault Ship (General Purpose) LHD - Amphibious Assault Ship (Multi Purpose)
LOI - Level of Interoperability LOS - Line of Sight
MCS - Mission Control System MOB - Main Operating Base nm - nautical miles
UA - Unmanned Aircraft

## Table 12
Track to Budget
RDT&E
Appn |  | BA | PE
Navy | 1319 07 |  | 0305205N
| Project |  |  |  | Name
| 4020 |  | MQ-4C Triton |  |  | (Shared) (Sunk)
Navy | 1319 07 |  | 0305220N
| Project |  |  |  | Name
| 4020 |  | MQ-4C Triton
Notes
RDT&E funding totaling $681.2M (TY) in FY 2015 - FY 2021 funded in PE 0305421N associated with phased modifications to update sensor and system performance, including upgrades to the MQ-4C Triton's Multiple Intelligence (Multi-INT) capabilities in support of the Chief of Naval Operations N2/N6 Intelligence, Surveillance, Reconnaissance and Targeting transition plan, continues to be omitted from this report and will be reflected in the Milestone C APB and subsequent SAR.
Procurement
Appn |  | BA | PE
Navy | 1506 04 |  | 0305220N
| Line Item |  |  | Name
| 442 |  | BAMS UAS
Navy | 1506 06 |  | 0305220N
| Line Item |  |  | Name
| 605 |  | BAMS UAS |  |  |  | (Shared)
Notes
Aircraft procurement funding totaling $674.0M (TY) in FY 2018 - FY 2032 associated with phased modifications to update sensor and system performance, including upgrades to the MQ-4C Triton's Multi-INT capabilities in support of the CNOs N2/N6 Intelligence, Surveillance, Reconnaissance and Targeting transition plan, continues to be omitted from this report and will be reflected in the Milestone C APB and subsequent SAR.
MILCON
Appn |  | BA | PE
Navy | 1205 01 |  | 0203176N
| Project |  | Name
| 207655 |  | BAMS Mission Control Complex |  |  | (Sunk)
Navy | 1205 01 |  | 0212176N
| Project |  | Name
| 207662 |  | BAMS Mission Control System |  |  | (Sunk)

## Table 13
Navy | 1205 02 | 0212176N
| Project | Name
| 620240 | BAMS Facility
Navy | 1205 01 | 0212176N
| Project | Name
| 62995407 | BAMS Aircraft and Maintenance Hangar | (Sunk)
| 69232577 | BAMS Forward Operating Base 3rd Fleet
| 69232593 | BAMS Consolidated Maintenance Hangar | (Sunk)
| C1002960 | BAMS Operational Facilities | (Sunk)
Navy | 1205 01 | 0712876N
| Project | Name
| 62995407 | BAMS Triton Hangar and Operations Facility | (Sunk)
Navy | 1205 01 | 0805976N
| Project | Name
| 69232607 | Triton Avionics and Fuel Systems Trainer | (Sunk)
Navy | 1205 01 | 0815976N
| Project | Name
| 207153 | BAMS UAS Operator Training Facility | (Sunk)
| 41557625 | BAMS Forward Operational and Maintenance Hangar | (Sunk)
| 63042900 | BAMS Maintenance Training Facility | (Sunk)
| C1002154 | BAMS UAS Operator Training Facility
Navy | 1205 01 | 0816376N
| Project | Name
| 0428A263 | BAMS Test and Evaluation Facility | (Sunk)
Notes
Two new MILCON projects 69232607 and 62995407 were added to correctly align MILCON projects with program plans. No funds were expended under project 69232954.

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2008 $M |  |  |  | BY 2008 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 2989.3 |  | 3586.8 | 3945.5 |  | 3582.8 |  | 3223.6 |  | 3885.8 |  | 3858
Procurement | 8871.2 |  | 7589.9 | 8348.9 |  | 7660.9 |  | 11525.6 |  | 10315 |  | 10267.2
Flyaway | -- |  | -- | -- |  | 5852.8 |  | -- |  | -- |  | 7916.8
Recurring | -- |  | -- | -- |  | 5440.2 |  | -- |  | -- |  | 7386.6
Non Recurring | -- |  | -- | -- |  | 412.6 |  | -- |  | -- |  | 530.2
Support | -- |  | -- | -- |  | 1808.1 |  | -- |  | -- |  | 2350.4
Other Support | -- |  | -- | -- |  | 1521.8 |  | -- |  | -- |  | 2012.3
Initial Spares | -- |  | -- | -- |  | 286.3 |  | -- |  | -- |  | 338.1
MILCON | 364 |  | 292.7 | 322 |  | 267.9 |  | 423.1 |  | 342.6 |  | 309.5
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 12224.5 |  | 11469.4 | N/A |  | 11511.6 |  | 15172.3 |  | 14543.4 |  | 14434.7
Current APB Cost Estimate Reference
Service Cost Position dated April 25, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current APB cost estimate assumes sufficient resources to execute the program under normal conditions; encountering average levels of technical, schedule, and programmatic risk and external interference. It is consistent with average resource expenditures based on historical actual cost data and represents a notional 50% confidence level when established.
Cost Notes
RDT&E funding totaling $681.2M (TY) in FY 2015 - FY 2021 and Aircraft Procurement, Navy funding totaling $674.0M (TY) in FY 2018 - FY 2032 associated with phased modifications to update sensor and system performance, including upgrades to the MQ-4C Triton's Multiple Intelligence capabilities in support of the Chief of Naval Operations N2/N6 Intelligence, Surveillance, Reconnaissance, and Targeting transition plan, continues to be omitted from this report.
Funding values are based on PB 2017.

## Table 15
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 5 | 4 | 4
Procurement | 65 | 66 | 66
Total | 70 | 70 | 70

## Table 16
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 3508.1 | 227.1 |  | 111.7 |  | 9 | 2.1 |  | 0 |  | 0 |  | 0 |  |  | 3858
Procurement | 67.7 | 723.6 |  | 579.1 |  | 637.2 | 651.7 |  | 670.5 |  | 702.9 |  | 6234.5 |  |  | 10267.2
MILCON | 158 | 51.9 |  | 71.9 |  | 0 | 27.7 |  | 0 |  | 0 |  | 0 |  |  | 309.5
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
PB 2017 Total | 3733.8 | 1002.6 |  | 762.7 |  | 646.2 | 681.5 |  | 670.5 |  | 702.9 |  | 6234.5 |  |  | 14434.7
PB 2016 Total | 3766 | 981.9 |  | 768.9 |  | 690.3 | 688.6 |  | 660.2 |  | 762.1 |  | 6010.5 |  |  | 14328.5
Delta | -32.2 | 20.7 |  | -6.2 |  | -44.1 | -7.1 |  | 10.3 |  | -59.2 |  | 224 |  |  | 106.2
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 4 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 4
Production | 0 |  | 0 |  | 4 | 2 | 3 |  | 3 |  | 5 | 6 |  | 43 |  | 66
PB 2017 Total | 4 |  | 0 |  | 4 | 2 | 3 |  | 3 |  | 5 | 6 |  | 43 |  | 70
PB 2016 Total | 4 |  | 0 |  | 3 | 3 | 4 |  | 4 |  | 4 | 4 |  | 44 |  | 70
Delta | 0 |  | 0 |  | 1 | -1 | -1 |  | -1 |  | 1 | 2 |  | -1 |  | 0

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 420.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 438.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 525.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 550.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 612.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 375.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 419.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 227.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 111.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
Subtotal |  | 4 | -- |  | -- |  | -- |  | -- |  | -- |  | 3858

## Table 18
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.6
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 82.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 410.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 421.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 494.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 509
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 560.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 338.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 373.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 199.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 96.2
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.6
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
Subtotal |  | 4 | -- |  | -- |  | -- |  | -- |  | -- |  | 3582.8

## Table 19
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | -- | 67.7 |  | -- |  | -- |  | 67.7 |  | -- |  | 67.7
2016 |  | 4 | 352.2 |  | -- |  | 94.4 |  | 446.6 |  | 277 |  | 723.6
2017 |  | 2 | 265.9 |  | -- |  | 55.5 |  | 321.4 |  | 257.7 |  | 579.1
2018 |  | 3 | 321.4 |  | -- |  | 87.3 |  | 408.7 |  | 228.5 |  | 637.2
2019 |  | 3 | 363.1 |  | -- |  | 46.5 |  | 409.6 |  | 242.1 |  | 651.7
2020 |  | 5 | 489.9 |  | -- |  | 50.5 |  | 540.4 |  | 130.1 |  | 670.5
2021 |  | 6 | 510.7 |  | -- |  | 16.7 |  | 527.4 |  | 175.5 |  | 702.9
2022 |  | 4 | 418.3 |  | -- |  | 8.2 |  | 426.5 |  | 120 |  | 546.5
2023 |  | 4 | 426.7 |  | -- |  | 8.3 |  | 435 |  | 86.4 |  | 521.4
2024 |  | 4 | 435.7 |  | -- |  | 8.4 |  | 444.1 |  | 79.2 |  | 523.3
2025 |  | 4 | 445 |  | -- |  | 8.6 |  | 453.6 |  | 79.2 |  | 532.8
2026 |  | 4 | 454.7 |  | -- |  | 8.8 |  | 463.5 |  | 80.9 |  | 544.4
2027 |  | 4 | 464.9 |  | -- |  | 9 |  | 473.9 |  | 72.5 |  | 546.4
2028 |  | 4 | 475.4 |  | -- |  | 9.2 |  | 484.6 |  | 74 |  | 558.6
2029 |  | 4 | 486.3 |  | -- |  | 9.4 |  | 495.7 |  | 75.5 |  | 571.2
2030 |  | 4 | 497.7 |  | -- |  | 9.6 |  | 507.3 |  | 77 |  | 584.3
2031 |  | 4 | 481.7 |  | -- |  | 9.8 |  | 491.5 |  | 78.6 |  | 570.1
2032 |  | 3 | 429.3 |  | -- |  | 90 |  | 519.3 |  | 216.2 |  | 735.5
Subtotal |  | 66 | 7386.6 |  | -- |  | 530.2 |  | 7916.8 |  | 2350.4 |  | 10267.2

## Table 20
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | -- | 59.6 |  | -- |  | -- |  | 59.6 |  | -- |  | 59.6
2016 |  | 4 | 304.7 |  | -- |  | 81.7 |  | 386.4 |  | 239.6 |  | 626
2017 |  | 2 | 225.7 |  | -- |  | 47.1 |  | 272.8 |  | 218.8 |  | 491.6
2018 |  | 3 | 267.6 |  | -- |  | 72.7 |  | 340.3 |  | 190.3 |  | 530.6
2019 |  | 3 | 296.4 |  | -- |  | 38 |  | 334.4 |  | 197.6 |  | 532
2020 |  | 5 | 392.1 |  | -- |  | 40.4 |  | 432.5 |  | 104.1 |  | 536.6
2021 |  | 6 | 400.7 |  | -- |  | 13.1 |  | 413.8 |  | 137.7 |  | 551.5
2022 |  | 4 | 321.8 |  | -- |  | 6.3 |  | 328.1 |  | 92.3 |  | 420.4
2023 |  | 4 | 321.8 |  | -- |  | 6.3 |  | 328.1 |  | 65.1 |  | 393.2
2024 |  | 4 | 322.1 |  | -- |  | 6.2 |  | 328.3 |  | 58.6 |  | 386.9
2025 |  | 4 | 322.6 |  | -- |  | 6.2 |  | 328.8 |  | 57.4 |  | 386.2
2026 |  | 4 | 323.1 |  | -- |  | 6.3 |  | 329.4 |  | 57.5 |  | 386.9
2027 |  | 4 | 323.9 |  | -- |  | 6.3 |  | 330.2 |  | 50.5 |  | 380.7
2028 |  | 4 | 324.7 |  | -- |  | 6.3 |  | 331 |  | 50.6 |  | 381.6
2029 |  | 4 | 325.7 |  | -- |  | 6.3 |  | 332 |  | 50.5 |  | 382.5
2030 |  | 4 | 326.8 |  | -- |  | 6.3 |  | 333.1 |  | 50.5 |  | 383.6
2031 |  | 4 | 310 |  | -- |  | 6.3 |  | 316.3 |  | 50.6 |  | 366.9
2032 |  | 3 | 270.9 |  | -- |  | 56.8 |  | 327.7 |  | 136.4 |  | 464.1
Subtotal |  | 66 | 5440.2 |  | -- |  | 412.6 |  | 5852.8 |  | 1808.1 |  | 7660.9

## Table 21
Cost Quantity Information 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2008 $M
2015 | -- | --
2016 | 4 | 304.7
2017 | 2 | 225.7
2018 | 3 | 267.6
2019 | 3 | 296.4
2020 | 5 | 392.1
2021 | 6 | 400.7
2022 | 4 | 321.8
2023 | 4 | 321.8
2024 | 4 | 322.1
2025 | 4 | 322.6
2026 | 4 | 323.1
2027 | 4 | 323.9
2028 | 4 | 324.7
2029 | 4 | 325.7
2030 | 4 | 326.8
2031 | 4 | 310
2032 | 3 | 330.5
Subtotal | 66 | 5440.2

## Table 22
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2011 | 33
2012 | 4.5
2013 | 65
2014 | 55.5
2015 | --
2016 | 51.9
2017 | 71.9
2018 | --
2019 | 27.7
Subtotal | 309.5

## Table 23
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2008 $M
Total Program
2011 | 30.4
2012 | 4.1
2013 | 58.1
2014 | 48.9
2015 | --
2016 | 44.2
2017 | 60
2018 | --
2019 | 22.2
Subtotal | 267.9

## Table 24
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2008-04-18 | 2011-11-01
Approved Quantity | 10 | 10
Reference | Milestone B ADM | ADM
Start Year | 2013 | 2013
End Year | 2015 | 2017
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the establishment of an initial production base for the system and an orderly and efficient increase in the production rate.
The April 18, 2008 Milestone B ADM approved the planning for the program's Milestone C LRIP decision and stipulated the quantity will not exceed ten unmanned aircraft systems and related ground control systems.
A subsequent ADM directed redesignation of the first lot of aircraft from LRIP Lot 1 to System Demonstration Test Articles (SDTAs), with LRIP Lot 1 to follow. The SDTA aircraft will validate critical KPPs in developmental test and serve as the test articles for Operational Evaluation (OPEVAL). These aircraft will receive hardware and software updates as required to make them production representative and will be transferred for operational use at the conclusion of OPEVAL. The result of redesignating this lot of aircraft is a net reduction in the quantity produced as LRIP. The program is authorized to
procure ten LRIP aircraft but currently plans to procure six aircraft before proceeding to a FRP decision. The total number of vehicles delivered for operational use over the life of the program, and the funding source for each lot of aircraft, are unaffected by this decision.

## Table 25
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Germany 4/2/2015 2.0 Agreement number: GY-P-GPT is an active planning case which provides technical data on the MQ-4C Triton.
Australia 8/1/2013 5.0 Agreement number: AT-P-GTJ is an active planning case which provides technical data on the MQ-4C Triton.
Notes
The program office is currently executing two FMS technical services planning cases for information on the MQ-4C Triton with both Australia and Germany to help them determine if the MQ-4C Triton will meet their needs for a platform. Other interested foreign governments include Canada, Japan, Germany, Norway and the United Kingdom.
Nuclear Costs
None

## Table 26
Unit Cost
Unit Cost Report
Item |  | BY 2008 $M | BY 2008 $M |  |  | % Change
|  | Current UCR Baseline (Jul 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 11469.4 |  |  |  | 11511.6
Quantity | 70 |  |  |  | 70
Unit Cost | 163.849 |  |  |  | 164.451 |  | 0.37
Average Procurement Unit Cost
Cost | 7589.9 |  |  |  | 7660.9
Quantity | 66 |  |  |  | 66
Unit Cost | 114.998 |  |  |  | 116.074 |  | 0.94
Item |  | BY 2008 $M |  | BY 2008 $M |  | % Change
|  | Original UCR Baseline (Feb 2009 APB) |  | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 12224.5 |  |  |  | 11511.6
Quantity | 70 |  |  |  | 70
Unit Cost | 174.636 |  |  |  | 164.451 |  | -5.83
Average Procurement Unit Cost
Cost | 8871.2 |  |  |  | 7660.9
Quantity | 65 |  |  |  | 66
Unit Cost | 136.48 |  |  |  | 116.074 |  | -14.95

## Table 27
Unit Cost History
Item | [5 empty] | Date |  |  | BY 2008 $M | [5 empty] | TY $M
[9 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Feb 2009 | [5 empty] | 174.636 |  |  |  | 136.48 |  |  | 216.747 |  |  | 177.317
APB as of January 2006 |  |  | N/A | [5 empty] | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A | [5 empty] | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Jan 2012 | [5 empty] | 174.636 |  |  |  | 136.48 |  |  | 216.747 |  |  | 177.317
Current APB |  |  | Jul 2014 | [5 empty] | 163.849 |  |  |  | 114.998 |  |  | 207.763 |  |  | 156.288
Prior Annual SAR |  |  | Dec 2014 | [5 empty] | 162.361 |  |  |  | 115.08 |  |  | 204.693 |  |  | 155.253
Current Estimate |  |  | Dec 2015 | [5 empty] | 164.451 |  |  |  | 116.074 |  |  | 206.21 |  |  | 155.564
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [15 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  |  | Eng | Est |  | Oth |  | Spt |  | Total
216.747 -7.233 1.732 19.107 -0.407 3.004 0.000 -26.740 -10.537 206.210
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [15 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng | Est |  | Oth |  | Spt |  | Total
177.317 -6.618 -0.850 20.265 0.000 -5.680 0.000 -28.870 -21.753 155.564

## Table 28
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Apr 2008 | N/A | Apr 2008
Milestone C | N/A | May 2013 | N/A | May 2016
IOC | N/A | Dec 2015 | N/A | Sep 2018
Total Cost (TY $M) | N/A | 15172.3 | N/A | 14434.7
Total Quantity | N/A | 70 | N/A | 70
PAUC | N/A | 216.747 | N/A | 206.21

## Table 29
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 3223.6 | 11525.6 | 423.1 | 15172.3
Previous Changes
Economic | -57.5 | -350.8 | -2.8 | -411.1
Quantity | -- | 121.2 | -- | 121.2
Schedule | -- | 1348.6 | -- | 1348.6
Engineering | 22.3 | -- | -- | 22.3
Estimating | 550.7 | -954.1 | -111.2 | -514.6
Other | -- | -- | -- | --
Support | 33.6 | -1443.8 | -- | -1410.2
Subtotal | 549.1 | -1278.9 | -114 | -843.8
Current Changes
Economic | -7.4 | -86 | -1.8 | -95.2
Quantity | -- | -- | -- | --
Schedule | -- | -11.1 | -- | -11.1
Engineering | -50.8 | -- | -- | -50.8
Estimating | 143.5 | 579.2 | 2.2 | 724.9
Other | -- | -- | -- | --
Support | -- | -461.6 | -- | -461.6
Subtotal | 85.3 | 20.5 | 0.4 | 106.2
Total Changes | 634.4 | -1258.4 | -113.6 | -737.6
CE - Cost Variance | 3858 | 10267.2 | 309.5 | 14434.7
CE - Cost & Funding | 3858 | 10267.2 | 309.5 | 14434.7

## Table 30
Summary BY 2008 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 2989.3 | 8871.2 | 364 | 12224.5
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | 81 | -- | 81
Schedule | -- | 588.6 | -- | 588.6
Engineering | 19.2 | -- | -- | 19.2
Estimating | 464.4 | -752.3 | -97.9 | -385.8
Other | -- | -- | -- | --
Support | 31 | -1193.2 | -- | -1162.2
Subtotal | 514.6 | -1275.9 | -97.9 | -859.2
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | 1.7 | -- | 1.7
Engineering | -43.1 | -- | -- | -43.1
Estimating | 122 | 435.9 | 1.8 | 559.7
Other | -- | -- | -- | --
Support | -- | -372 | -- | -372
Subtotal | 78.9 | 65.6 | 1.8 | 146.3
Total Changes | 593.5 | -1210.3 | -96.1 | -712.9
CE - Cost Variance | 3582.8 | 7660.9 | 267.9 | 11511.6
CE - Cost & Funding | 3582.8 | 7660.9 | 267.9 | 11511.6
Previous Estimate: December 2014

## Table 31
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -7.4
Adjustment for current and prior escalation. (Estimating) | 6.7 | 7.4
Revised estimate to align with the current approved program baseline. (Estimating) | 115.3 | 136.1
Revised estimate to align work scope not included in the baseline MQ-4C Triton APB to the | -43.1 | -50.8
Modernization PE. (Engineering)
RDT&E Subtotal +78.9 +85.3
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -86.0
Adjustment for current and prior escalation. (Estimating) +2.9 +3.2
Acceleration of procurement buy profile (moved 1 Unmanned Aircraft (UA) from FY 2017 to FY 2016). (Schedule)
0.0 -17.6
Additional schedule variance (moved 1 UA from FY 2017 to FY 2016). (Schedule) +1.7 +6.5
Realized savings based on providing Electro-Optical Infrared as Government Furnished Equipment. (Estimating)
Revised estimate for obsolescence methodology change from three years to annually. (Estimating)
Revised estimate for radar modification to Antenna Group Assembly to reduce future O&S costs. (Estimating)
Revised estimate for Triton major sub-contractors using actuals provided with the LRIP 1 Proposal. (Estimating)
Revised estimate for the MQ-4C Triton wing using actuals provided with the LRIP 1 Proposal. (Estimating)
Revised estimate for Northrop Grumman Corporation prime labor using actuals provided with the LRIP 1 Proposal. (Estimating)
-44.7 -60.8
+60.3 +78.4
+25.0 +30.0
+89.0 +123.7
+205.9 +278.7
+97.5 +126.0
Adjustment for current and prior escalation. (Support) +2.3 +2.8
Decrease in Other Support for Production Engineering Support, organic depot planning, and organic depot stand-up. (Support)
Decrease in Initial Spares as a result of Congressional reduction in FY 2016 which shifted the initial spares account to a replenishment account increasing risk to aircraft availability during an interim period following IOC. (Support)
-150.0 -183.1
-224.3 -281.3
Procurement Subtotal +65.6 +20.5
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -1.8
Adjustment for current and prior escalation. (Estimating) | 0.9 | 1
Revised estimate due to Navy-wide funding adjustments. (Estimating) | 0.9 | 1.2
MILCON Subtotal | 1.8 | 0.4

## Table 32
Contracts
General Notes
In previous years SARs (2011-2014) the System Development and Demonstration (SDD) and System Development Test Article (SDTA) contracts were reported as one effort under the same contract number. This year the program is reporting all CLINs on the SDD contract individually to increase transparency as each individual effort is over 40M TY$.
Contract Identification
Appropriation: RDT&E
Contract Name: BAMS UAS SDD Contract
Contractor: Northrop Grumman Systems Corporation
Contractor Location: 17006 Goldentop Rd
San Diego, CA 92150
Contract Number: N00019-08-C-0023
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: April 22, 2008
Definitization Date: April 22, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1164.0 N/A 2 1970.9 N/A 2 2666.1 2615.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract scope increases negotiated to satisfy United States Navy requirements.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) |  |  |  | -106.1 |  |  |  | -38
Previous Cumulative Variances |  |  |  | -22.3 |  |  |  | -51.2
Net Change |  |  |  | -83.8 |  |  |  | 13.2

## Table 33
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to continued greater than expected software defect corrections, increased and extended mission systems flight and ground test support at Patuxent River, MD, and test procedure maturity.
The favorable net change in the schedule variance is due to [See General Variance Explanation below]. There is not a favorable net change in schedule variance. There is an unfavorable net change in schedule variance.
General Contract Variance Explanation
Due to the break out of the SDTA and Air-to-Air Radar Sub-System (AARSS) CLINs, the contract variance section was manually calculated. This issue will be corrected in the 2016 SAR submission:
Cumulative Variances To Date (01/26/2016): Cost: -106.1/Schedule: -38.0 Previous Cumulative Variances: Cost: -24.9/Schedule: -28.2 Net Change: Cost: -81.2/Schedule: -9.8
Schedule Variance Explanations
The unfavorable net change in the schedule variance is due to Integrated Functional Capability-3.1 schedule delays impacting software configuration, coupon testing and fatigue test analysis efforts being delayed, and flight test delays.

## Table 34
Contract Identification
Appropriation: RDT&E
Contract Name: BAMS UAS SDD Contract SDTA CLIN
Contractor: Northrop Grumman Systems Corporation
Contractor Location: 17006 Goldentop Rd
San Diego, CA 92150
Contract Number: N00019-08-C-0023/1 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: November 04, 2011
Definitization Date: November 04, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
280.3 N/A 3 283.4 N/A 2 241.6 292.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract scope increases negotiated to satisfy United States Navy requirements.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) -1.2 -30.3
Previous Cumulative Variances -- --
Net Change -1.2 -30.3
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to the Air Vehicle team’s effort to assist with the repair of the wings.
The unfavorable cumulative schedule variance is due to wing quality issues at Triumph that are delaying the wing deliveries.
Notes
This is the first time this contract is being reported.
Due to the break out of the System Demonstration Test Article and Air-to-Air Radar Sub-System (AARSS) CLINs the contract variance section was manually calculated, this issue will be corrected in the 2016 SAR submission:
Cumulative Variances To Date (1/29/2016): Cost: -1.2/Schedule: -30.3 Previous Cumulative Variances: Cost: +2.7/Schedule: -22.9 Net Change: Cost: -3.9/Schedule: -7.4

## Table 35
Contract Identification
Appropriation: RDT&E
Contract Name: BAMS UAS SDD Contract AARSS CLIN
Contractor: Northrop Grumman Systems Corporation
Contractor Location: 17066 Goldentop Rd
San Diego, CA 92150
Contract Number: N00019-08-C-0023/402
Contract Type: Cost (CR)
Award Date: June 16, 2015
Definitization Date: June 16, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
39.1 N/A 0 39.1 N/A 0 38.9 39.1
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/29/2016) -0.9 -0.5
Previous Cumulative Variances -- --
Net Change -0.9 -0.5
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to the antenna development, radar build, and integration work being completed with less than planned amount of resources and also due to the work being lower than expected cost.
The unfavorable cumulative schedule variance is due to the Thin Tile Subarray Assembly development work experiencing delays.
Notes
This is the first time this contract is being reported.
A modification is anticipated that will increase the contract value above $40M.

## Table 36
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 2 | 2 | 4 | 50%
Production | 0 | 0 | 66 | 0%
Total Program Quantity Delivered | 2 | 2 | 70 | 2.86%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
14434.7
3554.8
24.63%
29
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
13
44.83%
4736.4
32.81%
The above data is current as of March 02, 2016.

## Table 37
Operating and Support Cost
Cost Estimate Details
Date of Estimate: April 09, 2014
Source of Estimate: SCP
Quantity to Sustain: 68
Unit of Measure: Aircraft
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2018 - FY 2045
The average monthly flight hour utilization rate is 256.2 flight hours/month/aircraft, and the average annual flight hour utilization rate is 3,074.4 flight hours/year/aircraft. Primary Authorized Aircraft is 20, and these 20 aircraft are to be distributed equally across five orbits. The program is estimated to have four year ramp up period, followed by a 20 year service period, followed by a four year ramp down period which results in 456.832 aircraft years. The predicted attrition rate of this Unmanned Aircraft System is four per 100,000 flight hours. Two of the 70 aircraft will remain as test articles, resulting in a quantity to sustain of 68 aircraft.
Sustainment Strategy
The MQ-4C Sustainment Strategy focuses on total platform support to ensure compliance with operational requirements and metrics as defined by the Fleet via a Warfighter Performance Based Agreement. The Life Cycle Sustainment Strategy is being evaluated by a series of single element Business Case Analyses and studies to identify element support strategies that provide the greatest cost, benefit, performance and risk solutions for each element to comply with Naval Organizational, Intermediate, and Depot Level Maintenance Concepts. Maintenance support will be Organic.
Antecedent Information
No Antecedent. The MQ-4C Triton is projected to fly significantly more hours than the closest analogous airframe and has different missions, different concept of operations, and different payloads; resulting in substantially different projected avionics repair costs (the next major O&S cost driver after the number of flight hours).
Annual O&S Costs BY2008 $M
Cost Element | MQ-4C Triton Average Annual Cost Per Aircraft | No Antecedent (Antecedent) N/A
Unit-Level Manpower | 3.558 | 0
Unit Operations | 1.848 | 0
Maintenance | 15.404 | 0
Sustaining Support | 0.793 | 0
Continuing System Improvements | 1.757 | 0
Indirect Support | 1.337 | 0
Other | 0 | 0
Total | 24.697 | --

## Table 38
Item | Total O&S Cost $M
| MQ-4C Triton | [5 empty] | No Antecedent (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 11282.4 |  | 12410.6 |  |  | 11282.4 | N/A
Then Year | 17309 |  | N/A |  |  | 17309 | 0
Equation to Translate Annual Cost to Total Cost
Total Aircraft O&S = Unitized cost * number of operational aircraft years ($11,282.4M = $24.697M * 456.832 aircraft years)
O&S Cost Variance
Category |  | BY 2008 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
11282.4
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 11282.4
Disposal Estimate Details
Date of Estimate: April 09, 2014
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2008 $M): Total costs for disposal of all Aircraft are 15.6
Disposal of attrition aircraft is included in the Disposal estimate.