## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-334
P-8A Poseidon Multi-Mission Maritime Aircraft (P-8A)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 10
Schedule 11
Performance 12
Track to Budget 14
Cost and Funding 16
Low Rate Initial Production 25
Foreign Military Sales 26
Nuclear Costs 26
Unit Cost 27
Cost Variance 30
Contracts 33
Deliveries and Expenditures 36
Operating and Support Cost 37

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
P-8A Poseidon Multi-Mission Maritime Aircraft (P-8A)
DoD Component
Navy
Responsible Office
CAPT Scott Dillon
PMA-290, Maritime Patrol & Reconnaissance Aircraft Program Executive Office, Air Anti-Submarine Warfare, Assault and Special Mission Programs
22347 Cedar Point Rd, Building 2185, STE 3190, Unit 6 Patuxent River, MD 20670-1161
william.dillon@navy.mil
Phone: 301-757-5703
Fax: 301-757-5681
DSN Phone: 757-5703
DSN Fax: 757-5681
Date Assigned: May 29, 2012
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Progam Baseline (APB) dated October 22, 2010
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 5, 2014

## Table 6
Mission and Description
The primary roles of P-8A Poseidon Multi-mission Maritime Aircraft (P-8A) are persistent Anti-Submarine Warfare and Anti- Surface Warfare. The P-8A is the replacement system for the P-3C, Orion. The P-8A, is based on the 737-800 ERX developed by The Boeing Company. The management of the contracted effort is located at The Boeing Company in Seattle, Washington. The system requirements are based on the P-8A CPD #791-88-09, validated and approved on June 22, 2009. The P-8A system will sustain and improve the armed maritime and littoral Intelligence, Surveillance, and Reconnaissance capabilities for United States Naval forces in traditional, joint and combined roles to counter changing and emerging threats. The P-8A program is structured on an evolutionary systems replacement approach that aligns the processes employed for requirements definition, acquisition strategy, and system development into a dynamic and flexible means to attain the strategic vision for tomorrow's Naval forces. The P-8A is part of the Maritime Patrol and Reconnaissance Force Family of Systems that also includes the MQ-4C Triton Unmanned Aircraft System, the EP-3, and the Tactical Operations Center.

## Table 7
Executive Summary
Program Highlights Since Last Report: In 2015, the P-8A Poseidon program remained focused on aircraft production, deliveries, and site stand-up in support of fleet transition. Current program focus also includes procurement of depot and intermediate level maintenance capabilities, full scale fatigue testing, and continued integration and fleet delivery of pre- planned incremental capability upgrades. The first upgrade under P-8A Increment 2 (Inc 2) added a broad-area, multi-static acoustic ASW capability to the aircraft. This capability, referred to as Multi-Static Active Coherent (MAC), significantly increases the P-8A's ASW search rate in littoral environments. MAC completed Follow on Test and Evaluation in April 2015 and has been delivered to the fleet. The capability is scheduled to receive periodic future enhancements in order to pace the ASW threat. The U.S. Navy (USN) is on track to field additional Inc 2 MAC and High Altitude ASW Sensor capability in 2016, followed by a High Altitude ASW Weapon capability as part of the P-8A’s on-going incremental upgrade strategy. The P-8 airframe full scale fatigue test program initiated the Advanced Airborne Sensor pod carriage phase in September 2015.
Aircraft production and delivery continues on schedule in support of the on-going transition of fleet squadrons from P-3C to P-8A. Six lots of production aircraft, including 62 aircraft, trainers, spares and support equipment, are on contract with Boeing Defense Space and Security. As of February 2016, fleet squadrons have taken delivery of 35 aircraft on or ahead of schedule. The P-8A Material Support Date (MSD), marking the transition of supply support responsibilities from the Prime Contractor to the Navy Supply System, was successfully achieved on October 1, 2015. The P-8A is successfully meeting flight line commitments post-MSD. The P-8A Integrated Training Center at Naval Air Station (NAS) Jacksonville, Florida continues to meet training requirements of the Fleet Replacement Squadron (FRS) and transitioning squadrons.
Continuous 7th fleet operational deployments are underway. The first 5th fleet deployment will commence April 2016.
The sixth of ten planned annual production contracts was awarded August 27, 2015. This contract included the first four of eight Royal Australian Air Force P-8A aircraft, with the initial Australian delivery scheduled for November 2016. On November 23, 2015 the Prime Minister of the United Kingdom (UK) announced an intention to procure nine P-8As. The USN is supporting planning for this anticipated acquisition via a UK P-8A Technical Assistance case.
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation:
February 29, 2000: The Broad Area Maritime and Littoral Armed Intelligence Surveillance and Reconnaissance Mission Needs Statement was validated and approved by the JROC.
April 17, 2000: The P-8A Poseidon (formerly Multi-Mission Maritime Aircraft (MMA)) program received Milestone 0 approval to enter Concept Exploration.
January 18, 2002: P-8A received approval to enter the Component Advanced Development (CAD) work effort on January 18, 2002. CAD included competitively awarded contracts to Lockheed Martin for the Orion 21 concept (P-3 derivative) and to Boeing for the military derivative of the 737 aircraft.
December 3, 2003: The MMA ORD/CDD was validated and approved by JROC.
May 28, 2004: The USD (AT&L) approved the program and entry into System Development and Demonstration (SDD) after completing a successful Milestone (MS) B DAB Review.
June 4, 2004: MS B ADM signed.
June 14, 2004: The SDD contract was awarded to BDS (formerly, McDonnell Douglas Corporation, a wholly-owned subsidiary of The Boeing Company) for the 737-800 ERX based system. The contracted effort included the design and development of Systems Integration Labs and the design, development, and build of ground and flight test articles.
June 11-15, 2007: The P-8A program conducted the Critical Design Review.

## Table 8
August 27, 2007: The P-8A program completed the Design Readiness Review.
December 2007: The P-8A program initiated the fabrication of its first flight test aircraft at Spirit AeroSystems in Wichita, Kansas.
April 2008: The P-8A program conducted the Integration Readiness Review.
December 23, 2008: The Record of Decision was approved for basing 12 P-8A squadrons and 1 FRS at NAS Jacksonville, Florida, NAS Whidbey Island, Washington, and Marine Corps Base Hawaii at Kaneohe Bay, Hawaii.
April 2009: Australia joined as a cooperative partner of P-8A Inc 2. The Inc 2 Memorandum of Understanding (MOU) authorizes Australian participation in P-8A Inc 2 development.
April 13, 2009: The P-8A program completed the Interim Program Review and awarded the Advance Acquisition Contract (AAC) for LRIP Advance Procurement (AP).
May 2009: The P-8A program conducted Test Readiness Reviews for the first flight test aircraft and the first ground test aircraft for static test.
September 2009: The Operational Assessment was initiated utilizing the Weapon System Integration Lab.
August 27, 2010: The USD (AT&L) signed the MS C ADM granting authorization to: proceed with LRIP Lots I through III that included 6 aircraft in FY 2010, 7 aircraft in FY 2011, and 11 aircraft in FY 2012. In addition, the MS C ADM approved the request to obligate FY 2012 AP funding for FRP and authorized the Navy to proceed with Automatic Identification System, MAC, High Altitude ASW Weapon Capability, Rapid Capability Insertion, Acoustics Algorithms, and Tactical Operations Center updates.
January 21, 2011: The LRIP Lot I contract was definitized for six aircraft.
April 13, 2011: The USD (AT&L) documented in a Memorandum for the Record that the P-8A program satisfied the MS C ADM waived affordability and funding provisions of section 2366b of title 10, United States Code (U.S.C.). At MS C, the USD (AT&L) certified the program in accordance with section 2366b of Title 10, U.S.C., waiving two elements in that certification, namely 2366b(a)(l)(B) and 2366b(a)(1)(D), affordability and funding.
November 3, 2011: The LRIP Lot II contract was definitized for seven aircraft.
March 2012: The Production, Sustainment, and Follow-on Development MOU authorizes Australian procurement of Inc 2 capable P-8 aircraft, participation in development of common sustainment strategies for the life of the aircraft, and participation in development of new platform capabilities.
September 21, 2012: The LRIP Lot III contract was definitized for 11 aircraft. February 2013: Live Fire Test and Evaluation was completed.
March 2013: The P-8A Poseidon successfully completed Initial Operational Test and Evaluation (IOT&E).
July 2013: The IOT&E report released by Commander, Operational Test and Evaluation Force rated the P-8A as operationally effective, operationally suitable, and recommended Fleet introduction.
July 15, 2013: In order to maintain fleet transition rates, the USD (AT&L) approved a change to the P-8A Acquisition Strategy to add a fourth lot of 13 LRIP aircraft in FY 2013.
July 30, 2013: The LRIP Lot IV contract was definitized for 13 aircraft.
September 2013: Integrated testing of deficiency corrections and the Harpoon Anti-Surface Warfare weapon integration were successfully completed.

## Table 9
December 2013: The P-8A achieved IOC and commenced first Fleet operational deployment. January 3, 2014: The USD(AT&L) signed the FRP ADM approving the FRP decision.
February 2014: The Australian government announced its plan to purchase eight P-8A aircraft and supporting infrastructure.
February 25, 2014: The FRP I (Lot V) contract was definitized for 16 aircraft.
August 14, 2014: USN awarded the P-8A FRP II (Lot VI) AAC for AP funding for 8 USN and 4 Royal Australian Air Force (RAAF) aircraft. Contract value is $295.6M.
January 2, 2015: January 2, 2015: USN awarded a $60.7 million contract modification to BDS to the P-8A LRIP IV and FRP I Contract (N00019-12-C-0112) to incorporate recurring Advanced Airborne Sensor Capability Platform Integration Kits In- Line modifications to LRIP IV (13 aircraft) and FRP I (16 aircraft).
January 24, 2015: P-8A MAC operational evaluation was completed during a VX-1 detachment to Jacksonville, FL. Feedback indicated that all requirements to satisfy the Operational Test plan for P-8A Inc 2 ECP 1 were successfully completed.
February 12, 2015: Fleet Squadron (VP-5) returned home completing the second P-8A operational deployment. March 3, 2015: Fleet Squadron (VP-10) began P-3 to P-8 transition training along with the RAAF Exchange Cadre.
August 27, 2015: The FRP II Lot VI P-8A production contract definitized for $1.5 billion. The contract includes 9 USN and 4 Australian Lot VI aircraft, as well as a priced option for 16 USN and 4 Australian Lot VII aircraft.
September 2015: Fleet Squadron (VP-16) commenced the fourth consecutive seven month P-8A operational deployment. VP-16 began operational deployment to PACOM AOR, marking the first return P-8 deployer.
October 2015: Fleet Squadron (VP-26) began P-3 to P-8A transition training.

## Table 10
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 11
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | May 2004 | May 2004 | Nov 2004 | May 2004
Design Readiness Review (DRR) | Jul 2007 | Jul 2007 | Jan 2008 | Aug 2007
Interim Program Review (IPR) | Apr 2009 | Apr 2009 | Oct 2009 | Apr 2009
Milestone C | May 2010 | May 2010 | Nov 2010 | Aug 2010
Initial Operational Test & Evaluation (IOT&E)
Start | Apr 2012 | Apr 2012 | Oct 2012 | Sep 2012
Complete | Feb 2013 | Feb 2013 | Aug 2013 | Mar 2013
IOC | Jul 2013 | Jul 2013 | Jan 2014 | Dec 2013
Full Rate Production (FRP) | Apr 2013 | Nov 2013 | May 2014 | Jan 2014
Change Explanations

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Mission Radius/Endurance Subsurface attack (nm)
>=1,600/>=4 | >=1,600/>=4 | 1,200/4 | 1262 | 1262
Mixed Stores Loadout (ASW)(lbs)
12500 | 12500 | 10000 | 13275 | 25000
Initial On-station Altitude (ft)
49000 | 49000 | 25000 | 39000 | 39000
Operational Availability (ASW)
0.8 | (Objective = Threshold) .8 | 0.8 | 0.85 | .8 at IOC plus 2 years
Force Protection (%)
100 | (Objective = Threshold) 100 | 100 | 100 | 100
Net-Ready
Fully support execution of joint operational activities | Fully support execution of joint operational activities | Fully support execution of joint critical operational activities | Fully support execution of joint operational activities. JITC certification letter signed October 25, 2013. | Fully support execution of joint operational activities
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Production Document (CPD) (Increment 1) dated June 22, 2009 and Capability Development Document (CDD) (Increment 2 and 3) dated June 25, 2010
Change Explanations
None
Notes
JROC Memorandum 111-09 dated June 22, 2009 approved the P-8A Increment 1 CPD (Serial # 791-88-09). In the Milestone C ADM, the USD(AT&L) authorized the following capabilities to be acquired as ECPs within the baseline program: Automatic Identification System, Multi-static Active Coherent, High Altitude Anti-Submarine Warfare Weapon Capability and Sensors, Rapid Capability Insertion Acoustics Algorithms, and Tactical Operations Center updates. These ECPs provide additional capabilities beyond the P-8A Increment 1 capability and will be incorporated in-line with production or via retrofit.
Operational Availability (ASW) demonstrated performance improved to .85 based upon monthly actuals of deployed squadrons since IOC.

## Table 13
Acronyms and Abbreviations
ASW - Anti-Submarine Warfare ECP - Engineering Change Proposal ft - Feet
JITC - Joint Interoperability Test Command lbs - Pounds
nm - Nautical miles

## Table 14
Track to Budget
General Notes
The RDT&E cost parameters include the costs associated with Project Unit 2696 (Increment 1 SDD) and Project Unit 3181 (Increment 2 next Phase of Capabilities (previously called Spiral One)). Project Unit 3181 capabilities will be integrated into the P-8A through Engineering Change Proposals (ECPs) as approved in the Milestone C ADM, dated August 27, 2010. These ECPs are: Automatic Identification System, Multi-static Active Coherent, High Altitude Anti- submarine Warfare Weapon Capability and Sensors, Rapid Capability Insertion Acoustics Algorithms, and Tactical Operations Center updates. Project Unit 3218 (P-8A Increment 3 (previously called Spiral Two)) was not included in the APB cost parameters established at Milestone C and are excluded from the funding reported in this SAR.
RDT&E
Appn |  | BA | PE
Navy 1319 05 0605500N
Project | Name
2696 Multi-mission Maritime Aircraft 3181 P-8A Spiral One Development
Notes: P-8A Multi-mission Maritime Aircraft Increment 2 (formerly Spiral 1)
Procurement
Appn |  | BA | PE
Navy 1506 01 0204251N
Line Item Name
0193 P-8A Poseidon
Navy 1506 06 0204251N
Line Item Name
0605 Spares and Repair Parts
MILCON
Appn |  | BA | PE
Navy 1205 01 0212176N
Project | Name
P116 P-8A Detachment Support Facility
Notes: Joint Base Pearl Harbor Hickam
P259 P-8A Aircraft Apron and Support Facility
Notes: Naval Air Station Whidbey Island
P334 P-8 Fleet Support Facility Addition
Notes: Naval Air Station Jacksonville
P659 P-8 Training and Parking

## Table 15
| Notes: | Apron Expansion Naval Air Station Jacksonville Integrated Training Center
Navy | 1205 01 | 0703676N
| Project | Name
| P630 | P-8/MMA Facilities Modification (Sunk)
| Notes: | Naval Air Station Jacksonville (Facilities Modifications)
| P654 | P-8A Hangar Upgrades
| Notes: | Naval Air Station Jacksonville
Navy | 1205 01 | 0712876N
| Project | Name
| P655 | P-8A Hangar & Training Facility
| Notes: | Naval Air Station Sigonella
| P955 | P-8A Hangar & Training Facility
| Notes: | Naval Support Activity Bahrain
Navy | 1205 01 | 0805376N
| Project | Name
| P146 | MMA Test Facilities, (Sunk) Renovation & Modn
| Notes: | Multi-mission Maritime Hangar Test Facility Modifications Naval Air Station Patuxent River
| P147 | MMA Technical Supt Facs, (Sunk) Pax River MD
| Notes: | Multi-mission Maritime Hangar Test Facility Build Naval Air Station Patuxent River
Navy | 1205 01 | 0805976N
| Project | Name
| P623 | MMA Simulator Training (Sunk) Building
| Notes: | Naval Air Station Jacksonville (Build of Integrated Training Center)
Navy | 1205 01 | 0815976N
| Project | Name
| P251 | P-8A Hangar & Training Facility
| Notes: | Naval Air Station Whidbey Island
| P624 | P-8A Training Facility (Sunk)
| Notes: | Naval Air Station Jacksonville

## Table 16
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2010 $M | [6 empty] | BY 2010 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 8019.1 |  |  | 8303.1 | 9133.4 |  |  | 8219.6 |  | 7951.7 |  |  | 8341.5 |  | 8222.7
Procurement |  | 23519.1 |  |  | 21912.5 | 24103.8 |  |  | 21508.5 |  | 25654.7 |  |  | 24954.2 |  | 23833.9
Flyaway |  | -- |  |  | -- | -- |  |  | 17570.6 |  | -- |  |  | -- |  | 19487
Recurring |  | -- |  |  | -- | -- |  |  | 16885.9 |  | -- |  |  | -- |  | 18705.2
Non Recurring |  | -- |  |  | -- | -- |  |  | 684.7 |  | -- |  |  | -- |  | 781.8
Support |  | -- |  |  | -- | -- |  |  | 3937.9 |  | -- |  |  | -- |  | 4346.9
Other Support |  | -- |  |  | -- | -- |  |  | 3474 |  | -- |  |  | -- |  | 3847.9
Initial Spares |  | -- |  |  | -- | -- |  |  | 463.9 |  | -- |  |  | -- |  | 499
MILCON |  | 807.7 |  |  | 381.3 | 419.4 |  |  | 317.9 |  | 894.3 |  |  | 428.7 |  | 347.5
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 32345.9 |  |  | 30596.9 | N/A |  |  | 30046 |  | 34500.7 |  |  | 33724.4 |  | 32404.1
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current APB cost estimate provided sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule, and programmatic risk and external interference. It was consistent with average resource expenditures based on historical actual cost data and represents a notional 50% confidence level when established. The 50% confidence level does not account for sequestration impacts.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 5 |  |  |  | 5 |  |  |  |  | 5
Procurement |  |  | 117 |  |  |  | 109 |  |  |  |  | 109
Total |  |  | 122 |  |  |  | 114 |  |  |  |  | 114
Quantity Notes
Warfighting requirement is 117 production aircraft.

## Table 17
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 8003.7 | 142.3 |  |  | 57.1 | 18.8 | 0.8 |  | 0 |  | 0 |  | 0 |  | 8222.7
Procurement | 14228.3 | 3229.9 |  |  | 2108.1 | 1532.9 | 2637.5 |  | 97.2 |  | 0 |  | 0 |  | 23833.9
MILCON | 264.3 | 83.2 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 347.5
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 22496.3 | 3455.4 |  |  | 2165.2 | 1551.7 | 2638.3 |  | 97.2 |  | 0 |  | 0 |  | 32404.1
PB 2016 Total | 22495.9 | 3505.6 |  |  | 2487.5 | 2475.6 | 1712.1 |  | 0 |  | 0 |  | 0 |  | 32676.7
Delta | 0.4 | -50.2 |  |  | -322.3 | -923.9 | 926.2 |  | 97.2 |  | 0 |  | 0 |  | -272.6
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 5 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 5
Production | 0 |  | 62 |  | 17 | 11 | 6 |  | 13 | 0 |  | 0 |  | 0 |  | 109
PB 2017 Total | 5 |  | 62 |  | 17 | 11 | 6 |  | 13 | 0 |  | 0 |  | 0 |  | 114
PB 2016 Total | 5 |  | 62 |  | 16 | 12 | 12 |  | 7 | 0 |  | 0 |  | 0 |  | 114
Delta | 0 |  | 0 |  | 1 | -1 | -6 |  | 6 | 0 |  | 0 |  | 0 |  | 0

## Table 18
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 470.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 927
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1100
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 860.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1089.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1125.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 893.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 576.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 358.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 220.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 212.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 142.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.8
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
Subtotal |  | 5 | -- |  | -- |  | -- |  | -- |  | -- |  | 8222.7

## Table 19
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.4
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 75
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 73.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 512.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 979
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1134
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 870.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1089.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1108.6
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 859.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 545.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 335.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 203.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 193.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 127.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
Subtotal |  | 5 | -- |  | -- |  | -- |  | -- |  | -- |  | 8219.6

## Table 20
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | -- | 109.1 |  | -- |  | -- |  | 109.1 |  | -- |  | 109.1
2010 |  | 6 | 1360.6 |  | -- |  | 54.3 |  | 1414.9 |  | 383.9 |  | 1798.8
2011 |  | 7 | 1382 |  | -- |  | 31.5 |  | 1413.5 |  | 492.3 |  | 1905.8
2012 |  | 11 | 1977.5 |  | -- |  | 29.4 |  | 2006.9 |  | 280.8 |  | 2287.7
2013 |  | 13 | 2252.9 |  | -- |  | 32.3 |  | 2285.2 |  | 454.4 |  | 2739.6
2014 |  | 16 | 2603.6 |  | -- |  | 53.9 |  | 2657.5 |  | 558.5 |  | 3216
2015 |  | 9 | 1312.7 |  | -- |  | 62.8 |  | 1375.5 |  | 795.8 |  | 2171.3
2016 |  | 17 | 2713.9 |  | -- |  | 72.5 |  | 2786.4 |  | 443.5 |  | 3229.9
2017 |  | 11 | 1729.2 |  | -- |  | 89.1 |  | 1818.3 |  | 289.8 |  | 2108.1
2018 |  | 6 | 1271.3 |  | -- |  | 97.4 |  | 1368.7 |  | 164.2 |  | 1532.9
2019 |  | 13 | 1992.4 |  | -- |  | 161.4 |  | 2153.8 |  | 483.7 |  | 2637.5
2020 |  | -- | -- |  | -- |  | 97.2 |  | 97.2 |  | -- |  | 97.2
Subtotal |  | 109 | 18705.2 |  | -- |  | 781.8 |  | 19487 |  | 4346.9 |  | 23833.9

## Table 21
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | -- | 107.8 |  | -- |  | -- |  | 107.8 |  | -- |  | 107.8
2010 |  | 6 | 1317.1 |  | -- |  | 52.6 |  | 1369.7 |  | 371.7 |  | 1741.4
2011 |  | 7 | 1311.8 |  | -- |  | 29.9 |  | 1341.7 |  | 467.4 |  | 1809.1
2012 |  | 11 | 1850.6 |  | -- |  | 27.5 |  | 1878.1 |  | 262.8 |  | 2140.9
2013 |  | 13 | 2085.9 |  | -- |  | 29.9 |  | 2115.8 |  | 420.7 |  | 2536.5
2014 |  | 16 | 2379.6 |  | -- |  | 49.3 |  | 2428.9 |  | 510.5 |  | 2939.4
2015 |  | 9 | 1182 |  | -- |  | 56.5 |  | 1238.5 |  | 716.6 |  | 1955.1
2016 |  | 17 | 2402.1 |  | -- |  | 64.2 |  | 2466.3 |  | 392.6 |  | 2858.9
2017 |  | 11 | 1502 |  | -- |  | 77.4 |  | 1579.4 |  | 251.7 |  | 1831.1
2018 |  | 6 | 1083 |  | -- |  | 83 |  | 1166 |  | 139.9 |  | 1305.9
2019 |  | 13 | 1664 |  | -- |  | 134.8 |  | 1798.8 |  | 404 |  | 2202.8
2020 |  | -- | -- |  | -- |  | 79.6 |  | 79.6 |  | -- |  | 79.6
Subtotal |  | 109 | 16885.9 |  | -- |  | 684.7 |  | 17570.6 |  | 3937.9 |  | 21508.5

## Table 22
FY 2020 Non-Recurring Flyaway reflects $78 million in Production Line Shutdown cost.
Cost Quantity Information 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2010 $M
2009 | -- | --
2010 | 6 | 1271.9
2011 | 7 | 1305.4
2012 | 11 | 1777.1
2013 | 13 | 2032.2
2014 | 16 | 2360.8
2015 | 9 | 1481.5
2016 | 17 | 2132.5
2017 | 11 | 1643.6
2018 | 6 | 985.7
2019 | 13 | 1895.2
2020 | -- | --
Subtotal | 109 | 16885.9

## Table 23
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2006 | 5.8
2007 | 16.3
2008 | --
2009 | 48.2
2010 | 5.9
2011 | --
2012 | 31.2
2013 | --
2014 | 100.7
2015 | 56.2
2016 | 83.2
Subtotal | 347.5

## Table 24
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2010 $M
Total Program
2006 | 6
2007 | 16.6
2008 | --
2009 | 47.5
2010 | 5.7
2011 | --
2012 | 28.9
2013 | --
2014 | 90.8
2015 | 49.9
2016 | 72.5
Subtotal | 317.9

## Table 25
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2004-06-04 | 2013-07-15
Approved Quantity | 34 | 37
Reference | Milestone B ADM | LRIP Lot IV ADM
Start Year | 2010 | 2010
End Year | 2012 | 2013
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the necessity to establish the initial production base and to achieve an orderly and efficient increase in both the production rate and industry workforce. 35 of 37 LRIP aircraft have been delivered.

## Table 26
Foreign Military Sales
None
Nuclear Costs
None

## Table 27
Unit Cost
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Current UCR Baseline (Feb 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 30596.9 |  |  | 30046
Quantity | 114 |  |  | 114
Unit Cost | 268.394 |  |  | 263.561 |  | -1.8
Average Procurement Unit Cost
Cost | 21912.5 |  |  | 21508.5
Quantity | 109 |  |  | 109
Unit Cost | 201.032 |  |  | 197.326 |  | -1.84
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Original UCR Baseline (Jun 2004 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 30271.9 |  |  | 30046
Quantity | 115 |  |  | 114
Unit Cost | 263.234 |  |  | 263.561 |  | 0.12
Average Procurement Unit Cost
Cost | 22791.2 |  |  | 21508.5
Quantity | 108 |  |  | 109
Unit Cost | 211.03 |  |  | 197.326 |  | -6.49

## Table 28
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2010 $M | [7 empty] | TY $M
[12 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  |  | APUC
Original APB |  |  |  |  | Jun 2004 | [6 empty] | 263.234 |  |  |  | 211.03 | [5 empty] | 273.292 |  |  |  | 225.149
APB as of January 2006 |  |  |  |  | Jun 2004 | [6 empty] | 263.234 |  |  |  | 211.03 | [5 empty] | 273.292 |  |  |  | 225.149
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  |  |  | N/A | [5 empty] | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Oct 2010 | [6 empty] | 265.13 |  |  |  | 201.018 | [5 empty] | 282.793 |  |  |  | 219.271
Current APB |  |  |  |  | Feb 2014 | [6 empty] | 268.394 |  |  |  | 201.032 | [5 empty] | 295.828 |  |  |  | 228.938
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 264.81 |  |  |  | 198.719 | [5 empty] | 286.638 |  |  |  | 221.197
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 263.561 |  |  |  | 197.326 | [5 empty] | 284.246 |  |  |  | 218.66
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [22 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  |  |  | Spt |  |  | Total
273.292 3.671 -4.044 5.221 10.630 -17.830 0.000 11.853 9.501 282.793
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [20 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth |  |  |  | Spt |  | Total
282.793 1.974 6.156 4.568 -1.088 -9.206 0.000 -0.951 1.453 284.246

## Table 29
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [10 empty] | APUC Production Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
225.149 1.793 -3.468 5.332 0.000 -21.894 0.000 12.359 -5.878 219.271
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
219.271 1.604 1.777 4.098 1.589 -8.685 0.000 -0.994 -0.611 218.660
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | May 2004 |  |  |  | May 2004 |  |  | May 2004
Milestone C |  |  | N/A |  |  | May 2010 |  |  |  | May 2010 |  |  | Aug 2010
IOC |  |  | N/A |  |  | Jul 2013 |  |  |  | Jul 2013 |  |  | Dec 2013
Total Cost (TY $M) |  |  | N/A |  |  | 31428.6 |  |  |  | 34500.7 |  |  | 32404.1
Total Quantity |  |  | N/A |  |  | 115 |  |  |  | 122 |  |  | 114
PAUC |  |  | N/A |  |  | 273.292 |  |  |  | 282.793 |  |  | 284.246

## Table 30
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 7951.7 | 25654.7 | 894.3 | 34500.7
Previous Changes
Economic | 41.7 | 299 | 15 | 355.7
Quantity | -- | -1560.4 | -- | -1560.4
Schedule | 72.9 | 433.8 | 1.1 | 507.8
Engineering | 76.3 | 111.9 | -373.5 | -185.3
Estimating | 80.2 | -755.6 | -193.5 | -868.9
Other | -- | -- | -- | --
Support | -- | -72.9 | -- | -72.9
Subtotal | 271.1 | -1544.2 | -550.9 | -1824
Current Changes
Economic | -4.9 | -124.2 | -1.6 | -130.7
Quantity | -- | -- | -- | --
Schedule | -- | 12.9 | -- | 12.9
Engineering | -- | 61.3 | -- | 61.3
Estimating | 4.8 | -191.1 | 5.7 | -180.6
Other | -- | -- | -- | --
Support | -- | -35.5 | -- | -35.5
Subtotal | -0.1 | -276.6 | 4.1 | -272.6
Total Changes | 271 | -1820.8 | -546.8 | -2096.6
CE - Cost Variance | 8222.7 | 23833.9 | 347.5 | 32404.1
CE - Cost & Funding | 8222.7 | 23833.9 | 347.5 | 32404.1

## Table 31
Summary BY 2010 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 8019.1 | 23519.1 | 807.7 | 32345.9
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -1276.4 | -- | -1276.4
Schedule | 68.1 | 111.7 | -0.4 | 179.4
Engineering | 68.4 | 94 | -328.6 | -166.2
Estimating | 59.5 | -642.2 | -165.9 | -748.6
Other | -- | -- | -- | --
Support | -- | -145.8 | -- | -145.8
Subtotal | 196 | -1858.7 | -494.9 | -2157.6
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -2.8 | -- | -2.8
Engineering | -- | 50.7 | -- | 50.7
Estimating | 4.5 | -167.9 | 5.1 | -158.3
Other | -- | -- | -- | --
Support | -- | -31.9 | -- | -31.9
Subtotal | 4.5 | -151.9 | 5.1 | -142.3
Total Changes | 200.5 | -2010.6 | -489.8 | -2299.9
CE - Cost Variance | 8219.6 | 21508.5 | 317.9 | 30046
CE - Cost & Funding | 8219.6 | 21508.5 | 317.9 | 30046
Previous Estimate: December 2014

## Table 32
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -4.9
Revised estimate to reflect prior year actuals. (Estimating) | -5.6 | -6.3
Adjustment due to FY 2017 PB funding realignment. (Estimating) | 5.9 | 6.6
Adjustment for current and prior escalation. (Estimating) | 4.2 | 4.5
RDT&E Subtotal | 4.5 | -0.1
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -124.2
Schedule Variance resulting from re-phasing aircraft (FY 2016 +1, FY 2017 -1, FY 2018 -6,
FY 2019 +6). (Schedule)
0.0 +17.5
Additional Schedule Variance due to re-phasing aircraft in FY 2016-2019. (Schedule) -2.8 -4.6 Revised estimate to reflect increase in Ancillary Equipment. (Engineering) +50.7 +61.3
Revised estimate to reflect increase to Non-Recurring Engineering for forward fit of product configuration changes and movement of Production Line Shutdown cost from Support. (Estimating)
Revised estimate to reflect decrease due to cost estimating methodology update (Boeing Commercial Aircraft effort). (Estimating)
Revised estimate to reflect decrease due to Program Management Office adjustments from Lots 6 and 7 negotiations. (Estimating)
Revised estimate to reflect decrease due to Government Furnished Equipment APY-10 Radar contract settlement. (Estimating)
+89.6 +107.2
-212.1 -242.6
-87.6 -103.1
-6.7 -7.4
Adjustment for current and prior escalation. (Estimating) +48.9 +54.8
Adjustment for current and prior escalation. (Support) +13.2 +14.0
Decrease in Other Support reflects updated actuals for Peculiar Ground Support Equipment, Peculiar Training Equipment and Production Line Shutdown. (Support)
-52.8 -58.2
Increase in Initial Spares allocation. (Support) | 7.7 | 8.7
Procurement Subtotal | -151.9 | -276.6
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -1.6
Revised estimate to reflect prior year actuals. (Estimating) | 3.7 | 4.1
Adjustment for current and prior escalation. (Estimating) | 1.4 | 1.6
MILCON Subtotal | 5.1 | 4.1

## Table 33
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: P-8A Production Contract for LRIP Lot IV
Contractor: The Boeing Company
Contractor Location: 7755 East Marginal Way
Seattle, WA 98108
Contract Number: N00019-12-C-0112/0
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Firm Fixed Price (FFP)
Award Date: August 31, 2012
Definitization Date: July 31, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
244.9 244.9 N/A 1969.4 2012.5 13 1969.4 1969.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional awards to Boeing Defense Space and Security for Advanced Procurement and LRIP Lot IV and associated spares, support equipment, technical data/publications, tools, training devices, and long lead materials.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (10/26/2015) +7.1 -11.0
Previous Cumulative Variances -5.6 -17.5
Net Change +12.7 +6.5
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to production operations manufacturing resources have been temporarily reallocated to support other contracts. Program and engineering less than originally planned due to efficiencies in the early stages of Lot 4 engineering.
The favorable net change in the schedule variance is due to early aircraft delivery and recovery of previously late high value material deliveries.
Notes
Cost and Schedule Variances reflect LRIP Lot IV performance. 11 of 13 LRIP Lot IV aircraft delivered.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 34
Contract Identification
Appropriation: Procurement
Contract Name: P-8A Production Contract for FRP Lot V
Contractor: The Boeing Company
Contractor Location: 7755 East Marginal Way South
Seattle, WA 98105
Contract Number: N00019-12-C-0112/1
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Firm Fixed Price (FFP)
Award Date: July 31, 2013
Definitization Date: February 25, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
300.7 300.7 N/A 2339.6 2389.3 16 2339.6 2339.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional awards to Boeing Defense Space and Security for Advanced Procurement and FRP Lot V and associated spares, support equipment, technical data/publications, tools, training devices, and long lead materials.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF/FFP) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because a Class Deviation from Defense Federal Acquisition Regulation Supplement Subpart 234.2 was approved by the Deputy Assistant Secretary of the Navy (Acquisition and Procurement) on September 30, 2014. This Class Deviation authorizes the removal of EVM requirements from the P- 8A FRP Lots V - VII contracts.
Notes
The first aircraft delivery is projected for May 2016.

## Table 35
Contract Identification
Appropriation: Procurement
Contract Name: P-8A Production Contract for FRP Lot VI
Contractor: The Boeing Company
Contractor Location: 7755 East Marginal Way South
Seattle, WA 98105
Contract Number: N00019-14-C-0067/0
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Firm Fixed Price (FFP)
Award Date: August 14, 2014
Definitization Date: August 27, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
295.6 N/A N/A 1227.4 1234.6 9 1227.4 1227.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional awards to Boeing Defense Space and Security for Advanced Procurement and FRP Lot VI and associated spares, support equipment, technical data/publications, tools, training devices, and long lead materials.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF/FFP) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because a Class Deviation from Defense Federal Acquisition Regulation Supplement Subpart 234.2 was approved by the Deputy Assistant Secretary of the Navy (Acquisition and Procurement) on September 30, 2014. This Class Deviation authorizes the removal of EVM requirements from the P- 8A FRP Lots V - VII contracts.

## Table 36
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 5 | 5 | 5 | 100%
Production | 35 | 35 | 109 | 32.11%
Total Program Quantity Delivered | 40 | 40 | 114 | 35.09%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
32404.1
17351.8
53.55%
19
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
15
78.95%
25951.7
80.09%
The above data is current as of February 29, 2016.
Although RDT&E deliveries commenced with the first flight test aircraft (airworthiness, T-1), it is not included in the Planned or Actual deliveries since it is not a fully configured end item. The RDT&E delivered quantities include: the second flight test aircraft (mission equipped, T-2); the third flight test aircraft (mission equipped for weapon separation testing, T-3); and T-4, T-5 and T-6, System Development and Demonstration Stage II production representative aircraft. The fleet has taken delivery of 35 total LRIP Lots I - IV aircraft supporting initial fleet transition training and operational deployment. All aircraft have been delivered early or on-time to contracted delivery dates.

## Table 37
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 27, 2016
Source of Estimate: POE
Quantity to Sustain: 109
Unit of Measure: Aircraft
Service Life per Unit: 25.00 Years
Fiscal Years in Service: FY 2012 - FY 2044
All five of the P-8A RDT&E-funded development aircraft will remain as test articles (SDD aircraft) and are funded within the Continuing System Improvements cost element. The Quantity to Sustain number of 109 reflects the 109 procurement funded aircraft.
Flight hours per aircraft per year are: P-8A = 677. The calculation is based on summing the total operational flight hours and dividing by total operational aircraft. P-8A operations are based on: one Fleet Replacement Squadron (12 aircraft) and 12 Fleet squadrons (6-7 aircraft each).
Sustainment Strategy
P-8A O&S costs are based on limited 3-level maintenance. Post-Material Support Date contracts will be managed by Naval Supply Systems Command and the Defense Logistics Agency. Intermediate level maintenance is currently estimated for 84 parts with additional intermediate level capability assessments ongoing.
Antecedent Information
P-3C O&S costs are based on a 3-level maintenance system. P-3C data was pulled from the Naval Visibility and Management of Operating and Support Cost database Aircraft Type Model Series Report in December 2015 (BY 2010 dollar average for FY 2004-FY 2014). Aircraft quantities: P-3C = 150 Total Aircraft Inventory and 141 Primary Authorized Aircraft. Flight hours per aircraft per year are: P-3C = 502. The calculation is based on summing the total operational flight hours and dividing by total operational aircraft. The annual P-3C sustainment cost (2004-2014 average) is $1.68 CY 2010 $B while the annual P-8A sustainment cost is $1.36 CY 2010 $B resulting in an annual cost avoidance of $0.32 CY 2010 $B.
Indirect support for P-3C was estimated based on a ratio of mission personnel and intermediate maintenance government labor. Indirect support calculation now in alignment with P-8A calculation, by multiplying the Mission Personnel cost by a factor of 46.68%, which was determined by dividing the annual steady state P-8A Indirect Cost by the P-8A Mission Personnel cost.

## Table 38
Annual O&S Costs BY2010 $M
Cost Element |  | P-8A Average Annual Cost Per Aircraft | [5 empty] | P-3C (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  | 4.161 | [5 empty] | 3.733
Unit Operations |  | 2.771 | [5 empty] | 1.559
Maintenance |  | 4.844 | [5 empty] | 2.874
Sustaining Support |  | 0.919 | [5 empty] | 0.188
Continuing System Improvements |  | 0.834 | [5 empty] | 1.801
Indirect Support |  | 2.078 | [5 empty] | 1.743
Other |  | 0 | [5 empty] | 0
Total |  | 15.607 | [5 empty] | 11.898
This estimate that has been reviewed and updated as follows:
1. PB 2017 quantity profile.
2. Updated parts list and aircraft configuration information from Interim Support Items List Rev N.
3. 2016 inflation rates, Naval Supply Systems Command rates, mission personnel labor rates, and indirect labor rates.
4. Flight hours per aircraft per year calculation reflects phase-in and phase-out of aircraft.
Item | Total O&S Cost $M
| P-8A | [7 empty] | P-3C (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 34917.5 |  |  | 38409.3 |  |  | 35052.7 |  | 26663.4
Then Year | 50434.9 |  |  | N/A |  |  | 50397.7 |  | N/A
Equation to Translate Annual Cost to Total Cost
The annual cost per aircraft is derived by taking the total O&S cost by element and dividing it by the total operating aircraft years. ($35,053 BY 2010 $M Total O&S Cost / 2,246 P-8A aircraft years = $15.607 BY 2010 $M Cost per aircraft per year).
O&S Cost Variance
Category |  |  | BY 2010 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
33325.2
Programmatic/Planning Factors 261.9 Increase for aircraft procurement schedule, Flying Hour
Program (FHP) adjustments including Intermediate Level stand-up and phasing of aircraft delivery and flight hours, and change of sustainment Program Related Engineering and Program Related Logistics efforts within production phase.

## Table 39
Cost Estimating Methodology -435.3 Decrease for incorporation of actuals and budget data.
Cost Data Update 603.7 Increase for updated consumable prices and repair prices, license costs, and engine depot costs.
Labor Rate 206.7 Increase for Military Pay rates and indirect rates.
Energy Rate -305.6 Decrease for updated fuel $/gal rate.
Technical Input 1396.1 Increase for new and deleted parts, quantity per aircraft and aircraft configuration, updated Reliability and Maintainability, additional crew member for sixth workstation and airframe and engine depot overhaul schedule.
Other 0.0
Total Changes 1727.5
Current Estimate 35052.7
The updated estimate is roughly a 5.2% increase from the December 2014 SAR estimate, from $33.325B CY 2010 $B to
$35.053B CY 2010 $B
Disposal Estimate Details
Date of Estimate: January 27, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2010 $M): Total costs for disposal of all Aircraft are 27.5
This Rough Order of Magnitude estimate will be refined as the System Disposal Plan Annex to the Life Cycle Sustainment Plan is developed.