## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-376
B-2 RMP
As of September 30, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 4
Threshold Breaches |  | 5
Schedule |  | 6
Performance |  | 7
Track To Budget |  | 11
Cost and Funding |  | 12
Low Rate Initial Production |  | 19
Nuclear Cost |  | 19
Foreign Military Sales |  | 19
Unit Cost |  | 20
Cost Variance |  | 23
Contracts |  | 26
Deliveries and Expenditures |  | 27
Operating and Support Cost |  | 28

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
B-2 Radar Modernization Program
DoD Component
Air Force
Responsible Office
Responsible Office
Col Mark Williams | Phone | 937-255-9484
B-2 SPM | Fax | 937-656-7207
2690 Loop Road West | DSN Phone | 785-9484
Area B Bldg 556 Wright Patterson AFB, OH 45433-7148 | DSN Fax | 986-7207
Mark.Williams@wpafb.af.mil | Date Assigned | June 4, 2010
References
SAR Baseline (Production Estimate)
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated January 29, 2009
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated January 29, 2009

## Table 4
Mission and Description
The currently fielded B-2 radar system, designated the AN/APQ-181, was developed on the original B-2 Engineering and Manufacturing Development contract. The AN/APQ-181 is a multi-mode radar designed to support a wide variety of missions and functions. The primary requirements are to provide navigation updates, support penetration of enemy air defenses, support rendezvous with tanker aircraft and other B-2s, support bomb damage assessment, detect hazardous weather, support weapons delivery, determine runway status, and operate with a low probability of intercept. This last requirement resulted in the radar designed to operate in a frequency spectrum where the government is considered a secondary user.
In October 2000, the Department of Commerce notified the Department of Defense that the portion of the electromagnetic spectrum used by the B-2 radar would be redesignated for commercial use. Consequently, the B-2 will not be able to operate without interference with primary users. In order to ensure the continued operation of the B-2, the B-2 radar system must be modified to operate in another portion of the electromagnetic spectrum where the United States Government is guaranteed primary user status. The National Telecommunications and Information Administration (NTIA) requires all actions be completed by a classified Near Term Date, after which current B-2
radar operation will be prohibited. Recently, the NTIA issued a temporary legacy frequency assignment applicable to the United States and Possessions. However, this extension can be revoked at any time if a primary user emerges.
The B-2 Radar Modernization Program replaces the radar antenna and modifies its associated support electronics to enable the B-2 to remain compliant with law by changing the operating frequency of the radar and maintaining spectral purity within the portion of the electromagnetic spectrum. No changes to radar signal processing or radar data processing are required or anticipated.
Executive Summary
This quarterly exception SAR is being submitted to terminate reporting for the B-2 RMP which reports greater than 90 percent expended; therefore, pursuant to section 2432 of title 10, United State Code, this will be the final Selected Acquisition Report (SAR) for the program.
Since the last SAR in December 2010, the Low Rate Initial Production (LRIP) phase was completed and the Full Rate Production (FRP) contract option 2 continued to execute on schedule.
Life-of-Type (LOT) III contract for 38,976 parts progressed and started delivery of parts in September 2011 (three months early).
The LRIP installs completed June 6, 2011. The LRIP contract closed out June 24, 2011. FRP installs are progressing on schedule. The first FRP install was delivered August 26, 2011 (five days ahead of schedule). The remaining installs are progressing on schedule.
There are no significant software issues with this program.

## Table 5
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Explanation of Breach
The schedule breach was reported in the December 2009 Selected Acquisition Report.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 6
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | SEP 2004 | SEP 2004 | SEP 2004 | AUG 2004
Milestone C | SEP 2008 | SEP 2008 | SEP 2008 | DEC 2008 1
Full Rate Production Decision Review | SEP 2009 | SEP 2009 | MAR 2010 | SEP 2009
Delivery of Mode Set 2 capability | SEP 2009 | SEP 2009 | MAR 2010 | SEP 2009
RAA | DEC 2009 | DEC 2009 | JUN 2010 | MAR 2010
1APB Breach
Acronyms And Abbreviations
RAA - Required Assets Available
Change Explanations
None
Memo
RAA is defined as sufficient support equipment, spares, hardware, and fully qualified Mode Set 1 software to support five operational aircraft at Whiteman Air Force Base.
Milestone C changed from September 2008 to December 2008 to match the date the Acquistion Decision Memorandum was signed. This was reported in the 2009 Selected Acquisition Report.

## Table 7
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Enable the aircraft to employ weapons | Aircraft system level CEP shall not exceed the results from the baseline tests (2005- 2006). | Aircraft system level CEP shall not exceed the results from the baseline tests (2005- 2006). | Aircraft system level CEP shall not exceed the results from the baseline tests (2005- 2006). | Demon- strated early 2008; IOT&E report accepted by DT&E 29 May; Beyond LRIP Report to Congress in Sep 09. | Weapon accuracy (CEP) IAW FY04-06 Force Development Evaluation results.
Enable location and characterization of atmospheric conditions
Thunderstorms/Nuclear Debris | Avoid thunder- storms, with a min. rain rate of 1 mm/hr, by a min. of 40 NM; avoid nuclear debris clouds. | Avoid thunder- storms, with a min. rain rate of 1 mm/hr, by a min. of 40 NM; avoid nuclear debris clouds. | Avoid thunder- storms, with a min. rain rate of 1 mm/hr, by a min. of 40 NM; avoid nuclear debris clouds. | Demon- strated thunder- storm short range perform- ance. Compliant via flight tests and data analysis. IOT&E report, accepted by DOT&E on 29 May 09. Nuclear debris is part of Mode Set 2 flight testing which completed in Apr 09. FOT&E in Sep 09 to test Mode Set 2. | Avoid thunder- storms, with a min. rain rate of 1 mm/hr, by a min. of 40 NM; avoid nuclear debris clouds.
Rainfall/Debris Density | Display green, yellow and red bands based on | Display green, yellow and red bands based on | Display green, yellow and red bands based on | Compliant via flight tests and data analysis. | Display green, yellow and red bands based on

## Table 8
| rainfall rates | rainfall rates | rainfall rates | IOT&E | rainfall rates
| and debris | and debris | and debris | report, | and debris
| density out | density out | density out | accepted by | density out
| to 160 NM. | to 160 NM. | to 160 NM. | DOT&E on | to 160 NM
| Avoid | Avoid | Avoid | 29 May 09.
| thunder- | thunder- | thunder-
| storms, with | storms, with | storms, with
| a min. rain | a min. rain | a minimum
| rate of | rate of | rain rate of
| 1mm/hr, by a | 1mm/hr, by a | 1mm/hr, by a
| min. of 40 | min. of 40 | minimum of
| NM. | NM. | 40 NM.
Shall not diminish current | a) Once | a) Once | a) Once | LO flight test | a) B-2 RMP
B-2 penetration | modified, the | modified, the | modified, the | conducted in | installation
capabilities and | aircraft shall | aircraft shall | aircraft shall | May 07; LPI | meets the
survivability | not exceed | not exceed | not exceed | flight tests in | Block 30
characteristics | the values in | the values in | the values in | Jul & Aug | Appendix 70
| App 70 of | App 70 of | App 70 of | 8 | specification
| the Weapon | the Weapon | the Weapon | Peformance | for the
| System | System | System | met | current
| Specification | Specification | Specification | expectations. | radar's
| b) Improve | b) Improve | b) LPI |  | portion of the
| performance. | performance. | performance |  | LO budget;
|  |  | of RMP shall |  | b) LPI
|  |  | meet the |  | performance
|  |  | performance |  | to Block 30
|  |  | of the legacy |  | radar
|  |  | radar when |  | I/FOT&E and
|  |  | tested under |  | FDE test
|  |  | similar |  | results
conditions.
Shall comply with | Achieve and | Achieve and | Achieve and | Stage 4 | Achieve and
spectrum management | comply with | comply with | comply with | application | comply with
directives | DD1494 | DD1494 | DD1494 | submitted; in | DD1494
| Stage 3 | Stage 3 | Stage 3 | review at | Stage 3
| Certification | Certification | Certification | 88th Comm | Certification
| prior to | prior to | prior to | Grp; no | prior to
| range | range | range | issues. | range
| testing; | testing; | testing; | Planned to | testing;
| achieve and | achieve and | achieve and | be signed by | achieve and
| comply with | comply with | comply with | Apr 2010. | comply with
| DD1494 | DD1494 | DD1494 |  | DD1494
| Stage 4 | Stage 4 | Stage 4 |  | Stage 4
| Certification | Certification | Certification |  | Certification
| prior to initial | prior to initial | prior to initial |  | prior to initial
| operational | operational | operational |  | operational
| capability. | capability. | capability. |  | capability.
Shall not degrade | a) Detect a | a) Detect a | a) Detect a | Flight tested | Minimum
situational awareness-- | tanker at up | tanker at up | tanker in | in May 08. | capability of
tanker rendezvous, | to Y NM. | to Y NM. | RWS and | Significant | 80NM with
station keeping, and air- | (see | (see | lock on in | capability to | positional
traffic capability | classified | classified | AAT by X | detect/track/ | accuracy to
| App); b) | App); b) | NM (see | rendezvous | ensure safe

## Table 9
| Enable the B- | Enable the B- | classified | with tanker, | separation
| 2 to maintain | 2 to maintain | App); b) | station | of at least
| 0.5 NM min. | 0.5 NM min. | Enable the B- | keeping and | 0.5NM
| separation | separation | 2 to maintain | air traffic
| using the 5 | using the 5 | 0.5 NM min. | situational
| NM scope. | NM scope. | separation | awareness
|  |  | using the 5 | has been
|  |  | NM scope. | demonstrate
d. IOT&E
report
accepted by
DT&E May
29, 2009;
Beyond
LRIP Report
to Congress.
All top-level IERs will be | 100% of top- | 100% of top- | 100% of top- | 100% of Top- | 100% of top-
satisfied to the standards | level IERs | level IERs | level IERs | level IERs | level IERs
specified in the |  |  | designated | satisfied.
thresholds and objective |  |  | critical
values
Requirements Source:
Capability Production Document (CPD) for B-2 Radar Modernization Program (RMP), validated July 11, 2006.
Acronyms And Abbreviations
AAT - Air to Air Track App - Appendix
CEP - Circular Error Probability
DOT&E - Director, Operational Test & Evaluation DT&E - Developmental Test & Evaluation
FDE - Force Development Evaluation hr - hour
I/FOT&E - Initial and Follow-on Operational Test & Evaluation IAW - In Accordance With
IER - Information Exchange Requirement KPP - Key Performance Parameter
LO - Low Observability
LPI - Low Probability of Intercept Min - Minimum
mm - millimeter
NM - Nautical Miles
TBD - To Be Determined
Change Explanations
None
Memo

## Table 10
Classified Performance information is provided in the classified annex to this submission.

## Table 11
Track To Budget
General Memo
The funding for the B-2 Radar Modernization Program (RMP) is embedded within the primary B-2 Program Elements. These lines are shared with other B-2 programs that support the B-2 weapon system, which includes the B-2 Extremely High Frequency (EHF) Increment I program.
Aircraft Procurement, Air Force BA 05 line is shared for all B-2 Mods (B-2 RMP is Mod No. 110033 on the Exhibit P-40, Budget Item Justification). Funding for Initial Spares is in the shared BA 06 line.
RDT&E
APPN 3600 | BA 07 | PE 0101127F | (Air Force)
| Project 5345 | B-2 Advanced Technology Bomber/B-2 Advanced Technology Bomber | (Shared) | (Sunk)
APPN 3600 | BA 05 | PE 0604240F | (Air Force)
| Project 3843 | B-2 Advanced Technology Bomber/B-2 Advanced Technology Bomber | (Shared) | (Sunk)
Procurement
APPN 3010 | BA 06 | PE 0101127F | (Air Force)
| ICN 000999 | B-2 Radar Modernization Program (RMP) | (Shared)
APPN 3010 | BA 05 | PE 0101127F | (Air Force)
| ICN B00200 | B-2 Radar Modernization Program (RMP) | (Shared)

## Table 12
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
| BY2008 $M |  |  |  |  | BY2008 $M |  | TY $M
Appropriation | SAR Baseline Prod Est |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Prod Est | Current APB Production Objective | Current Estimate
RDT&E | 730.9 |  | 730.9 |  | 804 | 666.8 |  | 719.1 | 719.1 | 648.5
Procurement | 593.6 |  | 593.6 |  | 653 | 545 |  | 629.3 | 629.3 | 566.7
Flyaway | 481.1 |  | -- |  | -- | 507.6 |  | 508.7 | -- | 527.1
Recurring | 398.1 |  | -- |  | -- | 460.6 |  | 420.5 | -- | 478.1
Non Recurring | 83 |  | -- |  | -- | 47 |  | 88.2 | -- | 49
Support | 112.5 |  | -- |  | -- | 37.4 |  | 120.6 | -- | 39.6
Other Support | 88 |  | -- |  | -- | 14.4 |  | 93.7 | -- | 14.9
Initial Spares | 24.5 |  | -- |  | -- | 23 |  | 26.9 | -- | 24.7
MILCON | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Acq O&M | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Total | 1324.5 |  | 1324.5 |  | N/A | 1211.8 |  | 1348.4 | 1348.4 | 1215.2
The RMP Full Rate Production (FRP) program office estimate was validated by the Air Force Cost Analysis Agency (AFCAA) on September 10, 2009. The cost estimate reflected a 55% confidence level due to the low risk of the production effort; the development cost estimate was based on actual costs incurred as the development program was more than 96% complete.
Quantity |  | SAR Baseline Prod Est |  | Current APB Production |  |  | Current Estimate
RDT&E |  | 7 |  | 7 |  |  | 7
Procurement |  | 13 |  | 13 |  |  | 13
Total |  | 20 |  | 20 |  |  | 20
The unit of measure is modified aircraft.

## Table 13
Cost and Funding
Funding Summary
Appropriation and Quantity Summary SEP 2011 Exception SAR (TY $M)
Appropriation |  | Prior | FY2011 |  | FY2012 |  | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  | To Complete |  | Total
RDT&E |  | 647.3 | 1.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 648.5
Procurement |  | 530.4 | 23.1 |  | 13.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 566.7
MILCON |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SEP 2011 Total |  | 1177.7 | 24.3 |  | 13.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1215.2
PB 2012 Total |  | 1186.5 | 23.8 |  | 14.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1225.1
Delta |  | -8.8 | 0.5 |  | -1.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -9.9
Quantity | Undistributed |  |  | Prior |  | FY2011 |  | FY2012 | FY2013 | FY2014 |  | FY2015 |  | FY2016 |  | To Complete |  | Total
Development | 7 |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 7
Production | 0 |  |  | 13 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 13
SEP 2011 Total | 7 |  |  | 13 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 20
PB 2012 Total | 7 |  |  | 13 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 20
Delta | 0 |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
FY2012 President's Budget / December 2010 SAR (TY$ M)
Appropriation |  | Prior | FY2011 |  | FY2012 |  |  | FY2013 | FY2014 |  | FY2015 |  | FY2 | 16 | To Complete |  | T | otal
RDT&E | 647.5 |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 647.5
Procurement | 539 |  | 23.8 |  |  | 14.8 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 577.6
MILCON | 0 |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2012 Total | 1186.5 |  | 23.8 |  |  | 14.8 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1225.1
PB 2011 Total | 1227.9 |  | 23.2 |  |  | 14.7 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1265.8
Delta | -41.4 |  | 0.6 |  |  | 0.1 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | -40.7

## Table 14
Quantity | Undistributed | Prior | FY2011 | FY2012 | FY2013 | FY2014 | FY2015 | FY2016 | To Complete | Total
Development | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
Production | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
PB 2012 Total | 7 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
PB 2011 Total | 7 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2005 | -- | -- | -- | -- | -- | -- | 170.7
2006 | -- | -- | -- | -- | -- | -- | 200.4
2007 | -- | -- | -- | -- | -- | -- | 93.2
2008 | -- | -- | -- | -- | -- | -- | 112.4
2009 | -- | -- | -- | -- | -- | -- | 69.6
2010 | -- | -- | -- | -- | -- | -- | 1
2011 | -- | -- | -- | -- | -- | -- | 1.2
Subtotal | 7 | -- | -- | -- | -- | -- | 648.5

## Table 16
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2008 $M | Non End Item Recurring Flyaway BY 2008 $M | Non Recurring Flyaway BY 2008 $M | Total Flyaway BY 2008 $M | Total Support BY 2008 $M | Total Program BY 2008 $M
2005 | -- | -- | -- | -- | -- | -- | 182.6
2006 | -- | -- | -- | -- | -- | -- | 208.1
2007 | -- | -- | -- | -- | -- | -- | 94.3
2008 | -- | -- | -- | -- | -- | -- | 111.5
2009 | -- | -- | -- | -- | -- | -- | 68.2
2010 | -- | -- | -- | -- | -- | -- | 1
2011 | -- | -- | -- | -- | -- | -- | 1.1
Subtotal | 7 | -- | -- | -- | -- | -- | 666.8

## Table 17
Annual Funding TY$
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2008 | -- | 57.9 | -- | 0.5 | 58.4 | 1.6 | 60
2009 | 6 | 246.7 | 1.1 | 26.4 | 274.2 | 6.1 | 280.3
2010 | 7 | 164.6 | 1.3 | 21.1 | 187 | 3.1 | 190.1
2011 | -- | -- | 4.9 | 1 | 5.9 | 17.2 | 23.1
2012 | -- | -- | 1.6 | -- | 1.6 | 11.6 | 13.2
Subtotal | 13 | 469.2 | 8.9 | 49 | 527.1 | 39.6 | 566.7

## Table 18
Annual Funding BY$
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2008 $M | Non End Item Recurring Flyaway BY 2008 $M | Non Recurring Flyaway BY 2008 $M | Total Flyaway BY 2008 $M | Total Support BY 2008 $M | Total Program BY 2008 $M
2008 | -- | 56.8 | -- | 0.5 | 57.3 | 1.6 | 58.9
2009 | 6 | 238.6 | 1.1 | 25.5 | 265.2 | 5.9 | 271.1
2010 | 7 | 156.8 | 1.2 | 20.1 | 178.1 | 3 | 181.1
2011 | -- | -- | 4.6 | 0.9 | 5.5 | 16.2 | 21.7
2012 | -- | -- | 1.5 | -- | 1.5 | 10.7 | 12.2
Subtotal | 13 | 452.2 | 8.4 | 47 | 507.6 | 37.4 | 545

## Table 19
Cost Quantity Information
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Flyaway
Fiscal Year | Quantity | (Aligned with
Quantity)
BY 2008
$M
2008 | -- | --
2009 | 6 | 236.3
2010 | 7 | 215.9
2011 | -- | --
2012 | -- | --
Subtotal | 13 | 452.2
Low Rate Initial Production
|  | Initial LRIP Decision | Current Total LRIP
Approval Date |  | 8/17/2004 9/4/2008 4 6 Milestone B Milestone C 2007 2008 2007 2009
Approved Quantity
Reference
Start Year
End Year
RMP Milestone C Decision was accomplished in September 2008. The Air Force aligned funding in FY 2009 President's Budget (PB) to support the purchase of six Low Rate Initial Production (LRIP) ship sets in FY 2009
and seven Full Rate Production (FRP) ship sets in FY 2010. The LRIP quantity is greater than 10% due to the small fleet size.
Foreign Military Sales
None
Nuclear Cost
None

## Table 20
Unit Cost
Unit Cost Report
|  | BY2008 $M | BY2008 $M
Unit Cost |  | Current UCR Baseline (JAN 2009 APB) | Current Estimate (SEP 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1324.5 |  |  | 1211.8
Quantity | 20 |  |  | 20
Unit Cost | 66.225 |  |  | 60.59 |  | -8.51
Average Procurement Unit Cost (APUC)
Cost | 593.6 |  |  | 545
Quantity | 13 |  |  | 13
Unit Cost | 45.662 |  |  | 41.923 |  | -8.19
|  | BY2008 $M | BY2008 $M
Unit Cost |  | Original UCR Baseline (AUG 2004 APB) | Current Estimate (SEP 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1273.8 |  |  | 1211.8
Quantity | 21 |  |  | 20
Unit Cost | 60.657 |  |  | 60.59 |  | -0.11
Average Procurement Unit Cost (APUC)
Cost | 559 |  |  | 545
Quantity | 14 |  |  | 13
Unit Cost | 39.929 |  |  | 41.923 |  | 4.99

## Table 21
Unit Cost History
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
[11 empty] | BY2008 $M | [6 empty] | TY $M
[5 empty] | Date | [5 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  |  |  | AUG 2004 | [5 empty] | 60.657 |  |  | 39.929 |  |  |  | 58.095 |  |  | 39.15
APB as of January 2006 |  |  |  |  | AUG 2004 | [5 empty] | 60.657 |  |  | 39.929 |  |  |  | 58.095 |  |  | 39.15
Revised Original APB |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  |  |  | AUG 2004 | [5 empty] | 60.657 |  |  | 39.929 |  |  |  | 58.095 |  |  | 39.15
Current APB |  |  |  |  | JAN 2009 | [5 empty] | 66.225 |  |  | 45.662 |  |  |  | 67.42 |  |  | 48.408
Prior Annual SAR |  |  |  |  | DEC 2010 | [5 empty] | 61.065 |  |  | 42.723 |  |  |  | 61.255 |  |  | 44.431
Current Estimate |  |  |  |  | SEP 2011 | [5 empty] | 60.59 |  |  | 41.923 |  |  |  | 60.76 |  |  | 43.592
Initial PAUC Dev Est | Changes | [18 empty] | PAUC Prod Est
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  |  | Oth |  |  | Spt |  | Total
58.095 1.795 1.040 5.845 2.110 -5.515 0.000 -0.080 5.195 67.420
Current SAR Baseline to Current Estimate (TY $M)
PAUC Prod Est |  | Changes | [16 empty] | PAUC Current Est
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  | Oth |  |  | Spt |  | Total
67.420 -0.795 0.000 0.000 0.000 -1.930 0.000 -3.935 -6.660 60.760

## Table 22
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Dev Est | Changes | [13 empty] | APUC Prod Est
| Econ | Qty |  |  | Sch | Eng | Est |  | Oth |  | Spt |  |  | Total
39.150 1.408 0.142 1.377 1.715 2.323 0.000 -0.123 6.842 48.408
Current SAR Baseline to Current Estimate (TY $M)
APUC Prod Est | Changes | [13 empty] | APUC Current Est
| Econ |  | Qty |  | Sch | Eng | Est |  | Oth | Spt |  |  | Total
48.408 -0.869 0.000 0.000 0.000 2.108 0.000 -6.054 -4.815 43.592
SAR Baseline History
Item/Event |  |  |  | SAR Planning Estimate (PE) |  |  |  | SAR Development Estimate (DE) |  |  |  | SAR Production Estimate (PdE) |  |  |  | Current Estimate
Milestone A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Milestone B |  |  |  | N/A |  |  |  | JUL 2004 |  |  |  | SEP 2004 |  |  |  | AUG 2004
Milestone C |  |  |  | N/A |  |  |  | FEB 2007 |  |  |  | SEP 2008 |  |  |  | DEC 2008
IOC |  |  |  | N/A |  |  |  | OCT 2007 |  |  |  | DEC 2009 |  |  |  | MAR 2010
Total Cost (TY $M) |  |  |  | N/A |  |  |  | 1220 |  |  |  | 1348.4 |  |  |  | 1215.2
Total Quantity |  |  |  | N/A |  |  |  | 21 |  |  |  | 20 |  |  |  | 20
Prog. Acq. Unit Cost (PAUC) |  |  |  | N/A |  |  |  | 58.095 |  |  |  | 67.42 |  |  |  | 60.76
Required Assets Available (RAA) is used in place of Initial Operational Capability (IOC) date in the table above. RAA is defined as sufficient support equipment, spares, hardware, and fully qualified Mode Set 1 software to support five operational aircraft at Whiteman Air Force Base.

## Table 23
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Prod Est) | 719.1 | 629.3 | -- | 1348.4
Previous Changes
Economic | -4.6 | -11.3 | -- | -15.9
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -67 | 35.3 | -- | -31.7
Other | -- | -- | -- | --
Support | -- | -75.7 | -- | -75.7
Subtotal | -71.6 | -51.7 | -- | -123.3
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 1 | -7.9 | -- | -6.9
Other | -- | -- | -- | --
Support | -- | -3 | -- | -3
Subtotal | 1 | -10.9 | -- | -9.9
Total Changes | -70.6 | -62.6 | -- | -133.2
CE - Cost Variance | 648.5 | 566.7 | -- | 1215.2
CE - Cost & Funding | 648.5 | 566.7 | -- | 1215.2

## Table 24
Summary Base Year 2008 $M
| RDT | &E | Proc | MILCON | Total
SAR Baseline (Prod Est) Previous Changes |  | 730.9 | 593.6 | -- | 1324.5
Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | -65 | 34.1 | -- | -30.9
Other |  | -- | -- | -- | --
Support |  | -- | -72.3 | -- | -72.3
Subtotal |  | -65 | -38.2 | -- | -103.2
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | 0.9 | -7.6 | -- | -6.7
Other |  | -- | -- | -- | --
Support |  | -- | -2.8 | -- | -2.8
Subtotal |  | 0.9 | -10.4 | -- | -9.5
Total Changes |  | -64.1 | -48.6 | -- | -112.7
CE - Cost Variance |  | 666.8 | 545 | -- | 1211.8
CE - Cost & Funding |  | 666.8 | 545 | -- | 1211.8
Previous Estimate: December 2010

## Table 25
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Increase to cost estimate based on actuals to complete Engineering Design Model (EDM) antenna work. (Estimating)
+0.9 +1.0
RDT&E Subtotal +0.9 +1.0
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Decrease due to Air Force withhold to fund higher priority requirements (Estimating) -5.7 -6.0
Decrease to program office estimate to reflect reduced cost to complete Prime Power Conditioning Unit (PPCU) retrofits and change orders (Estimating)
Decrease in Other Support due to reduced costs for Program Management Administration (PMA) costs (Support)
-1.9 -1.9
-0.6 -0.7
Decrease in Initial Spares based on actual costs (Support) | -2.2 |  |  | -2.3
Procurement Subtotal | -10.4 |  |  | -10.9

## Table 26
Contracts
Appropriation: Procurement
Contract Name B-2 Radar Modernization Program Production Phase
Contractor Northrop Grumman Corporation
Contractor Location El Segundo, CA 90245 Contract Number, Type F33657-99-D-0028/41, FPIF Award Date December 29, 2008
Definitization Date December 29, 2008
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
232.5 241.8 13 462.6 481.1 13 463.8 462.6
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (9/20/2011) |  |  |  | 14.8 |  |  | -7.9
Previous Cumulative Variances |  |  |  | 18.9 |  |  | 1.1
Net Change |  |  |  | -4.1 |  |  | -9
Cost And Schedule Variance Explanations
The unfavorable net change in the cost variance is due to additional costs to complete Environmental Stress Screening and Nearfield antenna test failures that required investigation and rework efforts. In addition, the net change variance was driven by the removal and replacement of non compliant Isolators.
The unfavorable net change in the schedule variance is due to Low Rate Initial Production and Full Rate Production antenna test failures, delays in the start of integration and test efforts, delays in final quality inspection tasks and late receipt of material. The schedule variance is based on net change.
Contract Comments
The difference between the initial contract price target and the current contract price target is due to the exercise of the Full Rate Production option, as well as a contract option for eight kit installs.
Contract performance data is based on the September 20, 2011 Contract Performance Report which includes data as of August 26, 2011.

## Table 27
Deliveries and Expenditures
The expenditure data is current as of October 26, 2011.
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 7 |  | 7 |  | 7 | 100%
Production | 7 |  | 7 |  | 13 | 53.85%
Total Program Quantities Delivered | 14 |  | 14 |  | 20 | 70%
Expenditures and |  | Appropriations (TY $M)
Total Acquisition Cost | 1215.2 | Years Appropriated |  |  | 7
Expenditures To Date | 1106.3 | Percent Years Appropriated |  |  | 87.5%
Percent Expended | 91.04% | Appropriated to Date |  |  | 1202
Total Funding Years | 8 | Percent Appropriated |  |  | 98.91%

## Table 28
Operating and Support Cost
Assumptions And Ground Rules
There are no Operating and Support (O&S) costs for B-2 RMP since it is forecasted to be lower than the legacy radar system, due mostly to the higher expected reliability of the RMP antenna and the deletion of the high- maintenance transmitter.
The maintenance concept for the B-2 RMP will be the same as the legacy radar system, which has two levels (organizational and depot). Organizational maintenance will consist of Air Force maintenance personnel removing and replacing failed items, performing preventative maintenance, and conducting fault isolation actions. All repairs of Line Replaceable Units removed from B-2 aircraft will be accomplished at the depot level.
The supply support concept and the manpower and personnel requirements for the B-2 RMP will remain the same as for the legacy radar system.
The expected B-2 RMP O&S costs by element were analyzed where a delta from legacy requirements is projected. The only element expected to change in the transition from Legacy B-2 to B-2 RMP is Depot Maintenance. The Average Annual costs per Air Vehicle, for Legacy B-2 affected subsystems, is $0.2 (FY 2004 Constant (Base-Year) Dollars in Millions). The Average Annual costs per Air Vehicle, for B-2 RMP affected subsystems, is $0.1 (FY 2004 Constant (Base-Year) Dollars in Millions). There is no antecedent system for this modification. Air Force Cost Analysis Full Rate Production Decision O&S estimate has not changed from the Milestone C estimate.
Costs BY2008 $M
Cost Element | B-2 RMP N/A | No Antecedent N/A
Unit-Level Manpower | -- | --
Unit Operations | -- | --
Maintenance | -- | --
Sustaining Support | -- | --
Continuing System Improvements | -- | --
Indirect Support | -- | --
Other | -- | --
Total Unitized Cost (Base Year 2008 $) | -- | --
Total O&S Costs $M | B-2 RMP | No Antecedent
Base Year | -- | --
Then Year | -- | --