## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-365
COBRA JUDY REPLACEMENT
As of December 31, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 5
Threshold Breaches |  | 6
Schedule |  | 7
Performance |  | 9
Track To Budget |  | 11
Cost and Funding |  | 12
Low Rate Initial Production |  | 15
Nuclear Cost |  | 15
Foreign Military Sales |  | 15
Unit Cost |  | 16
Cost Variance |  | 19
Contracts |  | 22
Deliveries and Expenditures |  | 23
Operating and Support Cost |  | 24

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
Cobra Judy Replacement (COBRA JUDY REPLACEMENT)
DoD Component
Navy
Responsible Office
Responsible Office
CAPT Roderick Wester
Commander, Naval Sea Systems Command Attn: PEO IWS 2I (CAPT R. Wester)
1333 Isaac Hall Ave., SE, Stop 2318 Washington Navy, DC 20376-2318
Phone Fax
DSN Phone DSN Fax
202-781-1221
202-781-4589
--
--
roderick.wester@navy.mil Date Assigned February 11, 2009
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 1, 2003
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 8, 2011

## Table 4
Mission and Description
The COBRA JUDY REPLACEMENT (CJR) program replaces the capability of the current United States Naval Ship (USNS) Observation Island (OBIS), its COBRA JUDY radar suite, and other mission essential systems. CJR will fulfill the same mission as the current COBRA JUDY/OBIS. CJR will collect foreign ballistic missile data in support of international treaty verification.
CJR represents an integrated mission solution: ship, radar suite, and other Mission Equipment (ME). CJR will consist of a radar suite including active S-Band and X-Band Phased Array Radars (PARs), weather equipment, and a Mission Communications Suite (MCS). The radar suite will be capable of autonomous volume search and acquisition. The S-Band PAR will serve as the primary search and acquisition sensor and will be capable of tracking and collecting data on a large number of objects in a multi-target complex. The X-Band PAR will provide very high- resolution data on particular objects of interest. Both systems will employ a variety of waveforms and bandwidths to provide operational flexibility and high quality data collection. The Common Back-End (CBE) controls the radars and provides overall data and signal processing and data recording functions for the CJR ME. The CBE provides interfaces to the operator, external systems via the MCS and weather data via weather satellite. The CBE also provides pre-and post-mission processing software for mission profile generation, search volume file generation, scenario generation and mission training, data analysis, mission playback and post-mission reporting. CJR's ME is projected to have a 30-year operating system life-cycle.
The CJR platform, missile range instrumentation ship (T-AGM) USNS Howard O. Lorenzen (T-AGM 25), is a commercially designed and constructed ship, classed to American Bureau of Shipping standards, certified by the
U.S. Coast Guard in accordance with Safety of Life at Sea, and in compliance with other commercial regulatory body rules and regulations, and other Military Sealift Command (MSC) standards. The ship is U.S. flagged, operated by a Merchant Marine or MSC Civilian Mariner crew, with a minimum of military specifications. The ship is projected to have a 30-year operating system life-cycle.
The U.S. Navy has procured one CJR for the U.S. Air Force (USAF) using Research, Development, Test and Evaluation-only funding. CJR will be turned over to the USAF at Initial Operational Capability for all operations and maintenance support.

## Table 5
Executive Summary
This is the final SAR for the COBRA JUDY REPLACEMENT (CJR) program. The program is over 90% expended.
Raytheon completed installation of the X and S-band radars on the missile range instrumentation ship (T-AGM) United States Naval Ship (USNS) Howard O. Lorenzen (T-AGM 25) at Kiewit Offshore Services (KOS) in December 2011. The ship sailed away from KOS on January 22, 2012 for a two-week dry dock period in Mobile, Alabama.
The ship will sail to Norfolk, Virginia in February 2012 for in-port radar calibration prior to commencing integration and test in the Virginia Capes operating area (VACAPES). The Program Management Office (PMO) plans to conduct final Developmental Test and Operational Test (DT/OT) during the second through fourth quarters of FY 2013, consistent with the program baseline. The program is proceeding to Initial Operational Capability (IOC) and transition to the U.S. Air Force (USAF) in September 2013. The U.S. Navy is coordinating with the USAF to ensure a seamless transition.
Highlights of program progress since the previous SAR follow.
Mission Equipment (ME)
ME installation began shortly after arrival of the ship at KOS on June 20, 2011. The Space and Naval Warfare Systems Command loaded the Mission Communications Suite equipment on-board commencing June 22, 2011. Raytheon began installation of the ME on July 5, 2011. Raytheon and Northrop installed X and S-band wrap room interconnections, antenna servo control system cabinets, prime power systems, and the Common Back End (CBE) equipment in July/August 2011. Raytheon installed the X-band radar antenna and pedestal assembly in July 2011 followed by the S-band radar antenna and pedestal assembly in August 2011. Raytheon successfully demonstrated X and S-band antenna pedestal full rate motion in both azimuth and elevation in October 2011.
Initial shipboard integration is in-process. Raytheon completed initial-light off of the CBE and X and S-band radar power and cooling systems in November 2011. Raytheon loaded CJR software onto the CBE and successfully executed a digital simulation scenario onboard the ship. Raytheon initiated X-band single element testing and verified CBE control of all S-band multi-subarray assemblies in January 2012.
USNS Howard O. Lorenzen (T-AGM 25)
VT Halter Marine, Inc. (VTHM) conducted the final Builder’s Trial in June 2011. Two at-sea Acceptance Trials (AT) were conducted in May and June 2011. An in-port AT was completed in September 2011. The ship was provided to Raytheon as Government-Furnished Equipment on July 5, 2011. Contractual delivery of the USNS Howard O. Lorenzen (T-AGM 25) occurred on January 10, 2012, past the November 2011 Acquisition Program Baseline (APB) threshold date. Delivery was delayed until VTHM completed all requirements for contractual delivery. Ship construction and test are complete. The ship is currently manned and operated by a Military Sealift Command crew.
Late ship delivery will not result in a breach in the remaining APB parameters. The PMO decision to commence shipboard installation of ME in July 2011, upon completion of AT and prior to contractual delivery, mitigated the impact of late ship delivery to IOC. PMO estimates for DT/OT are within current APB schedule parameters. The IOC objective date remains September 2013. There is no impact to the program acquisition unit cost. The FY 2013 President’s Budget contains sufficient funds to complete the program.
Effective November 1, 2011 the USAF designated the operational name for the CJR radar system as COBRA KING.
There are no significant software-related issues with this program at this time.

## Table 6
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
Explanation of Breach
VT Halter Marine, Inc. (VTHM) delivered the missile range instrumentation ship (T-AGM) United States Naval Ship Howard O. Lorenzen (T-AGM 25) to the U.S. Navy on January 10, 2012, breaching the November 2011 threshold date. Delivery was delayed until VTHM completed all requirements for contractual delivery. The Program Management Office submitted a Program Deviation Report in December 2011.
Late ship delivery will not result in a breach in the remaining Acquisition Program Baseline (APB) schedule parameters. VTHM sailed the ship
to Kiewit Offshore Services for Mission Equipment (ME) installation in June 2011. ME installation is complete. Ship construction and test are complete. Developmental/operational test dates are within current APB parameters. The Initial Operational Capability objective date remains September 2013.
Nunn-McCurdy Breaches

## Table 7
Schedule
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B/C | SEP 2003 | SEP 2003 | MAR 2004 | OCT 2003
X-Band Phased Array Critical Design Review | AUG 2005 | AUG 2005 | FEB 2006 | FEB 2006
S-Band Phased Array Critical Design Review | SEP 2005 | SEP 2005 | MAR 2006 | MAR 2006
Milestone Decision Authority (MDA) Review | SEP 2005 | AUG 2006 | SEP 2006 | SEP 2006
Ship Procurement | APR 2006 | APR 2006 | OCT 2006 | SEP 2006
Ship Construction / Conversion Start | JUL 2007 | JUL 2007 | JAN 2008 | NOV 2007
Mission Equipment Delivery | JUN 2009 | OCT 2010 | APR 2011 | MAR 2011
Ship Delivery | DEC 2009 | MAY 2011 | NOV 2011 | JAN 2012 1
TECHEVAL Start | DEC 2009 | JAN 2013 | JUL 2013 | FEB 2013
TECHEVAL Completion | JUN 2010 | APR 2013 | OCT 2013 | MAY 2013
OPEVAL Start | AUG 2010 | MAY 2013 | NOV 2013 | JUN 2013
OPEVAL Completion | FEB 2011 | JUL 2013 | JAN 2014 | AUG 2013
Initial Operational Capability | JUN 2011 | SEP 2013 | MAR 2014 | SEP 2013
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
1APB Breach
Acronyms And Abbreviations

## Table 8
OPEVAL - Operational Evaluation TECHEVAL - Technical Evaluation
Change Explanations
(Ch-1) Ship Delivery was changed from May 2011 to January 2012 to reflect the actual ship contractual delivery, which occurred on January 10, 2012. Ship delivery was delayed until all conditions for contractual delivery were complete.
Late ship delivery will not result in a breach in the remaining Acquisition Program Baseline parameters. The Program Management Office decision to commence shipboard installation of mission equipment in July 2011, upon completion of acceptance trials and prior to contractual delivery, mitigated the impact of late ship delivery to Initial Operational Capability.
The following milestones are impacted by late ship delivery. TECHEVAL Start was changed from January 2013 to February 2013. TECHEVAL Completion was changed from April 2013 to May 2013. OPEVAL Start was changed from May 2013 to June 2013.
OPEVAL Completion was changed from July 2013 to August 2013.

## Table 9
Performance
Characteristics | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Propulsion Plant, | Ship | Ship | Ship | Ship | Ship
Sustained and Loiter | Duration = | Duration = | Duration = | Construction | Duration =
Speed | 12,000 NM. | 12,000 NM. | 12,000 NM. | Test and | 12,000 NM.
| The ship | The ship | The ship | Trials - | The ship
| shall be | shall be | shall be | Acceptance | shall be
| capable of | capable of | capable of | trials | capable of
| traveling | traveling | traveling | included: Full | traveling
| 12,000 NM | 12,000 NM | 12,000 NM | power trial: | 12,000 NM
| at 20 knots | at 20 knots | at 20 knots | over a 4 hour | at 20 knots
| sustained | sustained | sustained | period | sustained
| speed | speed | speed | averaged 22 | speed
knots /
endurance at
full power:
14,058 NM;
and
Endurance
trial:
maintained
20 knots for
4 hours/
endurance at
20 knots:
18,284 NM
Mission Capable Rates | System | System | System | TBD | System
and Inherent | Availability = | Availability = | Availability = |  | Availability =
Availability (Ai) | 90%. In | 90%. In | 90%. In |  | 90%. In
| order to | order to | order to |  | order to
| achieve the | achieve the | achieve the |  | achieve the
| FMC Ai | FMC Ai | FMC Ai |  | FMC Ai
| requirement, | requirement, | requirement, |  | requirement,
| the CJR | the CJR | the CJR |  | the CJR
| system must | system must | system must |  | system must
| be available | be available | be available |  | be available
| at least 90% | at least 90% | at least 90% |  | at least 90%
| of the time. | of the time. | of the time. |  | of the time.
| FMC for the | FMC for the | FMC for the |  | FMC for the
| CJR is | CJR is | CJR is |  | CJR is
| defined as | defined as | defined as |  | defined as
| both the | both the | both the |  | both the
| platform and | platform and | platform and |  | platform and
| mission | mission | mission |  | mission
| equipment | equipment | equipment |  | equipment
| functioning | functioning | functioning |  | functioning
| as required | as required | as required |  | as required
| to achieve | to achieve | to achieve |  | to achieve
| the | the | the |  | the

## Table 10
| operational mission | operational mission | operational mission |  | operational mission
Interoperability - All top- | 100% of all | 100% of all | 100% of | TBD | 100% of all
level IERs will be | Top-Level | Top-Level | Top-Level |  | Top-Level
satisfied to the | IERs | IERs | IERs |  | IERs
standards identified in |  |  | designated
the threshold and |  |  | critical (IERs
objective values in |  |  | 1-5)
CJR Top-Level
Information Exchange
Requirements Matrix
Requirements Source: The Joint Requirements Oversight Council approved the COBRA JUDY REPLACEMENT (CJR) Operational Requirements Document (ORD), United States Air Force (USAF) Combat Air Force(CAF) 315- 02, on April 24, 2003.
Acronyms And Abbreviations
FMC - Full Mission Capability
IER - Informational Exchange Requirements NM - Nautical Mile
TBD - To Be Determined
Change Explanations
None
Classified Performance information is provided in the classified annex to this submission.

## Table 11
Track To Budget
RDT&E
APPN 1319 | BA 07 Project 4003 | PE 0303901N SIRIUS | (Navy) | (Sunk)
APPN 1319 | BA 07 Project 4021 | PE 0305149N COBRA JUDY | (Navy) | (Sunk)

## Table 12
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
| BY2003 $M |  |  |  |  | BY2003 $M |  | TY $M
Appropriation | SAR Baseline Dev Est |  | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 1365 |  | 1529.6 |  | 1682.6 | 1524.8 |  | 1464 | 1716.6 | 1713.9
Procurement | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Flyaway | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Recurring | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Non Recurring | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Support | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Other Support | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Initial Spares | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
MILCON | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Acq O&M | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Total | 1365 |  | 1529.6 |  | N/A | 1524.8 |  | 1464 | 1716.6 | 1713.9
Confidence Level For the Current APB Cost is 50% - The independent cost estimate to support CJR, like all life-cycle cost estimates previously performed by the Cost Assessment and Program Evaluation team, is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and Government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for major defense acquisition programs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Quantity |  | SAR Baseline Dev Est |  | Current APB Development |  |  | Current Estimate
RDT&E |  | 1 |  | 1 |  |  | 1
Procurement |  | 0 |  | 0 |  |  | 0
Total |  | 1 |  | 1 |  |  | 1

## Table 13
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2013 President's Budget / December 2011 SAR (TY$ M)
The U.S. Navy (USN) will use Navy Research, Development, Test and Evaluation (RDT&E) funding to develop and deliver CJR. The USN will not receive Procurement, Military Construction, or Operations and Maintenance (O&M) funding. CJR will be transitioned to the U.S. Air Force at Initial Operational Capability for all O&M support.
Only one RDT&E unit will be acquired; no procurement units are planned. The revised Acquisition Program Baseline was approved by the Under Secretary of Defense (Acquisition, Technology and Logistics) on April 8, 2011.
Appropriation |  | Prior | FY2012 |  | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
RDT&E |  | 1600.2 | 80.6 |  | 33.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1713.9
Procurement |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MILCON |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2013 Total |  | 1600.2 | 80.6 |  | 33.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1713.9
PB 2012 Total |  | 1600.5 | 80.6 |  | 33.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1714.2
Delta |  | -0.3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -0.3
Quantity | Undistributed |  |  | Prior |  | FY2012 |  | FY2013 | FY2014 | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
Development | 1 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1
Production | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2013 Total | 1 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1
PB 2012 Total | 1 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1
Delta | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 14
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2003 | -- | -- | -- | -- | -- | -- | 101
2004 | -- | -- | -- | -- | -- | -- | 126
2005 | -- | -- | -- | -- | -- | -- | 175.1
2006 | -- | -- | -- | -- | -- | -- | 236.8
2007 | -- | -- | -- | -- | -- | -- | 263.2
2008 | -- | -- | -- | -- | -- | -- | 267.8
2009 | -- | -- | -- | -- | -- | -- | 243.8
2010 | -- | -- | -- | -- | -- | -- | 115.8
2011 | -- | -- | -- | -- | -- | -- | 70.7
2012 | -- | -- | -- | -- | -- | -- | 80.6
2013 | -- | -- | -- | -- | -- | -- | 33.1
Subtotal | 1 | -- | -- | -- | -- | -- | 1713.9

## Table 15
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2003 $M | Non End Item Recurring Flyaway BY 2003 $M | Non Recurring Flyaway BY 2003 $M | Total Flyaway BY 2003 $M | Total Support BY 2003 $M | Total Program BY 2003 $M
2003 | -- | -- | -- | -- | -- | -- | 99.8
2004 | -- | -- | -- | -- | -- | -- | 121.1
2005 | -- | -- | -- | -- | -- | -- | 163.9
2006 | -- | -- | -- | -- | -- | -- | 215
2007 | -- | -- | -- | -- | -- | -- | 233.3
2008 | -- | -- | -- | -- | -- | -- | 233.1
2009 | -- | -- | -- | -- | -- | -- | 209.5
2010 | -- | -- | -- | -- | -- | -- | 98
2011 | -- | -- | -- | -- | -- | -- | 58.7
2012 | -- | -- | -- | -- | -- | -- | 65.8
2013 | -- | -- | -- | -- | -- | -- | 26.6
Subtotal | 1 | -- | -- | -- | -- | -- | 1524.8
Low Rate Initial Production
There is no Low Rate Initial Production for the CJR program.
Foreign Military Sales
None
Nuclear Cost
None

## Table 16
Unit Cost
Unit Cost Report
|  | BY2003 $M | BY2003 $M
Unit Cost |  | Current UCR Baseline (APR 2011 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1529.6 |  |  | 1524.8
Quantity | 1 |  |  | 1
Unit Cost | 1529.6 |  |  | 1524.8 |  |  | -0.31
Average Procurement Unit Cost (APUC)
Cost | 0 |  |  | 0
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  |  | --
|  | BY2003 $M | BY2003 $M
Unit Cost |  | Original UCR Baseline (OCT 2003 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1365 |  |  | 1524.8
Quantity | 1 |  |  | 1
Unit Cost | 1365 |  |  | 1524.8 |  | 11.71
Average Procurement Unit Cost (APUC)
Cost | -- |  |  | 0
Quantity Unit Cost | -- -- |  |  | 0 -- |  | --

## Table 17
Unit Cost History
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
[9 empty] | BY2003 $M | [6 empty] | TY $M
|  |  | Date | [5 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  | APUC
Original APB |  |  | OCT 2003 | [5 empty] | 1365 |  | N/A |  |  |  |  | 1464 |  | N/A
APB as of January 2006 |  |  | OCT 2003 | [5 empty] | 1365 |  | N/A |  |  |  |  | 1464 |  | N/A
Revised Original APB |  |  | N/A | [5 empty] | N/A |  | N/A |  |  |  |  | N/A |  | N/A
Prior APB |  |  | FEB 2008 | [5 empty] | 1365 |  | N/A |  |  |  |  | 1464 |  | N/A
Current APB |  |  | APR 2011 | [5 empty] | 1529.6 |  | N/A |  |  |  |  | 1716.6 |  | N/A
Prior Annual SAR |  |  | DEC 2010 | [5 empty] | 1527.6 |  | N/A |  |  |  |  | 1714.2 |  | N/A
Current Estimate |  |  | DEC 2011 | [5 empty] | 1524.8 |  | N/A |  |  |  |  | 1713.9 |  | N/A
Initial PAUC Dev Est | Changes | [15 empty] | PAUC Current Est
| Econ | Qty |  | Sch |  | Eng | Est |  |  | Oth |  | Spt |  | Total
1464.000 54.200 0.000 36.300 0.000 159.400 0.000 0.000 249.900 1713.900
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes | [15 empty] | APUC Current Est
| Econ | Qty |  |  | Sch | Eng |  | Est |  | Oth |  |  | Spt |  | Total
0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000

## Table 18
SAR Baseline History
Item/Event | SAR Planning Estimate (PE) | SAR Development Estimate (DE) | SAR Production Estimate (PdE) | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | SEP 2003 | N/A | OCT 2003
Milestone C | N/A | N/A | N/A | N/A
IOC | N/A | JUN 2011 | N/A | SEP 2013
Total Cost (TY $M) | N/A | 1464 | N/A | 1713.9
Total Quantity | N/A | 1 | N/A | 1
Prog. Acq. Unit Cost (PAUC) | N/A | 1464 | N/A | 1713.9
On October 1, 2003, the Milestone Decision Authority approved Milestone B/C and allowed the program to enter into the System Development and Demonstration and Production phases.

## Table 19
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Dev Est) 1464.0 -- -- 1464.0
Previous Changes
Economic |  | 51.2 |  | -- |  | -- |  | 51.2
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | 36.3 |  | -- |  | -- |  | 36.3
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 162.7 |  | -- |  | -- |  | 162.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 250.2 |  | -- |  | -- |  | 250.2
Current Changes Economic |  | 3 |  | -- |  | -- |  | 3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -3.3 |  | -- |  | -- |  | -3.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -0.3 |  | -- |  | -- |  | -0.3
Total Changes |  | 249.9 |  | -- |  | -- |  | 249.9
CE - Cost Variance |  | 1713.9 |  | -- |  | -- |  | 1713.9
CE - Cost & Funding |  | 1713.9 |  | -- |  | -- |  | 1713.9

## Table 20
Summary Base Year 2003 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Dev Est) 1365.0 -- -- 1365.0
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | 30 |  | -- |  | -- |  | 30
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 132.6 |  | -- |  | -- |  | 132.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 162.6 |  | -- |  | -- |  | 162.6
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -2.8 |  | -- |  | -- |  | -2.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -2.8 |  | -- |  | -- |  | -2.8
Total Changes |  | 159.8 |  | -- |  | -- |  | 159.8
CE - Cost Variance |  | 1524.8 |  | -- |  | -- |  | 1524.8
CE - Cost & Funding |  | 1524.8 |  | -- |  | -- |  | 1524.8
Previous Estimate: December 2010

## Table 21
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 3
Budget decrease due to Navy withholds. (Estimating) | -0.6 | -0.7
Adjustment for current and prior escalation. (Estimating) | -2.2 | -2.6
RDT&E Subtotal | -2.8 | -0.3

## Table 22
Contracts
There are no Contracts data to display.

## Table 23
Deliveries and Expenditures
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 1 | 0%
Production | 0 |  | 0 |  | 0 | --
Total Program Quantities Delivered | 0 |  | 0 |  | 1 | 0%
Expendi | tures and | Appropriations (TY $M)
Total Acquisition Cost | 1713.9 | Years Appropriated |  |  | 10
Expenditures To Date | 1560.5 | Percent Years Appropriated |  |  | 90.91%
Percent Expended | 91.05% | Appropriated to Date |  |  | 1680.8
Total Funding Years | 11 | Percent Appropriated |  |  | 98.07%
Expenditures are as of December 31, 2011.
Only one Research, Development, Test and Evaluation unit will be acquired; no procurement units are planned.

## Table 24
Operating and Support Cost
Assumptions And Ground Rules
Annual Operating and Support (O&S) costs for CJR reflect the Cost Assessment and Program Evaluation Independent Cost Estimate of May 2003, which is reflected in the Acquisition Program Baseline. Total O&S costs are projected for a 30-year operating system life-cycle and include disposal costs.
Annual O&S costs from the antecedent system, the current COBRA JUDY program owned and managed by the
U.S. Air Force, represent an average of actual costs from FY 2003-2011, and estimated costs for FY 2012.
Total O&S costs for the COBRA JUDY program include data from FY 1999-2012. Cost data prior to FY 1999 was not available.
Costs BY2003 $M
Cost Element | COBRA JUDY REPLACEMENT Annual Cost | COBRA JUDY Annual Cost
Unit-Level Manpower | 11.064 | 12.889
Unit Operations | 5.582 | 8.216
Maintenance | 5.742 | 12.46
Sustaining Support | 2.543 | 1.283
Continuing System Improvements | 4.833 | 1.421
Indirect Support | 0.032 | 0.91
Other | 0.9 | 1.878
Total Unitized Cost (Base Year 2003 $) | 30.696 | 39.057
Total O&S Costs $M | COBRA JUDY REPLACEMENT | COBRA JUDY
Base Year | 950.2 | 541.2
Then Year | 1522.8 | 588.5