## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-247
Joint High Speed Vessel (JHSV)
As of December 31, 2012
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 5
Threshold Breaches |  | 6
Schedule |  | 7
Performance |  | 9
Track To Budget |  | 17
Cost and Funding |  | 18
Low Rate Initial Production |  | 29
Foreign Military Sales |  | 30
Nuclear Cost |  | 30
Unit Cost |  | 31
Cost Variance |  | 34
Contracts |  | 37
Deliveries and Expenditures |  | 46
Operating and Support Cost |  | 47

## Table 3
Program Information
Program Name
Joint High Speed Vessel (JHSV)
DoD Component
Navy
Responsible Office
Responsible Office
CAPT Henry Stevens | Phone | 202-781-1187
1333 Isaac Hull Avenue | Fax | 202-781-4574
Building 197 | DSN Phone | 326-1187
Washington Navy Yard, DC 20376 | DSN Fax | 326-4574
henry.stevens@navy.mil | Date Assigned | June 1, 2011
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 11, 2009
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 11, 2009

## Table 4
Mission and Description
The Joint High Speed Vessel (JHSV) is a shallow draft, commercial-based ship capable of intra-theater personnel and cargo lift providing combatant commanders high-speed sealift mobility with inherent cargo handling capability and agility to achieve positional advantage over operational distances. Bridging the gap between low-speed sealift and high-speed airlift, the JHSV will transport personnel, equipment, and supplies over operational distances with access to littoral offload points including austere, minor and degraded ports in support of the Global War on Terrorism (GWOT)/Theater Security Cooperation Program (TSCP); Intra-theater Operational/Littoral Maneuver and Sustainment; and Seabasing. The JHSV will enable the rapid projection, agile maneuver, and sustainment of modular, tailored forces in response to a wide range of military and civilian contingencies such as Non-Combatant Evacuation Operations, humanitarian assistance, and disaster relief.

## Table 5
Executive Summary
Austal delivered JHSV 1 (USNS SPEARHEAD) on December 5, 2012. The ship was subsequently transferred to the Military Sealift Command. In advance of delivery, the vessel successfully completed Acceptance Trials conducted by the Navy’s Board of Inspection and Survey (INSURV) in August 2012. USNS SPEARHEAD will undergo Initial Operational Test and Evaluation (IOT&E) in 2013 during the Post Delivery phase, culminating in Initial Operational Capability for the first ship of the class.
Austal launched JHSV 2 (CHOCTAW COUNTY) on October 1, 2012, after a formal Christening ceremony on September 15, 2012, presided over by the Secretary of the Navy. Austal and the Navy have been preparing for and readying the vessel for ship trials, which commenced in 2nd Quarter FY 2013.
Construction continued on JHSV 3 (MILLINOCKET), as the shipyard began the transition from modular construction to ship assembly. A Keel Laying ceremony was held at Austal on May 3, 2012, to mark the movement into ship erection. Main engines have been loaded onto the ship, and all of the modules have now been erected. The Navy is anticipating the vessel to be launched in 3rd Quarter FY 2013.
Austal started construction on JHSV 4 (FALL RIVER) in May 2012, largely focused on the fabrication and assembly of individual modules in its Modular Manufacturing Facility. However, the first modules began erection in the assembly bay in early 2013, and a Keel Laying ceremony is planned for 3rd Quarter FY 2013.
Austal started construction on JHSV 5 (TRENTON) in February 2013. Construction material ordering has been initiated for JHSVs 6 through 9 with start of construction planned as follows: JHSV 6 (BRUNSWICK) in 4th Quarter FY 2013, JHSV 7 (CARSON CITY) in 2nd Quarter FY 2014, JHSV 8 in 4th Quarter FY 2014, and JHSV 9 in 2nd Quarter FY 2015.
The tenth and final ship of the existing contract was awarded to Austal on December 20, 2012. That ship is forecasted to deliver to the Navy in FY 2017.
This SAR has been updated with current information and data as of April 29, 2013.
This is the final SAR submission for JHSV, because the FY 2013 President’s Budget truncated the program from 18 to 10 ships, thereby reducing total costs below the Major Defense Acquisition Program threshold in section 2430 of title 10, United States Code.
There are no significant software-related issues with this program at this time.

## Table 6
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Explanation of Breach
The lead ship was ready for delivery prior to the end of November, but formal delivery did not occur until December 5, 2012.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 7
Schedule

## Table 8
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
DAB MS B | OCT 2008 | OCT 2008 | APR 2009 | OCT 2008
Contract Award | NOV 2008 | NOV 2008 | MAY 2009 | NOV 2008
Initial Critical Design Review | MAY 2009 | MAY 2009 | NOV 2009 | MAY 2009
Production Readiness Review | NOV 2009 | NOV 2009 | MAY 2010 | OCT 2009
Keel Laying | MAY 2010 | MAY 2010 | NOV 2010 | JUL 2010
Lead Ship Delivery | NOV 2011 | NOV 2011 | NOV 2012 | DEC 2012 1
IOC | OCT 2012 | OCT 2012 | OCT 2013 | NOV 2013 1
Follow Ship 0901N Delivery | JAN 2013 | JAN 2013 | JAN 2014 | JUN 2013
IOT&E Complete | SEP 2012 | SEP 2012 | SEP 2013 | AUG 2013
DAB MS C | SEP 2012 | SEP 2012 | SEP 2013 | N/A 1
Follow Ship 0902A Delivery | JUL 2013 | JUL 2013 | JUL 2014 | DEC 2013
Follow Ship 1001N Delivery | JAN 2014 | JAN 2014 | JAN 2015 | JUN 2014
Follow Ship 1002A Delivery | JUL 2014 | JUL 2014 | JUL 2015 | DEC 2014
Follow Ship 1101N Delivery | JAN 2015 | JAN 2015 | JAN 2016 | JUN 2015
Follow Ship 1102A Delivery | JUL 2015 | JUL 2015 | JUL 2016 | DEC 2015
Follow Ship 1201N Delivery | JAN 2016 | JAN 2016 | JAN 2017 | JUN 2016
Follow Ship 1202A Delivery | JUL 2016 | JUL 2016 | JUL 2017 | DEC 2016
Follow Ship 1301N Delivery | JAN 2017 | JAN 2017 | JAN 2018 | JUN 2017
1APB Breach
(Ch-1)
(Ch-2)
(Ch-3)
(Ch-2)
(Ch-4)
(Ch-3)
(Ch-3)
(Ch-3)
(Ch-3)
(Ch-3)
(Ch-3)
(Ch-3)
(Ch-3)
Acronyms And Abbreviations
DAB - Defense Acquisition Board IOC - Initial Operational Capability
IOT&E - Initial Operational Test and Evaluation MS - Milestone
N/A - Not Applicable
Change Explanations
(Ch-1) The current estimate for Lead Ship Delivery changed from April 2012 to December 2012 to complete lead ship testing. The ship was ready for delivery prior to the end of November; however, formal delivery did not occur until December 5, 2012.
(Ch-2) The current estimate for IOC changed from December 2012 to November 2013 and for IOT&E Complete from April 2013 to August 2013 due to lead ship delivery delays.
(Ch-3) The current estimate for JHSV 2 delivery changed from January 2013 to June 2013 due to the delay in delivery of JHSV 1. Delivery of the follow JHSVs is also delayed due to lead ship delivery.
(Ch-4) MS C is no longer required due to truncation of the program from 18 to 10 ships.

## Table 9
Performance
Characteristics | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Transport Capability | JHSV shall | JHSV shall | JHSV shall | In progress | JHSV shall
| be capable | be capable | be capable |  | be capable
| of | of | of |  | of
| transporting | transporting | transporting |  | transporting
| 700 ST | 700 ST | 600 ST of |  | 600 ST
| 1200 NM at | 1200 NM at | troops, |  | 1200 NM at
| an average | an average | supplies, |  | an average
| speed of 35 | speed of 35 | and |  | speed of 35
| kts in a | kts in a | equipment |  | kts in a
| significant | significant | 1200 NM at |  | significant
| wave height | wave height | an average |  | wave height
| of 1.25 | of 1.25 | speed of 35 |  | of 1.25
| meters prior | meters prior | kts in a |  | meters prior
| to needing | to needing | significant |  | to needing
| refueling. | refueling. | wave height |  | refueling.
of 1.25
meters prior
to needing
refueling.
Draft | JHSV shall | JHSV shall | JHSV shall | In progress | JHSV shall
| have a draft | have a draft | have a draft |  | have a draft
| of less than | of less than | of less than |  | of less than
| or equal to | or equal to | or equal to |  | or equal to
| 10 ft. | 10 ft. | 15 ft. |  | 13 ft.
Ramp (M1A2 Capable) | JHSV shall | JHSV shall | JHSV shall | In progress | JHSV shall
| have a ramp | have a ramp | have a ramp |  | have a ramp
| capable of | capable of | capable of |  | capable of
| interfacing | interfacing | interfacing |  | interfacing
| with RRDFs, | with RRDFs, | with RRDFs, |  | with RRDFs,
| piers with | piers with | piers with |  | piers with
| curb heights | curb heights | curb heights |  | curb heights
| of up to 15 | of up to 15 | of up to 15 |  | of up to 15
| in., quay | in., quay | in., quay |  | in., quay
| walls and | walls and | walls and |  | walls and
| other | other | other |  | other
| austere on- | austere on- | austere on- |  | austere on-
| and off-load | and off-load | and off-load |  | and off-load
| points and | points and | points and |  | points and
| on/off- | on/off- | on/off- |  | on/off-
| loading a | loading a | loading a |  | loading a
| combat- | combat- | combat- |  | combat-
| loaded | loaded | loaded |  | loaded
| M1A2 with | M1A2 with | M1A2 with |  | M1A2 with
| articulation | articulation | articulation |  | articulation

## Table 10
| from dead astern to 40 deg abaft the beam to either side. | from dead astern to 40 deg abaft the beam to either side. | from dead astern to 40 deg abaft the beam towards one side. |  | from dead astern to 40 deg abaft the beam to one side.
Cargo movement | JHSV shall | JHSV shall | JHSV shall | In progress | JHSV shall
between mission deck | have the | have the | have the |  | have the
and flight deck; | capability to | capability to | capability to |  | capability to
between pier and | move | move | move |  | move
mission deck. | 27,000 lbs of | 27,000 lbs of | 27,000 lbs of |  | 27,000 lbs of
| cargo in a | cargo in a | cargo in a |  | cargo in a
| single lift | single lift | single lift |  | single lift
| between the | between the | between the |  | between the
| flight deck | flight deck | flight deck |  | flight deck
| and the | and the | and the |  | and the
| mission | mission | mission |  | mission
| deck in a | deck in a | deck in a |  | deck in a
| significant | significant | significant |  | significant
| wave height | wave height | wave height |  | wave height
| of 1.25 | of 1.25 | of 1.25 |  | of 1.25
| meters. | meters. | meters. |  | meters.
| JHSV shall | JHSV shall | JHSV shall |  | JHSV shall
| have the | have the | have the |  | have the
| capability to | capability to | capability to |  | capability to
| move | move | move |  | move
| 40,000 lbs of | 40,000 lbs of | 40,000 lbs of |  | 40,000 lbs of
| cargo in a | cargo in a | cargo in a |  | cargo in a
| single lift | single lift | single lift |  | single lift
| between the | between the | between the |  | between the
| mission | mission | mission |  | mission
| deck and the | deck and the | deck and the |  | deck and the
| pier in a | pier in a | pier in a |  | pier in a
| significant | significant | significant |  | significant
| wave height | wave height | wave height |  | wave height
| of 0.1 | of 0.1 | of 0.1 |  | of 0.1
| meters. | meters. | meters. |  | meters.
Net-Ready KPP | The system | The system | The system | In progress | The system
| must fully | must fully | must fully |  | must fully
| support | support | support |  | support
| execution of | execution of | execution of |  | execution of
| all | all | joint critical |  | all
| operational | operational | operational |  | operational
| activities | activities | activities |  | activities
| identified in | identified in | identified in |  | identified in
| the | the | the |  | the
| applicable | applicable | applicable |  | applicable
| joint and | joint and | joint and |  | joint and
| system | system | system |  | system
| integrated | integrated | integrated |  | integrated
| architectures | architectures | architectures |  | architectures

## Table 11
and the | and the | and the | and the
system must | system must | system must | system must
satisfy the | satisfy the | satisfy the | satisfy the
technical | technical | technical | technical
requirements | requirements | requirements | requirements
for Net- | for Net- | for transition | for Net-
Centric | Centric | to Net- | Centric
military | military | Centric | military
operations | operations | military | operations
to include 1) | to include 1) | operations | to include 1)
DISR | DISR | to include 1) | DISR
mandated | mandated | DISR | mandated
GIG IT | GIG IT | mandated | GIG IT
standards | standards | GIG IT | standards
and profiles | and profiles | standards | and profiles
identified in | identified in | and profiles | identified in
the TV-1, 2) | the TV-1, 2) | identified in | the TV-1, 2)
DISR | DISR | the TV-1, 2) | DISR
mandated | mandated | DISR | mandated
GIG KIPs | GIG KIPs | mandated | GIG KIPs
identified in | identified in | GIG KIPs | identified in
the KIP | the KIP | issuance of | the KIP
declaration | declaration | an IATO by | declaration
table, 3) | table, 3) | the DAA, | table, 3)
NCOW RM | NCOW RM | and 3) | NCOW RM
Enterprise | Enterprise | NCOW RM | Enterprise
Services 4) | Services 4) | Enterprise | Services 4)
IA | IA | Services 4) | IA
requirements | requirements | IA | requirements
including | including | requirements | including
availability, | availability, | including | availability,
integrity, | integrity, | availability, | integrity,
authentica- | authentica- | integrity, | authentica-
tion, | tion, | authentica- | tion,
confidential- | confidential- | tion, | confidenti-
ity, and | ity, and | confidential- | ality, and
nonrepudia- | nonrepudia- | ity, and | nonrepudia-
tion, and | tion, and | nonrepudia- | tion, and
issuance of | issuance of | tion, and | issuance of
an ATO by | an ATO by | issuance of | an ATO by
the DAA, | the DAA, | an ATO by | the DAA,
and 5) | and 5) | the DAA, | and 5)
Operationally | Operationally | and 5) | Operationally
effective | effective | Operationally | effective
information | information | effective | information
exchanges; | exchanges; | information | exchanges;
and mission | and mission | exchanges; | and mission
critical | critical | and mission | critical
performance | performance | critical | performance
and IA | and IA | performance | and IA
attributes, | attributes, | and IA | attributes,

## Table 12
| data | data | attributes, |  | data
| correctness, | correctness, | data |  | correctness,
| data | data | correctness, |  | data
| availability, | availability, | data |  | availability,
| and | and | availability, |  | and
| consistent | consistent | and |  | consistent
| data | data | consistent |  | data
| processing | processing | data |  | processing
| specified in | specified in | processing |  | specified in
| the | the | specified in |  | the
| applicable | applicable | the |  | applicable
| joint and | joint and | applicable |  | joint and
| system | system | joint and |  | system
| integrated | integrated | system |  | integrated
| architecture | architecture | integrated |  | architecture
| views. | views. | architecture |  | views.
views.
Force Protection | The JHSV | The JHSV | JHSV shall | In progress | JHSV shall
| shall | shall | be equipped |  | be equipped
| possess a | possess a | with a crew- |  | with a crew-
| force | force | served |  | served
| protection | protection | weapons |  | weapons
| system to | system to | system. |  | system.
| sense, | sense, | Additionally, |  | Additionally,
| identify and | identify and | JHSV shall |  | JHSV shall
| lethally | lethally | provide the |  | provide the
| engage | engage | space, |  | space,
| surface | surface | weight and |  | weight and
| threats such | threats such | power for |  | power for
| as patrol | as patrol | obtaining the |  | obtaining the
| boats and | boats and | objective. |  | objective.
| Boghammer | Boghammer
| type threats. | type threats.
| The SST | The SST
| function shall | function shall
| provide the | provide the
| capability to | capability to
| sense, | sense,
| identify and | identify and
| track | track
| potential | potential
| surface | surface
| threats in | threats in
| nighttime, | nighttime,
| low light, and | low light, and
| limited | limited
| visibility | visibility
| conditions | conditions
| such as haze | such as haze
| and light fog | and light fog
| throughout | throughout

## Table 13
360 | 360
degrees. | degrees.
The SST | The SST
function shall | function shall
provide | provide
JHSV watch | JHSV watch
standers | standers
capability to | capability to
sense | sense
potential | potential
surface | surface
threats at a | threats at a
range no | range no
less than the | less than the
effective line- | effective line-
of-sight of | of-sight of
the JHSV’s | the JHSV’s
navigation | navigation
radars. The | radars. The
SST function | SST function
shall provide | shall provide
simultaneous | simultaneous
and | and
continuous | continuous
visual auto- | visual auto-
tracking of | tracking of
no less than | no less than
two operator | two operator
selected | selected
surface | surface
threats at a | threats at a
range of no | range of no
less than | less than
750 meters | 750 meters
during | during
daytime, | daytime,
nighttime | nighttime
(low-light | (low-light
conditions) | conditions)
and during | and during
limited | limited
visibility | visibility
conditions | conditions
such as haze | such as haze
or light fog. | or light fog.
JHSV shall | JHSV shall
possess | possess
sufficient | sufficient
small arms | small arms
gun mounts | gun mounts
to engage | to engage

## Table 14
threat | threat
surface | surface
platforms | platforms
throughout | throughout
no less than | no less than
360 deg. | 360 deg.
The gun | The gun
mounts shall | mounts shall
be stabilized | be stabilized
in at least 2 | in at least 2
axis in sea | axis in sea
states with a | states with a
significant | significant
wave heights | wave heights
of up to 6-8 | of up to 6-8
ft. during | ft. during
wind | wind
conditions of | conditions of
17-21 kts. | 17-21 kts.
The gun | The gun
mount(s) | mount(s)
shall have | shall have
the | the
capability to | capability to
lethally | lethally
engage | engage
patrol boats / | patrol boats /
Boghammer | Boghammer
threats with | threats with
a hit | a hit
probability of | probability of
no less than | no less than
70 % at 500 | 70 % at 500
yds. Gun | yds. Gun
mounts shall | mounts shall
be remotely | be remotely
linked to the | linked to the
SST and be | SST and be
capable of | capable of
being slaved | being slaved
to the SST | to the SST
tracking | tracking
function or | function or
being | being
remotely | remotely
operated by | operated by
JHSV | JHSV
watchstander | watchstander
(s). Gun | (s). Gun
mounts shall | mounts shall
be capable | be capable

## Table 15
| of hosting a | of hosting a
| variety of | variety of
| small arms | small arms
| to include: | to include:
| M2 .50 | M2 .50
| caliber | caliber
| machine | machine
| guns and | guns and
| MK-19 | MK-19
| grenade | grenade
| launchers. | launchers.
| The surface | The surface
| force | force
| protection | protection
| system shall | system shall
| be | be
| completely | completely
| operable | operable
| from the | from the
| watch | watch
| standing | standing
| bridge. | bridge.
Survivability | JHSV will be | JHSV will be | JHSV will be | In progress | JHSV will be
| built to | built to | built to |  | built to
| commercial | commercial | commercial |  | commercial
| ABS | ABS | ABS |  | ABS
| standards | standards | standards |  | standards
| and will not | and will not | and will not |  | and will not
| be shock | be shock | be shock |  | be shock
| hardened. | hardened. | hardened. |  | hardened.
Mission Deck Weight | Mission | Mission | Mission | In progress | Mission
Loading | deck | deck | deck |  | deck
| capable of | capable of | capable of |  | capable of
| supporting a | supporting a | supporting a |  | supporting a
| maximum | maximum | maximum |  | maximum
| vehicle | vehicle | vehicle |  | vehicle
| size/weight | size/weight | size/weight |  | size/weight
| to on/offload | to on/offload | to on/offload |  | to on/offload
| a combat | a combat | a combat |  | a combat
| ready M1A2 | ready M1A2 | ready M1A2 |  | ready M1A2
| main battle | main battle | main battle |  | main battle
| tank (total | tank (total | tank (total |  | tank (total
| weight); a | weight); a | weight); a |  | weight); a
| fully loaded | fully loaded | fully loaded |  | fully loaded
| HEMTT-PLS | HEMTT-PLS | HEMTT-PLS |  | Heavy
| with a 20 ft | with a 20 ft | with a 20 ft |  | Expanded
| ISO | ISO | ISO |  | Mobility
| container | container | container |  | Tactical
| loaded | loaded | loaded |  | Truck -
| (point | (point | (point |  | Palletized
| loading). | loading). | loading). |  | Load

## Table 16
System (HEMTT- PLS) with a 20 ft ISO container loaded (point loading).
Requirements Source: Capability Development Document (CDD) dated January 29, 2007
Acronyms And Abbreviations
ABS - American Bureau of Shipping ATO - Approval to Operate
DAA - Designated Approval Authority deg - Degrees
DISR - DOD Information Technology Standards and Profile Registry ft - Feet/Foot
GIG - Global Information Grid
HEMTT-PLS - Heavy Expanded Mobility Tactical Truck- Palletized Load System IA - Information Assurance
IATO - Interim Approval to Operate in - Inches
ISO - International Standard for Organizations IT - Information Technology
KIP - Key Interface Profile
KPP - Key Performance Parameter kts - Knots
lbs - Pounds
NCOW-RM - Net Centric Operations Warfare Reference Model NM - Nautical Mile
RRDF - Roll-on/Roll-off Discharge Facillities SST - Search, Sense and Tracking
ST - Short Tons
TV - Technical Standards View yd - Yards
Change Explanations
None

## Table 17
Track To Budget
RDT&E
APPN 1319 | BA 07 | PE 0208058N | (Navy)
| Project 3131 | Intratheater Connectors (Concept Studies) |  | (Sunk)
| Project 3134 | Intratheater Connectors (Contract Design)
APPN 1319 | BA 04 | PE 0603564N | (Navy)
| Project 3131 | Intratheater Connectors |  | (Sunk)
APPN 1319 | BA 05 | PE 0604567N | (Navy)
| Project 3134 | Intratheater Connectors |  | (Sunk)
APPN 2040 | BA 07 | PE 0208058A | (Army)
| Project JH1 | Joint High Speed Vessel (JHSV) |  | (Sunk)
Procurement
APPN 1611 | BA 03 | PE 0208058N | (Navy)
| ICN 3043 | JOINT HIGH SPEED VESSEL (JHSV)
APPN 1611 | BA 05 | PE 0208058N | (Navy)
| ICN 5110 | JOINT HIGH SPEED VESSEL (JHSV)
APPN 2035 | BA 03 | PE 0208058A | (Army)
| ICN M11203 | JOINT HIGH SPEED VESSEL (JHSV) |  | (Sunk)

## Table 18
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
|  | BY2008 $M | [6 empty] | BY2008 $M
Appropriation |  | SAR Baseline Dev Est |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Dev Est | Current APB Development Objective |  |  | Current Estimate
RDT&E |  | 122.2 |  |  |  | 122.2 |  | 134.4 |  | 115.6 |  | 124.8 | 124.8 | 116.6
Procurement |  | 3337.8 |  |  |  | 3337.8 |  | 3671.6 |  | 1836.3 |  | 3767.5 | 3767.5 | 2061.7
Flyaway |  | 3079.2 |  |  |  | -- |  | -- |  | 1719 |  | 3463 | -- | 1916.4
Recurring |  | 3079.2 |  |  |  | -- |  | -- |  | 1679.8 |  | 3463 | -- | 1876.3
Non Recurring |  | 0 |  |  |  | -- |  | -- |  | 39.2 |  | 0 | -- | 40.1
Support |  | 258.6 |  |  |  | -- |  | -- |  | 117.3 |  | 304.5 | -- | 145.3
Other Support |  | 143.5 |  |  |  | -- |  | -- |  | 80.4 |  | 170.1 | -- | 100.1
Initial Spares |  | 115.1 |  |  |  | -- |  | -- |  | 36.9 |  | 134.4 | -- | 45.2
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 3460 |  |  |  | 3460 |  | N/A |  | 1951.9 |  | 3892.3 | 3892.3 | 2178.3
The FY 2013 President's Budget requested a total of 10 ships within the Future Years Defense Program (FYDP), which is a reduction of eight ships from the 18 ships authorized at Milestone B.
Quantity |  |  | SAR Baseline Dev Est |  |  |  | Current APB Development |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  | 0
Procurement |  |  | 18 |  |  |  | 18 |  |  |  | 10
Total |  |  | 18 |  |  |  | 18 |  |  |  | 10

## Table 19
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2014 President's Budget / December 2012 SAR (TY$ M)
RDT&E | 113.7 |  |  | 1.9 |  |  | 1 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 116.6
Procurement | 1723.8 |  |  | 218.9 |  |  | 27 |  |  | 33.5 |  | 25.1 |  |  | 21.1 |  |  | 12.3 |  |  | 0 |  | 2061.7
MILCON | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
PB 2014 Total | 1837.5 |  |  | 220.8 |  |  | 28 |  |  | 33.5 |  | 25.1 |  |  | 21.1 |  |  | 12.3 |  |  | 0 |  | 2178.3
PB 2013 Total | 1835.3 |  |  | 221.6 |  |  | 35.9 |  |  | 34.2 |  | 14.4 |  |  | 9.1 |  |  | 32.9 |  |  | 0 |  | 2183.4
Delta | 2.2 |  |  | -0.8 |  |  | -7.9 |  |  | -0.7 |  | 10.7 |  |  | 12 |  |  | -20.6 |  |  | 0 |  | -5.1
Program funding and production quantities listed in this SAR are consistent with the FY 2014 President's Budget (PB). The FY 2014 PB did not reflect the enacted DoD appropriation for FY 2013, nor sequestration; it reflected the President's requested amounts for FY 2013.
Appropriation |  | Prior | FY2013 |  |  | FY2014 |  | FY2015 |  |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | To Complete |  | Total
Quantity | Undistributed |  |  |  | Prior |  | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  | To Complete |  |  | Total
Development | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
Production | 0 |  |  |  | 9 |  | 1 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 10
PB 2014 Total | 0 |  |  |  | 9 |  | 1 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 10
PB 2013 Total | 0 |  |  |  | 9 |  | 1 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 10
Delta | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0

## Table 20
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2006 | -- | -- | -- | -- | -- | -- | 6.5
2007 | -- | -- | -- | -- | -- | -- | 14.1
2008 | -- | -- | -- | -- | -- | -- | 18.4
2009 | -- | -- | -- | -- | -- | -- | 11.5
2010 | -- | -- | -- | -- | -- | -- | 8.2
2011 | -- | -- | -- | -- | -- | -- | 3.5
2012 | -- | -- | -- | -- | -- | -- | 4
2013 | -- | -- | -- | -- | -- | -- | 1.9
2014 | -- | -- | -- | -- | -- | -- | 1
Subtotal | -- | -- | -- | -- | -- | -- | 69.1

## Table 21
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2008 $M | Non End Item Recurring Flyaway BY 2008 $M | Non Recurring Flyaway BY 2008 $M | Total Flyaway BY 2008 $M | Total Support BY 2008 $M | Total Program BY 2008 $M
2006 | -- | -- | -- | -- | -- | -- | 6.7
2007 | -- | -- | -- | -- | -- | -- | 14.2
2008 | -- | -- | -- | -- | -- | -- | 18.2
2009 | -- | -- | -- | -- | -- | -- | 11.2
2010 | -- | -- | -- | -- | -- | -- | 7.9
2011 | -- | -- | -- | -- | -- | -- | 3.3
2012 | -- | -- | -- | -- | -- | -- | 3.7
2013 | -- | -- | -- | -- | -- | -- | 1.7
2014 | -- | -- | -- | -- | -- | -- | 0.9
Subtotal | -- | -- | -- | -- | -- | -- | 67.8

## Table 22
Annual Funding TY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2005 | -- | -- | -- | -- | -- | -- | 10
2006 | -- | -- | -- | -- | -- | -- | 3.1
2007 | -- | -- | -- | -- | -- | -- | 20.2
2008 | -- | -- | -- | -- | -- | -- | 5
2009 | -- | -- | -- | -- | -- | -- | 2.9
2010 | -- | -- | -- | -- | -- | -- | 3.1
2011 | -- | -- | -- | -- | -- | -- | 3.2
Subtotal | -- | -- | -- | -- | -- | -- | 47.5

## Table 23
Annual Funding BY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2008 $M | Non End Item Recurring Flyaway BY 2008 $M | Non Recurring Flyaway BY 2008 $M | Total Flyaway BY 2008 $M | Total Support BY 2008 $M | Total Program BY 2008 $M
2005 | -- | -- | -- | -- | -- | -- | 10.6
2006 | -- | -- | -- | -- | -- | -- | 3.2
2007 | -- | -- | -- | -- | -- | -- | 20.3
2008 | -- | -- | -- | -- | -- | -- | 4.9
2009 | -- | -- | -- | -- | -- | -- | 2.8
2010 | -- | -- | -- | -- | -- | -- | 3
2011 | -- | -- | -- | -- | -- | -- | 3
Subtotal | -- | -- | -- | -- | -- | -- | 47.8

## Table 24
Annual Funding TY$
1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2009 | 1 | 192.3 | -- | -- | 192.3 | -- | 192.3
2010 | 1 | 177.4 | -- | -- | 177.4 | -- | 177.4
2011 | 1 | 179.7 | -- | -- | 179.7 | 1.3 | 181
2012 | 2 | 372.3 | -- | -- | 372.3 | 0.2 | 372.5
2013 | 1 | 189.2 | -- | -- | 189.2 | 29.7 | 218.9
2014 | -- | 2.7 | -- | -- | 2.7 | 24.3 | 27
2015 | -- | 5.8 | -- | -- | 5.8 | 27.7 | 33.5
2016 | -- | 5.8 | -- | -- | 5.8 | 19.3 | 25.1
2017 | -- | 5.8 | -- | -- | 5.8 | 15.3 | 21.1
2018 | -- | 1.8 | -- | -- | 1.8 | 10.5 | 12.3
Subtotal | 6 | 1132.8 | -- | -- | 1132.8 | 128.3 | 1261.1

## Table 25
Annual Funding BY$
1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2008 $M | Non End Item Recurring Flyaway BY 2008 $M | Non Recurring Flyaway BY 2008 $M | Total Flyaway BY 2008 $M | Total Support BY 2008 $M | Total Program BY 2008 $M
2009 | 1 | 174.4 | -- | -- | 174.4 | -- | 174.4
2010 | 1 | 155.7 | -- | -- | 155.7 | -- | 155.7
2011 | 1 | 153 | -- | -- | 153 | 1.1 | 154.1
2012 | 2 | 310.7 | -- | -- | 310.7 | 0.2 | 310.9
2013 | 1 | 154.9 | -- | -- | 154.9 | 24.4 | 179.3
2014 | -- | 2.2 | -- | -- | 2.2 | 19.5 | 21.7
2015 | -- | 4.6 | -- | -- | 4.6 | 21.8 | 26.4
2016 | -- | 4.5 | -- | -- | 4.5 | 14.9 | 19.4
2017 | -- | 4.4 | -- | -- | 4.4 | 11.6 | 16
2018 | -- | 1.3 | -- | -- | 1.3 | 7.9 | 9.2
Subtotal | 6 | 965.7 | -- | -- | 965.7 | 101.4 | 1067.1

## Table 26
Cost Quantity Information
1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
End Item
Recurring
Flyaway
Fiscal Year | Quantity | (Aligned with
Quantity)
BY 2008
$M
2009 | 1 | 174.4
2010 | 1 | 155.7
2011 | 1 | 153
2012 | 2 | 310.7
2013 | 1 | 171.9
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
Subtotal | 6 | 965.7

## Table 27
Annual Funding TY$
2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2008 | 1 | 196.4 | -- | 30.1 | 226.5 | -- | 226.5
2009 | 1 | 168.3 | -- | -- | 168.3 | -- | 168.3
2010 | 1 | 193 | -- | 10 | 203 | -- | 203
2011 | 1 | 185.8 | -- | -- | 185.8 | 17 | 202.8
Subtotal | 4 | 743.5 | -- | 40.1 | 783.6 | 17 | 800.6

## Table 28
Annual Funding BY$
2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2008 $M | Non End Item Recurring Flyaway BY 2008 $M | Non Recurring Flyaway BY 2008 $M | Total Flyaway BY 2008 $M | Total Support BY 2008 $M | Total Program BY 2008 $M
2008 | 1 | 193.2 | -- | 29.6 | 222.8 | -- | 222.8
2009 | 1 | 163.4 | -- | -- | 163.4 | -- | 163.4
2010 | 1 | 183.9 | -- | 9.6 | 193.5 | -- | 193.5
2011 | 1 | 173.6 | -- | -- | 173.6 | 15.9 | 189.5
Subtotal | 4 | 714.1 | -- | 39.2 | 753.3 | 15.9 | 769.2

## Table 29
Low Rate Initial Production
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the JHSV program entering the Engineering and Manufacturing Development phase with approval for a Low Rate Initial Production (LRIP) quantity of 10 ships.
| Initial LRIP Decision | Current Total LRIP
Approval Date | 11/12/2008 11/12/2008 10 10 Milestone B ADM Milestone B ADM 2008 2008 2013 2013
Approved Quantity
Reference
Start Year
End Year

## Table 30
Foreign Military Sales
None
Nuclear Cost
None

## Table 31
Unit Cost
Unit Cost Report
|  | BY2008 $M | BY2008 $M
Unit Cost |  | Current UCR Baseline (FEB 2009 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 3460 |  |  | 1951.9
Quantity | 18 |  |  | 10
Unit Cost | 192.222 |  |  | 195.19 |  | 1.54
Average Procurement Unit Cost (APUC)
Cost | 3337.8 |  |  | 1836.3
Quantity | 18 |  |  | 10
Unit Cost | 185.433 |  |  | 183.63 |  | -0.97
|  | BY2008 $M | BY2008 $M
Unit Cost |  | Original UCR Baseline (FEB 2009 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 3460 |  |  | 1951.9
Quantity | 18 |  |  | 10
Unit Cost | 192.222 |  |  | 195.19 |  | 1.54
Average Procurement Unit Cost (APUC)
Cost | 3337.8 |  |  | 1836.3
Quantity | 18 |  |  | 10
Unit Cost | 185.433 |  |  | 183.63 |  | -0.97

## Table 32
Unit Cost History
[7 empty] | BY2008 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | FEB 2009 |  |  |  | 192.222 |  | 185.433 |  |  | 216.239 |  | 209.306
APB as of January 2006 |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current APB |  |  | FEB 2009 |  |  |  | 192.222 |  | 185.433 |  |  | 216.239 |  | 209.306
Prior Annual SAR |  |  | DEC 2011 |  |  |  | 197.99 |  | 186.1 |  |  | 218.34 |  | 206.33
Current Estimate |  |  | DEC 2012 |  |  |  | 195.19 |  | 183.63 |  |  | 217.83 |  | 206.17
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Dev Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
216.239 8.340 12.191 2.190 0.000 -4.340 0.000 -16.790 1.591 217.830

## Table 33
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes | [10 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth | Spt |  | Total
209.306 8.400 6.644 2.190 0.000 -3.580 0.000 -16.790 -3.136 206.170
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  |  | SAR Development Estimate (DE) |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone A |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  |  | OCT 2008 |  |  | N/A |  |  | OCT 2008
Milestone C |  |  | N/A |  |  |  | SEP 2012 |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  |  | OCT 2012 |  |  | N/A |  |  | NOV 2013
Total Cost (TY $M) |  |  | N/A |  |  |  | 3892.3 |  |  | N/A |  |  | 2178.3
Total Quantity |  |  | N/A |  |  |  | 18 |  |  | N/A |  |  | 10
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  |  | 216.239 |  |  | N/A |  |  | 217.83

## Table 34
Cost Variance
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 124.8 | 3767.5 | -- | 3892.3
Previous Changes
Economic | -0.7 | 54 | -- | 53.3
Quantity | -- | -1608 | -- | -1608
Schedule | -- | 21.9 | -- | 21.9
Engineering | -- | -- | -- | --
Estimating | -4 | -43.9 | -- | -47.9
Other | -- | -- | -- | --
Support | -- | -128.2 | -- | -128.2
Subtotal | -4.7 | -1704.2 | -- | -1708.9
Current Changes
Economic | 0.1 | 30 | -- | 30.1
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -3.6 | 8.1 | -- | 4.5
Other | -- | -- | -- | --
Support | -- | -39.7 | -- | -39.7
Subtotal | -3.5 | -1.6 | -- | -5.1
Total Changes | -8.2 | -1705.8 | -- | -1714
CE - Cost Variance | 116.6 | 2061.7 | -- | 2178.3
CE - Cost & Funding | 116.6 | 2061.7 | -- | 2178.3

## Table 35
Summary Base Year 2008 $M
| RDT&E |  | Proc | MILCON | Total
SAR Baseline (Dev Est) Previous Changes |  | 122.2 | 3337.8 | -- | 3460
Economic |  | -- | -- | -- | --
Quantity |  | -- | -1320 | -- | -1320
Schedule |  | -- | -10.9 | -- | -10.9
Engineering |  | -- | -- | -- | --
Estimating |  | -3.3 | -35.6 | -- | -38.9
Other |  | -- | -- | -- | --
Support |  | -- | -110.3 | -- | -110.3
Subtotal |  | -3.3 | -1476.8 | -- | -1480.1
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | -3.3 | 6.3 | -- | 3
Other |  | -- | -- | -- | --
Support |  | -- | -31 | -- | -31
Subtotal |  | -3.3 | -24.7 | -- | -28
Total Changes |  | -6.6 | -1501.5 | -- | -1508.1
CE - Cost Variance |  | 115.6 | 1836.3 | -- | 1951.9
CE - Cost & Funding |  | 115.6 | 1836.3 | -- | 1951.9
Previous Estimate: December 2011

## Table 36
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A +0.1
Decrease in estimate due to reduction in testing for the Army ships transferred to the Navy (Army). (Estimating)
Decrease in estimate due to reduction in testing and research and development to support Navy ships (Navy). (Estimating)
-2.9 -3.2
-0.3 -0.3
Adjustment for current and prior escalation. (Estimating) | -0.1 | -0.1
RDT&E Subtotal | -3.3 | -3.5
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 30
Adjustment for current and prior escalation. (Estimating) | -20.8 | -24.5
Increase in actual costs for overhead and labor rates and additional material costs. (Estimating)
Increase in estimate for engineering and program management support needed to complete the JHSV program when it was truncated from 18 to 10 ships. (Estimating)
+10.1 +11.0
+17.0 +21.6
Adjustment for current and prior escalation. (Support) -0.8 -1.2
Decrease in Other Support due to actual post delivery requirement being less than planned (Navy). (Support)
Decrease in Initial Spares due to actual spares requirement being less than planned (Navy). (Support)
-7.4 -9.7
-22.8 -28.8
Procurement Subtotal -24.7 -1.6

## Table 37
Contracts
General Contract Memo
There is one contract between the Navy and Austal USA for the detail design and construction of JHSVs. The contract was initially awarded for detailed design and construction of JHSV 1 with options for 9 additional ships. In addition to awarding the basic contract for JHSV 1, the Navy has exercised the options for JHSVs 2 to 10. These options are shown as separate contracts in this section.
Appropriation: Procurement
Contract Name Joint High Speed Vessel - JHSV 2
Contractor Austal USA
Contractor Location Mobile, AL 36610
Contract Number, Type N00024-08-C-2217/2, FPIF
Award Date June 17, 2009
Definitization Date June 17, 2009
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
152.9 176.1 1 152.9 175.7 1 166.0 168.2
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | -23.4 |  |  | -3.6
Previous Cumulative Variances |  |  |  | -6.7 |  |  | -15.9
Net Change |  |  |  | -16.7 |  |  | 12.3
Cost And Schedule Variance Explanations
The unfavorable net change in the cost variance is due to unplanned cost growth for production material and overhead and labor rates.
The favorable net change in the schedule variance is due to the close out of outstanding tasks as the ship approaches delivery.
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 38
Appropriation: Procurement
Contract Name Joint High Speed Vessel - JHSV 3
Contractor Austal USA
Contractor Location Mobile, AL 36610
Contract Number, Type N00024-08-C-2217/3, FPIF
Award Date June 17, 2009
Definitization Date June 17, 2009
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
150.9 173.3 1 150.4 172.7 1 159.6 163.1
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | -17.9 |  |  | -15.4
Previous Cumulative Variances |  |  |  | 1.6 |  |  | -5.8
Net Change |  |  |  | -19.5 |  |  | -9.6
Cost And Schedule Variance Explanations
The unfavorable net change in the cost variance is due to unplanned cost growth for production material and overhead and labor rates.
The unfavorable net change in the schedule variance is due to JHSV 2 shipyard schedule delay affecting JHSV 3.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the net impact of a reduction in scope for the Mission Bay Interface Panels and Mission Bay Tie Down Arrangements and an increase in scope for the Spare High Expansion Foam Concentrate Stowage.

## Table 39
Appropriation: Procurement
Contract Name Joint High Speed Vessel - JHSV 4
Contractor Austal USA
Contractor Location Mobile, AL 36610
Contract Number, Type N00024-08-C-2217/4, FPIF
Award Date October 12, 2010
Definitization Date October 12, 2010
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
151.7 174.2 1 151.1 173.5 1 154.6 161.3
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | -2.6 |  |  | -14
Previous Cumulative Variances |  |  |  | -21.2 |  |  | 0
Net Change |  |  |  | 18.6 |  |  | -14
Cost And Schedule Variance Explanations
The favorable net change in the cost variance is due to the prior JHSV SAR reporting only actual costs with no performance measurement baseline for JHSV 4.
The unfavorable net change in the schedule variance is due to the effect of schedule delays from prior ship delays.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a reduction in scope for the Mission Bay Interface Panels and Mission Bay Tie Down Arrangements.

## Table 40
Appropriation: Procurement
Contract Name Joint High Speed Vessel - JHSV 5
Contractor Austal USA
Contractor Location Mobile, AL 36610
Contract Number, Type N00024-08-C-2217/5, FPIF
Award Date October 12, 2010
Definitization Date October 12, 2010
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
152.5 175.0 1 151.8 174.3 1 151.8 159.6
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | -45.2 |  |  | 0
Previous Cumulative Variances |  |  |  | -12.7 |  |  | 0
Net Change |  |  |  | -32.5 |  |  | 0
Cost And Schedule Variance Explanations
The unfavorable net change in the cost variance is due to Austal reporting only actual costs for JHSV 5.
General Contract Variance Explanation
Schedule variance reporting has not commenced because Earned Value Management (EVM) reporting against a performance measurement baseline has not yet started for JHSV 5.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a reduction in scope for the Mission Bay Interface Panels and Mission Bay Tie Down Arrangements.

## Table 41
Appropriation: Procurement
Contract Name Joint High Speed Vessel - JHSV 6
Contractor Austal USA
Contractor Location Mobile, AL 36610
Contract Number, Type N00024-08-C-2217/6, FPIF
Award Date June 30, 2011
Definitization Date June 30, 2011
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
155.5 178.5 1 154.9 177.9 1 154.9 160.3
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | -26 |  |  | 0
Previous Cumulative Variances |  |  |  | 0 |  |  | 0
Net Change |  |  |  | -26 |  |  | 0
Cost And Schedule Variance Explanations
The unfavorable net change in the cost variance is due to Austal reporting only actual costs for JHSV 6.
General Contract Variance Explanation
Schedule variance reporting has not commenced because Earned Value Management (EVM) reporting against a performance measurement baseline has not yet started for JHSV 6.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a reduction in scope for the Mission Bay Interface Panels and Mission Bay Tie Down Arrangements.

## Table 42
Appropriation: Procurement
Contract Name Joint High Speed Vessel - JHSV 7
Contractor Austal USA
Contractor Location Mobile, AL 36610
Contract Number, Type N00024-08-C-2217/7, FPIF
Award Date June 30, 2011
Definitization Date June 30, 2011
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
157.4 180.7 1 156.8 180.0 1 156.8 160.4
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | -16.1 |  |  | 0
Previous Cumulative Variances |  |  |  | 0 |  |  | 0
Net Change |  |  |  | -16.1 |  |  | 0
Cost And Schedule Variance Explanations
The unfavorable net change in the cost variance is due to Austal reporting only actual costs for JHSV 7.
General Contract Variance Explanation
Schedule variance reporting has not commenced because Earned Value Management (EVM) reporting against a performance measurement baseline has not yet started for JHSV 7.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a reduction in scope for the Mission Bay Interface Panels and Mission Bay Tie Down Arrangements.

## Table 43
Appropriation: Procurement
Contract Name Joint High Speed Vessel - JHSV 8
Contractor Austal USA
Contractor Location Mobile, AL 36610
Contract Number, Type N00024-08-C-2217/8, FPIF
Award Date February 24, 2012
Definitization Date February 24, 2012
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
160.5 184.2 1 159.8 183.4 1 159.8 161.8
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | -12.7 |  |  | 0
Previous Cumulative Variances |  |  |  | -- |  |  | --
Net Change |  |  |  | -12.7 |  |  | 0
Cost And Schedule Variance Explanations
The unfavorable cumulative cost variance is due to Austal reporting only actual costs for JHSV 8.
General Contract Variance Explanation
Schedule variance reporting has not commenced because Earned Value Management (EVM) reporting against a performance measurement baseline has not yet started for JHSV 8.
Contract Comments
This is the first time this contract is being reported.
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a reduction in scope for the Mission Bay Interface Panels and Mission Bay Tie Down Arrangements.

## Table 44
Appropriation: Procurement
Contract Name Joint High Speed Vessel - JHSV 9
Contractor Austal USA
Contractor Location Mobile, AL 36610
Contract Number, Type N00024-08-C-2217/9, FPIF
Award Date February 24, 2012
Definitization Date February 24, 2012
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
162.6 186.6 1 161.9 185.9 1 161.9 162.7
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (3/31/2013) |  |  |  | -12.7 |  |  | 0
Previous Cumulative Variances |  |  |  | -- |  |  | --
Net Change |  |  |  | -12.7 |  |  | 0
Cost And Schedule Variance Explanations
The unfavorable cumulative cost variance is due to Austal reporting only actual costs for JHSV 9.
General Contract Variance Explanation
Schedule variance reporting has not commenced because Earned Value Management (EVM) reporting against a performance measurement baseline has not yet started for JHSV 9.
Contract Comments
This is the first time this contract is being reported.
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a reduction in scope for the Mission Bay Interface Panels and Mission Bay Tie Down Arrangements.

## Table 45
Appropriation: Procurement
Contract Name Joint High Speed Vessel - JHSV 10
Contractor Austal USA
Contractor Location Mobile, AL 36610
Contract Number, Type N00024-08-C-2217/10, FPIF
Award Date December 20, 2012
Definitization Date December 20, 2012
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
167.6 192.3 1 166.9 191.6 1 166.9 167.3
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date |  |  |  | 0 |  |  | 0
Previous Cumulative Variances |  |  |  | -- |  |  | --
Net Change |  |  |  | 0 |  |  | 0
Cost And Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variance reporting has not commenced because the option for JHSV 10 was awarded on December 20, 2012, and Earned Value Management (EVM) reporting against a performance measurement baseline has not yet started.
Contract Comments
This is the first time this contract is being reported.
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a reduction in scope for the Mission Bay Interface Panels and Mission Bay Tie Down Arrangements.

## Table 46
Deliveries and Expenditures
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 0 | --
Production | 1 |  | 1 |  | 10 | 10%
Total Program Quantities Delivered | 1 |  | 1 |  | 10 | 10%
Expenditures and |  | Appropriations (TY $M)
Total Acquisition Cost | 2178.3 | Years Appropriated |  |  | 9
Expenditures To Date | 867.1 | Percent Years Appropriated |  |  | 64.29%
Percent Expended | 39.81% | Appropriated to Date |  |  | 2058.3
Total Funding Years | 14 | Percent Appropriated |  |  | 94.49%
The above data is current as of 3/20/2013.

## Table 47
Operating and Support Cost
JHSV
Assumptions and Ground Rules
Cost Estimate Reference:
These Operating and Support (O&S) costs are based on the Naval Sea Systems Command (NAVSEA)
05C August 2012 Gate 6 update of the JHSV O&S Program Life Cycle Estimate (PLCCE) of October 1, 2008, and reflect the reduction in authorized JHSVs from 18 to 10 and transfer of the 5 Army ships to the Navy.
Estimates were calculated and analyzed using the Operating and Support Cost Analysis Model (OSCAM) Naval Suite, sponsored by the Naval Center for Cost Analysis (NCCA). Data was obtained from a variety of sources, including Military Sealift Command (MSC) guidance, JHSV technical specifications, and the Visibility and Management of Operating and Support Costs (VAMOSC) historical database, also sponsored by NCCA.
Below are a number of critical assumptions, based on the current program of record:
● 10 ships total (all Navy with MSC crew)
● Primary construction material/hull form: Aluminum/Catamaran
● Design standard: American Bureau of Shipping, High Speed Naval Craft (HSNC)
● Estimated service life: 20 years
● Nominal operational tempo (annually): 3,000 hours steaming underway; 3,000 hours steaming not underway
● Marine Diesel Fuel Cost (per barrel): $132
● Maintenance Concept: Two-level (Organizational and Depot-level)
Sustainment Strategy:
● MSC designated Life Cycle Manager
● Streamlined to standard MSC maintenance philosophy
● Two-level maintenance approach
Antecedent Information:
There is no antecedent system to the JHSV. The program represents a new materiel solution for DoD in intra- theater sealift, leveraging international commercial best practices in high speed ferry technology.

## Table 48
Unitized O&S Costs BY2008 $M
Cost Element |  | JHSV Average Annual Cost Per Hull |  |  | No Antecedent System (Antecedent)
Unit-Level Manpower |  |  | 4.7 |  | 0
Unit Operations |  |  | 14.6 |  | 0
Maintenance |  |  | 4.5 |  | 0
Sustaining Support |  |  | 0.4 |  | 0
Continuing System Improvements |  |  | 0.3 |  | 0
Indirect Support |  |  | 5.4 |  | 0
Other |  |  | 0 |  | 0
Total |  |  | 29.9 |  | --
Unitized Cost Comments: Unit of measure is Average Annual Cost Per Hull.
Total O&S Cost $M
| Current Development APB Objective/Threshold |  |  | Current Estimate
| JHSV |  |  | JHSV |  | No Antecedent System (Antecedent)
Base Year | 9621.9 10584.1 5981.2 N/A
Then Year | 11343.7 N/A 7273.4 0.0
Total O&S Costs Comments:
None
Disposal Costs
The sale of recyclable material is estimated to cover the disposal of the vessel; therefore, the net total cost of JHSV disposal is $0. Estimate based on correspondence from the Chief Operating Office at International Shipbreaking Limited LLC (2008).