## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-293
MP-RTIP
As of December 31, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 5
Threshold Breaches |  | 6
Schedule |  | 7
Performance |  | 8
Track To Budget |  | 9
Cost and Funding |  | 10
Low Rate Initial Production |  | 13
Nuclear Cost |  | 13
Foreign Military Sales |  | 13
Unit Cost |  | 14
Cost Variance |  | 17
Contracts |  | 20
Deliveries and Expenditures |  | 21
Operating and Support Cost |  | 22

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
Multi-Platform Radar Technology Insertion Program (MP-RTIP)
DoD Component
Air Force
Responsible Office
Responsible Office
Col David Hiltz
System Program Manager, Mulit-Platform Radar Technology Insertion Program
AFMC ESC/HBG
75 Vandenberg Rd, Bldg 1630 Hanscom AFB, MA 01731-2103
Phone Fax
DSN Phone DSN Fax
781-225-5174
--
845-5174
--
david.hiltz@hanscom.af.mil Date Assigned July 12, 2010
Lt. Col Michael Harm
Program Manager, Multi-Platform Technology Insertion Program AFMC ESC/HBG
75 Vandenberg Rd, Bldg 1630 Hanscom, AFB MA 01731 Phone: (781) 225-5275
DSN: 845-5275
michael.harm@hanscom.af.mil
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 4, 2003
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 1, 2005

## Table 4
Mission and Description
The Multi-Platform Radar Technology Insertion Program (MP-RTIP) is the result of a restructuring of the Joint Surveillance Target Attack Radar System (Joint STARS) Radar Technology Insertion Program, formerly a Pre- Planned Product Improvement to Joint STARS. MP-RTIP is developing modular, scalable, surveillance and reconnaissance radar(s) to be installed on the RQ-4B Block 40 Global Hawk Unmanned Aerial Vehicle (UAV). Under current OUSD/AT&L direction, the E-10A Technology Development Program and the associated MP-RTIP Wide Area Surveillance development were terminated, receiving zero funds in FY 2008 and beyond. The MP-RTIP Selected Acquisition Report includes only Research, Development, Test and Evaluation funding since radars will be procured and budgeted by the host platforms. At this time, the North Atlantic Treaty Organization (NATO) has chosen the Global Hawk Block 40 UAV platform for the NATO Alliance Ground Surveillance program.
MP-RTIP will be accomplished in two phases: (Phase I) Pre-System Development and Demonstration (SDD) for Global Hawk radar design, (Phase II) SDD for radar development, fabrication, test and integration.
When installed on the Global Hawk Block 40 UAV, MP-RTIP will provide improved Ground Moving Target Indicator and Synthetic Aperture Radar imaging over current capability on a long endurance platform.

## Table 5
Executive Summary
This is the final SAR submission for the Multi-Platform Radar Technology Insertion Program (MP-RTIP), because the program is 90% or more expended.
The FY 2008 President's Budget (PB) eliminated funding for the E-10A version of the MP-RTIP Wide Area Surveillance radar in FY 2008 and beyond. Global Hawk MP-RTIP execution continued and the FY 2009 through FY 2012 PBs included funding to continue developmental and operational testing of the Global Hawk MP-RTIP variant on the Global Hawk Block 40 air vehicle platform. The Global Hawk program office is responsible for all MP-RTIP production, platform integration, developmental test and fielding.
Several Global Hawk program dates, including Initial Operation Test & Evaluation (IOT&E), have independently slipped, causing sensor and platform budgets and schedules to extend to FY 2014. The contractor proposed cost to support this extended integration ground and flight testing through FY 2014 was $84.1M. Subsequently, the MP-RTIP program office issued a revised Statement of Work and schedule to contain costs within currently available budget. From the contractor’s most recent schedule extension proposal received August 26, 2011, this will require $48.1M in FY 2012 and FY 2013. The MP-RTIP program office awarded the contract extension on March 8, 2012. The MP- RTIP and Global Hawk program offices continue to pursue options to accelerate IOT&E to provide capability to the Warfighter sooner and significantly reduce the overall program cost.
The final Concurrent Mode Contractor Development Test & Evaluation and Dedicated Mode regression test flight was flown on the surrogate test vehicle, Proteus, on November 18, 2010, the culmination of over 270 test flights. Production Unit (PU)-1 was removed from Proteus on November 19, 2010 and returned to the Global Hawk program for Block 40 integration and testing efforts. The MP-RTIP hardware baseline is stable with platform integration and subsequent Global Hawk Block 40 system test and evaluation beginning in December 2010. Certain advanced modes, such as Air Moving Target Indicator and High Range Resolution continue to be deferred.
In July 2010, the Command and Control/Combat Support Program Executive Officer commissioned an Independent Review Team (IRT) to assess MP-RTIP sensor testing to date, the readiness of the sensor for Global Hawk integration testing, and the state of program management cost accounting and external communications. The IRT found there were no significant testing issues and the sensor was deemed ready for integration; however, they did find an issue with the prime contractor's management cost accounting system. The IRT in conjunction with the Earned Value Management (EVM) Center of Excellence, identified several areas of concern with Northrop Grumman’s
(NG) EVM data for the MP-RTIP program. Defense Contract Management Agency (DCMA) issued a Level-3 Corrective Action Request (CAR) to NG on November 24, 2010. The prime contractor submitted their Corrective Action Plan (CAP) to DCMA which was approved on March 31, 2011. Monitoring for compliance to the CAP is an ongoing activity. The prime contractor has made sufficient progress, however several deficiencies still remain open pending further action by NG. Final closure for the CAR is dependent on EVM Operation Directorate concurrence.
Significant Accomplishments:
On July 21, 2011 at Edwards Air Force Base, Global Hawk Block 40 test aircraft #2025 conducted the first successful flight tests with an AN-ZPY2 (MP-RTIP) sensor on-board representing the first time the sensor was in flight on a Global Hawk Block 40 platform.
Preliminary integration testing continued through the end of the year. Radar System Level Performance Verification remains on track to begin in March 2012.
There are no significant software-related issues with this program at this time.

## Table 6
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Explanation of Breach
Breach was previously reported in the December 2010 SAR.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 7
Schedule
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
MP-RTIP MS B | APR 2003 | APR 2003 | OCT 2003 | OCT 2003
MP RTIP Final Design Review | JUN 2004 | JUN 2004 | DEC 2004 | JUN 2004
MP-RTIP Global Hawk Surrogate Testbed Integration and First Flight | DEC 2006 | DEC 2006 | JUN 2007 | SEP 2006
MP-RTIP E-10A 1st Radar DU Build/SIL Test | MAY 2008 | APR 2009 | OCT 2009 | N/A 1
MP-RTIP E-10A Testbed Integration and First Flight | OCT 2009 | MAY 2010 | NOV 2010 | N/A 1
1APB Breach
Acronyms And Abbreviations
DU - Development Unit
MP-RTIP - Multi-Platform Radar Technology Insertion Program MS - Milestone
SIL - System Integration Lab
Change Explanations
None
Memo
There are no MP-RTIP sensor Acquisition Program Baseline (APB) milestones associated with the Global Hawk Block 40.
Under Secretary of Defense for Acquistion, Technology, & Logistics Acquisition Decision Memorandum of May 30, 2007 terminated the E-10A Technology Development Program. However, it directed the Air Force to continue a limited risk reduction effort in Wide Area Surveillance radar development through May 2008. Because of the termination direction, the final two E-10A APB Milestones are no longer valid.

## Table 8
Performance
Memo
The MP-RTIP program is a System Development & Demonstration program. System Key Performance Parameters are documented with the Global Hawk Block 40 host weapon system.

## Table 9
Track To Budget
RDT&E
APPN 3600 | BA 07 | PE 0207449F | (Air Force)
| Project 675065 | C2 Constellation (Sensors) |  | (Sunk)
APPN 3600 | BA 05 | PE 0207450F | (Air Force)
| Project 655132 | E-10 Squadrons (Sensors) |  | (Sunk)
APPN 3600 | BA 07 | PE 0207581F | (Air Force)
| Project 670003 Project 674995 | JSTARS (JSTARS) JSTARS (MP-RTIP) | (Shared) | (Sunk) (Sunk)
APPN 3600 | BA 07 | PE 0305220F | (Air Force)
| Project 675144 Project 67RTIP | RQ-4 UAV (Global Hawk) RQ-4 UAV (MP-RTIP) | (Shared) | (Sunk)
E-10 Airframe utilized one Program Element (PE) 0207450F with two Budget Program Activity Code (BPAC). 655131 (Airframe) and 655132 (E-10 Squadrons Sensor). Upon termination of E-10A, PE 0305220F/BPAC 675144 (RQ-4 UAV Global Hawk) funds were used in FY 2009 for remaining existing MP-RTIP requirements. Subsequently, a new BPAC, 67RTIP, was created within PE 0305220F for FY 2010 and beyond.

## Table 10
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
| BY2000 $M |  |  |  |  | BY2000 $M |  | TY $M
Appropriation | SAR Baseline Dev Est |  | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 1449.3 |  | 1449.3 |  | 1594.2 | 1158.9 |  | 1568.4 | 1568.4 | 1303.8
Procurement | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Flyaway | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Recurring | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Non Recurring | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Support | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Other Support | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Initial Spares | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
MILCON | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Acq O&M | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Total | 1449.3 |  | 1449.3 |  | N/A | 1158.9 |  | 1568.4 | 1568.4 | 1303.8
Quantity |  | SAR Baseline Dev Est |  | Current APB Development |  |  | Current Estimate
RDT&E |  | 0 |  | 0 |  |  | 0
Procurement |  | 0 |  | 0 |  |  | 0
Total |  | 0 |  | 0 |  |  | 0

## Table 11
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2013 President's Budget / December 2011 SAR (TY$ M)
Appropriation | Prior | FY2012 |  | FY2013 |  | FY2014 | FY2015 |  | FY2016 |  | FY2 | 17 | To Complete |  | T | otal
RDT&E | 1197.7 | 40.3 |  | 17.7 |  | 11.6 | 11.9 |  | 12.2 |  | 12.4 |  | 0 |  | 1303.8
Procurement | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2013 Total | 1197.7 | 40.3 |  | 17.7 |  | 11.6 | 11.9 |  | 12.2 |  | 12.4 |  | 0 |  | 1303.8
PB 2012 Total | 1197.5 | 40.3 |  | 17.7 |  | 11.6 | 11.9 |  | 12 |  | 0 |  | 0 |  | 1291
Delta | 0.2 | 0 |  | 0 |  | 0 | 0 |  | 0.2 |  | 12.4 |  | 0 |  | 12.8
Quantity | ndistributed |  | Prior |  | FY2012 | FY2013 | FY2014 | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
PB 2013 Total | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
PB 2012 Total | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
U

## Table 12
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2000 | -- | -- | -- | -- | -- | -- | 6.9
2001 | -- | -- | -- | -- | -- | -- | 41.8
2002 | -- | -- | -- | -- | -- | -- | 73.3
2003 | -- | -- | -- | -- | -- | -- | 200.6
2004 | -- | -- | -- | -- | -- | -- | 145.6
2005 | -- | -- | -- | -- | -- | -- | 192.3
2006 | -- | -- | -- | -- | -- | -- | 131.5
2007 | -- | -- | -- | -- | -- | -- | 198.1
2008 | -- | -- | -- | -- | -- | -- | 67.3
2009 | -- | -- | -- | -- | -- | -- | 40.2
2010 | -- | -- | -- | -- | -- | -- | 72.2
2011 | -- | -- | -- | -- | -- | -- | 27.9
2012 | -- | -- | -- | -- | -- | -- | 40.3
2013 | -- | -- | -- | -- | -- | -- | 17.7
2014 | -- | -- | -- | -- | -- | -- | 11.6
2015 | -- | -- | -- | -- | -- | -- | 11.9
2016 | -- | -- | -- | -- | -- | -- | 12.2
2017 | -- | -- | -- | -- | -- | -- | 12.4
Subtotal | -- | -- | -- | -- | -- | -- | 1303.8

## Table 13
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
2000 | -- | -- | -- | -- | -- | -- | 6.8
2001 | -- | -- | -- | -- | -- | -- | 40.9
2002 | -- | -- | -- | -- | -- | -- | 70.9
2003 | -- | -- | -- | -- | -- | -- | 191.4
2004 | -- | -- | -- | -- | -- | -- | 135.5
2005 | -- | -- | -- | -- | -- | -- | 174.5
2006 | -- | -- | -- | -- | -- | -- | 115.9
2007 | -- | -- | -- | -- | -- | -- | 170.1
2008 | -- | -- | -- | -- | -- | -- | 56.6
2009 | -- | -- | -- | -- | -- | -- | 33.4
2010 | -- | -- | -- | -- | -- | -- | 59.2
2011 | -- | -- | -- | -- | -- | -- | 22.4
2012 | -- | -- | -- | -- | -- | -- | 31.8
2013 | -- | -- | -- | -- | -- | -- | 13.7
2014 | -- | -- | -- | -- | -- | -- | 8.9
2015 | -- | -- | -- | -- | -- | -- | 8.9
2016 | -- | -- | -- | -- | -- | -- | 9
2017 | -- | -- | -- | -- | -- | -- | 9
Subtotal | -- | -- | -- | -- | -- | -- | 1158.9
Low Rate Initial Production
There is no LRIP for this program.
Foreign Military Sales
None
Nuclear Cost
None

## Table 14
Unit Cost
Unit Cost Report
|  | BY2000 $M | BY2000 $M
Unit Cost |  | Current UCR Baseline (MAR 2005 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1449.3 |  |  | 1158.9
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  | --
Average Procurement Unit Cost (APUC)
Cost | -- |  |  | 0
Quantity | -- |  |  | 0
Unit Cost | -- |  |  | -- |  | --
|  | BY2000 $M | BY2000 $M
Unit Cost |  | Original UCR Baseline (DEC 2003 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1449.3 |  |  | 1158.9
Quantity Unit Cost | 0 -- |  |  | 0 -- |  | --
Average Procurement Unit Cost (APUC)
Cost | -- |  |  | 0
Quantity Unit Cost | -- -- |  |  | 0 -- |  | --

## Table 15
Unit Cost History
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
[7 empty] | BY2000 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | DEC 2003 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
APB as of January 2006 |  |  | MAR 2005 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | DEC 2003 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current APB |  |  | MAR 2005 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior Annual SAR |  |  | DEC 2010 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current Estimate |  |  | DEC 2011 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Initial PAUC Dev Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes | [11 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000

## Table 16
SAR Baseline History
Item/Event | SAR Planning Estimate (PE) | SAR Development Estimate (DE) | SAR Production Estimate (PdE) | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | APR 2003 | N/A | OCT 2003
Milestone C | N/A | N/A | N/A | N/A
IOC | N/A | N/A | N/A | N/A
Total Cost (TY $M) | N/A | 1568.4 | N/A | 1303.8
Total Quantity | N/A | 0 | N/A | 0
Prog. Acq. Unit Cost (PAUC) | N/A | N/A | N/A | N/A

## Table 17
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 1568.4 | -- | -- | 1568.4
Previous Changes
Economic | 43.1 | -- | -- | 43.1
Quantity | -- | -- | -- | --
Schedule | 222.1 | -- | -- | 222.1
Engineering | -351 | -- | -- | -351
Estimating | -191.6 | -- | -- | -191.6
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -277.4 | -- | -- | -277.4
Current Changes
Economic | 1.9 | -- | -- | 1.9
Quantity | -- | -- | -- | --
Schedule | 12.6 | -- | -- | 12.6
Engineering | -- | -- | -- | --
Estimating | -1.7 | -- | -- | -1.7
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 12.8 | -- | -- | 12.8
Total Changes | -264.6 | -- | -- | -264.6
CE - Cost Variance | 1303.8 | -- | -- | 1303.8
CE - Cost & Funding | 1303.8 | -- | -- | 1303.8

## Table 18
Summary Base Year 2000 $M
| RDT&E |  | Proc | MILCON | Total
SAR Baseline (Dev Est) Previous Changes |  | 1449.3 | -- | -- | 1449.3
Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | 165.7 | -- | -- | 165.7
Engineering |  | -289.7 | -- | -- | -289.7
Estimating |  | -174 | -- | -- | -174
Other |  | -- | -- | -- | --
Support |  | -- | -- | -- | --
Subtotal |  | -298 | -- | -- | -298
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | 9.1 | -- | -- | 9.1
Engineering |  | -- | -- | -- | --
Estimating |  | -1.5 | -- | -- | -1.5
Other |  | -- | -- | -- | --
Support |  | -- | -- | -- | --
Subtotal |  | 7.6 | -- | -- | 7.6
Total Changes |  | -290.4 | -- | -- | -290.4
CE - Cost Variance |  | 1158.9 | -- | -- | 1158.9
CE - Cost & Funding |  | 1158.9 | -- | -- | 1158.9
Previous Estimate: December 2010

## Table 19
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 1.9
Funding was added for FY 2013 President's Budget. (Schedule) | 9.1 | 12.6
Revised estimate to reflect actuals. (Estimating) | -0.5 | -0.5
Adjustment for current and prior escalation. (Estimating) | -1 | -1.2
RDT&E Subtotal | 7.6 | 12.8

## Table 20
Contracts
Appropriation: RDT&E
Contract Name MP-RTIP - SDD Phase II
Contractor Northrop Grumman
Contractor Location El Segundo, CA 90245
Contract Number, Type F19628-00-C-0100/2, CPAF/CPFF
Award Date April 30, 2004
Definitization Date April 30, 2004
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
887.9 N/A 0 917.9 N/A 0 1012.0 1003.0
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (12/30/2011) |  |  |  | -1 |  |  | -0.8
Previous Cumulative Variances |  |  |  | 1.8 |  |  | -2
Net Change |  |  |  | -2.8 |  |  | 1.2
Cost And Schedule Variance Explanations
The unfavorable net change in the cost variance is due to contractor inefficiencies during qualification testing and integration activities. This variance is against an Over Target Baseline (OTB) of $62.8M. The OTB is due to Contractor Developmental Test and Evaluation (CDT&E) delays.
The favorable net change in the schedule variance is due to progress for sensor to platform integration activities.
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.
The difference between the initial contract price target and the current contract price target is due to several Engineering Change Proposals and Contract Change Proposals.

## Table 21
Deliveries and Expenditures
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 0 | --
Production | 0 |  | 0 |  | 0 | --
Total Program Quantities Delivered | 0 |  | 0 |  | 0 | --
Expenditures and |  | Appropriations (TY $M)
Total Acquisition Cost | 1303.8 | Years Appropriated |  |  | 13
Expenditures To Date | 1183.5 | Percent Years Appropriated |  |  | 72.22%
Percent Expended | 90.77% | Appropriated to Date |  |  | 1238
Total Funding Years | 18 | Percent Appropriated |  |  | 94.95%

## Table 22
Operating and Support Cost
Assumptions And Ground Rules
The Multi-Platform Radar Technology Insertion Program (MP-RTIP) effort includes the Research, Development, Test and Evaluation of radars for the Global Hawk (Block 40). This is in accordance with the MP-RTIP Single Acquisition Management Plan, Milestone B, and revised Acquisition Program Baseline. The cost for MP-RTIP Production and Operations and Support is allocated in the respective host weapon system.
Costs BY2000 $M
Cost Element | MP-RTIP | Antecedent System
Unit-Level Manpower | -- | --
Unit Operations | -- | --
Maintenance | -- | --
Sustaining Support | -- | --
Continuing System Improvements | -- | --
Indirect Support | -- | --
Other | -- | --
Total Unitized Cost (Base Year 2000 $) | -- | --
Total O&S Costs $M | MP-RTIP | Antecedent System
Base Year | -- | --
Then Year | -- | --