## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-592
T-AKE
As of September 30, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 4
Threshold Breaches |  | 5
Schedule |  | 6
Performance |  | 7
Track To Budget |  | 10
Cost and Funding |  | 11
Low Rate Initial Production |  | 17
Nuclear Cost |  | 17
Foreign Military Sales |  | 17
Unit Cost |  | 18
Cost Variance |  | 21
Contracts |  | 24
Deliveries and Expenditures |  | 25
Operating and Support Cost |  | 26

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
T-AKE LEWIS and CLARK Class Dry Cargo/Ammunition Ship
DoD Component
Navy
Responsible Office
Responsible Office
Mr. Frank McCarthey
Program Executive Office, Ships 1333 Isaac Hull Ave S.E.
Washington Navy Yard, DC 20376-2501
Phone Fax
DSN Phone DSN Fax
202-781-0740
202-781-4732
326-0740
--
frank.mccarthey@navy.mil Date Assigned February 23, 2009
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 20, 2001
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated September 12, 2009

## Table 4
Mission and Description
The LEWIS and CLARK Class Dry Cargo/Ammunition Ship (T-AKE) acquisition program will provide a two product (ammunition and combat stores - including dry stores, frozen and chilled products, spare parts and consumables) replacement for the aging single product combat stores (T-AFS) and ammunition (T-AE) shuttle ships. Working in concert with an oiler (T-AO), the team can perform a "substitute" station ship mission that will allow the retirement of the three product fast combat support ships (AOE 1 Class). In its shuttle role, T-AKE will provide logistics lift to station ships and other ships operating with naval sources from supply sources, such as friendly ports, and at sea from Modular Cargo Delivery System (MCDS) equipped merchant vessels.
The T-AKE will have the capability to effectively and efficiently provide naval forces with ordnance, stores, and spare parts through both connected replenishment (CONREP) and vertical replenishment (VERTREP). Organic helicopter operations to conduct VERTREP require T-AKE to support two military cargo logistics helicopters or two equivalent commercial variants and associated aviation personnel. Additionally, T-AKE will have the capability to transfer a limited quantity of fuel by means of CONREP or Astern Refueling.
The T-AKE end force structure will be such that it meets fleet peacetime requirements and satisfies the majority of wartime requirements. Wartime operations will require augmentation by additional shuttle ships (such as MCDS equipped ships currently in the Ready Reserve Force).
Executive Summary
This quarterly exception SAR is being submitted to provide notification that the LEWIS and CLARK Class Dry Cargo/Ammunition Ship (T-AKE) program has reached 90% expended. In accordance with Title 10 Section 2432 this will be the final SAR for this program.
On May 13, 2011, T-AKE 10 through T-AKE 14 were converted from Fixed-Price Incentive Fee (FPIF) to Firm Fixed Price (FFP). On July 7, 2011, the T-AKE program received the 2011 Secretary of the Navy Safety Excellence award for safety integration in acquisition.
T-AKE 12: Delivered September 28, 2011.
T-AKE 13: Delivery is expected to occur April 12, 2012. Ship is 83% complete.
T-AKE 14: Delivery is expected to occur October 10, 2012. Ship is 51% complete.
There are no software-related issues for this program at this time.

## Table 5
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 6
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Contract Award | SEP 2001 | SEP 2001 | MAR 2002 | OCT 2001
Initial Critical Design Review & OIPT | MAR 2002 | MAR 2002 | SEP 2002 | MAY 2002
OT II-A Start | APR 2002 | APR 2002 | OCT 2002 | AUG 2002
OT II-A Complete | MAR 2003 | MAR 2003 | SEP 2003 | JAN 2003
Final Critical Design Review & OIPT | MAR 2003 | MAR 2003 | SEP 2003 | APR 2003
OT II-B Start | APR 2003 | APR 2004 | OCT 2004 | JUN 2004
Lead Ship Delivery | JUL 2005 | MAY 2006 | OCT 2006 | JUN 2006
OT II-B Complete | JUL 2005 | DEC 2004 | JUN 2005 | MAR 2005
OPEVAL Start | APR 2006 | NOV 2006 | MAY 2007 | NOV 2006
OPEVAL Complete | JUN 2006 | JAN 2007 | JUL 2007 | FEB 2007
IOC | OCT 2006 | APR 2007 | OCT 2007 | MAY 2007
Acronyms And Abbreviations
IOC - Initial Operational Capability
OIPT - Overarching Integrated Product Team OPEVAL - Operational Evaluation
OT - Operational Test
Change Explanations
None

## Table 7
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Intership Cargo Handling Interoperability | Provide all REP sys and equip. req'd for seamless interface w/existing and planned US ships | Provide all REP sys and equip. req'd for seamless interface w/existing and planned US ships | Provide all REP sys and equip. req'd for seamless interface w/existing and planned US ships | Provides all REP sys and equip. req'd for seamless interface w/existing and planned US ships | Provides all REP sys and equip. req'd for seamless interface w/existing and planned US ships
C4I Interoperability | 100% Top Level and Navy IERs | 100% Top Level and Navy IERs | 100% Top Level and Navy IERs designated as CRITICAL | 100% Top Level and Navy IERs | 100% Top Level and Navy IERs
Survivability | The ship will survive flooding caused by damage to the shell at any location. The final damaged heel angle will not exceed 15 deg and the margin lines will not be submerged. | The ship will survive flooding caused by damage to the shell at any location. The final damaged heel angle will not exceed 15 deg and the margin lines will not be submerged. | The ship will survive flooding caused by damage to the shell at any location except the transverse bulkheads bounding an aft machinery space. The final damaged heel angle will not exceed 25 deg. | The ship will survive flooding caused by damage to the shell at any location. The final damaged heel angle will not exceed 15 degrees and the margin lines will not be submerged. | The ship will survive flooding caused by damage to the shell at any location. The final damaged heel angle will not exceed 15 degrees and the margin lines will not be submerged.
Endurance | 14000 NM (20 kts) | 14000 NM (20 kts) | 14000 NM (20 kts | Exceeds 14,000 NM (20 kts) | Exceeds 14,000 NM (20 kts)
Sustained Speed | > 20 kts NTE 80% MCR | > 20 kts NTE 80% MCR | 20 kts NTE 80% MCR | 20 kts NTE 80% MCR | 20 kts NTE 80% MCR
Cargo Transfer Rate (Sea State 2) | > 274 MTPH palletized ordnance to CV (CONREP & VERTREP), > 220 MTPH palletized | > 274 MTPH palletized ordnance to CV (CONREP & VERTREP), > 220 MTPH palletized | =/> 149 MTPH palletized ordnance to CV (CONREP & VERTREP), =/> 138 | 216 MTPH to CV using 2 CONREP & 2 VERTREP stations. 221 MTPH to 216 MTPH | 216 MTPH to CV using 2 CONREP & 2 VERTREP stations. 221 MTPH to 216 MTPH

## Table 8
| ordnance to CV & CG simultaneous -ly (CONREP) | ordnance to CV & CG simultaneous -ly (CONREP) | MTPH palletized ordnance to CV & CG simultaneous -ly (CONREP) | to CV using 2 CONREP & 2 VERTREP stations 221 MTPH to CV & CG simultaneousl y using 4 CONREP stations | to CV using 2 CONREP & 2 VERTREP stations 221 MTPH to CV & CG simultaneousl y using 4 CONREP stations
Supportability | MSC Stds (CGCERT & ABS) | MSC Stds (CG CERT & ABS) | MSC Stds (CG CERT & ABS) | MSC Stds (CG CERT & ABS) | MSC Stds (CG CERT & ABS)
Reliability (Ship Systems) | Highest commercial stds, ABS Rules, R1 (redundancy) notation for propulsion, steering & aux sys. Redundancy in excess of commercial reqmts for mission critical systems | Highest commercial stds, ABS Rules, R1 (redundancy) notation for propulsion, steering & aux sys. Redundancy in excess of commercial reqmts for mission critical systems | Highest commercial stds, ABS Rules, R1 (redundancy) notation for propulsion, steering & aux sys. Redundancy in excess of commercial reqmts for mission critical systems | Highest commercial stds, ABS Rules, R1 (redundancy) notation for propulsion, steering & aux sys. Redundancy in excess of commercial reqmts for mission critical systems | Highest commercial stds, ABS Rules, R1 (redundancy) notation for propulsion, steering & aux sys. Redundancy in excess of commercial reqmts for mission critical systems
Reliability (Cargo Transfer Systems) | Ao=0.98 | Ao=0.98 | Ao=0.80 | Ao=.98 | Ao=.98
Requirements Source:
Thresholds and objectives are abbreviated directly from the Table of Key Performance Parameters (KPPs) in the T- AKE Operational Requirements Document (ORD) no. 541-4-99, dated July 3, 2001.
Acronyms And Abbreviations
ABS - American Bureau of Shipping aft - towards the stern (rear) of the ship Ao - Operational Availability
aux - auxiliary
C4I - Command, Control, Communications, Computers and Intelligence CERT - Certification
CONREP - Connected Replenishment CV&CG - Aircraft Carrier & Cruiser equip - equipment
IER - Information Exchange Requirements kts - Knots
MCR - Maximum Continuous Rating MSC - Military Sealift Command

## Table 9
MTPH - Metric Tons Per Hour NM - Nautical mile
NTE - Not to exceed
R1 - ABS Redundancy notation "... indicating that a vessel is fitted with multiple machines but only one propeller and steering system..."
REP - Replenishment req'd - required
Stds - Standards sys - system(s)
US - United States
USCG - United States Coast Guard VERTREP - Vertical Replenishment
Change Explanations
None
Memo
Mission critical systems include cargo refrigeration, cargo handling gear, auxiliary equipment for mobility, fire fighting, and exterior communications.

## Table 10
Track To Budget
RDT&E
APPN 1319 | BA 04 | PE 0603564N | (Navy)
| Project 0408 | Research and Development, T- AKE | (Shared) | (Sunk)
APPN 1319 | BA 05 | PE 0604567N | (Navy)
| Project 1803 | Research and Development, T- AKE | (Shared) | (Sunk)
Procurement
APPN 4557 | BA 01 | PE 0408042N | (Navy)
| ICN 0120 | T-AKE |  | (Sunk)
| ICN 5000 | NDSF Post Delivery and Outfitting | (Shared)

## Table 11
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
| BY2000 $M |  |  |  |  | BY2000 $M |  | TY $M
Appropriation | SAR Baseline Prod Est |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Prod Est | Current APB Production Objective | Current Estimate
RDT&E | 26 |  | 26 |  | 28.6 | 26 |  | 25.9 | 25.9 | 25.9
Procurement | 4236.6 |  | 5394 |  | 5933.4 | 5301.7 |  | 4864.3 | 6868 | 6832.3
Flyaway | 4236.6 |  | -- |  | -- | 5301.7 |  | 4864.3 | -- | 6832.3
Recurring | 4236.6 |  | -- |  | -- | 5204.5 |  | 4864.3 | -- | 6728.7
Non Recurring | 0 |  | -- |  | -- | 97.2 |  | 0 | -- | 103.6
Support | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Other Support | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Initial Spares | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
MILCON | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Acq O&M | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Total | 4262.6 |  | 5420 |  | N/A | 5327.7 |  | 4890.2 | 6893.9 | 6858.2
A 95% confidence level is given to the current approved Acquisition Program Baseline dated September 12, 2009 for September 2011 SAR estimates. The rationale for selecting a 95% confidence level is based on actual cost returns on twelve delivered ships.
Quantity |  | SAR Baseline Prod Est |  | Current APB Production |  |  | Current Estimate
RDT&E |  | 0 |  | 0 |  |  | 0
Procurement |  | 12 |  | 14 |  |  | 14
Total |  | 12 |  | 14 |  |  | 14

## Table 12
Cost and Funding
Funding Summary
Appropriation and Quantity Summary
SEP 2011 Exception SAR (TY $M)
Appropriation | Prior | FY2011 |  | FY2012 |  | FY2013 | FY2014 |  | FY2015 |  | FY2 | 16 | To Complete |  | T | otal
RDT&E | 25.9 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 25.9
Procurement | 6783.1 | 31.2 |  |  | 18 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 6832.3
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
SEP 2011 Total | 6809 | 31.2 |  |  | 18 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 6858.2
PB 2012 Total | 6810.3 | 31.2 |  |  | 18 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 6859.5
Delta | -1.3 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | -1.3
Quantity | ndistributed |  | Prior |  | FY2011 | FY2012 | FY2013 | FY2014 |  | FY2015 |  | FY2016 |  | To Complete |  | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 14 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 14
SEP 2011 Total | 0 |  | 14 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 14
PB 2012 Total | 0 |  | 14 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 14
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
FY2012 President's Budget / December 2010 SAR (TY$ M)
Appropriation | Prior | FY2011 |  | FY2012 |  | FY2013 | FY2014 |  | FY2015 |  | FY2 | 16 | To Complete |  | T | otal
RDT&E | 25.9 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 25.9
Procurement | 6784.4 | 31.2 |  |  | 18 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 6833.6
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2012 Total | 6810.3 | 31.2 |  |  | 18 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 6859.5
PB 2011 Total | 6889.2 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 6889.2
Delta | -78.9 | 31.2 |  |  | 18 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | -29.7
Quantity | ndistributed |  | Prior |  | FY2011 | FY2012 | FY2013 | FY2014 |  | FY2015 |  | FY2016 |  | To Complete |  | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 14 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 14
PB 2012 Total | 0 |  | 14 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 14
PB 2011 Total | 0 |  | 14 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 14
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
U
U

## Table 13
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 1.1
1997 | -- | -- | -- | -- | -- | -- | 3.6
1998 | -- | -- | -- | -- | -- | -- | 3.8
1999 | -- | -- | -- | -- | -- | -- | 5.9
2000 | -- | -- | -- | -- | -- | -- | 11.5
Subtotal | -- | -- | -- | -- | -- | -- | 25.9

## Table 14
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
1996 | -- | -- | -- | -- | -- | -- | 1.1
1997 | -- | -- | -- | -- | -- | -- | 3.7
1998 | -- | -- | -- | -- | -- | -- | 3.9
1999 | -- | -- | -- | -- | -- | -- | 5.9
2000 | -- | -- | -- | -- | -- | -- | 11.4
Subtotal | -- | -- | -- | -- | -- | -- | 26

## Table 15
Annual Funding TY$
4557 ¦ Procurement ¦ National Defense Sealift Fund, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2000 | 1 | 393.4 | -- | 103.6 | 497 | -- | 497
2001 | 1 | 357.8 | -- | -- | 357.8 | -- | 357.8
2002 | 1 | 357 | -- | -- | 357 | -- | 357
2003 | 1 | 386.3 | -- | -- | 386.3 | -- | 386.3
2004 | 2 | 720 | -- | -- | 720 | -- | 720
2005 | 2 | 767.8 | -- | -- | 767.8 | -- | 767.8
2006 | 1 | 396.7 | -- | -- | 396.7 | -- | 396.7
2007 | 1 | 531.3 | -- | -- | 531.3 | -- | 531.3
2008 | -- | 803.4 | -- | -- | 803.4 | -- | 803.4
2009 | 2 | 998.7 | -- | -- | 998.7 | -- | 998.7
2010 | 2 | 967.1 | -- | -- | 967.1 | -- | 967.1
2011 | -- | 31.2 | -- | -- | 31.2 | -- | 31.2
2012 | -- | 18 | -- | -- | 18 | -- | 18
Subtotal | 14 | 6728.7 | -- | 103.6 | 6832.3 | -- | 6832.3

## Table 16
Annual Funding BY$
4557 ¦ Procurement ¦ National Defense Sealift Fund, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
2000 | 1 | 369 | -- | 97.2 | 466.2 | -- | 466.2
2001 | 1 | 324.5 | -- | -- | 324.5 | -- | 324.5
2002 | 1 | 321.9 | -- | -- | 321.9 | -- | 321.9
2003 | 1 | 329.3 | -- | -- | 329.3 | -- | 329.3
2004 | 2 | 592.3 | -- | -- | 592.3 | -- | 592.3
2005 | 2 | 605.4 | -- | -- | 605.4 | -- | 605.4
2006 | 1 | 302.5 | -- | -- | 302.5 | -- | 302.5
2007 | 1 | 389.6 | -- | -- | 389.6 | -- | 389.6
2008 | -- | 573.6 | -- | -- | 573.6 | -- | 573.6
2009 | 2 | 698.4 | -- | -- | 698.4 | -- | 698.4
2010 | 2 | 664.9 | -- | -- | 664.9 | -- | 664.9
2011 | -- | 21.1 | -- | -- | 21.1 | -- | 21.1
2012 | -- | 12 | -- | -- | 12 | -- | 12
Subtotal | 14 | 5204.5 | -- | 97.2 | 5301.7 | -- | 5301.7

## Table 17
Cost Quantity Information
4557 ¦ Procurement ¦ National Defense Sealift Fund, Navy
End Item
Recurring
Flyaway
Fiscal Year | Quantity | (Aligned with
Quantity)
BY 2000
$M
2000 | 1 | 357.1
2001 | 1 | 324.5
2002 | 1 | 322.6
2003 | 1 | 331.2
2004 | 2 | 631.8
2005 | 2 | 620.2
2006 | 1 | 305
2007 | 1 | 631.4
2008 | -- | --
2009 | 2 | 848.7
2010 | 2 | 832
2011 | -- | --
2012 | -- | --
Subtotal | 14 | 5204.5
Low Rate Initial Production
There is no Low Rate Initial Production (LRIP) for the T-AKE Program.
Foreign Military Sales
None
Nuclear Cost
None

## Table 18
Unit Cost
Unit Cost Report
|  | BY2000 $M | BY2000 $M
Unit Cost |  | Current UCR Baseline (SEP 2009 APB) | Current Estimate (SEP 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 5420 |  |  | 5327.7
Quantity | 14 |  |  | 14
Unit Cost | 387.143 |  |  | 380.55 |  | -1.7
Average Procurement Unit Cost (APUC)
Cost | 5394 |  |  | 5301.7
Quantity | 14 |  |  | 14
Unit Cost | 385.286 |  |  | 378.693 |  | -1.71
|  | BY2000 $M | BY2000 $M
Unit Cost |  | Original UCR Baseline (SEP 2001 APB) | Current Estimate (SEP 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 4262.6 |  |  | 5327.7
Quantity | 12 |  |  | 14
Unit Cost | 355.217 |  |  | 380.55 |  | 7.13
Average Procurement Unit Cost (APUC)
Cost | 4236.6 |  |  | 5301.7
Quantity | 12 |  |  | 14
Unit Cost | 353.05 |  |  | 378.693 |  | 7.26

## Table 19
Unit Cost History
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
[7 empty] | BY2000 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | SEP 2001 |  |  |  | 355.217 |  | 353.05 |  |  | 407.517 |  | 405.358
APB as of January 2006 |  |  | APR 2003 |  |  |  | 355.217 |  | 353.05 |  |  | 407.517 |  | 405.358
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | JAN 2006 |  |  |  | 355.217 |  | 353.05 |  |  | 407.517 |  | 405.358
Current APB |  |  | SEP 2009 |  |  |  | 387.143 |  | 385.286 |  |  | 492.421 |  | 490.571
Prior Annual SAR |  |  | DEC 2010 |  |  |  | 380.614 |  | 378.757 |  |  | 489.964 |  | 488.114
Current Estimate |  |  | SEP 2011 |  |  |  | 380.55 |  | 378.693 |  |  | 489.871 |  | 488.021
Initial PAUC Prod Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
407.517 28.707 13.397 3.750 0.000 36.500 0.000 0.000 82.354 489.871
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Prod Est | Changes | [11 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
405.358 28.707 13.706 3.750 0.000 36.500 0.000 0.000 82.663 488.021

## Table 20
SAR Baseline History
Item/Event | SAR Planning Estimate (PE) | SAR Development Estimate (DE) | SAR Production Estimate (PdE) | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | N/A | N/A
Milestone C | N/A | N/A | N/A | N/A
IOC | N/A | N/A | OCT 2006 | MAY 2007
Total Cost (TY $M) | N/A | N/A | 4890.2 | 6858.2
Total Quantity | N/A | N/A | 12 | 14
Prog. Acq. Unit Cost (PAUC) | N/A | N/A | 407.517 | 489.871

## Table 21
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 25.9 4864.3 -- 4890.2
Previous Changes
Economic |  | -- |  | 401.9 |  | -- |  | 401.9
Quantity |  | -- |  | 1002.6 |  | -- |  | 1002.6
Schedule |  | -- |  | 52.5 |  | -- |  | 52.5
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | 512.3 |  | -- |  | 512.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -- |  | 1969.3 |  | -- |  | 1969.3
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | -1.3 |  | -- |  | -1.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -- |  | -1.3 |  | -- |  | -1.3
Total Changes |  | -- |  | 1968 |  | -- |  | 1968
CE - Cost Variance |  | 25.9 |  | 6832.3 |  | -- |  | 6858.2
CE - Cost & Funding |  | 25.9 |  | 6832.3 |  | -- |  | 6858.2

## Table 22
Summary Base Year 2000 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 26.0 4236.6 -- 4262.6
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 669.2 |  | -- |  | 669.2
Schedule |  | -- |  | 13.3 |  | -- |  | 13.3
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | 383.5 |  | -- |  | 383.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -- |  | 1066 |  | -- |  | 1066
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | -0.9 |  | -- |  | -0.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -- |  | -0.9 |  | -- |  | -0.9
Total Changes |  | -- |  | 1065.1 |  | -- |  | 1065.1
CE - Cost Variance |  | 26 |  | 5301.7 |  | -- |  | 5327.7
CE - Cost & Funding |  | 26 |  | 5301.7 |  | -- |  | 5327.7
Previous Estimate: December 2010

## Table 23
Procurement | $M
Current Change Explanations | Base Year | Then Year
Above Threshold Reprogramming (ATR) transferred FY 2008 funding from the National Defense Sealift Fund (NDSF) to the FY 2006 funding within the Shipbuilding and Conversion, Navy (SCN) appropriation. (Estimating)
-0.9 -1.3
Procurement Subtotal -0.9 -1.3

## Table 24
Contracts
General Contract Memo
The major contract (N00024-02-C-2300) for the T-AKE program has been completed.
No contracts

## Table 25
Deliveries and Expenditures
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 0 | --
Production | 12 |  | 12 |  | 14 | 85.71%
Total Program Quantities Delivered | 12 |  | 12 |  | 14 | 85.71%
Expenditures and |  | Appropriations (TY $M)
Total Acquisition Cost | 6858.2 | Years Appropriated |  |  | 16
Expenditures To Date | 6300.2 | Percent Years Appropriated |  |  | 94.12%
Percent Expended | 91.86% | Appropriated to Date |  |  | 6840.2
Total Funding Years | 17 | Percent Appropriated |  |  | 99.74%
Expenditures as of October 14, 2011.

## Table 26
Operating and Support Cost
Assumptions And Ground Rules
In the LEWIS and CLARK Class Dry Cargo/Ammunition (T-AKE) Program Life Cycle Cost Estimate, Revision D, dated November 19, 2002, the assumptions for the Cost Element categories are as follows:
Unit-Level Manpower - The Program Office developed a spreadsheet based on "The Center for Naval Analysis (CNA) CRM 97-28.10/November 1999 Combat Logistics Force (CLF) Analysis of Alternatives: Cost Estimating Methodology (CNA CRM 97-28.10)" to calculate a composite of United States Navy (USN) and Military Sealift Command (MSC) monthly salary cost for officer and enlisted personnel. The costs generated accurately reflect the specific complement for T-AKE. These values were then input into a Navy Center for Cost Analysis (NCCA) Operating and Support Cost Analysis Model (OSCAM) and used to generate this cost.
Unit Operations - Unit-level consumption consists of Ship Petroleum Oil Lubricants (POL), Repair Parts/Supplies, Depot Level Repairables, and Purchased Equipment/Services that were calculated as follows:
1. Ship POL - The Program Office developed spreadsheets to calculate fuel consumption based on the actual propulsion plant characteristics and the ship's operating/speed profile. These values were then input into OSCAM.
2. Repair Parts/Supplies - The Program Office developed a spreadsheet which used Center for Naval Analysis CNA 97-28.10 Cost Estimating Relationships (CERs) for Supplies (USN) and Consumables (MSC) to calculate the composite USN and MSC value. This value was then input into OSCAM.
3. Depot Level Repairables - The Program Office used the average cost of material consumed for repair for the CLF ships being replaced. This value was then input into OSCAM.
4. Purchased Equipment/Services - The Program Office used the NCCA CER for Variable Alongside Support Services to represent this cost.This value was then input into OSCAM.
Maintenance - MSC conducts Voyage Repairs (VR). The OSCAM Intermediate Maintenance Ashore function was used in conjunction with the ship's notional operating schedule (one VR per ship per operating quarter between Depot Level Maintenance periods) to generate the cost of VRs. The Depot Level Maintenance profile used in OSCAM was developed based on MSC's notional Depot Maintenance schedule. The Program Office used average costs for the CLF ships being replaced and NCCA CERs to estimate the associated costs.
Sustaining Support - This element is comprised of the following cost items:
1. Centrally Provided Material (CPM) - The Program Office used a spreadsheet to calculate CPM. The value generated was based on a weighted average of the CLF ships being replaced. This value was then input into OSCAM.
2. Engineering Technical Services - The NCCA CER for Engineering Technical Services that encompasses services provided to a ship by Mobile Technical Units, In-Service Engineering Agents and Navy Sea Center (Atlantic and Pacific) was used. This value was input into OSCAM.
3. Receipt, Segregation, Storage, Issue - The Program Office used a spreadsheet using CNA 97-28.10 Cost Estimating Methodology to calculate publication costs, which were used to represent this cost category. This value was input into OSCAM.
Indirect Support - The Program Office developed a spreadsheet using CNA 97-28.10 Cost Estimating Methodology to calculate a composite USN and MSC monthly salary cost for officer and enlisted personnel. The resulting composite values included only indirect costs associated with USN officer and enlisted monthly pay. These values were then input into OSCAM.
There is no antecedent system for this program. The assumed service life for the T-AKE is 40 years; quantity is 14 ships.

## Table 27
Costs BY2000 $M
Cost Element | T-AKE Avg Annual Cost per T-AKE Ship | No Antecedent
Unit-Level Manpower | 13.58 | --
Unit Operations | 8.51 | --
Maintenance | 4.67 | --
Sustaining Support | 0.74 | --
Continuing System Improvements | 0 | --
Indirect Support | 0.2 | --
Other | 0 | --
Total Unitized Cost (Base Year 2000 $) | 27.7 | --
Total O&S Costs $M | T-AKE | No Antecedent
Base Year | 15512 | --
Then Year | -- | --
Operating and Support (O&S) Costs have been updated to reflect the increase in quantity and actual data provided by the Military Sealift Command. The O&S Cost Estimate dated November 19, 2002 has no Then-Year dollar component.