## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-346
WIN-T INCREMENT 1
As of December 31, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 5
Threshold Breaches |  | 6
Schedule |  | 7
Performance |  | 8
Track To Budget |  | 9
Cost and Funding |  | 10
Low Rate Initial Production |  | 16
Nuclear Cost |  | 16
Foreign Military Sales |  | 16
Unit Cost |  | 17
Cost Variance |  | 20
Contracts |  | 23
Deliveries and Expenditures |  | 26
Operating and Support Cost |  | 27

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
Warfighter Information Network-Tactical Increment 1 (WIN-T INCREMENT 1)
DoD Component
Army
Responsible Office
Responsible Office
COL Edward Swanson | Phone | 443-395-7223
PM WIN-T | Fax | 443-395-7208
ATTN: SFAE-C3T-WIN | DSN Phone | 648-7223
6010 Frankford St Aberdeen Proving Ground, MD 21005 | DSN Fax | 648-7208
edward.j.swanson.mil@mail.mil | Date Assigned | September 29, 2011
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 18, 2007
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 18, 2007

## Table 4
Mission and Description
Warfighter Information Network-Tactical (WIN-T) is the implementation of the Army's strategy to achieve a world- class Joint expeditionary network, enabled by information technologies that support the goals of the Army Campaign Plan and other Army/Joint mandates. WIN-T is a cornerstone tactical communications system supporting the implementation of the LandWarNet strategy during the 2007 to 2025 time-frame. The WIN-T program is establishing a single integrating framework creating a network of networks for the Army.
The WIN-T program focus is to design, develop, produce and field the Future Modular Force on-the-move network, while leveraging mature technologies that can enhance the Current Modular Force to operate in an emerging noncontiguous environment. WIN-T will be developed and fielded in increments that will successively build upon one another.
WIN-T Increment 1 (formerly Joint Network Node-Network (JNN-N)) is currently a Program of Record based on Annex I of the Bridge to Future Networks (BFN) Capabilities Production Document (CPD), approved by the Joint Requirements Oversight Council (JROC) in October 2006. WIN-T Increment 1 is further sub-divided into two versions: WIN-T Increment 1a, the JNN-N follow-on with added Ka military satellite capability, and WIN-T Increment 1b, which will incorporate technology insertions, via the Modification Work Order (MWO) process, from the developmental WIN-T Increment 2 program. The Army's legacy tactical communications network and Command and Control, Communications and Computers, Intelligence, Surveillance and Reconnaissance (C4ISR) capabilities were not designed for, nor capable of supporting the current and future Warfighter needs. WIN-T Increment 1 provides a much broader spectrum of information services: video/multimedia, graphics data, imagery, collaborative planning tools, and one Common Operating Picture just to name a few. The program provides the battle commander with an offensively oriented network with extended reach and reach-back, and increased throughput. The Network provides connectivity between the organic Network Support Companies in the Brigade Combat Teams (BCTs) and
the division Support Brigades (SBs) to allow these units to be self-supporting, as derived from the Chief of Staff of the Army's charge to create modular, self-contained Brigade sized units capable of deployment. It
provides organic network support transmission facilities to provide a more capable system than the legacy Area Common User System (ACUS). WIN-T Increment 1 enhances the current forces with technologies that ensure operational relevancy and interoperability with future systems. It also provides the current Warfighter with a state-of- the art communications backbone that enables them to exchange information (voice, data, and video) at high speeds with high reliability throughout the tactical Division, BCT, and Battalion level elements.
WIN-T Increment 1 is a communications system that provides reliable, high-speed information services and information exchanges to enable the Warfighter with the means to control battlefield tempo by getting the right information to the right place at the right time.

## Table 5
Executive Summary
The Product Manager (PdM) for WIN-T Increment 1 continues to acquire and field WIN-T Increment 1a nodes in accordance with the operational requirements of the Army, per authorization contained in the Acquisition Decision Memorandum (ADM) dated June 5, 2007. Each transportable node contains a configuration of satellite and baseband networking equipment that supports the simultaneous transmission of voice, video, and data using Internet Protocol (IP) technology at the quick halt. These nodes vary in configuration, capacities, and quantities according to the level of command they support. The three types of transportable nodes are: the Tactical Hub Node (THN), which supports division headquarters; the Joint Network Node (JNN), which supports brigade level headquarters; and the Battalion Command Post Node (BnCPN), which supports battalion level headquarters. The fourth type of node, the Regional Hub Node (RHN), is a fixed installation equivalent to three THNs, which is used to support theater level operations.
The Defense Acquisition Executive (DAE) signed an Acquisition Decision Memorandum on May 21, 2011 to waive a requirement for a Full Rate Production (FRP) Decision. Conditional Materiel Release for Increment 1 nodes was approved on December 20, 2011.
Production of WIN-T Increment 1 nodes continues at a rate adequate to meet the operational needs of the Army. Increment 1 has been delivered to 95% of the Army Units. Pursuant to section 2432 of title 10, United States Code, this will be the final WIN-T Increment 1 SAR.
There are no significant software-related issues with this program at this time.

## Table 6
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Explanation of Breach
Schedule breach and Research, Development, Test & Evaluation (RDT&E) breach have previously been reported in 2010 SAR.
The Defense Acquisition Executive (DAE) signed an Acquisition Decision Memorandum on May 21, 2011 to waive a requirement for a Full Rate Production (FRP) Decision.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 7
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone C | JUN 2007 | JUN 2007 | JUN 2007 | JUN 2007
Initial Operational Test (IOT) (Increment 1a)
Start | OCT 2008 | OCT 2008 | OCT 2009 | OCT 2008
Complete | DEC 2008 | DEC 2008 | DEC 2009 | DEC 2008
Initial Operational Capability (IOC) | JAN 2009 | JAN 2009 | JAN 2010 | JUL 2009
Full Rate Production Decision Review | JUN 2009 | JUN 2009 | JUN 2010 | MAY 2011 1
Operational Test Increment 1b
Start | MAY 2010 | MAY 2010 | MAY 2011 | MAY 2012 1
Complete | AUG 2010 | AUG 2010 | AUG 2011 | MAY 2012 1
(Ch-1)
(Ch-2)
1APB Breach
Change Explanations
(Ch-1) Current Estimate changed from April 2011 to May 2011 due to an Acquisition Decision Memorandum dated May 21, 2011 that waived requirement for a Full Rate Production decision.
(Ch-2) Increment 1b operational test start date changed from Apr 2012 to May 2012 to accommodate the Army Network Integration Exercise (NIE).

## Table 8
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net-Ready KPP | Satisfy | Satisfy | Satisfy | TBD | Satisfy
| 100% of | 100% of | 100% of |  | 100% of
| interfaces, | interfaces, | interfaces; |  | interfaces,
| services, | services, | services; |  | services,
| policy- | policy- | policy- |  | policy-
| enforcement | enforcement | enforcement |  | enforcement
| controls; and | controls; and | controls; and |  | controls; and
| data | data | data |  | data
| correctness, | correctness, | correctness, |  | correctness,
| availability | availability | availability |  | availability
| and | and | and |  | and
| processing | processing | processing |  | processing
| requirements | requirements | requirements |  | requirements
| in the Jt | in the Jt | designated |  | in the Jt
| integrated | integrated | as |  | integrated
| architecture | architecture | enterprise- |  | architecture
level or
critical in the
Jt integrated
architecture
Requirements Source: Bridge to Future Networks (BFN) Capabilities Production Document (CPD) with Annexes, approved by the Joint Requirements Oversight Council (JROC) on October 18, 2006
Acronyms And Abbreviations
Jt - Joint
KPP - Key Performance Parameter TBD - To be determined
Change Explanations
None
Memo
The sole Performance Characteristic, Net-Ready, is documented in the Joint Network Node-Network (JNN-N) Annex I of the Bridge to Future Networks (BFN) Capabilities Production Document (CPD), approved October 2006. The Net-Ready Key Performance Parameter (KPP), the only KPP, was not successfully demonstrated during 2008 IOT&E. The Increment 1b operational test is scheduled to start in May 2012.

## Table 9
Track To Budget
General Memo
WIN-T Increment 1 procurement is funded under BB1601 through FY 2008, and under BW7110 in FY 2009 and beyond. Parent Line is BW7100.
RDT&E
APPN 2040 | BA 05 | PE 06054818A | (Army)
| Project JN1 | JNN/Joint Network Node
Procurement
APPN 2035 | BA 02 | PE 0310704A | (Army)
| ICN BB1601 ICN BW7110 | JNN WIN-T Increment 1

## Table 10
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  | Current Estimate
|  | BY2007 $M |  |  |  |  | BY2007 $M
Appropriation |  | SAR Baseline Prod Est |  | Current APB Production Objective/Threshold |  |  | Current Estimate
RDT&E |  | 23 |  | 23 |  | 29.9 | 34.3 1 |  | 23.7 | 23.7 | 36.2
Procurement |  | 3775 |  | 3775 |  | 4152.5 | 4074.4 |  | 3856 | 3856 | 4185.3
Flyaway |  | 2206.2 |  | -- |  | -- | 2236.2 |  | 2232 | -- | 2252
Recurring |  | 2173.1 |  | -- |  | -- | 2192.8 |  | 2197.6 | -- | 2207.1
Non Recurring |  | 33.1 |  | -- |  | -- | 43.4 |  | 34.4 | -- | 44.9
Support |  | 1568.8 |  | -- |  | -- | 1838.2 |  | 1624 | -- | 1933.3
Other Support |  | 1339.2 |  | -- |  | -- | 1602.6 |  | 1395 | -- | 1698.9
Initial Spares |  | 229.6 |  | -- |  | -- | 235.6 |  | 229 | -- | 234.4
MILCON |  | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Total |  | 3798 |  | 3798 |  | N/A | 4108.7 |  | 3879.7 | 3879.7 | 4221.5
1 APB Breach
Quantity |  | SAR Baseline Prod Est |  |  | Current APB Production |  |  | Current Estimate
RDT&E |  | 0 |  |  | 0 |  |  | 0
Procurement |  | 1677 |  |  | 1677 |  |  | 1860
Total |  | 1677 |  |  | 1677 |  |  | 1860
Unit of measure is a combination of communications nodes, which vary in configuration, capacities, and quantities according to the level of command they support. The three types of transportable nodes are: the Tactical Hub Node (THN), which supports division headquarters; the Joint Network Node (JNN), which supports brigade level headquarters; and the Battalion Command Post Node (BnCPN), which supports battalion level headquarters. The fourth type of node, the Regional Hub Node (RHN), is a fixed installation equivalent to three THNs, which is used to support theater level operations.

## Table 11
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2013 President's Budget / December 2011 SAR (TY$ M)
Appropriation | Prior | FY2012 |  | FY2013 |  | FY2014 | FY2015 |  | FY2016 |  | FY2 | 17 | To Complete |  | T | otal
RDT&E | 23 | 13.2 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 36.2
Procurement | 3736 | 34.8 |  |  | 98.3 | 175 | 130.9 |  | 10.3 |  | 0 |  | 0 |  | 4185.3
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2013 Total | 3759 | 48 |  |  | 98.3 | 175 | 130.9 |  | 10.3 |  | 0 |  | 0 |  | 4221.5
PB 2012 Total | 3759.2 | 48 |  |  | 27.7 | 265.3 | 128.6 |  | 74.3 |  | 0 |  | 0 |  | 4303.1
Delta | -0.2 | 0 |  |  | 70.6 | -90.3 | 2.3 |  | -64 |  | 0 |  | 0 |  | -81.6
Quantity | ndistributed |  | Prior |  | FY2012 | FY2013 | FY2014 | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 1860 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 1860
PB 2013 Total | 0 |  | 1860 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 1860
PB 2012 Total | 0 |  | 1860 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 1860
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
U

## Table 12
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2006 | -- | -- | -- | -- | -- | -- | 7.2
2007 | -- | -- | -- | -- | -- | -- | --
2008 | -- | -- | -- | -- | -- | -- | 15.8
2009 | -- | -- | -- | -- | -- | -- | --
2010 | -- | -- | -- | -- | -- | -- | --
2011 | -- | -- | -- | -- | -- | -- | --
2012 | -- | -- | -- | -- | -- | -- | 13.2
Subtotal | -- | -- | -- | -- | -- | -- | 36.2

## Table 13
Annual Funding BY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2007 $M | Non End Item Recurring Flyaway BY 2007 $M | Non Recurring Flyaway BY 2007 $M | Total Flyaway BY 2007 $M | Total Support BY 2007 $M | Total Program BY 2007 $M
2006 | -- | -- | -- | -- | -- | -- | 7.2
2007 | -- | -- | -- | -- | -- | -- | --
2008 | -- | -- | -- | -- | -- | -- | 15.2
2009 | -- | -- | -- | -- | -- | -- | --
2010 | -- | -- | -- | -- | -- | -- | --
2011 | -- | -- | -- | -- | -- | -- | --
2012 | -- | -- | -- | -- | -- | -- | 11.9
Subtotal | -- | -- | -- | -- | -- | -- | 34.3

## Table 14
Annual Funding TY$
2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2004 | 195 | 302.3 | -- | -- | 302.3 | 41.9 | 344.2
2005 | 215 | 296.7 | -- | -- | 296.7 | 121.2 | 417.9
2006 | 349 | 452.1 | -- | 5.8 | 457.9 | 325 | 782.9
2007 | 327 | 385.9 | -- | -- | 385.9 | 80.4 | 466.3
2008 | 741 | 701 | -- | 39.1 | 740.1 | 800.2 | 1540.3
2009 | 33 | 69.1 | -- | -- | 69.1 | 56.3 | 125.4
2010 | -- | -- | -- | -- | -- | 29.3 | 29.3
2011 | -- | -- | -- | -- | -- | 29.7 | 29.7
2012 | -- | -- | -- | -- | -- | 34.8 | 34.8
2013 | -- | -- | -- | -- | -- | 98.3 | 98.3
2014 | -- | -- | -- | -- | -- | 175 | 175
2015 | -- | -- | -- | -- | -- | 130.9 | 130.9
2016 | -- | -- | -- | -- | -- | 10.3 | 10.3
Subtotal | 1860 | 2207.1 | -- | 44.9 | 2252 | 1933.3 | 4185.3

## Table 15
Annual Funding BY$
2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2007 $M | Non End Item Recurring Flyaway BY 2007 $M | Non Recurring Flyaway BY 2007 $M | Total Flyaway BY 2007 $M | Total Support BY 2007 $M | Total Program BY 2007 $M
2004 | 195 | 319.4 | -- | -- | 319.4 | 44.2 | 363.6
2005 | 215 | 304.8 | -- | -- | 304.8 | 124.5 | 429.3
2006 | 349 | 452.4 | -- | 5.8 | 458.2 | 325.2 | 783.4
2007 | 327 | 377.1 | -- | -- | 377.1 | 78.5 | 455.6
2008 | 741 | 673.6 | -- | 37.6 | 711.2 | 768.8 | 1480
2009 | 33 | 65.5 | -- | -- | 65.5 | 53.4 | 118.9
2010 | -- | -- | -- | -- | -- | 27.3 | 27.3
2011 | -- | -- | -- | -- | -- | 27.1 | 27.1
2012 | -- | -- | -- | -- | -- | 31.2 | 31.2
2013 | -- | -- | -- | -- | -- | 86.6 | 86.6
2014 | -- | -- | -- | -- | -- | 151.5 | 151.5
2015 | -- | -- | -- | -- | -- | 111.3 | 111.3
2016 | -- | -- | -- | -- | -- | 8.6 | 8.6
Subtotal | 1860 | 2192.8 | -- | 43.4 | 2236.2 | 1838.2 | 4074.4
Funding (mostly Supplemental) from FY 2004 to FY 2007 was used to acquire Joint Network Node under the condition of urgency for units deploying to Operation Iraqi Freedom / Operation Enduring Freedom. FY 2008 and FY 2009 supplemental funding has been used to acquire WIN-T Increment 1 to outfit units in accordance with Army priorities.
Procurement dollars in FY 2010 and beyond are for technology insertions – a planned Modification Work Order to provide Net-Centric Waveform and colorless core (enhanced encryption) technology.

## Table 16
Low Rate Initial Production
| Initial LRIP Decision | Current Total LRIP
Approval Date | 6/5/2007 6/5/2007 199 216 WIN-T Program ADM WIN-T Program ADM 2007 2007 2010 2011
Approved Quantity
Reference
Start Year
End Year
WIN-T Increment 1 Low Rate Initial Production (LRIP) is consistent with Defense Acquisition Executive (DAE) direction in the WIN-T Program Acquisition Decision Memorandum (ADM), dated June 5, 2007, and the Office of Secretary of Defense (OSD) Cost Analysis Improvement Group (CAIG) estimate. The WIN-T Program ADM defines Increment 1 LRIP as the quantities required "to meet operational requirements of the Army". The ADM also directs Increment 1 fielding up "to about 199 [total] units", which represents the Full Operational Capability requirement, not including expected Army growth. Therefore, the ADM LRIP permits acquisition of more than 10 percent of the total program quantity. The most current estimate, including Grow the Army, is 216 units.
Foreign Military Sales
None
Nuclear Cost
None

## Table 17
Unit Cost
Unit Cost Report
|  | BY2007 $M | BY2007 $M
Unit Cost |  | Current UCR Baseline (OCT 2007 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 3798 |  |  | 4108.7
Quantity | 1677 |  |  | 1860
Unit Cost | 2.265 |  |  | 2.209 |  | -2.47
Average Procurement Unit Cost (APUC)
Cost | 3775 |  |  | 4074.4
Quantity | 1677 |  |  | 1860
Unit Cost | 2.251 |  |  | 2.191 |  | -2.67
|  | BY2007 $M | BY2007 $M
Unit Cost |  | Original UCR Baseline (OCT 2007 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 3798 |  |  | 4108.7
Quantity | 1677 |  |  | 1860
Unit Cost | 2.265 |  |  | 2.209 |  | -2.47
Average Procurement Unit Cost (APUC)
Cost | 3775 |  |  | 4074.4
Quantity | 1677 |  |  | 1860
Unit Cost | 2.251 |  |  | 2.191 |  | -2.67

## Table 18
Unit Cost History
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
[7 empty] | BY2007 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | OCT 2007 |  |  |  | 2.265 |  | 2.251 |  |  | 2.313 |  | 2.299
APB as of January 2006 |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current APB |  |  | OCT 2007 |  |  |  | 2.265 |  | 2.251 |  |  | 2.313 |  | 2.299
Prior Annual SAR |  |  | DEC 2010 |  |  |  | 2.251 |  | 2.232 |  |  | 2.313 |  | 2.294
Current Estimate |  |  | DEC 2011 |  |  |  | 2.209 |  | 2.191 |  |  | 2.27 |  | 2.25
Initial PAUC Prod Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
2.313 -0.008 -0.100 0.000 0.000 -0.104 0.000 0.169 -0.043 2.270
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Prod Est | Changes | [11 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
2.299 -0.008 -0.098 -0.001 0.000 -0.111 0.000 0.169 -0.049 2.250

## Table 19
SAR Baseline History
Item/Event | SAR Planning Estimate (PE) | SAR Development Estimate (DE) | SAR Production Estimate (PdE) | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | N/A | N/A
Milestone C | N/A | N/A | JUN 2007 | JUN 2007
IOC | N/A | N/A | JAN 2009 | JUL 2009
Total Cost (TY $M) | N/A | N/A | 3879.7 | 4221.5
Total Quantity | N/A | N/A | 1677 | 1860
Prog. Acq. Unit Cost (PAUC) | N/A | N/A | 2.313 | 2.27

## Table 20
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 23.7 3856.0 -- 3879.7
Previous Changes
Economic |  | -0.1 |  | -26.2 |  | -- |  | -26.3
Quantity |  | -- |  | 238 |  | -- |  | 238
Schedule |  | 0.4 |  | -1.1 |  | -- |  | -0.7
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 12.2 |  | -205.2 |  | -- |  | -193
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 405.4 |  | -- |  | 405.4
Subtotal |  | 12.5 |  | 410.9 |  | -- |  | 423.4
Current Changes Economic |  | 0.2 |  | 10.5 |  | -- |  | 10.7
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -0.2 |  | -1 |  | -- |  | -1.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -91.1 |  | -- |  | -91.1
Subtotal |  | -- |  | -81.6 |  | -- |  | -81.6
Total Changes |  | 12.5 |  | 329.3 |  | -- |  | 341.8
CE - Cost Variance |  | 36.2 |  | 4185.3 |  | -- |  | 4221.5
CE - Cost & Funding |  | 36.2 |  | 4185.3 |  | -- |  | 4221.5

## Table 21
Summary Base Year 2007 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 23.0 3775.0 -- 3798.0
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 227.8 |  | -- |  | 227.8
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 11.5 |  | -196.9 |  | -- |  | -185.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 345.7 |  | -- |  | 345.7
Subtotal |  | 11.5 |  | 376.6 |  | -- |  | 388.1
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -0.2 |  | -0.9 |  | -- |  | -1.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -76.3 |  | -- |  | -76.3
Subtotal |  | -0.2 |  | -77.2 |  | -- |  | -77.4
Total Changes |  | 11.3 |  | 299.4 |  | -- |  | 310.7
CE - Cost Variance |  | 34.3 |  | 4074.4 |  | -- |  | 4108.7
CE - Cost & Funding |  | 34.3 |  | 4074.4 |  | -- |  | 4108.7
Previous Estimate: December 2010

## Table 22
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 0.2
Adjustment for current and prior escalation. (Estimating) | -0.2 | -0.2
RDT&E Subtotal | -0.2 | 0
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 10.5
Adjustment for current and prior escalation. (Estimating) | -0.9 | -1
Adjustment for current and prior escalation. (Support) | -1.8 | -1.7
Decrease in Other Support is due to redefining the Network Operations Convergence -74.3 -89.1
Decrease in Initial Spares requirement. (Support) | -0.2 | -0.3
Procurement Subtotal | -77.2 | -81.6
requirement. (Support)

## Table 23
Contracts
Appropriation: Procurement
Contract Name World-Wide Satellite Systems (WWSS)
Contractor General Dynamics SATCOM Technologies
Contractor Location Duluth, GA 30096
Contract Number, Type W15P7T-06-D-L219/5, FFP
Award Date August 21, 2007
Definitization Date August 21, 2007
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
50.3 N/A 103 475.6 N/A 800 993.0 993.0
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
The difference between the initial contract price target and the current contract price target is due to changes in quantity as Army G3 identified the specific units that are to receive Increment 1 nodes, in accordance with the terms of the Acquisition Decision Memorandum dated June 5, 2007.
The WIN-T Increment 1 delivery order on this contractual vehicle acquires some of the satellite terminal equipment and vehicles required to complete the communications nodes procured under the Baseband contract (W15P7T-07- D-K001).

## Table 24
Appropriation: Procurement
Contract Name World-Wide Satellite Systems (WWSS)
Contractor General Dynamics SATCOM Technologies
Contractor Location Duluth, GA 30096
Contract Number, Type W15P7T-06-D-L219/10, FFP
Award Date September 29, 2009
Definitization Date September 29, 2009
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
30.7 N/A 3 33.1 N/A 3 61.1 61.1
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
The difference between the initial contract price target and the current contract price target is due to the incremental funding of this portion of the overall initiative; it is not due to price or requirement changes.
This Delivery Order (DO) includes all of the services and some of the hardware required to build three additional Regional Hub Nodes (RHNs) for Fort Bragg, Guam, and Camp Roberts.

## Table 25
Appropriation: Procurement
Contract Name WIN-T Increment 1
Contractor GD C4 Systems
Contractor Location Taunton, MA 02780
Contract Number, Type W15P7T-07-D-K001, FFP/IDIQ/TM/CPFF
Award Date September 28, 2007
Definitization Date September 28, 2007
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
78.3 N/A 336 721.2 N/A 1053 1427.0 1427.0
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP/IDIQ/TM/CPFF contract.
Contract Comments
The difference between the initial contract price target and the current contract price target is due to change in quantity and contract services as Army G3 identified the specific units that are to receive Increment 1 nodes; it is not due to unscheduled price or performance requirement changes.

## Table 26
Deliveries and Expenditures
In the Acquisition Decision Memorandum dated June 5, 2007, the Defense Acquisition Executive directed the Army to secure full funding for Increment 1 acquisition and support.
Percent delivered is as of January 15, 2012.
Deliveries To Date | Plan To | Date | Actual To Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 0 | --
Production | 1760 |  | 1760 |  | 1860 | 94.62%
Total Program Quantities Delivered | 1760 |  | 1760 |  | 1860 | 94.62%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 4221.5 | Years Appropriated |  |  | 9
Expenditures To Date | 3327 | Percent Years Appropriated |  |  | 69.23%
Percent Expended | 78.81% | Appropriated to Date |  |  | 3807
Total Funding Years | 13 | Percent Appropriated |  |  | 90.18%

## Table 27
Operating and Support Cost
Assumptions And Ground Rules
1. No antecedent for this system.
2. Operating and support costs based on the Program Office Estimate dated February 2007, as updated in January 2012.
3. Costs estimated in accordance with Army Cost Analysis Manual, Deputy Assistant Secretary of the Army, US Army Cost and Economics Analysis Center May 2001.
4. Operating and support cost factors taken from Operating and Support Management Information System.
5. Military Pay and Allowances estimates extracted from Army Manpower Cost System based on the known Military Occupational Specialty staffing requirements.
6. Estimated costs based on Operating Tempo as provided by Headquarters, Department of the Army.
7. Costs based on two-level maintenance concept.
8. Operating and support costs presented ramp up and extend through FY2027, representing 23 years.
9. Operating and support costs reflect the total average annual cost for all WIN-T Increment 1 systems. Multiplying the total average annual cost by 23 years will achieve the total cost.
10. Estimate below does not include disposal cost of the system.
Costs BY2007 $M
Cost Element | WIN-T INCREMENT 1 Total Average Annual Cost | Antecedent System N/A
Unit-Level Manpower | 192.1 | --
Unit Operations | -- | --
Maintenance | -- | --
Sustaining Support | -- | --
Continuing System Improvements | -- | --
Indirect Support | -- | --
Other | 169.2 | --
Total Unitized Cost (Base Year 2007 $) | 361.3 | --
Total O&S Costs $M | WIN-T INCREMENT 1 | Antecedent System
Base Year | 8311 | --
Then Year | 9763.1 | --