## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-202
AB3A REMANUFACTURE
As of December 31, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 5
Threshold Breaches |  | 6
Schedule |  | 7
Performance |  | 8
Track To Budget |  | 10
Cost and Funding |  | 11
Low Rate Initial Production |  | 17
Nuclear Cost |  | 18
Foreign Military Sales |  | 18
Unit Cost |  | 19
Cost Variance |  | 22
Contracts |  | 25
Deliveries and Expenditures |  | 26
Operating and Support Cost |  | 27

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
APACHE BLOCK IIIA REMANUFACTURE (AB3A REMANUFACTURE)
DoD Component
Army
Responsible Office
Responsible Office
COL Shane Openshaw Project Manager ATTN: SFAE-AV-AAH
Bldg 5681
Redstone Arsenal, AL 35898-5000
Phone Fax
DSN Phone DSN Fax
256-313-4200
256-313-4497
897-4200
--
Shane.Openshaw@peoavn.army.mil Date Assigned August 14, 2008
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB), dated December 16, 2010.
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 16, 2010

## Table 4
Mission and Description
The Apache Block III (AB3) is the heavy attack helicopter of the current and future force. It is a twin engine, four bladed, tandem seat, attack helicopter with 30mm ammunition, 2.75" rockets, laser & Radio Frequency (RF) Hellfire missiles. AB3 is the Army's network-centric, multi-role weapon system within the Future Modular Force (FMF). It will provide the capability to simultaneously conduct (or quickly transition between) close combat, mobile strike, armed reconnaissance, security and vertical maneuver missions across the full spectrum of warfare from Stability And Support Operations (SASO) to Major Combat Operations (MCO) when required in day, night, obscured battlefield and adverse weather conditions. AB3 will enable the Joint Air/Ground Maneuver Team to dominate the battle space by providing air-ground synergy through real-time Intelligence, Surveillance and Reconnaissance (ISR) information and responsive precision fires. AB3 will be linked to Joint and Combined Arms Air/Ground Maneuver Teams via Enhanced Digital Communications, Unmanned Aircraft Systems (UAS) Data Link and Joint Networking waveforms.
The AB3 is an Apache Attack Helicopter modified as required to effectively and efficiently integrate the Longbow Apache well into the 21st century, by providing improvements to make it relevant in FMF operations. It provides a significantly enhanced warfighting capability over the AH-64A and AH-64D. It is capable of being employed day or night in adverse weather and obscurants, and can effectively engage and destroy advanced threat weapon systems on the air-land battlefield. Tactically, the AB3 provides significant war fighting advantages over the original AH-64D and multiplies the combat effectiveness of the entire fleet. It will be fully capable of employing the Longbow Fire Control Radar (FCR) mission kit, the Modernized Target Acquisition Designation System/Modernized Pilot Night Vision System (M-TADS/M-PNVS), the Longbow Hellfire missiles, and future improved munitions in addition to the normal complement of AH-64D munitions.
The AB3 will be fully network-centric capable with current digitized forces and FMF equipped forces. This will enable interoperability with current and future Tactical Operations Center (TOC) and Army Battle Command System forces. In addition, it will reduce the logistics footprint and enhance its deployability, reduce operational and support costs, improve AH-64D model flight performance and provide a means to effectively utilize already funded technology insertions.
AB3 will operate within the future force system-of-systems environment, where maximum combat power is delivered to units only in coherent packages of systems with synergistic interdependence. The FMF concept drives the demand for network centric interdependence and joint integration across the force to new levels. The AB3 meets the challenge of providing and integrating Command and Control (C2); ISR; and communications connectivity for attack/reconnaissance aviation within brigade combat teams, divisions and corps.

## Table 5
Executive Summary
On June 28, 2006, the Defense Acquisition Executive (DAE) conducted a successful Milestone B (MS B) review of the Apache Block III (AB3) program. As a result, the DAE signed an Acquisition Decision Memorandum (ADM), dated July 10, 2006, approving MS B, authorizing the AB3 program to enter System Development and Demonstration (SDD) and designating it as an Acquisition Category (ACAT) ID program. On July 14, 2006, the Apache Project Manager awarded an SDD contract to the Boeing Company to begin the development effort for AB3. An SDD contract was awarded to the Longbow Limited (LBL) Company on September 29, 2006. This effort will specifically develop the subsystem improvements for the AB3 Fire Control Radar and enable the Level IV Unmanned Aircraft System (UAS) control. A follow-on ADM was approved on March 7, 2007 authorizing Low Rate Initial Production (LRIP) quantity of 59 aircraft and granting Army authority to procure long-lead items beginning in Fiscal Year (FY) 2009. The Acquisition Program Baseline (APB) milestones established for the Preliminary Design Review and the Critical Design Review were successfully completed on April 19, 2007 and January 30, 2008 respectively. The Limited User Test was successfully executed in November 2009.
The AB3 program was directed to increase total quantity procurement by 56 aircraft through the FY 2011 President's Budget (PB11) at a total additional cost of $2.5 Billion (B). The baseline program was a remanufacture production. These additional aircraft procurements will be New Build aircraft at a unit cost significantly higher than the remanufacture unit cost. The cost for a remanufacture aircraft is only 30 percent of the cost of a New Build aircraft.
The addition of the New Build aircraft along with minor fact of life changes to the program since the beginning of Research, Development, Test, and Evaluation (RDTE) caused a Nunn-McCurdy unit cost breach to the Average Procurement Unit Cost (a Base Year 2006 change of +31.2 percent), which was reflected in the December 2009 SAR. The DAE supported a rapid Nunn-McCurdy process which was completed June 1, 2010 with an ADM certifying the program to move forward to Milestone C (MS C) and separating the baseline program into two Major Defense Acquisition Programs (MDAP) for cost accounting purposes (AB3A Remanufacture and AB3B New Build). As part of the Nunn-McCurdy certification and MS C process, the Office of the Secretary of Defense (OSD) Cost Assessment and Program Evaluation (CAPE) produced an Independent Cost Estimate (ICE) for both the AB3A and AB3B programs. While the ICE for the AB3B was slightly less than the New Build portion of the December 2009 SAR, the ICE for the AB3A was significantly higher than the remanufacture program as estimated in the Program Office Estimate (POE). The major differences between the ICE and POE for the AB3A remanufacture program are as follows: the ICE assumes more manhours will be required for completion of the Software development effort and level loads those manhours resulting in an additional year of RDTE; the ICE assumes significantly more manhours in the remanufacture process as well as higher material costs. A successful MS C Defense Acquisition Board (DAB) was completed on September 27, 2010. The resultant AB3A ADM directed the Army to fund the AB3A program to the ICE. Actual program funding was not increased in the Future Years Defense Program (FYDP). The ICE “bought to the budget” in the FYDP with resultant zero sums between the RDTE and Army Procurement appropriations as well as reduced quantities. The AB3 DAB allowed the move into LRIP and advance procurement actions for Full Rate Production (FRP). An LRIP contract was awarded on October 22, 2010. The first AB3A production delivery occurred October 24, 2011 with a formal roll out ceremony held November 2, 2011. Initial Operational Test and Evaluation (IOT&E) will occur with AB3A production aircraft March 2012.
There are no significant software-related issues with this program.

## Table 6
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 7
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | JUN 2006 | JUN 2006 | DEC 2006 | JUL 2006
Preliminary Design Review | APR 2007 | APR 2007 | OCT 2007 | APR 2007
Critical Design Review | JAN 2008 | JAN 2008 | JUL 2008 | JAN 2008
LUT | NOV 2009 | NOV 2009 | MAY 2010 | NOV 2009
Milestone C | JUL 2010 | JUL 2010 | JAN 2011 | SEP 2010
IOT&E | MAR 2012 | MAR 2012 | SEP 2012 | MAR 2012
FRP | JUL 2012 | JUL 2012 | JAN 2013 | JUL 2012
First Unit Equipped | NOV 2012 | NOV 2012 | MAY 2013 | NOV 2012
IOC | MAY 2013 | MAY 2013 | NOV 2013 | MAY 2013
Acronyms And Abbreviations
FRP - Full Rate Production
IOC - Initial Operating Capability
IOT&E - Initial Operational Test and Evaluation LUT - Limited User Test
Change Explanations
None

## Table 8
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net Ready | Fully support execution of all operational activities. | Fully support execution of all operational activities. | Fully support execution of joint critical operational activities. | TBD | Support execution of all critical operational activities
Performance
6000' PA, 95 F OGE Hover (lbs/payload) | 4100 | 4100 | 3400 | TBD | 3400
Mission Reliability
MTBF(M) hrs.
Lot 1 | 22 | 22 | 15.3 | TBD | 15.3
Lot 4 | 22 | 22 | 17 | TBD | 17
MR for 3.5 hr. flight (%) | 85 | 85 | 80 | TBD | 80
Survivability
Safe operation (minutes) | 30 | 30 | 30 | TBD | 30
Survive Band IV MANPADS IR Missile Engagement | IAW JROCM 086-10 | IAW JROCM 086-10 | IAW JROCM 086-10 | TBD | IAW JROCM 086-10
Force Protection
Crewstation armor survivability (mm) | IAW JROCM 086-10 | IAW JROCM 086-10 | IAW JROCM 086-10 | TBD | IAW JROCM 086-10
Crewstation armor barrier survivability (mm) | IAW JROCM 086-10 | IAW JROCM 086-10 | IAW JROCM 086-10 | TBD | IAW JROCM 086-10
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
Requirements Source:
Capability Production Document (CPD) approved by Joint Requirements Oversight Council Memorandum (JROCM), June 1, 2010.
Acronyms And Abbreviations
% - Percent
F - Fahrenheit hr - hour
hrs - hours
IAW - In Accordance With IR - Infrared
JROCM - Joint Requirements Oversight Council Memorandum

## Table 9
lbs - Pounds
MANPADS - Man Portable Air Defense System mm - Millimeters
MR - Mission Reliability
MTBF(M) - Mean Time Between Failure (Maintenance) OGE - Out of Ground Effect
PA - Pressure Altitude TBD - To Be Determined
Change Explanations
(Ch-1) Current estimate revised to reflect Initial Operational Test and Evaluation (IOT&E) threshold values. The performance current estimate changed as indicated:
- Performance changed from 4,100 to 3,400
- Mission Reliability Lot 1 changed from 22 to 15.3
- Mission Reliability Lot 4 changed from 22 to 17
- Mission Reliability for 3.5 hr. flight (%) changed from 85 to 80
- Survive Band IV changed fromIAW JROCM 132.06 to to JROCM 086-10
- Crewstation armor survivability changed from 12.7 to IAW JROCM 086-10
- Crewstation armor barrier survivability changed from 23 to IAW JROCM 086-10.

## Table 10
Track To Budget
RDT&E
APPN 2040 | BA 07 | PE 0203744A | (Army)
| Project D17 | Apache Block III
Procurement
APPN 2031 | BA 01 | PE 0210100A | (Army)
| ICN A05111 | Apache Longbow Block III A Reman
APPN 2031 | BA 02 | PE 0210102A | (Army)
| ICN AA6606 | AH-64 Mods | (Shared) (Sunk)
This line is shared because in FY 2009, before AB3 was a separate program from AH-64 Mods, there was AB3 advance procurement that has to be captured in the AB3 Selected Acquisition Report.

## Table 11
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
| BY2010 $M |  |  |  |  | BY2010 $M |  | TY $M
Appropriation | SAR Baseline Prod Est |  | Current Product Objective/Th |  | APB ion reshold | Current Estimate |  | SAR Baseline Prod Est | Current APB Production Objective | Current Estimate
RDT&E | 1611.8 |  | 1611.8 |  | 1773 | 1610.4 |  | 1664.7 | 1664.7 | 1678.9
Procurement | 8856.9 |  | 8856.9 |  | 9742.6 | 8639 |  | 10231.9 | 10231.9 | 10289.4
Flyaway | 7383.2 |  | -- |  | -- | 7226.7 |  | 8543.6 | -- | 8625.5
Recurring | 7128.5 |  | -- |  | -- | 6967.8 |  | 8277 | -- | 8353.2
Non Recurring | 254.7 |  | -- |  | -- | 258.9 |  | 266.6 | -- | 272.3
Support | 1473.7 |  | -- |  | -- | 1412.3 |  | 1688.3 | -- | 1663.9
Other Support | 1306.3 |  | -- |  | -- | 1223.9 |  | 1496.9 | -- | 1439.8
Initial Spares | 167.4 |  | -- |  | -- | 188.4 |  | 191.4 | -- | 224.1
MILCON | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Acq O&M | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Total | 10468.7 |  | 10468.7 |  | N/A | 10249.4 |  | 11896.6 | 11896.6 | 11968.3
Confidence Level For Current APB Cost 50% - based on the Independent Cost Estimate (ICE) prepared for the Acquisition Program Baseline (APB).
The ICE to support Apache Block III Remanufacture (AB3A) Milestone Decision C is similar to all life-cycle cost estimates previously performed by the Cost Assessment and Program Evaluation (CAPE). This ICE is built upon a work breakdown structure that wherever possible uses actual cost information along with conservative assumptions that are consistent with contractor and government performance demonstrated in other successful Department acquisition programs. This strategy fully supports the APB objective and threshold positions.
It is difficult to precisely calculate confidence levels associated with life cycle cost estimates for Major Defense Acquisition Programs. Despite collecting and incorporating extensive historical cost information, our projections show that the estimate is equally likely to be too low or too high when executing the current program. We are confident that, as we accumulate additional cost data, we will be better able to predict the life cycle costs.
Quantity |  | SAR Baseline Prod Est |  | Current APB Production |  |  | Current Estimate
RDT&E |  | 5 |  | 5 |  |  | 5
Procurement |  | 634 |  | 634 |  |  | 634
Total |  | 639 |  | 639 |  |  | 639

## Table 12
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2013 President's Budget / December 2011 SAR (TY$ M)
Appropriation | Prior | FY2012 |  | FY2013 |  | FY2014 | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | T | otal
RDT&E | 895.2 | 92.7 |  | 124.5 |  | 153.9 | 160 |  | 138.2 |  | 114.4 |  | 0 |  | 1678.9
Procurement | 766.7 | 561.3 |  | 684.8 |  | 618.8 | 517.7 |  | 605.9 |  | 526.2 |  | 6008 |  | 10289.4
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2013 Total | 1661.9 | 654 |  | 809.3 |  | 772.7 | 677.7 |  | 744.1 |  | 640.6 |  | 6008 |  | 11968.3
PB 2012 Total | 1632.9 | 696.5 |  | 704.4 |  | 628.6 | 850 |  | 964.5 |  | 973.3 |  | 5442.9 |  | 11893.1
Delta | 29 | -42.5 |  | 104.9 |  | 144.1 | -172.3 |  | -220.4 |  | -332.7 |  | 565.1 |  | 75.2
Quantity | ndistributed |  | Prior |  | FY2012 | FY2013 | FY2014 | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
Development | 5 |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 5
Production | 0 |  |  | 24 | 19 | 40 | 38 |  | 37 |  | 44 |  | 37 | 395 |  | 634
PB 2013 Total | 5 |  |  | 24 | 19 | 40 | 38 |  | 37 |  | 44 |  | 37 | 395 |  | 639
PB 2012 Total | 5 |  |  | 24 | 19 | 40 | 24 |  | 43 |  | 53 |  | 60 | 371 |  | 639
Delta | 0 |  |  | 0 | 0 | 0 | 14 |  | -6 |  | -9 |  | -23 | 24 |  | 0
U

## Table 13
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2005 | -- | -- | -- | -- | -- | -- | 57
2006 | -- | -- | -- | -- | -- | -- | 104.1
2007 | -- | -- | -- | -- | -- | -- | 118.9
2008 | -- | -- | -- | -- | -- | -- | 185.4
2009 | -- | -- | -- | -- | -- | -- | 192.2
2010 | -- | -- | -- | -- | -- | -- | 146.9
2011 | -- | -- | -- | -- | -- | -- | 90.7
2012 | -- | -- | -- | -- | -- | -- | 92.7
2013 | -- | -- | -- | -- | -- | -- | 124.5
2014 | -- | -- | -- | -- | -- | -- | 153.9
2015 | -- | -- | -- | -- | -- | -- | 160
2016 | -- | -- | -- | -- | -- | -- | 138.2
2017 | -- | -- | -- | -- | -- | -- | 114.4
Subtotal | 5 | -- | -- | -- | -- | -- | 1678.9

## Table 14
Annual Funding BY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2010 $M | Non End Item Recurring Flyaway BY 2010 $M | Non Recurring Flyaway BY 2010 $M | Total Flyaway BY 2010 $M | Total Support BY 2010 $M | Total Program BY 2010 $M
2005 | -- | -- | -- | -- | -- | -- | 61.7
2006 | -- | -- | -- | -- | -- | -- | 109.7
2007 | -- | -- | -- | -- | -- | -- | 122.3
2008 | -- | -- | -- | -- | -- | -- | 187.2
2009 | -- | -- | -- | -- | -- | -- | 191.6
2010 | -- | -- | -- | -- | -- | -- | 144.2
2011 | -- | -- | -- | -- | -- | -- | 87.2
2012 | -- | -- | -- | -- | -- | -- | 87.6
2013 | -- | -- | -- | -- | -- | -- | 115.4
2014 | -- | -- | -- | -- | -- | -- | 140.2
2015 | -- | -- | -- | -- | -- | -- | 143.1
2016 | -- | -- | -- | -- | -- | -- | 121.4
2017 | -- | -- | -- | -- | -- | -- | 98.8
Subtotal | 5 | -- | -- | -- | -- | -- | 1610.4

## Table 15
Annual Funding TY$
2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2009 | -- | 11.1 | -- | -- | 11.1 | -- | 11.1
2010 | 8 | 138.5 | -- | 66.7 | 205.2 | 59.4 | 264.6
2011 | 16 | 240.2 | -- | 128.5 | 368.7 | 122.3 | 491
2012 | 19 | 370.2 | -- | 52.3 | 422.5 | 138.8 | 561.3
2013 | 40 | 518.7 | -- | 9.6 | 528.3 | 156.5 | 684.8
2014 | 38 | 520.1 | -- | 15.2 | 535.3 | 83.5 | 618.8
2015 | 37 | 446.8 | -- | -- | 446.8 | 70.9 | 517.7
2016 | 44 | 526.6 | -- | -- | 526.6 | 79.3 | 605.9
2017 | 37 | 446.9 | -- | -- | 446.9 | 79.3 | 526.2
2018 | 33 | 548 | -- | -- | 548 | 85.2 | 633.2
2019 | 48 | 674.3 | -- | -- | 674.3 | 104.1 | 778.4
2020 | 48 | 657.1 | -- | -- | 657.1 | 109 | 766.1
2021 | 48 | 652.8 | -- | -- | 652.8 | 106 | 758.8
2022 | 48 | 632.7 | -- | -- | 632.7 | 104 | 736.7
2023 | 48 | 663.3 | -- | -- | 663.3 | 108.3 | 771.6
2024 | 48 | 636.3 | -- | -- | 636.3 | 99.5 | 735.8
2025 | 48 | 455.7 | -- | -- | 455.7 | 96.1 | 551.8
2026 | 26 | 213.9 | -- | -- | 213.9 | 61.7 | 275.6
Subtotal | 634 | 8353.2 | -- | 272.3 | 8625.5 | 1663.9 | 10289.4

## Table 16
Annual Funding BY$
2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2010 $M | Non End Item Recurring Flyaway BY 2010 $M | Non Recurring Flyaway BY 2010 $M | Total Flyaway BY 2010 $M | Total Support BY 2010 $M | Total Program BY 2010 $M
2009 | -- | 11 | -- | -- | 11 | -- | 11
2010 | 8 | 134.8 | -- | 64.9 | 199.7 | 57.8 | 257.5
2011 | 16 | 229.3 | -- | 122.5 | 351.8 | 116.8 | 468.6
2012 | 19 | 346.5 | -- | 49 | 395.5 | 129.9 | 525.4
2013 | 40 | 477.5 | -- | 8.8 | 486.3 | 144.2 | 630.5
2014 | 38 | 470.5 | -- | 13.7 | 484.2 | 75.5 | 559.7
2015 | 37 | 397 | -- | -- | 397 | 63 | 460
2016 | 44 | 459.6 | -- | -- | 459.6 | 69.3 | 528.9
2017 | 37 | 383.2 | -- | -- | 383.2 | 68 | 451.2
2018 | 33 | 461.6 | -- | -- | 461.6 | 71.7 | 533.3
2019 | 48 | 557.9 | -- | -- | 557.9 | 86.1 | 644
2020 | 48 | 534 | -- | -- | 534 | 88.6 | 622.6
2021 | 48 | 521.2 | -- | -- | 521.2 | 84.6 | 605.8
2022 | 48 | 496.2 | -- | -- | 496.2 | 81.6 | 577.8
2023 | 48 | 511 | -- | -- | 511 | 83.4 | 594.4
2024 | 48 | 481.5 | -- | -- | 481.5 | 75.3 | 556.8
2025 | 48 | 338.8 | -- | -- | 338.8 | 71.4 | 410.2
2026 | 26 | 156.2 | -- | -- | 156.2 | 45.1 | 201.3
Subtotal | 634 | 6967.8 | -- | 258.9 | 7226.7 | 1412.3 | 8639

## Table 17
Cost Quantity Information
2031 ¦ Procurement ¦ Aircraft Procurement, Army
End Item
Recurring
Flyaway
Fiscal Year | Quantity | (Aligned with
Quantity)
BY 2010
$M
2009 | -- | --
2010 | 8 | 135
2011 | 16 | 201.6
2012 | 19 | 265.3
2013 | 40 | 455.2
2014 | 38 | 514.5
2015 | 37 | 406.2
2016 | 44 | 447.6
2017 | 37 | 398.2
2018 | 33 | 468.8
2019 | 48 | 507.3
2020 | 48 | 535.7
2021 | 48 | 523.3
2022 | 48 | 503.4
2023 | 48 | 514.6
2024 | 48 | 490.9
2025 | 48 | 351.8
2026 | 26 | 248.4
Subtotal | 634 | 6967.8
Low Rate Initial Production
|  | Initial LRIP Decision | Current Total LRIP
Approval Date |  | 10/7/2010 10/7/2010 51 51 ADM ADM 2010 2010 2013 2013
Approved Quantity
Reference
Start Year
End Year
Low Rate Initial Production Rate (LRIP) quantity is 51 in accordance with Acquisition Decision Memorandum (ADM) approved October 7, 2010.

## Table 18
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Memo
United Arab Emirates 30 542.0 Projected Letter of Acceptance (LOA) signature date is October 2013.
United Kingdom 67 2000.0 Projected Letter of Acceptance (LOA) signature date is October 2013.
Nuclear Cost
None

## Table 19
Unit Cost
Unit Cost Report
|  | BY2010 $M | BY2010 $M
Unit Cost |  | Current UCR Baseline (DEC 2010 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 10468.7 |  |  | 10249.4
Quantity | 639 |  |  | 639
Unit Cost | 16.383 |  |  | 16.04 |  | -2.09
Average Procurement Unit Cost (APUC)
Cost | 8856.9 |  |  | 8639
Quantity | 634 |  |  | 634
Unit Cost | 13.97 |  |  | 13.626 |  | -2.46
|  | BY2010 $M | BY2010 $M
Unit Cost |  | Revised Original UCR Baseline (DEC 2010 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 10468.7 |  |  | 10249.4
Quantity | 639 |  |  | 639
Unit Cost | 16.383 |  |  | 16.04 |  | -2.09
Average Procurement Unit Cost (APUC)
Cost | 8856.9 |  |  | 8639
Quantity | 634 |  |  | 634
Unit Cost | 13.97 |  |  | 13.626 |  | -2.46

## Table 20
Unit Cost History
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
[11 empty] | BY2010 $M | [6 empty] | TY $M
[5 empty] | Date | [5 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  |  |  | AUG 2006 | [5 empty] | 11.735 |  |  | 9.945 |  |  |  | 13.445 |  |  | 11.649
APB as of January 2006 |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Revised Original APB |  |  |  |  | DEC 2010 | [5 empty] | 16.383 |  |  | 13.97 |  |  |  | 18.618 |  |  | 16.139
Prior APB |  |  |  |  | JUN 2007 | [5 empty] | 12.008 |  |  | 10.349 |  |  |  | 14.069 |  |  | 12.396
Current APB |  |  |  |  | DEC 2010 | [5 empty] | 16.383 |  |  | 13.97 |  |  |  | 18.618 |  |  | 16.139
Prior Annual SAR |  |  |  |  | DEC 2010 | [5 empty] | 16.358 |  |  | 13.968 |  |  |  | 18.612 |  |  | 16.158
Current Estimate |  |  |  |  | DEC 2011 | [5 empty] | 16.04 |  |  | 13.626 |  |  |  | 18.73 |  |  | 16.229
Initial PAUC Dev Est | Changes | [18 empty] | PAUC Prod Est
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  |  | Oth |  |  | Spt |  | Total
13.445 -0.626 -0.159 0.231 0.000 3.961 0.000 1.766 5.173 18.618
Current SAR Baseline to Current Estimate (TY $M)
PAUC Prod Est |  | Changes | [16 empty] | PAUC Current Est
|  | Econ |  | Qty |  | Sch | Eng |  | Est |  |  | Oth |  |  | Spt |  | Total
18.618 0.318 0.000 0.221 0.000 -0.343 0.000 -0.084 0.112 18.730

## Table 21
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Dev Est | Changes | [15 empty] | APUC Prod Est
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
11.649 -0.614 -0.056 0.233 0.000 3.147 0.000 1.780 4.490 16.139
Current SAR Baseline to Current Estimate (TY $M)
APUC Prod Est | Changes | [15 empty] | APUC Current Est
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  |  | Total
16.139 0.297 0.000 0.223 0.000 -0.345 0.000 -0.084 0.091 16.229
SAR Baseline History
Item/Event |  |  |  | SAR Planning Estimate (PE) | [5 empty] | SAR Development Estimate (DE) |  |  |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone A |  |  |  | N/A | [5 empty] | N/A |  |  |  |  | N/A |  |  | N/A
Milestone B |  |  |  | N/A | [5 empty] | JUN 2006 |  |  |  |  | JUN 2006 |  |  | JUL 2006
Milestone C |  |  |  | N/A | [5 empty] | APR 2010 |  |  |  |  | JUL 2010 |  |  | SEP 2010
IOC |  |  |  | N/A | [5 empty] | JAN 2013 |  |  |  |  | MAY 2013 |  |  | MAY 2013
Total Cost (TY $M) |  |  |  | N/A | [5 empty] | 8093.9 |  |  |  |  | 11896.6 |  |  | 11968.3
Total Quantity |  |  |  | N/A | [5 empty] | 602 |  |  |  |  | 639 |  |  | 639
Prog. Acq. Unit Cost (PAUC) |  |  |  | N/A | [5 empty] | 13.445 |  |  |  |  | 18.618 |  |  | 18.73

## Table 22
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 1664.7 10231.9 -- 11896.6
Previous Changes
Economic |  | 0.1 |  | 15.2 |  | -- |  | 15.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -15.8 |  | 78.5 |  | -- |  | 62.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -81.5 |  | -- |  | -81.5
Subtotal |  | -15.7 |  | 12.2 |  | -- |  | -3.5
Current Changes Economic |  | 15.1 |  | 173.1 |  | -- |  | 188.2
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 141.5 |  | -- |  | 141.5
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 14.8 |  | -297.4 |  | -- |  | -282.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 28.1 |  | -- |  | 28.1
Subtotal |  | 29.9 |  | 45.3 |  | -- |  | 75.2
Total Changes |  | 14.2 |  | 57.5 |  | -- |  | 71.7
CE - Cost Variance |  | 1678.9 |  | 10289.4 |  | -- |  | 11968.3
CE - Cost & Funding |  | 1678.9 |  | 10289.4 |  | -- |  | 11968.3

## Table 23
Summary Base Year 2010 $M
| RDT&E |  | Proc | MILCON | Total
SAR Baseline (Prod Est) Previous Changes |  | 1611.8 | 8856.9 | -- | 10468.7
Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | -15 | 68 | -- | 53
Other |  | -- | -- | -- | --
Support |  | -- | -69.2 | -- | -69.2
Subtotal |  | -15 | -1.2 | -- | -16.2
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | 13.6 | -224.5 | -- | -210.9
Other |  | -- | -- | -- | --
Support |  | -- | 7.8 | -- | 7.8
Subtotal |  | 13.6 | -216.7 | -- | -203.1
Total Changes |  | -1.4 | -217.9 | -- | -219.3
CE - Cost Variance |  | 1610.4 | 8639 | -- | 10249.4
CE - Cost & Funding |  | 1610.4 | 8639 | -- | 10249.4
Previous Estimate: December 2010

## Table 24
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | 15.1
Adjustment for current and prior escalation. (Estimating) |  | -3.4 | -3.5
Increase based on refinement of Program Office Estimate (POE). (Estimating) |  | 17 | 18.3
RDT&E Subtotal |  | 13.6 | 29.9
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A +173.1
Extended procurement buy profile due to annual quantity decrease in FY 2013 President's Budget. (Schedule)
0.0 +141.5
Revised POE due to actual contract cost information. (Estimating) | -213.2 |  |  | -285.9
Adjustment for current and prior escalation. (Estimating) | -11.3 |  |  | -11.5
Adjustment for current and prior escalation. (Support) | -3.1 |  |  | -3.7
Changes in Other Support due to adjustment of training requirements. (Support) | -10.4 |  |  | 1.8
Increase in Initial Spares due to extension of schedule. (Support) | 21.3 |  |  | 30
Procurement Subtotal | -216.7 |  |  | 45.3

## Table 25
Contracts
Appropriation: RDT&E
Contract Name AB3 SDD and Risk and Reduction
Contractor The Boeing Company
Contractor Location Mesa, AZ 85215
Contract Number, Type W58RGZ-05-C-0001, CPIF
Award Date July 14, 2006
Definitization Date July 14, 2006
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
619.3 N/A 5 680.7 N/A 5 597.9 597.9
Variance |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2012) |  |  |  | -10.8 |  |  | -6.4
Previous Cumulative Variances |  |  |  | -3.8 |  |  | -10.9
Net Change |  |  |  | -7 |  |  | 4.5
Cost And Schedule Variance Explanations
The unfavorable net change in the cost variance is due to difficulties associated with instrumentation failures and weather delays which have caused most of the cost variance in structures aircraft testing.
The favorable net change in the schedule variance is due to several accounts being completed.
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.
The difference between the initial contract price target and the current contract price target is due to government directed changes.
The initial contract target price represented initial award of AB3 Risk Reduction and System Development and Demonstration (SDD) in June 2005. The current contract name, contract type, award, definitization, and current contract target price reflect status with the award of the AB3 SDD through production Lot 3 configuration and associated directed changes to that contract.

## Table 26
Deliveries and Expenditures
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 5 |  | 5 |  | 5 | 100%
Production | 3 |  | 3 |  | 634 | 0.47%
Total Program Quantities Delivered | 8 |  | 8 |  | 639 | 1.25%
Expenditures and |  | Appropriations (TY $M)
Total Acquisition Cost | 11968.3 | Years Appropriated |  |  | 8
Expenditures To Date | 1151.7 | Percent Years Appropriated |  |  | 36.36%
Percent Expended | 9.62% | Appropriated to Date |  |  | 2315.9
Total Funding Years | 22 | Percent Appropriated |  |  | 19.35%
This data is as of December 31, 2011.

## Table 27
Operating and Support Cost
Assumptions And Ground Rules
Assumes the fielding of 690 aircraft, each flying 203.4 hours per year. The estimate is based on a 20-year service life. The Mean Time Between Failure (MTBF) goal for the aircraft system is 22 hours at maturity (50,000) hours. The costs are updated annually to reflect the Operating and Support Management Information System (OSMIS) database. The Operating and Support (O&S) Cost estimate is based on the Program Office Estimate dated December 2011. The Longbow Apache is the antecedent aircraft to the Apache Block III.
AB3 O&S costs = Total Unitized Cost * Fleet Size * Fleet Life
$33638.9 M = $2437.6K * 690 * 20
Longbow O&S costs = Total Unitized Cost * Remaining Flying Hours
$15350.4M = $2285.3K * 6717
Costs BY2010 $K
Cost Element | AB3A REMANUFACTURE Avg Annual Cost Per AB3 Aircraft |  | Longbow Apache Avg Annual Cost Per Longbow Aircraft
Unit-Level Manpower |  | 1076 |  | 855.7
Unit Operations |  | 795.2 |  | 912
Maintenance |  | 94.8 |  | 54.5
Sustaining Support |  | 89.7 |  | 28.3
Continuing System Improvements |  | 182.1 |  | 234
Indirect Support |  | 199.8 |  | 201
Other |  | 0 |  | 0
Total Unitized Cost (Base Year 2010 $) |  | 2437.6 |  | 2285.5
Total O&S Costs $M | AB3A REMANUFACTURE |  | Longb | ow Apache
Base Year |  | 33638.9 |  | 15350.4
Then Year |  | 45781.5 |  | 17869
O&S costs include AB3A as well as AB3B.
Demil costs are included in this O&S estimate. |  | $3,885 to demil one AB3 aircraft.
Reduction of Total O&S Costs is due to estimation error. Too many total soldiers were included in the original personnel estimate for purposes of training. This error encompassed both the reserve and active component formations.