## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-456
Next Generation Operational Control System (GPS OCX)
As of FY 2015 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations |  | 3
Program Information |  | 4
Responsible Office |  | 4
References |  | 4
Mission and Description |  | 5
Executive Summary |  | 6
Threshold Breaches |  | 8
Schedule |  | 9
Performance |  | 11
Track to Budget |  | 18
Cost and Funding |  | 19
Low Rate Initial Production |  | 23
Foreign Military Sales |  | 24
Nuclear Costs |  | 24
Unit Cost |  | 25
Cost Variance |  | 28
Contracts |  | 31
Deliveries and Expenditures |  | 32
Operating and Support Cost |  | 33

## Table 3
Common Acronyms and Abbreviations
Acq O&M - Acquisition-Related Operations and Maintenance APB - Acquisition Program Baseline
APPN - Appropriation
APUC - Average Procurement Unit Cost BA - Budget Authority/Budget Activity
BY - Base Year
DAMIR - Defense Acquisition Management Information Retrieval Dev Est - Development Estimate
DoD - Department of Defense DSN - Defense Switched Network Econ - Economic
Eng - Engineering Est - Estimating
FMS - Foreign Military Sales FY - Fiscal Year
IOC - Initial Operational Capability
$K - Thousands of Dollars
LRIP - Low Rate Initial Production
$M - Millions of Dollars MILCON - Military Construction N/A - Not Applicable
O&S - Operating and Support Oth - Other
PAUC - Program Acquisition Unit Cost PB - President’s Budget
PE - Program Element Proc - Procurement
Prod Est - Production Estimate QR - Quantity Related
Qty - Quantity
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
Sch - Schedule Spt - Support
TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting

## Table 4
Program Information
Program Name
Next Generation Operational Control System (GPS OCX)
DoD Component
Air Force
Responsible Office
Responsible Office
Col William Cooley | Phone | 310-653-3001
483 N. Aviation Blvd | Fax | 310-653-3005
El Segundo, CA 90245 | DSN Phone | 633-3001
| DSN Fax | 633-3005
william.cooley@us.af.mil | Date Assigned | June 13, 2013
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated November 19, 2012
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated November 19, 2012

## Table 5
Mission and Description
The Global Positioning System (GPS) is a space based positioning, navigation, and timing distribution system, which operates through weather and electromagnetic environments (jamming, spoofing, etc.). GPS supports both civil and military users in air, space, sea, and land operations. GPS is a satellite-based radio navigation system that serves military and civil users worldwide. GPS users process satellite signals to determine accurate position, velocity, and time. GPS must comply with 10 United States Code (USC) Section 2281 which requires that the Secretary of Defense ensures the continued sustainment and operation of GPS for military and civilian purposes and 51 USC Section 50112, which requires that GPS complies with certain standards and facilitates international cooperation.
The GPS Next Generation Operational Control System (OCX) program procures and fields a modernized satellite command and control (C2) system which replaces the current ground control system for all legacy and new GPS satellites. OCX implements a modern flexible architecture with built-in robust information assurance to address emerging cyber threats. The Air Force is taking a block approach to develop OCX with each block delivering upgrades as they become available.
The OCX program of record consists of 2 block deliverables: Block 1, and Block 2. OCX Block 0, a subset of Block 1, will allow OCX to support the launch and checkout of GPS III satellites. OCX Block 1 replaces the existing legacy GPS C2 system and fields the operational capability to control all legacy satellites (GPS IIR, IIR-M, and IIF) and control existing signals (L1 C/A, L1P(Y), L2P(Y)). OCX Block 1 also adds the operational capability to command and control the GPS III satellites and the modernized civil signals (L2C and L5). OCX Block 2 adds operational control of the new international open/civil L1C signal in compliance with 2004 European Union-United States agreement and adds control of the modernized Military Code (M-Code) signal.

## Table 6
Executive Summary
Since approval of Milestone B in November 2012, the program has continued with design and development of OCX hardware and software. The prime contractor successfully completed the hardware Critical Design Reviews (CDRs) for the monitoring station and legacy ground antenna elements, as well as the CDR for the Global Positioning System (GPS) III Launch and Checkout System ((LCS), also known as Block 0). The prime contractor developed and completed the information assurance hardened software infrastructure to protect against emerging cyber threats. This software is the foundation upon which all remaining OCX software will be built. The remaining Block 0 software necessary to launch and check out GPS III satellites completed coding, is now in software integration, and remains on track for delivery by the APB threshold of May 2015.
OCX participated in two successful space-to-ground launch readiness exercises and a hardware compatibility test with GPS III. These exercises and test demonstrated that OCX software could perform basic launch, checkout, command and control, and anomaly resolution of the GPS III satellites.
The prime contractor completed multiple design reviews. In June 2013, the contractor conducted a CDR for LCS (Block 0). Overall, the design artifacts assessed by the Government team demonstrated that the contractor’s design and software architecture were adequate and will meet requirements.
In addition, the contractor held a Hardware CDR for the OCX Monitor Station/Legacy Ground Antenna (MS/LGA).
The design and hardware architecture showed an improvement in the performance and security of the program’s continental United States and overseas hardware and software assets. This milestone is a gate for
production readiness and supports production and 17 worldwide site installations that will begin next year. The GPS monitoring station receiver anti-tamper design was approved by the Government. This, in conjunction with the successful monitoring station CDR, enabled the start of manufacturing and installation for 17 worldwide monitor station sites.
In spite of these accomplishments, the prime contractor has struggled with software development, resulting in significant cost overruns and schedule delays to both the Block 0 LCS capability, as well as the Block 1 capability slated to replace the legacy GPS ground segment. Incomplete systems engineering resulted in significant rework during software coding. Information assurance implementation proved to be more difficult than anticipated.
Additionally, the contractor experienced delays due to the complexity in configuring and maintaining the test/operational infrastructure. The cumulative effect of these issues resulted in four to six months delay to contractor forecasted delivery. The contractor has applied lessons learned and corrective actions to resolve these issues.
Even with these schedule slips, the prime contractor forecasts delivery within the APB schedule thresholds. Due to the cost and schedule variances, the program team is implementing an Over Target Baseline (OTB) and Over Target Schedule (OTS), planned to complete in 2014. After the OTB is complete, the program office will be able to better evaluate and estimate any impact to the APB schedule.
In November 2012, in conjunction with the Milestone B decision, certification was made pursuant to section 2366b of title 10, United States Code. Based on program maturity, GPS OCX was deemed ready to enter the Engineering and Manufacturing phase. The Under Secretary of Defense for Acquisition, Technology and Logistics certified provisions (a)(1)(B) and (a)(1)(D) (with waivers) in accordance with subsection (d) on the basis that the program was not fully funded in the FY 2013 PB and the associated Future Years Defense Program. The certification requirement for these two provisions has not yet been met, and the Department will continue to review the GPS OCX program at least annually until the certification components are satisfied.
Overall, OCX has made significant progress in 2013, but has also experienced challenges in software development, resulting in cost and schedule overruns. Despite these overruns, the program remains on track to meet all APB

## Table 7
commitments.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Development Contract Award | FEB 2010 | FEB 2010 | FEB 2010 | FEB 2010
Block 1 and 2 PDR | AUG 2011 | AUG 2011 | AUG 2011 | AUG 2011
Milestone B | NOV 2012 | NOV 2012 | NOV 2012 | NOV 2012
Block 0 (LCS Delivery) | NOV 2014 | NOV 2014 | MAY 2015 | APR 2015
Milestone C | OCT 2015 | OCT 2015 | APR 2016 | APR 2016
Block 1 RTO | OCT 2016 | OCT 2016 | OCT 2017 | SEP 2017
Block 2 RTO | JUN 2017 | JUN 2017 | JUN 2018 | APR 2018
Change Explanations
(Ch-1) The current estimate of Block 0 (LCS Delivery) was delayed from November 2014 to April 2015; the current estimate of Milestone C was delayed from October 2015 to April 2016; the current estimate of Block 1 RTO was delayed from October 2016 to September 2017; and the current estimate of Block 2 RTO was delayed from June 2017 to April 2018 due to an increased level of unplanned work and rework. The contractor struggled with incomplete systems engineering during coding, information assurance being more difficult than expected, and challenges with configuration management of test/operational infrastructure. The cumulative effects resulted in changes to the Block 0, 1, 2 and Milestone C estimates.
Memo
RTO will be achieved when the Control Segment can support GPS III SV01-08 and operational Block II satellites, can monitor broadcast GPS navigation signals, and can support NAVWAR mission planning by JSpOC. At RTO, the system is turned over to the operational community.

## Table 10
Acronyms and Abbreviations
JSpOC - Joint Space Operations Center LCS - Launch and Checkout System NAVWAR - Navigation Warfare
PDR - Preliminary Design Review
RTO - Ready to Transition to Operations SV - Space Vehicle

## Table 11
Performance
Characteristics | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Backward | All | All | All | TBD | All
Compatibility | modifications | modifications | modifications |  | modifications
| made to the | made to the | made to the |  | made to the
| existing | existing | existing |  | existing
| GPS Space | GPS Space | GPS Space |  | GPS Space
| Segment | Segment | Segment |  | Segment
| and Control | and Control | and Control |  | and Control
| Segment | Segment | Segment |  | Segment
| shall allow | shall allow | shall allow |  | shall allow
| the | the | the |  | the
| continued | continued | continued |  | continued
| operation of | operation of | operation of |  | operation of
| existing IS- | existing IS- | existing IS- |  | existing IS-
| GPS-200, IS- | GPS-200, IS- | GPS-200, IS- |  | GPS-200, IS-
| GPS-700, IS- | GPS-700, IS- | GPS-700, IS- |  | GPS-700, IS-
| GPS-705 | GPS-705 | GPS-705 |  | GPS-705
| and SS- | and SS- | and SS- |  | and SS-
| GPS-001 | GPS-001 | GPS-001 |  | GPS-001
| compliant | compliant | compliant |  | compliant
| UE and | UE and | UE and |  | UE and
| continued | continued | continued |  | continued
| operation of | operation of | operation of |  | operation of
| legacy | legacy | legacy |  | legacy
| receivers (to | receivers (to | receivers (to |  | receivers (to
| include | include | include |  | include
| Federal | Federal | Federal |  | Federal
| augmentation | augmentation | augmentation |  | augmentation
| system | system | system |  | system
| receivers) | receivers) | receivers) |  | receivers)
| IAW | IAW | IAW |  | IAW
| performance | performance | performance |  | performance
| meeting the | meeting the | meeting the |  | meeting the
| APB | APB | APB |  | APB
| Precise | Precise | Precise |  | Precise
| Positioning | Positioning | Positioning |  | Positioning
| Service | Service | Service |  | Service
| Performance | Performance | Performance |  | Performance
| Standard | Standard | Standard |  | Standard
| and GPS | and GPS | and GPS |  | and GPS
| Positioning | Positioning | Positioning |  | Positioning
| Service | Service | Service |  | Service
| Performance | Performance | Performance |  | Performance
| Standard, | Standard, | Standard, |  | Standard,
| and Federal | and Federal | and Federal |  | and Federal

## Table 12
| augmentation | augmentation | augmentation |  | augmentation
| system | system | system |  | system
| specifica- | specifica- | specifica- |  | specificat-
| tions for the | tions for the | tions for the |  | ions for the
| Local Area | Local Area | Local Area |  | Local Area
| Augmenta- | Augmenta- | Augmenta- |  | Augmenta-
| tion System, | tion System, | tion System, |  | tion System,
| Wide Area | Wide Area | Wide Area |  | Wide Area
| Augmenta- | Augmenta- | Augmenta- |  | Augmenta-
| tion System, | tion System, | tion System, |  | tion System,
| Nationwide | Nationwide | Nationwide |  | Nationwide
| Differential | Differential | Differential |  | Differential
| GPS, and | GPS, and | GPS, and |  | GPS, and
| Maritime | Maritime | Maritime |  | Maritime
| Differential | Differential | Differential |  | Differential
| GPS. | GPS. | GPS. |  | GPS.
[Threshold =
Objective]
Availability of Position | UEE = 0.8 m | UEE = 0.8 m | a. 1.2 m | TBD | UEE = 0.8 m
Accuracy a. b. | rms a. 4.5 m | rms a. 4.5 m | (95%) @ |  | rms a. 4.5 m
Horizontal c.d. Vertical | (95%) @ | (95%) @ | 90% |  | (95%) @
| 90% | 90% | availability |  | 90%
| availability | availability | any lat/long |  | availability
| any lat/long | any lat/long | b. 1.2 m |  | any lat/long
| b. 4.0 m | b. 4.0 m | (95%) @ |  | b. 4.0 m
| (95%) @ | (95%) @ | 99.9% |  | (95%) @
| 99.9% | 99.9% | availability |  | 99.9%
| availability | availability | global |  | availability
| global | global | average c. |  | global
| average c. | average c. | 1.9 m (95%) |  | average c.
| 7.0 m (95%) | 7.0 m (95%) | @ 90% |  | 7.0 m (95%)
| @ 90% | @ 90% | availability |  | @ 90%
| availability | availability | any lat/long |  | availability
| any lat/long | any lat/long | d. 1.9 m |  | any lat/long
| d. 7.0 m | d. 7.0 m | (95%) @ |  | d. 7.0 m
| (95%) @ | (95%) @ | 99.9% |  | (95%) @
| 99.9% | 99.9% | availability |  | 99.9%
| availability | availability | global |  | availability
| global | global | average |  | global
| average | average | Note: (a) and |  | average
| UEE = 2.6 m | UEE = 2.6 m | (c) values |  | UEE = 2.6 m
| rms a. 11.5 | rms a. 11.5 | equal 1 m |  | rms a. 11.5
| m (95%) @ | m (95%) @ | SEP Note: |  | m (95%) @
| 90% | 90% | no UEE |  | 90%
| availability | availability | assumed for |  | availability
| any lat/long | any lat/long | objective |  | any lat/long
| b. 11.5 m | b. 11.5 m | because |  | b. 11.5 m
| (95%) @ | (95%) @ | requirement |  | (95%) @
| 99.9% | 99.9% | is stated in |  | 99.9%
| availability | availability | FCS ORD. |  | availability
| global | global |  |  | global

## Table 13
| average c. 17.7 m (95%) @ 90% availability any lat/long d. 17.7 m (95%) @ 99.9% availability global average. | average c. 17.7 m (95%) @ 90% availability any lat/long d. 17.7 m (95%) @ 99.9% availability global average. |  |  | average c. 17.7 m (95%) @ 90% availability any lat/long d. 17.7 m (95%) @ 99.9% availability global average.
Position and Time Transfer Integrity | GPS III SV 1- 8 shall not transmit MSI to the user with a probability greater than 0.0001 per hour. | GPS III SV 1- 8 shall not transmit MSI to the user with a probability greater than 0.0001 per hour. | GPS III SV 1- 8 shall not transmit MSI to the user with a probability greater than 0.0000001 per hour. | TBD | GPS III SV 1- 8 shall not transmit MSI to the user with a probability greater than 0.0001 per hour.
Availability of Dynamic Time Transfer Accuracy | UEE = 0.8 m rms Any lat/long 15 nanoseconds (ns) (95%) @ 90% availability Global Average 15 ns (95%) @ 99.9% availability UEE = 2.6 m rms Any lat/long 40 ns (95%) @ 90% availability Global Average 50 ns (95%) | UEE = 0.8 m rms Any lat/long 15 ns (95%) @ 90% availability Global Average 15 ns (95%) @ 99.9% availability UEE = 2.6 m rms Any lat/long 40 ns (95%) @ 90% availability Global Average 50 ns (95%) | Any lat/long 4.5 ns (95%) @ 90% availability Global Average 4.5 ns (95%) @ 99.9% availability Note: no UEE assumed for objective because requirement is derived from the FCS ORD Objective SEP accuracy requirement | TBD | UEE = 0.8 m rms any lat/long 15 ns (95%) @ 90% availability Global Average 15 ns (95%) @ 99.9% availability UEE = 2.6 m rms any lat/long 40 ns (95%) @ 90% availability Global Average 50 ns (95%).
Availability of Static Time Transfer Accuracy | 3.0 ns (95%) @ > 99.9% availability | 3.0 ns (95%) @ > 99.9% availability | 1.0 ns (95%) @ > 99.9% availability | TBD | 3.0 ns (95%) @ > 99.9% availability.
Net-Ready KPP | The system must fully support execution of joint critical | The system must fully support execution of joint critical | The system must fully support execution of all | TBD | The system must fully support execution of joint critical

## Table 14
operational | operational | operational | operational
activities | activities | activities | activities
and | and | and | and
information | information | information | information
exchanges | exchanges | exchanges | exchanges
identified in | identified in | identified in | identified in
the DoD | the DoD | DoD | the DoD
Enterprise | Enterprise | Enterprise | Enterprise
Architecture | Architecture | Architecture | Architecture
and solution | and solution | and solution | and solution
architectures | architectures | architectures | architectures
based on | based on | based on | based on
integrated | integrated | integrated | integrated
DoD AF | DoD AF | DoD AF | DoD AF
content, and | content, and | content, and | content, and
must satisfy | must satisfy | must satisfy | must satisfy
the technical | the technical | the technical | the technical
requirements | requirements | requirements | requirements
for transition | for transition | for transition | for transition
to Net- | to Net- | to Net- | to Net-
Centric | Centric | Centric | Centric
military | military | military | military
operations | operations | operations | operations
to include: 1) | to include: 1) | to include 1) | to include: 1)
Solution | Solution | Solution | Solution
architecture | architecture | architecture | architecture
products | products | products | products
compliant | compliant | compliant | compliant
with DoD | with DoD | with DoD | with DoD
Enterprise | Enterprise | Enterprise | Enterprise
Architecture | Architecture | Architecture | Architecture
based on | based on | based on | based on
integrated | integrated | integrated | integrated
DoD AF | DoD AF | DoD AF | DoD AF
content, | content, | content, | content,
including | including | including | including
specified | specified | specified | specified
operationally | operationally | operationally | operationally
effective | effective | effective | effective
information | information | information | information
exchanges | exchanges | exchanges | exchanges
2) Compliant | 2) Compliant | 2) Compliant | 2) Compliant
with Net- | with Net- | with Net– | with Net-
Centric Data | Centric Data | Centric Data | Centric Data
Strategy, | Strategy, | Strategy and | Strategy,
and Net- | and Net- | Net-Centric | and Net-
centric | centric | Services | centric
Services | Services | Strategy, | Services
Strategy and | Strategy and | and the | Strategy and
the | the | principles | the
principles | principles | and rules | principles

## Table 15
and rules | and rules | identified in | and rules
identified in | identified in | the DoD | identified in
the DoD | the DoD | IEA, | the DoD
IEA, | IEA, | excepting | IEA,
excepting | excepting | tactical and | excepting
tactical and | tactical and | non-IP | tactical and
non-IP | non-IP | communic- | non-IP
communic- | communic- | ations 3) | communicat-
ations 3) | ations 3) | Compliant | ions 3)
Compliant | Compliant | with GIG | Compliant
with GIG | with GIG | Technical | with GIG
Technical | Technical | Guidance to | Technical
Guidance to | Guidance to | include IT | Guidance to
include IT | include IT | Standards | include IT
Standards | Standards | identified in | Standards
identified in | identified in | the TV-1 and | identified in
the TV-1 and | the TV-1 and | implementa- | the TV-1 and
implement- | implementa- | tion | implementat-
ation | tion | guidance of | ion guidance
guidance of | guidance of | GESPs, | of GESPs
GESPs | GESPs | necessary to | necessary to
necessary to | necessary to | meet all | meet all
meet all | meet all | operational | operational
operational | operational | requirements | requirements
requirements | requirements | specified in | specified in
specified in | specified in | the DoD | the DoD
the DoD | the DoD | Enterprise | Enterprise
Enterprise | Enterprise | Architecture | Architecture
Architecture | Architecture | and solution | and solution
and solution | and solution | architecture | architecture
architecture | architecture | views 4) | views 4)
views 4) | views 4) | Information | Information
Information | Information | assurance | assurance
assurance | assurance | requirements | requirements
requirements | requirements | including | including
including | including | availability, | availability,
availability, | availability, | integrity, | integrity,
integrity, | integrity, | authentica- | authenticati-
authentic- | authentica- | tion, | on,
ation, | tion, | confidential- | confidential-
confidential- | confidential- | ity, and non- | ity, and non-
ity, and non- | ity, and non- | repudiation, | repudiation,
repudiation, | repudiation, | and | and
and | and | issuance of | issuance of
issuance of | issuance of | an ATO by | an IATO or
an IATO or | an IATO or | the DAA, | ATO by the
ATO by the | ATO by the | and 5) | DAA, and 5)
DAA, and 5) | DAA, and 5) | Support- | Supportabili-
Support- | Support- | ability | ty
ability | ability | requirements | requirements
requirements | requirements | to include | to include

## Table 16
| to include SAASM, Spectrum, and JTRS requir- ements. | to include SAASM, Spectrum, and JTRS require- ments. | SAASM, Spectrum and JTRS require- ments. |  | SAASM, Spectrum, and JTRS requir- ements.
Sustainment--Materiel | The | The | The | TBD | The
Availability | achievement | achievement | achievement |  | achievement
| of the | of the | of the |  | of the
| Availability | Availability | Availability |  | Availability
| of Position | of Position | of Position |  | of Position
| Accuracy | Accuracy | Accuracy |  | Accuracy
| KPP and | KPP and | KPP and |  | KPP and
| Time | Time | Time |  | Time
| Transfer | Transfer | Transfer |  | Transfer
| Accuracy | Accuracy | Accuracy |  | Accuracy
| KPP | KPP | KPP |  | KPP
| Thresholds. | Thresholds. | Thresholds. |  | Thresholds.
[Threshold =
Objective]
Requirements Source
GPS III Capability Development Document (CDD) dated September 17, 2009
Change Explanations
None
Memo
This performance baseline is for OCX and was derived from the system-level Capability Development Document (CDD) requirements. The GPS III program will track their cost, schedule, and performance separately
in its own baseline.

## Table 17
Acronyms and Abbreviations
AF - Air Force
ATO - Authority To Operate
DAA - Designated Approval Authority FCS - Future Combat System
GESP - GIG Enterprise Service Profiles GIG - Global Information Grid
GPS - Global Positioning System IATO - Interim Authority to Operate IAW - In Accordance With
IEA - Information Enterprise Architecture IP - Internet Protocol
IS - Interface Specifications
JTRS - Joint Tactical Radio System KPP - Key Performance Parameter lat - Latitude
long - Longitude m - meter
MSI - Misleading SIS Information ns - nanosecond
ORD - Operational Requirements Document RMS - root-mean-square
SAASM - Selective Availability/Anti-Spoofing Module SEP - Spherical Error Probable
SIS - Signal in Space
SS - System Specifications SV - Space Vehicle
TV - Technical View UE - User Equipment
UEE - User Equipment Error

## Table 18
Track to Budget
RDT&E
Appn | BA | PE
Air Force 3600 | 7 | 0603421F
Project |  | Name
4993 |  | GPS III | (Shared) | (Sunk)
Air Force 3600 | 7 | 0603423F
Project |  | Name
67A021 |  | Global Positioning System III - Operational Control Segment (OCX)
67A025 |  | GPS Enterprise Integrator

## Table 19
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
|  | BY2012 $M | [6 empty] | BY2012 $M
Appropriation |  | SAR Baseline Dev Est |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Dev Est | Current APB Development Objective |  |  | Current Estimate
RDT&E |  | 3347.2 |  |  |  | 3347.2 |  | 3681.9 |  | 3341.8 |  | 3413 | 3413 | 3412.4
Procurement |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Flyaway |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Recurring |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Non Recurring |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Support |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Other Support |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Initial Spares |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 3347.2 |  |  |  | 3347.2 |  | N/A |  | 3341.8 |  | 3413 | 3413 | 3412.4
Confidence Level for Current APB Cost 60% -
The Air Force Service Cost Position for the OCX Program is at the mean of the cost estimate distribution. It takes into consideration all relevant program risks, providing sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external interference.
Quantity |  |  | SAR Baseline Dev Est |  |  |  | Current APB Development |  |  |  | Current Estimate
RDT&E |  |  | 1 |  |  |  | 1 |  |  |  | 1
Procurement |  |  | 0 |  |  |  | 0 |  |  |  | 0
Total |  |  | 1 |  |  |  | 1 |  |  |  | 1

## Table 20
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2015 President's Budget / December 2013 SAR (TY$ M)
In addition to above, the 2015 PB request includes $41.5M of the Other Procurement Air Force funding. These funds are not a part of the approved OCX APB and will be transferred to Operations and Maintenance in a future budget cycle.
Appropriation |  | Prior | FY2014 |  |  | FY2015 |  |  | FY2016 |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  |  | To Complete |  | Total
RDT&E | 2006.1 |  |  | 373.1 |  |  | 299.8 |  |  | 282.1 |  | 212.4 |  |  | 118.3 |  |  | 120.6 |  |  | 0 |  | 3412.4
Procurement | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
MILCON | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
PB 2015 Total | 2006.1 |  |  | 373.1 |  |  | 299.8 |  |  | 282.1 |  | 212.4 |  |  | 118.3 |  |  | 120.6 |  |  | 0 |  | 3412.4
PB 2014 Total | 2068.1 |  |  | 383.5 |  |  | 303.5 |  |  | 285.4 |  | 214.5 |  |  | 119.3 |  |  | 38.1 |  |  | 0 |  | 3412.4
Delta | -62 |  |  | -10.4 |  |  | -3.7 |  |  | -3.3 |  | -2.1 |  |  | -1 |  |  | 82.5 |  |  | 0 |  | 0
Quantity | Undistributed |  |  |  | Prior |  |  | FY2014 |  | FY2015 | FY2016 |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  | To Complete |  |  | Total
Development | 1 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 1
Production | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
PB 2015 Total | 1 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 1
PB 2014 Total | 1 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 1
Delta | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0

## Table 21
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2007 | -- | -- | -- | -- | -- | -- | 168.4
2008 | -- | -- | -- | -- | -- | -- | 249.5
2009 | -- | -- | -- | -- | -- | -- | 289.6
2010 | -- | -- | -- | -- | -- | -- | 288.4
2011 | -- | -- | -- | -- | -- | -- | 353.6
2012 | -- | -- | -- | -- | -- | -- | 347
2013 | -- | -- | -- | -- | -- | -- | 309.6
2014 | -- | -- | -- | -- | -- | -- | 373.1
2015 | -- | -- | -- | -- | -- | -- | 299.8
2016 | -- | -- | -- | -- | -- | -- | 282.1
2017 | -- | -- | -- | -- | -- | -- | 212.4
2018 | -- | -- | -- | -- | -- | -- | 118.3
2019 | -- | -- | -- | -- | -- | -- | 120.6
Subtotal | 1 | -- | -- | -- | -- | -- | 3412.4

## Table 22
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
2007 | -- | -- | -- | -- | -- | -- | 181
2008 | -- | -- | -- | -- | -- | -- | 262.8
2009 | -- | -- | -- | -- | -- | -- | 301.1
2010 | -- | -- | -- | -- | -- | -- | 296.1
2011 | -- | -- | -- | -- | -- | -- | 356.3
2012 | -- | -- | -- | -- | -- | -- | 343.6
2013 | -- | -- | -- | -- | -- | -- | 301.1
2014 | -- | -- | -- | -- | -- | -- | 356.9
2015 | -- | -- | -- | -- | -- | -- | 281.6
2016 | -- | -- | -- | -- | -- | -- | 259.9
2017 | -- | -- | -- | -- | -- | -- | 191.9
2018 | -- | -- | -- | -- | -- | -- | 104.8
2019 | -- | -- | -- | -- | -- | -- | 104.7
Subtotal | 1 | -- | -- | -- | -- | -- | 3341.8
The total Research Development Test and Evaluation (RDT&E) costs listed in the table above does not include
the contribution of $82.3M (Then Year dollars (TY$)) of civil funding to support OCX . The civil funding contribution in TY$ is as follows:
FY 2011: $13.2M
FY 2012: $28.2M
FY 2013: $27.8M
FY 2014: $9.5M
FY 2015: $2.8M
FY 2016: $0.4M
FY 2017: $0.4M

## Table 23
Low Rate Initial Production
There is no LRIP for this Program.

## Table 24
Foreign Military Sales
None
Nuclear Costs
None

## Table 25
Unit Cost
Unit Cost Report
|  | BY2012 $M | BY2012 $M
Unit Cost |  | Current UCR Baseline (NOV 2012 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 3347.2 |  |  | 3341.8
Quantity | 1 |  |  | 1
Unit Cost | 3347.2 |  |  | 3341.8 |  | -0.16
Average Procurement Unit Cost (APUC)
Cost | 0 |  |  | 0
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  | --
|  | BY2012 $M | BY2012 $M
Unit Cost |  | Original UCR Baseline (NOV 2012 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 3347.2 |  |  | 3341.8
Quantity | 1 |  |  | 1
Unit Cost | 3347.2 |  |  | 3341.8 |  | -0.16
Average Procurement Unit Cost (APUC)
Cost | 0 |  |  | 0
Quantity Unit Cost | 0 -- |  |  | 0 -- |  | --
PAUC is based on RDT&E costs and quantities only.

## Table 26
Unit Cost History
[7 empty] | BY2012 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | NOV 2012 |  |  |  | 3347.2 |  | N/A |  |  | 3413 |  | N/A
APB as of January 2006 |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current APB |  |  | NOV 2012 |  |  |  | 3347.2 |  | N/A |  |  | 3413 |  | N/A
Prior Annual SAR |  |  | DEC 2012 |  |  |  | 3335.7 |  | N/A |  |  | 3412.4 |  | N/A
Current Estimate |  |  | DEC 2013 |  |  |  | 3341.8 |  | N/A |  |  | 3412.4 |  | N/A
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Dev Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
3413.000 -3.200 0.000 0.000 0.000 2.600 0.000 0.000 -0.600 3412.400

## Table 27
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes | [10 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
0.000 -- -- -- -- -- -- -- -- 0.000
APUC Unit Cost History is not available: No Initial APUC Estimate calculated due to lack of defined quantities.
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  | SAR Development Estimate (DE) |  |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | NOV 2012 |  |  |  | N/A |  |  | NOV 2012
Milestone C |  |  | N/A |  |  | OCT 2015 |  |  |  | N/A |  |  | APR 2016
IOC |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Total Cost (TY $M) |  |  | N/A |  |  | 3413 |  |  |  | N/A |  |  | 3412.4
Total Quantity |  |  | N/A |  |  | 1 |  |  |  | N/A |  |  | 1
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  | 3413 |  |  |  | N/A |  |  | 3412.4

## Table 28
Cost Variance
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 3413 | -- | -- | 3413
Previous Changes
Economic | 11.9 | -- | -- | 11.9
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -12.5 | -- | -- | -12.5
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -0.6 | -- | -- | -0.6
Current Changes
Economic | -15.1 | -- | -- | -15.1
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 15.1 | -- | -- | 15.1
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -- | -- | --
Total Changes | -0.6 | -- | -- | -0.6
CE - Cost Variance | 3412.4 | -- | -- | 3412.4
CE - Cost & Funding | 3412.4 | -- | -- | 3412.4

## Table 29
Summary Base Year 2012 $M
| RDT&E |  | Proc | MILCON | Total
SAR Baseline (Dev Est) Previous Changes |  | 3347.2 | -- | -- | 3347.2
Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | -11.5 | -- | -- | -11.5
Other |  | -- | -- | -- | --
Support |  | -- | -- | -- | --
Subtotal |  | -11.5 | -- | -- | -11.5
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | 6.1 | -- | -- | 6.1
Other |  | -- | -- | -- | --
Support |  | -- | -- | -- | --
Subtotal |  | 6.1 | -- | -- | 6.1
Total Changes |  | -5.4 | -- | -- | -5.4
CE - Cost Variance |  | 3341.8 | -- | -- | 3341.8
CE - Cost & Funding |  | 3341.8 | -- | -- | 3341.8
Previous Estimate: December 2012

## Table 30
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -15.1
Adjustment for current and prior escalation. (Estimating) | 6.1 | 6.4
Increased costs for OCX development. (Estimating) | 72.4 | 83.4
Sequestration reductions for FY 2013. (Estimating) | -28.1 | -28.9
Congressional reductions for FY 2013. (Estimating) | -21.4 | -22
Budgetary allocation for Small Business Innovative Research. (Estimating) | -10.8 | -11.1
Non-pay inflation adjustment. (Estimating) | -2.2 | -2.3
Congressional reductions for Federally Funded Research and Development Centers for -0.4 -0.4
Additional Congressional reductions for FY 2014. (Estimating) | -9.5 | -10
RDT&E Subtotal | 6.1 | 0
FY 2014. (Estimating)

## Table 31
Contracts
Appropriation: RDT&E
Contract Name OCX Phase B Contract
Contractor Raytheon (Intelligence and Information Systems)
Contractor Location 16800 E Centre Tech Pkwy Aurora, CO 80011
Contract Number, Type FA8807-10-C-0001, CPAF
Award Date February 25, 2010
Definitization Date February 25, 2010
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
886.4 N/A 1 972.1 N/A 1 1469.1 1440.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to increases in scope such as Technical Baseline efforts which include adding an interim Block 0 delivery, Request for Equitable Adjustments for GPS III system and satellite simulators, engineering studies, and Engineering Change Proposals offset by affordability efforts.
Variance |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/26/2014) |  |  |  | -226.8 |  |  |  | -39.6
Previous Cumulative Variances |  |  |  | -128.2 |  |  |  | -17.8
Net Change |  |  |  | -98.6 |  |  |  | -21.8
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to an increased level of unplanned work and rework. The contractor struggled with incomplete systems engineering during coding, information assurance being more difficult than expected, and challenges with configuration and management of test/operational infrastructure.
The unfavorable net change in the schedule variance is due to an increased level of unplanned work and rework. The contractor struggled with incomplete systems engineering during coding, information assurance being more difficult than expected, and challenges with configuration and management of test/operational infrastructure.
Contract Comments
For tracking purposes, initial contract price information is based on the initial monthly contractor's performance report ending March 28, 2010.

## Table 32
Deliveries and Expenditures
Delivered to Date | Plan to Da | te | Actual to Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 1 | 0%
Production | 0 |  | 0 |  | 0 | --
Total Program Quantity Delivered | 0 |  | 0 |  | 1 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost | 3412.4 | Years Appropriated |  |  | 8
Expended to Date | 1955.1 | Percent Years Appropriated |  |  | 61.54%
Percent Expended | 57.29% | Appropriated to Date |  |  | 2379.2
Total Funding Years | 13 | Percent Appropriated |  |  | 69.72%
The above data is current as of 2/28/2014.

## Table 33
Operating and Support Cost
GPS OCX
Assumptions and Ground Rules
Cost Estimate Reference:
Estimated Costs are part of the Service Cost Estimate supported by the Air Force Cost Analysis Agency as part of the Acquisition Program Baseline, dated November 19, 2012.
Sustainment Strategy:
O&S costs include all costs of operating, maintaining, and supporting the Global Positioning System III (GPS III) and GPS II legacy spacecraft from the dedicated Master Control Station (MCS) located at Schriever Air Force Base (AFB), CO and the Alternate MCS (AMCS) located at Vandenberg AFB, CA, both of which include the ground antenna and monitoring stations. Also included are the costs of operating, maintaining, and supporting seventeen monitoring stations, six controlled by the 50th Space Wing and eleven co-located at National Geo-spatial Intelligence Agency (NGA) sites. Satellite operations at the MCS include mission planning, mission payload operations, and monitoring of satellite state of health. Monitor stations receive mission payload data and transfer this data to the MCS to ensure spacecraft are operating as desired.
O&S begins approximately eighteen months after Block 1 Ready to Transition to Operations (RTO) and assumes a ten year service life for this one system. Manpower assumes a mixture of Air Force personnel performing organic work with assistance from contractor engineers. The estimate assumes organic depot hardware maintenance with 30% organic software maintenance and 70% contractor software maintenance.
Manpower, operations and maintenance is analogous to the currently operating GPS Operational Control System (OCS) with adjustments modeled to reflect the new OCX footprint.
Sustainment support is based on operator and non-operator training and sustainment engineering support is analogous to GPS OCS.
Continuing system improvements are factored in as hardware modifications and software maintenance and modifications.
Antecedent Information:
GPS OCS is the currently operating control system limited to operating GPS II satellites. GPS OCS costs are derived from actuals collected from the last GPS OCS official Cost Data Summary Report submission in 2011.

## Table 34
Unitized O&S Costs BY2012 $M
Cost Element |  | GPS OCX Estimated Average Annual Costs Per System |  |  | GPS Operational Control System (OCS) (Antecedent) Actual Annual Costs from 2011 Per System
Unit-Level Manpower |  | 13.7 |  |  | 12.1
Unit Operations |  | 54.3 |  |  | 51.4
Maintenance |  | 8.7 |  |  | 5.4
Sustaining Support |  | 5 |  |  | 4.4
Continuing System Improvements |  | 29.1 |  |  | 31.5
Indirect Support |  | 4.6 |  |  | 0.5
Other |  | 1.8 |  |  | 0
Total |  | 117.2 |  |  | 105.3
Unitized Cost Comments:
The estimated GPS OCX average annual cost is slightly higher than the GPS OCS actuals due to higher lines-of code size, included Commercial-Off-The-Shelf (COTS) refresh costs, slightly higher manpower estimates, and additional costs attributed to inflation uncertainty. Also, the GPS OCX estimate used estimating methodologies analogous to GPS OCS but were not based entirely on GPS OCS actuals.
The OCX cost estimate over ten years totals to $1153.7M plus $18.4M for Other costs (depot stand-up) equals
$1172.1M (BY 2012).
Total O&S Cost $M
| Current Development APB Objective/Threshold |  |  | Current Estimate
| GPS OCX |  |  | GPS OCX |  | GPS Operational Control System (OCS) (Antecedent)
Base Year | 1380.9 |  | 1518.2 | 1172.1 |  | N/A
Then Year | 1469 |  | N/A | 1469 |  | N/A
Total O&S Costs Comments:
The BY objective value estimate in the APB ($1380.9M) was incorrectly calculated. After the correct application of the indices, the corrected BY objective value should reflect $1172.1M. This is accurately reflected in the current estimate.
Disposal Costs:
There are no disposal costs. Disposal costs will be included in future ground segment estimates.