## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-372
Joint Land Attack Cruise Missile Defense Elevated Netted Sensor System (JLENS)
As of FY 2015 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations |  | 3
Program Information |  | 4
Responsible Office |  | 4
References |  | 4
Mission and Description |  | 5
Executive Summary |  | 6
Threshold Breaches |  | 8
Schedule |  | 9
Performance |  | 11
Track to Budget |  | 13
Cost and Funding |  | 14
Low Rate Initial Production |  | 21
Foreign Military Sales |  | 22
Nuclear Costs |  | 22
Unit Cost |  | 23
Cost Variance |  | 26
Contracts |  | 29
Deliveries and Expenditures |  | 30
Operating and Support Cost |  | 31

## Table 3
Common Acronyms and Abbreviations
Acq O&M - Acquisition-Related Operations and Maintenance APB - Acquisition Program Baseline
APPN - Appropriation
APUC - Average Procurement Unit Cost BA - Budget Authority/Budget Activity
BY - Base Year
DAMIR - Defense Acquisition Management Information Retrieval Dev Est - Development Estimate
DoD - Department of Defense DSN - Defense Switched Network Econ - Economic
Eng - Engineering Est - Estimating
FMS - Foreign Military Sales FY - Fiscal Year
IOC - Initial Operational Capability
$K - Thousands of Dollars
LRIP - Low Rate Initial Production
$M - Millions of Dollars MILCON - Military Construction N/A - Not Applicable
O&S - Operating and Support Oth - Other
PAUC - Program Acquisition Unit Cost PB - President’s Budget
PE - Program Element Proc - Procurement
Prod Est - Production Estimate QR - Quantity Related
Qty - Quantity
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
Sch - Schedule Spt - Support
TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting

## Table 4
Program Information
Program Name
Joint Land Attack Cruise Missile Defense Elevated Netted Sensor System (JLENS)
DoD Component
Army
Responsible Office
Responsible Office
COL Terrence L. Howard | Phone | 256-876-4927
Project Manager | Fax | 256-955-0925
Cruise Missile Defense Systems | DSN Phone | 746-4927
Building 5250, Martin Road Redstone Arsenal, AL 35898-5000 | DSN Fax | 645-0925
terrence.l.howard.mil@mail.mil | Date Assigned | June 27, 2012
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated August 5, 2005
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated August 8, 2013

## Table 5
Mission and Description
Joint Land Attack Cruise Missile Defense Elevated Netted Sensor System (JLENS) is a supporting program of the Army and Joint Integrated Air and Missile Defense, providing persistent, over the horizon surveillance and fire control quality data on Army and Joint networks enabling protection of the United States and coalition forces as well as geopolitical assets from Cruise Missiles, Aircraft, Unmanned Air Vehicles, Tactical Ballistic Missiles, Large Caliber Rockets, and Surface Moving Targets.
JLENS uses advanced sensor and networking technologies to provide persistent, 360-degree, wide-area surveillance and precision tracking of Land Attack Cruise Missiles and other types of Air Breathing Threats. This information is distributed via joint service networks and provides fire control quality data to Surface-to-Air missile systems such as Army Patriot and Navy Aegis, increasing the weapons' capabilities by allowing systems to engage targets normally below, outside, or beyond surface-based weapons' field of view. JLENS also provides fire control quality data to fighter aircraft allowing them to engage hostile threats from extended ranges, and contributes to the development of a single integrated air picture.
A JLENS orbit consists of two systems: a fire control radar system and a wide-area surveillance radar system. Each radar system employs a separate 74-meter tethered aerostat, mobile mooring station, radar and communications payload, processing station, and associated ground support equipment. The systems are designed to work together, but can operate independently. The JLENS orbit is transportable by road, rail, sea, and air.
JLENS does not replace an antecedent system.

## Table 6
Executive Summary
The Department of Army notified Congress on March 27, 2012, that the JLENS program had incurred a Critical Nunn-McCurdy (NM) unit cost breach with the submission of the FY 2013 PB due to a 100-percent reduction in planned procurement quantities. On May 24, 2012, the Defense Acquisition Executive (DAE) signed the NM Acquisition Decision Memorandum (ADM) certifying the restructured JLENS program consisting of two Engineering and Manufacturing Development (EMD) orbits. The NM ADM allowed the Army to complete scheduled EMD test and evaluation in 2013, but directed the JLENS program to not plan for production. The NM ADM also directed the JLENS program to assist in site selection and planning for the employment of one JLENS orbit in support of an operational Continental United States-based exercise and, when a location was determined and orders were approved by the National Command Authority, to conduct such employment. The JLENS program continued to develop planned capabilities to completion, assess test results, correct short comings/deficiencies, and develop documentation to track and assess program status.
On January 31, 2013, the Joint Requirements Oversight Council concurred with the proposed JLENS employment to Aberdeen Proving Ground (APG), Maryland, for an operational exercise in FY 2014 to FY 2017.
On May 30, 2013, the JLENS Product Office and the Lower Tier Project Office (LTPO) conducted a successful JLENS-to-Fighter Integrated Fire Control (IFC) walk-up at the Utah Test and Training Range (UTTR). The walkup event successfully demonstrated the end-to-end IFC communication link between the JLENS Fire Control Radar, the Warfighter Real-Time Analysis Interoperability with Truth (WRAITH) at Fire Break Alpha, and a fighter aircraft equipped with an Instrumented Test Vehicle.
On June 14, 2013, the JLENS Early User Test 2 (EUT-2) was successfully completed at UTTR. The EUT-2 demonstrated JLENS tactical operational endurance by staying aloft and radiating 24/7 for a period of three weeks. The EUT-2 evaluated JLENS operational performance against live air and ground targets consisting of air breathing threats and land-based surface moving targets (boats, cars, and trucks) using approved threat profiles.
On July 17, 2013, the JLENS-to-Fighter IFC demonstration was successfully conducted at UTTR. JLENS passed track data via Link-16 to a U.S. Air Force fighter in support of its engagement of a cruise missile surrogate target. Data flow between JLENS and the fighter was facilitated by WRAITH, an LTPO developed test asset used for demonstrating IFC capability.
On August 8, 2013, the DAE approved the revised APB for the restructured JLENS program. On August 9, 2013, the DAE delegated Milestone Decision Authority for JLENS to the Army and designated the program as Acquisition Category IC.
On August 19-21, 2013, the JLENS orbit at UTTR participated in a North American Aerospace Defense Command National Capital Region (NCR) Integrated Air Defense Systems Proof of Concept. JLENS was successfully integrated into the representative NCR Command and Control architecture and surveillance data was passed across the network and then distributed to the designated remote weapons platforms. JLENS effectively supported eight
Air-to-Air IFC engagements, two organic Ground-to-Air engagements, and one Ground-to-Air IFC engagement.
On September 10, 2013, a modification to the JLENS EMD contract was executed extending the period of performance from September 30, 2013 to December 31, 2013. This extension facilitated several final major events required to ensure JLENS would be functionally ready to support the Northern Command exercise including Identification Friend or Foe (IFF) Mode 5 certification, Cooperative Engagement Capability integration, and completion of the Functional Configuration Audit.

## Table 7
On October 30, 2013, the JLENS Product Office, with representatives from the Security Assistance Management Directorate and the U.S. Army Security Assistance Command (USASAC), provided a Government of Japan delegation and information brief regarding JLENS FMS capability. The Pricing and Availability Case #1 and Case
#2 were completed and sent back to USASAC on February 28, 2014.
The $20.9M in MILCON funding for JLENS site construction was authorized and appropriated in the FY 2014 budget. The Army Budget Office distributed JLENS MILCON funding to the Assistant Chief of Staff for Installation Management on February 21, 2014.
On December 3, 2013, the U.S. Army Corps of Engineers construction contract request for proposals for development of two operational sites at APG, Maryland, was published in the Federal Biz Ops.
On December 9-13, 2013, the JLENS Product Office conducted test operations at UTTR. JLENS completed Phase I of IFF Box and Platform testing. Certification will be completed in April 2014.
During first quarter FY 2014, shutdown and transfer of the JLENS site at the White Sands Missile Range (WSMR), New Mexico, was accomplished with completion on December 12, 2013. Orbit 2 Tactical Hardware and Government-Furnished Equipment were shipped from the WSMR test site to the JLENS UTTR test site for storage.
On December 18, 2013, ownership of the two JLENS orbits was transferred to the Government.
On December 31, 2013, the EMD contract period of performance was completed.
During 2013, soldiers from the Air Defense Artillery Battalion were actively engaged in a series of training activities. From January 6, 2014 to January 28, 2014, 14 soldiers graduated from the Communications and Processing Group maintenance course taught at UTTR. The soldiers were trained to perform preventive maintenance and field-level corrective maintenance to include Line Replaceable Units removal and replacement required to maintain the workstations, the Environmental Control System, and the communications payload equipment of the JLENS. From January 6, 2014 to February 20, 2014, 17 soldiers graduated from the Aerostat Mechanical course and the Aerostat Electrical course taught at the Tethered Communications facility in Elizabeth
City, North Carolina. As well, from February 10, 2014 to February 27, 2014, 14 soldiers graduated from the Systems Administration course, which was also taught at UTTR. The soldiers were trained to perform critical tasks required for operation and maintenance of JLENS during the three-year operational exercise at APG, Maryland.
There are no significant software-related issues with this program at this time.
This is the final SAR submission for JLENS, because the program is 90% or more delivered.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Explanation of Breach
After certification of the restructured JLENS program following completion of the Nunn-McCurdy process, in August 2013 the Defense Acquisition Executive reset the APB and delegated Milestone Decision Authority for JLENS to the Army.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B Review | AUG 2005 | AUG 2005 | AUG 2005 | AUG 2005
Critical Design Review (CDR) | SEP 2008 | DEC 2008 | DEC 2008 | DEC 2008
Milestone C Review | SEP 2010 | N/A | N/A | N/A
First Unit Equipped (FUE) | APR 2011 | N/A | N/A | N/A
Initial Operational Test and Evaluation (IOTE)
IOTE Start | JUL 2011 | N/A | N/A | N/A
IOTE Complete | SEP 2011 | N/A | N/A | N/A
Full Rate Production (FRP) | JUN 2013 | N/A | N/A | N/A
Initial Operational Capability (IOC) | SEP 2013 | N/A | N/A | N/A
Orbit #1 Emplacement at Aberdeen Proving Grounds, Maryland
Surveillance Radar System | N/A | SEP 2014 | MAR 2015 | SEP 2014
Fire Control Radar System | N/A | DEC 2014 | SEP 2015 | DEC 2014
Exercise Completion | N/A | SEP 2017 | MAR 2018 | SEP 2017
(Ch-1)
(Ch-1)
(Ch-1)

## Table 10
Change Explanations
(Ch-1) Milestones were added for Orbit #1 Emplacement at Aberdeen Proving Grounds and Exercise Completion to allow JLENS to complete the restructured program and execute a JLENS operational exercise in accordance with the NM certification ADM.
Acronyms and Abbreviations
ADM - Acquisition Decision Memorandum NM - Nunn-McCurdy

## Table 11
Performance
Characteristics | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
KPP 1 Single Integrated Air Picture (SIAP)
Surveillance coverage (deg) | 360 | 360 | 360 | 360 | 360
KPP 2 Integrated Fire Control (IFC) | Forward Pass (FP) | Forward Pass (FP) | Engage-on- Remote (EOR) | EOR | EOR
KPP 3 Combat Identification (CID)
Identification Friend or Foe (IFF) | All DoD Validated IFF and Warsaw Pact/ Coalition modes | All DoD Validated IFF and Warsaw Pact/ Coalition modes | All DoD validated IFF modes | Modes 1, 2, 3, and 4 | All DoD Validated IFF and Warsaw Pact/Co- alition modes
Precise Participant Location and Identification (PPLI) Correlation | Correlated PPLI messages w/JLENS organic tracks | Correlated PPLI messages w/JLENS organic tracks | Correlated PPLI messages w/JLENS organic tracks | Correlated PPLI messages with JLENS organic tracks | Correlated PPLI messages w/ JLENS organic tracks
KPP 4 C4I Interoperability
Information Exchange Requirements (IERs) | 100% of all top level IERs | 100% of all top level IERs | 100% of all top level critical IERs | 100% of all top level IERs | 100% of all top level IERs
Theater Air and Missile Defense Integrated Architecture | Available behavior models | Available behavior models | Data complete- ness, data availability, and common processing | Data complete- ness, data availability, and common processing | Available behavior models
Net Ready (NR) KPP | Develop Migration Plan to show how we plan to meet NR- KPP | Develop Migration Plan to show how we plan to meet NR- KPP | Develop Migration Plan to show how we plan to meet NR- KPP | Link-16, CEC, JRE, IBS-receive only, ABCS via AMDWS | Develop Migration Plan to show how we plan to meet NR- KPP

## Table 12
Classified Performance information is provided in the classified annex to this submission.
Requirements Source
Operational Requirements Document (ORD) dated February 24, 2004
Change Explanations
None
Memo
JLENS KPPs were demonstrated during Developmental Testing 1 (November 7, 2011 to December 16, 2011),
Developmental Testing 2 (August 23, 2012 to September 27, 2012), the Early User Test (EUT) (October 29, 2012
to December 7, 2012), the JLENS-to-Fighter IFC live fire (July 17, 2013), the EUT-2 (April 3, 2013 to June 14, 2013), and the Weapons System Evaluation Program (August 19-21, 2013).
There have been no changes in the demonstrated performance since the December 2012 SAR.
Acronyms and Abbreviations
ABCS - Air Battle Command System
AMDWS - Air and Missile Defense Workstation
C4I - Command, Control, Communications, Computers, and Intelligence CEC - Cooperative Engagement Capability
deg - degrees
IBS - Information Broadcast System JRE - Joint Range Extension
KPP - Key Performance Parameter w/ - with

## Table 13
Track to Budget
RDT&E
Appn | BA | PE
Army 2040 07 0102419A
Project | Name
E55
Joint Land Attack Cruise Missile Defense Elevated Netted Sensor System (JLENS)
MILCON
Appn | BA | PE
Army 2050 01 0805796A
Project | Name
071948 Vehicle Maintenance Shop (Sunk)
081875 Operations and Maintenance (Sunk)

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
|  | BY2005 $M |  |  |  |  | BY2005 $M
Appropriation |  | SAR Baseline Dev Est |  | Current APB Development Objective/Threshold |  |  | Current Estimate
TY $M
SAR Baseline Dev Est | Current APB Development Objective |  | Current Estimate
RDT&E |  | 1760 |  |  | 2251.5 | 2476.7 |  | 2249.9 | 1948 | 2561.5 | 2553.8
Procurement |  | 4027 |  |  | 0 | -- |  | 0 | 5126 | 0 | 0
Flyaway |  | -- |  |  | -- | -- |  | 0 | -- | -- | 0
Recurring |  | -- |  |  | -- | -- |  | 0 | -- | -- | 0
Non Recurring |  | -- |  |  | -- | -- |  | 0 | -- | -- | 0
Support |  | -- |  |  | -- | -- |  | 0 | -- | -- | 0
Other Support |  | -- |  |  | -- | -- |  | 0 | -- | -- | 0
Initial Spares |  | -- |  |  | -- | -- |  | 0 | -- | -- | 0
MILCON |  | 63 |  |  | 33.8 | 37.2 |  | 34 | 77 | 40.9 | 40.9
Acq O&M |  | 0 |  |  | 0 | -- |  | 0 | 0 | 0 | 0
Total |  | 5850 |  |  | 2285.3 | N/A |  | 2283.9 | 7151 | 2602.4 | 2594.7
Confidence Level for Current APB Cost 80% -
The JLENS Product Office entered a confidence level of 80 percent for the following reasons. Milestone B approval for JLENS was granted in August 2005. When the program was curtailed in the FY 2013 President's Budget, considerable development effort had been completed resulting in the majority of the Total Acquisition Costs being sunk. In addition, the path forward for the remainder of the program is fairly well defined.

## Table 15
Quantity | SAR Baseline Dev Est | Current APB Development | Current Estimate
RDT&E | 2 | 2 | 2
Procurement | 14 | 0 | 0
Total | 16 | 2 | 2
The two RDT&E funded Engineering and Manufacturing Development (EMD) orbits are considered fully configured and production representative. Based on asset utilization required to complete EMD and support the Secretary of Defense directed Combatant Command Exercise, Organizational Support Equipment was acquired for EMD Orbit #1. The EMD Orbit #2 was used to support EMD and will be stored in accordance
with the guidance received at the conclusion of the Nunn-McCurdy process.
The unit of measure is a JLENS orbit, which consists of two systems: a fire control radar system and a wide-area surveillance radar system. Each radar system employs a separate 74-meter tethered aerostat, mobile mooring station, radar and communications payload, processing station, and associated ground support equipment. The systems are designed to work together, but can operate independently.

## Table 16
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2015 President's Budget / December 2013 SAR (TY$ M)
RDT&E | 2323.8 |  |  | 83.5 |  |  | 54.1 |  |  | 50.2 |  | 39.6 |  |  | 2.6 |  |  | 0 |  |  | 0 |  | 2553.8
Procurement | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
MILCON | 20 |  |  | 20.9 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 40.9
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
PB 2015 Total | 2343.8 |  |  | 104.4 |  |  | 54.1 |  |  | 50.2 |  | 39.6 |  |  | 2.6 |  |  | 0 |  |  | 0 |  | 2594.7
PB 2014 Total | 2391.9 |  |  | 119.4 |  |  | 46.6 |  |  | 47.5 |  | 37.8 |  |  | 2.6 |  |  | 0 |  |  | 0 |  | 2645.8
Delta | -48.1 |  |  | -15 |  |  | 7.5 |  |  | 2.7 |  | 1.8 |  |  | 0 |  |  | 0 |  |  | 0 |  | -51.1
Additional funding was added in FY 2015 - FY 2017 for the integration of the JLENS orbit into the National Capital Region to support the Combatant Command (COCOM) Exercise.
The Senate Appropriations Committee report for the FY 2014 National Defense Authorization Act directed that the JLENS RDT&E parent funding line be divided between two separate funding lines, Engineering and Manufacturing Development (EMD) and COCOM Exercise, which are summed under the parent funding line.
The EMD line will be funded at $60.0M and the COCOM Exercise line will be funded at $23.5M for a total of
$83.5M in FY 2014.
Appropriation |  | Prior | FY2014 |  |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  |  | To Complete |  | Total
Quantity | Undistributed |  |  |  | Prior |  | FY2014 |  | FY2015 |  | FY2016 |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  | To Complete |  |  | Total
Development | 2 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 2
Production | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
PB 2015 Total | 2 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 2
PB 2014 Total | 2 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 2
Delta | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2006 | -- | -- | -- | -- | -- | -- | 99.8
2007 | -- | -- | -- | -- | -- | -- | 237.8
2008 | -- | -- | -- | -- | -- | -- | 464.9
2009 | -- | -- | -- | -- | -- | -- | 344.8
2010 | -- | -- | -- | -- | -- | -- | 317.1
2011 | -- | -- | -- | -- | -- | -- | 399.5
2012 | -- | -- | -- | -- | -- | -- | 317.4
2013 | -- | -- | -- | -- | -- | -- | 142.5
2014 | -- | -- | -- | -- | -- | -- | 83.5
2015 | -- | -- | -- | -- | -- | -- | 54.1
2016 | -- | -- | -- | -- | -- | -- | 50.2
2017 | -- | -- | -- | -- | -- | -- | 39.6
2018 | -- | -- | -- | -- | -- | -- | 2.6
Subtotal | 2 | -- | -- | -- | -- | -- | 2553.8

## Table 18
Annual Funding BY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2005 $M | Non End Item Recurring Flyaway BY 2005 $M | Non Recurring Flyaway BY 2005 $M | Total Flyaway BY 2005 $M | Total Support BY 2005 $M | Total Program BY 2005 $M
2006 | -- | -- | -- | -- | -- | -- | 94.8
2007 | -- | -- | -- | -- | -- | -- | 220.6
2008 | -- | -- | -- | -- | -- | -- | 423.2
2009 | -- | -- | -- | -- | -- | -- | 309.9
2010 | -- | -- | -- | -- | -- | -- | 280.7
2011 | -- | -- | -- | -- | -- | -- | 346.8
2012 | -- | -- | -- | -- | -- | -- | 271.1
2013 | -- | -- | -- | -- | -- | -- | 119.5
2014 | -- | -- | -- | -- | -- | -- | 68.2
2015 | -- | -- | -- | -- | -- | -- | 43.3
2016 | -- | -- | -- | -- | -- | -- | 39.4
2017 | -- | -- | -- | -- | -- | -- | 30.4
2018 | -- | -- | -- | -- | -- | -- | 2
Subtotal | 2 | -- | -- | -- | -- | -- | 2249.9

## Table 19
Annual Funding TY$
2050 ¦ MILCON ¦ Military Construction, Army
Fiscal Year | Total Program TY $M
2010 20.0
2011 --
2012 --
2013 --
2014 20.9
Subtotal | 40.9

## Table 20
Annual Funding BY$
2050 ¦ MILCON ¦ Military Construction, Army
Fiscal Year | Total Program BY 2005 $M
2010 17.3
2011 --
2012 --
2013 --
2014 16.7
Subtotal | 34
Funding shown in FY 2010 excludes cost budgeted for non-system specific facilities (barracks, roads, utilities, and infrastructure) in JLENS Military Construction Program Elements.
Funding shown in FY 2014 includes cost budgeted for the following tasks: construction of aerostat pads, roads, operation and support facilities, communications infrastructure, and electrical power transmission and distribution infrastructure to support missile defense equipment at Aberdeen Proving Grounds, Maryland.

## Table 21
Low Rate Initial Production
The FY 2013 PB suspended all JLENS procurement, including the two LRIP orbits.
The May 24, 2012 Nunn-McCurdy Acquisition Decision Memorandum directs Army not to plan for entry of the JLENS program into the production phase.
| Initial LRIP Decision | Current Total LRIP
Approval Date | 8/5/2005 2 Milestone B ADM See notes below 2011 2012
Approved Quantity
Reference
Start Year
End Year

## Table 22
Foreign Military Sales
None
Nuclear Costs
None

## Table 23
Unit Cost
Unit Cost Report
|  | BY2005 $M | BY2005 $M
Unit Cost |  | Current UCR Baseline (AUG 2013 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 2285.3 |  |  | 2283.9
Quantity | 2 |  |  | 2
Unit Cost | 1142.65 |  |  | 1141.95 |  | -0.06
Average Procurement Unit Cost (APUC)
Cost | 0 |  |  | 0
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  | --

## Table 24
Unit Cost History
[7 empty] | BY2005 $M |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  | PAUC |  | APUC
Original APB |  |  | AUG 2005 |  |  |  | 365.625 |  | 287.643 |  | 446.938 |  | 366.143
APB as of January 2006 |  |  | AUG 2005 |  |  |  | 365.625 |  | 287.643 |  | 446.938 |  | 366.143
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  | N/A |  | N/A
Prior APB |  |  | AUG 2005 |  |  |  | 365.625 |  | 287.643 |  | 446.938 |  | 366.143
Current APB |  |  | AUG 2013 |  |  |  | 1142.65 |  | N/A |  | 1301.2 |  | N/A
Prior Annual SAR |  |  | DEC 2012 |  |  |  | 1160.7 |  | N/A |  | 1322.9 |  | N/A
Current Estimate |  |  | DEC 2013 |  |  |  | 1141.95 |  | N/A |  | 1297.35 |  | N/A
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Dev Est | Changes | [10 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth | Spt | Total
446.938 -3.600 1239.112 31.600 -1.050 -41.150 0.000 -374.500 850.412 1297.350

## Table 25
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes | [9 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est | Oth | Spt |  | Total
366.143 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  | SAR Development Estimate (DE) |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | AUG 2005 |  |  | N/A |  |  | AUG 2005
Milestone C |  |  | N/A |  |  | SEP 2010 |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  | SEP 2013 |  |  | N/A |  |  | N/A
Total Cost (TY $M) |  |  | N/A |  |  | 7151 |  |  | N/A |  |  | 2594.7
Total Quantity |  |  | N/A |  |  | 16 |  |  | N/A |  |  | 2
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  | 446.938 |  |  | N/A |  |  | 1297.35

## Table 26
Cost Variance
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Dev Est) 1948.0 5126.0 77.0 7151.0
Previous Changes
Economic |  | 28.4 |  | -30.3 |  | 1.6 |  | -0.3
Quantity |  | -- |  | -3778.9 |  | -- |  | -3778.9
Schedule |  | 325 |  | -261.8 |  | -- |  | 63.2
Engineering |  | -2.1 |  | -- |  | -- |  | -2.1
Estimating |  | 305.6 |  | -306 |  | -37.7 |  | -38.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -749 |  | -- |  | -749
Subtotal |  | 656.9 |  | -5126 |  | -36.1 |  | -4505.2
Current Changes Economic |  | -6.6 |  | -- |  | -0.3 |  | -6.9
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -44.5 |  | -- |  | 0.3 |  | -44.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -51.1 |  | -- |  | -- |  | -51.1
Total Changes |  | 605.8 |  | -5126 |  | -36.1 |  | -4556.3
CE - Cost Variance |  | 2553.8 |  | -- |  | 40.9 |  | 2594.7
CE - Cost & Funding |  | 2553.8 |  | -- |  | 40.9 |  | 2594.7

## Table 27
Summary Base Year 2005 $M
| RDT&E |  | Proc | MILCON | Total
SAR Baseline (Dev Est) Previous Changes |  | 1760 | 4027 | 63 | 5850
Economic |  | -- | -- | -- | --
Quantity |  | -- | -2881.6 | -- | -2881.6
Schedule |  | 278.2 | -329.9 | -- | -51.7
Engineering |  | -- | -- | -- | --
Estimating |  | 249.4 | -223.5 | -29.2 | -3.3
Other |  | -- | -- | -- | --
Support |  | -- | -592 | -- | -592
Subtotal |  | 527.6 | -4027 | -29.2 | -3528.6
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | -37.7 | -- | 0.2 | -37.5
Other |  | -- | -- | -- | --
Support |  | -- | -- | -- | --
Subtotal |  | -37.7 | -- | 0.2 | -37.5
Total Changes |  | 489.9 | -4027 | -29 | -3566.1
CE - Cost Variance |  | 2249.9 | -- | 34 | 2283.9
CE - Cost & Funding |  | 2249.9 | -- | 34 | 2283.9
Previous Estimate: December 2012

## Table 28
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -6.6
Adjustment for current and prior escalation. (Estimating) +4.7 +5.5
Budgetary reduction for Small Business Innovative Research and Small Business Technology Transfer in FY 2013. (Estimating)
Revised estimate due to Congressional reductions in FY 2013 and FY 2014. (Estimating)
Revised estimate to integrate the JLENS orbit into the National Capital Region to support the Combatant Command Exercise. (Estimating)
-3.8 -4.5
-37.8 -45.5
+10.2 +13.0
Refined estimate. (Estimating) | -0.3 | -0.3
Revised estimate due to sequestration reduction in FY 2013. (Estimating) | -10.7 | -12.7
RDT&E Subtotal | -37.7 | -51.1
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.3
Adjustment for current and prior escalation. (Estimating) | 0.2 | 0.3
MILCON Subtotal | 0.2 | 0

## Table 29
Contracts
Appropriation: RDT&E
Contract Name JLENS EMD
Contractor Raytheon Company
Contractor Location 350 Lowell St
Andover, MA 01810
Contract Number, Type DASG60-98-C-0001, CPIF
Award Date October 25, 2005
Definitization Date September 30, 2013
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1428.8 N/A 2 1679.0 N/A 2 1804.0 1802.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to 46 contract modifications to incorporate changes to the Engineering and Manufacturing Development (EMD) contract from August 2007 to March 2012. The largest single component is the FY 2009 EMD contract restructure ($134.7M) to synchronize the JLENS and Army Integrated Air and Missile Defense programs. Other components of the contract price increase include: acquisition of IBM Signal Data Processors (SDP), performance specification changes, customer funds for analytical studies, Cooperative Engagement Capability SDP modifications, addition of Air and Missile Defense Workstation Hardware, Broadband Power Amplifiers, Environmental Control Units, integration of Defense Threat Reduction Agency Phase II, and an update of the Integrated Support Plan in support of the deployment Transition Plan.
Variance |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2013) |  |  |  | -147.7 |  |  |  | -4.8
Previous Cumulative Variances |  |  |  | -124.1 |  |  |  | -1.8
Net Change |  |  |  | -23.6 |  |  |  | -3
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to the contractor, Raytheon, using factored budgets and applying proportional budgets based on the remaining amount of dollars available on contract.
The unfavorable net change in the schedule variance is due to the extension of the contract period of performance from September 30, 2013 to December 31, 2013 and the inability of the contractor to deliver spares within the period of performance.
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 30
Deliveries and Expenditures
Delivered to Date | Plan to Da | te | Actual to Date | Total Quantity |  | Percent Delivered
Development | 2 |  | 2 |  | 2 | 100%
Production | 0 |  | 0 |  | 0 | --
Total Program Quantity Delivered | 2 |  | 2 |  | 2 | 100%
Expended and Appropriated (TY $M)
Total Acquisition Cost | 2594.7 | Years Appropriated |  |  | 9
Expended to Date | 2299.4 | Percent Years Appropriated |  |  | 69.23%
Percent Expended | 88.62% | Appropriated to Date |  |  | 2448.2
Total Funding Years | 13 | Percent Appropriated |  |  | 94.35%
The above data is current as of 2/25/2014.

## Table 31
Operating and Support Cost
JLENS
Assumptions and Ground Rules
Cost Estimate Reference:
N/A
Sustainment Strategy:
N/A
Antecedent Information:
N/A
Unitized O&S Costs BY2005 $M
Cost Element |  | JLENS Average Annual Cost Per Orbit |  | No Antecedent System (Antecedent) N/A
Unit-Level Manpower |  | 0 |  | 0
Unit Operations |  | 0 |  | 0
Maintenance |  | 0 |  | 0
Sustaining Support |  | 0 |  | 0
Continuing System Improvements |  | 0 |  | 0
Indirect Support |  | 0 |  | 0
Other |  | 0 |  | 0
Total |  | -- |  | --
Unitized Cost Comments: N/A
Total O&S Cost $M
| Current Development APB Objective/Threshold |  | Current Estimate
| JLENS |  | JLENS |  | No Antecedent System (Antecedent)
Base Year | 0.0 0.0 N/A N/A
Then Year | 0.0 N/A N/A N/A
Total O&S Costs Comments:
The May 24, 2012 Nunn-McCurdy Acquisition Decision Memorandum (ADM) rescinded the Milestone B approval granted on August 5, 2005. The ADM also directed the Army not to plan for entry of the JLENS program into the production phase; therefore, no O&S will be required.
Disposal Costs:

## Table 32
N/A