## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-282
MH-60S Fleet Combat Support Helicopter (MH-60S)
As of FY 2015 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)
Table of Contents
Common Acronyms and Abbreviations |  | 3
Program Information |  | 4
Responsible Office |  | 4
References |  | 4
Mission and Description |  | 5
Executive Summary |  | 6
Threshold Breaches |  | 7
Schedule |  | 8
Performance |  | 10
Track to Budget |  | 13
Cost and Funding |  | 14
Low Rate Initial Production |  | 21
Foreign Military Sales |  | 22
Nuclear Costs |  | 22
Unit Cost |  | 23
Cost Variance |  | 26
Contracts |  | 29
Deliveries and Expenditures |  | 31
Operating and Support Cost |  | 32
Common Acronyms and Abbreviations
Acq O&M - Acquisition-Related Operations and Maintenance APB - Acquisition Program Baseline
APPN - Appropriation
APUC - Average Procurement Unit Cost BA - Budget Authority/Budget Activity
BY - Base Year
DAMIR - Defense Acquisition Management Information Retrieval Dev Est - Development Estimate
DoD - Department of Defense DSN - Defense Switched Network Econ - Economic
Eng - Engineering Est - Estimating
FMS - Foreign Military Sales FY - Fiscal Year
IOC - Initial Operational Capability
$K - Thousands of Dollars
LRIP - Low Rate Initial Production
$M - Millions of Dollars MILCON - Military Construction N/A - Not Applicable
O&S - Operating and Support Oth - Other
PAUC - Program Acquisition Unit Cost PB - President’s Budget
PE - Program Element Proc - Procurement
Prod Est - Production Estimate QR - Quantity Related
Qty - Quantity
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
Sch - Schedule Spt - Support
TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting

## Table 2
Program Information
Program Name
MH-60S Fleet Combat Support Helicopter (MH-60S)
DoD Component
Navy
Responsible Office
Responsible Office
CAPT James Glass | Phone | 301-757-5409
Air Anti-Submarine Warfare, Assault and Special | Fax | 301-757-5276
Mission | DSN Phone | 757-5409
Programs (PMA-299), 47123 Buse Road Unit IPT, Suite 156 Patuxent River, MD 20670-1547 | DSN Fax | 757-5276
james.glass@navy.mil | Date Assigned | July 28, 2011
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated November 9, 2002
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated November 29, 2010
Mission and Description
The MH-60S Multi-Mission Helicopter Sea Combat (HSC) support helicopters fielded as three "Blocks" of aircraft with slightly different capabilities. Block 1 Combat Support provides Vertical Replenishment; internal transport of passengers, mail and cargo; Vertical On-Board Delivery; Airhead Operations; and day/night Search and Rescue. Secondary roles include torpedo and drone recovery, Noncombatant Evacuation Operations, Sea Air Land and Explosive Ordnance Disposal support.
Block 2 Airborne Mine Countermeasures (AMCM) provides an organic AMCM capability for the Littoral Combat Ship Mine Countermeasures Mission Package. Block 2A AMCM includes the Carriage, Stream, Tow and Recovery System, Common Console, and the AES-1 Airborne Laser Mine Detection System. Block 2B includes the ASQ-235 Airborne Mine Neutralization System.
Block 3 Armed Helo provides the Navy with organic Surface Warfare, Force Protection, and Combat Search and Rescue capabilities. Additional Armed Helo mission areas include Naval Special Warfare and Maritime Interdiction Operations.
These missions are vital to the Navy's role in power projection in the littoral areas of the world. The first 50 aircraft are only capable of performing Block 1 Combat Support Missions. Aircraft 51 to 275 will be capable of performing Block 1 Combat Support Missions, as well as Block 2 AMCM missions and Block 3 Armed Helo missions with installation of ancillary kits.
Executive Summary
The MH-60S program has delivered 246 of 275 helicopters as of March 31, 2014. In response to the Fast Attack Craft / Fast Inshore Attack Craft (FAC/FIAC) threat the program has fielded a 20mm Fixed Forward Firing Gun and fielded an unguided rocket capability. MH-60S helicopters have been utilized for Humanitarian Assistance and Disaster Relief, including support in 2012 for Hurricane Sandy and most recently in 2013 for Cyclone Phailin.
The MH-60R/S Mission Systems and Common Cockpit Multi-Year Procurement (MYP) contract (MY2) with Lockheed Martin Mission Systems and Training was awarded April 5, 2012. The MH-60R/S Airframe MYP contract (MY8) with Sikorsky Aircraft Corporation was awarded July 6, 2012. These two contracts will complete the MH-60S production buys which conclude in FY 2015.
MH-60S Armed Helicopter fixed forward firing weapons integration and test activities continued through 2013. A Quick Reaction Assessment (QRA) of the LAU-61C/A with 2.75 inch unguided High Explosive (HE)
rockets completed in April 2013 and a QRA of the LAU-61 C/A with 2.75 inch unguided Flechette rockets was completed in July 2013. Both capabilities were fielded to fleet users in 2013. The LAU-61G/A Digital Rocket Launcher (DRL) with Advanced Precision Kill Weapons Systems guided rockets completed developmental test in 2013. A QRA of the LAU-61 G/A DRL completed December 2013 and fielded in March 2014.
MH-60S Airborne Mine Countermeasures (AMCM) integration and test activities continued through 2013. Individual AMCM system operational test schedules were aligned with the Littoral Combat Ship (LCS) Mine Countermeasures (MCM) Mission Package schedule. Developmental testing of the MH-60S with the AN/AQS-235 Airborne Mine Neutralizer System continued in 2013.
The program has breached its schedule for AMCM IOC and has experienced an O&S cost breach due to the addition of AMCM and Armed Helo missions and an additional five years of anticipated aircraft service life. Program Deviation Reports for both breaches have been issued by the Program Manager. The program no longer has an APUC breach for unit cost.
There are no significant software-related issues with this program at this time.
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC Significant
APUC None
Explanation of Breach
Schedule: This program realized a schedule breach previously reported in the December 2011 SAR. The Airborne Mine Countermeasures (AMCM) IOC changed from October 2014 to September 2015. The change is based on alignment of the MH-60S AMCM schedule with Littoral Combat Ship Mine Countermeasures Mission package Schedule.
An O&S Breach was previously reported in the December 2012 SAR.
This program realized a significant Nunn-McCurdy breach to the original baseline that was first reported in the December 2005 SAR. The supporting breach information and explanations can be found in the Unit Cost Report section of that SAR.
Program Deviations Reports were submitted by the Program Manager at the time of each breach.
Nunn-McCurdy Breaches
Schedule

## Table 3
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
MS-II/LRIP | JUL 1998 | JUL 1998 | JAN 1999 | JUL 1998
Common Cockpit Critical Design Review | JUL 1998 | JUL 1998 | JAN 1999 | JUL 1998
AMCM Phase l Static Tow Test and OEI Test | DEC 1999 | DEC 1999 | JUN 2000 | DEC 1999
LRIP First Flight | JAN 2000 | JAN 2000 | JUL 2000 | JAN 2000
AMCM Phase II Dynamic Tow Test | JAN 2000 | JAN 2000 | JUL 2000 | JAN 2000
AMCM Interim Process Review I | MAY 2000 | MAY 2000 | NOV 2000 | MAY 2000
AMCM Phase III AN/AQS-20 Tow Demonstration | OCT 2000 | OCT 2000 | APR 2001 | OCT 2000
Technical Evaluation Complete | JAN 2001 | JAN 2001 | JUL 2001 | JAN 2001
LRIP 3 Contract Award | JUN 2001 | JUN 2001 | DEC 2001 | JUN 2001
AMCM Interim Process Review II | DEC 2001 | DEC 2001 | JUN 2002 | DEC 2001
Operational Evaluation Complete | JAN 2002 | JAN 2002 | JUL 2002 | MAR 2002
MS-III (NAV SAE FRP) | AUG 2002 | AUG 2002 | FEB 2003 | AUG 2002
IOC | AUG 2002 | AUG 2002 | FEB 2003 | AUG 2002
AMCM Interim Process Review III | APR 2005 | NOV 2005 | APR 2006 | APR 2006
Armed Helo IOC | MAR 2006 | MAY 2007 | SEP 2007 | JUN 2007
AMCM Interim Process Review IV | N/A | JAN 2012 | JUL 2012 | MAY 2012
AMCM IOC | JUN 2005 | AUG 2011 | FEB 2012 | SEP 2015 1
1APB Breach
(Ch-1)
Change Explanations
(Ch-1) The Current estimate for AMCM IOC has changed from Oct 2014 to Sep 2015. This will align AMCM IOC with the LCS Mine Countermeasures Mission Package IOT&E and subsequent IOC, as driven by the LCS Test and Evaluation Master Plan.
Acronyms and Abbreviations
AMCM - Airborne Mine Countermeasure AN/AQS-20A - Sonar Mine Detection Set IOT&E - Initial Operational Test and Evaluation LCS - Littoral Combat Ship
MS - Milestone
NAV SAE FRP - Navy Service Acquisition Executive Full Rate Production OEI - One Engine Inoperative

## Table 4
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
*Airspeed-VMAX (KIAS) (Block 1 configuration) | 175 | 175 | 150 | 154 | 154
*Amphibious SAR Mission Radius (nm) (Block 1 configuration) | 150 | 150 | 50 | 50 | 50
*VERTREP Endurance (hrs) (Block 1 configuration) | 3 | 3 | 1.75 | 1.85 | 1.85
*VERTREP, External (lbs) (Block 1 configuration) | 5500 | 5500 | 5500 | 6000 | 7500
*VOD (lbs) (Block 1 configuration) | 5500 | 5500 | 5500 | 5000 | 5500
MTBF (hrs) | 20.3 | N/A | N/A | N/A | N/A
MTTR (hrs) | 3.6 | N/A | N/A | N/A | N/A
*Organic CSAR Overland Mission Radius (nm) | 300 | 200 | 150 | 194 | 194
*SWS Mission Radius (nm) | 300 | N/A | N/A | N/A | N/A
*CV Plane Guard/SAR Mission Radius (nm) | 200 | 200 | 100 | 114 | 114
*AMCM Free Flight Endurance (mins) | 150 | 150 | 120 | 210 | 210
*AMCM Hover Endurance (mins) | 90 | 90 | 75 | TBD | 75
*AMCM Tow Endurance (mins) /6 | 75 | 75 | 60 | 71.6 | 71.6
*AMCM Hot Temp Tow Endurance(105 deg F) | 45 | 45 | 30 | 30 | 30
*AMCM Tow Turns (25 knot wind) (deg/sec) | 1.5 | 1.5 | 1 | 1.5 | 1.5
*AMCM Wind Speed Tow (KIAS) | 30 | 30 | 25 | 26 | 26
*AMCM Block 2 Information Dissemination (%) | 95 | N/A | N/A | N/A | N/A
*AMCM Block 2 Information Integrity (%) | 99 | N/A | N/A | N/A | N/A
*AMCM Block 2 Interoperability (%) | 100 | N/A | N/A | N/A | N/A
*Armed Helo Airspeed- | 165 | 130 | 130 | 135 | 135
VMAX (KIAS)
*Armed Helo FMC Rate (%) | 60 | 60 | 56 | 60 | 60
*Armed Helo MC Rate (%) | 75 | 75 | 69 | 74 | 74
*HC Interoperability (%) | 100 | N/A | N/A | N/A | N/A
*Net Ready (%) | N/A | 100 | 100 | Met all evaluation criteria | 100
*Force Protection | N/A | Crash Worthy Seats Pilot 35G, 25G, 20G Crew 20G, 20G, 20G | Crash Worthy Seats Pilot 20G, 20G, 10G Crew 14G, 8G, 12G | Seats Designed to meet Pilot 35G, 25G, 20G Crew 18G, 14.5G, 14G | Crash Worthy Seats Pilot 35G, 25G, 20G, Crew 18G, 14.5G 14G
*Combat Survivability | N/A | Pred Survive 95% prior to launch 80% after launch | Warning & Protect RF/IR, Threat | Warning & Protect RF/IR, Threat | Warning & Protect RF/IR, Threat
*Operational Availability (Ao) (%) (Block 2) | N/A | 85 | 75 | 83.1 | 85
Information Awareness (%) (Block 1 & 3 configuration) | N/A | 99.9 | 99 | Met all evaluation criteria | 99.9
Information Dissemination (%) (Block 1 & 3) | N/A | 95 | 95 | Met all evaluation criteria | 95
Information Integrity (%) (Block 1 & 3) | N/A | 99.999 | 99.99 | Met all evaluation criteria | 99.999
Requirements Source
Operational Requirements Document (ORD) Change 2 dated February 15, 2008
Change Explanations
None
Memo
* Denotes Key Performance Parameters (KPPs)
Acronyms and Abbreviations
AMCM - Airborne Mine Countermeasures Ao - Operational Availability
CSAR - Combat Search and Rescue CV - Carrier
deg - Degree F - Fahrenheit
FMC - Fully Mission Capable G - Gravitational Load
HC - Helicopter Combat Support hrs - Hours
KIAS - Knots Indicated Airspeed lbs - Pounds
LCS - Littoral Combat Ship MC - Mission Capable mins - Minutes
MTBF - Mean Time Between Failures MTTR - Mean Time to Repair
nm - Nautical Miles
RF/IR - Radio Frequency/Infrared SAR - Search and Rescue
sec - Seconds
SWS - Special Warfare Support VERTREP - Vertical Replenishment VMAX - Velocity Maximum
VOD - Vertical Onboard Delivery

## Table 5
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy 1319 05 0604212N
1709 ASW and Other Helo Development/MH-60S VERTREP
ASW and Other Helo
(Sunk)
Project |  |  | Name
2415
Development/MH-60S Development , VERTREP
2772 ASW and Other Helo
(Sunk)
Development/Sentient Sensor ASW and Other Helo
| 2773 |  |  | Development/MH-60S Engineering Development | (Sunk)
| 9213 |  |  | ASW and Other Helo Development/ADV Tow Cable | (Sunk)
Design
Navy | 1319 | 5 |  | 0604216N
| Project |  |  | Name
3053 Multi-Mission Helicopter Upgrade Development/MH-60S AMCM
(Sunk)
Procurement
Appn |  |  | BA | PE
Navy | 1506 |  | 1 | 0204453N
| Line Item |  |  | Name
| 179 |  |  | MH-60S (MYP)
Navy | 1506 |  | 2 | 0204453N
| Line Item |  |  | Name
| 240 |  |  | MH-60S |  | (Sunk)
Navy | 1506 |  | 6 | 0204453N
| Line Item |  |  | Name
| 605 |  |  | MH-60S | (Shared)

## Table 6
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
|  | BY1998 $M | [6 empty] | BY1998 $M
Appropriation |  | SAR Baseline Prod Est |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  |  | Current Estimate
RDT&E |  | 390.9 |  |  |  | 634.6 |  | 698.1 |  | 674.1 |  | 421.4 | 723.8 | 779
Procurement |  | 4879.2 |  |  |  | 6062 |  | 6668.2 |  | 5797.4 |  | 5672.4 | 7134.8 | 6985.4
Flyaway |  | -- |  |  |  | -- |  | -- |  | 4705.7 |  | -- | -- | 5688.2
Recurring |  | -- |  |  |  | -- |  | -- |  | 3875.7 |  | -- | -- | 4661.5
Non Recurring |  | -- |  |  |  | -- |  | -- |  | 830 |  | -- | -- | 1026.7
Support |  | -- |  |  |  | -- |  | -- |  | 1091.7 |  | -- | -- | 1297.2
Other Support |  | -- |  |  |  | -- |  | -- |  | 934.8 |  | -- | -- | 1121.1
Initial Spares |  | -- |  |  |  | -- |  | -- |  | 156.9 |  | -- | -- | 176.1
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 5270.1 |  |  |  | 6696.6 |  | N/A |  | 6471.5 |  | 6093.8 | 7858.6 | 7764.4
Confidence Level for Current APB Cost 50% -
The current APB cost estimate provided sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk and external interference. It was consistent with average resource expenditures on historical efforts of similar size, scope, and complexity and represents a notional 50% confidence level.
Quantity |  |  | SAR Baseline Prod Est |  |  |  | Current APB Production |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  | 0
Procurement |  |  | 237 |  |  |  | 271 |  |  |  | 275
Total |  |  | 237 |  |  |  | 271 |  |  |  | 275

## Table 7
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2015 President's Budget / December 2013 SAR (TY$ M)
Appropriation |  | Prior | FY2014 |  |  | FY2015 |  | FY2016 |  | FY2017 |  | FY2018 |  |  | FY2019 |  |  | To Complete |  | Total
RDT&E | 731.3 |  |  | 21.8 |  |  | 25.9 |  | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 779
Procurement | 6350.7 |  |  | 396.2 |  |  | 210.2 |  | 28.3 | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 6985.4
MILCON | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0
PB 2015 Total | 7082 |  |  | 418 |  |  | 236.1 |  | 28.3 | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 7764.4
PB 2014 Total | 7136.2 |  |  | 455.4 |  |  | 271.6 |  | 28.6 | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 7891.8
Delta | -54.2 |  |  | -37.4 |  |  | -35.5 |  | -0.3 | 0 |  |  | 0 |  |  | 0 |  | 0 |  | -127.4
Quantity | Undistributed |  |  |  | Prior |  | FY2014 |  | FY2015 | FY2016 | FY2 |  | 17 | FY2018 |  |  | FY2019 |  | To Complete |  | Total
Development | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 0
Production | 0 |  |  |  | 249 |  | 18 |  | 8 | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 275
PB 2015 Total | 0 |  |  |  | 249 |  | 18 |  | 8 | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 275
PB 2014 Total | 0 |  |  |  | 249 |  | 18 |  | 8 | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 275
Delta | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 0

## Table 8
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1997 | -- | -- | -- | -- | -- | -- | 6.9
1998 | -- | -- | -- | -- | -- | -- | 29.7
1999 | -- | -- | -- | -- | -- | -- | 36.8
2000 | -- | -- | -- | -- | -- | -- | 42.3
2001 | -- | -- | -- | -- | -- | -- | 30.5
2002 | -- | -- | -- | -- | -- | -- | 50.2
2003 | -- | -- | -- | -- | -- | -- | 24.1
2004 | -- | -- | -- | -- | -- | -- | 49.8
2005 | -- | -- | -- | -- | -- | -- | 77.9
2006 | -- | -- | -- | -- | -- | -- | 78.8
2007 | -- | -- | -- | -- | -- | -- | 81.3
2008 | -- | -- | -- | -- | -- | -- | 38.1
2009 | -- | -- | -- | -- | -- | -- | 42.9
2010 | -- | -- | -- | -- | -- | -- | 48
2011 | -- | -- | -- | -- | -- | -- | 39.4
2012 | -- | -- | -- | -- | -- | -- | 34.1
2013 | -- | -- | -- | -- | -- | -- | 20.5
2014 | -- | -- | -- | -- | -- | -- | 21.8
2015 | -- | -- | -- | -- | -- | -- | 25.9
Subtotal | -- | -- | -- | -- | -- | -- | 779

## Table 9
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 1998 $M | Non End Item Recurring Flyaway BY 1998 $M | Non Recurring Flyaway BY 1998 $M | Total Flyaway BY 1998 $M | Total Support BY 1998 $M | Total Program BY 1998 $M
1997 | -- | -- | -- | -- | -- | -- | 6.9
1998 | -- | -- | -- | -- | -- | -- | 29.5
1999 | -- | -- | -- | -- | -- | -- | 36.2
2000 | -- | -- | -- | -- | -- | -- | 41
2001 | -- | -- | -- | -- | -- | -- | 29.1
2002 | -- | -- | -- | -- | -- | -- | 47.5
2003 | -- | -- | -- | -- | -- | -- | 22.5
2004 | -- | -- | -- | -- | -- | -- | 45.2
2005 | -- | -- | -- | -- | -- | -- | 68.8
2006 | -- | -- | -- | -- | -- | -- | 67.5
2007 | -- | -- | -- | -- | -- | -- | 68
2008 | -- | -- | -- | -- | -- | -- | 31.3
2009 | -- | -- | -- | -- | -- | -- | 34.8
2010 | -- | -- | -- | -- | -- | -- | 38.4
2011 | -- | -- | -- | -- | -- | -- | 30.7
2012 | -- | -- | -- | -- | -- | -- | 26.1
2013 | -- | -- | -- | -- | -- | -- | 15.5
2014 | -- | -- | -- | -- | -- | -- | 16.2
2015 | -- | -- | -- | -- | -- | -- | 18.9
Subtotal | -- | -- | -- | -- | -- | -- | 674.1

## Table 10
Annual Funding TY$
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1998 | 1 | 16.3 | -- | 11.3 | 27.6 | 2.1 | 29.7
1999 | 5 | 109.7 | -- | -- | 109.7 | 28 | 137.7
2000 | 16 | 298.1 | -- | -- | 298.1 | 63.4 | 361.5
2001 | 15 | 218.8 | -- | 6.3 | 225.1 | 94.3 | 319.4
2002 | 13 | 188.7 | -- | 13.4 | 202.1 | 70.6 | 272.7
2003 | 15 | 251.2 | -- | 37.3 | 288.5 | 75.5 | 364
2004 | 13 | 221 | -- | 70.5 | 291.5 | 135.2 | 426.7
2005 | 15 | 258 | -- | 61.2 | 319.2 | 79.4 | 398.6
2006 | 26 | 391.4 | -- | 78.3 | 469.7 | 67.6 | 537.3
2007 | 18 | 315 | -- | 37.1 | 352.1 | 124.4 | 476.5
2008 | 20 | 331.8 | -- | 139.5 | 471.3 | 99.9 | 571.2
2009 | 20 | 348.6 | -- | 145.3 | 493.9 | 78.3 | 572.2
2010 | 18 | 319.4 | -- | 92.6 | 412 | 60.3 | 472.3
2011 | 18 | 312.4 | -- | 124.4 | 436.8 | 92.9 | 529.7
2012 | 18 | 336.1 | -- | 66.1 | 402.2 | 44.5 | 446.7
2013 | 18 | 330.8 | -- | 59.9 | 390.7 | 43.8 | 434.5
2014 | 18 | 295.6 | -- | 39.3 | 334.9 | 61.3 | 396.2
2015 | 8 | 118.6 | -- | 44.2 | 162.8 | 47.4 | 210.2
2016 | -- | -- | -- | -- | -- | 28.3 | 28.3
Subtotal | 275 | 4661.5 | -- | 1026.7 | 5688.2 | 1297.2 | 6985.4

## Table 11
Annual Funding BY$
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 1998 $M | Non End Item Recurring Flyaway BY 1998 $M | Non Recurring Flyaway BY 1998 $M | Total Flyaway BY 1998 $M | Total Support BY 1998 $M | Total Program BY 1998 $M
1998 | 1 | 16 | -- | 11.1 | 27.1 | 2.1 | 29.2
1999 | 5 | 106.4 | -- | -- | 106.4 | 27.2 | 133.6
2000 | 16 | 285.4 | -- | -- | 285.4 | 60.7 | 346.1
2001 | 15 | 207 | -- | 6 | 213 | 89.2 | 302.2
2002 | 13 | 176.3 | -- | 12.5 | 188.8 | 66 | 254.8
2003 | 15 | 230.1 | -- | 34.2 | 264.3 | 69.2 | 333.5
2004 | 13 | 197.3 | -- | 62.9 | 260.2 | 120.7 | 380.9
2005 | 15 | 224 | -- | 53.1 | 277.1 | 68.9 | 346
2006 | 26 | 330.6 | -- | 66.2 | 396.8 | 57.1 | 453.9
2007 | 18 | 260 | -- | 30.6 | 290.6 | 102.7 | 393.3
2008 | 20 | 269.8 | -- | 113.5 | 383.3 | 81.2 | 464.5
2009 | 20 | 279.6 | -- | 116.5 | 396.1 | 62.8 | 458.9
2010 | 18 | 250.8 | -- | 72.7 | 323.5 | 47.4 | 370.9
2011 | 18 | 240.3 | -- | 95.7 | 336 | 71.4 | 407.4
2012 | 18 | 254.5 | -- | 50 | 304.5 | 33.7 | 338.2
2013 | 18 | 246.3 | -- | 44.6 | 290.9 | 32.6 | 323.5
2014 | 18 | 216.2 | -- | 28.7 | 244.9 | 44.9 | 289.8
2015 | 8 | 85.1 | -- | 31.7 | 116.8 | 34 | 150.8
2016 | -- | -- | -- | -- | -- | 19.9 | 19.9
Subtotal | 275 | 3875.7 | -- | 830 | 4705.7 | 1091.7 | 5797.4

## Table 12
Cost Quantity Information
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Flyaway
Fiscal Year | Quantity | (Aligned with
Quantity)
BY 1998
$M
1998 | 1 | 16
1999 | 5 | 81.5
2000 | 16 | 237.5
2001 | 15 | 213.1
2002 | 13 | 178.6
2003 | 15 | 223.8
2004 | 13 | 186.5
2005 | 15 | 216.9
2006 | 26 | 348.7
2007 | 18 | 258.3
2008 | 20 | 283
2009 | 20 | 276.9
2010 | 18 | 251.7
2011 | 18 | 246.3
2012 | 18 | 250.5
2013 | 18 | 257.4
2014 | 18 | 241.5
2015 | 8 | 107.5
2016 | -- | --
Subtotal | 275 | 3875.7

## Table 13
Low Rate Initial Production
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the MS II decision on July 8, 1998, which set LRIP at 15% of the total procurement quantity or 37 aircraft. The LRIP quantity was appropriate due to the low risk of integrating Navy H-60 Seahawk components into the Army H-60 Blackhawk as well as allowing use of an existing Army multi-year contract for procurement.
| Initial LRIP Decision | Current Total LRIP
Approval Date | 7/8/1998 7/8/1998 37 37 Milestone (MS) II ADM MS II ADM 1998 1998 2001 2001
Approved Quantity
Reference
Start Year
End Year

## Table 14
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Memo
Thailand 3/29/2007 2 64.1 Total Cost based on amended Letter of Offer and
Acceptance (LOA) signed January 28, 2011.
Nuclear Costs
None

## Table 15
Unit Cost
Unit Cost Report
|  | BY1998 $M | BY1998 $M
Unit Cost |  | Current UCR Baseline (NOV 2010 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 6696.6 |  |  | 6471.5
Quantity | 271 |  |  | 275
Unit Cost | 24.711 |  |  | 23.533 |  |  | -4.77
Average Procurement Unit Cost (APUC)
Cost | 6062 |  |  | 5797.4
Quantity | 271 |  |  | 275
Unit Cost | 22.369 |  |  | 21.081 |  |  | -5.76
|  | BY1998 $M | BY1998 $M
Unit Cost |  | Original UCR Baseline (JUL 1998 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 2769 |  |  | 6471.5
Quantity | 166 |  |  | 275
Unit Cost | 16.681 |  |  | 23.533 |  | +41.08 1
Average Procurement Unit Cost (APUC)
Cost | 2698 |  |  | 5797.4
Quantity | 165 |  |  | 275
Unit Cost | 16.352 |  |  | 21.081 |  | 28.92
1 Nunn-McCurdy Breach
This program realized a significant Nunn-McCurdy breach to the original baseline that was first reported in the December 2005 SAR. The supporting breach information and explanations can be found in the Unit Cost Report section of that SAR.

## Table 16
Unit Cost History
[7 empty] | BY1998 $M |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  | PAUC |  |  | APUC
Original APB |  |  | JUL 1998 |  |  |  | 16.681 |  | 16.352 |  | 19.567 |  |  | 19.334
APB as of January 2006 |  |  | MAY 2005 |  |  |  | 24.369 |  | 22.369 |  | 28.489 |  |  | 26.328
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  | N/A |  |  | N/A
Prior APB |  |  | DEC 2008 |  |  |  | 24.369 |  | 22.369 |  | 28.489 |  |  | 26.328
Current APB |  |  | NOV 2010 |  |  |  | 24.711 |  | 22.369 |  | 28.999 |  |  | 26.328
Prior Annual SAR |  |  | DEC 2012 |  |  |  | 23.816 |  | 21.325 |  | 28.697 |  |  | 25.807
Current Estimate |  |  | DEC 2013 |  |  |  | 23.533 |  | 21.081 |  | 28.234 |  |  | 25.401
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Dev Est | Changes | [11 empty] | PAUC Prod Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt |  | Total
19.000 -0.766 -0.164 -0.001 2.211 3.739 0.000 1.693 6.712 25.712

## Table 17
Current SAR Baseline to Current Estimate (TY $M)
PAUC Prod Est | Changes | [13 empty] | PAUC Current Est
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth | Spt |  | Total
25.712 0.691 -0.751 0.825 -0.468 0.981 0.000 1.244 2.522 28.234
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Dev Est | Changes | [13 empty] | APUC Prod Est
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est | Oth | Spt |  | Total
18.679 -0.765 -0.147 -0.001 1.123 3.352 0.000 1.693 5.255 23.934
Current SAR Baseline to Current Estimate (TY $M)
APUC Prod Est | Changes | [13 empty] | APUC Current Est
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth | Spt |  | Total
23.934 0.658 -0.506 0.825 -0.592 -0.162 0.000 1.244 1.467 25.401
SAR Baseline History
Item/Event |  |  |  | SAR Planning Estimate (PE) |  |  |  |  | SAR Development Estimate (DE) |  |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone II |  |  |  | N/A |  |  |  |  | APR 1998 |  |  |  | JUL 1998 |  |  | JUL 1998
Milestone III |  |  |  | N/A |  |  |  |  | SEP 2000 |  |  |  | AUG 2002 |  |  | AUG 2002
IOC |  |  |  | N/A |  |  |  |  | DEC 2001 |  |  |  | AUG 2002 |  |  | AUG 2002
Total Cost (TY $M) |  |  |  | N/A |  |  |  |  | 3154 |  |  |  | 6093.8 |  |  | 7764.4
Total Quantity |  |  |  | N/A |  |  |  |  | 166 |  |  |  | 237 |  |  | 275
Prog. Acq. Unit Cost (PAUC) |  |  |  | N/A |  |  |  |  | 19 |  |  |  | 25.712 |  |  | 28.234

## Table 18
Cost Variance
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 421.4 5672.4 -- 6093.8
Previous Changes
Economic |  | 10.3 |  | 201.1 |  | -- |  | 211.4
Quantity |  | -- |  | 770.4 |  | -- |  | 770.4
Schedule |  | -- |  | 227 |  | -- |  | 227
Engineering |  | 50.2 |  | -163.9 |  | -- |  | -113.7
Estimating |  | 313.1 |  | 52.3 |  | -- |  | 365.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 337.5 |  | -- |  | 337.5
Subtotal |  | 373.6 |  | 1424.4 |  | -- |  | 1798
Current Changes Economic |  | -1.1 |  | -20.2 |  | -- |  | -21.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -16 |  | 1 |  | -- |  | -15
Estimating |  | 1.1 |  | -96.8 |  | -- |  | -95.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 4.6 |  | -- |  | 4.6
Subtotal |  | -16 |  | -111.4 |  | -- |  | -127.4
Total Changes |  | 357.6 |  | 1313 |  | -- |  | 1670.6
CE - Cost Variance |  | 779 |  | 6985.4 |  | -- |  | 7764.4
CE - Cost & Funding |  | 779 |  | 6985.4 |  | -- |  | 7764.4

## Table 19
Summary Base Year 1998 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 390.9 4879.2 -- 5270.1
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 572.5 |  | -- |  | 572.5
Schedule |  | -- |  | 121.8 |  | -- |  | 121.8
Engineering |  | 38.9 |  | -123.9 |  | -- |  | -85
Estimating |  | 255.4 |  | 174.6 |  | -- |  | 430
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 240.1 |  | -- |  | 240.1
Subtotal |  | 294.3 |  | 985.1 |  | -- |  | 1279.4
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -11.9 |  | 0.7 |  | -- |  | -11.2
Estimating |  | 0.8 |  | -70.6 |  | -- |  | -69.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 3 |  | -- |  | 3
Subtotal |  | -11.1 |  | -66.9 |  | -- |  | -78
Total Changes |  | 283.2 |  | 918.2 |  | -- |  | 1201.4
CE - Cost Variance |  | 674.1 |  | 5797.4 |  | -- |  | 6471.5
CE - Cost & Funding |  | 674.1 |  | 5797.4 |  | -- |  | 6471.5
Previous Estimate: December 2012

## Table 20
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.1
Reductions in scope of targeting solution for Fast Attack Craft/Fast Inshore Attack Craft Forward Firing Weapons (FAC/FIAC FFW). (Engineering)
Correction of deficiencies for Airborne Mine Countermeasures (AMCM) Airborne Mine Neutralization System Operational Assement (OA) and Littoral Combat Ship Mine Countermeasures Mission Package OA. (Engineering)
-7.4 -10.0
-4.5 -6.0
Adjustment for current and prior escalation. (Estimating) +0.6 +0.8
Revised estimate to reflect the application of new outyear escalation indices. (Estimating)
+0.2 +0.3
RDT&E Subtotal -11.1 -16.0
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -20.2
Incorporation of additional Sikorsky Airframe Engineering Change Proposals. (Engineering)
+0.7 +1.0
Adjustment for current and prior escalation. (Estimating) +11.3 +14.8
Revised estimate to reflect the application of new outyear escalation indices. (Estimating)
+2.2 +3.1
Revised cost estimate for Government Furnished Equipment. (Estimating) +0.6 +0.8
Incorporation of the purchase of refurbished engines vice new engines to meet production line delivery requirements. (Estimating)
Revised Non-Recurring Engineering for Production Line Shutdown and Fatigue Life Assessment. (Estimating)
Decrease in cost estimate for Ancillary equipment, i.e. Armed Helo kits, AMCM fielding requirements, and auxiliary fuel tanks. (Estimating)
-4.3 -5.9
-19.7 -26.6
-60.7 -83.0
Adjustment for current and prior escalation. (Support) +1.6 +2.3
Increase in Other Support for peculiar ground support equipment to establish Core Depot Standup capability. (Support)
+1.5 +2.7
Decrease in Initial Spares for actuals. (Support) | -0.1 |  |  | -0.4
Procurement Subtotal | -66.9 |  |  | -111.4

## Table 21
Contracts
Appropriation: Procurement
Contract Name MH-60S Common Cockpit (Lots 14-17)
Contractor Lockheed Martin Corporation
Contractor Location 1801 State Rt 17C Owego, NY 13827
Contract Number, Type N00019-11-C-0020, FFP
Award Date April 05, 2012
Definitization Date April 05, 2012
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
111.1 N/A 62 111.1 N/A 62 111.1 111.1
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this FFP contract.

## Table 22
Appropriation: Procurement
Contract Name MH-60S Production Aircraft (Lots 14-17)
Contractor Sikorsky Aircraft Corporation
Contractor Location 6900 Main Street Stratford, CT 06614-1385
Contract Number, Type W58RGZ-12-C-0008, FFP
Award Date July 06, 2012
Definitization Date July 06, 2012
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
888.8 N/A 62 888.8 N/A 62 888.8 888.8
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this FFP contract.

## Table 23
Deliveries and Expenditures
Delivered to Date | Plan to D | ate | Actual to Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 0 | --
Production | 245 |  | 246 |  | 275 | 89.45%
Total Program Quantity Delivered | 245 |  | 246 |  | 275 | 89.45%
Expended and |  | Appropriated (TY $M)
Total Acquisition Cost | 7764.4 | Years Appropriated |  |  | 18
Expended to Date | 6675.3 | Percent Years Appropriated |  |  | 90%
Percent Expended | 85.97% | Appropriated to Date |  |  | 7500
Total Funding Years | 20 | Percent Appropriated |  |  | 96.59%
The above data is current as of 3/31/2014.
Operating and Support Cost
MH-60S
Assumptions and Ground Rules
Cost Estimate Reference:
Date of Estimate: February 2014
Source: Naval Air System Command Cost Department; Operating & Sustainment Division
The MH-60S Operating and Support (O&S) cost estimate was updated from the Navy Service Cost Position (SCP) dated November 1, 2010. Maintenance Cost consisting of Aviation Depot Level Repairables (AVDLR) and Consumables were updated using a bottoms-up estimating model that is based on actual MH-60S reliability performance and cost instead of analogous data from other H-60 platforms. In addition, the MH-60S specific manning document and sundown plan is now being utilized instead of the analogous data from other H-60 platforms. A phased approach estimate includes the ramp-up of aircraft as they are introduced to the fleet through the retirement of the MH-60S aircraft from service with a total aircraft procurement of 275.
Sustainment Strategy:
- Quantity: 275 (5 stricken)
- Service Life (useful life): 10,000 hours or 20 years
- Estimated duration = Fiscal Year 2000 to 2035
- Aircraft Attrition Rate = 0.7% of Total Aircraft Inventory (TAI) per year
- Aircraft Pipeline Rate = 15% of TAI per year
- Average Flight Hours per Month per Aircraft = 30.6
- Total Operating Aircraft Years = 4,518
Antecedent Information:
The antecedent system is the HH-60H aircraft. All costs are from the FY 2012 Navy Visibility and Management of Operating and Support Costs (VAMOSC) Aviation Type Model Series Report (ATMSR) database (data from 2009 through 2012) and the FY 2013 Aircraft Program Data File (APDF) Primary Authorized Aircraft (PAA). (6.0) Indirect Support is a function of unit-level manpower costs.
Legacy systems have experienced and continue to experience service life adjustments and system modifications that make the compilation of total O&S cost by assuming a static service life (e.g. 25 years) not credible.
In addition, the capture of O&S data in available reporting systems has changed significantly over time. VAMOSC, the navy's official system for collecting and reporting O&S cost, provides cost from 1997 - present. The cost data for platforms in existence prior to 1997 is either unavailable or incomplete. In summary, sufficient historical data and resources do not exist to create a comparable, credible Total O&S cost.
For comparison purposes, the Base Year Antecedent Total O&S costs is the product of the Antecedent's Average Annual Cost per Aircraft and the Operational Aircraft Years of the MH-60S.

## Table 24
Unitized O&S Costs BY1998 $K
Cost Element |  | MH-60S Average Annual Cost Per Aircraft |  |  |  | HH-60H (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  | 1592.4 |  |  |  | 1500
Unit Operations |  | 121.6 |  |  |  | 130
Maintenance |  | 1209.7 |  |  |  | 1390
Sustaining Support |  | 56.4 |  |  |  | 80
Continuing System Improvements |  | 228.7 |  |  |  | 200
Indirect Support |  | 675.1 |  |  |  | 590
Other |  | 0 |  |  |  | 0
Total |  | 3883.9 |  |  |  | 3890
Unitized Cost Comments:
Total O&S cost is the product of the average annual cost per unit multiplied by the operational aircraft years.
Total O&S Cost $M
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
| MH-60S |  |  |  | MH-60S |  | HH-60H (Antecedent)
Base Year | 14424.9 |  | 15867.4 |  | 17548.0 1 |  | 17575
Then Year | 0 |  | N/A |  | 27330 |  | N/A
1 APB O&S Cost Breach
Total O&S Costs Comments:
O&S Cost Variance Explanation
Category |  | BY1998 $M |  | Explanation
DEC 2012 SAR O&S Estimate |  | 17200
Cost Estimating Methodology |  | 158 |  | Refined I-Level personnel counts
Cost Data Update |  | 103 |  | Updated historical cost information (FY actuals)
Labor Rate |  | 82 |  | Composite Labor and Indirect Rates update
Energy Rate |  | 13 |  | Fuel Rate update
Technical Input |  | 0
Programmatic/Planning |  | -8 |  | FHP calculation update
Other |  | 0
Total Changes |  | 348
Current Estimate |  | 17548
The Program has realized an O&S APB breach, as reported in the December 31, 2012 SAR, due to the addition of Airborne Mine Countermeasures, Armed Helo missions and an additional five years of anticipated aircraft service life.
Disposal Costs:
The Rough Order Magnitude estimated cost of the demilitarization/disposal phase for the remaining aircraft is
$68.7M (BY 1998$). The estimate will be refined as the system Disposal Plan Annex to the the Life Cycle Sustainment Plan is developed.