## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-253
MQ-8 Vertical Takeoff and Landing Tactical Unmanned Aerial Vehicle Fire Scout (VTUAV)
As of FY 2015 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations |  | 3
Program Information |  | 4
Responsible Office |  | 4
References |  | 4
Mission and Description |  | 5
Executive Summary |  | 6
Threshold Breaches |  | 7
Schedule |  | 8
Performance |  | 9
Track to Budget |  | 12
Cost and Funding |  | 13
Low Rate Initial Production |  | 24
Foreign Military Sales |  | 25
Nuclear Costs |  | 25
Unit Cost |  | 26
Cost Variance |  | 31
Contracts |  | 34
Deliveries and Expenditures |  | 35
Operating and Support Cost |  | 36

## Table 3
Common Acronyms and Abbreviations
Acq O&M - Acquisition-Related Operations and Maintenance APB - Acquisition Program Baseline
APPN - Appropriation
APUC - Average Procurement Unit Cost BA - Budget Authority/Budget Activity
BY - Base Year
DAMIR - Defense Acquisition Management Information Retrieval Dev Est - Development Estimate
DoD - Department of Defense DSN - Defense Switched Network Econ - Economic
Eng - Engineering Est - Estimating
FMS - Foreign Military Sales FY - Fiscal Year
IOC - Initial Operational Capability
$K - Thousands of Dollars
LRIP - Low Rate Initial Production
$M - Millions of Dollars MILCON - Military Construction N/A - Not Applicable
O&S - Operating and Support Oth - Other
PAUC - Program Acquisition Unit Cost PB - President’s Budget
PE - Program Element Proc - Procurement
Prod Est - Production Estimate QR - Quantity Related
Qty - Quantity
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
Sch - Schedule Spt - Support
TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting

## Table 4
Program Information
Program Name
MQ-8 Vertical Takeoff and Landing Tactical Unmanned Aerial Vehicle Fire Scout (VTUAV)
DoD Component
Navy
Responsible Office
Responsible Office
CAPT Patrick Smith | Phone | 301-757-9020
22707 Cedar Point Road | Fax | 301-757-7261
Building 3261 | DSN Phone | 757-9020
Patuxent River, MD 20670 | DSN Fax | 757-7261
patrick.smith@navy.mil | Date Assigned | June 17, 2011
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated February 2, 2009
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated June 20, 2011

## Table 5
Mission and Description
The MQ-8 Vertical Takeoff and Landing Tactical Unmanned Aerial Vehicle Fire Scout (VTUAV) program supports the Close Range Reconnaissance, Surveillance and Target Acquisition Capability Mission Need Statement, and the Capability Production Document for the VTUAV System, as ammended May 15, 2009. Additionally, the performance attributes of the MQ-8 support the Littoral Combat Ship, the Vertical Unmanned Air Vehicle (UAV), the Assured Maritime Access in the Littorals, the Joint Strike Enable and the Penetrating Intelligence, Surveillance, and Reconnaissance for Area Denial Threat Environments Initial Capabilities Documents.
An MQ-8 system is composed of air vehicles, Electro Optic/Infrared/Laser Designator Range Finder payload (one per air vehicle), Ground Control Station (GCS), Tactical Control System software, Tactical Common Data
Link, UAV Common Automatic Recovery System for automatic take-offs and landings, and associated spares and support equipment. The MQ-8 launches and recovers vertically and can operate from all air capable ships as well as confined area land bases. Other characteristics include autonomous waypoint navigation with command override capability, a heavy fuel engine, and the ability to incorporate future mission packages. Each GCS will perform mission planning, air vehicle and mission payload control, receive incoming payload data and distribute the data to existing shipboard Command, Control, Communication, and Computer Information systems.

## Table 6
Executive Summary
The MQ-8 VTUAV Fire Scout is an Acquisition Category (ACAT) IC program. The program is post-Milestone C and has procured 23 LRIP air vehicles, 20 Ground Control Stations, and 22 Unmanned Aerial Vehicle Common Automatic Recovery Systems. The program is aligned to the Littoral Combat Ship (LCS) Surface Warfare, Mine Counter Measures, and Anti-Submarine Warfare Mission Packages. In FY 2013, the program completed over 4,500 operational flight hours while deployed aboard Guided Missile Frigates supporting United States Africa Command (AFRICOM) Joint Emergent Operational Needs Statement (JEONS), AF-0002; and supporting the Intelligence, Surveillance, and Reconnaissance (ISR) Task Force in Afghanistan. The program has initiated fleet fielding and plans to declare IOC in the second quarter of FY 2014.
The FY 2015 PB defers air vehicle procurement to better align with LCS deliveries, while focusing on system wholeness with the integration and test of improved capabilities (endurance upgrade, radar, and weapons) into the Program of Record (POR) to support LCS mission packages. The procurement budget funds control stations, ancillary equipment, training equipment, support equipment, technical support and logistics which are critically needed to outfit the ships and train the aviation detachments for LCS. Integrating the endurance upgrade (MQ-8C) capability into the POR allows the total air vehicle procurement quantity to be reduced from 168 to 119 production air vehicles.
This combined increase in warfighter capability and reduction in total air vehicle quantity results in a Critical Nunn- McCurdy Unit Cost breach to the program’s APUC and PAUC metrics. Although the APUC grew 52 percent over the 2012 SAR, total procurement dollars grew $43M (BY 2006 dollars) or 2.4 percent. Similarly, PAUC grew $192M (BY 2006 dollars) or 7.9 percent over the 2012 SAR due to additional funding for transition of increased capabilities. Overall, the additional transition investment will result in reduced air vehicle quantities and reduced sustainment cost.
A Program Deviation Report (PDR) was signed by the Program Manager on March 10, 2014. The Program Executive Office for Strike Weapons and Unmanned Aviation endorsed and forwarded the PDR to the Milestone Decision Authority, Assistant Secretary of the Navy for Research, Development and Acquisition, on March 10, 2014.
Funding included in this report is for the MQ-8 Fire Scout ACAT IC baseline POR that supports LCS mission packages and the planned transition of endurance upgrade (MQ-8C), radar and weapons capabilities into the acquisition framework. The funding for the Rapid Deployment Capabilities to support the AFRICOM JEONS and Navy Central Command Urgent Operational Needs Statement requirements for a sea-based ISR Unmanned Aircraft System with radar and weapons is not included in this report consistent with previous reports.
No APB changes have occurred since the September 30, 2012, out-of-cycle SAR that was submitted due to schedule breaches for Operational Evaluation, IOC, and Full Rate Production. The program plans to address these schedule breaches and the Critical Nunn-McCurdy Unit Cost breaches in 2014.
There are no significant software-related issues with this program at this time.

## Table 7
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC Critical
APUC Critical
Original UCR Baseline
PAUC Critical
APUC Critical
Explanation of Breach
The FY 2015 PB defers air vehicle procurement to better align with Littoral Combat Ship (LCS) deliveries, while focusing on system wholeness with the integration and test of improved capabilities (endurance upgrade, radar, and weapons) into the Program of Record (POR) to support LCS mission packages. The procurement budget resources control stations, ancillary equipment, training equipment, support equipment, technical support and logistics which are critically needed to outfit the ships and train the aviation detachments for LCS. Integrating the endurance upgrade (MQ-8C) capability into the POR allows the total air vehicle procurement quantity to be reduced from 168 to 119 production air vehicles.
This combined increase in warfighter capability and reduction in total air vehicle quantity results in a Critical Nunn-McCurdy Unit Cost breach to the program’s APUC and PAUC metrics. Unit cost growth is not due to program management issues or out of control contractor cost growth.
Although the APUC grew 52 percent over the 2012 SAR, total procurement dollars grew $43M (BY 2006 dollars) or 2.4 percent. Similarly, PAUC grew $192M (BY 2006 dollars) or 7.9 percent over the 2012 SAR due to additional funding for transition of increased capabilities. Overall, the additional transition investment will result in reduced air vehicle quantities and reduced sustainment cost.
A Program Deviation Report (PDR) was signed by the Program Manager on March 10, 2014. The Program Executive Office for Strike Weapons and Unmnanned Aviation endorsed and forwarded the PDR to the Milestone Decision Authority, Assistant Secretary of the Navy for Research, Development and Acquisition, on March 10, 2014.
No APB changes have occurred since the September 30, 2012 out-of- cycle SAR that was submitted due to schedule breaches for Operational Evaluation, IOC, and Full-Rate Production. The program plans to address these schedule breaches and the Critical Nunn-McCurdy Unit Cost breaches in Calendar Year 2014.
Nunn-McCurdy Breaches

## Table 8
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone II | JAN 2000 | JAN 2000 | JUL 2000 | JAN 2000
Milestone C | FEB 2007 | FEB 2007 | AUG 2007 | MAY 2007
OPEVAL Complete | SEP 2009 | NOV 2011 | MAY 2012 | N/A 1
FRP Decision Review | NOV 2009 | APR 2012 | OCT 2012 | N/A 1
IOC | SEP 2009 | NOV 2011 | MAY 2012 | MAR 2014 1
1APB Breach
(Ch-1)
(Ch-1)
(Ch-2)
Change Explanations
(Ch-1) The OPEVAL Complete current estimate has changed from November 2011 to N/A and the FRP DR current estimate has changed from November 2011 to N/A because the Navy does not plan to complete any more Operational Testing, nor to purchase any additional MQ-8B air vehicles. New current estimates for OPEVAL Complete and FRP DR for the MQ-8 system will be developed and reported after the Navy approves the final Acquisition Strategy in FY 2014 and updates the APB in FY 2015.
(Ch-2) The IOC current estimate has changed from April 2012 to March 2014 due to delays in the completion of a Military Utility Assessment for the MQ-8 system aboard a Guided Missile Frigate. The testing was completed in November 2013 and the release of the Commander, Operational Test and Evaluation Forces report supporting the IOC decision was approved in March 2014.
Acronyms and Abbreviations
FRP DR - Full Rate Production Decision Review OPEVAL - Operational Evaluation

## Table 9
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Automatic Launch/Recovery (Ship Operations)
Deck Pitch (degrees) | +/- 5 | +/- 5 | +/-3 | +/-2 at seas; +/-5 land | +/-5
Deck Roll (degrees) | +/- 8 | +/- 8 | +/- 5 | +/-5 at seas; +/-10 land | +/- 8
Target Identification
Slant Range (km) | 16 | 16 | 6 | 10 | 16
Operational Availability | >= 0.95 | >= 0.95 | >= 0.85 | 0.88 | >= 0.85
Net-Ready | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric Military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1. 2) DISR mandated | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric Military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1. 2) DISR mandated | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric Military operations to include 1) ISR mandated GIG IT standards and profiles identified in the TV-1. 2) DISR mandated | The system has demonstra- ted all Net Ready Capabilities that have been implemented in the host FFG and LCS class ships. | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric Military operations to include 1) ISR mandated GIG IT standards and profiles identified in the TV-1. 2) DISR mandated

## Table 10
| GIG IPs | GIG IPs | GIG KIPs | GIG KIPs
| identified in | identified in | identified in | identified in
| the KIP | the KIP | the KIP | the KIP
| declaration | declaration | declaration | declaration
| table. 3) | table. 3) | table. 3) | table. 3)
| NCOW RW | NCOW RW | NCOW RW | NCOW RW
| Enterprise | Enterprise | Enterprise | Enterprise
| Services. 4) | Services. 4) | Services. 4) | Services. 4)
| IA | IA | IA | IA
| requirements | requirements | requirements | requirements
| including | including | including | including
| availability, | availability, | availability, | availability,
| integrity, | integrity, | integrity, | integrity,
| authenticat- | authenticat- | authenticat- | authentica-
| ion, | ion, | ion, | tion,
| confidential- | confidential- | confidential- | confidential-
| ity, and | ity, and | ity, and | ity, and
| issuance of | issuance of | issuance of | issuance of
| an ATO by | an ATO by | an IATO by | an IATO by
| the DAA. 5) | the DAA. 5) | the DAA. 5) | the DAA. 5)
| Operationally | Operationally | Operationally | Operationally
| effective | effective | effective | effective
| information | information | information | information
| exchanges; | exchanges; | exchanges; | exchanges;
| and mission | and mission | and mission | and mission
| critical | critical | critical | critical
| performance | performance | performance | performance
| and IA | and IA | and IA | and IA
| attributes, | attributes, | attributes, | attributes,
| data | data | data | data
| correctness, | correctness, | correctness, | correctness,
| data | data | data | data
| availability, | availability, | availability, | availability,
| and | and | and | and
| consistent | consistent | consistent | consistent
| data | data | data | data
| processing | processing | processing | processing
| specified in | specified in | specified in | specified in
| the | the | the | the
| applicable | applicable | applicable | applicable
| joint and | joint and | joint and | joint and
| system | system | system | system
| integrated | integrated | integrated | integrated
| architectural | architectural | architectural | architectural
| views. | views. | views. | views.
Requirements Source
Capability Production Document (CPD) dated May 15, 2009

## Table 11
Change Explanations
None
Acronyms and Abbreviations
ATO - Authority to Operate
DAA - Designated Approving Authority
DISR - Defense Information Standards Registry FFG - Guided Missile Frigate
GIG - Global Information Grid IA - Information Assurance
IATO - Interim Authority to Operate IP - Information Protocol
ISR - Information Standards Registry IT - Information Technology
KIP - Key Information Protocol km - Kilometer
LCS - Littoral Combat Ship
NCOW RM - Net-Centric Operational Warfare Reference Model TV - Technical View

## Table 12
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy 1319 07 0305204N
2768 Tactical Unmanned Aerial
(Shared) (Sunk)
Project |  |  | Name
| Notes: |  |  | Vehicles/VTUAV PU2768, VTUAV
Navy | 1319 | 7 |  | 0305231N
| Project |  |  | Name
| 2768 |  |  | MQ-8 UAV
Notes: PU2768, MQ-8 UAV
In FY 2010, VTUAV was moved from PE 0305204N to PE 0305231N.
(Shared)
RDT&E funding within the PE 0305231N now includes the planned transition of endurance upgrade (MQ-8C), radar and weapons capabilities into the acquisition framework, so the PE is no longer sunk. The funding for the Rapid Deployment Capabilities (RDC) to support the United States Africa Command Joint Emergent Operational Needs Statement and Navy Central Command Urgent Operational Needs Statement requirements for a sea- based Intelligence Surveillance and Reconnaissance Unmanned Aircraft System with radar and weapons are not included in this SAR.
Procurement
Appn |  |  | BA | PE
Navy | 1506 |  | 4 | 0305204N
| Line Item |  |  | Name
| 44300 |  |  | Vertical Take-off UAV (VTUAV) |  | (Sunk)
Navy | 1506 |  | 4 | 0305231N
| Line Item |  |  | Name
| 44300 |  |  | MQ-8 UAV | (Shared)
Navy | 1506 |  | 6 | 0305231N
| Line Item |  |  | Name
| 605 |  |  | MQ-8 UAV | (Shared)
In FY 2010, VTUAV was moved from PE 0305204N to PE 0305231N.
The majority of the funding included in PE 0305231N in FY 2012 - FY 2014 is associated with the endurance upgrade RDC and is not included in this SAR.

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
|  | BY2006 $M | [6 empty] | BY2006 $M
Appropriation |  | SAR Baseline Prod Est |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  |  | Current Estimate
RDT&E |  | 541.1 |  |  |  | 617.1 |  | 678.8 |  | 1 765.8 |  | 530.3 | 614.4 | 801.7
Procurement |  | 1522.4 |  |  |  | 1748.9 |  | 1923.8 |  | 1848.9 |  | 1821.5 | 2226.1 | 2669.1
Flyaway |  | -- |  |  |  | -- |  | -- |  | 1376.7 |  | -- | -- | 2019.9
Recurring |  | -- |  |  |  | -- |  | -- |  | 1321.5 |  | -- | -- | 1941.8
Non Recurring |  | -- |  |  |  | -- |  | -- |  | 55.2 |  | -- | -- | 78.1
Support |  | -- |  |  |  | -- |  | -- |  | 472.2 |  | -- | -- | 649.2
Other Support |  | -- |  |  |  | -- |  | -- |  | 403.7 |  | -- | -- | 570.9
Initial Spares |  | -- |  |  |  | -- |  | -- |  | 68.5 |  | -- | -- | 78.3
MILCON |  | 119.6 |  |  |  | 0 |  | -- |  | 0 |  | 126 | 0 | 0
Acq O&M |  | 183.3 |  |  |  | 0 |  | -- |  | 0 |  | 309.3 | 0 | 0
Total |  | 2366.4 |  |  |  | 2366 |  | N/A |  | 2614.7 |  | 2787.1 | 2840.5 | 3470.8
1 APB Breach
Confidence Level for Current APB Cost 60% -
The current estimate aims to provide sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk, and external interference. It is consistent with average resource expenditures on historical efforts of similar size, scope, and complexity.
Quantity |  |  | SAR Baseline Prod Est |  |  |  | Current APB Production |  |  |  | Current Estimate
RDT&E |  |  | 9 |  |  |  | 7 |  |  |  | 7
Procurement |  |  | 168 |  |  |  | 168 |  |  |  | 119
Total |  |  | 177 |  |  |  | 175 |  |  |  | 126

## Table 14
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2015 President's Budget / December 2013 SAR (TY$ M)
Funding included in this report is for the MQ-8 Fire Scout Acquisition Category IC baseline Program of Record that supports Littoral Combat Ship mission packages and the planned transition of endurance upgrade (MQ- 8C), radar and weapons capabilities into the acquisition framework. The funding for the Rapid Deployment Capabilities to support the United States Africa Command Joint Emergent Operational Needs Statement and Navy Central Command Urgent Operational Needs Statement requirement for a sea-based Intelligence Surveillance and Reconnaissance Unmanned Aircraft System with radar and weapons are not included in this report; therefore, the SAR does not match the budget exhibits for this PE.
Appropriation |  | Prior | FY2014 |  |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  |  | To Complete |  |  | Total
RDT&E | 609.4 |  |  | 5 |  |  | 47.3 |  |  | 53.2 |  | 33.5 |  |  | 6.5 |  |  | 6.6 |  |  | 40.2 |  |  | 801.7
Procurement | 395.1 |  |  | 20.4 |  |  | 47.3 |  |  | 44.2 |  | 28.6 |  |  | 24.7 |  |  | 26.1 |  |  | 2082.7 |  |  | 2669.1
MILCON | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
PB 2015 Total | 1004.5 |  |  | 25.4 |  |  | 94.6 |  |  | 97.4 |  | 62.1 |  |  | 31.2 |  |  | 32.7 |  |  | 2122.9 |  |  | 3470.8
PB 2014 Total | 1004.7 |  |  | 19.4 |  |  | 34.7 |  |  | 37 |  | 22.6 |  |  | 18.9 |  |  | 125.4 |  |  | 1894.1 |  |  | 3156.8
Delta | -0.2 |  |  | 6 |  |  | 59.9 |  |  | 60.4 |  | 39.5 |  |  | 12.3 |  |  | -92.7 |  |  | 228.8 |  |  | 314
Quantity | Undistributed |  |  |  | Prior |  | FY2014 |  | FY2015 |  | FY2016 |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  |  | To Complete |  |  | Total
Development | 7 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 7
Production | 0 |  |  |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 96 |  |  | 119
PB 2015 Total | 7 |  |  |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 96 |  |  | 126
PB 2014 Total | 7 |  |  |  | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 7 |  |  | 138 |  |  | 175
Delta | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | -7 |  |  | -42 |  |  | -49

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year |  | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M |  | Total Flyaway TY $M |  | Total Support TY $M |  | Total Program TY $M
2000 | -- |  | -- | -- | -- | -- |  | -- |  | 34.8
2001 | -- |  | -- | -- | -- | -- |  | -- |  | 66.2
2002 | -- |  | -- | -- | -- | -- |  | -- |  | 47.8
2003 | -- |  | -- | -- | -- | -- |  | -- |  | 39.3
2004 | -- |  | -- | -- | -- | -- |  | -- |  | 36
2005 | -- |  | -- | -- | -- | -- |  | -- |  | 59.1
2006 | -- |  | -- | -- | -- | -- |  | -- |  | 93.2
2007 | -- |  | -- | -- | -- | -- |  | -- |  | 100
2008 | -- |  | -- | -- | -- | -- |  | -- |  | 62.8
2009 | -- |  | -- | -- | -- | -- |  | -- |  | 22.5
2010 | -- |  | -- | -- | -- | -- |  | -- |  | 25.5
2011 | -- |  | -- | -- | -- | -- |  | -- |  | 19.7
2012 | -- |  | -- | -- | -- | -- |  | -- |  | 2.5
2013 | -- |  | -- | -- | -- | -- |  | -- |  | --
2014 | -- |  | -- | -- | -- | -- |  | -- |  | 5
2015 | -- |  | -- | -- | -- | -- |  | -- |  | 47.3
2016 | -- |  | -- | -- | -- | -- |  | -- |  | 53.2
2017 | -- |  | -- | -- | -- | -- |  | -- |  | 33.5
2018 | -- |  | -- | -- | -- | -- |  | -- |  | 6.5
2019 | -- |  | -- | -- | -- | -- |  | -- |  | 6.6
2020 | -- |  | -- | -- | -- | -- |  | -- |  | 6.7
2021 | -- |  | -- | -- | -- | -- |  | -- |  | 6.7
2022 | -- |  | -- | -- | -- | -- |  | -- |  | 6.7
2023 | -- |  | -- | -- | -- | -- |  | -- |  | 6.7
2024 | -- |  | -- | -- | -- | -- |  | -- |  | 6.7
2025 | -- |  | -- | -- | -- | -- |  | -- |  | 6.7

## Table 16
Subtotal | 7 | -- | -- | -- | -- | -- | 801.7

## Table 17
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2006 $M | Non End Item Recurring Flyaway BY 2006 $M | Non Recurring Flyaway BY 2006 $M | Total Flyaway BY 2006 $M | Total Support BY 2006 $M | Total Program BY 2006 $M
2000 | -- | -- | -- | -- | -- | -- | 38.6
2001 | -- | -- | -- | -- | -- | -- | 72.4
2002 | -- | -- | -- | -- | -- | -- | 51.8
2003 | -- | -- | -- | -- | -- | -- | 42
2004 | -- | -- | -- | -- | -- | -- | 37.4
2005 | -- | -- | -- | -- | -- | -- | 59.8
2006 | -- | -- | -- | -- | -- | -- | 91.5
2007 | -- | -- | -- | -- | -- | -- | 95.8
2008 | -- | -- | -- | -- | -- | -- | 59.1
2009 | -- | -- | -- | -- | -- | -- | 20.9
2010 | -- | -- | -- | -- | -- | -- | 23.3
2011 | -- | -- | -- | -- | -- | -- | 17.6
2012 | -- | -- | -- | -- | -- | -- | 2.2
2013 | -- | -- | -- | -- | -- | -- | --
2014 | -- | -- | -- | -- | -- | -- | 4.2
2015 | -- | -- | -- | -- | -- | -- | 39.5
2016 | -- | -- | -- | -- | -- | -- | 43.5
2017 | -- | -- | -- | -- | -- | -- | 26.9
2018 | -- | -- | -- | -- | -- | -- | 5.1
2019 | -- | -- | -- | -- | -- | -- | 5.1
2020 | -- | -- | -- | -- | -- | -- | 5.1
2021 | -- | -- | -- | -- | -- | -- | 5
2022 | -- | -- | -- | -- | -- | -- | 4.9
2023 | -- | -- | -- | -- | -- | -- | 4.8
2024 | -- | -- | -- | -- | -- | -- | 4.7
2025 | -- | -- | -- | -- | -- | -- | 4.6
Subtotal | 7 | -- | -- | -- | -- | -- | 765.8

## Table 18
Annual Funding TY$
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year |  | Quantity |  | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M |  | Non Recurring Flyaway TY $M |  | Total Flyaway TY $M |  | Total Support TY $M |  | Total Program TY $M
2007 | 3 |  | 32.2 |  | -- | 3.9 |  | 36.1 |  | 11.5 |  | 47.6
2008 | 3 |  | 32.4 |  | -- | 1.4 |  | 33.8 |  | 11.6 |  | 45.4
2009 | 3 |  | 31.6 |  | -- | 3.2 |  | 34.8 |  | 22.3 |  | 57.1
2010 | 11 |  | 109.8 |  | -- | 5.8 |  | 115.6 |  | 28.6 |  | 144.2
2011 | 3 |  | 31.3 |  | -- | 1.3 |  | 32.6 |  | 14.5 |  | 47.1
2012 | -- |  | 0.3 |  | -- | 1 |  | 1.3 |  | 24.6 |  | 25.9
2013 | -- |  | 11.8 |  | -- | -- |  | 11.8 |  | 16 |  | 27.8
2014 | -- |  | 1 |  | -- | -- |  | 1 |  | 19.4 |  | 20.4
2015 | -- |  | 11.5 |  | -- | -- |  | 11.5 |  | 35.8 |  | 47.3
2016 | -- |  | 15.9 |  | -- | -- |  | 15.9 |  | 28.3 |  | 44.2
2017 | -- |  | 8 |  | -- | -- |  | 8 |  | 20.6 |  | 28.6
2018 | -- |  | 7.6 |  | -- | -- |  | 7.6 |  | 17.1 |  | 24.7
2019 | -- |  | 8 |  | -- | -- |  | 8 |  | 18.1 |  | 26.1
2020 | 6 |  | 98.9 |  | -- | 8.6 |  | 107.5 |  | 28.5 |  | 136
2021 | 6 |  | 99.9 |  | -- | 3.5 |  | 103.4 |  | 22.6 |  | 126
2022 | 6 |  | 101 |  | -- | 3.5 |  | 104.5 |  | 22.3 |  | 126.8
2023 | 6 |  | 100.1 |  | -- | 3.4 |  | 103.5 |  | 22.6 |  | 126.1
2024 | 6 |  | 98.3 |  | -- | 3.3 |  | 101.6 |  | 21.1 |  | 122.7
2025 | 6 |  | 100 |  | -- | 3.4 |  | 103.4 |  | 22.2 |  | 125.6
2026 | 6 |  | 101.5 |  | -- | 3.5 |  | 105 |  | 22.1 |  | 127.1
2027 | 6 |  | 97.6 |  | -- | 3.4 |  | 101 |  | 22.9 |  | 123.9
2028 | 6 |  | 99.3 |  | -- | 3.4 |  | 102.7 |  | 22.9 |  | 125.6
2029 | 6 |  | 101 |  | -- | 3.5 |  | 104.5 |  | 23.7 |  | 128.2
2030 | 6 |  | 102.7 |  | -- | 3.5 |  | 106.2 |  | 23.7 |  | 129.9
2031 | 6 |  | 104.4 |  | -- | 3.6 |  | 108 |  | 24.6 |  | 132.6
2032 | 6 |  | 106.2 |  | -- | 3.6 |  | 109.8 |  | 24.5 |  | 134.3
2033 | 6 |  | 107.8 |  | -- | 3.7 |  | 111.5 |  | 25.4 |  | 136.9
2034 | 6 |  | 109.8 |  | -- | 3.8 |  | 113.6 |  | 25.4 |  | 139
2035 | 6 |  | 111.9 |  | -- | 3.8 |  | 115.7 |  | 26.3 |  | 142

## Table 19
Subtotal | 119 | 1941.8 | -- | 78.1 | 2019.9 | 649.2 | 2669.1

## Table 20
Annual Funding BY$
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year |  | Quantity | End Item Recurring Flyaway BY 2006 $M | Non End Item Recurring Flyaway BY 2006 $M |  | Non Recurring Flyaway BY 2006 $M |  |  | Total Flyaway BY 2006 $M | Total Support BY 2006 $M |  | Total Program BY 2006 $M
2007 | 3 |  | 30.4 |  | -- |  | 3.7 | 34.1 |  | 10.9 | 45
2008 | 3 |  | 30.2 |  | -- |  | 1.3 | 31.5 |  | 10.8 | 42.3
2009 | 3 |  | 29 |  | -- |  | 2.9 | 31.9 |  | 20.5 | 52.4
2010 | 11 |  | 98.8 |  | -- |  | 5.2 | 104 |  | 25.7 | 129.7
2011 | 3 |  | 27.6 |  | -- |  | 1.1 | 28.7 |  | 12.8 | 41.5
2012 | -- |  | 0.3 |  | -- |  | 0.9 | 1.2 |  | 21.3 | 22.5
2013 | -- |  | 10.1 |  | -- |  | -- | 10.1 |  | 13.6 | 23.7
2014 | -- |  | 0.8 |  | -- |  | -- | 0.8 |  | 16.3 | 17.1
2015 | -- |  | 9.5 |  | -- |  | -- | 9.5 |  | 29.4 | 38.9
2016 | -- |  | 12.8 |  | -- |  | -- | 12.8 |  | 22.8 | 35.6
2017 | -- |  | 6.3 |  | -- |  | -- | 6.3 |  | 16.3 | 22.6
2018 | -- |  | 5.9 |  | -- |  | -- | 5.9 |  | 13.2 | 19.1
2019 | -- |  | 6.1 |  | -- |  | -- | 6.1 |  | 13.7 | 19.8
2020 | 6 |  | 73.6 |  | -- |  | 6.4 | 80 |  | 21.2 | 101.2
2021 | 6 |  | 72.9 |  | -- |  | 2.6 | 75.5 |  | 16.5 | 92
2022 | 6 |  | 72.3 |  | -- |  | 2.5 | 74.8 |  | 15.9 | 90.7
2023 | 6 |  | 70.2 |  | -- |  | 2.4 | 72.6 |  | 15.9 | 88.5
2024 | 6 |  | 67.6 |  | -- |  | 2.3 | 69.9 |  | 14.5 | 84.4
2025 | 6 |  | 67.4 |  | -- |  | 2.3 | 69.7 |  | 15 | 84.7
2026 | 6 |  | 67.1 |  | -- |  | 2.3 | 69.4 |  | 14.6 | 84
2027 | 6 |  | 63.3 |  | -- |  | 2.2 | 65.5 |  | 14.8 | 80.3
2028 | 6 |  | 63.1 |  | -- |  | 2.2 | 65.3 |  | 14.5 | 79.8
2029 | 6 |  | 62.9 |  | -- |  | 2.2 | 65.1 |  | 14.8 | 79.9
2030 | 6 |  | 62.7 |  | -- |  | 2.1 | 64.8 |  | 14.5 | 79.3
2031 | 6 |  | 62.5 |  | -- |  | 2.2 | 64.7 |  | 14.7 | 79.4
2032 | 6 |  | 62.3 |  | -- |  | 2.1 | 64.4 |  | 14.4 | 78.8
2033 | 6 |  | 62 |  | -- |  | 2.1 | 64.1 |  | 14.7 | 78.8
2034 | 6 |  | 61.9 |  | -- |  | 2.1 | 64 |  | 14.4 | 78.4
2035 | 6 |  | 61.9 |  | -- |  | 2.1 | 64 |  | 14.5 | 78.5

## Table 21
Subtotal | 119 | 1321.5 | -- | 55.2 | 1376.7 | 472.2 | 1848.9
This note is related to the Cost Quantity Information Table: The procurement funding in FY 2012 - FY 2019 is associated with the purchase of Ground Control Stations, ship's ancillary equipment, and spares required to support ship installations and deployments in those years. It is accounted for with the aircraft quantity in FY 2020 - FY 2022, although other aircraft may be used to support those ships.

## Table 22
Cost Quantity Information
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Flyaway
Fiscal Year |  | Quantity |  | (Aligned with
Quantity)
BY 2006
$M
2007 | 3 |  | 30.4
2008 | 3 |  | 30.2
2009 | 3 |  | 29
2010 | 11 |  | 98.8
2011 | 3 |  | 27.6
2012 | -- |  | --
2013 | -- |  | --
2014 | -- |  | --
2015 | -- |  | --
2016 | -- |  | --
2017 | -- |  | --
2018 | -- |  | --
2019 | -- |  | --
2020 | 6 |  | 90.9
2021 | 6 |  | 90.2
2022 | 6 |  | 89.5
2023 | 6 |  | 70.2
2024 | 6 |  | 67.6
2025 | 6 |  | 67.4
2026 | 6 |  | 67.1
2027 | 6 |  | 63.3
2028 | 6 |  | 63.1
2029 | 6 |  | 62.9
2030 | 6 |  | 62.7
2031 | 6 |  | 62.5
2032 | 6 |  | 62.3
2033 | 6 |  | 62

## Table 23
2034 | 6 | 61.9
2035 | 6 | 61.9
Subtotal | 119 | 1321.5

## Table 24
Low Rate Initial Production
The Current Total LRIP Quantity is more than 10% of the total production quantity due to August 4, 2010, Congressional Emergency Supplemental Appropriation HR-4899 which funded Overseas Contingency Operations to convert eight Army airframes bought under the Army's Future Combat System program into Navy Fire Scouts.
The initial Acquisition Decision Memorandum for Milestone C approved the program to purchase up to four aircraft, and to buy-to-budget. This guidance resulted in a purchase of three aircraft.
An LRIP decision on September 30, 2008 authorized purchase of three aircraft for LRIP 2 and three aircraft for LRIP 3.
An LRIP decision on July 22, 2010, authorized purchase of five aircraft for LRIP 4 and three aircraft for LRIP 5. Only three new aircraft were purchased under LRIP 4.
| Initial LRIP Decision | Current Total LRIP
Approval Date | 5/29/2007 7/22/2010 4 23 Milestone C ADM Congressional Emergency Supplemental Appropriation HR-4899 2007 2007 2007 2012
Approved Quantity
Reference
Start Year
End Year

## Table 25
Foreign Military Sales
None
Nuclear Costs
None

## Table 26
Unit Cost
Unit Cost Report
|  | BY2006 $M | BY2006 $M
Unit Cost |  | Current UCR Baseline (JUN 2011 APB) | Current Estimate (DEC 2013 SAR) |  |  |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 2366 |  |  | 2614.7
Quantity | 175 |  |  | 126
Unit Cost | 13.52 |  |  | 20.752 |  |  |  | +53.49 1
Average Procurement Unit Cost (APUC)
Cost | 1748.9 |  |  | 1848.9
Quantity | 168 |  |  | 119
Unit Cost | 10.41 |  |  | 15.537 |  |  |  | +49.25 1
|  | BY2006 $M | BY2006 $M
Unit Cost |  | Original UCR Baseline (DEC 2006 APB) | Current Estimate (DEC 2013 SAR) |  |  |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 2366.4 |  |  |  | 2614.7
Quantity | 177 |  |  |  | 126
Unit Cost | 13.369 |  |  |  | 20.752 |  |  | +55.22 1
Average Procurement Unit Cost (APUC)
Cost | 1522.4 |  |  |  | 1848.9
Quantity | 168 |  |  |  | 119
Unit Cost | 9.062 |  |  |  | 15.537 |  |  | +71.45 1
TY $M
Unit Cost |  | Current UCR Baseline (JUN 2011 APB) | Current Estimate (DEC 2013 SAR) |  |  | TY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 2840.5 |  |  | 3470.8
Unit Cost | 16.231 |  |  | 27.546 |  |  |  | 69.71
Average Procurement Unit Cost (APUC)
Cost | 2226.1 |  |  | 2669.1
Unit Cost | 13.251 |  |  | 22.429 |  |  |  | 69.26

## Table 27
TY $M
Unit Cost |  |  | Original UCR Baseline (DEC 2006 APB) |  |  | Current Estimate (DEC 2013 SAR) |  |  | TY % Change
Program Acquisition Unit Cost (PAUC)
Cost |  | 2787.1 |  |  |  |  | 3470.8
Unit Cost |  | 15.746 |  |  |  |  | 27.546 |  |  | 74.94
Average Procurement Unit Cost (APUC)
Cost |  | 1821.5 |  |  |  |  | 2669.1
Unit Cost |  | 10.842 |  |  |  |  | 22.429 |  |  | 106.87
1 Nunn-McCurdy Breach
The FY 2015 PB defers air vehicle procurement to better align with Littoral Combat Ship (LCS) deliveries, while focusing on system wholeness with the integration and test of improved capabilities (endurance upgrade, radar, and weapons) into the Program of Record (POR) to support LCS mission packages. The procurement budget resources control stations, ancillary equipment, training equipment, support equipment, technical support and logistics which are critically needed to outfit the ships and train the aviation detachments for LCS. Integrating the endurance upgrade (MQ-8C) capability into the POR allows the total air vehicle procurement quantity to be reduced from 168 to 119 production air vehicles.
This combined increase in warfighter capability and reduction in total air vehicle quantity results in a Critical Nunn-McCurdy Unit Cost breach to the program’s APUC and PAUC metrics. Unit cost growth is not due to program management issues or out-of-control contractor cost growth. Although the APUC grew 52 percent over the 2012 SAR, total procurement dollars grew $43M (BY 2006 dollars) or 2.4 percent. Similarly, PAUC grew
$192M (BY 2006 dollars) or 7.9 percent over the 2012 SAR due to additional funding for transition of increased capabilities. Overall, the additional transition investment will result in reduced air vehicle quantities and reduced sustainment cost.
Unit Cost Breach Data
Changes from Previous S | AR |  |  | $ | M/Qty. |  |  | Percent
PAUC (BY $M) |  |  |  |  | 6.932 |  |  | 50.16
APUC (BY $M) |  |  |  |  | 4.786 |  |  | 44.52
PAUC Quantity |  |  |  |  | -49 |  |  | 0
PAUC (TY $M) |  |  |  |  | 9.507 |  |  | 52.7
APUC (TY $M) |  |  |  |  | 7.266 |  |  | 47.92
Initial SAR Information |  |  |  | BY $M |  |  |  | TY $M
Program Acquisition Cost |  |  |  |  | 2366.4 |  |  | 2787.1
Unit Cost PAUC Changes
PAUC increases 55 percent over the original APB. The FY 2015 PB transitions the endurance upgrade (MQ- 8C), radar, and weapons capabilities into the Fire Scout System. The increase in capability allows for a decrease in air vehicle procurement quantities from 168 to 119. The combined impact of the procurement of the added capability, and the reduced quantity, increases the PAUC 49 percent. Prior year PAUC growth of 4 percent was attributed to production line stretching (2 percent) and air vehicle cost growth of the MQ-8B LRIP

## Table 28
units (2 percent).
Unit Cost APUC Changes
APUC increases 71 percent over the original APB. The FY 2015 PB transitions the endurance upgrade (MQ- 8C), radar, and weapons capabilities into the Fire Scout System. The increase in capability allows for a decrease in air vehicle quantities from 168 to 119. The combined impact of the procurement of the added capability, and reduced quantity, increases the APUC 52 percent. Prior year APUC growth of 19 percent was attributed to production line stretching due to schedule delays (12 percent) and air vehicle cost growth of the MQ- 8B LRIP units (7 percent).
Impact of Performance or Schedule Changes
The increase in capability of the endurance upgrade (MQ-8C), radar, and weapons contributes to program growth: PAUC 29 percent, and APUC 26 percent. Quantity and production rate (schedule stretch out) play a significant part in the unit cost growth to the Critical Nunn-McCurdy level. Reducing the procurement quantity to 119 amortizes all of the ship components over a smaller denominator: although the APUC grew 52 percent over the 2012 SAR, total procurement dollars grew $43M (BY 2006 dollars) or 2.4 percent.
Program Management or Control
Program management and controls are in place and have been effective for the program. The program has been managed within cost controls since its inception in FY 2000. Prior schedule breaches for Operational Evaluation, IOC, and Full Rate Production were attributed to ship platform availability and system reliability.
Cost Control Actions
Actions already taken to control costs: transitioned multiple production items to fixed price; transitioned Contractor Furnished Equipment items to Government Furnished Equipment (GFE). Additional actions are planned to compete the purchase of GFE items.
Nunn-McCurdy Comments
It is the Office of the Secretary of Defense's intent to execute a Nunn-McCurdy review as directed by statute.

## Table 29
Unit Cost History
[11 empty] | BY2006 $M | [6 empty] | TY $M
[5 empty] | Date | [5 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  |  |  | DEC 2006 | [5 empty] | 13.369 |  |  | 9.062 |  |  |  | 15.746 |  |  | 10.842
APB as of January 2006 |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Revised Original APB |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  |  |  | FEB 2009 | [5 empty] | 13.369 |  |  | 9.062 |  |  |  | 15.746 |  |  | 10.842
Current APB |  |  |  |  | JUN 2011 | [5 empty] | 13.52 |  |  | 10.41 |  |  |  | 16.231 |  |  | 13.251
Prior Annual SAR |  |  |  |  | DEC 2012 | [5 empty] | 13.82 |  |  | 10.751 |  |  |  | 18.039 |  |  | 15.163
Current Estimate |  |  |  |  | DEC 2013 | [5 empty] | 20.752 |  |  | 15.537 |  |  |  | 27.546 |  |  | 22.429
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Dev Est | Changes | [18 empty] | PAUC Prod Est
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  |  | Oth |  |  | Spt |  | Total
15.746 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 15.746
Current SAR Baseline to Current Estimate (TY $M)
PAUC Prod Est |  | Changes | [16 empty] | PAUC Current Est
|  | Econ |  | Qty |  |  | Sch | Eng | Est |  |  | Oth |  |  | Spt |  | Total
15.746 0.156 2.354 3.769 5.620 -1.946 0.000 1.847 11.800 27.546

## Table 30
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Dev Est | Changes | [13 empty] | APUC Prod Est
| Econ | Qty |  | Sch | Eng |  | Est |  | Oth |  | Spt |  |  | Total
10.842 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 10.842
Current SAR Baseline to Current Estimate (TY $M)
APUC Prod Est | Changes | [13 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt |  |  | Total
10.842 0.171 0.208 3.991 4.334 0.928 0.000 1.955 11.587 22.429
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  |  | SAR Development Estimate (DE) |  |  |  |  | SAR Production Estimate (PdE) |  |  |  | Current Estimate
Milestone I |  |  | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A
Milestone II |  |  | N/A |  |  |  | JAN 2000 |  |  |  |  | JAN 2000 |  |  |  | JAN 2000
Milestone C |  |  | N/A |  |  |  | FEB 2007 |  |  |  |  | FEB 2007 |  |  |  | MAY 2007
IOC |  |  | N/A |  |  |  | N/A |  |  |  |  | SEP 2009 |  |  |  | MAR 2014
Total Cost (TY $M) |  |  | N/A |  |  |  | 2787.1 |  |  |  |  | 2787.1 |  |  |  | 3470.8
Total Quantity |  |  | N/A |  |  |  | 177 |  |  |  |  | 177 |  |  |  | 126
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  |  | 15.746 |  |  |  |  | 15.746 |  |  |  | 27.546

## Table 31
Cost Variance
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Acq O&M |  | Total
SAR Baseline (Prod Est) 530.3 1821.5 126.0 309.3 2787.1
Previous Changes
Economic Quantity |  | -0.6 -- |  | +24.3 -- |  | -- -- |  | -- -- |  | +23.7 --
Schedule |  | -- |  | 276 |  | -- |  | -- |  | 276
Engineering |  | -- |  | -- |  | -- |  | -- |  | --
Estimating |  | 79.7 |  | 111.2 |  | -126 |  | -309.3 |  | -244.4
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 314.4 |  | -- |  | -- |  | 314.4
Subtotal |  | 79.1 |  | 725.9 |  | -126 |  | -309.3 |  | 369.7
Current Changes Economic |  | -- |  | -4 |  | -- |  | -- |  | -4
Quantity |  | -- |  | -506.5 |  | -- |  | -- |  | -506.5
Schedule |  | -- |  | 198.9 |  | -- |  | -- |  | 198.9
Engineering |  | 192.3 |  | 515.8 |  | -- |  | -- |  | 708.1
Estimating |  | -- |  | -0.8 |  | -- |  | -- |  | -0.8
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -81.7 |  | -- |  | -- |  | -81.7
Subtotal |  | 192.3 |  | 121.7 |  | -- |  | -- |  | 314
Total Changes |  | 271.4 |  | 847.6 |  | -126 |  | -309.3 |  | 683.7
CE - Cost Variance |  | 801.7 |  | 2669.1 |  | -- |  | -- |  | 3470.8
CE - Cost & Funding |  | 801.7 |  | 2669.1 |  | -- |  | -- |  | 3470.8

## Table 32
Summary Base Year 2006 $M
| RDT&E |  | Proc |  | MILCON |  | Acq O&M |  | Total
SAR Baseline (Prod Est) 541.1 1522.4 119.6 183.3 2366.4
Previous Changes
Economic |  | -- |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -2.5 |  | -- |  | -- |  | -2.5
Engineering |  | 0.2 |  | -- |  | -- |  | -- |  | 0.2
Estimating |  | 71.1 |  | 111.5 |  | -119.6 |  | -183.3 |  | -120.3
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 174.7 |  | -- |  | -- |  | 174.7
Subtotal |  | 71.3 |  | 283.7 |  | -119.6 |  | -183.3 |  | 52.1
Current Changes Economic |  | -- |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -307.8 |  | -- |  | -- |  | -307.8
Schedule |  | -- |  | 75.9 |  | -- |  | -- |  | 75.9
Engineering |  | 153.4 |  | 330 |  | -- |  | -- |  | 483.4
Estimating |  | -- |  | -0.5 |  | -- |  | -- |  | -0.5
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -54.8 |  | -- |  | -- |  | -54.8
Subtotal |  | 153.4 |  | 42.8 |  | -- |  | -- |  | 196.2
Total Changes |  | 224.7 |  | 326.5 |  | -119.6 |  | -183.3 |  | 248.3
CE - Cost Variance |  | 765.8 |  | 1848.9 |  | -- |  | -- |  | 2614.7
CE - Cost & Funding |  | 765.8 |  | 1848.9 |  | -- |  | -- |  | 2614.7
Previous Estimate: December 2012

## Table 33
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Additional funding to transition the endurance upgrade, radar, and weapons capabilities to the Program of Record (POR). (Engineering)
+153.4 +192.3
RDT&E Subtotal +153.4 +192.3
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -4.0
Adjustment for current and prior escalation. (Estimating) +0.3 +0.3
Total Quantity variance resulting from a decrease of 49 aircraft, from 168 to 119. (Subtotal)
Quantity variance resulting from a decrease of 49 aircraft from 168 to 119. (Quantity)
-311.2 -512.0
(-307.8) (-506.5)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -2.5 |  |  | -4.1
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -0.9 |  |  | -1.4
Stretch-out of the procurement buy profile that moved aircraft purchases from FY 2014 - FY 2019 to FY 2032 - FY 2035 and reduced aircraft procurement rates from FY 2019 - | 0 |  |  | 80.1
FY 2032. (Schedule)
Additional schedule variance for Material Cost and Ground Control Station procurement profile changes. (Schedule) | 78.4 |  |  | 122.9
Additional funding for payload and endurance capabilities for the POR. (Engineering) | 330 |  |  | 515.8
Revised estimate due to Navy priority shifts. (Estimating) | 0.1 |  |  | 0.3
Adjustment for current and prior escalation. (Support) | 0.7 |  |  | 0.7
Decrease in Other Support due to decrease in aircraft quantity. (Support) (QR) | -63.6 |  |  | -92.3
Increase in Initial Spares due to increased flight hour estimates to support the warfighter. (Support) | 8.1 |  |  | 9.9
Procurement Subtotal +42.8 +121.7
(QR) Quantity Related

## Table 34
Contracts
Appropriation: Procurement
Contract Name LRIP
Contractor Northrop Grumman Corporation
Contractor Location San Diego, CA 92150-9066
Contract Number, Type N00019-07-C-0041, FFP
Award Date June 21, 2007
Definitization Date April 24, 2008
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
40.3 N/A 3 213.7 N/A 23 213.7 213.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the additional Contract Line Item Numbers added to the contract for the additional LRIP buys authorized by various Acquisition Decision Memoranda from FY 2008 - FY 2010. This resulted in the addition of 20 aircraft to the total contract quantity.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this FFP contract.
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 35
Deliveries and Expenditures
Delivered to Date | Plan to Date |  | Actual to Date | Total Quantity |  | Percent Delivered
Development | 7 |  | 7 |  | 7 | 100%
Production | 21 |  | 21 |  | 119 | 17.65%
Total Program Quantity Delivered | 28 |  | 28 |  | 126 | 22.22%
Expended and |  | Appropriated (TY $M)
Total Acquisition Cost | 3470.8 | Years Appropriated |  |  | 15
Expended to Date | 960.4 | Percent Years Appropriated |  |  | 41.67%
Percent Expended | 27.67% | Appropriated to Date |  |  | 1029.9
Total Funding Years | 36 | Percent Appropriated |  |  | 29.67%
The above data is current as of 3/10/2014.

## Table 36
Operating and Support Cost
VTUAV
Assumptions and Ground Rules
Cost Estimate Reference:
The O&S costs are based on the most current Program Life Cycle Cost Estimate from January 2011 and will be updated after the Nunn-McCurdy certification is complete (FY 2014) and the Navy approves the final Acquisition Strategy (FY 2014), updates the Service Cost Position (FY 2014), and updates the APB (FY 2015). All costs are estimated in BY 2006.
Sustainment Strategy:
The VTUAV Sustainment strategy supports 168 aircraft and 55 ship-based ground control segments. The strategy includes a mixture of both Organic and Contractor Organizational to Depot sustainment support. Upon further Business Case Analyses the anticipated mix of sustainment is to optimize Organic and Contractor solutions. The air vehicle has a design life, which minimizes the air vehicle Total Ownership Costs over 6,000 flight hours and 20 years. The VTUAV system will be operated and maintained from FY 2010 – FY 2035, with an IOC of FY
2014. This estimate includes attrition of 7.09 aircraft for every 100,000 flight hours. The system is expected to meet that attrition rate after the system has accumulated 100,000 flight hours. The current estimate is based upon 1,624 total operational aircraft years.
As defined by the Cost Assessment and Program Evaluation Department O&S Cost Estimating Guide of October 2007, Total O&S Costs for the VTUAV represents the program office’s current estimate for 168 procured aircraft with a Primary Aircraft Authorized of 114 over the estimate duration of FY 2010 - FY 2035.
Antecedent Information:
There is no antecedent for this system.
Unitized O&S Costs BY2006 $K
Cost Element | VTUAV Average Annual Cost per Air Vehicle | No Antecedent (Antecedent) N/A
Unit-Level Manpower | 347.6 | --
Unit Operations | 32 | --
Maintenance | 1325.6 | --
Sustaining Support | 198 | --
Continuing System Improvements | 158 | --
Indirect Support | 174.8 | --
Other | 0 | --
Total | 2236 | --
Unitized Cost Comments:
The Average Annual Cost per Air Vehicle of 2.236 $M is calculated by dividing Total O&S cost of 3,631.4 $M by the total number of operational aircraft years of 1,624.

## Table 37
Total O&S Cost $M
| Current Production APB Objective/Threshold | Current Estimate
| VTUAV | VTUAV | No Antecedent (Antecedent)
Base Year | 3307.0 3637.7 3631.4 N/A
Then Year | 5131.3 N/A 5537.3 N/A
Total O&S Costs Comments: None
Disposal Costs:
The VTUAV disposal costs are estimated to be 21.1 $M (BY 2006 dollars).