## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-531
Patriot/Medium Extended Air Defense System Combined Aggregate Program (Patriot/MEADS CAP)
As of FY 2015 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations |  | 3
Program Information |  | 4
Responsible Office |  | 4
References |  | 4
Mission and Description |  | 5
Executive Summary |  | 6
Threshold Breaches |  | 8
Schedule |  | 9
Performance |  | 12
Track to Budget |  | 16
Cost and Funding |  | 18
Low Rate Initial Production |  | 30
Foreign Military Sales |  | 31
Nuclear Costs |  | 31
Unit Cost |  | 32
Cost Variance |  | 38
Contracts |  | 44
Deliveries and Expenditures |  | 48
Operating and Support Cost |  | 49

## Table 3
Common Acronyms and Abbreviations
Acq O&M - Acquisition-Related Operations and Maintenance APB - Acquisition Program Baseline
APPN - Appropriation
APUC - Average Procurement Unit Cost BA - Budget Authority/Budget Activity
BY - Base Year
DAMIR - Defense Acquisition Management Information Retrieval Dev Est - Development Estimate
DoD - Department of Defense DSN - Defense Switched Network Econ - Economic
Eng - Engineering Est - Estimating
FMS - Foreign Military Sales FY - Fiscal Year
IOC - Initial Operational Capability
$K - Thousands of Dollars
LRIP - Low Rate Initial Production
$M - Millions of Dollars MILCON - Military Construction N/A - Not Applicable
O&S - Operating and Support Oth - Other
PAUC - Program Acquisition Unit Cost PB - President’s Budget
PE - Program Element Proc - Procurement
Prod Est - Production Estimate QR - Quantity Related
Qty - Quantity
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
Sch - Schedule Spt - Support
TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting

## Table 4
Program Information
Program Name
Patriot/Medium Extended Air Defense System Combined Aggregate Program (Patriot/MEADS CAP)
DoD Component
Army
Responsible Office
Responsible Office
COL John Eggert | Phone | 256-955-3240
Project Manager | Fax | 256-955-3108
Lower Tier Project Office | DSN Phone | 645-3240
Building 5250, Martin Road Redstone Arsenal, AL 35898-8000 | DSN Fax | 645-4656
john.m.eggert2.mil@mail.mil | Date Assigned | July 24, 2013
References
Fire Unit
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated August 6, 2004
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated August 6, 2004
Missile
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated August 6, 2004
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated August 6, 2004

## Table 5
Mission and Description
The Patriot/Medium Extended Air Defense System Combined Aggregate Program (Patriot/MEADS CAP) represents the process through which the Patriot system transitions to MEADS. The MEADS program is a Tri- National co-development program among the United States, Germany, and Italy to replace the U.S. Patriot air defense systems, Patriot and Hawk systems in Germany, and the Nike system in Italy. The MEADS mission will provide Joint and Coalition forces with critical asset and defended area protection against multiple and
simultaneous attacks by low-to-medium altitude Air and Missile Defense (AMD) with the capability to counter, defeat, or destroy Tactical Ballistic Missiles, Air-Breathing Threats to include cruise missiles, unmanned aerial vehicles, tactical air-to-surface missiles, and anti-radiation missiles. The Patriot system provides a combat demonstrated capability against these threats. MEADS will employ a netted distributed architecture with modular components to increase survivability and flexibility of employment in a number of operational configurations. The Patriot Advanced Capability-3 (PAC-3) Missile Segment Enhancement (MSE) missile, as evolved from the current PAC-3 missile's Cost Reduction Initiative (CRI) design, provides a more agile, lethal interceptor missile resulting in substantial missile performance improvement while enhancing Insensitive Munitions (IM) compliance.
MEADS will provide significant improvements in strategic deployability, transportability, mobility, and maneuverability. Its substantially reduced lift requirements enable MEADS to be deployed rapidly with essential combat loads via inter/intra-theater land, sea, and airlift anywhere in the world. MEADS will provide air and missile defense of vital unit of employment and unit of action assets associated with Army maneuver forces. MEADS will provide combatant commanders with an AMD system that is fully transportable by C-130 and C-17 aircraft for deployment during early entry operations. Furthermore, MEADS represents decreased size/weight over the current Patriot system and, with the ability to conduct rapid march order and system emplacement, will enhance maneuverability thereby providing better AMD protection to maneuvering forces. The Army's initial program plan was to ultimately field 16 MEADS Battalions by FY 2030 leading to complete replacement of the U.S. Patriot forces.
The objective MEADS battery, which will be scalable and tailorable to operational requirements, will consist of: the Integrated AMD Battle Command System Tactical Operations Center, enabling distributed system operations and beyond-line-of-sight engagements for maximum protection of supported forces by engaging at longer ranges; a near-vertical launcher capable of transporting and launching up to eight missiles; a Launcher Reloader; the PAC-3 MSE missile; ultra high frequency Surveillance Radar capability that provides 360-degree coverage and near-range detection of targets having low radar cross-section signatures; and two X-band Multi-Function Fire Control
Radars that provide 360-degree coverage and are designed for high-precision handover to the in-flight missile, discrimination capabilities, and short-range target detection and horizon search.
The PAC-3 MSE missile was accepted as the baseline missile for MEADS and is being developed by the U.S. to meet that operational requirement. The PAC-3 MSE improves upon the current PAC-3 CRI missile capability with a higher performance solid rocket motor, modified lethality enhancer, more responsive control surfaces, upgraded guidance software, and IM improvements.

## Table 6
Executive Summary
A. Fire Unit Subprogram:
In February 2011, the DoD decided to continue the MEADS Design and Development (D&D) phase by providing funding up to the agreed Memorandum of Understanding (MoU) cost ceiling of $4B in equivalent U.S. dollars (2004). The U.S. proposed focusing the remaining activities on implementing a "Demonstration of Capabilities" (DoC) effort through 2013 with the remaining MoU funds to provide a meaningful capability for Germany and Italy and a possible future option for the U.S.
The U.S. will continue security oversight for Government Furnished Equipment items until the end of MEADS D&D, such as the U.S.-developed and technology-restricted Exciter and Exportable Missile Model, sensitive U.S. communications and cryptographic equipment, and the Patriot Advanced Capability-3 (PAC-3) Missile Segment Enhancement (MSE) missile. The U.S. developed MEADS technologies will transition to valid FMS cases once those become effective.
With the ramp-down and closeout of direct U.S. support as part of MEADS D&D, Germany has submitted three preliminary FMS requests for support of its future European Follow-on Program, to include the Exciter support case, a PAC-3 MSE flight test support case, and a request for support for MEADS simulation tools, Exportable Missile Model, and cryptographic equipment. These requests are being reviewed by the U.S. Government. The U.S. has also received informally a draft letter of FMS request from Italy which is review awaiting formal submission.
The FY 2014 PB included funds for the final year of the MEADS DoC. Completion of the DoC will bring the MEADS development program to a close under Contract Amendment #28 and will also start activities that support the European Follow-on-Program. Under the DoC, the program will continue verification and testing of the MEADS 360- degree Multi-Function Fire Control Radar and will leverage the ability of the PAC-3 MSE missile to intercept targets from the lightweight, near-vertical MEADS launcher. Data archival efforts will also be completed for all major MEADS elements, to include design documentation, drawings, and specifications with delivery of final archived data scheduled for the 2nd Quarter FY 2015. Planning for the transition of MEADS to an FMS-supported approach will continue in parallel with the DoC execution.
The MEADS system participated in a successful Joint Planning Optic Windmill (JPOW) exercise from May 21 to June 5, 2013. The MEADS system successfully conducted three interoperability experiments, achieving a majority of test objectives and demonstrating capabilities to the North Atlantic Treaty Organization AMD community. The JPOW exercise was the first MEADS event where trained German soldiers operated the system. MEADS was determined to be reliable and the MEADS Link 16 status was rated 'Green'.
The MEADS system successfully executed a dual target intercept mission on November 6, 2013, at White Sands Missile Range (WSMR), New Mexico. The MEADS system concurrently engaged and intercepted the QF-4 and Lance Tactical Ballistic Missile (TBM) targets using three PAC-3 MSE interceptors. All elements of the MEADS system worked as planned and the program achieved all primary objectives.
This is the final SAR submission for the Fire Unit subprogram, because this subprogram is 90% or more expended.
B. Missile Subprogram:
On June 6, 2013, the U.S. Army Lower Tier Project Office successfully conducted the PAC-3 MSE 7-5 Missile Flight Test at WSMR, intercepting a TBM target and an Air Breathing Target with PAC-3 MSE missiles. Patriot ground support equipment (with Post Deployment Build-7 software and Modern Man Stations), operated by soldiers from

## Table 7
the 2/43 Air Defense Battalion, ripple-fired two production representative PAC-3 MSE missiles to intercept a threat representative TBM target in the MSE extended battlespace. This was the second flight test with the Zombie target, designed to substantially reduce the cost of TBM threat representative targets. This test also demonstrated the capability of the Patriot system to detect, track, and kill a low altitude cruise missile surrogate target with a PAC-3 MSE missile. Test data indicates that the flight test mission objectives were successfully achieved. This was the final missile flight test required to support the PAC-3 MSE production decision. The FY 2015 PB includes a program increase of $150M in FY 2014 for procurement of additional MSE missiles to support combatant commanders.
With the termination of the Fire Unit Subprogram in this SAR, the Missile Subprogram will be established as a separate PAC-3 MSE program. On March 27, 2014, the Defense Acquisition Executive signed an Acquisition Decision Memorandum authorizing the PAC-3 MSE program to enter the Production and Deployment phase and to proceed with LRIP. The production APB for PAC-3 MSE will be completed later this year, at which time the program will begin reporting separately from the Patriot/MEADS CAP. The cost estimates for the Missile Subprogram in this report are based on the original program of record.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
Fire Unit
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
Missile
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Explanation of Breach
The cost and schedule breaches for the Missile Subprogram were previously reported in the December 2009 SAR.
APB Breaches
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
Fire Unit
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | AUG 2004 | AUG 2004 | FEB 2005 | AUG 2004
Design & Development Contract Award | SEP 2004 | SEP 2004 | MAR 2005 | SEP 2004
Acquisition Increment 1
Milestone C | OCT 2007 | OCT 2007 | OCT 2008 | OCT 2007
FUE | MAR 2009 | MAR 2009 | MAR 2010 | MAR 2009
IOT&E
Start | MAR 2009 | MAR 2009 | MAR 2010 | MAR 2009
Complete | SEP 2009 | SEP 2009 | SEP 2010 | SEP 2009
Full Rate Production Decision | OCT 2009 | OCT 2009 | OCT 2010 | OCT 2009
Acquisition Increment 2
Milestone C | OCT 2009 | OCT 2009 | OCT 2010 | OCT 2009
Lightweight Launcher FUE | MAR 2011 | MAR 2011 | MAR 2012 | MAR 2011
IOT&E
Start | JUN 2011 | JUN 2011 | JUN 2012 | JUN 2011
Complete | SEP 2011 | SEP 2011 | SEP 2012 | SEP 2011
Full Rate Production Decision | NOV 2011 | NOV 2011 | NOV 2012 | NOV 2011
Acquisition Increment 3
Milestone C | NOV 2012 | NOV 2012 | NOV 2013 | NOV 2012
FUE | SEP 2015 | SEP 2015 | SEP 2016 | SEP 2015
IOT&E
Start | JUN 2016 | JUN 2016 | JUN 2017 | JUN 2016
Complete | DEC 2016 | DEC 2016 | DEC 2017 | DEC 2016
Full Rate Production Decision | MAR 2017 | MAR 2017 | MAR 2018 | MAR 2017
IOC | SEP 2017 | SEP 2017 | SEP 2018 | SEP 2017
Change Explanations
None
Memo
Based on the February 11, 2011, U.S. DoD decision to place a ceiling on MEADS spending at $4B and continue with a modified Design and Development phase in a "Demonstration of Capabilities" effort funded through 2013, the Fire Unit schedule milestones are maintained at the objective dates. FY 2013 was the final year of funding for the Fire Unit Subprogram.
The Defense Acquistion Board approved the Acquisition Strategy for the Patriot/MEADS CAP on August 6, 2004, as follows: Acqusition Increment 1 as the initial MEADS Battle Management Command, Control, Communications, Computers and Intelligence capability fielded to Patriot Battalions; Acquisition Increment 2 fields the MEADS Lightweight Launcher capabililty and the Missile Segment Enhancement capability to current Patriot Battalions; and Acquisition Increment 3 fields the MEADS Surveillance Radars and Multi-Function Fire Control Radars, which provide the MEADS objective capability.

## Table 11
Acronyms and Abbreviations
FUE - First Unit Equipped
IOT&E - Initial Operational Test and Evaluation
Missile
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Acquisition Increment 2
MSE First Intercept | JUN 2008 | JUN 2008 | JUN 2009 | FEB 2010 1
MSE FUE | MAR 2011 | MAR 2011 | MAR 2012 | SEP 2015 1
1APB Breach
Change Explanations
None
Memo
The December 2009 SAR reported breaches to the schedule milestones for the MSE First Intercept and the MSE FUE. The MSE First Intercept and the MSE FUE current estimate breaches were due to the unsuccessful
MSE Guided Test Flight - 1 that occured on March 25, 2009. A successful re-test of the first intercept mission was conducted on February 17, 2010, validating intercept objectives. Additional intercept missions were successfully conducted in March 2011, December 2012, and June 2013.
Acronyms and Abbreviations
FUE - First Unit Equipped
MSE - Missile Segment Enhancement

## Table 12
Performance
Fire Unit
Characteristics | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Identification - ABT | Fire unit will | Fire unit will | Fire unit will | TBD | Fire unit will
Targets | automatically | automatically | automatically |  | automatically
| declare ABT | declare ABT | declare ABT |  | declare ABT
| targets as | targets as | targets as |  | targets as
| friend, foe, | friend, foe, | friend, foe, |  | friend, foe,
| or unknown | or unknown | or unknown |  | or unknown
| using all | using all | using all |  | using all
| available | available | available |  | available
| sources of | sources of | sources of |  | sources of
| information | information | information |  | information
Transportability/Mobility
Drive-on, Drive-off | Drive-on | Drive-on | Drive-on | TBD | Drive-on
| Drive-off | Drive-off | Drive-off |  | Drive-off
| loading and | loading and | loading and |  | loading and
| unloading : | unloading: C- | unloading: C- |  | unloading: C-
| C-5, C-17 | 5, C-17 | 5, C-17 |  | 5, C-17
Roll-on, Roll-off | Roll-on Roll- | Roll-on Roll- | Roll-on Roll- | TBD | Roll-on Roll-
| offloading | offloading | offloading |  | offloading
| and | and | and |  | and
| unloading in | unloading in | unloading in |  | unloading in
| a transport | a transport | a transport |  | a transport
| configuration | configuration | configuration |  | configuration
| on A400M, | on A400M, | on A400M, |  | on A400M,
| C-130 | C-130 | C-130 |  | C-130
Corps Maneuver and | Provide | Provide | Provide | TBD | Provide
Support Elements | continuous | continuous | continuous |  | continuous
| air defense | air defense | air defense |  | air defense
| coverage of | coverage of | coverage of |  | coverage of
| corps | corps | corps |  | corps
| maneuver | maneuver | maneuver |  | maneuver
| and support | and support | and support |  | and support
| elements as | elements as | elements as |  | elements as
| they | they | they |  | they
| advance up | advance up | advance up |  | advance up
| to 400 km | to 400 km | to 250km |  | to 400 km
| per day at a | per day at a | per day at a |  | per day at a
| rate of 50 | rate of 50 | rate of 25 |  | rate of 50
| kmph off- | kmph off- | kmph |  | kmph off-
| road/90 | road/90 |  |  | road/90
| kmph on- | kmph on- |  |  | kmph on-
| road | road |  |  | road
External | By CH-47 | By CH-47 | By CH-47 | TBD | By CH-47

## Table 13
Transportability | and CH-53 class cargo helicopters up to an ambient temp of 70 deg F, 2000 ft alt MSL, over a 30 nm dist ance; assembly and disassembly from a march order to a transport configurat- ion with organic equipment in 15 min | and CH-53 class cargo helicopters up to an ambient temp of 70 deg F, 2000 ft alt MSL, over a 30 nm distance; assembly and disassembly from a march order to a transport configuration with organic equipment in 15 min | and CH-53 class cargo helicopters up to an ambient temp of 70 deg F, 2000 ft alt MSL, over a 30 nm distance; assembly and disassembly from a march order to a transport configuration with organic equipment in 30 min |  | and CH-53 class cargo helicopters up to an ambient temp of 70 deg F, 2000 ft alt MSL, over a 30 nm distance; assembly and disassembly from a march order to a transport configuration with organic equipment in 15 min
Interoperability | Will interoperate with existing and planned National (top- level)/Joint/ Combined Air Defense BMC4I systems of the respective national forces in accordance with each nation's IERs | Will inter- operate with existing and planned National (top- level)/Joint/ Combined Air Defense BMC4I systems of the respective national forces in accordance with each nation's IERs | Will inter- operate with existing and planned National (critical top- level)/Joint/ Combined Air Defense BMC4I systems of the respective national forces in accordance with each nation's IERs | TBD | Will inter- operate with existing and planned National (top- level)/Joint/ Combined Air Defense BMC4I systems of the respective national forces in accordance with each nation's IERs
Flexibility
MEADS in all configurations | Capable of netted distributed and site- centered operations | Capable of netted distributed and site- centered operations | Capable of netted distributed and site- centered operations | TBD | Capable of netted distributed and site- centered operations
MEADS Battalion | Will provide air and missile defense of | Will provide air and missile defense of | Will provide air and missile defense of | TBD | Will provide air and missile defense of

## Table 14
| selected critical assets and organizations located in an operationally equivalent area of 100km by 100km | selected critical assets and organizations located in an operationally equivalent area of 100km by 100km | selected critical assets and organizations located in an operationally equivalent area of 100km by 100km |  | selected critical assets and organizations located in an operationally equivalent area of 100km by 100km
Plug and Fight | Intra/intersyst | Intra/inter- | Intra/inter- | TBD | Intra/inter-
| em plug-and- | system plug- | system plug- |  | system plug-
| fight capable | and-fight | and-fight |  | and-fight
| by | capable by | capable by |  | capable by
| implementing | implementing | implementing |  | implementing
| a MEADS | a MEADS | a MEADS |  | a MEADS
| network | network | network |  | network
| standard to | standard to | standard to |  | standard to
| be able to | be able to | be able to |  | be able to
| dynamically | dynamically | dynamically |  | dynamically
| integrate | integrate | integrate |  | integrate
| MEADS and | MEADS and | MEADS and |  | MEADS and
| non-MEADS | non-MEADS | non-MEADS |  | non-MEADS
| major end | major end | major end |  | major end
| items (that | items (that | items (that |  | items (that
| comply with | comply with | comply with |  | comply with
| MEADS | MEADS | MEADS |  | MEADS
| network | network | network |  | network
| standard) | standard) | standard) |  | standard)
Classified Performance information is provided in the classified annex to this submission.
Requirements Source
Capability Development Document (CDD) (MEADS Increment 1) dated June 14, 2004
Change Explanations
None

## Table 15
Acronyms and Abbreviations
ABT - Air Breathing Threat alt - Altitude
BMC4I - Battle Management Command, Control, Communications, Computers, and Intelligence deg - degrees
F - Fahrenheit ft - feet
IER - Information Exchange Requirement km - Kilometer
kmph - Kilometers per hour min - minute
MSL - Mean Sea Level nm - nautical mile
temp - temperature
Missile
Memo
Classified Performance information for the Missile Subprogram is captured in the classified annex for the Fire Unit Subprogram.

## Table 16
Track to Budget
Fire Unit
RDT&E
Appn |  |  |  |  | BA |  | PE
Army 2040 04 0603869A
Project |  |  |  |  | Name
01B
Patriot/Medium Extended Air Defense System (MEADS)
(Sunk)
Combined Aggregate Program
(CAP)
Army |  | 2040 |  | 5 |  |  | 0604869A
|  | Project |  |  |  |  | Name
M06 Patriot/MEADS Combined Aggregate Program (CAP)
(Sunk)
Procurement
Appn |  |  |  |  | BA |  | PE
Army 2032 02
Line Item |  |  |  |  | Name
C53201 Patriot/MEADS GSE (Sunk)
Missile
RDT&E
Appn |  |  |  |  | BA |  | PE
Army 2040 04 0603869A
Project |  |  |  |  | Name
01B
Patriot/Medium Extended Air Defense System (MEADS) Combined Aggregate Program
(Sunk)
(CAP)
Army | 2040 |  | 5 |  |  | 0604869A
| Project |  |  |  |  | Name
M06 Patriot/MEADS Combined Aggregate Program (CAP)
Army 2040 05 0605456A
PA3 Patriot PAC-3/Missile Segment Enhancement
(Sunk)
(Shared) (Sunk)
Project |  |  |  |  | Name

## Table 17
Procurement
Appn |  | BA | PE
Army | 2032 | 2 | 0605456A
| Line Item |  | Name
| C53101 |  | MSE Missile

## Table 18
Cost and Funding
Cost Summary - Total Program
Total Acquisition Cost and Quantity - Total Program
|  | BY2004 $M |  |  |  |  | BY2004 $M
Appropriation |  | SAR Baseline Dev Est |  | Current APB Development Objective/Threshold |  |  | Current Estimate
TY $M
SAR Baseline Dev Est | Current APB Development Objective |  | Current Estimate
RDT&E |  | 4992.3 |  |  | 4992.3 | -- |  | 3410.7 | 5737 | 5737 | 3897.7
Procurement |  | 17759.1 |  |  | 17759.1 | -- |  | 5908.6 | 24158.4 | 24158.4 | 8718.6
Flyaway |  | -- |  |  | -- | -- |  | 5397.5 | -- | -- | 7972.8
Recurring |  | -- |  |  | -- | -- |  | 5329.1 | -- | -- | 7889.6
Non Recurring |  | -- |  |  | -- | -- |  | 68.4 | -- | -- | 83.2
Support |  | -- |  |  | -- | -- |  | 511.1 | -- | -- | 745.8
Other Support |  | -- |  |  | -- | -- |  | 511.1 | -- | -- | 745.8
Initial Spares |  | -- |  |  | -- | -- |  | 0 | -- | -- | 0
MILCON |  | 0 |  |  | 0 | -- |  | 0 | 0 | 0 | 0
Acq O&M |  | 0 |  |  | 0 | -- |  | 0 | 0 | 0 | 0
Total |  | 22751.4 |  |  | 22751.4 | N/A |  | 9319.3 | 29895.4 | 29895.4 | 12616.3

## Table 19
Cost and Funding
Cost Summary - Fire Unit
Total Acquisition Cost and Quantity - Fire Unit
|  | BY2004 $M | [6 empty] | BY2004 $M
Appropriation |  | SAR Baseline Dev Est |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Dev Est | Current APB Development Objective |  |  | Current Estimate
RDT&E |  | 4531.4 |  |  |  | 4531.4 |  | 5211.1 |  | 2708.8 |  | 5255 | 5255 | 3112.4
Procurement |  | 11999.1 |  |  |  | 11999.1 |  | 13199 |  | 0 |  | 16584.4 | 16584.4 | 0
Flyaway |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Recurring |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Non Recurring |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Support |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Other Support |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
Initial Spares |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 16530.5 |  |  |  | 16530.5 |  | N/A |  | 2708.8 |  | 21839.4 | 21839.4 | 3112.4
Current estimate is based on the February 11, 2011, U.S. DoD decision to place a ceiling on MEADS spending at $4B and continue with a modified Design and Development phase in a "Demonstration of Capabilities"
effort funded through FY 2013. FY 2013 was the final year of funding for the Fire Unit (FU) Subprogram.
Quantity |  |  | SAR Baseline Dev Est |  |  |  | Current APB Development |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  | 0
Procurement |  |  | 48 |  |  |  | 48 |  |  |  | 0
Total |  |  | 48 |  |  |  | 48 |  |  |  | 0
Unit of Measure: The FU is a representative unit of measure defined to include the ground support elements of the objective MEADS system: a Surveillance Radar; two Multi-Function Fire Control Radars; two Battle Management Command, Control, Communications, Computers and Intelligence Tactical Operations Centers; six Launchers; and three Launcher Reloaders. The program FU development estimate quantity is based on the planned objective force of 48 tactical FUs, which comprise 16 Battalions with three FUs each. Unit cost calculations include equipment at the Battalion level, which is above that at the FU level.

## Table 20
Cost Summary - Missile
Total Acquisition Cost and Quantity - Missile
|  | BY2004 $M | [6 empty] | BY2004 $M
Appropriation |  | SAR Baseline Dev Est |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Dev Est | Current APB Development Objective |  |  | Current Estimate
RDT&E |  | 460.9 |  |  |  | 460.9 |  | 530 |  | 1 701.9 |  | 482 | 482 | 785.3
Procurement |  | 5760 |  |  |  | 5760 |  | 6336 |  | 5908.6 |  | 7574 | 7574 | 8718.6
Flyaway |  | -- |  |  |  | -- |  | -- |  | 5397.5 |  | -- | -- | 7972.8
Recurring |  | -- |  |  |  | -- |  | -- |  | 5329.1 |  | -- | -- | 7889.6
Non Recurring |  | -- |  |  |  | -- |  | -- |  | 68.4 |  | -- | -- | 83.2
Support |  | -- |  |  |  | -- |  | -- |  | 511.1 |  | -- | -- | 745.8
Other Support |  | -- |  |  |  | -- |  | -- |  | 511.1 |  | -- | -- | 745.8
Initial Spares |  | -- |  |  |  | -- |  | -- |  | 0 |  | -- | -- | 0
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 6220.9 |  |  |  | 6220.9 |  | N/A |  | 6610.5 |  | 8056 | 8056 | 9503.9
1 APB Breach
The Patriot/MEADS CAP missile procurement funds in FY 2010 - FY 2013 were transferred to the Patriot Advanced Capability-3 (PAC-3) procurement funding line to obtain additional PAC-3 missile quantities.
Quantity |  |  | SAR Baseline Dev Est |  |  |  | Current APB Development |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  | 0
Procurement |  |  | 1528 |  |  |  | 1528 |  |  |  | 1528
Total |  |  | 1528 |  |  |  | 1528 |  |  |  | 1528
Unit of Measure: The Misssile Segment Enhancement is the representative unit of measure for the Missile Subprogram.

## Table 21
Cost and Funding
Funding Summary - Total Program
Appropriation and Quantity Summary - Total Program FY2015 President's Budget / December 2013 SAR (TY$ M)
Appropriation | Prior | FY2014 |  | FY2015 |  | FY2016 |  | FY2017 |  | FY2018 |  | FY2019 |  | To Complete |  | Total
RDT&E | 3897.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3897.7
Procurement | 83.2 |  | 690.4 |  | 384.6 |  | 419.8 |  | 422.6 |  | 458.7 |  | 497.6 |  | 5761.7 | 8718.6
MILCON | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
Acq O&M | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
PB 2015 Total | 3980.9 |  | 690.4 |  | 384.6 |  | 419.8 |  | 422.6 |  | 458.7 |  | 497.6 |  | 5761.7 | 12616.3
PB 2014 Total | 4038.3 |  | 540.4 |  | 540.5 |  | 559.6 |  | 566.8 |  | 655.2 |  | 536.8 |  | 5394.4 | 12832
Delta | -57.4 |  | 150 |  | -155.9 |  | -139.8 |  | -144.2 |  | -196.5 |  | -39.2 |  | 367.3 | -215.7

## Table 22
Cost and Funding
Funding Summary - Fire Unit
Appropriation and Quantity Summary - Fire Unit FY2015 President's Budget / December 2013 SAR (TY$ M)
Appropriation |  | Prior | FY2014 |  |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  |  | To Complete |  | Total
RDT&E | 3112.4 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 3112.4
Procurement | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
MILCON | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
PB 2015 Total | 3112.4 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 3112.4
PB 2014 Total | 3165.1 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 3165.1
Delta | -52.7 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | -52.7
Quantity | Undistributed |  |  |  | Prior |  | FY2014 |  | FY2015 |  | FY2016 |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  | To Complete |  |  | Total
Development | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
Production | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
PB 2015 Total | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
PB 2014 Total | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0
Delta | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0

## Table 23
Funding Summary - Missile
Appropriation and Quantity Summary - Missile
FY2015 President's Budget / December 2013 SAR (TY$ M)
The Army Acquisition Objective for the Patriot Advanced Capability-3 Missile Segment Enhancement is 3,376 missiles.
The cost estimates for the Missile Subprogram in this report are based on the original program of record.
Appropriation |  | Prior | FY2014 |  |  | FY2015 |  |  | FY2016 |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  |  | To Complete |  |  | Total
RDT&E |  | 785.3 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 785.3
Procurement |  | 83.2 |  | 690.4 |  |  | 384.6 |  |  | 419.8 |  | 422.6 |  |  | 458.7 |  |  | 497.6 |  |  | 5761.7 |  |  | 8718.6
MILCON |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Acq O&M |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
PB 2015 Total |  | 868.5 |  | 690.4 |  |  | 384.6 |  |  | 419.8 |  | 422.6 |  |  | 458.7 |  |  | 497.6 |  |  | 5761.7 |  |  | 9503.9
PB 2014 Total |  | 873.2 |  | 540.4 |  |  | 540.5 |  |  | 559.6 |  | 566.8 |  |  | 655.2 |  |  | 536.8 |  |  | 5394.4 |  |  | 9666.9
Delta |  | -4.7 |  | 150 |  |  | -155.9 |  |  | -139.8 |  | -144.2 |  |  | -196.5 |  |  | -39.2 |  |  | 367.3 |  |  | -163
Quantity | Undistributed |  |  |  | Prior |  |  | FY2014 |  | FY2015 | FY2016 |  | FY2017 |  |  | FY2018 |  |  | FY2019 |  |  | To Complete |  |  | Total
Development | 0 |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Production | 0 |  |  |  | 0 |  |  | 86 |  | 70 | 76 |  | 80 |  |  | 88 |  |  | 94 |  |  | 1034 |  |  | 1528
PB 2015 Total | 0 |  |  |  | 0 |  |  | 86 |  | 70 | 76 |  | 80 |  |  | 88 |  |  | 94 |  |  | 1034 |  |  | 1528
PB 2014 Total | 0 |  |  |  | 0 |  |  | 56 |  | 72 | 80 |  | 82 |  |  | 104 |  |  | 108 |  |  | 1026 |  |  | 1528
Delta | 0 |  |  |  | 0 |  |  | 30 |  | -2 | -4 |  | -2 |  |  | -16 |  |  | -14 |  |  | 8 |  |  | 0

## Table 24
Cost and Funding
Annual Funding By Appropriation - Fire Unit
Annual Funding TY$ - Fire Unit
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2004 | -- | -- | -- | -- | -- | -- | 126.9
2005 | -- | -- | -- | -- | -- | -- | 164
2006 | -- | -- | -- | -- | -- | -- | 193
2007 | -- | -- | -- | -- | -- | -- | 211
2008 | -- | -- | -- | -- | -- | -- | 316.3
2009 | -- | -- | -- | -- | -- | -- | 423.7
2010 | -- | -- | -- | -- | -- | -- | 501.1
2011 | -- | -- | -- | -- | -- | -- | 450.6
2012 | -- | -- | -- | -- | -- | -- | 377.6
2013 | -- | -- | -- | -- | -- | -- | 348.2
Subtotal | -- | -- | -- | -- | -- | -- | 3112.4

## Table 25
Annual Funding BY$ - Fire Unit
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2004 $M | Non End Item Recurring Flyaway BY 2004 $M | Non Recurring Flyaway BY 2004 $M | Total Flyaway BY 2004 $M | Total Support BY 2004 $M | Total Program BY 2004 $M
2004 | -- | -- | -- | -- | -- | -- | 124
2005 | -- | -- | -- | -- | -- | -- | 155.7
2006 | -- | -- | -- | -- | -- | -- | 178.3
2007 | -- | -- | -- | -- | -- | -- | 190.4
2008 | -- | -- | -- | -- | -- | -- | 280.1
2009 | -- | -- | -- | -- | -- | -- | 370.4
2010 | -- | -- | -- | -- | -- | -- | 431.5
2011 | -- | -- | -- | -- | -- | -- | 380.5
2012 | -- | -- | -- | -- | -- | -- | 313.8
2013 | -- | -- | -- | -- | -- | -- | 284.1
Subtotal | -- | -- | -- | -- | -- | -- | 2708.8

## Table 26
Annual Funding By Appropriation - Missile
Annual Funding TY$ - Missile
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2004 | -- | -- | -- | -- | -- | -- | 109.9
2005 | -- | -- | -- | -- | -- | -- | 87.3
2006 | -- | -- | -- | -- | -- | -- | 81.4
2007 | -- | -- | -- | -- | -- | -- | 111.9
2008 | -- | -- | -- | -- | -- | -- | 53.5
2009 | -- | -- | -- | -- | -- | -- | 31
2010 | -- | -- | -- | -- | -- | -- | 65.1
2011 | -- | -- | -- | -- | -- | -- | 121.5
2012 | -- | -- | -- | -- | -- | -- | 86.1
2013 | -- | -- | -- | -- | -- | -- | 37.6
Subtotal | -- | -- | -- | -- | -- | -- | 785.3

## Table 27
Annual Funding BY$ - Missile
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2004 $M | Non End Item Recurring Flyaway BY 2004 $M | Non Recurring Flyaway BY 2004 $M | Total Flyaway BY 2004 $M | Total Support BY 2004 $M | Total Program BY 2004 $M
2004 | -- | -- | -- | -- | -- | -- | 107.4
2005 | -- | -- | -- | -- | -- | -- | 82.9
2006 | -- | -- | -- | -- | -- | -- | 75.2
2007 | -- | -- | -- | -- | -- | -- | 101
2008 | -- | -- | -- | -- | -- | -- | 47.4
2009 | -- | -- | -- | -- | -- | -- | 27.1
2010 | -- | -- | -- | -- | -- | -- | 56.1
2011 | -- | -- | -- | -- | -- | -- | 102.6
2012 | -- | -- | -- | -- | -- | -- | 71.5
2013 | -- | -- | -- | -- | -- | -- | 30.7
Subtotal | -- | -- | -- | -- | -- | -- | 701.9

## Table 28
Annual Funding TY$ - Missile
2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2012 | -- | -- | -- | 75 | 75 | -- | 75
2013 | -- | -- | -- | 8.2 | 8.2 | -- | 8.2
2014 | 86 | 603.4 | -- | -- | 603.4 | 87 | 690.4
2015 | 70 | 336.1 | -- | -- | 336.1 | 48.5 | 384.6
2016 | 76 | 377.8 | -- | -- | 377.8 | 42 | 419.8
2017 | 80 | 382 | -- | -- | 382 | 40.6 | 422.6
2018 | 88 | 414.7 | -- | -- | 414.7 | 44 | 458.7
2019 | 94 | 449.8 | -- | -- | 449.8 | 47.8 | 497.6
2020 | 90 | 467.8 | -- | -- | 467.8 | 35.2 | 503
2021 | 90 | 466 | -- | -- | 466 | 36.7 | 502.7
2022 | 90 | 465.8 | -- | -- | 465.8 | 36.7 | 502.5
2023 | 90 | 465.3 | -- | -- | 465.3 | 36.7 | 502
2024 | 90 | 464.7 | -- | -- | 464.7 | 36.7 | 501.4
2025 | 90 | 464.1 | -- | -- | 464.1 | 36.7 | 500.8
2026 | 90 | 463.5 | -- | -- | 463.5 | 36.7 | 500.2
2027 | 90 | 464.5 | -- | -- | 464.5 | 35 | 499.5
2028 | 90 | 464.1 | -- | -- | 464.1 | 34.9 | 499
2029 | 90 | 463.7 | -- | -- | 463.7 | 34.9 | 498.6
2030 | 90 | 463.3 | -- | -- | 463.3 | 34.9 | 498.2
2031 | 44 | 213 | -- | -- | 213 | 16 | 229
2032 | -- | -- | -- | -- | -- | 12.4 | 12.4
2033 | -- | -- | -- | -- | -- | 12.4 | 12.4
Subtotal | 1528 | 7889.6 | -- | 83.2 | 7972.8 | 745.8 | 8718.6

## Table 29
Annual Funding BY$ - Missile
2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2004 $M | Non End Item Recurring Flyaway BY 2004 $M | Non Recurring Flyaway BY 2004 $M | Total Flyaway BY 2004 $M | Total Support BY 2004 $M | Total Program BY 2004 $M
2012 | -- | -- | -- | 61.8 | 61.8 | -- | 61.8
2013 | -- | -- | -- | 6.6 | 6.6 | -- | 6.6
2014 | 86 | 477.6 | -- | -- | 477.6 | 68.8 | 546.4
2015 | 70 | 261.4 | -- | -- | 261.4 | 37.7 | 299.1
2016 | 76 | 288.1 | -- | -- | 288.1 | 32 | 320.1
2017 | 80 | 285.5 | -- | -- | 285.5 | 30.4 | 315.9
2018 | 88 | 303.9 | -- | -- | 303.9 | 32.3 | 336.2
2019 | 94 | 323.2 | -- | -- | 323.2 | 34.3 | 357.5
2020 | 90 | 329.5 | -- | -- | 329.5 | 24.8 | 354.3
2021 | 90 | 321.8 | -- | -- | 321.8 | 25.3 | 347.1
2022 | 90 | 315.4 | -- | -- | 315.4 | 24.8 | 340.2
2023 | 90 | 308.8 | -- | -- | 308.8 | 24.4 | 333.2
2024 | 90 | 302.4 | -- | -- | 302.4 | 23.9 | 326.3
2025 | 90 | 296.1 | -- | -- | 296.1 | 23.4 | 319.5
2026 | 90 | 289.9 | -- | -- | 289.9 | 23 | 312.9
2027 | 90 | 284.8 | -- | -- | 284.8 | 21.5 | 306.3
2028 | 90 | 279 | -- | -- | 279 | 21 | 300
2029 | 90 | 273.3 | -- | -- | 273.3 | 20.6 | 293.9
2030 | 90 | 267.7 | -- | -- | 267.7 | 20.2 | 287.9
2031 | 44 | 120.7 | -- | -- | 120.7 | 9 | 129.7
2032 | -- | -- | -- | -- | -- | 6.9 | 6.9
2033 | -- | -- | -- | -- | -- | 6.8 | 6.8
Subtotal | 1528 | 5329.1 | -- | 68.4 | 5397.5 | 511.1 | 5908.6

## Table 30
Low Rate Initial Production
Fire Unit
| Initial LRIP Decision | Current Total LRIP
Approval Date | 8/6/2004 2/11/2011 7 0 Milestone B ADM DoD Memorandum 2013 2016
Approved Quantity
Reference
Start Year
End Year
The Defense Acquisition Executive approved LRIP quantities for the MEADS objective system Major End Items (MEIs) at Milestone B on August 6, 2004. The LRIP quantities of the MEIs are: 17 Surveillance Radars, 28 Multi- Function Fire Control Radars; eight Battle Management Command, Control, Communications, Computers and Intelligence Tactical Operations Centers; 12 Lightweight Launchers; and six Launcher Reloaders. The LRIP quantities are the minimum required to conduct testing and evaluate performance before Full Rate Production. The Fire Unit (FU) quantities represent the collection of the unique MEIs into operational units. Therefore, FU LRIP quantity based on the approved MEI LRIP quantities is seven FUs.
Based on the February 11, 2011, U.S. DoD decision to place a ceiling on MEADS spending at $4B and continue with a modified Design and Development phase in a "Demonstration of Capabilities" effort funded through
2013, the FU LRIP data, while relevant for historical reference, is no longer valid for the December 2013 SAR.
Missile
| Initial LRIP Decision | Current Total LRIP
Approval Date | 8/6/2004 8/6/2004 148 148 Milestone B ADM Milestone B ADM 2010 2010 2011 2011
Approved Quantity
Reference
Start Year
End Year

## Table 31
Foreign Military Sales
Fire Unit
None
Missile
None
Nuclear Costs
Fire Unit
None
Missile
None

## Table 32
Unit Cost
Fire Unit
Unit Cost Report
|  | BY2004 $M | BY2004 $M
Unit Cost |  | Current UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 16530.5 |  |  | 2708.8
Quantity | 48 |  |  | 0
Unit Cost | 344.385 |  |  | -- |  | --
Average Procurement Unit Cost (APUC)
Cost | 11999.1 |  |  | 0
Quantity | 48 |  |  | 0
Unit Cost | 249.981 |  |  | -- |  | --
|  | BY2004 $M | BY2004 $M
Unit Cost |  | Original UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 16530.5 |  |  | 2708.8
Quantity | 48 |  |  | 0
Unit Cost | 344.385 |  |  | -- |  | --
Average Procurement Unit Cost (APUC)
Cost | 11999.1 |  |  | 0
Quantity | 48 |  |  | 0
Unit Cost | 249.981 |  |  | -- |  | --

## Table 33
Fire Unit
Unit Cost History
[7 empty] | BY2004 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | AUG 2004 |  |  |  | 344.385 |  | 249.981 |  |  | 454.988 |  | 345.508
APB as of January 2006 |  |  | AUG 2004 |  |  |  | 344.385 |  | 249.981 |  |  | 454.988 |  | 345.508
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current APB |  |  | AUG 2004 |  |  |  | 344.385 |  | 249.981 |  |  | 454.988 |  | 345.508
Prior Annual SAR |  |  | DEC 2012 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current Estimate |  |  | DEC 2013 |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Dev Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
454.988 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000

## Table 34
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes | [9 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est | Oth | Spt |  | Total
345.508 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000 0.000
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  | SAR Development Estimate (DE) |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | AUG 2004 |  |  | N/A |  |  | AUG 2004
Milestone C |  |  | N/A |  |  | NOV 2012 |  |  | N/A |  |  | NOV 2012
IOC |  |  | N/A |  |  | SEP 2017 |  |  | N/A |  |  | SEP 2017
Total Cost (TY $M) |  |  | N/A |  |  | 21839.4 |  |  | N/A |  |  | 3112.4
Total Quantity |  |  | N/A |  |  | 48 |  |  | N/A |  |  | 0
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  | 454.988 |  |  | N/A |  |  | N/A
FIRE UNIT:
The Defense Acquisition Board approved program was structured with three increments, each having a separate Milestone C. Increments 1 and 2 are no longer required in accordance with the Army Integrated Air and Missile Defense Acquisition Strategy. The Patriot/MEADS CAP program schedule identifies a Milestone C for the intermediate Acquisition Increments (1 and 2); however, full MEADS objective capability was planned to be achieved at Milestone C for Acquisition Increment 3. Per the U.S. DoD decision on February 11, 2011, funding has been limited to completion of the Design and Development phase. FY 2013 was the final year of funding for the Fire Unit Subprogram.

## Table 35
Missile
Unit Cost Report
|  | BY2004 $M | BY2004 $M
Unit Cost |  | Current UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 6220.9 |  |  | 6610.5
Quantity | 1528 |  |  | 1528
Unit Cost | 4.071 |  |  | 4.326 |  | 6.26
Average Procurement Unit Cost (APUC)
Cost | 5760 |  |  | 5908.6
Quantity | 1528 |  |  | 1528
Unit Cost | 3.77 |  |  | 3.867 |  | 2.57
|  | BY2004 $M | BY2004 $M
Unit Cost |  | Original UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 6220.9 |  |  | 6610.5
Quantity | 1528 |  |  | 1528
Unit Cost | 4.071 |  |  | 4.326 |  | 6.26
Average Procurement Unit Cost (APUC)
Cost | 5760 |  |  | 5908.6
Quantity | 1528 |  |  | 1528
Unit Cost | 3.77 |  |  | 3.867 |  | 2.57

## Table 36
Missile
Unit Cost History
[7 empty] | BY2004 $M |  |  |  |  | TY $M
|  |  | Date |  |  |  | PAUC |  | APUC |  |  | PAUC |  | APUC
Original APB |  |  | AUG 2004 |  |  |  | 4.071 |  | 3.77 |  |  | 5.272 |  | 4.957
APB as of January 2006 |  |  | AUG 2004 |  |  |  | 4.071 |  | 3.77 |  |  | 5.272 |  | 4.957
Revised Original APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Prior APB |  |  | N/A |  |  |  | N/A |  | N/A |  |  | N/A |  | N/A
Current APB |  |  | AUG 2004 |  |  |  | 4.071 |  | 3.77 |  |  | 5.272 |  | 4.957
Prior Annual SAR |  |  | DEC 2012 |  |  |  | 4.442 |  | 3.984 |  |  | 6.327 |  | 5.813
Current Estimate |  |  | DEC 2013 |  |  |  | 4.326 |  | 3.867 |  |  | 6.22 |  | 5.706
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Dev Est | Changes | [11 empty] | PAUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth |  | Spt | Total
5.272 0.189 0.000 0.309 0.000 0.408 0.000 0.042 0.948 6.220

## Table 37
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes | [9 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est | Oth | Spt |  | Total
4.957 0.178 0.000 0.309 0.000 0.220 0.000 0.042 0.749 5.706
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  | SAR Development Estimate (DE) |  |  | SAR Production Estimate (PdE) |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
FUE |  |  | N/A |  |  | MAR 2011 |  |  | N/A |  |  | SEP 2015
Total Cost (TY $M) |  |  | N/A |  |  | 8056 |  |  | N/A |  |  | 9503.9
Total Quantity |  |  | N/A |  |  | 1528 |  |  | N/A |  |  | 1528
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  | 5.272 |  |  | N/A |  |  | 6.22

## Table 38
Cost Variance
Fire Unit
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Dev Est) 5255.0 16584.4 -- 21839.4
Previous Changes
Economic |  | 127.2 |  | -193.6 |  | -- |  | -66.4
Quantity |  | -- |  | -12555.5 |  | -- |  | -12555.5
Schedule |  | -- |  | -86.5 |  | -- |  | -86.5
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -2217.1 |  | -706.7 |  | -- |  | -2923.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -3042.1 |  | -- |  | -3042.1
Subtotal |  | -2089.9 |  | -16584.4 |  | -- |  | -18674.3
Current Changes Economic |  | -7 |  | -- |  | -- |  | -7
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -45.7 |  | -- |  | -- |  | -45.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -52.7 |  | -- |  | -- |  | -52.7
Total Changes |  | -2142.6 |  | -16584.4 |  | -- |  | -18727
CE - Cost Variance |  | 3112.4 |  | -- |  | -- |  | 3112.4
CE - Cost & Funding |  | 3112.4 |  | -- |  | -- |  | 3112.4

## Table 39
Summary Base Year 2004 $M
| RDT&E |  | Proc | MILCON | Total
SAR Baseline (Dev Est) Previous Changes |  | 4531.4 | 11999.1 | -- | 16530.5
Economic |  | -- | -- | -- | --
Quantity |  | -- | -8875.5 | -- | -8875.5
Schedule |  | -- | -148 | -- | -148
Engineering |  | -- | -- | -- | --
Estimating |  | -1785.5 | -795.4 | -- | -2580.9
Other |  | -- | -- | -- | --
Support |  | -- | -2180.2 | -- | -2180.2
Subtotal |  | -1785.5 | -11999.1 | -- | -13784.6
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | -37.1 | -- | -- | -37.1
Other |  | -- | -- | -- | --
Support |  | -- | -- | -- | --
Subtotal |  | -37.1 | -- | -- | -37.1
Total Changes |  | -1822.6 | -11999.1 | -- | -13821.7
CE - Cost Variance |  | 2708.8 | -- | -- | 2708.8
CE - Cost & Funding |  | 2708.8 | -- | -- | 2708.8
Previous Estimate: December 2012

## Table 40
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -7
Adjustment for current and prior escalation. (Estimating) | 5.9 | 7
Decrease in FY 2013 funding due to Congressional reduction. (Estimating) | -43 | -52.7
RDT&E Subtotal | -37.1 | -52.7

## Table 41
Cost Variance
Missile
Summary Then Year $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Dev Est) 482.0 7574.0 -- 8056.0
Previous Changes
Economic |  | 18.5 |  | 325.9 |  | -- |  | 344.4
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 634.8 |  | -- |  | 634.8
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 284.8 |  | 335.2 |  | -- |  | 620
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 11.7 |  | -- |  | 11.7
Subtotal |  | 303.3 |  | 1307.6 |  | -- |  | 1610.9
Current Changes Economic |  | -1.1 |  | -54.2 |  | -- |  | -55.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -162.6 |  | -- |  | -162.6
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 1.1 |  | 1.1 |  | -- |  | 2.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 52.7 |  | -- |  | 52.7
Subtotal |  | -- |  | -163 |  | -- |  | -163
Total Changes |  | 303.3 |  | 1144.6 |  | -- |  | 1447.9
CE - Cost Variance |  | 785.3 |  | 8718.6 |  | -- |  | 9503.9
CE - Cost & Funding |  | 785.3 |  | 8718.6 |  | -- |  | 9503.9

## Table 42
Summary Base Year 2004 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Dev Est) 460.9 5760.0 -- 6220.9
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 48.6 |  | -- |  | 48.6
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 240.1 |  | 302.9 |  | -- |  | 543
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -24.6 |  | -- |  | -24.6
Subtotal |  | 240.1 |  | 326.9 |  | -- |  | 567
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -208.2 |  | -- |  | -208.2
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 0.9 |  | 1.3 |  | -- |  | 2.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 28.6 |  | -- |  | 28.6
Subtotal |  | 0.9 |  | -178.3 |  | -- |  | -177.4
Total Changes |  | 241 |  | 148.6 |  | -- |  | 389.6
CE - Cost Variance |  | 701.9 |  | 5908.6 |  | -- |  | 6610.5
CE - Cost & Funding |  | 701.9 |  | 5908.6 |  | -- |  | 6610.5
Previous Estimate: December 2012

## Table 43
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -1.1
Adjustment for current and prior escalation. (Estimating) | 0.9 | 1.1
RDT&E Subtotal | 0.9 | 0
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -54.2
Stretch-out of procurement buy profile in FY 2020 through FY 2033. (Schedule) (Schedule)
0.0 +93.3
Adjustment for current and prior escalation. (Estimating) +4.8 +5.8
Additional Schedule Variance due to the acceleration of 30 missiles in FY 2014 (procurement changed from 56 to 86 missiles). (Schedule)
-208.2 -255.9
Decrease in FY 2013 funding due to Congressional reduction. (Estimating) -3.5 -4.7
Adjustment for current and prior escalation. (Support) +0.5 +0.8
Increase in Other Support due to stretch-out of procurement buy profile. (Support) (Support)
+28.1 +51.9
Procurement Subtotal -178.3 -163.0

## Table 44
Contracts
Appropriation: RDT&E
Contract Name Design & Development
Contractor MEADS International Inc.
Contractor Location 5600 W Sand Lake Road Orlando, FL 32819
Contract Number, Type NAMEAD-04-C-6000, CPFF
Award Date September 28, 2004
Definitization Date February 16, 2005
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
3400.0 N/A 0 3653.0 N/A 0 3653.0 3653.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications implemented for emerging program requirements, which included Missile Segment Enhancement integration, extended risk reduction actvities, and flight test activities.
Variance |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2014) |  |  |  | -2.5 |  |  |  | -3.1
Previous Cumulative Variances |  |  |  | 29.9 |  |  |  | -15.3
Net Change |  |  |  | -32.4 |  |  |  | 12.2
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to additional Integrated Product Team (IPT) support requirements leading up to the November 2013 flight test and continued activities to support additional testing at the White Sands Missile Range, New Mexico, as well as continued software build work for FY 2014 demonstrations.
The favorable net change in the schedule variance is due to the fact that IPTs implemented revised contract performance measurement baselines to reflect current flight test dates and revised test requirements.

## Table 45
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.
The North Atlantic Treaty Organization Medium Extended Air Defense System Management Agency (NAMEADSMA) awarded a contract on May 5, 2005, to MEADS International (MI) for the Design and Development (D&D) of MEADS. The assigned contract number is NAMEADSMO/CF/6000/04. NAMEADSMA manages the program on behalf of the participating nations of the U.S., Italy, and Germany. MI is a multi-national joint venture with MBDA-Italia, the European Aeronatuic Defence and Space Company, MBDA-Lenkflugkorpersysteme (LFK) in Germany, and Lockheed Martin Corporation in the U.S.
The initial contract price represents the value of the D&D contract with international participation by the U.S., Italy, and Germany. The D&D contract price, including European partners' shares, is $3.4B, broken out as $1,982.0M (U.S.), 848M Euros (Germany), and 558M Euros (Italy).
On March 26, 2013, the President signed the FY 2014 PB, which included the $380.8M in FY 2013 to fund the final year of a MEADS "Demonstration of Capabilities" effort and bring the MEADS development program to closure.

## Table 46
Appropriation: RDT&E
Contract Name MSE Follow on Test Prg
Contractor Lockheed Martin Corporation
Contractor Location 1701 W Marshall Drive Dallas, TX 75265
Contract Number, Type W31P4Q-07-G-0001/12, CPFF
Award Date August 23, 2010
Definitization Date July 18, 2011
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
49.1 N/A N/A 51.0 N/A N/A 77.4 78.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a contract modification to extend the period of performance.
However, the Contractor and Program Manager Estimated Prices at Completion have increased due to an undefinitized contract modification for components for four test missiles. The effort was placed on contract as authorized unpriced work; therefore, until definitized, the Current Contract Price Target is unchanged.
Variance |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/26/2014) |  |  |  | -0.1 |  |  |  | -0.5
Previous Cumulative Variances |  |  |  | 1.2 |  |  |  | -1.4
Net Change |  |  |  | -1.3 |  |  |  | 0.9
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to additional manpower added to support the preparation for the Flight Test 7-5. Manpower increased due to added effort to procure and assemble four Patriot Advanced Capability-3 (PAC-3) Missile Segment Enhancement (MSE) missiles.
The favorable net change in the schedule variance is due to successful Flight Tests 7-4 and 7-5 with minimal remaining tasks to be completed.
Contract Comments
The purpose of this effort is to conduct two flight test campaigns to intercept two Tactical Ballistic Missiles and one Air Breathing Threat representative target for Patriot. The contractor shall provide and utilize five PAC-3 MSE missiles representing the MSE production configuration that incorporates the final configuration of PAC-3 obsolescence upgrades.

## Table 47
Appropriation: Procurement
Contract Name MSE IPF
Contractor Lockheed Martin Corporation
Contractor Location 1701 W Marshall Drive Dallas, TX 75265
Contract Number, Type W31P4Q-12-C-0001, CPIF
Award Date July 02, 2012
Definitization Date July 02, 2012
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
69.0 N/A 0 69.0 N/A 0 77.4 78.2
Variance |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/26/2014) |  |  |  | 2.2 |  |  |  | -9.3
Previous Cumulative Variances |  |  |  | 0.1 |  |  |  | 0.2
Net Change |  |  |  | 2.1 |  |  |  | -9.5
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to contract requirements not being met, which delayed major purchase orders during the 12-month period.
The unfavorable net change in the schedule variance is due to delays in tool fabrication and development of control surfaces during the first six months. During the last six-month period, delays were driven by tool fabrication, material delivery and tool orders, and Dallas production operations tool capacity issues. Aerojet also experienced delays with its subtier suppliers ordering materials and tools.
Contract Comments
The purpose of the effort is to set forth the requirements for the manufacture, modification, and/or procurement of production special tooling, special test equipment, and special inspection equipment to support the Patriot Advanced Capability (PAC-3) Missile Segment Enhancement (MSE) missile program. The Initial Production Facilities (IPF) production equipment is to be proved-out and in place 24 months following contract award. The
PAC-3 MSE IPF contract stresses production of MSE missiles at the lowest feasible life-cycle cost. The objective of the PAC-3 MSE IPF is to establish and sustain the capability to produce PAC-3 MSE missiles at a rate of up to 20 per month. The contract was awarded and definitized on July 2, 2012, with a total contract value of $69.0M.

## Table 48
Deliveries and Expenditures Fire Unit
Delivered to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 0 | --
Total Program Quantity Delivered | 0 | 0 | 0 | --
Expended and Appropriated (TY $M)
Total Acquisition Cost | 3112.4 | Years Appropriated |  | 10
Expended to Date | 3149.9 | Percent Years Appropriated |  | 100%
Percent Expended | 101.2% | Appropriated to Date |  | 3112.4
Total Funding Years | 10 | Percent Appropriated |  | 100%
The above data is current as of 3/24/2014.
Missile
Delivered to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 1528 | 0%
Total Program Quantity Delivered | 0 | 0 | 1528 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost | 9503.9 | Years Appropriated |  | 11
Expended to Date | 726.2 | Percent Years Appropriated |  | 36.67%
Percent Expended | 7.64% | Appropriated to Date |  | 1558.9
Total Funding Years | 30 | Percent Appropriated |  | 16.4%
The above data is current as of 3/24/2014.

## Table 49
Operating and Support Cost
Fire Unit
Assumptions and Ground Rules
Cost Estimate Reference:
The U.S. DoD made a decision on February 11, 2011, to place a ceiling on MEADS spending at $4B and continue with a modified Design and Development phase resulting in a "Demonstration of Capabilities" effort funded through FY 2013. FY 2013 was the final year of funding for the Fire Unit (FU) Subprogram.
Therefore, since this program will not go into production and fielding, there are no FU O&S costs.
Sustainment Strategy: None
Antecedent Information: None
Unitized O&S Costs BY2004 $M
Cost Element |  | Fire Unit Average Annual Cost Of All Fire Units |  | No Antecedent System (Antecedent)
Unit-Level Manpower |  | 0 |  | 0
Unit Operations |  | 0 |  | 0
Maintenance |  | 0 |  | 0
Sustaining Support |  | 0 |  | 0
Continuing System Improvements |  | 0 |  | 0
Indirect Support |  | 0 |  | 0
Other |  | 0 |  | 0
Total |  | -- |  | --
Unitized Cost Comments: None
Total O&S Cost $M
| Current Development APB Objective/Threshold |  | Current Estimate
| Fire Unit |  | Fire Unit |  | No Antecedent System (Antecedent)
Base Year | 33094.4 36403.8 0.0 N/A
Then Year | 61902.2 N/A 0.0 N/A
Total O&S Costs Comments: None

## Table 50
Disposal Costs:
Disposal costs are TBD.

## Table 51
Missile
Assumptions and Ground Rules
Cost Estimate Reference:
The Production Missile Segment Enhancement (MSE) O&S cost estimate was established in the 2004 APB in support of the Patriot/MEADS CAP Milestone B decision.
The current O&S cost estimate for the Missile Subprogram (MSE) has been updated since the prior annual SAR to reflect the program procurement quantity current estimate. The estimate was completed in Automated Cost Estimating-Integrated Tools. The O&S estimate covers a life cycle of 44 years, FY 2016 through FY 2060, and includes the cost to support the Patriot Advanced Capability (PAC-3) MSE missile. The estimate is based on analogous costs for repair and recertification of the PAC-3 missile. The estimate also uses an analogous historical factor to estimate the quantity of missiles that will require annual repair and the program losses for operational use, flight testing, and planned field surveillance.
Sustainment Strategy:
The PAC-3 MSE missile procurement quantity is 1,528. The missile will be recertified twice, at ten-year intervals, within its 30-year planned service life. Contractor Logistics Support (CLS) is used to support maintenance and repair of the PAC-3 MSE certified missile rounds. The missile is a self-contained major end item and does not require sustainment in the field. There are no intermediate-level maintenance tasks for the missile and the organic depot/agency does not possess the required repair capacity, tools, and test equipment for depot level sustainment, supply support, and software support. Missile subsystems are required to be shipped to subcontractor facilities for repair and replacement of subsystem components. The Government has limited technical data rights and relies on CLS for missile sustainment.
Antecedent Information:
There is no antecedent system.
Unitized O&S Costs BY2004 $M
Cost Element | Missile Average Annual Cost Of All Missiles | No Antecedent System (Antecedent)
Unit-Level Manpower | 0 | 0
Unit Operations | 0 | 0
Maintenance | 50.7 | 0
Sustaining Support | 5.5 | 0
Continuing System Improvements | 7.2 | 0
Indirect Support | 13.3 | 0
Other | 0 | 0
Total | 76.7 | --
Unitized Cost Comments:
Unitized costs are calculated based on total O&S current cost estimate of $3,373.9M (BY$ 2004) distributed over a planned service life of 44 years. The Unitized Annual O&S Costs reflect O&S for total inventory per year of 1,528 missiles (76.7 annual missile cost x 44-year service life).

## Table 52
Total O&S Cost $M
| Current Development APB Objective/Threshold | Current Estimate
| Missile | Missile | No Antecedent System (Antecedent)
Base Year | 4582.6 5040.9 3373.9 N/A
Then Year | 8571.8 N/A 7169.9 N/A
Total O&S Costs Comments:
The differences between the current estimate and the APB are attributed to a change in quantity and refinement of the estimate using actual cost.
Disposal Costs:
Disposal costs are TBD.