## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-429
VH-92A Presidential Helicopter (VH-92A)
As of June 30, 2014
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 21
Unit Cost 22
Cost Variance 25
Contracts 28
Deliveries and Expenditures 29
Operating and Support Cost 30

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Presidential Helicopter Fleet Replacement (VXX)
DoD Component
Navy
Responsible Office
Col Robert Pridgen 48202 Bronson Road
Building 2805
Patuxent River, MD 20670
robert.d.pridgen@navy.mil
Phone: 301-757-5782
Fax: 301-757-7999
DSN Phone: DSN Fax:
Date
Assigned: July 2, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 17, 2014
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 17, 2014

## Table 6
Mission and Description
The Presidential Helicopter Fleet Replacement (VXX) program mission is to provide safe, reliable, and timely transportation for the President, Vice President, Foreign Heads of State, and other official parties as directed by the Director of the White House Military Office. Presidential helicopter transportation requirements are executed by Marine Helicopter Squadron One (HMX-1) and support the President worldwide and the Vice President primarily inside the National Capital Region. Mission tasking encompasses two (2) main types of missions, administrative lift (Mission Tasking 1) and contingency operations (Mission Tasking 2). The VXX platform will replace both In-Service aircraft (VH-3D and VH-60N) and is based on Sikorsky’s commercial S-92A helicopter. The acquisition strategy for the VXX program involves integration of mature government- defined mission systems and an executive interior into the existing S-92A air vehicle.

## Table 7
Executive Summary
This is the initial SAR submission for the Presidential Helicopter Fleet Replacement (VXX) program. After successfully completing the Milestone B Defense Acquisition Board review, the Under Secretary of Defense (Acquisition, Technology and Logistics) (USD(AT&L)) approved the program to enter the Engineering and Manufacturing Development (EMD) phase in an Acquisition Decision Memorandum dated April 17, 2014. The APB was approved on April 17, 2014, and a Fixed Price Incentive Firm contract was competitively awarded to Sikorsky Aircraft Corporation on May 7, 2014. A total quantity of 23 aircraft will be procured, consisting of 21 operational aircraft and 2 test aircraft.
In accordance with section 2366b(e) of title10, United States Code, the VXX program has received a waiver for the requirement to conduct a Preliminary Design Review (PDR) and a post-PDR assessment prior to Milestone B. As documented in the Congressional notification letters dated April 17, 2014, this provision was waived because delaying the start of EMD until completion of the PDR and post-PDR assessment would unnecessarily cause a significant delay and cost increase to replace the existing, aging aircraft with a modern aircraft utilizing advanced technologies that provide capability improvements. A delay in availability of the aircraft will affect initial operational capability and will not meet the critical national security objective to deliver the replacement for the existing Presidential helicopter by FY 2020. The USD (AT&L) will continue to review the program annually until the program satisfies all certification requirements.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Materiel Development Decision | Jun 2010 | Jun 2010 | Jun 2010 | Jun 2010
Pre-EMD | Mar 2013 | Mar 2013 | Mar 2013 | Mar 2013
Milestone B | Mar 2014 | Mar 2014 | Sep 2014 | Apr 2014
Critical Design Review | Jul 2016 | Jul 2016 | Jan 2017 | Jul 2016
Milestone C | Jan 2019 | Jan 2019 | Jul 2019 | Jan 2019
IOT&E Complete | Mar 2020 | Mar 2020 | Sep 2020 | Mar 2020
IOC | Jul 2020 | Jul 2020 | Jan 2021 | Jul 2020
FRP Decision | May 2021 | May 2021 | Nov 2021 | May 2021
Full Operational Capability | Jul 2022 | Jul 2022 | Jan 2023 | Jul 2022
Change Explanations
Acronyms and Abbreviations
EMD - Engineering and Manufacturing Development FRP - Full Rate Production
IOT&E - Initial Operational Test & Evaluation

## Table 10
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Passenger Seating and Lift Capacity
(Objective= Threshold) MT-1: 14 passengers MT-2 | (Objective= Threshold) MT-1: 14 passengers MT-2 | MT-1: 12 passengers MT-2: 14 passengers | TBD | MT-1: 12 passengers MT-2: 14 passengers
Range (Operational Day)
MT-1 NCR, NCR Return: >100 NM MT-1 CONUS/OCONUS: >200 NM MT-2: >300 NM | MT-1 NCR, NCR Return: >100 NM MT-1 CONUS/OCONUS: >200 NM MT-2: >300 NM | MT-1 NCR, NCR Return: >50 NM MT-1 CONUS/OCONUS: >150 NM MT-2: >250 NM | TBD | MT-1 NCR, NCR Return: >50 NM MT-1 CONUS/OCONUS: >150 NM MT-2: >250 NM
Hover Performance
HOGE with mission payload and other required equipment (High Hot Day) | HOGE with mission payload and other required equipment (High Hot Day) | HOGE with mission payload and other required equipment (Operational Day) | TBD | HOGE with mission payload and other required equipment (Operational Day)
Transportability
(Objective= Threshold) MT-2: (1) MT-2 aircraft and all required equipment, personnel (29), and SE necessary to execute deployed maintenance and mission requirements shall be transportable using (1) C-17. | (Objective= Threshold) MT-2: (1) MT-2 aircraft and all required equipment, personnel (29), and SE necessary to execute deployed maintenance and mission requirements shall be transportable using (1) C-17. | MT-2: (1) MT-2 aircraft and all required equipment, personnel (29), and SE necessary to execute deployed maintenance and mission requirements shall be transportable using (1) C-17. | TBD | MT-2: (1) MT-2 aircraft and all required equipment, personnel (29), and SE necessary to execute deployed maintenance and mission requirements shall be transportable using (1) C-17.
Landing Zone Suitability
(Objective= Threshold) Maintain at least a 50 foot obstacle clearance during all phases of approach, landing, take- off, and departure from the existing White House South Lawn. | (Objective= Threshold) Maintain at least a 50 foot obstacle clearance during all phases of approach, landing, take- off, and departure from the existing White House South Lawn. | Maintain at least a 50 foot obstacle clearance during all phases of approach, landing, take -off, and departure from the existing White House South Lawn. | TBD | Maintain at least a 50 foot obstacle clearance during all phases of approach, landing, take -off, and departure from the existing White House South Lawn.
Sustainment: Materiel Availability - Am, Operational Availability -Ao
Am ≥ 59% MT-1: Ao ≥ 85% MT-2: Ao ≥ 85% | Am ≥ 59% MT-1: Ao ≥ 85% MT-2: Ao ≥ 85% | Am ≥ 57% MT-1: Ao ≥ 80% MT-2: Ao ≥ 83% | TBD | Am ≥ 57% MT-1: Ao ≥ 80% MT-2: Ao ≥ 83%
Training

## Table 11
(Objective= Threshold) Reduce the overall time to train for pilots and crew chiefs from current In-Service aircraft time to train utilizing a Systems Approach to Training. | (Objective= Threshold) Reduce the overall time to train for pilots and crew chiefs from current In-Service aircraft time to train utilizing a Systems Approach to Training. | Reduce the overall time to train for pilots and crew chiefs from current In-Service aircraft time to train utilizing a Systems Approach to Training. | TBD | Reduce the overall time to train for pilots and crew chiefs from current In-Service aircraft time to train utilizing a Systems Approach to Training.
Net-Ready
(Objective= Threshold) | (Objective= Threshold) | Support net-centric | TBD | Support net-centric
Support net-centric | Support net-centric | military operations |  | military operations
military operations Enter | military operations Enter | Enter and be managed |  | Enter and be managed
and be managed on the | and be managed on the | on the network |  | on the network
network Exchanges | network Exchanges | Exchanges information. |  | Exchanges information.
information. | information.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Development Document (CDD) dated January 3, 2013
Change Explanations
None
Notes
With J-4 concurrence and as documented in the VXX CDD, Energy KPP is not applicable for VXX. Net Ready KPP Products are detailed in the VXX CDD, Appendix A.
The VXX program was planned and budgeted to the performance threshold.
Acronyms and Abbreviations
Am - Materiel Availability Ao - Operational Availability
CONUS - Continental United States HOGE - Hover out of Ground Effect KPP - Key Performance Parameter
MT-1 - Mission Tasking 1 (administrative lift)
MT-2 - Mission Tasking 2 (contingency operations) NCR - National Capital Region
NM - Nautical Mile
OCONUS - Outside the Continental United States SE - Support Equipment

## Table 12
Track to Budget
RDT&E
Appn |  | BA | PE
Navy 1319 05 0604273N
Project | Name
3300 Presidential Helicopter (VXX)
Procurement
Appn |  | BA | PE
Navy 1506 04 0901212M
Line Item | Name
0455 VH-XX Executive Helo

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2014 $M | [6 empty] | BY 2014 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 2606.1 |  |  | 2606.1 | 2866.7 |  |  | 2601.8 |  | 2805.7 |  |  | 2805.7 |  | 2805.7
Procurement |  | 2043.6 |  |  | 2043.6 | 2248 |  |  | 2037.4 |  | 2379 |  |  | 2379 |  | 2379
Flyaway |  | -- |  |  | -- | -- |  |  | 1468.7 |  | -- |  |  | -- |  | 1712.3
Recurring |  | -- |  |  | -- | -- |  |  | 1468.7 |  | -- |  |  | -- |  | 1712.3
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 568.7 |  | -- |  |  | -- |  | 666.7
Other Support |  | -- |  |  | -- | -- |  |  | 302.8 |  | -- |  |  | -- |  | 357.1
Initial Spares |  | -- |  |  | -- | -- |  |  | 265.9 |  | -- |  |  | -- |  | 309.6
MILCON |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 4649.7 |  |  | 4649.7 | N/A |  |  | 4639.2 |  | 5184.7 |  |  | 5184.7 |  | 5184.7
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current APB cost estimate provides sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk and external interference. It is consistent with average resource expenditures on historical efforts of similar size, scope, and complexity and represents a notional 50% confidence level.
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 6 |  |  |  | 6 |  |  |  |  | 6
Procurement |  |  | 17 |  |  |  | 17 |  |  |  |  | 17
Total |  |  | 23 |  |  |  | 23 |  |  |  |  | 23

## Table 14
Cost and Funding
Funding Summary
Appropriation Summary
Jun 2014 Exception SAR (TY $M)
Appropriation | Prior | FY 2014 |  | FY 2015 |  | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | To Complete |  | Total
RDT&E | 202.1 | 94.2 |  | 388.1 |  | 582.1 |  | 614.6 |  | 415.9 |  | 276.7 |  | 232 |  | 2805.7
Procurement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 795.6 |  | 1583.4 |  | 2379
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Jun 2014 Total | 202.1 | 94.2 |  | 388.1 |  | 582.1 |  | 614.6 |  | 415.9 |  | 1072.3 |  | 1815.4 |  | 5184.7
| -- | -- |  | -- |  | -- |  | -- |  | -- |  | -- |  | -- |  | --
Quantity Summary
Jun 2014 Exception SAR (TY $M)
Quantity | Undistributed |  | Prior |  | FY 2014 | FY 2015 | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | To Complete |  | Total
Development | 6 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 6 |  | 11 |  | 17
Jun 2014 Total | 6 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 6 |  | 11 |  | 23
| -- |  | -- |  | -- | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 73.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 94.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 388.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 582.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 614.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 415.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 276.7
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 135.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.8
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.6
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.9
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.2
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.2
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.2
Subtotal |  | 6 | -- |  | -- |  | -- |  | -- |  | -- |  | 2805.7

## Table 16
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 76
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 92.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 372.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 548.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 567.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 376.5
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 245.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.2
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.1
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.7
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.9
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.7
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.4
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.4
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
Subtotal |  | 6 | -- |  | -- |  | -- |  | -- |  | -- |  | 2601.8

## Table 17
For RDT&E aircraft, 4 will support Initial Operational Test & Evaluation and then transition to operational status. The other 2 aircraft will remain test and evaluation assets.

## Table 18
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | 6 | 594.6 |  | -- |  | -- |  | 594.6 |  | 201 |  | 795.6
2020 |  | 6 | 596.7 |  | -- |  | -- |  | 596.7 |  | 183.4 |  | 780.1
2021 |  | 5 | 521 |  | -- |  | -- |  | 521 |  | 229.9 |  | 750.9
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | 36 |  | 36
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | 16.4 |  | 16.4
Subtotal |  | 17 | 1712.3 |  | -- |  | -- |  | 1712.3 |  | 666.7 |  | 2379

## Table 19
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | 6 | 519.7 |  | -- |  | -- |  | 519.7 |  | 175.7 |  | 695.4
2020 |  | 6 | 511.3 |  | -- |  | -- |  | 511.3 |  | 157.1 |  | 668.4
2021 |  | 5 | 437.7 |  | -- |  | -- |  | 437.7 |  | 193.1 |  | 630.8
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | 29.6 |  | 29.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | 13.2 |  | 13.2
Subtotal |  | 17 | 1468.7 |  | -- |  | -- |  | 1468.7 |  | 568.7 |  | 2037.4

## Table 20
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2014-04-17 | 2014-04-17
Approved Quantity | 12 | 12
Reference | Milestone B ADM | Milestone B ADM
Start Year | 2019 | 2019
End Year | 2022 | 2022

## Table 21
Foreign Military Sales
None
Nuclear Costs
None

## Table 22
Unit Cost
Unit Cost Report
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Current UCR Baseline (Apr 2014 APB) | Current Estimate (Jun 2014 SAR)
Program Acquisition Unit Cost
Cost | 4649.7 |  |  | 4639.2
Quantity | 23 |  |  | 23
Item | 202.161 |  |  | 201.704 |  | -0.23
Average Procurement Unit Cost
Cost | 2043.6 |  |  | 2037.4
Quantity | 17 |  |  | 17
Unit Cost | 120.212 |  |  | 119.847 |  | -0.3
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Original UCR Baseline (Apr 2014 APB) | Current Estimate (Jun 2014 SAR)
Program Acquisition Unit Cost
Cost | 4649.7 |  |  | 4639.2
Quantity | 23 |  |  | 23
Unit Cost | 202.161 |  |  | 201.704 |  | -0.23
Average Procurement Unit Cost
Cost | 2043.6 |  |  | 2037.4
Quantity | 17 |  |  | 17
Unit Cost | 120.212 |  |  | 119.847 |  | -0.3

## Table 23
Unit Cost History
Item |  |  |  |  | Date |  | BY 2014 $M | [5 empty] | TY $M
[7 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Apr 2014 |  |  |  | 202.161 |  |  | 120.212 |  |  |  | 225.422 |  |  | 139.941
APB as of January 2006 |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Current APB |  |  | Apr 2014 |  |  |  | 202.161 |  |  | 120.212 |  |  |  | 225.422 |  |  | 139.941
Prior Annual SAR |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Current Estimate |  |  | Jun 2014 |  |  |  | 201.704 |  |  | 119.847 |  |  |  | 225.422 |  |  | 139.941
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est | Oth |  |  | Spt | Total
225.422 0.583 0.000 0.000 0.000 -0.992 0.000 0.409 0.000 225.422
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est | Oth |  |  | Spt | Total
139.941 0.435 0.000 0.000 0.000 -0.988 0.000 0.553 0.000 139.941

## Table 24
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Mar 2014 | N/A | Apr 2014
Milestone C | N/A | Jan 2019 | N/A | Jan 2019
IOC | N/A | Jul 2020 | N/A | Jul 2020
Total Cost (TY $M) | N/A | 5184.7 | N/A | 5184.7
Total Quantity | N/A | 23 | N/A | 23
PAUC | N/A | 225.422 | N/A | 225.422

## Table 25
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
2805.7 2379.0 -- 5184.7
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | -- |  | -- |  | --
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -- |  | -- |  | -- |  | --
Current Changes Economic |  | 6 |  | 7.4 |  | -- |  | 13.4
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -6 |  | -16.8 |  | -- |  | -22.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 9.4 |  | -- |  | 9.4
Subtotal |  | -- |  | -- |  | -- |  | --
Total Changes |  | -- |  | -- |  | -- |  | --
Current Estimate |  | 2805.7 |  | 2379 |  | -- |  | 5184.7

## Table 26
Summary BY 2014 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
2606.1 2043.6 -- 4649.7
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | -- |  | -- |  | --
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | -- |  | -- |  | -- |  | --
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -4.3 |  | -14.3 |  | -- |  | -18.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 8.1 |  | -- |  | 8.1
Subtotal |  | -4.3 |  | -6.2 |  | -- |  | -10.5
Total Changes |  | -4.3 |  | -6.2 |  | -- |  | -10.5
Current Estimate |  | 2601.8 |  | 2037.4 |  | -- |  | 4639.2
Initial SAR - Above variances (if any) reflect changes since the SAR Baseline/APB.
SAR Baseline Reference: Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 17, 2014

## Table 27
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | 6
Adjustment for current and prior escalation. (Estimating) |  | -1.5 | -1.5
Revised estimate to align with FY 2015 PB. (Estimating) |  | 1.2 | 0
Revised estimate to reflect the application of new outyear inflation indices (Estimating) |  | -4 | -4.5
RDT&E Subtotal |  | -4.3 | 0
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A +7.4
Revised estimate to align with FY 2015 PB. (Estimating) +0.2 0.0
Realignment of Airframe Non-Recurring Engineering costs to Support; these are dollars intended for Interim Contract Support (ICS) to System Demonstration Test Article (SDTA) aircraft. (Estimating)
-9.8 -11.6
Revised estimate to reflect the application of new outyear inflation indices. (Estimating) | -4.7 |  |  | -5.2
Increase in ICS for SDTA aircraft. (Support) | 5.9 |  |  | 7.2
Increase in Initial Spares to align with current requirement. (Support) | 2.2 |  |  | 2.2
Procurement Subtotal | -6.2 |  |  | 0

## Table 28
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: Presidential Helicopter Replacement Program (EMD)
Contractor: Sikorsky Aircraft Corp.
Contractor Location: 6900 Main Street PO Box 9731
Stratford, CT 06615-9131
Contract Number: N00019-14-C-0050
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: May 07, 2014
Definitization Date: May 07, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1464.7 1559.5 6 1464.7 1559.5 6 1464.7 1464.7
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (6/7/2014) 0.0 0.0
Previous Cumulative Variances -- --
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
The Engineering and Manufacturing Development (EMD) Fixed Price Incentive Firm (FPIF) type contract was awarded May 2014, and cost/schedule variance reporting will commence August 2014.

## Table 29
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 6 | 0%
Production | 0 | 0 | 17 | 0%
Total Program Quantity Delivered | 0 | 0 | 23 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
5184.7
198.8
3.83%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
5
23.81%
296.3
5.71%
The above data is current as of June 24, 2014.

## Table 30
Operating and Support Cost
Assumptions and Ground Rules
Cost Estimate Reference:
- Estimate Source: Department of Navy Service Cost Position approved January 16, 2014
Sustainment Strategy:
- Organizational, limited Intermediate and Depot level maintenance capabilities
- Depot level contractor maintenance support for depot level repairables
- Organic depot level Integrated Maintenance Program for aircraft rework
- Contractor in-service engineering support
- Helicopter Service Life: 40 years
- Estimate Duration: FY 2021 to 2062
- Aircraft Attrition: 1 aircraft over the life of the program
- Aircraft Pipeline Factor: 19% of Total Aircraft Inventory (TAI)
- Total Helicopters Sustained: 21
- Squadrons: Marine Helicopter Squadron One (HMX-1)
- Helicopters per (active) squadron: 16
- Monthly Flight Hours per Helicopter: 19.8
- Total TAI Helicopter Years: 840
- Total Primary Authorized Aircraft Helicopter Years: 648
Antecedent Information:
- Antecedent VH-3D/VH-60N data representative of FY 2010 to FY 2012 average of Visibility And Management of Operating and Support Cost reported cost data.

## Table 31
Unitized O&S Costs BY2014 $K
Cost Element |  | VXX Average Annual Cost Per Aircraft |  |  |  | VH-3D/VH-60N (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  | 1745.1 |  |  |  | 1745.1
Unit Operations |  | 362.8 |  |  |  | 340.5
Maintenance |  | 5979.3 |  |  |  | 5273.2
Sustaining Support |  | 811.5 |  |  |  | 653.9
Continuing System Improvements |  | 2189.8 |  |  |  | 3912.4
Indirect Support |  | 307.9 |  |  |  | 349.9
Other |  | 0 |  |  |  | 0
Total |  | 11396.4 |  |  |  | 12275
Unitized Cost Comments:
Total O&S Costs = Average annual O&S Cost/aircraft * total aircraft operating years = $11,396.4K * 840 = $9,573.0M
VXX cost comparison to the existing fielded platform is not fitting since the antecedent’s costs are comprised of recent actuals (an average of FY10-12 data) and are not life cycle representative for which VXX cost estimates were developed
– meaning, estimated out in the 2021 thru 2062 timeframe.
Item | Total O&S Cost $M
| VXX | [5 empty] | VH-3D/VH-60N (Antecedent)
| Current Development APB Objective/Threshold |  |  | Current Estimate
Base Year | 10140.4 |  | 11154.4 |  | 9573 |  | N/A
Then Year | 17674.3 |  | N/A |  | 16631.1 |  | N/A
Total O&S Cost Comment
For this initial SAR submission, the current O&S estimate represents the latest Program Office estimate. The most notable areas affecting this program estimate are related to the maintenance concept for a commercial helicopter and associated future planned system improvements.
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2014 $M):
Based on the identified programmatic baseline, the estimated cost of the Demil/Disposal phase for the VXX is $1.2 million (BY 2014 $). The estimate will be refined at Milestone C based on the System Disposal Plan Annex to the Life Cycle Sustainment Plan.