## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-176
Evolved Expendable Launch Vehicle (EELV)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 10
Schedule 11
Performance 12
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 27
Foreign Military Sales 28
Nuclear Costs 28
Unit Cost 29
Cost Variance 32
Contracts 35
Deliveries and Expenditures 40
Operating and Support Cost 41

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Evolved Expendable Launch Vehicle (EELV)
DoD Component
Air Force
In the Pre-EMD phase, RDT&E funding was also received from Defense Advanced Research Projects Agency (Defense- Wide PE 0603226E) and the National Reconnaissance Office.
Responsible Office
Dr. Claire Leon, Director SMC/LE
Los Angeles Air Force Base
483 N. Aviation Blvd, 271-B3-583 El Segundo, CA 90245-2808
Claire.Leon@us.af.mil
Phone: | 310-653-3134
Fax: | 310-653-3151
DSN Phone: | 633-3134
DSN Fax: | 633-3151
Date Assigned: | December 2, 2014
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 10, 2013
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated February 10, 2013

## Table 6
Mission and Description
The mission of the Evolved Expendable Launch Vehicle (EELV) program is to acquire launch services to provide critical space support required to satisfy DoD warfighter, national security, and other Government spacelift missions while fostering interagency and commercial cooperation. This mission includes the execution of flight worthiness certification processes and booster-to-satellite mission integration to maintain assured access to space and achieve 100% mission success.
The EELV system includes launch vehicles, launch capability, a standard payload interface, support systems, mission integration (includes mission unique requirements), flight instrumentation and range interfaces, special studies (alternative upper and lower stage rocket propulsion sub-systems, mission feasibility analysis, secondary payloads, dual
integration, special flight instrumentation, loads analysis, etc.), post-flight data evaluation and analysis, mission assurance, infrastructure, critical component engineering, Government Mission Director support, system/process and reliability improvements, training, and other technical support. The system also includes launch site operations activities, activities in support of assured access, systems integration and tests, and other related support activities. Previous launch services were provided by Titan II, Delta II, Atlas II, and Titan IV launch vehicle systems. Additionally the program is working to develop two or more domestic, commercially viable, space launch providers that meet all National Security Space (NSS) launch requirements.
In accordance with section 2273 title 10, United States Code (USC) and 2013 U.S. Space Transportation Policy the DoD is responsible for maintaining assured access to space. EELV is the foundation for the access for intermediate and larger class payloads for the foreseeable future. In accordance with policy, EELV maintains at least two families of space launch vehicles capable of reliably launching national security payloads.

## Table 7
Executive Summary
Since the 2014 SAR (containing launch data as of January 2015) there have been nine successful National Security Space (NSS) EELV program launches and three commercially procured missions. Of those, nine were Atlas V launch vehicles and three were Delta IV launch vehicles: Magnetospheric Multiscale (MMS) for the National Aeronautics and Space Administration (NASA) on March 12, 2015; Global Positioning System (GPS) IIF-9 on March 25, 2015; AFSPC-5 on May 20, 2015; GPS IIF-10 on July 15, 2015; Wideband Global SATCOM (WGS)-7 on July 23, 2015; Mobile User Objective System (MUOS)-4 on September 2, 2015; Morelos 3 for the Mexican Ministry of Communications and Transportation on October 2, 2015; National Reconnaissance Office Launch (NROL)-55 on October 8, 2015; GPS IIF-11 on October 31, 2015; the International Space Station supply spacecraft Cygnus for NASA on December 6, 2015; GPS IIF-12 on February 05, 2016; and NROL-45 on February 10, 2016. The remaining CY 2016 NSS missions include ten launches: eight from the Eastern Range and two from the Western Range.
The current EELV Acquisition Strategy, approved in 2013, is being executed in two phases (Phase 1 and Phase 1A) prior to moving to the fully revised Acquisition Strategy being developed for Phase 2. The Phase 1 contract, awarded in December 2013, established a “Block Buy” requirements construct to reduce launch service cost and stabilize the industrial base. Per the approved procurement plan, all FY 2015 launch procurements have been ordered and the FY 2016 orders are on schedule to finish in May 2016, completing all contractual commitments to date.
EELV Phase 1A marks a milestone in the Air Force’s (AF) ongoing efforts to reintroduce competition into the program. Phase 1A is projected to compete 9 missions for procurement through FY 2017, a GPS III mission being the first competitive solicitation. The draft version of the Request for Proposal (RFP) for the GPS III launch service competitive bids was posted on FedBizOpps on May 13, 2015. When the draft RFP was posted a Space and Missile Systems Center (SMC) internal Comment Resolution Matrix (CRM) was inadvertently exposed for approximately seven hours. The AF handled the situation as a potential Procurement Integrity Act violation in order to ensure a fair competition. SMC notified Offerors on May 15, 2015, addressed all of the offerors' concerns, and coordinated resolution. The Assistant Secretary of the Air Force (General Counsel) (SAF/GC), OUSD (AT&L) and Defense Procurement and Acquisition Policy (DPAP) conducted independent reviews and found no issues. Final closure was documented in the AF Determinations and Findings stating “the inadvertent release discussed above did not have any impact on the pending award or selection of the contractor for the EELV Phase 1A GPS III acquisition.”
The final Phase 1A RFP for the first GPS III Launch Services was released on September 30, 2015 and proposals were received on November 16, 2015. The launch service includes launch vehicle production, mission integration, and launch operations. Source selection is on-going with planned contract award in March 2016.
The FY 2015 National Defense Authorization Act (NDAA) restricted the use of Russian engines (RD-180) for NSS missions. It provided an exemption for Phase 1 “Block Buy” contract missions as well as any Russian engines procured prior to February 2014. The DoD Office of General Counsel (DoD/OGC) reviewed United Launch Alliance’s (ULA) contract for procurement of RD-180 engines. The OSD/GC determined that ULA only has five engines (referred to as “Golden Engines”) that meet the fully paid for exception, therefore limiting the number engine available for competitions. ULA informed SMC/Launch Systems Enterprise Directorate (SMC/LE), in August 2015, that they had released the five “Golden Engines” into their production flow to meet current contractual commitments; therefore additional engines would be required for ULA to compete the Atlas V launch vehicle. On November 16, 2015, ULA publicly announced they would not bid for the first GPS III competitive mission due in part to the RD-180 restrictions. The FY 2016 NDAA language provided four additional engines available for new launch service contracts. Subsequently, FY 2016 Appropriations Act allowed for use of FY 2016 funds for EELV services competitive procurements for any certified launch vehicle regardless of the country of origin of the rocket engine, notwithstanding any other provision of law. Based on this language and since the AF anticipates only three FY 2016 funded competition, the FY 2016 NDAA and FY 2016 Appropriations Act are not in conflict for 2016 and the AF does not expect to rely on this provision of law. The AF supports the continued use of RD-180 engines until a capable alternative is developed to maintain assured access to space and foster robust competition. Therefore, the AF position is that Section 1608 FY 2015 NDAA should be amended to avoid the need for annual appropriations to allow for future competitions.

## Table 8
The AF announced on May 26, 2015 that Space Exploration Technologies Corporation's (SpaceX’s) Falcon 9 Launch System was certified for NSS launches with Falcon 9v1.1 as the baseline. This certification takes into account all of the Spring 2015 Secretary of the Air Force’s Independent Review Committee's recommendations, to include allowing New Entrant certification with some open work, provided there are jointly approved work plans in place that support potential NSS mission processing timelines. SpaceX is now eligible for an award of specified NSS missions to include the GPS III-2 launch service. SpaceX has also evolved their Falcon 9v1.1 configuration into the Falcon 9 Upgrade. To update the certification baseline, SpaceX and AF built Joint Work Plans for the verifications and demonstrations of certification requirements with a credible Integrated Master Schedule. AF announced that the certified baseline configuration of SpaceX’s Falcon 9 Launch System was updated to Falcon 9 Upgrade for use in NSS missions on January 25, 2016.
A Falcon 9 v1.1 commercial launch experienced an in-flight mishap resulting in loss of vehicle on June 28, 2015. An official investigation was led by a SpaceX/Federal Aviation Administration (FAA) Anomaly Investigation Team (AIT). The AIT completed its investigation and presented findings to the Air Force Space Command (AFSPC) Commander on October 21, 2015. The AIT briefed the FAA on November 18, 2015 and submitted their final report. The 45th Space Wing authorized the return to flight operations from a Range Safety perspective on December 1, 2015. The FAA officially closed the investigation on December 9, 2015 based on their oversight during the investigation and review of the final report. SMC is also conducting an independent assessment of the mishap and the SpaceX investigation, due to be completed in early 2016. The mishap does not affect the certification status of the SpaceX Falcon 9 v1.1 launch system. Any corrective actions will be addressed as part of the AF’s established mission assurance processes. SpaceX returned to flight on December 21, 2015, with the successful launch of the commercial ORBCOMM-2 mission.
SMC/LE continues to be actively engaged with a number of industry partners to expeditiously certify three additional launch systems to launch NSS missions. First, ULA submitted a Statement of Intent (SOI) for their next generation launch system, named the Vulcan, on February 11, 2015. Vulcan completed a launch system Preliminary Design Review in December 2015, and the Vulcan Certification Plan is expected to be completed by early 2016. Secondly, SpaceX submitted a SOI for the Falcon Heavy launch vehicle in 2015. Finally, a third provider submitted a SOI on November 13, 2015 (identification is Proprietary and not releasable at this time). The AF acknowledged receipt, assembled a team, has engaged with the provider, and will begin certification plan development in early 2016.
AFSPC and SMC/LE are working together to develop a Spacelift CPD. The CPD will replace the current EELV ORD which has been in use since EELV program formation. The CPD includes EELV-class as well as smaller lift requirements, reorganizes and updates many system requirements (Key Performance Parameters, Key System Attributes, and Other System Attributes), updates EELV mission reference orbits including mass-to-orbit values and orbital insertion accuracy values, and addresses several other requirements topics (resiliency, rideshare, stage disposal, and debris). The JROC approval of the CPD is expected by Summer 2016.
SMC/LE is executing the requirements in the FY 2015 NDAA and Appropriations Act for a new engine technical maturation and risk reduction program, and the development of a Rocket Propulsion System (RPS). Work is already underway with NASA's ABEDRR program, AFRL's HydroCarbon Boost (HCB) program, and combustion stability tool modeling with Georgia Tech Research Institute. SMC/LE is also working with SMC/Advanced Systems and Development Directorate to execute ten Broad AgencyAnnouncement contracts to advance domestic technology, improve technical maturity, and reduce engine development risks. SMC/LE is also executing two RPS Other Transaction Agreements with 1) Orbital ATK for development of prototypes of the Common Booster Segment (CBS) solid rocket motor (main stage), GEM 63XL strap- on solid rocket motor, and an Extendable Nozzle for Blue Origin's BE-3U upper stage engine and 2) SpaceX for the development of a prototype of the Raptor engine for the upper stage of the Falcon 9 and Falcon Heavy launch vehicles to effectively, efficiently, and expediently transition off the RD-180. Ongoing awards are planned through February 2016.
The FY 2017 President’s Budget leverages the $492M of RPS FY 2014-2016 funding for the development of new launch systems via a public-private partnership agreements with launch system providers. These investment agreements will deliver launch capability for NSS missions including completing the U.S. produced RPS started in FY 2014-2016. While a priority is to quickly eliminate the use of foreign-produced systems, the AF also intends to improve assured access to space by transitioning to a long-term sustained competitive environment and fully implement the National Space Transportation Policy direction: to increase the U.S. commercial space transportation industry robustness and cost effectiveness; foster innovation-driven entrepreneurship and international competitiveness; and benefit the U.S. economy. The overall goal of the

## Table 9
launch system investment is to ensure two or more domestic, commercially viable launch providers that also meet NSS requirements will be available by the end of Phase 2 (FY 2022) or earlier.
There will be a period of transition for launch service missions procured between FY 2018-2022, known as Phase 2. The strategy will require multiple approaches to acquire launch services, the AF plans to sole source two NRO heavy missions on Delta IV Heavy launch vehicles in order to meet required launch dates. The remaining launch service missions during this timeframe will be open to all certified launch service providers. Due to the restrictions on the use of the RD-180 powered Atlas V launch vehicle for NSS missions, the AF may allocate, or dual-sole source, missions among the available providers to assure access to space for all national security missions.
The AF, in coordination with the NRO, is developing a total program SCP. The SCP will support a revised APB and addresses the current RDT&E Total Cost APB breach.
There are no significant software-related issues with this program at this time.

## Table 10
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
The RDT&E breach was previously reported in the December 2014 SAR.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 11
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone I | Dec 1996 | Dec 1996 | Dec 1996 | Dec 1996
Milestone II | Jun 1998 | Jun 1998 | Jun 1998 | Jun 1998
Tailored CDR | Oct 1999 | Oct 1999 | Oct 1999 | Oct 1999
MLV First Operational Flight | Aug 2002 | Aug 2002 | Aug 2002 | Aug 2002
HLV OLSD Flight | Dec 2004 | Dec 2004 | Dec 2004 | Dec 2004
Initial & Full Operational Capability | Jun 2006 | Jun 2006 | Jun 2006 | Jun 2006
HLV First Operational Flight | Nov 2007 | Nov 2007 | Nov 2007 | Nov 2007
Milestone C Reapproval | Feb 2013 | Feb 2013 | Feb 2013 | Feb 2013
Change Explanations
Acronyms and Abbreviations
CDR - Critical Design Review HLV - Heavy-Lift Vehicle
MLV - Medium-Lift Vehicle
OLSD - Operational Launch Service Demonstration

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Performance Mass to Orbit
LEO: 100nm X 100nm 63.4 deg (lbs)
19550 | 19550 | 17000 | 17000 | 17000
POLAR 1: 450nm x 450nm, 98.2 deg (lbs)
5,060-8,050 (15%) | 5,060-8,050 (15%) | 4,400-7,000 | 4,400-7,000 | 4,400-7,000
POLAR 2: 100nm x 100nm, 90 deg (lbs)
43050 | 43050 | 41000 | 41000 | 41000
SEMI-SYNC: 10,998nm x 100nm, 55.0 deg (lbs)
2,875-5,152 (15%) | 2,875-5,152 (15%) | 2,500-4,725 | 2,500-4,725 | 2,500-4,725
GTO: 19,324nm x 90nm, 27 deg (lbs)
7,015-9,775 (15%) | 7,015-9,775 (15%) | 6,100-8,500 | 6,100-8,500 | 6,100-8,500
MOLNIYA: 21,150nm x 650nm, 63.4 deg (lbs)
8050 | 8050 | 7000 | 7000 | 7000
GEO: 19,323nm x19,323nm, 0 deg (lbs)
14175 | 14175 | 13500 | 13500 | 13500
Vehicle Design Reliability (%)
>98 | >98 | 98 | 98 | 98
Standardization
Launch Pads
Standardized and | Standardized and | Standardized and able | Standardized and able to | Standardized and able
able to launch all | able to launch all | to launch all configs of | launch all configs of | to launch all configs of
configs of EELV for | configs of EELV for | EELV for that site | EELV for that site | EELV for that site
that site | that site
Payload interfaces
One std payload | One std payload | Std payload interface | Std payload interface for | Std payload interface
interface | interface | for each vehicle class | each vehicle class (add'l | for each vehicle class
|  | (add'l interface rqmts | interface rqmts met by | (add'l interface rqmts
|  | met by payload | payload adapter) | met by payload
|  | adapter) |  | adapter)
Requirements Reference
Operational Requirements Document (ORD) II dated September 15, 1998

## Table 13
Change Explanations
None
Notes
There have been 92 successful launches (59 NSS and 33 NASA and commercial).
Performance Characteristics were not designed to represent any specific satellite mission. Demonstrated Performance has been verified via Government review and analysis.
Acronyms and Abbreviations
add'l - additional configs - configurations deg - degree
GEO - Geosynchronous Earth Orbit GTO - Geosynchronous Transfer Orbit lbs - pounds
LEO - Low Earth Orbit
MOLNIYA - A highly inclined, highly elliptical orbit first used by the Russian MOLNIYA satellite NASA - National Aeronautics and Space Administration
nm - nautical mile
NSS - National Security Space POLAR - Polar Orbit
rqmts - requirements
SEMI-SYNC - Semi-Sychronous Orbit Std - Standard

## Table 14
Track to Budget
RDT&E
Appn |  | BA | PE
Air Force | 3600 04 |  | 0603853F
| Project |  | Name
| 650006 |  | EELV Pre-EMD | (Sunk)
| Notes: |  | FY 1995-1998
Air Force | 3600 05 |  | 0604853F
| Project |  | Name
| 650004 |  | Evolved Expendable Launch Vehicle EMD | (Sunk)
| 650006 |  | Next Generation Liquid Rocket Engine
Notes
The program also received funding from Defense Advanced Research Projects Agency (Defense-Wide PE 0603226E) and National Reconnaissance Office (Sunk).
Procurement
Appn |  | BA | PE
Air Force | 3020 05 |  | 0305953F
| Line Item |  | Name
| MSEELC MSEELV |  | Evolved Expendable Launch Capability Evolved Expendable Launch Vehicle |  | (Sunk) (Sunk)
Air Force | 3021 01 |  | 0305953F
| Line Item |  | Name
| MSEELC MSEELV |  | Evolved Expendable Launch Capability (Space) Evolved Expendable Launch Vehicle (Space)
Notes
The program also receives funding from Navy for procurement of EELV Launch Services (ELS) for Mobile User Objective System (MUOS) spacecraft (APPN 1507, BA 02, PE 0303109N, Line Item 243300), as well as from the National Reconnaissance Office.
In December 2014, the Office of Management and Budget directed the DoD to establish a new space procurement APPN as a five-year availability account. Beginning in FY 2016, Air Force major procurement funding formerly under APPN 3020F (Missile Procurement, Air Force) BA 05 will now be under 3021F (Space Procurement, Air Force) BA 01.

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2012 $M |  |  |  | BY 2012 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 2365.1 |  | 2365.1 | 2601.6 |  | 3886.41 |  | 1962.1 |  | 1962.1 |  | 3642.6
Procurement | 59078.3 |  | 59078.3 | 64986.1 |  | 51690 |  | 67367.3 |  | 67367.3 |  | 58795.4
Flyaway | -- |  | -- | -- |  | 51690 |  | -- |  | -- |  | 58795.4
Recurring | -- |  | -- | -- |  | 51690 |  | -- |  | -- |  | 58795.4
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Other Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total | 61443.4 |  | 61443.4 | N/A |  | 55576.4 |  | 69329.4 |  | 69329.4 |  | 62438
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 50%
This Independent Cost Estimate (ICE), like all life cycle cost estimates developed by the Office of the Secretary of Defense Cost Assessment and Program Evaluation (OSD CAPE), is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
Cost Notes
The deviation is due to receiving additional RDT&E funding to transition off the Russian RD-180 engine. The sources of the additional funding are the FY 2014 Omnibus reprogramming for a technical maturation and risk reduction program to invest in key propulsion technologies; the FY 2015 National Defense Authorization Act (NDAA) and Appropriations Act, 2015 for development of a Rocket Propulsion System no later than FY 2019; the FY 2016 NDAA, Appropriations Act, 2016 and additional funding in the FY 2017 PB to invest in one or more launch provider’s emerging launch systems. The breach will be resolved with a revised APB based on the approval of an updated Acquisition Strategy incorporating the increased scope.

## Table 16
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 1 | 1 | 1
Procurement | 151 | 151 | 160
Total | 152 | 152 | 161
Quantity Notes
The decrease in quantity from 164 in the previous report to 160 is due to a decrease in launch vehicle requirements.

## Table 17
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 2178 | 227.8 |  |  | 296.6 | 296.6 | 247.2 |  | 197.8 |  | 198.6 |  |  | 0 |  | 3642.6
Procurement | 21184.8 | 1891.8 |  |  | 2307 | 2209.7 | 2715.9 |  | 2521.4 |  | 2205.2 |  |  | 23759.6 |  | 58795.4
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 23362.8 | 2119.6 |  |  | 2603.6 | 2506.3 | 2963.1 |  | 2719.2 |  | 2403.8 |  |  | 23759.6 |  | 62438
PB 2016 Total | 23338.8 | 2245.4 |  |  | 2493.8 | 2454.3 | 2761.4 |  | 2484.5 |  | 3273.4 |  |  | 25728.2 |  | 64779.8
Delta | 24 | -125.8 |  |  | 109.8 | 52 | 201.7 |  | 234.7 |  | -869.6 |  |  | -1968.6 |  | -2341.8
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 1
Production | 0 |  | 76 |  | 7 | 7 | 5 |  | 8 |  | 7 | 6 |  | 44 |  | 160
PB 2017 Total | 1 |  | 76 |  | 7 | 7 | 5 |  | 8 |  | 7 | 6 |  | 44 |  | 161
PB 2016 Total | 1 |  | 76 |  | 8 | 7 | 6 |  | 7 |  | 7 | 8 |  | 45 |  | 165
Delta | 0 |  | 0 |  | -1 | 0 | -1 |  | 1 |  | 0 | -2 |  | -1 |  | -4

## Table 18
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.8
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 110.6
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.9
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 92.3
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 242
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 321.8
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 388
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 321.8
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 225.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 227.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 296.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 296.6
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 247.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 197.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 198.6
Subtotal |  | 1 | -- |  | -- |  | -- |  | -- |  | -- |  | 3642.6

## Table 19
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.2
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.7
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 143.7
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.6
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 117.5
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 305.1
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 399.4
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 474.6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 389.6
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 214.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 213.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 273.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 268.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 219
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 171.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 169.1
Subtotal |  | 1 | -- |  | -- |  | -- |  | -- |  | -- |  | 3886.4

## Table 20
Quantity of one represents the Heavy-Lift Vehicle (HLV) Operational Launch Service Demonstration (OLSD), also referred to as the Heavy Demo, launched in December 2004.
Included in the previous years funds above are Defense Advanced Research Projects Agency (DARPA) and National Reconnaissance Office (NRO) provided funding. Previously stated in past SARs as Advanced Research Projects Agency (ARPA) and National User.

## Table 21
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | 1 | 68.1 |  | -- |  | -- |  | 68.1 |  | -- |  | 68.1
2001 |  | 5 | 518.4 |  | -- |  | -- |  | 518.4 |  | -- |  | 518.4
2002 |  | -- | -- |  | 6.1 |  | -- |  | 6.1 |  | -- |  | 6.1
2003 |  | 1 | 200.2 |  | -- |  | -- |  | 200.2 |  | -- |  | 200.2
2004 |  | 7 | 1094.2 |  | -- |  | -- |  | 1094.2 |  | -- |  | 1094.2
2005 |  | 4 | 670.6 |  | -- |  | -- |  | 670.6 |  | -- |  | 670.6
2006 |  | 1 | 721.7 |  | -- |  | -- |  | 721.7 |  | -- |  | 721.7
2007 |  | 3 | 1013.1 |  | -- |  | -- |  | 1013.1 |  | -- |  | 1013.1
2008 |  | 5 | 1586 |  | -- |  | -- |  | 1586 |  | -- |  | 1586
2009 |  | 6 | 2213.2 |  | -- |  | -- |  | 2213.2 |  | -- |  | 2213.2
2010 |  | 5 | 1558.5 |  | -- |  | -- |  | 1558.5 |  | -- |  | 1558.5
2011 |  | 8 | 2097.9 |  | -- |  | -- |  | 2097.9 |  | -- |  | 2097.9
2012 |  | 9 | 3070.5 |  | -- |  | -- |  | 3070.5 |  | -- |  | 3070.5
2013 |  | 7 | 2254.8 |  | -- |  | -- |  | 2254.8 |  | -- |  | 2254.8
2014 |  | 6 | 1877.3 |  | -- |  | -- |  | 1877.3 |  | -- |  | 1877.3
2015 |  | 8 | 2234.2 |  | -- |  | -- |  | 2234.2 |  | -- |  | 2234.2
Subtotal |  | 76 | 21178.7 |  | 6.1 |  | -- |  | 21184.8 |  | -- |  | 21184.8

## Table 22
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | 1 | 83.6 |  | -- |  | -- |  | 83.6 |  | -- |  | 83.6
2001 |  | 5 | 629.5 |  | -- |  | -- |  | 629.5 |  | -- |  | 629.5
2002 |  | -- | -- |  | 7.3 |  | -- |  | 7.3 |  | -- |  | 7.3
2003 |  | 1 | 236.6 |  | -- |  | -- |  | 236.6 |  | -- |  | 236.6
2004 |  | 7 | 1265.3 |  | -- |  | -- |  | 1265.3 |  | -- |  | 1265.3
2005 |  | 4 | 753.5 |  | -- |  | -- |  | 753.5 |  | -- |  | 753.5
2006 |  | 1 | 788.6 |  | -- |  | -- |  | 788.6 |  | -- |  | 788.6
2007 |  | 3 | 1079.8 |  | -- |  | -- |  | 1079.8 |  | -- |  | 1079.8
2008 |  | 5 | 1660.1 |  | -- |  | -- |  | 1660.1 |  | -- |  | 1660.1
2009 |  | 6 | 2285 |  | -- |  | -- |  | 2285 |  | -- |  | 2285
2010 |  | 5 | 1585.3 |  | -- |  | -- |  | 1585.3 |  | -- |  | 1585.3
2011 |  | 8 | 2091.5 |  | -- |  | -- |  | 2091.5 |  | -- |  | 2091.5
2012 |  | 9 | 3010.2 |  | -- |  | -- |  | 3010.2 |  | -- |  | 3010.2
2013 |  | 7 | 2161.2 |  | -- |  | -- |  | 2161.2 |  | -- |  | 2161.2
2014 |  | 6 | 1774.5 |  | -- |  | -- |  | 1774.5 |  | -- |  | 1774.5
2015 |  | 8 | 2087.1 |  | -- |  | -- |  | 2087.1 |  | -- |  | 2087.1
Subtotal |  | 76 | 21491.8 |  | 7.3 |  | -- |  | 21499.1 |  | -- |  | 21499.1

## Table 23
Cost Quantity Information 3020 ¦ Procurement ¦ Missile Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2012 $M
2000 | 1 | 83.6
2001 | 5 | 629.5
2002 | -- | --
2003 | 1 | 236.6
2004 | 7 | 1265.3
2005 | 4 | 753.5
2006 | 1 | 1789.8
2007 | 3 | 2126.6
2008 | 5 | 1636.3
2009 | 6 | 2098.6
2010 | 5 | 1510.1
2011 | 8 | 2134.7
2012 | 9 | 2864.2
2013 | 7 | 2125.3
2014 | 6 | 1018.2
2015 | 8 | 1219.5
Subtotal | 76 | 21491.8

## Table 24
Annual Funding 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | 7 | 1891.8 |  | -- |  | -- |  | 1891.8 |  | -- |  | 1891.8
2017 |  | 7 | 2307 |  | -- |  | -- |  | 2307 |  | -- |  | 2307
2018 |  | 5 | 2209.7 |  | -- |  | -- |  | 2209.7 |  | -- |  | 2209.7
2019 |  | 8 | 2715.9 |  | -- |  | -- |  | 2715.9 |  | -- |  | 2715.9
2020 |  | 7 | 2521.4 |  | -- |  | -- |  | 2521.4 |  | -- |  | 2521.4
2021 |  | 6 | 2205.2 |  | -- |  | -- |  | 2205.2 |  | -- |  | 2205.2
2022 |  | 10 | 3216.8 |  | -- |  | -- |  | 3216.8 |  | -- |  | 3216.8
2023 |  | 6 | 2773.9 |  | -- |  | -- |  | 2773.9 |  | -- |  | 2773.9
2024 |  | 5 | 2783.9 |  | -- |  | -- |  | 2783.9 |  | -- |  | 2783.9
2025 |  | 5 | 2653.1 |  | -- |  | -- |  | 2653.1 |  | -- |  | 2653.1
2026 |  | 7 | 3055.3 |  | -- |  | -- |  | 3055.3 |  | -- |  | 3055.3
2027 |  | 7 | 3359.8 |  | -- |  | -- |  | 3359.8 |  | -- |  | 3359.8
2028 |  | 4 | 2505 |  | -- |  | -- |  | 2505 |  | -- |  | 2505
2029 |  | -- | 1680.7 |  | -- |  | -- |  | 1680.7 |  | -- |  | 1680.7
2030 |  | -- | 1731.1 |  | -- |  | -- |  | 1731.1 |  | -- |  | 1731.1
Subtotal |  | 84 | 37610.6 |  | -- |  | -- |  | 37610.6 |  | -- |  | 37610.6

## Table 25
Annual Funding 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | 7 | 1737.4 |  | -- |  | -- |  | 1737.4 |  | -- |  | 1737.4
2017 |  | 7 | 2079.4 |  | -- |  | -- |  | 2079.4 |  | -- |  | 2079.4
2018 |  | 5 | 1954.2 |  | -- |  | -- |  | 1954.2 |  | -- |  | 1954.2
2019 |  | 8 | 2354.2 |  | -- |  | -- |  | 2354.2 |  | -- |  | 2354.2
2020 |  | 7 | 2143 |  | -- |  | -- |  | 2143 |  | -- |  | 2143
2021 |  | 6 | 1836.8 |  | -- |  | -- |  | 1836.8 |  | -- |  | 1836.8
2022 |  | 10 | 2626.8 |  | -- |  | -- |  | 2626.8 |  | -- |  | 2626.8
2023 |  | 6 | 2221.6 |  | -- |  | -- |  | 2221.6 |  | -- |  | 2221.6
2024 |  | 5 | 2185.6 |  | -- |  | -- |  | 2185.6 |  | -- |  | 2185.6
2025 |  | 5 | 2042.7 |  | -- |  | -- |  | 2042.7 |  | -- |  | 2042.7
2026 |  | 7 | 2305.9 |  | -- |  | -- |  | 2305.9 |  | -- |  | 2305.9
2027 |  | 7 | 2484.5 |  | -- |  | -- |  | 2484.5 |  | -- |  | 2484.5
2028 |  | 4 | 1817.2 |  | -- |  | -- |  | 1817.2 |  | -- |  | 1817.2
2029 |  | -- | 1194.6 |  | -- |  | -- |  | 1194.6 |  | -- |  | 1194.6
2030 |  | -- | 1207 |  | -- |  | -- |  | 1207 |  | -- |  | 1207
Subtotal |  | 84 | 30190.9 |  | -- |  | -- |  | 30190.9 |  | -- |  | 30190.9

## Table 26
All EELV launch services are fully funded in the year ordered, two or three years prior to launch, depending on vehicle configuration, and are fixed price. Launch support and capability costs are funded on an annual basis.
The Air Force missions, purchased with Missile (3020) and Space (3021) Procurement funds, comprise 105 of the 160 total launches. The remaining missions in the table above include funding and quantities from other sources to include the National Reconnaissance Office, and the Department of the Navy. Navy funding is for procurement of launch
services for five Mobile User Objective System (MUOS) spacecraft. Navy procurement funding and quantities were first included in the December 2003 EELV SAR; however, the MUOS program baseline also includes these funds. There is one additional Air Force mission, the Heavy-Lift Vehicle Demonstration mission, that was purchased with RDT&E (3600) funds.
Cost Quantity Information 3021 ¦ Procurement ¦ Space Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2012 $M
2016 | 7 | 2589.4
2017 | 7 | 2694.4
2018 | 5 | 1753
2019 | 8 | 2366.1
2020 | 7 | 2408.7
2021 | 6 | 2137.5
2022 | 10 | 2649
2023 | 6 | 2230.9
2024 | 5 | 2193.4
2025 | 5 | 2065.5
2026 | 7 | 2320
2027 | 7 | 2487.6
2028 | 4 | 2295.4
2029 | -- | --
2030 | -- | --
Subtotal | 84 | 30190.9

## Table 27
Low Rate Initial Production
There is no LRIP for this program.

## Table 28
Foreign Military Sales
None
Nuclear Costs
None

## Table 29
Unit Cost
Unit Cost Report
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Current UCR Baseline (Feb 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 61443.4 |  |  | 55576.4
Quantity | 152 |  |  | 161
Unit Cost | 404.233 |  |  | 345.195 |  | -14.6
Average Procurement Unit Cost
Cost | 59078.3 |  |  | 51690
Quantity | 151 |  |  | 160
Unit Cost | 391.247 |  |  | 323.062 |  | -17.43
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Feb 2013 APB)
Program Acquisition Unit Cost
Cost | 61443.4 |  |  | 55576.4
Quantity | 152 |  |  | 161
Unit Cost | 404.233 |  |  | 345.195 |  | -14.6
Average Procurement Unit Cost
Cost | 59078.3 |  |  | 51690
Quantity | 151 |  |  | 160
Unit Cost | 391.247 |  |  | 323.062 |  | -17.43
Average unit cost figures reported above are a combination of each of three different launch vehicle configurations and annual launch capability requirements. The average unit cost will vary due to shifts in payload weight and volume, mission- unique services, number of missions per year and other factors.

## Table 30
Unit Cost History
Item | [6 empty] | Date |  |  |  | BY 2012 $M | [6 empty] | TY $M
[11 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Oct 1998 | [5 empty] | 97.147 |  |  |  | 87.193 |  |  |  | 95.844 |  |  |  | 87.827
APB as of January 2006 |  |  |  |  | Jul 2004 | [5 empty] | 236.886 |  |  |  | 223.191 |  |  |  | 230.358 |  |  |  | 219.571
Revised Original APB |  |  |  |  | Feb 2013 | [5 empty] | 404.233 |  |  |  | 391.247 |  |  |  | 456.114 |  |  |  | 446.141
Prior APB |  |  |  |  | Aug 2007 | [5 empty] | 236.886 |  |  |  | 223.191 |  |  |  | 230.358 |  |  |  | 219.571
Current APB |  |  |  |  | Feb 2013 | [5 empty] | 404.233 |  |  |  | 391.247 |  |  |  | 456.114 |  |  |  | 446.141
Prior Annual SAR |  |  |  |  | Dec 2014 | [5 empty] | 345.456 |  |  |  | 330.281 |  |  |  | 392.605 |  |  |  | 379.934
Current Estimate |  |  |  |  | Dec 2015 | [5 empty] | 345.195 |  |  |  | 323.062 |  |  |  | 387.814 |  |  |  | 367.471
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [19 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  |  | Oth |  |  | Spt |  | Total
95.844 -6.787 55.829 -1.019 1.510 310.650 0.087 0.000 360.270 456.114
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [17 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  | Oth |  |  | Spt |  | Total
456.114 1.390 -17.971 1.580 0.000 -53.299 0.000 0.000 -68.300 387.814

## Table 31
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [10 empty] | APUC Production Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
87.827 -6.789 54.306 -1.026 0.000 311.823 0.000 0.000 358.314 446.141
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
446.141 1.412 -17.523 1.590 0.000 -64.149 0.000 0.000 -78.670 367.471
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  | Dec 1996 |  |  | Dec 1996 |  |  |  | Dec 1996 |  |  | Dec 1996
Milestone II |  |  | Jun 1998 |  |  | N/A |  |  |  | Jun 1998 |  |  | Jun 1998
Milestone III |  |  | Jul 2003 |  |  | N/A |  |  |  | N/A |  |  | N/A
IOC |  |  | TBD |  |  | TBD |  |  |  | Jun 2006 |  |  | Jun 2006
Total Cost (TY $M) |  |  | 2000 |  |  | 17347.8 |  |  |  | 69329.4 |  |  | 62438
Total Quantity |  |  | N/A |  |  | 181 |  |  |  | 152 |  |  | 161
PAUC |  |  | N/A |  |  | 95.844 |  |  |  | 456.114 |  |  | 387.814

## Table 32
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1962.1 | 67367.3 | -- | 69329.4
Previous Changes
Economic | 1.4 | 599.8 | -- | 601.2
Quantity | -- | 2750 | -- | 2750
Schedule | -- | 254.4 | -- | 254.4
Engineering | -- | -- | -- | --
Estimating | 507.2 | -8662.4 | -- | -8155.2
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 508.6 | -5058.2 | -- | -4549.6
Current Changes
Economic | -3.6 | -373.8 | -- | -377.4
Quantity | -- | -1538.5 | -- | -1538.5
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 1175.5 | -1601.4 | -- | -425.9
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 1171.9 | -3513.7 | -- | -2341.8
Adjustments | -- | -- | -- | --
Total Changes | 1680.5 | -8571.9 | -- | -6891.4
CE - Cost Variance | 3642.6 | 58795.4 | -- | 62438
CE - Cost & Funding | 3642.6 | 58795.4 | -- | 62438

## Table 33
Summary BY 2012 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 2365.1 | 59078.3 | -- | 61443.4
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | 2120 | -- | 2120
Schedule | -- | 0.1 | -- | 0.1
Engineering | -- | -- | -- | --
Estimating | 469 | -7032.3 | -- | -6563.3
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 469 | -4912.2 | -- | -4443.2
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -1167 | -- | -1167
Schedule | -- | -9.3 | -- | -9.3
Engineering | -- | -- | -- | --
Estimating | 1052.3 | -1299.8 | -- | -247.5
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 1052.3 | -2476.1 | -- | -1423.8
Adjustments | -- | -- | -- | --
Total Changes | 1521.3 | -7388.3 | -- | -5867
CE - Cost Variance | 3886.4 | 51690 | -- | 55576.4
CE - Cost & Funding | 3886.4 | 51690 | -- | 55576.4
Previous Estimate: December 2014

## Table 34
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -3.6
Increased funding to invest in new launch systems providers to support National Security Space (NSS) mission requirements. (Estimating)
+1050.3 +1173.4
Adjustment for current and prior escalation. (Estimating) +2.0 +2.1
RDT&E Subtotal +1052.3 +1171.9
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -373.8
Quantity Variance resulting from a reduction of four launch services, from 164 to 160, based on decreased Satellite Vehicle requirements. (Quantity)
Stretch-out of Launch Vehicle configuration procurement profile due to requirements by Satellite Vehicles shifting between years. (Schedule)
Acceleration of procurement buy profile within the FYDP to align with new Satellite Vehicle requirements. (Schedule)
Increased funding required for changes in Launch Vehicle configuration requirements due to Satellite Vehicles requirements. (Estimating)
Revised estimate for launch service pricing from FY 2017 - FY 2028 based on final negotiated contract values. (Estimating)
-1167.0 -1538.5
-31.8 -24.1
+22.5 +24.1
+404.4 +491.6
-1756.5 -2148.2
Adjustment for current and prior escalation. (Estimating) +52.3 +55.2
Procurement Subtotal -2476.1 -3513.7
Change Explanations Notes
The FY 2017 PB provides additional RDT&E funds for investing in new launch systems. EELV will invest in public-private partnership agreements with launch system providers to deliver launch capability for NSS missions leveraging the U.S. produced propulsion systems while maintaining mission success. The results of the shared Government-industry investment will be multiple competitive, domestic launch service providers where each NSS mission can be supported by multiple launch providers.

## Table 35
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: FY13+ Phase I Buy
Contractor: United Launch Services, LLC
Contractor Location: 9501 East Panorama Circle
Centennial, CO 80112
Contract Number: FA8811-13-C-0003
Contract Type: Cost Plus Incentive Fee (CPIF), Cost Plus Fixed Fee (CPFF)
Award Date: June 26, 2013
Definitization Date: December 18, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1087.0 N/A 7 2576.8 N/A 0 2527.7 2536.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to an increase in the scope of work as a result of the increase in the quantity of launch services, twelve, on the FFP portion on the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2016) +63.9 -7.1
Previous Cumulative Variances +30.2 -11.0
Net Change +33.7 +3.9
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to launch cycle time reductions and streamlining project affordability .
The favorable net change in the schedule variance is due to updated schedule and performance as a result of the addition of the FY 2016 options.
Notes
Contract FA881-C-13-0003 is reported as two separate efforts to enable Cost and Schedule Variance reporting for the CPIF/CPFF efforts. Contract number FA881-C-13-0003/1 is the FFP portion, including the quantity, of the contract.

## Table 36
Contract Identification
Appropriation: Procurement
Contract Name: FY13+ Phase I Buy
Contractor: United Launch Services, LLC
Contractor Location: 9501 East Panorama Circle
Centennial, CO 80112
Contract Number: FA8811-13-C-0003/1
Contract Type: Firm Fixed Price (FFP)
Award Date: June 26, 2013
Definitization Date: December 18, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1946.2 N/A 14 3344.5 N/A 26 3344.5 3344.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the completion of negotiations and definitization of the contract, the addition of twelve launch procurements, and contract modifications.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
Contract FA881-C-13-0003 is reported as two separate efforts to enable Cost and Schedule Variance reporting for the CPIF/CPFF efforts. Contract number FA881-C-13-0003/1 is the FFP portion of the contract.
Of the 26 launch procurements, 5 have been launched. Contract completion is estimated to be in 2019.

## Table 37
Contract Identification
Appropriation: Procurement
Contract Name: FY12 EELV Launch Services (ELS5)
Contractor: United Launch Services, LLC.
Contractor Location: 9501 East Panorama Circle
Centennial, CO 80112
Contract Number: FA8811-13-C-0002
Contract Type: Firm Fixed Price (FFP)
Award Date: May 02, 2011
Definitization Date: January 10, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1787.0 N/A 10 513.0 N/A 4 513.0 513.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the April 2013 contract de-scope, moving 6 missions to the FY 2011 EELV Launch Services contract FA8811-11-C-0001 and the completion of negotiations and definitization of the contract on January 10, 2014.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
Of the 4 missions, 3 have been launched. Contract completion is estimated to be in 2018.

## Table 38
Contract Identification
Appropriation: RDT&E
Contract Name: Rocket Propulsion System Prototypes: Common Booster Segment, BE-3U Extendable Nozzle & GEM63XL
Contractor: ATK Launch Systems Inc
Contractor Location: 5000 S. 8400 W.
Magna, UT 84044-2202
Contract Number: FA8811-16-9-0002
Contract Type: Other Transaction Agreement (OTA)
Award Date: January 13, 2016
Definitization Date: January 13, 2016
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
47.0 N/A 0 47.0 N/A 0 47.0 47.0
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (OTA) contract.
Notes
This is the first time this contract is being reported.
Other Transaction Agreement for the shared cost investment in the development of subject Rocket Propulsion Systems Prototypes. With at most one-third statutory cost-sharing by contractor.

## Table 39
Contract Identification
Appropriation: Procurement
Contract Name: Initial Launch Services
Contractor: United Launch Services, LLC
Contractor Location: 9501 East Panorama Circle
Centennial, CO 80127
Contract Number: F04701-98-D-0001
Contract Type: Firm Fixed Price (FFP)
Award Date: October 16, 1998
Definitization Date: October 16, 1998
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
649.0 N/A 9 1633.6 N/A 16 1633.6 1633.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to an increase in the quantity of missions included in the contract and contract modifications.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
Of the 16 missions, 16 have been launched.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 40
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 1 | 1 | 1 | 100%
Production | 58 | 58 | 160 | 36.25%
Total Program Quantity Delivered | 59 | 59 | 161 | 36.65%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
62438
18654.6
29.88%
37
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
23
62.16%
25482.4
40.81%
The above data is current as of February 15, 2016.

## Table 41
Operating and Support Cost
Cost Estimate Details
Date of Estimate: December 31, 2015
Source of Estimate: Headquarter Air Force Space Command
Quantity to Sustain: 0
Unit of Measure: Years
Service Life per Unit: 31.00 Years
Fiscal Years in Service: FY 2000 - FY 2030
Sustainment Strategy
EELV is a launch service procurement. The Government never takes possession of hardware, therefore has no sustainment strategy.
Antecedent Information
The EELV program provides launch services for all DoD and National Reconnaissance Office satellite vehicles. No single antecedent system covered EELV's combined launch capabilities. Previous launch services were provided by Titan II, Delta II, Atlas II, and Titan IV launch vehicle systems. Titan IV was selected as the program that was the closest representation of an antecedent system. Cost details were provided by the Air Force Total Ownership Cost database.
Annual O&S Costs BY2012 $M
Cost Element |  | EELV Average Annual Cost Per Years |  |  |  | Titan IV (Antecedent) Average Annual Cost Per Launch Vehicle
Unit-Level Manpower |  | -- |  |  |  | 11.561
Unit Operations |  | -- |  |  |  | 67.656
Maintenance |  | -- |  |  |  | 12.638
Sustaining Support |  | -- |  |  |  | 0.003
Continuing System Improvements |  | -- |  |  |  | --
Indirect Support |  | -- |  |  |  | 0.343
Other |  | 40.5 |  |  |  | --
Total |  | 40.5 |  |  |  | 92.201
Other O&S funds support critical infrastructure at the Eastern and Western Ranges.
Item | Total O&S Cost $M
| EELV | [5 empty] | Titan IV (Antecedent)
| Current Production APB Objective/Threshold |  |  | Current Estimate
Base Year | 1256.8 |  | 1382.5 |  | 1255.5 |  | N/A
Then Year | 1388.3 |  | N/A |  | 1381.1 |  | N/A

## Table 42
Equation to Translate Annual Cost to Total Cost
EELV unitized costs are calculated by using the Total O&S Cost divided by the Service Life: BY12 $1,255.5M divided by 31 years to equal the annual cost of $40.5M.
O&S Cost Variance
Category | BY 2012 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
1255.5
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 1255.5
Disposal Estimate Details
Date of Estimate: December 31, 2015
Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2012 $M): Total costs for disposal of all Years are 0.0
EELV is a launch service and therefore has no disposal costs.