## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-257
HC/MC-130 Recapitalization Aircraft (HC/MC-130 Recap)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 13
Cost and Funding 15
Low Rate Initial Production 27
Foreign Military Sales 28
Nuclear Costs 28
Unit Cost 29
Cost Variance 32
Contracts 35
Deliveries and Expenditures 37
Operating and Support Cost 38

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
HC/MC-130 Recapitalization Aircraft (HC/MC-130 Recap)
DoD Component
Air Force
Responsible Office
Col Karl Schloer
1895 5th Street, Bldg 46
Wright Patterson Air Force Base, OH 45433-7233
Karl.Schloer@us.af.mil
Phone: | 937-656-8109
Fax: | 937-255-3768
DSN Phone: | 986-8109
DSN Fax: | 785-3768
Date Assigned: | June 24, 2014
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 29, 2010
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated October 7, 2013

## Table 6
Mission and Description
The HC/MC-130 Recapitalization Aircraft (HC/MC-130 Recap) will replace the HC-130P/N tanker aircraft that currently support Personnel Recovery. These tankers are currently operated by active duty Air Reserve Components. The MC-130 Recap aircraft will replace the legacy MC-130P/E tanker aircraft currently operated by the Air Force Special Operations Command. Most of these aircraft are more than 35 years old and are burdened by multiple unique aircraft configurations. These multiple configurations create significantly increased maintenance and sustainment challenges.
The primary mission of the HC/MC-130J aircraft is providing aerial refueling support to the respective component commanders. In addition to the specialized air refueling support to mission-unique receiver aircraft, the aircraft can provide a specialized mobility capability to position, supply, re-supply and recover specialized ground tactical units.
The HC/MC-130J is a medium size tanker that can transport airmen for infiltration and exfiltration operations. It is also an in- flight refueling receiver, which extends its combat mission and/or increases the amount of fuel available for offload to receivers. The HC/MC-130J incorporates state-of-the-art technology to reduce manpower requirements, lower operating cost and provide life-cycle cost savings over earlier C-130 models. The HC/MC-130J model climbs faster and higher, flies farther at a higher cruise speed and can take off and land in a shorter distance.

## Table 7
Executive Summary
The HC/MC-130 Recap Program successfully delivered six HC-130J and nine MC-130Js (two for AC-130J conversion) during the CY 2015. As of December 31, 2015, 53 aircraft have been delivered of 131 total (18 HC-130Js and 35 MC-130Js; 4 of the MC-130Js will be converted to AC-130Js).
In CY 2015, Enhanced-Integrated Cockpit System Trainer #2 and #3 were designated as Ready For Training (RFT)
at Kirtland Air Force Base (AFB) and Hurlburt AFB, respectively. In February 2015, Loadmaster Fuselage Trainer (LFT) #1 was designated RFT at Kirtland AFB. The LFT is a crucial training device for aircrew providing a practical experience in use of checklists, palletized loading, winching exercises, loading of vehicles, loading and rigging for aerial delivery, aeromedical and other rigging, and principles of cargo restraint for Loadmaster personnel. This allows for training without sacrificing aircraft availability. In December 2015, Weapon System Trainer #6 was accepted at Hurlburt AFB for conversion to become the first AC-130J Gunship training system.
The HC/MC-130 Recap Program Office utilized the savings from the FY 2013 aircraft buy negotiations to purchase an additional FY 2013 HC-130J. This aircraft will serve to fill a gap left by the removal of an HC-130J in FY 2019. In concert with the savings purchase, the Program Office was approved to purchase two FY 2013 HC-130Js and two FY 2013 MC-130Js as Congressional adds. The Program Office plans to utilize the savings from the Multi-Year Procurement Contract, which was awarded in December 2015, to purchase two additional aircraft in 2016, one FY 2014 AC-130J and one FY 2016 HC- 130J.
The Recap Program delivered a total of 15 aircraft for the year, 3 more than scheduled for 2015. Aircraft continued to deliver prior to contractual delivery dates.
The HC/MC-130 Recap Program, executed by the Special Operations Forces and Personnel Recovery Division, was recognized as the Air Force Life Cycle Management Center Outstanding Program Office for 2015.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Production Milestone Approval | Feb 2010 | Apr 2010 | Apr 2010 | Apr 2010
Airworthiness Certification Complete | Jan 2012 | Dec 2011 | Dec 2011 | Dec 2011
Initiate IOT&E | Mar 2012 | Mar 2012 | Mar 2012 | Mar 2012
Required Assets Available | Dec 2012 | Dec 2012 | Dec 2012 | Dec 2012
OT&E Report/ Beyond LRIP Report Approved | Dec 2012 | Apr 2013 | Apr 2013 | Apr 2013
Change Explanations
Acronyms and Abbreviations
IOT&E - Initial Operational Test and Evaluation OT&E - Operational Test and Evaluation

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Simultaneous air refueling (CSAR and SOF receivers)
While in flight, refuel full range of DoD probe equipped aircraft: rotary-wing, fixed- wing, and tilt rotor. | While in flight, refuel full range of DoD probe equipped aircraft: rotary-wing, fixed- wing, and tilt rotor. | While in flight, simultan-eously provide fuel to two CSAR recovery vehicles or SOF rotary wing receivers. Must aerial refuel one M/CV-22. | While in flight, simultaneously provide fuel to two CSAR recovery vehicles or SOF rotary wing receivers. Must aerial refuel one M/CV-22. | While in flight, simultaneously provide fuel to two CSAR recovery vehicles or SOF rotary wing receivers. Must aerial refuel one M/CV-22.
Net-ready
Fully support execution of all operational activities and must satisfy technical requirements for transition to Net- Centric military operations. | Fully support execution of all operational activities and must satisfy technical requirements for transition to Net- Centric military operations. | Fully support execution of joint critical operational activities and must satisfy technical requirements for transition to Net- Centric military operations. | Fully support execution of joint critical operational activities and must satisfy technical requirements for transition to Net- Centric military operations. | Fully support execution of joint critical operational activities and must satisfy technical requirements for transition to Net-Centric military operations.
Survivability (IR Signature)
In a single engagement, weapon system shall be able to defeat, 90% of time, specific IR threat. | In a single engagement, weapon system shall be able to defeat, 90% of time, specific IR threat. | In a single engagement, weapon system shall be able to defeat, 70% of the time, a specific IR threat. | In a single engagement, weapon system shall be able to defeat, 70% of the time, a specific IR threat. | In a single engagement, weapon system shall be able to defeat, 70% of the time, a specific IR threat.
Survivability (Threat warning)
Provide warning for EO/IR and RF threats and equivalent capability described in the LAIRCM ORD and the ASACM CDD, respectively. | Provide warning for EO/IR and RF threats and equivalent capability described in the LAIRCM ORD and the ASACM CDD, respectively. | Provide warning for EO/IR and RF threats. | Provide warning for EO/IR and RF threats. | Provide warning for EO/IR and RF threats.
Survivability (Flight critical damage tolerance)
Greater levels of ballistic | Greater levels of ballistic | Must withstand flight critical | Must withstand flight critical damage with | Must withstand flight critical damage with 95%

## Table 11
hardening/tol- erance are desired and should be incorporated, if achievable, without significant aircraft performance or cost penalties. | hardening/tol- erance are desired and should be incorporated, if achievable, without significant aircraft performance or cost penalties. | damage with 95% probability of survival against single impact (imposed by 7.62mm ball projectile at 100m) and continue operations for 30 minutes. | 95% probability of survival against single impact (imposed by 7.62mm ball projectile at 100m) and continue operations for 30 minutes. | probability of survival against single impact (imposed by 7.62mm ball projectile at 100m) and continue operations for 30 minutes.
Force Protection (Crew Protection)
Cargo | Cargo | Primary | Primary | Primary crewmember
compartment | compartment | crewmember | crewmember | positions and oxygen
positions should | positions should | positions and | positions and oxygen | supplies must be protected
be protected | be protected | oxygen supplies | supplies must be | against a single 7.62mm
against a single | against a single | must be protected | protected against a | ball projectile at 100m.
7.62mm ball | 7.62mm ball | against a single | single 7.62mm ball
projectile at 100m, | projectile at 100m, | 7.62mm ball | projectile at 100m.
with less than 3% | with less than 3% | projectile at 100m.
increase in | increase in
operating weight. | operating weight.
Materiel Availability (Sustainability)
80% average | 80% average | 76% average | During IOT&E, the | Average monthly AA rate is
monthly AA rate, | monthly AA rate, | monthly AA rate, | aircraft met the 76% | 78.08% for HC-130J and
89% average | 89% average | 85% average | AA rate, and the 85% | 82.69% for the MC-130J.
monthly MC rate; | monthly MC rate; | monthly MC rate; | average monthly MC | The average monthly MC
from 25 to 30 | from 25 to 30 | from 25 to 30 | rate. | should be 85%; from 25 to
months after both | months after both | months after both |  | 30 months after both
MAJCOMs declare | MAJCOMs declare | MAJCOMs declare |  | MAJCOMs declare IOC.
IOC. | IOC. | IOC. |  | AFSOC declared IOC in
December 2012. ACC
declared IOC in April 2013.
Effective January 2015, the
MC rate for HC-130J is
85.09% and the MC rate for
the MC-130J is 88.92%.
(Ch-1)
Requirements Reference
Capability Production Document (CPD) dated August 13, 2009
Change Explanations
(Ch-1) Materiel Availability (Sustainability) current estimate for the AA rate changed from 82.00% to 78.08% (HC-130J) and 81.24% to 82.69% (MC-130J) and the MC rate changed from 85.77% to 85.09% (HC-130J) and 88.07% to 88.92% (MC- 130J). The leading driver for the changes was a bird strike repair on aircraft 5708 accomplished at Robins Air Force Base, GA. The repair took 1710.5 hours to complete.

## Table 12
Acronyms and Abbreviations
AA - Aircraft Availability
ACC - Air Combat Command
AFSOC - Air Force Special Operations Command
ASACM - Advanced Situational Awareness Countermeasures CSAR - Combat Search And Rescue
EO/IR - Electro-Optical/Infrared
IOT&E - Initial Operational Test and Evaluation IR - Infrared (missile threat)
LAIRCM - Large Aircraft Infrared Countermeasures m - meter
MAJCOM - Major Command MC - Mission Capable
mm - millimeter
RF - Radio Frequency
SOF - Special Operations Forces

## Table 13
Track to Budget
RDT&E
Appn |  |  | BA | PE
Air Force 3600 05 0604261F
Project | Name
655249 Personnel Recovery System (Shared) (Sunk)
Notes: FY 2008 only Air Force 3600 05 0605278F
Project Name
655249 HC/MC-130 Recap (Sunk) Air Force 3600 07 0605278F
Project Name
675006 HC/MC-130 Recap (Shared)
Procurement
Appn |  |  | BA | PE
Air Force 3010 02 0401132F
Line Item | Name
C130J0 C-130J (Shared) (Sunk)
Notes: FY 2008 Global War on Terror Supplemental Funding
Air Force 3010 04 0207237F
Line Item | Name
C130JA AC-130 Recap (Sunk)
Air Force 3010 02 0207224F
|  | Line Item |  | Name
|  | C130JH |  | Combat Search and Rescue
Air Force |  | 3010 02 |  | 0207230F
|  | Line Item |  | Name
|  | C130JM |  | MC-130 Recap
Air Force |  | 3010 05 |  | 0207224F
|  | Line Item |  | Name
|  | HCMC00 |  | HC/MC-130 Modifications
Air Force |  | 3010 05 |  | 0207230F
|  | Line Item |  | Name
|  | HCMC00 |  | HC/MC-130 Modifications
Air Force |  | 3010 05 |  | 0401134F
|  | Line Item |  | Name
|  | HCMC00 |  | HC/MC-130 Modifications | (Sunk)
Air Force |  | 3010 02 |  | 0207224F

## Table 14
Line Item | Name
HMC130 Combat Search and Rescue (Sunk)
Air Force 3010 02 0207230F
Line Item | Name
HMC130 MC-130 Recap (Sunk)
Air Force 3010 05 0401134F
Line Item | Name
LAIRCM Large Aircraft Infrared
Countermeasures
Air Force 3010 04 0207237F
(Shared) (Sunk)
Line Item | Name
MC0130 AC-130 Recap (Sunk)
Defense-Wide 0300 02 1160429BB
Line Item | Name
2012C130J AC/MC-130J (Sunk)
MILCON
Appn |  | BA | PE
Air Force 3300 01 0207224F
Project | Name
VARIOUS Combat Rescue and Recovery (Shared)
Defense-Wide 0500 01 1140494BB
Project | Name
VARIOUS USSOCOM (Shared)

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2009 $M | [6 empty] | BY 2009 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 148 |  |  | 147.6 | 162.4 |  |  | 146.1 |  | 154.3 |  |  | 160.2 |  | 158.3
Procurement |  | 7436 |  |  | 12665.9 | 13932.5 |  |  | 12401.1 |  | 8054.2 |  |  | 14836.6 |  | 14271.4
Flyaway |  | -- |  |  | -- | -- |  |  | 9965.7 |  | -- |  |  | -- |  | 11469.1
Recurring |  | -- |  |  | -- | -- |  |  | 9744.1 |  | -- |  |  | -- |  | 11216.8
Non Recurring |  | -- |  |  | -- | -- |  |  | 221.6 |  | -- |  |  | -- |  | 252.3
Support |  | -- |  |  | -- | -- |  |  | 2435.4 |  | -- |  |  | -- |  | 2802.3
Other Support |  | -- |  |  | -- | -- |  |  | 1078.4 |  | -- |  |  | -- |  | 1234
Initial Spares |  | -- |  |  | -- | -- |  |  | 1357 |  | -- |  |  | -- |  | 1568.3
MILCON |  | 494.1 |  |  | 336.7 | 370.4 |  |  | 224.2 |  | 536.8 |  |  | 377.9 |  | 241.8
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 8078.1 |  |  | 13150.2 | N/A |  |  | 12771.4 |  | 8745.3 |  |  | 15374.7 |  | 14671.5
Confidence Level
Confidence Level of cost estimate for current APB: 55%
Cost is based on the HC/MC-130 Recap approved Service Cost Position, September 9, 2013.
The cost estimate represents the expected value, or mean, of the cost estimate distribution, and for both the Research, Development, Test and Evaluation (RDT&E) and production estimates, the confidence levels are approximately 55%. This portion of the estimate takes into consideration relevant risks, including ordinary levels of external and unforeseen events. It aims to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk and external influence.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  |  | 74 |  |  |  | 131 |  |  |  |  | 131
Total |  |  | 74 |  |  |  | 131 |  |  |  |  | 131

## Table 16
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 87.6 | 10.8 |  |  | 14 | 27.5 | 8.6 |  | 4.9 |  | 4.9 |  |  | 0 |  | 158.3
Procurement | 6955.7 | 1352.7 |  |  | 980.2 | 690.7 | 407.4 |  | 636 |  | 453.6 |  |  | 2795.1 |  | 14271.4
MILCON | 224.9 | 16.9 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 241.8
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 7268.2 | 1380.4 |  |  | 994.2 | 718.2 | 416 |  | 640.9 |  | 458.5 |  |  | 2795.1 |  | 14671.5
PB 2016 Total | 7320.4 | 1437.5 |  |  | 954.5 | 520.7 | 652 |  | 466.2 |  | 1449.8 |  |  | 2154.5 |  | 14955.6
Delta | -52.2 | -57.1 |  |  | 39.7 | 197.5 | -236 |  | 174.7 |  | -991.3 |  |  | 640.6 |  | -284.1
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 71 |  | 13 | 9 | 7 |  | 3 |  | 6 | 4 |  | 18 |  | 131
PB 2017 Total | 0 |  | 71 |  | 13 | 9 | 7 |  | 3 |  | 6 | 4 |  | 18 |  | 131
PB 2016 Total | 0 |  | 71 |  | 13 | 9 | 5 |  | 6 |  | 4 | 10 |  | 13 |  | 131
Delta | 0 |  | 0 |  | 0 | 0 | 2 |  | -3 |  | 2 | -6 |  | 5 |  | 0

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.5
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 158.3

## Table 18
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2009 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.3
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.3
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 146.1

## Table 19
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | 7 | 528.4 |  | -- |  | -- |  | 528.4 |  | 86.8 |  | 615.2
2009 |  | 13 | 866.2 |  | -- |  | 13 |  | 879.2 |  | 126.9 |  | 1006.1
2010 |  | 3 | 266.1 |  | 2 |  | -- |  | 268.1 |  | 184.7 |  | 452.8
2011 |  | 9 | 585.4 |  | 1.9 |  | 11.4 |  | 598.7 |  | 153.6 |  | 752.3
2012 |  | 10 | 814.5 |  | 31.4 |  | -- |  | 845.9 |  | 213.3 |  | 1059.2
2013 |  | 12 | 812.1 |  | 72.8 |  | -- |  | 884.9 |  | 128.6 |  | 1013.5
2014 |  | 10 | 953.5 |  | 86.3 |  | -- |  | 1039.8 |  | 130.1 |  | 1169.9
2015 |  | 7 | 569.6 |  | 43.2 |  | -- |  | 612.8 |  | 185.3 |  | 798.1
2016 |  | 13 | 900.7 |  | 27.4 |  | -- |  | 928.1 |  | 424.6 |  | 1352.7
2017 |  | 9 | 643.8 |  | 44.3 |  | 19.1 |  | 707.2 |  | 273 |  | 980.2
2018 |  | 7 | 480.4 |  | 42.4 |  | 22.2 |  | 545 |  | 145.7 |  | 690.7
2019 |  | 3 | 284.8 |  | 35.7 |  | 10.5 |  | 331 |  | 76.4 |  | 407.4
2020 |  | 6 | 509.5 |  | 4.2 |  | 21 |  | 534.7 |  | 101.3 |  | 636
2021 |  | 4 | 327.2 |  | 4.2 |  | 14 |  | 345.4 |  | 108.2 |  | 453.6
2022 |  | 6 | 625.6 |  | 63.2 |  | 17.5 |  | 706.3 |  | 154.5 |  | 860.8
2023 |  | 6 | 625.6 |  | 74.3 |  | 17.5 |  | 717.4 |  | 154.7 |  | 872.1
2024 |  | 6 | 625.6 |  | 75.3 |  | 17.5 |  | 718.4 |  | 154.6 |  | 873
2025 |  | -- | -- |  | 65.6 |  | -- |  | 65.6 |  | -- |  | 65.6
2026 |  | -- | -- |  | 55.4 |  | -- |  | 55.4 |  | -- |  | 55.4
2027 |  | -- | -- |  | 15.4 |  | -- |  | 15.4 |  | -- |  | 15.4
2028 |  | -- | -- |  | 52.8 |  | -- |  | 52.8 |  | -- |  | 52.8
Subtotal |  | 131 | 10419 |  | 797.8 |  | 163.7 |  | 11380.5 |  | 2802.3 |  | 14182.8

## Table 20
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2009 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | 7 | 525.1 |  | -- |  | -- |  | 525.1 |  | 86.2 |  | 611.3
2009 |  | 13 | 846.7 |  | -- |  | 12.7 |  | 859.4 |  | 124.1 |  | 983.5
2010 |  | 3 | 255.1 |  | 1.9 |  | -- |  | 257 |  | 177.1 |  | 434.1
2011 |  | 9 | 552.5 |  | 1.8 |  | 10.8 |  | 565.1 |  | 144.9 |  | 710
2012 |  | 10 | 757.2 |  | 29.2 |  | -- |  | 786.4 |  | 198.2 |  | 984.6
2013 |  | 12 | 739.6 |  | 66.3 |  | -- |  | 805.9 |  | 117.2 |  | 923.1
2014 |  | 10 | 856.8 |  | 77.5 |  | -- |  | 934.3 |  | 116.9 |  | 1051.2
2015 |  | 7 | 505.2 |  | 38.3 |  | -- |  | 543.5 |  | 164.3 |  | 707.8
2016 |  | 13 | 783.9 |  | 23.8 |  | -- |  | 807.7 |  | 369.6 |  | 1177.3
2017 |  | 9 | 549.9 |  | 37.8 |  | 16.3 |  | 604 |  | 233.2 |  | 837.2
2018 |  | 7 | 402.4 |  | 35.5 |  | 18.6 |  | 456.5 |  | 122.1 |  | 578.6
2019 |  | 3 | 233.8 |  | 29.3 |  | 8.6 |  | 271.7 |  | 62.8 |  | 334.5
2020 |  | 6 | 410.2 |  | 3.4 |  | 16.9 |  | 430.5 |  | 81.5 |  | 512
2021 |  | 4 | 258.1 |  | 3.3 |  | 11 |  | 272.4 |  | 85.5 |  | 357.9
2022 |  | 6 | 483.9 |  | 48.9 |  | 13.5 |  | 546.3 |  | 119.5 |  | 665.8
2023 |  | 6 | 474.6 |  | 56.4 |  | 13.3 |  | 544.3 |  | 117.3 |  | 661.6
2024 |  | 6 | 465.2 |  | 56 |  | 13 |  | 534.2 |  | 115 |  | 649.2
2025 |  | -- | -- |  | 47.8 |  | -- |  | 47.8 |  | -- |  | 47.8
2026 |  | -- | -- |  | 39.6 |  | -- |  | 39.6 |  | -- |  | 39.6
2027 |  | -- | -- |  | 10.8 |  | -- |  | 10.8 |  | -- |  | 10.8
2028 |  | -- | -- |  | 36.3 |  | -- |  | 36.3 |  | -- |  | 36.3
Subtotal |  | 131 | 9100.2 |  | 643.9 |  | 134.7 |  | 9878.8 |  | 2435.4 |  | 12314.2

## Table 21
Annual Funding 0300 ¦ Procurement ¦ Procurement, Defense-Wide
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | 56.9 |  | 56.9 |  | -- |  | 56.9
2009 |  | -- | -- |  | -- |  | 9.5 |  | 9.5 |  | -- |  | 9.5
2010 |  | -- | -- |  | -- |  | 1.5 |  | 1.5 |  | -- |  | 1.5
2011 |  | -- | -- |  | -- |  | 2 |  | 2 |  | -- |  | 2
2012 |  | -- | -- |  | -- |  | 18.7 |  | 18.7 |  | -- |  | 18.7
Subtotal |  | -- | -- |  | -- |  | 88.6 |  | 88.6 |  | -- |  | 88.6

## Table 22
Annual Funding 0300 ¦ Procurement ¦ Procurement, Defense-Wide
Fiscal Year | Quantity |  | BY 2009 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | 56.7 |  | 56.7 |  | -- |  | 56.7
2009 |  | -- | -- |  | -- |  | 9.3 |  | 9.3 |  | -- |  | 9.3
2010 |  | -- | -- |  | -- |  | 1.5 |  | 1.5 |  | -- |  | 1.5
2011 |  | -- | -- |  | -- |  | 1.9 |  | 1.9 |  | -- |  | 1.9
2012 |  | -- | -- |  | -- |  | 17.5 |  | 17.5 |  | -- |  | 17.5
Subtotal |  | -- | -- |  | -- |  | 86.9 |  | 86.9 |  | -- |  | 86.9

## Table 23
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | TY $M
Total Program
2010 | 22.6
2011 | 35.8
2012 | 12.5
2013 | 8.5
2014 | --
2015 | --
2016 | 16.9
Subtotal | 96.3

## Table 24
Annual Funding 3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | BY 2009 $M
Total Program
2010 | 21.8
2011 | 33.8
2012 | 11.6
2013 | 7.7
2014 | --
2015 | --
2016 | 14.6
Subtotal | 89.5

## Table 25
Annual Funding 0500 ¦ MILCON ¦ Military Construction, Defense-Wide
Fiscal Year | TY $M
Total Program
2010 | 14.2
2011 | 37.3
2012 | 94
Subtotal | 145.5

## Table 26
Annual Funding 0500 ¦ MILCON ¦ Military Construction, Defense-Wide
Fiscal Year | BY 2009 $M
Total Program
2010 | 13.5
2011 | 34.8
2012 | 86.4
Subtotal | 134.7

## Table 27
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2010-04-12 | 2011-05-09
Approved Quantity | 46 | 52
Reference | Milestone C ADM | Milestone C ADM
Start Year | 2008 | 2008
End Year | 2013 | 2013
The Current Total LRIP Quantity is more than 10% of the total production quantity due to user's urgent need and existing capability of the aircraft production line.

## Table 28
Foreign Military Sales
None
Nuclear Costs
None

## Table 29
Unit Cost
Unit Cost Report
Item |  | BY 2009 $M | BY 2009 $M |  | % Change
|  | Current UCR Baseline (Oct 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 13150.2 |  |  | 12771.4
Quantity | 131 |  |  | 131
Unit Cost | 100.383 |  |  | 97.492 |  | -2.88
Average Procurement Unit Cost
Cost | 12665.9 |  |  | 12401.1
Quantity | 131 |  |  | 131
Unit Cost | 96.686 |  |  | 94.665 |  | -2.09
Item |  | BY 2009 $M | BY 2009 $M |  | % Change
|  | Original UCR Baseline (Mar 2010 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 8078.1 |  |  | 12771.4
Quantity | 74 |  |  | 131
Unit Cost | 109.164 |  |  | 97.492 |  | -10.69
Average Procurement Unit Cost
Cost | 7436 |  |  | 12401.1
Quantity | 74 |  |  | 131
Unit Cost | 100.486 |  |  | 94.665 |  | -5.79

## Table 30
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2009 $M | [5 empty] | TY $M
[8 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Mar 2010 |  |  |  |  | 109.164 |  |  | 100.486 |  |  |  | 118.18 |  |  | 108.841
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  | Mar 2011 |  |  |  |  | 105.002 |  |  | 99.739 |  |  |  | 116.92 |  |  | 111.256
Current APB |  |  | Oct 2013 |  |  |  |  | 100.383 |  |  | 96.686 |  |  |  | 117.364 |  |  | 113.256
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 99.115 |  |  | 96.308 |  |  |  | 114.165 |  |  | 111.132
Current Estimate |  |  | Dec 2015 |  |  |  |  | 97.492 |  |  | 94.665 |  |  |  | 111.996 |  |  | 108.942
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [14 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth |  |  | Spt | Total
118.180 0.899 -3.193 -0.756 2.167 -14.908 0.000 9.607 -6.184 111.996
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth |  |  | Spt | Total
108.841 0.842 0.871 -0.756 2.167 -12.630 0.000 9.607 0.101 108.942

## Table 31
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | N/A | N/A
Milestone C | N/A | N/A | Feb 2010 | Apr 2010
RAA | N/A | N/A | Dec 2012 | Dec 2012
Total Cost (TY $M) | N/A | N/A | 8745.3 | 14671.5
Total Quantity | N/A | N/A | 74 | 131
PAUC | N/A | N/A | 118.18 | 111.996

## Table 32
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 154.3 | 8054.2 | 536.8 | 8745.3
Previous Changes
Economic | 0.4 | 178.7 | 7.9 | 187
Quantity | -- | 6318 | -- | 6318
Schedule | -- | -133.2 | -- | -133.2
Engineering | -- | 283.9 | -- | 283.9
Estimating | 0.8 | -1394.5 | -302.9 | -1696.6
Other | -- | -- | -- | --
Support | -- | 1251.2 | -- | 1251.2
Subtotal | 1.2 | 6504.1 | -295 | 6210.3
Current Changes
Economic | -0.4 | -68.4 | -0.4 | -69.2
Quantity | -- | -- | -- | --
Schedule | -- | 34.2 | -- | 34.2
Engineering | -- | -- | -- | --
Estimating | 3.2 | -260 | 0.4 | -256.4
Other | -- | -- | -- | --
Support | -- | 7.3 | -- | 7.3
Subtotal | 2.8 | -286.9 | -- | -284.1
Total Changes | 4 | 6217.2 | -295 | 5926.2
CE - Cost Variance | 158.3 | 14271.4 | 241.8 | 14671.5
CE - Cost & Funding | 158.3 | 14271.4 | 241.8 | 14671.5

## Table 33
Summary BY 2009 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 148 | 7436 | 494.1 | 8078.1
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | 5247.2 | -- | 5247.2
Schedule | -- | -104.5 | -- | -104.5
Engineering | -- | 261.1 | -- | 261.1
Estimating | -4.1 | -1214.8 | -270.3 | -1489.2
Other | -- | -- | -- | --
Support | -- | 991.4 | -- | 991.4
Subtotal | -4.1 | 5180.4 | -270.3 | 4906
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 2.2 | -231.4 | 0.4 | -228.8
Other | -- | -- | -- | --
Support | -- | 16.1 | -- | 16.1
Subtotal | 2.2 | -215.3 | 0.4 | -212.7
Total Changes | -1.9 | 4965.1 | -269.9 | 4693.3
CE - Cost Variance | 146.1 | 12401.1 | 224.2 | 12771.4
CE - Cost & Funding | 146.1 | 12401.1 | 224.2 | 12771.4
Previous Estimate: December 2014

## Table 34
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -0.4
Revised estimate as a result of baseline extension to FY 2021 and minor miscellaneous adjustments. (Estimating)
+2.2 +3.2
RDT&E Subtotal +2.2 +2.8
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -68.4
Adjustment for current and prior escalation. (Estimating) | 17.2 | 19.1
Stretch-out of procurement buy profile from FY 2023 to FY 2024. (Schedule) | 0 | 34.2
Reductions in FY 2013 funds for Omnibus Reprogramming actions during FY 2015. | -45.5 | -50.7
(Estimating)
Congressional Reduction in FY 2016. (Estimating) -50.5 -57.1
Revised estimate reflects updated estimating methodology for "To Complete" aircraft costs. (Estimating)
-152.6 -171.3
Adjustment for current and prior escalation. (Support) +4.1 +4.9
Decrease in Initial Spares as a result of prior SAR misallocation to Initial Spares and minor miscellaneous adjustments. (Support)
Increase in Other Support as a result of prior SAR misallocation to Initial Spares and minor miscellaneous adjustments. (Support)
-178.4 -233.7
+190.4 +236.1
Procurement Subtotal -215.3 -286.9
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.4
Adjustment for current and prior escalation. (Estimating) | 0.4 | 0.4
MILCON Subtotal | 0.4 | 0

## Table 35
Contracts
General Notes
The HC/MC-130 Recapitalization program uses the recently awarded Multi-Year Procurement Contract for production aircraft buys. The Five Year Option Contract (FYOC IV) ordering period ends January 31, 2016, and will be superseded by the Five Year Ordering Contract to be awarded in 3rd Quarter FY 2016.
Contract Identification
Appropriation: Procurement
Contract Name: HC/MC-130J Production (FYOC IV)
Contractor: Lockheed Martin
Contractor Location: 86 South Cobb Drive
Marietta, GA 39963-0290
Contract Number: FA8625-11-C-6597
Contract Type: Firm Fixed Price (FFP)
Award Date: March 17, 2011
Definitization Date: March 17, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
2.2 N/A 0 1573.0 N/A 23 1573.0 1573.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the program moving from LRIP to FRP.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 36
Contract Identification
Appropriation: Procurement
Contract Name: HC/MC-130J Multi-Year Procurement II (MYP II)
Contractor: Lockheed Martin
Contractor Location: 86 South Cobb Drive
Marietta, GA 39963-0290
Contract Number: FA8625-14-C-6450
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 09, 2013
Definitization Date: December 30, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
132.0 N/A 0 3027.2 3027.2 43 3027.2 3027.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to The difference between the Initial Contract PriceTarget and the Current Contract Price Target is due to the definitization of the MYP II contract that occurred December 30, 2015, placing 43 HC/MC aircraft on contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances -- --
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this FPIF contract, because EVM reporting has been waived. A class deviation to exclude Defense Federal Acquisition Regulation Supplement clauses 252.234-7001 and 252.234-7002 was approved by Headquarters Air Force Materiel Command on February 13, 2014.

## Table 37
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 53 | 53 | 131 | 40.46%
Total Program Quantity Delivered | 53 | 53 | 131 | 40.46%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
14671.5
5025.9
34.26%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
9
42.86%
8648.6
58.95%
The above data is current as of March 02, 2016.

## Table 38
Operating and Support Cost
Cost Estimate Details
Date of Estimate: November 17, 2014
Source of Estimate: POE
Quantity to Sustain: 131
Unit of Measure: Aircraft
Service Life per Unit: 30.00 Years
Fiscal Years in Service: FY 2013 - FY 2055
Sustainment Strategy
Two level maintenance is planned for fleet of 131 aircraft. Contractor Logistics Support for Airframe provide by Lockheed Martin and for Engines by Rolls Royce. Maintenance cycle for basic maintenance is six years and de-paint and scuff is 12 years.
Antecedent Information
The HC/MC-130 Recap program recapitalizes several antecedents, including the HC-130P/N and MC-130E/H/P fleets. It also provides aircraft which, after modification in a separate Special Operations Command (SOCOM) program, recapitalize the AC-130H/U/W gunship fleet. The total of these antecedents was 131 aircraft before retirements began.
Antecedent aircraft were designed for a 30-year service life; multiple center wing box replacements and other actions extended that life to 48 years for the last of the now-retired MC-130E. MC-130P retirement planning also reflects service lives of up to 48 years after similar extensions. O&S cost comparisons are based on the MC-130P.
Antecedent annual costs of the MC-130P are listed. Antecedent annual cost information is based on analysis of Air Force Total Ownership Cost 2010 data for HC/MC-130P.
Annual O&S Costs BY2009 $M
Cost Element | HC/MC-130 Recap Average Annual Cost Per Aircraft | MC-130P (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower | 4.077 | 4.5
Unit Operations | 0.95 | 1.7
Maintenance | 1.842 | 3.5
Sustaining Support | 0.411 | 0.4
Continuing System Improvements | 0.756 | 0.6
Indirect Support | 2.097 | 1.1
Other | -- | --
Total | 10.133 | 11.8

## Table 39
Item | Total O&S Cost $M
| HC/MC-130 Recap | [5 empty] | MC-130P (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 40008.6 |  | 44009.5 |  |  | 39822.6 | N/A
Then Year | 58602.4 |  | N/A |  |  | 63751.1 | 0
Equation to Translate Annual Cost to Total Cost
Total O&S cost were calculated based on 30 year useful life x quantity x unitized cost per aircraft (30 years x 131 aircraft x $10.133M average annual cost per aircraft = $39,822.6M).
O&S Cost Variance
Category |  | BY 2009 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
39822.6
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 39822.6
Disposal Estimate Details
Date of Estimate: October 03, 2013
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2009 $M): Total costs for disposal of all Aircraft are 10.7