## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-292
Global Positioning System III (GPS III)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 23
Foreign Military Sales 24
Nuclear Costs 24
Unit Cost 25
Cost Variance 28
Contracts 31
Deliveries and Expenditures 34
Operating and Support Cost 35

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Global Positioning System III (GPS III)
DoD Component
Air Force
Responsible Office
Col Steven Whitney 483 N. Aviation Blvd
El Segundo, CA 90245
steven.whitney.1@us.af.mil
Phone: | 310-653-3001
Fax: | 310-653-3005
DSN Phone: | 633-3001
DSN Fax: | 633-3005
Date Assigned: | July 8, 2015
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated January 31, 2011
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated January 31, 2016

## Table 6
Mission and Description
Global Positioning System (GPS) is a satellite-based radio navigation system that provides worldwide military and civil users satellite signals they can process to determine accurate position, velocity, and time. On May 8, 2000, the USD(AT&L) approved entry into the initial modernization efforts for Navstar GPS. GPS III, an Acquisition Category ID program, is the next generation space vehicle (SV) that will provide significant enhancements to complete the modernization of the constellation. GPS III complies with 10 United States Code (USC) § 2281, ensuring the continued sustainment and operation of GPS for military and civilian purposes, and 51 USC § 50112, continuing as an international standard available on a continuous worldwide basis free of direct user fees.
As captured in a November 6, 2006 Memorandum, the JROC validated and endorsed the GPS III CDD for the first increment, validating the requirements for the GPS III program and authorized the Air Force to deliver SV01-SV08. In his February 27, 2015 ADM, the USD(AT&L) directed the procurement of SV09/10 as technical equivalents for SV01-08. Follow
-on vehicles SV11+ will be procured in future increments.
The primary GPS III missions are worldwide positioning, navigation, and precise time transfer. GPS provides strategic and tactical support to the following DoD missions: Joint Operations by providing capabilities for Position, Navigation and Timing (PNT); Command, Control, Communications, and Intelligence; Special Operations; Military Operations in Urban Terrain; Defense-Wide Mission Support; Air Mobility; and Space Launch Orbital Support.
For military users, the GPS III program provides Precise Positioning Service (PPS) to military operations and force enhancement. It also provides increased anti-jam power to the earth coverage Military code signals and anti-exploitation techniques in order to prevent unauthorized use of the GPS PPS signal. In addition, the program will support the U.S. Nuclear Detonation Detection System mission for worldwide monitoring and detection of nuclear events via a hosted payload.
The GPS III program provides a Standard Positioning Service to a broad spectrum of civil users which will include the three civil signals (L1 C/A, L2C, and L5) flown on previous satellites. It will also transmit a new fourth civil signal (L1C), which is compatible with the European Galileo satellite navigation system signal, E1. L1C is also compatible with those signals planned for broadcast on Japan's Quazi-Zenith Satellite System, a system meant to augment GPS services. Once implemented, the common civil signal will be jointly broadcast by up to 60 satellites from both GPS and Galileo constellations, further increasing the accuracy and availability of user PNT solutions.

## Table 7
Executive Summary
Since the June 2015 quarterly exception SAR, measurable progress has been made on Space Vehicle (SV) 01. SV01 entered Thermal Vacuum (TVAC) testing on October 12, 2015, and successfully completed baseline TVAC testing on December 23, 2015 – a major system-level event. Significant confidence has been gained with contractor design and workmanship based on TVAC testing, demonstrating the satellite will perform successfully in a space environment.
Contractor Proposals for SV09-SV10 were received for the Long Lead Parts contract on July 30, 2015 and for the Production contract on August 31, 2015, with contract awards projected in the fourth Quarter of FY 2016.
The GPS III Non-Flight Satellite Testbed (GNST) continues to support bus and payload regression testing to verify test procedures. The GPS III program currently does not meet a Nuclear Detonation Detection System requirement for Electromagnetic Interference (EMI) noise emission at the Burst Detection Verification receiver band. The noise is radiating from the SV Bus, specifically the Scalable Power Regulation Unit and is being amplified by the solar arrays which act as highly efficient antennas. To effectively attenuate this noise, prototype EMI filtering hardware has been implemented on GNST, including prototype filter boxes, Faraday Cage improvements, and improved harnesses. Testing of these prototypes completed on February 19, 2016, and provided initial indications that the prototypes are likely to solve the EMI issue. SV01 EMI testing is scheduled for the third quarter FY 2016, and will be the test that determines if SV01 will need to be modified.
On January 31, 2016, USD(AT&L) signed the GPS III revised APB. This Change 1 to the APB was due to both cost and schedule breaches to the January 31, 2011 APB. In addition, this revised APB added SV09 and SV10 to the ACAT program of record.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
GPS III KDP-B | Feb 2008 | Feb 2008 | Aug 2008 | May 2008
GPS III Preliminary Design Review | Apr 2009 | Apr 2009 | Oct 2009 | May 2009
GPS III Critical Design Review | Jul 2010 | Jul 2010 | Jan 2011 | Aug 2010
GPS III Milestone C | Oct 2010 | Oct 2010 | Apr 2011 | Jan 2011
GPS III SV01 AFL | Apr 2014 | Aug 2016 | Feb 2017 | Aug 2016
GPS III SV02 AFL | Apr 2015 | Aug 2017 | Feb 2018 | Aug 2017
GPS III SV08 AFL | May 2018 | Dec 2019 | Jun 2020 | Dec 2019
GPS III SV10 AFL | N/A | Nov 2022 | May 2023 | Nov 2022
Change Explanations
(Ch-1) GPS III SV10 AFL was added in the January 31, 2016 APB in support of SV10 procurement.
Acronyms and Abbreviations
AFL - Available for Launch KDP - Key Decision Point SV - Space Vehicle

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Backward Compatibility
All modifications made | All modifications made | (T=O) All modifications | TBD | All modifications made
to the existing GPS | to the existing GPS | made to the existing |  | to the existing GPS
Space Segment and | Space Segment and | GPS Space Segment |  | Space Segment and
Control Segment shall | Control Segment shall | and Control Segment |  | Control Segment shall
allow continued | allow continued | shall allow continued |  | allow continued
operation of existing | operation of existing | operation of existing |  | operation of existing
ICD-GPS-200 and 700, | ICD-GPS-200 and 700, | ICD-GPS-200 and 700, |  | ICD-GPS-200 and 700,
IS-GPS-705, and SS- | IS-GPS-705, and SS- | IS-GPS-705, and SS- |  | IS-GPS-705, and SS-
GPS-001 compliant UE | GPS-001 compliant UE | GPS-001 compliant UE |  | GPS-001 compliant UE
and continued | and continued | and continued operation |  | and continued
operation of legacy | operation of legacy | of legacy receivers (to |  | operation of legacy
receivers (to include | receivers (to include | include Federal |  | receivers (to include
Federal augmentation | Federal augmentation | augmentation system |  | Federal augmentation
system receivers). | system receivers). | receivers). |  | system receivers).
User Range Error (meters)
0.2 | 0.2 | 1.1 | TBD | 1
Net-Ready
The system must fully | The system must fully | The system must fully | TBD | The system must fully
support execution of all | support execution of all | support execution of |  | support execution of all
joint operational | joint operational | joint critical operational |  | joint operational
activities identified in | activities identified in | activities identified in the |  | activities identified in
the applicable joint and | the applicable joint and | applicable joint and |  | the applicable joint and
system integrated | system integrated | system integrated |  | system integrated
architectures and the | architectures and the | architectures and the |  | architectures and the
system must satisfy | system must satisfy | system must satisfy the |  | system must satisfy
the technical | the technical | technical requirements |  | the technical
requirements for Net- | requirements for Net- | for transition to Net- |  | requirements for Net-
Centric military | Centric military | Centric military |  | Centric military
operations. | operations. | operations. |  | operations.
Satellite Availability
0.984 | 0.984 | (T=O) 0.984 | TBD | 0.984
Boosted Earth-Coverage M-Code Power (dBW)
-148 | -148 | -153 | TBD | -151.7
Minimum L1C Signal Power
-157 | -157 | (T=O) -157 | TBD | -157
Position and Time Transfer Integrity (Probability of Misleading SIS Information)
1e-08 | 1e-08 | 1e-05 | TBD | 1e-08

## Table 11
Requirements Reference
CDD for Increment A dated November 6, 2006
Change Explanations
None
Notes
KPPs Demonstrated Performance remains TBD until testing can be verified with the completion of the SV01 Final SPT.
For the Net Ready KPP, Demonstrated Performance is TBD until it is tested and verified with the completion of IST 3-1 which verifies that OCX Block 1 can command and control legacy GPS II and new GPS III SVs.
ECD for all of these tests is August 2016.
Acronyms and Abbreviations
dBW - Decibel-watt
ECD - Estimated Completion Date GPS - Global Positioning System ICD - Interface Control Document IS - Interface Specifications
IST - Integrated System Test M-Code - Military Code
SIS - Signal in Space
SPT - System Performance Test SS - System Specifications
SV - Space Vehicle UE - User Equipment

## Table 12
Track to Budget
General Notes
In December 2014, the Office of Management and Budget directed the DoD to establish a new space procurement appropriation as a five-year availability account. Beginning in FY 2016, Air Force major procurement funding formerly under appropriation 3020F (Missile Procurement, Air Force) BA 05 will now be under 3021F (Space Procurement, Air Force) BA 01.
RDT&E
Appn |  | BA | PE
Air Force 3600 07 0305265F
Project | Name
67A019 GPS IIIA (Shared)
Air Force 3600 04 0603421F
Project | Name
644993 GPS III Development (Sunk)
Notes
The shared funding line includes funding for SV11+ however these funds are not included in this SAR.
Procurement
Appn |  | BA | PE
Air Force 3020 05 0305265F
Line Item | Name
GPSIII GPS III Space Segment (Shared) (Sunk)
Air Force 3021 01 0305265F
Line Item | Name
GPSIII GPS III Space Segment (Shared)

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2010 $M | [5 empty] | BY 2010 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 2623.9 |  |  | 2981.9 | 3280.1 |  |  | 2926 |  | 2653.8 |  |  | 3080.1 |  | 3018.6
Procurement | 1519 |  |  | 2303.3 | 2533.9 |  |  | 2254.4 |  | 1616 |  |  | 2570 |  | 2538.8
Flyaway | -- |  |  | -- | -- |  |  | 1855.4 |  | -- |  |  | -- |  | 2041.1
Recurring | -- |  |  | -- | -- |  |  | 1847.5 |  | -- |  |  | -- |  | 2031.7
Non Recurring | -- |  |  | -- | -- |  |  | 7.9 |  | -- |  |  | -- |  | 9.4
Support | -- |  |  | -- | -- |  |  | 399 |  | -- |  |  | -- |  | 497.7
Other Support | -- |  |  | -- | -- |  |  | 399 |  | -- |  |  | -- |  | 497.7
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 4142.9 |  |  | 5285.2 | N/A |  |  | 5180.4 |  | 4269.8 |  |  | 5650.1 |  | 5557.4
Current APB Cost Estimate Reference
SCP dated July 02, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 60%
The current APB is established at the 60% confidence level. This estimate is built upon the February 2015 approved program rebaseline, historical actual cost information to the maximum extent possible, and most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Directorate has been successful.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 2 |  |  |  | 2 |  |  |  |  | 2
Procurement |  | 6 |  |  |  | 8 |  |  |  |  | 8
Total |  | 8 |  |  |  | 10 |  |  |  |  | 10

## Table 14
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 2668.5 | 142.2 |  | 91.7 |  | 27.1 | 28.5 |  | 24.2 |  | 7.2 |  | 29.2 |  | 3018.6
Procurement | 1797.9 | 187.7 |  | 30.7 |  | 34.9 | 51.5 |  | 72.4 |  | 55.5 |  | 308.2 |  | 2538.8
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 4466.4 | 329.9 |  | 122.4 |  | 62 | 80 |  | 96.6 |  | 62.7 |  | 337.4 |  | 5557.4
PB 2016 Total | 4205.7 | 126.7 |  | 42.2 |  | 45.7 | 68.9 |  | 64.9 |  | 34.7 |  | 121.9 |  | 4710.7
Delta | 260.7 | 203.2 |  | 80.2 |  | 16.3 | 11.1 |  | 31.7 |  | 28 |  | 215.5 |  | 846.7
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 2
Production | 0 |  | 7 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 8
PB 2017 Total | 2 |  | 7 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 10
PB 2016 Total | 2 |  | 6 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 8
Delta | 0 |  | 1 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 2

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 195.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 183.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 335.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 366.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 406
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 400.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 241.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 193.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 183.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 142.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.2
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.2
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.4
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.3
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.4
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 3018.6

## Table 16
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 202.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 185.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 335.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 362.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 394.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 381.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 226.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 179
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 128.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.6
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.3
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.2
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.9
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.3
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 2926

## Table 17
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | -- | 96 |  | -- |  | -- |  | 96 |  | -- |  | 96
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | 2 | 413.1 |  | -- |  | -- |  | 413.1 |  | 39 |  | 452.1
2013 |  | 2 | 458.2 |  | -- |  | -- |  | 458.2 |  | 33 |  | 491.2
2014 |  | 2 | 417.5 |  | -- |  | -- |  | 417.5 |  | 31.8 |  | 449.3
2015 |  | 1 | 289.1 |  | -- |  | 0.7 |  | 289.8 |  | 19.5 |  | 309.3
Subtotal |  | 7 | 1673.9 |  | -- |  | 0.7 |  | 1674.6 |  | 123.3 |  | 1797.9

## Table 18
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | -- | 94 |  | -- |  | -- |  | 94 |  | -- |  | 94
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | 2 | 390.1 |  | -- |  | -- |  | 390.1 |  | 36.8 |  | 426.9
2013 |  | 2 | 423 |  | -- |  | -- |  | 423 |  | 30.5 |  | 453.5
2014 |  | 2 | 379.9 |  | -- |  | -- |  | 379.9 |  | 29 |  | 408.9
2015 |  | 1 | 260.2 |  | -- |  | 0.6 |  | 260.8 |  | 17.5 |  | 278.3
Subtotal |  | 7 | 1547.2 |  | -- |  | 0.6 |  | 1547.8 |  | 113.8 |  | 1661.6

## Table 19
Cost Quantity Information 3020 ¦ Procurement ¦ Missile Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2010 $M
2010 | -- | --
2011 | -- | --
2012 | 2 | 442
2013 | 2 | 442.1
2014 | 2 | 442.1
2015 | 1 | 221
Subtotal | 7 | 1547.2

## Table 20
Annual Funding 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | 1 | 158.9 |  | -- |  | -- |  | 158.9 |  | 28.8 |  | 187.7
2017 |  | -- | 5.2 |  | -- |  | 2.3 |  | 7.5 |  | 23.2 |  | 30.7
2018 |  | -- | 7.8 |  | 3.7 |  | 3.1 |  | 14.6 |  | 20.3 |  | 34.9
2019 |  | -- | 18.7 |  | 6.4 |  | 1.1 |  | 26.2 |  | 25.3 |  | 51.5
2020 |  | -- | 31.6 |  | 8.6 |  | 1.1 |  | 41.3 |  | 31.1 |  | 72.4
2021 |  | -- | 30.1 |  | 8 |  | 1.1 |  | 39.2 |  | 16.3 |  | 55.5
2022 |  | -- | 37.5 |  | 6.2 |  | -- |  | 43.7 |  | 22.9 |  | 66.6
2023 |  | -- | 25.9 |  | 4.2 |  | -- |  | 30.1 |  | 23.3 |  | 53.4
2024 |  | -- | 0.5 |  | 2.2 |  | -- |  | 2.7 |  | 19.2 |  | 21.9
2025 |  | -- | -- |  | 1.5 |  | -- |  | 1.5 |  | 19 |  | 20.5
2026 |  | -- | -- |  | 0.8 |  | -- |  | 0.8 |  | 18.8 |  | 19.6
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | 18.8 |  | 18.8
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | 18.8 |  | 18.8
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | 18.8 |  | 18.8
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | 18.8 |  | 18.8
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | 17.7 |  | 17.7
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | 15.4 |  | 15.4
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | 11.9 |  | 11.9
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | 6 |  | 6
Subtotal |  | 1 | 316.2 |  | 41.6 |  | 8.7 |  | 366.5 |  | 374.4 |  | 740.9

## Table 21
Annual Funding 3021 ¦ Procurement ¦ Space Procurement, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | 1 | 140.5 |  | -- |  | -- |  | 140.5 |  | 25.4 |  | 165.9
2017 |  | -- | 4.5 |  | -- |  | 2 |  | 6.5 |  | 20.1 |  | 26.6
2018 |  | -- | 6.6 |  | 3.1 |  | 2.6 |  | 12.3 |  | 17.4 |  | 29.7
2019 |  | -- | 15.6 |  | 5.3 |  | 0.9 |  | 21.8 |  | 21.1 |  | 42.9
2020 |  | -- | 25.8 |  | 7 |  | 0.9 |  | 33.7 |  | 25.5 |  | 59.2
2021 |  | -- | 24.1 |  | 6.4 |  | 0.9 |  | 31.4 |  | 13.1 |  | 44.5
2022 |  | -- | 29.5 |  | 4.9 |  | -- |  | 34.4 |  | 17.9 |  | 52.3
2023 |  | -- | 20 |  | 3.2 |  | -- |  | 23.2 |  | 17.9 |  | 41.1
2024 |  | -- | 0.4 |  | 1.7 |  | -- |  | 2.1 |  | 14.4 |  | 16.5
2025 |  | -- | -- |  | 1.1 |  | -- |  | 1.1 |  | 14.1 |  | 15.2
2026 |  | -- | -- |  | 0.6 |  | -- |  | 0.6 |  | 13.6 |  | 14.2
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | 13.4 |  | 13.4
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | 13.1 |  | 13.1
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | 12.9 |  | 12.9
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | 12.6 |  | 12.6
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | 11.6 |  | 11.6
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | 9.9 |  | 9.9
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | 7.5 |  | 7.5
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | 3.7 |  | 3.7
Subtotal |  | 1 | 267 |  | 33.3 |  | 7.3 |  | 307.6 |  | 285.2 |  | 592.8

## Table 22
Cost Quantity Information 3021 ¦ Procurement ¦ Space Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2010 $M
2016 | 1 | 267
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
2022 | -- | --
2023 | -- | --
2024 | -- | --
2025 | -- | --
2026 | -- | --
2027 | -- | --
2028 | -- | --
2029 | -- | --
2030 | -- | --
2031 | -- | --
2032 | -- | --
2033 | -- | --
2034 | -- | --
Subtotal | 1 | 267

## Table 23
Low Rate Initial Production
There is no LRIP for this program.

## Table 24
Foreign Military Sales
None
Nuclear Costs
None

## Table 25
Unit Cost
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Current UCR Baseline (Jan 2016 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 5285.2 |  |  | 5180.4
Quantity | 10 |  |  | 10
Unit Cost | 528.52 |  |  | 518.04 |  |  | -1.98
Average Procurement Unit Cost
Cost | 2303.3 |  |  | 2254.4
Quantity | 8 |  |  | 8
Unit Cost | 287.912 |  |  | 281.8 |  |  | -2.12
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Original UCR Baseline (May 2008 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3840.8 |  |  | 5180.4
Quantity | 8 |  |  | 10
Unit Cost | 480.1 |  |  | 518.04 |  | 7.9
Average Procurement Unit Cost
Cost | 1381 |  |  | 2254.4
Quantity | 6 |  |  | 8
Unit Cost | 230.167 |  |  | 281.8 |  | 22.43

## Table 26
Unit Cost History
Item | [6 empty] | Date |  |  |  | BY 2010 $M | [7 empty] | TY $M
[11 empty] | PAUC |  |  |  | APUC |  |  |  | PAUC |  |  |  |  | APUC
Original APB |  |  |  |  | May 2008 | [6 empty] | 480.1 |  |  |  | 230.167 |  |  |  |  | 500.288 |  |  |  | 248.383
APB as of January 2006 |  |  |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Jan 2011 | [6 empty] | 517.862 |  |  |  | 253.167 |  |  |  |  | 533.725 |  |  |  | 269.333
Current APB |  |  |  |  | Jan 2016 | [6 empty] | 528.52 |  |  |  | 287.912 |  |  |  |  | 565.01 |  |  |  | 321.25
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 557.762 |  |  |  | 262.75 |  |  |  |  | 588.838 |  |  |  | 290.133
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 518.04 |  |  |  | 281.8 |  |  |  |  | 555.74 |  |  |  | 317.35
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  |  | Oth |  |  |  | Spt |  |  | Total
500.288 -9.013 0.000 0.775 0.000 63.063 -9.513 -11.875 33.437 533.725
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  |  | Oth |  | Spt |  | Total
533.725 3.050 -31.275 0.000 0.000 -0.110 0.000 50.350 22.015 555.740

## Table 27
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [14 empty] | APUC Production Estimate
| Econ | Qty |  | Sch |  | Eng |  |  | Est |  | Oth |  | Spt |  | Total
248.383 -6.450 0.000 1.033 0.000 54.933 -12.733 -15.833 20.950 269.333
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  |  | Est |  | Oth | Spt |  | Total
269.333 2.562 27.005 0.000 0.000 -44.488 0.000 62.938 48.017 317.350
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  |  | SAR Development Estimate | [5 empty] | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  |  |  | Feb 2008 | [5 empty] | Feb 2008 |  |  | May 2008
Milestone C |  |  | N/A |  |  |  |  | Sep 2009 | [5 empty] | Oct 2010 |  |  | Jan 2011
IOC |  |  | N/A |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A
Total Cost (TY $M) |  |  | N/A |  |  |  |  | 4002.3 | [5 empty] | 4269.8 |  |  | 5557.4
Total Quantity |  |  | N/A |  |  |  |  | 8 | [5 empty] | 8 |  |  | 10
PAUC |  |  | N/A |  |  |  |  | 500.288 | [5 empty] | 533.725 |  |  | 555.74

## Table 28
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
2653.8 1616.0 -- 4269.8
Economic |  | 14.6 |  | 26.3 |  | -- |  | 40.9
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 322.6 |  | -264.9 |  | -- |  | 57.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 342.9 |  | -- |  | 342.9
Subtotal |  | 337.2 |  | 104.3 |  | -- |  | 441.5
Current Changes Economic |  | -4.6 |  | -5.8 |  | -- |  | -10.4
Quantity |  | -- |  | 754.7 |  | -- |  | 754.7
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 32.2 |  | -91 |  | -- |  | -58.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 160.6 |  | -- |  | 160.6
Subtotal |  | 27.6 |  | 818.5 |  | -- |  | 846.1
Total Changes |  | 364.8 |  | 922.8 |  | -- |  | 1287.6
CE - Cost Variance |  | 3018.6 |  | 2538.8 |  | -- |  | 5557.4
CE - Cost & Funding |  | 3018.6 |  | 2538.8 |  | -- |  | 5557.4

## Table 29
Summary BY 2010 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
2623.9 1519.0 -- 4142.9
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 280.1 |  | -243 |  | -- |  | 37.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 284.2 |  | -- |  | 284.2
Subtotal |  | 280.1 |  | 41.2 |  | -- |  | 321.3
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 661.1 |  | -- |  | 661.1
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 22 |  | -81.7 |  | -- |  | -59.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 114.8 |  | -- |  | 114.8
Subtotal |  | 22 |  | 694.2 |  | -- |  | 716.2
Total Changes |  | 302.1 |  | 735.4 |  | -- |  | 1037.5
CE - Cost Variance |  | 2926 |  | 2254.4 |  | -- |  | 5180.4
CE - Cost & Funding |  | 2926 |  | 2254.4 |  | -- |  | 5180.4
Previous Estimate: June 2015

## Table 30
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -4.6
Adjustment for current and prior escalation. (Estimating) +3.5 +3.7
Revised estimate for Space Vehicle (SV) 01 and SV02 due to technical issues with the Mission Data Unit (MDU). (Estimating)
+88.7 +100.8
Reallocation of funding between SV01- SV10 to SV11+. (Estimating) | -55.2 |  |  | -56.4
Reduction due to higher Air Force priorities. (Estimating) | -8.7 |  |  | -9.1
Revised estimate for Small Business Innovation Research in FY 2015. (Estimating) | -6.3 |  |  | -6.8
RDT&E Subtotal | 22 |  |  | 27.6
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -5.8
Adjustment for current and prior escalation. (Estimating) +3.5 +3.8
Quantity variance resulting from an increase of 1 satellite from 0 to 1 (Space Procurement, Air Force (SPAF)). (Subtotal)
Quantity variance resulting from an increase of 1 satellite from 0 to 1 (SPAF). (Quantity)
+208.5 +235.9
(+253.2) (+286.4)
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-44.7) (-50.5)
Additional quantity variance due to actuals for the procurement of SV10 in FY 2016 (SPAF). (Quantity)
Quantity variance resulting from an increase of 1 satellite from 6 to 7 (Missile Procurement, Air Force (MPAF)). (Subtotal)
Quantity variance resulting from an increase of 1 satellite from 6 to 7 (MPAF). (Quantity)
+55.7 +77.6
+208.5 +231.7
(+253.2) (+281.4)
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-44.7) (-49.7)
Additional quantity variance due to increased costs and long lead and actuals for the procurement of SV09 in FY 2015 (MPAF). (Quantity)
+99.0 +109.3
Revised estimate to reclassify funds from support to flyaway. (Estimating) +0.7 +0.7
Revised estimate to reclassify funds from flyaway to support. (Estimating) -0.6 -0.7
Revised estimate for SV07 and SV08 production due to SV01 MDU technical issues. (Estimating)
+1.8 +2.1
Revised estimate for additional costs for Payload and storage. (Estimating) +2.3 +3.3
Adjustment for current and prior escalation. (Support) +0.5 +0.5
Decrease in Other Support due to reclassification of funds from support to flyaway and other miscellaneous adjustments (MPAF). (Support)
Increase in Other Support due to additional support requirements, increase in launch operations and SV processing, increase in other government costs, and reallocation efficiency (SPAF). (Support)
-14.3 -15.7
+128.6 +175.8
Procurement Subtotal +694.2 +818.5
(QR) Quantity Related

## Table 31
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: Global Positioning System (GPS) III (Development) Contractor: Lockheed Martin Space Systems Denver Contractor Location: Littleton, CO 80125
Contract Number: FA8807-08-C-0010
Contract Type: Cost Plus Incentive Fee (CPIF), Cost Plus Award Fee (CPAF)
Award Date: May 15, 2008
Definitization Date: May 15, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1249.1 N/A 2 1414.5 N/A 2 2180.8 2194.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional scope associated with the award of the GPS III Launch and Checkout Capability, associated information security upgrades, and additional costs as a result of immature technical requirements for parts and processes, as well as additional funds to cover provisional overruns.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/25/2015) +15.5 -11.4
Previous Cumulative Variances +10.8 -1.8
Net Change +4.7 -9.6
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to pre-acoustics installation and deployments for Space Vehicle (SV)01 requiring less work than planned and a delay to the start of the contingency operations study.
The unfavorable net change in the schedule variance is due to delays in starting Thermal Vacuum testing at the Lockheed Martin factory as well as a five-month delay in the delivery of the navigation payload element for SV02.
Notes
The estimated price at completion decreased primarily due to the reduction of available fee.

## Table 32
Contract Identification
Appropriation: Procurement
Contract Name: Global Positioning System (GPS) III (Production) Contractor: Lockheed Martin Space Systems Denver Contractor Location: Littleton, CO 80125
Contract Number: FA8807-08-C-0010/2
Contract Type: Cost Plus Incentive Fee (CPIF), Fixed Price Incentive(Firm Target) (FPIF)
Award Date: May 15, 2008
Definitization Date: May 15, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
74.7 N/A 2 767.5 N/A 6 1227.4 1230.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of the Space Vehicle (SV)05/06 and SV07/08 efforts, as well as adjustments in cost estimates resulting from the 2015 Over Target Baseline.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/25/2015) +13.8 +1.7
Previous Cumulative Variances +5.0 +5.3
Net Change +8.8 -3.6
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to Earned Value Management administrative corrections in June due to general ledger and frangibolt miscoding issues as well as efficient performance in the navigation payload element integrated product team during regression testing on Serial Number 103 Mission Data Units. Also Lockheed Martin is realigning their subcontract dates to better account for hardware delivery dates.
The unfavorable net change in the schedule variance is due to material actual cost transfers and subcontract correction and realignment. In the month of October, there was a negative schedule variance due to the correction of subcontract work being improperly coded within Lockheed Martin’s accounting system as material.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 33
Contract Identification
Appropriation: Procurement
Contract Name: GPS III Long Lead SV05-08
Contractor: Lockheed Martin Space Systems Denver
Contractor Location: Littleton, CO 80125
Contract Number: FA8807-13-C-0002
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: February 08, 2013
Definitization Date: February 08, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
119.5 142.4 4 134.0 142.4 4 133.5 133.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional funds to cover provisional overruns.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/25/2015) +0.4 -0.1
Previous Cumulative Variances +0.1 -14.2
Net Change +0.3 +14.1
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to transfer of material actuals.
The favorable net change in the schedule variance is due to transfers of material actuals within Lockheed Martin’s inventory and Earned Value systems.

## Table 34
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 2 | 0%
Production | 0 | 0 | 8 | 0%
Total Program Quantity Delivered | 0 | 0 | 10 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
5557.4
3292.1
59.24%
33
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
15
45.45%
4796.3
86.3%
The above data is current as of February 23, 2016.
Delivery of Space Vehicle 01 is on-track to be delivered in the 4th quarter of FY 2016.

## Table 35
Operating and Support Cost
Cost Estimate Details
Date of Estimate: Source of Estimate: Quantity to Sustain: Unit of Measure: Service Life per Unit:
Fiscal Years in Service:
The GPS III program will provide O&S for on-orbit support through the Launch and On-Orbit Support contract. For Space Vehicle (SV)01 and SV02, this is funded with RDT&E, AF and for SV03-08, it is funded with Space Procurement, AF. These costs are captured in the cost and funding section of the SAR and will not appear here. The O&S responsibility for the control system will be accomplished through the GPS Logistics Directorate within the Next Generation Operational Control System.
Sustainment Strategy
.
Antecedent Information
.
Annual O&S Costs BY2010 $M
Cost Element |  | GPS III |  |  |  | No Antecedant (Antecedent)
Unit-Level Manpower |  | -- |  |  |  | --
Unit Operations |  | -- |  |  |  | --
Maintenance |  | -- |  |  |  | --
Sustaining Support |  | -- |  |  |  | --
Continuing System Improvements |  | -- |  |  |  | --
Indirect Support |  | -- |  |  |  | --
Other |  | -- |  |  |  | --
Total |  | -- |  |  |  | --
Item | Total O&S Cost $M
| GPS III | [5 empty] | No Antecedant (Antecedent)
| Current Production APB Objective/Threshold |  |  | Current Estimate
Base Year | 0 |  | 0 |  | N/A |  | N/A
Then Year | 0 |  | N/A |  | N/A |  | 0
O&S Cost Variance

## Table 36
Category | BY 2010 $M | Change Explanations
Prior SAR Total O&S Estimates - Jun 2015 SAR
0
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 0.0
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2010 $M):