## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-555
Joint Air-to-Surface Standoff Missile (JASSM)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 6
Mission and Description 7
Executive Summary 8
Threshold Breaches 10
Schedule 11
Performance 14
Track to Budget 16
Cost and Funding 17
Low Rate Initial Production 33
Foreign Military Sales 34
Nuclear Costs 34
Unit Cost 35
Cost Variance 41
Contracts 47
Deliveries and Expenditures 51
Operating and Support Cost 52

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Joint Air-to-Surface Standoff Missile (JASSM)
DoD Component
Air Force
Joint Participants
Department of the Navy
Responsible Office
Col Christopher B. "Alf" Athearn
Long Range Systems Range Division JASSM System Program Office
205 West D Ave, Suite 632, Bldg 350 Eglin Air Force Base, FL 32542-6807
christopher.athearn@us.af.mil
Phone: | 850-883-5340
Fax: | 850-882-5394
DSN Phone: | 875-5340
DSN Fax: | 872-5394
Date Assigned: | July 21, 2014

## Table 6
References
JASSM Baseline
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 4, 2011
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated March 20, 2015
JASSM-ER
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 4, 2011
Approved APB
Air Force Acquisition Executive (AFAE) Approved Acquisition Program Baseline (APB) dated March 20, 2015

## Table 7
Mission and Description
Introduction:
The Joint Air-to-Surface Standoff Missile (JASSM) is a next generation cruise missile enabling the U.S. Air Force to destroy the enemy’s war-sustaining capabilities from outside its area air defenses. It is precise, lethal, survivable, flexible, and adverse-weather capable. JASSM’s inherent accuracy (three meters (m) or less using the Imaging Infrared (IIR) seeker and less than 13 m with Global Positioning System (GPS)/Inertial Navigation System (INS) only) reduces the number of weapons and sorties required to destroy a target.
Mission:
JASSM provides both fighter and bomber aircraft the capability to strike critical, high value, heavily defended targets early in a campaign.
Vision:
To provide the warfighter with an autonomous, precision standoff strike weapon product line at an affordable cost and on schedule.
Description:
JASSM Baseline (BL) and JASSM-Extended Range (ER) are low observable, highly survivable, subsonic cruise missiles which carry a 1000-pound class, hardened, penetrating warhead with a robust blast fragmentation capability. The missiles employ an IIR seeker system to attack fixed, point targets requiring precision targeting. The missiles use GPS/INS for mid- course navigation and as a back up for terminal guidance. A launch can occur over a wide range of altitudes and at ranges greater than 200 nautical miles (nm) (Baseline) or greater than 500 nm (ER). JASSM Baseline and JASSM-ER (Lots 1-10) have a 15-year warranty. Lot 11 and out will be under Contractor Logistics Support.
CONOPS:
JASSM employment will occur primarily in the early stages of conflict before air superiority is established, and in the later stages of conflict against high value targets remaining heavily defended. JASSM can also be employed in those cases where, due to rules of engagement/political constraints, high value, point targets must be attacked from international airspace. JASSM may be employed independently or the missile may be used as part of a composite package.

## Table 8
Executive Summary
Pursuant to section 2432 of title 10, United States Code, this is the final SAR submission for the JASSM BL subprogram, because the subprogram is 90% or more expended.
During CY 2015, the Defense Contract Management Agency accepted 34 of 40 JASSM-ER LRIP Lot 3 missiles, the remaining 8 JASSM BL Lot 10 missiles, and 148 of 190 BL Lot 11 missiles. Production began on BL Lot 12 and ER LRIP Lot 4 in November 2015. JASSM BL is in sustained production with over 1,520 missiles currently in inventory. ER continues with LRIP, having 90 missiles in its inventory.
The BL and ER Lot 13 Production Contract was awarded to Lockheed Martin (LM) on October 9, 2015 for 100 BL and 140 ER missiles. ER Lot 14a was awarded on December 1, 2015 for 100 JASSM BL missiles and 140 ER missiles. Lot 14b is expected to be exercised for 100 additional ER missiles upon funding availability. Unit prices for JASSM-ER decreased by 17% for Lot 13 and 22% for Lot 14. Total quantity for the two lots is 200 BL, 380 ER, and 86 FMS.
On April 15, 2015, the fourth and fifth of five planned Product Verification Test (PVT) launches were completed and achieved all major test objectives for the Guidance Navigation and Control/Aerodynamic (GN&C) (inverted) flight performance capability. This test will provide important data to assess flight performance improvements in the new missile Operational Flight Program. The missile flights were nominal; all test objectives appear to have been met.
The last two of the planned five GN&C/Aero software flights, PVT 13 and 14, were flown on April 15, 2015. The B-52 released both JASSM missiles from high altitude. Both missiles completed their planned missions, destroying their intended targets. Lessons learned from this series of flights will enable us to continue evaluating inverted flight and high altitude employments. Another product verification flight test, PVT 15, was conducted on November 23, 2015 with a JASSM-ER missile employed. The missile included a new Missile Control Unit, Trimble Global Positioning System (GPS) software version 0615, and Universal Armament Interface Missile Operational Flight Program 52.0.06. The missile was released by a B-1 in a degraded GPS environment and appeared to be successful.
During CY 2015, eight successful Weapon System Evaluation Program (WSEP) events were conducted delivering JASSM BL and JASSM-ER from five aircraft platforms. Air Combat Command's (ACC) May 2015 WSEP evaluations of JASSM BL were completed with three missiles. The first missile was employed by B-52 on May 4, 2015 in the presence of
significant degraded GPS environment. The second missile was employed by F-16 on May 11, 2015 in a degraded GPS environment. This missile was loaded with black keys (same GPS crypto as failed missile in 2014 WSEP); F-16 is the only platform capable of loading black keys. The third missile, which was the first lot 10 JASSM BL employed, was released from a B-2 on May 12, 2015. All of the missiles successfully flew their intended route and all appeared nominal. On August 11, 2015, two JASSM-ERs were launched from B-1B aircraft during a WSEP mission. Both missiles appeared to function nominally. This marks the first employment of a JASSM-ER missile in WSEP, ACC's follow-on operational test and evaluation program. Additionally, on August 13, 2015, a JASSM BL missile was launched from an F-15E which also appeared to function normally. The last WSEP missiles launched in CY 2015 were on November 4, 2015. Two JASSM-ERs were successfully employed from B-1B aircraft. Both appeared to function nominally and ended in high-order detonation.
Demonstrated reliability for both variants of JASSM meet or exceed specification; BL at 87% (requirement is 85%) and ER
at 92% (requirement at LRIP Lot 4 is 85%).
BL Material Availability (Am) is 81% (below the 95% requirement); Am decreased from 84.2% in 2015 due to the ACC world- wide inspection on BL missiles from Lots 2-7 in September 2015. 642 missiles were inspected and 137 were determined to be unserviceable. The Am get well plan moved from November 2017 to April 2019. LM has continually met warranty repair commitments of 24 per quarter throughout the year.
ER Am increased from 96.7% to 100% after of the two missiles that failed for the engine heatshield were repaired and are now serviceable.

## Table 9
There are no significant software-related issues with this program at this time.

## Table 10
Threshold Breaches
JASSM Baseline
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
JASSM-ER
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 11
Schedule

## Table 12
JASSM Baseline
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone 0 | Sep 1995 | Sep 1995 | Sep 1995 | Sep 1995
Milestone I | Jun 1996 | Jun 1996 | Jun 1996 | Jun 1996
PDRR Contract Award | Jun 1996 | Jun 1996 | Jun 1996 | Jun 1996
Milestone II | Nov 1998 | Nov 1998 | Nov 1998 | Nov 1998
EMD Contract Award | Nov 1998 | Nov 1998 | Nov 1998 | Nov 1998
LRIP Decision/Contract Award | Jan 2001 | Dec 2001 | Dec 2001 | Dec 2001
Lot II Contract Award | Jan 2002 | Nov 2002 | Nov 2002 | Nov 2002
RAA/B-52 | Sep 2002 | Sep 2003 | Sep 2003 | Sep 2003
Milestone III | Oct 2003 | Apr 2004 | Apr 2004 | Apr 2004
RAA/F-16 | Dec 2003 | Dec 2004 | Dec 2004 | Dec 2004
IOC/F/A-18 E/F | Jun 2009 | N/A | N/A | N/A
Change Explanations
None
Acronyms and Abbreviations
PDRR - Program Definition and Risk Reduction RAA - Required Assets Available

## Table 13
JASSM-ER
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
JASSM-ER MS C | Jan 2007 | Jan 2011 | Jan 2011 | Jan 2011
JASSM-ER LRIP Contract Award | Jan 2011 | Apr 2011 | Apr 2011 | Apr 2011
JASSM-ER AA/B1-B | Dec 2008 | Mar 2014 | Mar 2014 | Mar 2014
JASSM-ER FRP | Dec 2013 | Nov 2014 | Nov 2014 | Nov 2014
Change Explanations
None
Acronyms and Abbreviations
AA - Assets Available MS - Milestone

## Table 14
Performance
JASSM Baseline
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Carrier Operability (KPP)
Compatible with carrier ops | Compatible with carrier ops | Compatible with carrier ops | N/A | None
Interoperability (KPP)
100% of top-level IER | 100% of top-level IER | 100% of top-level IER designated critical | 100% of top-level IER | 100% of top-level IER
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Operational Requirements Document (ORD) dated January 20, 2004
Change Explanations
None
Notes
The Carrier Operability KPP was eliminated when the Department of the Navy withdrew from the JASSM program.
Acronyms and Abbreviations
IER - Information Exchange Requirement ops - operations

## Table 15
JASSM-ER
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Materiel Availability (KPP) (CPD Para 6.1.5)
0.98 | 0.98 | 0.95 | 1 | 0.97
Net-Ready (KPP) (CPD para 6.1.3)
All Ops | All Ops | Joint Critical Ops | All Ops | All Ops
Missile Reliability (KSA) (CPD para 6.2.8)
4th Lot .91 | 4th Lot .91 | IOT&E .80 4th Lot .85 | IOT&E .95 | 4th Lot .91
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Production Document (CPD) dated April 16, 2010, JASSM-ER Annex to the JASSM Operational Requirements Document (ORD) and ORD III dated January 31, 2005, and the ORD 303-95-III dated January 20, 2004
Change Explanations
None
Acronyms and Abbreviations
IOT&E - Initial Operational Test and Evaluation KSA - Key System Attributes
Ops - Operations para - paragraph

## Table 16
Track to Budget
JASSM Baseline
RDT&E
Appn |  |  | BA | PE
Navy |  | 1319 07 |  | 0604312N
|  | Project |  | Name
|  | 2242 |  | Joint Air-to-Surface Standoff Missile | (Shared) | (Sunk)
Air Force |  | 3600 07 |  | 0207325F
|  | Project |  | Name
|  | 674515 |  | Joint Air-to-Surface Standoff Missile | (Shared) | (Sunk)
|  | 675356 |  | JASSM Extended Range (JASSM-ER) | (Shared) | (Sunk)
Procurement
Air Force |  | 3020 04 |  | 0207325F
|  | Line Item |  | Name
|  | 999 |  | Initial Spares
Air Force |  | 3020 02 |  | 0207325F
|  | Line Item |  | Name
Appn |  |  | BA | PE
654515 Joint Air-to-Surface Standoff Missile (Shared) (Sunk) JASSM0 Joint Air-to-Surface Standoff Missile
JASSM-ER
RDT&E
Appn |  |  | BA | PE
Air Force 3600 07 0207325F
Project | Name
674515 Joint Air-to-Surface Standoff Missile (Shared) (Sunk) 675356 JASSM Extended Range (JASSM-ER)
Procurement
Appn |  |  | BA | PE
Air Force 3020 04 0207325F
Line Item | Name
000999 Initial Spares
Air Force 3020 02 0207325F
Line Item | Name
654515 Joint Air-to-Surface Standoff Missile (Shared) (Sunk) JASSM0 Joint Air-to-Surface Standoff Missile

## Table 17
Cost and Funding
Cost Summary - Total Program
Total Acquisition Cost - Total Program
Appropriation | BY 2010 $M |  |  |  | BY 2010 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 1405.8 |  | 1485.1 | -- |  | 1505.6 |  | 1199.8 |  | 1304.5 |  | 1326.7
Procurement | 3648.7 |  | 5157.5 | -- |  | 5213.3 |  | 3756.2 |  | 5954.3 |  | 5937.8
Flyaway | -- |  | -- | -- |  | 4286.8 |  | -- |  | -- |  | 4857.4
Recurring | -- |  | -- | -- |  | 4286.8 |  | -- |  | -- |  | 4857.4
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 926.5 |  | -- |  | -- |  | 1080.4
Other Support | -- |  | -- | -- |  | 923.6 |  | -- |  | -- |  | 1076.7
Initial Spares | -- |  | -- | -- |  | 2.9 |  | -- |  | -- |  | 3.7
MILCON | 31 |  | 0 | -- |  | 0 |  | 25.1 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total | 5085.5 |  | 6642.6 | N/A |  | 6718.9 |  | 4981.1 |  | 7258.8 |  | 7264.5

## Table 18
Cost and Funding
Cost Summary - JASSM Baseline
Total Acquisition Cost - JASSM Baseline
Appropriation | BY 2010 $M | [5 empty] | BY 2010 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 1246.7 |  |  | 1189.7 | 1308.7 |  |  | 1182 |  | 1053.2 |  |  | 1000.8 |  | 992
Procurement | 1612.8 |  |  | 1860.4 | 2046.4 |  |  | 1836.3 |  | 1601.4 |  |  | 1894.7 |  | 1858.4
Flyaway | -- |  |  | -- | -- |  |  | 1387.4 |  | -- |  |  | -- |  | 1401.6
Recurring | -- |  |  | -- | -- |  |  | 1387.4 |  | -- |  |  | -- |  | 1401.6
Non Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support | -- |  |  | -- | -- |  |  | 448.9 |  | -- |  |  | -- |  | 456.8
Other Support | -- |  |  | -- | -- |  |  | 448.5 |  | -- |  |  | -- |  | 456.3
Initial Spares | -- |  |  | -- | -- |  |  | 0.4 |  | -- |  |  | -- |  | 0.5
MILCON | 31 |  |  | 0 | 0 |  |  | 0 |  | 25.1 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 2890.5 |  |  | 3050.1 | N/A |  |  | 3018.3 |  | 2679.7 |  |  | 2895.5 |  | 2850.4
Current APB Cost Estimate Reference
Service Cost Position dated October 10, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Service Cost Position represents the expected value cost for the program. It takes into consideration relevant risks including ordinary levels of external and unforeseen events. It aims to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk.
Total Quantity - JASSM Baseline
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 87 |  |  |  | 87 |  |  |  |  | 87
Procurement |  | 2853 |  |  |  | 2054 |  |  |  |  | 2034
Total |  | 2940 |  |  |  | 2141 |  |  |  |  | 2121

## Table 19
Cost Summary - JASSM-ER
Total Acquisition Cost - JASSM-ER
Appropriation | BY 2010 $M | [5 empty] | BY 2010 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 159.1 |  |  | 295.4 | 324.9 |  |  | 323.6 |  | 146.6 |  |  | 303.7 |  | 334.7
Procurement | 2035.9 |  |  | 3297.1 | 3626.8 |  |  | 3377 |  | 2154.8 |  |  | 4059.6 |  | 4079.4
Flyaway | -- |  |  | -- | -- |  |  | 2899.4 |  | -- |  |  | -- |  | 3455.8
Recurring | -- |  |  | -- | -- |  |  | 2899.4 |  | -- |  |  | -- |  | 3455.8
Non Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support | -- |  |  | -- | -- |  |  | 477.6 |  | -- |  |  | -- |  | 623.6
Other Support | -- |  |  | -- | -- |  |  | 475.1 |  | -- |  |  | -- |  | 620.4
Initial Spares | -- |  |  | -- | -- |  |  | 2.5 |  | -- |  |  | -- |  | 3.2
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 2195 |  |  | 3592.5 | N/A |  |  | 3700.6 |  | 2301.4 |  |  | 4363.3 |  | 4414.1
Current APB Cost Estimate Reference
Service Cost Position dated October 10, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Service Cost Position represents the expected value cost for the program. It takes into consideration relevant risks including ordinary levels of external and unforeseen events. It aims to provide sufficient resources to execute the program under normal conditions encountering average levels of technical, schedule, and programmatic risk.
Cost Notes
M-Code funding totaling $60.8M was added to JASSM’s FY 2017 PB. The M-Code requirement was not included in the current APB. As a result of the additional funding the program is $2.3M under the RDT&E threshold. JASSM is working on new estimates to include M-Code and future updates to the APB.
Total Quantity - JASSM-ER
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 7 |  |  |  | 31 |  |  |  |  | 31
Procurement |  | 2500 |  |  |  | 2846 |  |  |  |  | 2866
Total |  | 2507 |  |  |  | 2877 |  |  |  |  | 2897

## Table 20
Cost and Funding
Funding Summary - Total Program
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | To Complete | Total
RDT&E | 1201.2 | 9.8 | 30 | 20.3 | 26 | 4.5 | 4.6 | 30.3 | 1326.7
Procurement | 2251.4 | 426.4 | 432 | 440.9 | 448.4 | 455.8 | 463.8 | 1019.1 | 5937.8
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2017 Total | 3452.6 | 436.2 | 462 | 461.2 | 474.4 | 460.3 | 468.4 | 1049.4 | 7264.5
PB 2016 Total | 3451.3 | 454.2 | 442.1 | 450 | 457.5 | 465.7 | 464.9 | 1049.3 | 7235
Delta | 1.3 | -18 | 19.9 | 11.2 | 16.9 | -5.4 | 3.5 | 0.1 | 29.5

## Table 21
Cost and Funding
Funding Summary - JASSM Baseline
Appropriation Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 992 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 992
Procurement | 1784.3 | 74.1 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1858.4
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 2776.3 | 74.1 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2850.4
PB 2016 Total | 2731.3 | 74.1 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2805.4
Delta | 45 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 45
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 87 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 87
Production | 0 |  | 1934 |  | 100 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2034
PB 2017 Total | 87 |  | 1934 |  | 100 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2121
PB 2016 Total | 87 |  | 1934 |  | 100 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2121
Delta | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 22
Funding Summary - JASSM-ER
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 209.2 | 9.8 |  |  | 30 | 20.3 | 26 |  | 4.5 |  | 4.6 |  |  | 30.3 |  | 334.7
Procurement | 467.1 | 352.3 |  |  | 432 | 440.9 | 448.4 |  | 455.8 |  | 463.8 |  |  | 1019.1 |  | 4079.4
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 676.3 | 362.1 |  |  | 462 | 461.2 | 474.4 |  | 460.3 |  | 468.4 |  |  | 1049.4 |  | 4414.1
PB 2016 Total | 720 | 380.1 |  |  | 442.1 | 450 | 457.5 |  | 465.7 |  | 464.9 |  |  | 1049.3 |  | 4429.6
Delta | -43.7 | -18 |  |  | 19.9 | 11.2 | 16.9 |  | -5.4 |  | 3.5 |  |  | 0.1 |  | -15.5
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 31 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 31
Production | 0 |  | 300 |  | 240 | 360 | 360 |  | 360 |  | 360 | 360 |  | 526 |  | 2866
PB 2017 Total | 31 |  | 300 |  | 240 | 360 | 360 |  | 360 |  | 360 | 360 |  | 526 |  | 2897
PB 2016 Total | 31 |  | 275 |  | 260 | 360 | 360 |  | 360 |  | 360 | 360 |  | 531 |  | 2897
Delta | 0 |  | 25 |  | -20 | 0 | 0 |  | 0 |  | 0 | 0 |  | -5 |  | 0

## Table 23
Cost and Funding
Annual Funding By Appropriation - JASSM Baseline
Annual Funding - JASSM Baseline 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.3
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.8
Subtotal |  | 6 | -- |  | -- |  | -- |  | -- |  | -- |  | 55.3

## Table 24
Annual Funding - JASSM Baseline 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.5
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.5
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.2
Subtotal |  | 6 | -- |  | -- |  | -- |  | -- |  | -- |  | 63.8

## Table 25
Annual Funding - JASSM Baseline 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.6
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 160.7
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 163.8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 121.7
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 154.4
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 82.8
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.5
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.4
Subtotal |  | 81 | -- |  | -- |  | -- |  | -- |  | -- |  | 936.7

## Table 26
Annual Funding - JASSM Baseline 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.5
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 198.4
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 200.8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 147.8
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 184.6
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 139.7
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 96.6
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.8
Subtotal |  | 81 | -- |  | -- |  | -- |  | -- |  | -- |  | 1118.2

## Table 27
Annual Funding - JASSM Baseline 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | 0.2 |  | -- |  | 0.2 |  | -- |  | 0.2
2002 |  | 76 | 33.6 |  | -- |  | -- |  | 33.6 |  | 9.1 |  | 42.7
2003 |  | 100 | 36.5 |  | -- |  | -- |  | 36.5 |  | 15.5 |  | 52
2004 |  | 240 | 90.2 |  | -- |  | -- |  | 90.2 |  | 10.7 |  | 100.9
2005 |  | 288 | 112.2 |  | -- |  | -- |  | 112.2 |  | 27 |  | 139.2
2006 |  | 75 | 69.9 |  | -- |  | -- |  | 69.9 |  | 28.8 |  | 98.7
2007 |  | 163 | 124.8 |  | -- |  | -- |  | 124.8 |  | 35.9 |  | 160.7
2008 |  | 111 | 103.5 |  | -- |  | -- |  | 103.5 |  | 56.5 |  | 160
2009 |  | 134 | 129 |  | -- |  | -- |  | 129 |  | 51.7 |  | 180.7
2010 |  | 3 | 2.6 |  | -- |  | -- |  | 2.6 |  | 17.2 |  | 19.8
2011 |  | 167 | 146.5 |  | -- |  | -- |  | 146.5 |  | 19.9 |  | 166.4
2012 |  | 174 | 153.6 |  | -- |  | -- |  | 153.6 |  | 24.8 |  | 178.4
2013 |  | 183 | 148.1 |  | -- |  | -- |  | 148.1 |  | 19.3 |  | 167.4
2014 |  | 120 | 100.1 |  | -- |  | -- |  | 100.1 |  | 77.7 |  | 177.8
2015 |  | 100 | 86 |  | -- |  | -- |  | 86 |  | 53.4 |  | 139.4
2016 |  | 100 | 64.8 |  | -- |  | -- |  | 64.8 |  | 9.3 |  | 74.1
Subtotal |  | 2034 | 1401.4 |  | 0.2 |  | -- |  | 1401.6 |  | 456.8 |  | 1858.4

## Table 28
Annual Funding - JASSM Baseline 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | 0.2 |  | -- |  | 0.2 |  | -- |  | 0.2
2002 |  | 76 | 38.7 |  | -- |  | -- |  | 38.7 |  | 10.4 |  | 49.1
2003 |  | 100 | 41.6 |  | -- |  | -- |  | 41.6 |  | 17.6 |  | 59.2
2004 |  | 240 | 100.5 |  | -- |  | -- |  | 100.5 |  | 11.9 |  | 112.4
2005 |  | 288 | 121.4 |  | -- |  | -- |  | 121.4 |  | 29.2 |  | 150.6
2006 |  | 75 | 73.6 |  | -- |  | -- |  | 73.6 |  | 30.3 |  | 103.9
2007 |  | 163 | 128.1 |  | -- |  | -- |  | 128.1 |  | 36.9 |  | 165
2008 |  | 111 | 104.3 |  | -- |  | -- |  | 104.3 |  | 57 |  | 161.3
2009 |  | 134 | 128.3 |  | -- |  | -- |  | 128.3 |  | 51.4 |  | 179.7
2010 |  | 3 | 2.5 |  | -- |  | -- |  | 2.5 |  | 16.9 |  | 19.4
2011 |  | 167 | 140.7 |  | -- |  | -- |  | 140.7 |  | 19.1 |  | 159.8
2012 |  | 174 | 145 |  | -- |  | -- |  | 145 |  | 23.4 |  | 168.4
2013 |  | 183 | 136.7 |  | -- |  | -- |  | 136.7 |  | 17.8 |  | 154.5
2014 |  | 120 | 91.1 |  | -- |  | -- |  | 91.1 |  | 70.8 |  | 161.9
2015 |  | 100 | 77.4 |  | -- |  | -- |  | 77.4 |  | 48 |  | 125.4
2016 |  | 100 | 57.3 |  | -- |  | -- |  | 57.3 |  | 8.2 |  | 65.5
Subtotal |  | 2034 | 1387.2 |  | 0.2 |  | -- |  | 1387.4 |  | 448.9 |  | 1836.3

## Table 29
Annual Funding By Appropriation - JASSM-ER
Annual Funding - JASSM-ER 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.3
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.6
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
Subtotal |  | 31 | -- |  | -- |  | -- |  | -- |  | -- |  | 334.7

## Table 30
Annual Funding - JASSM-ER 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.6
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.8
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.8
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.7
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
Subtotal |  | 31 | -- |  | -- |  | -- |  | -- |  | -- |  | 323.6

## Table 31
Annual Funding - JASSM-ER 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | 30 | 52.4 |  | -- |  | -- |  | 52.4 |  | 4.3 |  | 56.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.8 |  | 1.8
2012 |  | 30 | 52.3 |  | -- |  | -- |  | 52.3 |  | 4.6 |  | 56.9
2013 |  | 40 | 62.1 |  | -- |  | -- |  | 62.1 |  | 6.6 |  | 68.7
2014 |  | 60 | 89.8 |  | -- |  | -- |  | 89.8 |  | 3.5 |  | 93.3
2015 |  | 140 | 174.7 |  | -- |  | -- |  | 174.7 |  | 15 |  | 189.7
2016 |  | 240 | 315.7 |  | -- |  | -- |  | 315.7 |  | 36.6 |  | 352.3
2017 |  | 360 | 394.9 |  | -- |  | -- |  | 394.9 |  | 37.1 |  | 432
2018 |  | 360 | 402.6 |  | -- |  | -- |  | 402.6 |  | 38.3 |  | 440.9
2019 |  | 360 | 409.6 |  | -- |  | -- |  | 409.6 |  | 38.8 |  | 448.4
2020 |  | 360 | 416.3 |  | -- |  | -- |  | 416.3 |  | 39.5 |  | 455.8
2021 |  | 360 | 423.7 |  | -- |  | -- |  | 423.7 |  | 40.1 |  | 463.8
2022 |  | 360 | 420.4 |  | -- |  | -- |  | 420.4 |  | 46.3 |  | 466.7
2023 |  | 166 | 241.3 |  | -- |  | -- |  | 241.3 |  | 47.5 |  | 288.8
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | 18.7 |  | 18.7
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | 19.3 |  | 19.3
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | 19.8 |  | 19.8
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | 20.4 |  | 20.4
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | 21 |  | 21
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | 21.6 |  | 21.6
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | 22.2 |  | 22.2
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | 22.8 |  | 22.8
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | 23.4 |  | 23.4
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | 24.1 |  | 24.1
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | 24.8 |  | 24.8
2035 |  | -- | -- |  | -- |  | -- |  | -- |  | 25.5 |  | 25.5
Subtotal |  | 2866 | 3455.8 |  | -- |  | -- |  | 3455.8 |  | 623.6 |  | 4079.4

## Table 32
Annual Funding - JASSM-ER 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | 30 | 51.3 |  | -- |  | -- |  | 51.3 |  | 4.2 |  | 55.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.7 |  | 1.7
2012 |  | 30 | 49.4 |  | -- |  | -- |  | 49.4 |  | 4.3 |  | 53.7
2013 |  | 40 | 57.3 |  | -- |  | -- |  | 57.3 |  | 6.1 |  | 63.4
2014 |  | 60 | 81.8 |  | -- |  | -- |  | 81.8 |  | 3.1 |  | 84.9
2015 |  | 140 | 157.2 |  | -- |  | -- |  | 157.2 |  | 13.5 |  | 170.7
2016 |  | 240 | 279 |  | -- |  | -- |  | 279 |  | 32.4 |  | 311.4
2017 |  | 360 | 342.6 |  | -- |  | -- |  | 342.6 |  | 32.1 |  | 374.7
2018 |  | 360 | 342.6 |  | -- |  | -- |  | 342.6 |  | 32.6 |  | 375.2
2019 |  | 360 | 341.7 |  | -- |  | -- |  | 341.7 |  | 32.3 |  | 374
2020 |  | 360 | 340.5 |  | -- |  | -- |  | 340.5 |  | 32.3 |  | 372.8
2021 |  | 360 | 339.6 |  | -- |  | -- |  | 339.6 |  | 32.2 |  | 371.8
2022 |  | 360 | 330.4 |  | -- |  | -- |  | 330.4 |  | 36.3 |  | 366.7
2023 |  | 166 | 186 |  | -- |  | -- |  | 186 |  | 36.6 |  | 222.6
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | 14.1 |  | 14.1
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | 14.3 |  | 14.3
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | 14.4 |  | 14.4
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | 14.5 |  | 14.5
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | 14.7 |  | 14.7
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | 14.8 |  | 14.8
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | 14.9 |  | 14.9
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | 15 |  | 15
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | 15.1 |  | 15.1
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | 15.2 |  | 15.2
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | 15.4 |  | 15.4
2035 |  | -- | -- |  | -- |  | -- |  | -- |  | 15.5 |  | 15.5
Subtotal |  | 2866 | 2899.4 |  | -- |  | -- |  | 2899.4 |  | 477.6 |  | 3377

## Table 33
Low Rate Initial Production
JASSM Baseline
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2001-12-21 | 2003-12-21
Approved Quantity | 176 | 416
Reference | Milestone III ADM | FY 2004 Congressional Add
Start Year | 2001 | 2001
End Year | 2003 | 2003
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the MDA signing an ADM authorizing entry into LRIP on December 21, 2001. The December 2001 LRIP ADM approved the procurement of 76 missiles in Lot 1 and 100 missiles in Lot 2. In the summer of 2003, Congressional language for the FY 2004 budget dictated that the JASSM program remain in LRIP for Lot 3, which added an additional 240 missiles (increasing the total LRIP quantity from 176 to 416, which equates to 17 percent of expected total procurement).
JASSM-ER
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2011-01-10 | 2011-01-10
Approved Quantity | 100 | 160
Reference | Milestone C ADM | Milestone C ADM
Start Year | 2011 | 2011
End Year | 2013 | 2014
The January 10, 2011 ADM approved LRIP of 100 to 190 JASSM-ER missiles. JASSM-ER's current LRIP estimate has shifted to 160 missiles.

## Table 34
Foreign Military Sales
JASSM Baseline
Classified FMS information is provided in the classified annex to this submission.
JASSM-ER
None
Nuclear Costs
JASSM Baseline
None
JASSM-ER
None

## Table 35
Unit Cost
JASSM Baseline
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Current UCR Baseline (Mar 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3050.1 |  |  | 3018.3
Quantity | 2141 |  |  | 2121
Unit Cost | 1.425 |  |  | 1.423 |  |  | -0.14
Average Procurement Unit Cost
Cost | 1860.4 |  |  | 1836.3
Quantity | 2054 |  |  | 2034
Unit Cost | 0.906 |  |  | 0.903 |  |  | -0.33
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Apr 2011 APB)
Program Acquisition Unit Cost
Cost | 3679.4 |  |  | 3018.3
Quantity | 2487 |  |  | 2121
Unit Cost | 1.479 |  |  | 1.423 |  | -3.79
Average Procurement Unit Cost
Cost | 2503.2 |  |  | 1836.3
Quantity | 2400 |  |  | 2034
Unit Cost | 1.043 |  |  | 0.903 |  | -13.42

## Table 36
JASSM Baseline
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2010 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Nov 1998 |  |  |  |  | 0.914 |  |  | 0.516 |  |  | 0.84 |  |  | 0.504
APB as of January 2006 |  |  | Jul 2004 |  |  |  |  | 0.951 |  |  | 0.699 |  |  | 0.914 |  |  | 0.702
Revised Original APB |  |  | Apr 2011 |  |  |  |  | 1.479 |  |  | 1.043 |  |  | 1.468 |  |  | 1.11
Prior APB |  |  | Apr 2011 |  |  |  |  | 1.479 |  |  | 1.043 |  |  | 1.468 |  |  | 1.11
Current APB |  |  | Mar 2015 |  |  |  |  | 1.425 |  |  | 0.906 |  |  | 1.352 |  |  | 0.922
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 1.402 |  |  | 0.88 |  |  | 1.323 |  |  | 0.89
Current Estimate |  |  | Dec 2015 |  |  |  |  | 1.423 |  |  | 0.903 |  |  | 1.344 |  |  | 0.914
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
0.911 0.031 0.067 0.179 0.065 -0.087 0.000 0.178 0.433 1.344

## Table 37
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [9 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt | Total
0.561 0.029 -0.071 0.186 0.068 -0.045 0.000 0.186 0.353 0.914
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  | Jun 1996 |  |  | Jun 1996 |  |  | Jun 1996 |  |  | Jun 1996
Milestone II |  |  | Jun 1998 |  |  | Nov 1998 |  |  | Nov 1998 |  |  | Nov 1998
Milestone III |  |  | Apr 2001 |  |  | Jul 2002 |  |  | Oct 2003 |  |  | Apr 2004
IOC |  |  | Jun 2001 |  |  | Sep 2002 |  |  | Sep 2002 |  |  | Sep 2003
Total Cost (TY $M) |  |  | 811.3 |  |  | 2073.3 |  |  | 2679.7 |  |  | 2850.4
Total Quantity |  |  | 44 |  |  | 2469 |  |  | 2940 |  |  | 2121
PAUC |  |  | 18.439 |  |  | 0.84 |  |  | 0.911 |  |  | 1.344
In the chart above, IOC represents Required Assets Available (RAA) for B-52 at Barksdale Air Force Base. RAA was achieved on September 24, 2003.

## Table 38
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Current UCR Baseline (Mar 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3592.5 |  |  | 3700.6
Quantity | 2877 |  |  | 2897
Unit Cost | 1.249 |  |  | 1.277 |  | 2.24
Average Procurement Unit Cost
Cost | 3297.1 |  |  | 3377
Quantity | 2846 |  |  | 2866
Unit Cost | 1.159 |  |  | 1.178 |  | 1.64
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Original UCR Baseline (Apr 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3631.6 |  |  | 3700.6
Quantity | 2531 |  |  | 2897
Unit Cost | 1.435 |  |  | 1.277 |  | -11.01
Average Procurement Unit Cost
Cost | 3366.1 |  |  | 3377
Quantity | 2500 |  |  | 2866
Unit Cost | 1.346 |  |  | 1.178 |  | -12.48

## Table 39
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2010 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Apr 2011 |  |  |  |  | 1.435 |  |  | 1.346 |  |  | 1.733 |  |  | 1.648
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Apr 2011 |  |  |  |  | 1.435 |  |  | 1.346 |  |  | 1.733 |  |  | 1.648
Current APB |  |  | Mar 2015 |  |  |  |  | 1.249 |  |  | 1.159 |  |  | 1.517 |  |  | 1.426
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 1.274 |  |  | 1.192 |  |  | 1.529 |  |  | 1.448
Current Estimate |  |  | Dec 2015 |  |  |  |  | 1.277 |  |  | 1.178 |  |  | 1.524 |  |  | 1.423
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
0.918 0.031 0.022 -0.066 0.127 0.301 0.000 0.191 0.606 1.524

## Table 40
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [9 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt | Total
0.862 0.030 0.015 -0.058 0.102 0.279 0.000 0.193 0.561 1.423
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  | N/A |  |  | Jan 2007 |  |  | Jan 2011
IOC |  |  | N/A |  |  | N/A |  |  | Dec 2008 |  |  | Mar 2014
Total Cost (TY $M) |  |  | N/A |  |  | N/A |  |  | 2301.4 |  |  | 4414.1
Total Quantity |  |  | N/A |  |  | N/A |  |  | 2507 |  |  | 2897
PAUC |  |  | N/A |  |  | N/A |  |  | 0.918 |  |  | 1.524
In the chart abve, IOC represents Required Assets Available (RAA) for B-1B Dyess Air Force Base. RAA achieved was on March 21, 2014.

## Table 41
Cost Variance
JASSM Baseline
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1053.2 | 1601.4 | 25.1 | 2679.7
Previous Changes
Economic | 7.7 | 62.1 | -- | 69.8
Quantity | -- | -605.6 | -- | -605.6
Schedule | -- | 378.7 | -- | 378.7
Engineering | -- | 137.8 | -- | 137.8
Estimating | -66 | -73.6 | -25.1 | -164.7
Other | -- | -- | -- | --
Support | -- | 309.7 | -- | 309.7
Subtotal | -58.3 | 209.1 | -25.1 | 125.7
Current Changes
Economic | -0.3 | -3.7 | -- | -4
Quantity | -- | -- | -- | --
Schedule | -- | -0.1 | -- | -0.1
Engineering | -- | -- | -- | --
Estimating | -2.6 | -17.1 | -- | -19.7
Other | -- | -- | -- | --
Support | -- | 68.8 | -- | 68.8
Subtotal | -2.9 | 47.9 | -- | 45
Total Changes | -61.2 | 257 | -25.1 | 170.7
CE - Cost Variance | 992 | 1858.4 | -- | 2850.4
CE - Cost & Funding | 992 | 1858.4 | -- | 2850.4

## Table 42
Summary BY 2010 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1246.7 | 1612.8 | 31 | 2890.5
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -455.9 | -- | -455.9
Schedule | -- | -93.3 | -- | -93.3
Engineering | -- | 88.7 | -- | 88.7
Estimating | -62.3 | 326.3 | -31 | 233
Other | -- | -- | -- | --
Support | -- | 310.7 | -- | 310.7
Subtotal | -62.3 | 176.5 | -31 | 83.2
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -2.4 | -15.5 | -- | -17.9
Other | -- | -- | -- | --
Support | -- | 62.5 | -- | 62.5
Subtotal | -2.4 | 47 | -- | 44.6
Total Changes | -64.7 | 223.5 | -31 | 127.8
CE - Cost Variance | 1182 | 1836.3 | -- | 3018.3
CE - Cost & Funding | 1182 | 1836.3 | -- | 3018.3
Previous Estimate: December 2014

## Table 43
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.3
Adjustment for current and prior escalation. (Estimating) | 0.3 | 0.3
Reduction due to Air Force higher priorities in FY 2014. (Estimating) | -2.7 | -2.9
RDT&E Subtotal | -2.4 | -2.9
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -3.7
Adjustment for current and prior escalation. (Estimating) +2.5 +2.9
Acceleration of procurement buy profile between FY 2013 and FY 2014 resulted in the realignment of missiles. (Schedule)
Revised estimate to reflect the additional funds needed to support the test support and program tooling requirements (FY 2013-FY 2015). (Estimating)
0.0 -0.1
-18.0 -20.0
Adjustment for current and prior escalation. (Support) +0.9 +0.8
Increase in Other Support to realign cost between subprograms to support Lot 14 Factory Tooling and Test Equipment (FY 2014-FY 2015). (Support)
+61.6 +68.0
Procurement Subtotal +47.0 +47.9

## Table 44
Cost Variance
JASSM-ER
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
146.6 2154.8 -- 2301.4
Economic |  | 2.5 |  | 116.2 |  | -- |  | 118.7
Quantity |  | 64.9 |  | 356.8 |  | -- |  | 421.7
Schedule |  | -25.8 |  | -164.7 |  | -- |  | -190.5
Engineering |  | 14.7 |  | 292.5 |  | -- |  | 307.2
Estimating |  | 77.1 |  | 762.8 |  | -- |  | 839.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 631.2 |  | -- |  | 631.2
Subtotal |  | 133.4 |  | 1994.8 |  | -- |  | 2128.2
Current Changes Economic |  | -0.4 |  | -28.9 |  | -- |  | -29.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -1.2 |  | -- |  | -1.2
Engineering |  | 60.7 |  | -- |  | -- |  | 60.7
Estimating |  | -5.6 |  | 38 |  | -- |  | 32.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -78.1 |  | -- |  | -78.1
Subtotal |  | 54.7 |  | -70.2 |  | -- |  | -15.5
Total Changes |  | 188.1 |  | 1924.6 |  | -- |  | 2112.7
CE - Cost Variance |  | 334.7 |  | 4079.4 |  | -- |  | 4414.1
CE - Cost & Funding |  | 334.7 |  | 4079.4 |  | -- |  | 4414.1

## Table 45
Summary BY 2010 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
159.1 2035.9 -- 2195.0
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | 50.4 |  | 272 |  | -- |  | 322.4
Schedule |  | -7.2 |  | -6.7 |  | -- |  | -13.9
Engineering |  | 10.8 |  | 200.3 |  | -- |  | 211.1
Estimating |  | 62.5 |  | 429.6 |  | -- |  | 492.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 484.9 |  | -- |  | 484.9
Subtotal |  | 116.5 |  | 1380.1 |  | -- |  | 1496.6
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 53 |  | -- |  | -- |  | 53
Estimating |  | -5 |  | 31 |  | -- |  | 26
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -70 |  | -- |  | -70
Subtotal |  | 48 |  | -39 |  | -- |  | 9
Total Changes |  | 164.5 |  | 1341.1 |  | -- |  | 1505.6
CE - Cost Variance |  | 323.6 |  | 3377 |  | -- |  | 3700.6
CE - Cost & Funding |  | 323.6 |  | 3377 |  | -- |  | 3700.6
Previous Estimate: December 2014

## Table 46
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.4
Adjustment for current and prior escalation. (Estimating) | 0.2 | 0.2
Revised estimate to reflect latest actuals. (Estimating) | -1 | -1.3
Reduction due to Air Force higher priorities in FY 2014. (Estimating) | -1 | -1
Congressional reduction in FY 2016 which drove new estimate and extended scheduled | -2.8 | -3
events into FY 2017. (Estimating)
Reduction for Small Business Innovation Research in FY 2015. (Estimating) | -0.4 | -0.5
Additional funding received between FY 2017-2019 for M-Code requirements. (Engineering) | 53 | 60.7
RDT&E Subtotal | 48 | 54.7
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -28.9
Adjustment for current and prior escalation. (Estimating) +3.7 +4.1
Acceleration of procurement buy profile in FY 2015; Lot 13 negotiations yielded an additional 25 missiles. (Schedule)
0.0 -1.2
Congressional reduction in FY 2016. (Estimating) -13.3 -15.0
Revised estimate to reflect actuals. (Estimating) +40.6 +48.9
Adjustment for current and prior escalation. (Support) +0.6 +0.7
Decrease in Other Support to realign cost between subprograms to support Lot 14 Factory Tooling, Test Equipment (FY 2014-FY 2015), and reduction for Air Force higher priorities (FY 2017-FY 2021). (Support)
-70.6 -78.8
Procurement Subtotal -39.0 -70.2

## Table 47
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: JASSM Production (Lot 11 Baseline/LRIP Lot 3 ER)
Contractor: Lockheed Martin--Missile & Fire Control
Contractor Location: 5600 West Sand Lake Road
Orlando, FL 32819
Contract Number: FA8682-14-C-0069
Contract Type: Firm Fixed Price (FFP)
Award Date: December 19, 2013
Definitization Date: December 19, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
225.8 N/A 230 263.1 N/A 230 263.1 263.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the following contract modifications: Fuze Highly Accelerated Stress Screening Chamber Repair, F-15 Universal Armament Interface Capability, Radio Frequency Switch Last Time Buy, Value Engineering Change Proposal Lube Pump, Telemetry Instrumentation Kit Conversion JASSM BL to JASSM-ER, Service Life Extension Program, and JASSM-ER Weapon System Evaluation Program 2015.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
Funding identified here only represents production funding placed on contract to support 230 missiles;190 JASSM BL and 40 JASSM-ER missiles.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 48
Contract Identification
Appropriation: Procurement
Contract Name: JASSM Production (Lot 12 Baseline/LRIP Lot 4 ER)
Contractor: Lockheed Martin--Missile & Fire Control
Contractor Location: 5600 West Sand Lake Road
Orlando, FL 32819
Contract Number: FA8682-14-C-0084
Contract Type: Firm Fixed Price (FFP)
Award Date: December 19, 2013
Definitization Date: December 19, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
214.8 N/A 210 228.0 N/A 210 228.0 228.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the following contract modifications: Actuator Control Card, Lots 12 and 4 Systems Engineering Program Support/Program Tooling and Test Equipment, and JASSM-ER Standard Data Protocol (DS 101) Value Engineering Change Proposal.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
The funding identified here only represents production funding placed on contract to support 210 missiles; 150 JASSM BL and 60 JASSM-ER missiles.

## Table 49
Contract Identification
Appropriation: Procurement
Contract Name: JASSM Production (Lot 13)
Contractor: Lockheed Martin Corporation Missile and Fire Control
Contractor Location: 5600 W. Sand Lake Road
Orlando, FL 32819-8907
Contract Number: FA8682-16-C-0005/13
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: October 09, 2015
Definitization Date: October 09, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
263.3 N/A 240 263.3 N/A 240 263.3 263.3
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
Notes
This is the first time this contract is being reported.
The funding identified here only represents production funding placed on contract to support 240 missiles; 100 BL and 140 ER missiles.

## Table 50
Contract Identification
Appropriation: Procurement
Contract Name: JASSM Production (Lot 14)
Contractor: Lockheed Martin Corporation Fire and Missile Control
Contractor Location: 5600 West Sand Lake Road
Orlando, FL 32819
Contract Number: FA8682-16-C-0005/14
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 01, 2015
Definitization Date: December 01, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
371.0 N/A 340 388.4 N/A 340 388.4 388.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of contract mod P00004 for $17.4M.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
Notes
This is the first time this contract is being reported.
Lot 14 total quantity of 340 is comprised of 100 BL and 240 ER missiles.

## Table 51
Deliveries and Expenditures
JASSM Baseline
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 87 | 87 | 87 | 100%
Production | 1494 | 1681 | 2034 | 82.65%
Total Program Quantity Delivered | 1581 | 1768 | 2121 | 83.36%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2850.4
2565.3
90%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
21
100%
2850.4
100%
The above data is current as of March 03, 2016.
Production deliveries (DD Form 250) for Lots 1-10 total 1,494. The total of Lot 11 deliveries to-date are 183 missiles, and the total for Lot 12 is four missiles. The total JASSM BL missiles delivered to-date are 1,681.
JASSM-ER
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 31 | 31 | 31 | 100%
Production | 60 | 100 | 2866 | 3.49%
Total Program Quantity Delivered | 91 | 131 | 2897 | 4.52%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
4414.1
446.5
10.12%
33
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
14
42.42%
1038.4
23.52%
The above data is current as of March 03, 2016.
Production deliveries (DD Form 250) to-date for Lot 9/ER LRIP 1 through Lot 11/ER LRIP 3 total 100 JASSM-ER missiles.

## Table 52
Operating and Support Cost
JASSM Baseline
Cost Estimate Details
Date of Estimate: October 10, 2014
Source of Estimate: SCP
Quantity to Sustain: 2054
Unit of Measure: Total Quantity
Service Life per Unit: 15.00 Years
Fiscal Years in Service: FY 2003 - FY 2032
RDT&E quantities are not counted towards JASSM sustainment efforts. Additionally, during FY 2016 PB reviews in December 2014, the JASSM Baseline quantity profile changed from 2,054 to 2,034. The O&S estimate will be updated in the next SAR to reflect this change.
Sustainment Strategy
The sustainment and readiness plan/estimate for JASSM has evolved to a combination of 15-year Warranty and Contractor Logistics Support (CLS). Lots 1-10 will continue to be supported under a Warranty construct, while Lots 11-14 will be aligned under a CLS logisitics strategy.
JASSM Baseline and JASSM-ER are wooden rounds, meaning there is no routine maintenance required. Also, because production quantities have varied from lot-to-lot and assets continue to be expended during testing, an average unit cost is not a good indicator of operating and sustainment. For those reasons, total O&S costs are reported.
Antecedent Information
No Antecedent
Annual O&S Costs BY2010 $M
Cost Element | JASSM Baseline Average Annual Cost Per Total Quantity | No Antecedent (Antecedent) No Antecedent
Unit-Level Manpower | 1.655 | 0
Unit Operations | 0 | 0
Maintenance | 0.556 | 0
Sustaining Support | 5.479 | 0
Continuing System Improvements | 3.319 | 0
Indirect Support | 1.511 | 0
Other | 0 | 0
Total | 12.52 | --

## Table 53
Item | Total O&S Cost $M
| JASSM Baseline | [5 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 375.6 |  | 413.2 |  |  | 375.6 | N/A
Then Year | 428.6 |  | N/A |  |  | 428.6 | N/A
Equation to Translate Annual Cost to Total Cost
Total O&S Cost = service life * average annual cost = 30 * $12.520M = $375.600M
O&S Cost Variance
Category |  | BY 2010 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
375.6
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 375.6
Disposal Estimate Details
Date of Estimate: October 10, 2014
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2010 $M): Total costs for disposal of all Total Quantity are 45.4

## Table 54
JASSM-ER
Cost Estimate Details
Date of Estimate: October 10, 2014
Source of Estimate: SCP
Quantity to Sustain: 2846
Unit of Measure: Total Quantity
Service Life per Unit: 15.00 Years
Fiscal Years in Service: FY 2013 - FY 2040
RDT&E quantities are not counted towards JASSM sustainment efforts. Additionally, during FY 2016 PB reviews in December 2014, the JASSM Baseline quantity profile changed from 2,054 to 2,034. The O&S estimate will be updated in the next SAR to reflect this change.
Sustainment Strategy
The sustainment and readiness plan/estimate for JASSM has evolved to a combination of 15-year Warranty and Contractor Logistics Support (CLS). Lots 1-10 will continue to be supported under a Warranty construct, while Lots 11-14 will be aligned under a CLS logistics strategy.
JASSM Baseline and JASSM-ER are wooden rounds, meaning there is no routine maintenance required. Also, because production quantities have varied from lot-to-lot and assets continue to be expended during testing, an average unit cost is not a good indicator of operating and sustainment. For those reasons, total O&S costs are reported.
Antecedent Information
No Antecedent
Annual O&S Costs BY2010 $M
Cost Element | JASSM-ER Average Annual Cost Per Total Quantity | No Antecedent (Antecedent) No Antecedent
Unit-Level Manpower | 3.117 | 0
Unit Operations | 0 | 0
Maintenance | 2.328 | 0
Sustaining Support | 9.472 | 0
Continuing System Improvements | 5.403 | 0
Indirect Support | 1.912 | 0
Other | 0 | 0
Total | 22.232 | --

## Table 55
Item | Total O&S Cost $M
| JASSM-ER | [5 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 622.5 |  | 684.8 |  |  | 622.5 | N/A
Then Year | 908.6 |  | N/A |  |  | 908.6 | N/A
Equation to Translate Annual Cost to Total Cost
Total O&S Cost = service life * average annual cost = 28 * $22.232M = $622.500M
O&S Cost Variance
Category |  | BY 2010 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
622.5
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 622.5
Disposal Estimate Details
Date of Estimate: October 10, 2014
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2010 $M): Total costs for disposal of all Total Quantity are 64.3