## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-438
Space Fence Ground-Based Radar System Increment 1 (Space Fence Inc 1)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 17
Cost and Funding 18
Low Rate Initial Production 23
Foreign Military Sales 24
Nuclear Costs 24
Unit Cost 25
Cost Variance 28
Contracts 31
Deliveries and Expenditures 32
Operating and Support Cost 33

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Space Fence Ground-Based Radar System Increment 1 (Space Fence Inc 1)
DoD Component
Air Force
Responsible Office
Mr. Dana Whalley
11 Barksdale Street Bldg 1614 Hanscom Air Force Base, MA 01731
dana.whalley@us.af.mil
Phone: 781-225-0377
Fax: 781-225-0318
DSN Phone: 845-0377
DSN Fax:
Date Assigned: April 3, 2013
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 18, 2014
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated June 18, 2014

## Table 6
Mission and Description
The Space Fence Ground-Based Radar System (Space Fence) replaces the mission of the Air Force Space Surveillance System (AFSSS) Very High Frequency (VHF) "fence" radar that performed detection of orbiting space objects before decommissioning in FY 2013. The Space Fence mission is to improve Space Situational Awareness by fielding a capability to detect and report small objects in Low Earth Orbit/Medium Earth Orbit (LEO/MEO). The system, comprising one operations center and two radar sites operating at S-band frequencies, will have a modern, net-centric architecture. Fielded capabilities will include uncued capability to find, fix and track small objects in LEO/MEO; improved completeness and accuracy of the space catalog; improved timeliness of orbital event information; and support for improved characterization of space objects.
The Space Fence Ground-Based Radar System Increment 1 (Space Fence Inc 1) includes the operations center, located at the Reagan Test Site Operations Center Huntsville, AL, and one radar site, located at Kwajalein Atoll, Republic of the Marshall Islands.

## Table 7
Executive Summary
The Space Fence Increment 1 program includes development of the first radar site located at Kwajalein Atoll, Republic of the Marshall Islands, and associated operations center functionality to be deployed at the Reagan Test Site Operations Center in Huntsville, Alabama.
After satisfying the required entrance criteria with the Design Walk-Through and 95% Facilities Design Technical Interchange Meeting (TIM) in February 2015, Lockheed Martin conducted multiple Critical Design Review (CDR) events that began in March 2015 and concluded with the 100% Facilities Design TIM in May 2015. Notification of successful CDR completion was issued June 8, 2015, within the APB threshold of October 2015.
The program received a funding cut of $2.5M in FY 2016 as a result of the FY 2016 DoD Appropriations Act, December 2015.
Radar site construction broke ground on Kwajalein Atoll in February 2015. While completing radar site preparation and excavation, multiple differing site conditions were encountered to include underground utilities, contaminated soil, unusable laydown areas, and soil liquefaction. Addressing these conditions delayed planned efforts and resulted in Lockheed
Martin requests for equitable adjustment (REAs) totaling $15.4M thus far. The potential for additional REAs remains until all underground trenching work is completed in the second quarter of FY 2016. Construction efforts have
proceeded, recovering a significant portion of the delays caused by differing site conditions. At this time all array foundations have been poured and vertical construction has commenced.
Construction of the Integration Test Bed (ITB), a larger radar prototype relative to the CDR prototype that incorporates end- item hardware and software, is nearing completion and will be operational by March 2016 to serve as a platform for risk mitigation and testing.
Production Readiness Reviews (PRRs) were conducted from June through December 2015 in conjunction with transmit and receive Line Replaceable Unit (LRU) manufacturing activities to support achievement of the ramp-up required for
IOC system production. Proof of Design and Manufacturing LRU production was completed and an initial build of forty LRUs were installed in the CDR prototype. A build of 196 LRUs for installation in the Integration Test Bed was completed in January 2016.
The Space Fence and the Joint Space Operations Center Mission System programs signed an Interface Control Document in April 2015. The initial agreement established mutually agreed interface development requirements and planning parameters between the two systems so as to reduce uncertainty and risk. It continues to undergo refinement as part
of efforts to ensure alignment of the two development programs for synchronization of testing and integration.
Software Build 2 was completed in September 2015 and Build 3 is in progress.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone A | Mar 2009 | Mar 2009 | Mar 2009 | Mar 2009
Technology Development - Phase A - SDR Contract Award | Jun 2009 | Jun 2009 | Jun 2009 | Jun 2009
Technology Development - Phase A - PDR Contract Award | Jan 2011 | Jan 2011 | Jan 2011 | Jan 2011
PDR | Feb 2012 | Feb 2012 | Feb 2012 | Feb 2012
Milestone B - Increment 1 | May 2014 | May 2014 | Nov 2014 | May 2014
CDR | Apr 2015 | Apr 2015 | Oct 2015 | Jun 2015
IOT&E Start | Oct 2018 | Oct 2018 | Apr 2019 | Jun 2018
RAA | Jul 2019 | Jul 2019 | Jan 2020 | Oct 2018
Change Explanations
(Ch-1) CDR current estimate changed from March 2015 to June 2015 to reflect the actual date of completion.
Notes
RAA is defined as the date when the PM has provided sufficient equipment and logistics resources to support IOC determination. The RAA objective date assumes the EMD contract award in June 2014, and consists of:
- DD250 of at least one radar sensor and SOC
- Ensuring communications links and connectivity to the Global Information Grid are in compliance with then-existing Net- Centric Enterprise Services standards, guidance and direction
- Initial spares for one radar sensor and SOC

## Table 10
- Common and peculiar support equipment
- Interim contractor support established
- Stand-alone training systems and resources at Initial Qualification Training and Upgrade Qualification Training locations
For this SAR, RAA is being used as a surrogate for IOC.
Acronyms and Abbreviations
CDR - Critical Design Review
IOT&E - Initial Operational Test & Evaluation PDR - Preliminary Design Review
RAA - Required Assets Available SDR - System Design Review
SOC - Space Fence Operations Center

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
System Training
Using the ISD process, | Using the ISD process, | (Threshold = Objective) | TBD | Using the ISD process,
the Space Fence shall | the Space Fence shall | Using the ISD process, |  | the Space Fence shall
deliver a training system | deliver a training | the Space Fence shall |  | deliver a training
to applicable AFSPC | system to applicable | deliver a training |  | system to applicable
and AETC units (TBD), | AFSPC and AETC | system to applicable |  | AFSPC and AETC
that will enable units to | units (TBD), that will | AFSPC and AETC |  | units (TBD), that will
possess and maintain a | enable units to | units (TBD), that will |  | enable units to
SORTS readiness | possess and maintain | enable units to |  | possess and maintain
Category Level rating of | a SORTS readiness | possess and maintain |  | a SORTS readiness
C-1 prior to operational | Category Level rating | a SORTS readiness |  | Category Level rating
acceptance. The training | of C-1 prior to | Category Level rating of |  | of C-1 prior to
system shall include | operational | C-1 prior to operational |  | operational
Contract Special | acceptance. The | acceptance. The |  | acceptance. The
Training (Type 1) that | training system shall | training system shall |  | training system shall
provides the requisite | include Contract | include Contract |  | include Contract
competen-cies training | Special Training (Type | Special Training (Type |  | Special Training (Type
to test agency | 1) that provides the | 1) that provides the |  | 1) that provides the
personnel, initial AFSPC | requisite competen- | requisite competen- |  | requisite competen-
cadre and AETC | cies training to test | cies training to test |  | cies training to test
instructors to proficiency | agency personnel, | agency personnel, |  | agency personnel,
standards IAW AFI36- | initial AFSPC cadre | initial AFSPC cadre |  | initial AFSPC cadre
2201 (Ref 46). Before | and AETC instructors | and AETC instructors |  | and AETC instructors
the start of Type 1 | to proficiency | to proficiency |  | to proficiency
training, TOs must | standards IAW AFI36- | standards IAW AFI36- |  | standards IAW AFI36-
complete the | 2201 (Ref 46). Before | 2201 (Ref 46). Before |  | 2201 (Ref 46). Before
contractor's TO | the start of Type 1 | the start of Type 1 |  | the start of Type 1
certification process. | training, TOs must | training, TOs must |  | training, TOs must
Type 1 training shall be | complete the | complete the |  | complete the
conducted prior to start | contractor's TO | contractor's TO |  | contractor's TO
of Operational Test & | certification process. | certification process. |  | certification process.
Evaluation, but no earlier | Type 1 training shall be | Type 1 training shall be |  | Type 1 training shall be
than 12 months and not | conducted prior to start | conducted prior to start |  | conducted prior to start
later than 6 months prior | of Operational Test & | of Operational Test & |  | of Operational Test &
to operational | Evaluation, but no | Evaluation, but no |  | Evaluation, but no
acceptance of the | earlier than 12 months | earlier than 12 months |  | earlier than 12 months
weapon system. Type 1 | and not later than 6 | and not later than 6 |  | and not later than 6
training course(s) shall | months prior to | months prior to |  | months prior to
be tailored to meet the | operational acceptance | operational acceptance |  | operational acceptance
learning objectives of | of the weapon system. | of the weapon system. |  | of the weapon system.
each duty position using | Type 1 training course | Type 1 training course |  | Type 1 training course
the most cost-efficient | (s) shall be tailored to | (s) shall be tailored to |  | (s) shall be tailored to
training media, as | meet the learning | meet the learning |  | meet the learning
determined by the AF | objectives of each duty | objectives of each duty |  | objectives of each duty
ISD process. For CMR | position using the most | position using the most |  | position using the most

## Table 12
operations training and evaluation: The Space Fence shall deliver off- line training simulation capability with fidelity that emulates typical operations, which shall: Be physically and electronically separated from the operational system. Have software application(s) which utilize and integrate with the government- furnished SST software. Look, sound and feel like the actual operational equipment to support required proficiency levels. Be capable of being upgraded as operational functionality is upgraded. The Space Fence shall deliver the associated COTS- based hardware to applicable AFSPC and AETC units (TBD), that will: Fulfill the hardware compatibility requirements of the SST software. Fulfill the security accreditation requirements of the training simulation software. The Space Fence shall collaborate with the SST software vendor to integrate the simulation software with the COTS-based hardware and the government-furnished SST software. The Space Fence shall provide operations procedures and Type 1 training on the use of the integrated SST -based simulation capability to AETC instructors and AFSPC cadre. The integrated SST-based training simulation
cost-efficient training media, as determined by the AF ISD process. For CMR operations training and evaluation: The Space Fence shall deliver off-line training simulation capability with fidelity that emulates typical operations, which shall: Be physically and electronically separated from the operational system.
Have software application(s) which utilize and integrate with the government- furnished SST software. Look, sound and feel like the actual operational equipment to support required proficiency levels. Be capable of being upgraded as operational functionality is upgraded. The Space Fence shall deliver the associated COTS-based hardware to applicable AFSPC and AETC units (TBD), that will: Fulfill the hardware compatibility requirements of the SST software. Fulfill the security accreditation requirements of the training simulation software. The Space Fence shall collaborate with the SST software vendor to integrate the simulation software with the COTS-based hardware and the government-furnished SST software. The Space Fence shall provide operations procedures and Type 1
cost-efficient training media, as determined by the AF ISD process. For CMR operations training and evaluation: The Space Fence shall deliver off-line training simulation capability with fidelity that emulates typical operations, which shall: Be physically and electronically separated from the operational system. Have software application(s) which utilize and integrate with the government- furnished SST software. Look, sound and feel like the actual operational equipment to support required proficiency levels. Be capable of being upgraded as operational functionality is upgraded. The Space Fence shall deliver the associated COTS-based hardware to applicable AFSPC and AETC units (TBD), that will: Fulfill the hardware compatibility requirements of the SST software. Fulfill the security accreditation requirements of the training simulation software. The Space Fence shall collaborate with the SST software vendor to integrate the simulation software with the COTS-based hardware and the government-furnished SST software. The Space Fence shall provide operations procedures and Type 1 training on the use of
cost-efficient training media, as determined by the AF ISD process. For CMR operations training and evaluation: The Space Fence shall deliver off-line training simulation capability with fidelity that emulates typical operations, which shall: Be physically and electronically separated from the operational system.
Have software application(s) which utilize and integrate with the government- furnished SST software. Look, sound and feel like the actual operational equipment to support required proficiency levels. Be capable of being upgraded as operational functionality is upgraded. The Space Fence shall deliver the associated COTS-based hardware to applicable AFSPC and AETC units (TBD), that will: Fulfill the hardware compatibility requirements of the SST software. Fulfill the security accreditation requirements of the training simulation software. The Space Fence shall collaborate with the SST software vendor to integrate the simulation software with the COTS-based hardware and the government-furnished SST software. The Space Fence shall provide operations procedures and Type 1

## Table 13
capability shall be | training on the use of | the integrated SST - |  | training on the use of
delivered no earlier than | the integrated SST - | based simulation |  | the integrated SST -
12 months and not later | based simulation | capability to AETC |  | based simulation
than 6 months prior to | capability to AETC | instructors and AFSPC |  | capability to AETC
operational acceptance. | instructors and AFSPC | cadre. The integrated |  | instructors and AFSPC
The integrated SST - | cadre. The integrated | SST-based training |  | cadre. The integrated
based training | SST-based training | simulation capability |  | SST-based training
simulation capability | simulation capability | shall be delivered no |  | simulation capability
shall meet AFSPC | shall be delivered no | earlier than 12 months |  | shall be delivered no
SIMCERT require- | earlier than 12 months | and not later than 6 |  | earlier than 12 months
ments. | and not later than 6 | months prior to |  | and not later than 6
| months prior to | operational |  | months prior to
| operational | acceptance. The |  | operational
| acceptance. The | integrated SST -based |  | acceptance. The
| integrated SST -based | training simulation |  | integrated SST -based
| training simulation | capability shall meet |  | training simulation
| capability shall meet | AFSPC SIMCERT |  | capability shall meet
| AFSPC SIMCERT | require-ments. |  | AFSPC SIMCERT
| require-ments. |  |  | require-ments.
Net-Ready
Space Fence must fully | Space Fence must | Space Fence must fully | TBD | Space Fence must
support execution of all | fully support execution | support execution of |  | fully support execution
operational activities and | of all operational | joint critical operational |  | of all operational
information exchanges | activities and | activities and |  | activities and
identified in the DoD | information exchanges | information exchanges |  | information exchanges
Enterprise Architecture | identified in the DoD | identified in the DoD |  | identified in the DoD
and solution | Enterprise Architecture | Enterprise Architecture |  | Enterprise Architecture
architectures based on | and solution | and solution |  | and solution
integrated DoDAF | architectures based on | architectures based on |  | architectures based on
content, and must | integrated DoDAF | integrated DoDAF |  | integrated DoDAF
satisfy the technical | content, and must | content, and must |  | content, and must
requirements for | satisfy the technical | satisfy the technical |  | satisfy the technical
transition to Net-Centric | requirements for | requirements for |  | requirements for
military operations to | transition to Net- | transition to Net-Centric |  | transition to Net-
include: Solution | Centric military | military operations to |  | Centric military
architecture products | operations to include: | include: Solution |  | operations to include:
compliant with DoD | Solution architecture | architecture products |  | Solution architecture
Enterprise Architecture | products compliant | compliant with DoD |  | products compliant
based on integrated | with DoD Enterprise | Enterprise Architecture |  | with DoD Enterprise
DoDAF content, | Architecture based on | based on integrated |  | Architecture based on
including specified | integrated DoDAF | DoDAF content, |  | integrated DoDAF
operationally effective | content, including | including specified |  | content, including
information exchanges. | specified operationally | operationally effective |  | specified operationally
Compliant with Net - | effective information | information exchanges. |  | effective information
Centric Data Strategy | exchanges. Compliant | Compliant with Net - |  | exchanges. Compliant
and Net-Centric | with Net -Centric Data | Centric Data Strategy |  | with Net -Centric Data
Services Strategy, and | Strategy and Net- | and Net-Centric |  | Strategy and Net-
the principles and rules | Centric Services | Services Strategy, and |  | Centric Services
identified in the DoD IEA, | Strategy, and the | the principles and rules |  | Strategy, and the
excepting tactical and | principles and rules | identified in the DoD |  | principles and rules
non-IP communi- | identified in the DoD | IEA, excepting tactical |  | identified in the DoD
cations. Compliant with | IEA, excepting tactical | and non-IP communi- |  | IEA, excepting tactical
GIG Technical Guidance | and non-IP communi- | cations. Compliant with |  | and non-IP communi-

## Table 14
to include IT Standards identified in the StdV-1 and implemen-tation guidance of GESPs necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views. Information assurance requirements including availability, integrity, authent-ication, confident-iality, and non- repudiation, and issuance of an ATO by the DAA. Support-ability requirements to include SAASM, Spectrum and JTRS requirements | cations. Compliant with GIG Technical Guidance to include IT Standards identified in the StdV-1 and implemen-tation guidance of GESPs necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views. Information assurance requirements including availability, integrity, authent-ication, confident-iality, and non -repudiation, and issuance of an ATO by the DAA. Support- ability requirements to include SAASM, Spectrum and JTRS requirements | GIG Technical Guidance to include IT Standards identified in the StdV-1 and implemen-tation guidance of GESPs necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views. Information assurance requirements including availability, integrity, authent-ication, confident-iality, and non -repudiation, and issuance of an IATO or ATO by the DAA. Support-ability requirements to include SAASM, Spectrum and JTRS requirements |  | cations. Compliant with GIG Technical Guidance to include IT Standards identified in the StdV-1 and implemen-tation guidance of GESPs necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views. Information assurance requirements including availability, integrity, authent-ication, confident-iality, and non -repudiation, and issuance of an ATO by the DAA. Support- ability requirements to include SAASM, Spectrum and JTRS requirements
MDT Size
MDT = 10 cm (cubesat) at orbital altitudes ≥ 250km and <= 2,000 km. MDT = 20 cm (cubesat) at orbital altitudes ≥ 2,000km and <= 3,000 km | MDT = 10 cm (cubesat) at orbital altitudes ≥ 250km and <= 2,000 km. MDT = 20 cm (cubesat) at orbital altitudes ≥ 2,000km and <= 3,000 km | (Threshold = Objective) MDT = 10 cm (cubesat) at orbital altitudes ≥ 250km and <= 2,000 km. MDT = 20 cm (cubesat) at orbital altitudes ≥ 2,000km and <= 3,000 km | TBD | MDT = 10 cm (cubesat) at orbital altitudes ≥ 250km and <= 2,000 km. MDT = 20 cm (cubesat) at orbital altitudes ≥ 2,000km and <= 3,000 km
Fence Integrity
≥ 95% (Cued); ≥ 50% (Un-cued) | ≥ 95% (Cued); ≥ 50% (Un-cued) | (Threshold = Objective) ≥ 95% (Cued); ≥ 50% (Un-cued) | TBD | ≥ 95% (Cued); ≥ 50% (Un-cued)
Surveillance and Track Coverage
IOC: 1) 250-800 km: determined by scan angle required 800- 3,000 km; 2) 800-3,000 km: 2 tracks (Cued /Un- cued); FOC: 1) 250-550 km: determined by scan angle required for 550- 3,000 km; 2) 550-800 km: 2 tracks (Cued /Un- cued) • 800-3,000 km: 2 | IOC: 1) 250-800 km: determined by scan angle required 800- 3,000 km; 2) 800-3,000 km: 2 tracks (Cued /Un -cued); FOC: 1) 250- 550 km: determined by scan angle required for 550-3,000 km; 2) 550- 800 km: 2 tracks (Cued /Un-cued) • 800- | (Threshold = Objective) IOC: 1) 250-800 km: determined by scan angle required 800- 3,000 km; 2) 800-3,000 km: 2 tracks (Cued /Un -cued); FOC: 1) 250- 550 km: determined by scan angle required for 550-3,000 km; 2) 550- 800 km: 2 tracks | TBD | IOC: 1) 250-800 km: determined by scan angle required 800- 3,000 km; 2) 800-3,000 km: 2 tracks (Cued /Un -cued); FOC: 1) 250- 550 km: determined by scan angle required for 550-3,000 km; 2) 550- 800 km: 2 tracks (Cued /Un-cued) • 800-

## Table 15
tracks (Un-cued); 4 tracks (Cued) | 3,000 km: 2 tracks (Un- cued); 4 tracks (Cued) | (Cued /Un-cued) • 800- 3,000 km: 2 tracks (Un- cued); 4 tracks (Cued) |  | 3,000 km: 2 tracks (Un- cued); 4 tracks (Cued)
E3
All components of the | All components of the | (Threshold = Objective) | TBD | All components of the
Space Fence shall | Space Fence shall | All components of the |  | Space Fence shall
operate in their intended | operate in their | Space Fence shall |  | operate in their
operational electro- | intended operational | operate in their |  | intended operational
magnetic environment | electro-magnetic | intended operational |  | electro-magnetic
without suffering or | environment without | electro-magnetic |  | environment without
causing unacceptable | suffering or causing | environment without |  | suffering or causing
performance | unacceptable | suffering or causing |  | unacceptable
degradation due to EMI | performance | unacceptable |  | performance
from other electronic | degradation due to EMI | performance |  | degradation due to EMI
equipment in the same | from other electronic | degradation due to EMI |  | from other electronic
environment. The Space | equipment in the same | from other electronic |  | equipment in the same
Fence shall not cause | environment. The | equipment in the same |  | environment. The
negative impacts, | Space Fence shall not | environment. The |  | Space Fence shall not
mission degradation, or | cause negative | Space Fence shall not |  | cause negative
other interference with | impacts, mission | cause negative |  | impacts, mission
systems operating in the | degradation, or other | impacts, mission |  | degradation, or other
same shared electro- | interference with | degradation, or other |  | interference with
magnetic environment. | systems operating in | interference with |  | systems operating in
Systems operating in | the same shared | systems operating in |  | the same shared
the same shared electro | electro-magnetic | the same shared |  | electro-magnetic
-magnetic environment | environment. Systems | electro-magnetic |  | environment. Systems
as the Space Fence | operating in the same | environment. Systems |  | operating in the same
shall not cause | shared electro- | operating in the same |  | shared electro-
unacceptable impacts, | magnetic environment | shared electro- |  | magnetic environment
mission degradation, or | as the Space Fence | magnetic environment |  | as the Space Fence
other interference with | shall not cause | as the Space Fence |  | shall not cause
normal operations of the | unacceptable impacts, | shall not cause |  | unacceptable impacts,
Space Fence. | mission degradation, or | unacceptable impacts, |  | mission degradation, or
| other interference with | mission degradation, or |  | other interference with
| normal operations of | other interference with |  | normal operations of
| the Space Fence. | normal operations of |  | the Space Fence.
the Space Fence.
Sustainment Ao
Space Fence System | Space Fence System | (Threshold = Objective) | TBD | Space Fence System
(excluding SOC) Ao >= | (excluding SOC) Ao >= | Space Fence System |  | (excluding SOC) Ao >=
95% SOC Ao >= 98% | 95% SOC Ao >= 98% | (excluding SOC) Ao >= |  | 95% SOC Ao >= 98%
95% SOC Ao >= 98%
Requirements Reference
CDD dated June 11, 2012
Change Explanations
None

## Table 16
Acronyms and Abbreviations
AETC - Air Education and Training Command AF - Air Force
AFI - Air Force Instruction
AFSPC - Air Force Space Command Ao - Operational Availability
ATO - Authority To Operate cm - centimeter
CMR - Combat Mission Ready COTS - Commercial Off The Shelf
DAA - Designating Accrediting Authority
DoD IEA - DoD Information Enterprise Architecture DoDAF - Department of Defense Architecture Framework E3 - Electromagnetic Environmental Effects
EMI - Electromagnetic Interference GESPs - GIG Enterprise Service Profiles GIG - Global Information Grid
IAW - In Accordance With IP - Internet Protocol
ISD - Instructional Systems Design/Development IT - Information Technology
JTRS - Joint Tactical Radio System km - Kilometer
MDT - Minimum Detectable Target Ref - Reference
SAASM - Selective Availability Anti-spoofing Module SIMCERT - Simulator Certification
SOC - Space Operations Center
SORTS - Status of Resources and Training System SST - Standard Space Trainer
StdV - Standards View TO - Technical Order

## Table 17
Track to Budget
RDT&E
Appn |  | BA | PE
Air Force | 3600 05 |  | 0604425F
| Project |  |  | Name
| 65A009 |  | Space Fence |  | (Shared) (Sunk)
Air Force | 3600 05 |  | 0604426F
| Project |  |  | Name
| 65A009 |  | Space Fence
Notes
Prior to FY 2015 all funds were executed and reported in PE 0604225F (Space Situational Awareness Systems).

## Table 18
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2014 $M |  |  |  | BY 2014 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 1567.7 |  | 1567.7 | 1724.5 |  | 1491.3 |  | 1594.2 |  | 1594.2 |  | 1502.9
Procurement | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Flyaway | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Non Recurring | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Other Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 1567.7 |  | 1567.7 | N/A |  | 1491.3 |  | 1594.2 |  | 1594.2 |  | 1502.9
Current APB Cost Estimate Reference
CAPE ICE dated May 23, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The ICE to support the Space Fence Increment 1 program, like all life-cycle cost estimates previously performed by the Office of CAPE, is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and Government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 19
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 1 | 1 | 1
Procurement | 0 | 0 | 0
Total | 1 | 1 | 1

## Table 20
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 1038.3 | 240.7 |  | 168.4 |  | 50.2 |  | 5.3 |  | 0 |  | 0 |  | 0 |  | 1502.9
Procurement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1038.3 | 240.7 |  | 168.4 |  | 50.2 |  | 5.3 |  | 0 |  | 0 |  | 0 |  | 1502.9
PB 2016 Total | 1046.8 | 243.9 |  | 196 |  | 68.5 |  | 5.3 |  | 0 |  | 0 |  | 0 |  | 1560.5
Delta | -8.5 | -3.2 |  | -27.6 |  | -18.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | -57.6
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1
PB 2016 Total | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 21
Cost and Funding
Annual Funding By Appropriation
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 111.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 203.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 279.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 191.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 240.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.3
Subtotal |  | 1 | -- |  | -- |  | -- |  | -- |  | -- |  | 1502.9

## Table 22
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 143.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 204.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 276.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 187.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 232.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 159.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.8
Subtotal |  | 1 | -- |  | -- |  | -- |  | -- |  | -- |  | 1491.3

## Table 23
Low Rate Initial Production
There is no LRIP for this program.

## Table 24
Foreign Military Sales
None
Nuclear Costs
None

## Table 25
Unit Cost
Unit Cost Report
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Current UCR Baseline (Jun 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1567.7 |  |  | 1491.3
Quantity | 1 |  |  | 1
Unit Cost | 1567.7 |  |  | 1491.3 |  | -4.87
Average Procurement Unit Cost
Cost | 0 |  |  | 0
Quantity | 0 |  |  | 0
Unit Cost | -- |  |  | -- |  | --
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Original UCR Baseline (Jun 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1567.7 |  |  | 1491.3
Quantity | 1 |  |  | 1
Unit Cost | 1567.7 |  |  | 1491.3 |  | -4.87
Average Procurement Unit Cost
Cost | 0 |  |  | 0
Quantity Unit Cost | 0 -- |  |  | 0 -- |  | --

## Table 26
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2014 $M | [5 empty] | TY $M
[8 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Jun 2014 |  |  |  |  | 1567.7 |  |  |  | N/A |  |  | 1594.2 |  |  | N/A
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Jun 2014 |  |  |  |  | 1567.7 |  |  |  | N/A |  |  | 1594.2 |  |  | N/A
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 1541.3 |  |  |  | N/A |  |  | 1560.5 |  |  | N/A
Current Estimate |  |  | Dec 2015 |  |  |  |  | 1491.3 |  |  |  | N/A |  |  | 1502.9 |  |  | N/A
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [14 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth |  | Spt |  | Total
1594.200 -12.700 0.000 0.000 0.000 -78.600 0.000 0.000 -91.300 1502.900

## Table 27
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [9 empty] | APUC Current Estimate
| Econ | Qty | Sch | Eng |  | Est | Oth | Spt |  | Total
0.000 -- -- -- -- -- -- -- -- 0.000
An APUC Unit Cost History is not available, since no Initial APUC Estimate had been calculated due to a lack of defined quantities.
SAR Baseline History
Item |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  | N/A |  |  | Jun 2009 |  |  |  | N/A |  |  | Jun 2009
Milestone B |  | N/A |  |  | May 2014 |  |  |  | N/A |  |  | May 2014
Milestone C |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
IOC |  | N/A |  |  | Jul 2019 |  |  |  | N/A |  |  | Oct 2018
Total Cost (TY $M) |  | N/A |  |  | 1594.2 |  |  |  | N/A |  |  | 1502.9
Total Quantity |  | N/A |  |  | 1 |  |  |  | N/A |  |  | 1
PAUC |  | N/A |  |  | 1594.2 |  |  |  | N/A |  |  | 1502.9

## Table 28
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1594.2 | -- | -- | 1594.2
Previous Changes
Economic | -7.9 | -- | -- | -7.9
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -25.8 | -- | -- | -25.8
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -33.7 | -- | -- | -33.7
Current Changes
Economic | -4.8 | -- | -- | -4.8
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -52.8 | -- | -- | -52.8
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -57.6 | -- | -- | -57.6
Total Changes | -91.3 | -- | -- | -91.3
CE - Cost Variance | 1502.9 | -- | -- | 1502.9
CE - Cost & Funding | 1502.9 | -- | -- | 1502.9

## Table 29
Summary BY 2014 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1567.7 | -- | -- | 1567.7
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -26.4 | -- | -- | -26.4
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -26.4 | -- | -- | -26.4
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -50 | -- | -- | -50
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -50 | -- | -- | -50
Total Changes | -76.4 | -- | -- | -76.4
CE - Cost Variance | 1491.3 | -- | -- | 1491.3
CE - Cost & Funding | 1491.3 | -- | -- | 1491.3
Previous Estimate: December 2014

## Table 30
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -4.8
Adjustment for current and prior escalation. (Estimating) |  | 2.8 | 2.9
Revised estimate to realign with CAPE ICE. (Estimating) |  | -41.2 | -43.8
Congressional Reductions in FY 2016. (Estimating) |  | -2.4 | -2.5
Revised estimate to reflect Federally Funded Research and Development Centers |  | -0.7 | -0.7
reduction in FY 2016. (Estimating)
Revised estimate to reflect Small Business Innovative Research adjustment in FY 2015. (Estimating)
-8.2 -8.4
Revised estimate due to inflation rate adjustments for non-pay/non-fuel. (Estimating) Revised estimate to reflect application of new outyear inflation indices. (Estimating) | -2.1 +1.8 |  |  | -2.2 +1.9
RDT&E Subtotal | -50 |  |  | -57.6

## Table 31
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: Space Fence
Contractor: Lockheed Martin Corp.
Contractor Location: 199 Borton Landing Rd
Moorestown, NJ 08057
Contract Number: FA8709-14-C-0001
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Cost Plus Fixed Fee (CPFF), Cost (CR)
Award Date: June 02, 2014
Definitization Date: June 02, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
914.7 977.8 1 915.3 979.0 1 915.3 915.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to an erroneous initial price input by the program office in the previous SAR, which should have been 914.7. Additionally, an option CLIN 0026 was awarded on January 20, 2015 increasing the target price by 0.6.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/27/2015) -10.9 -20.6
Previous Cumulative Variances +3.7 -11.0
Net Change -14.6 -9.6
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to construction cost growth due to Differing Site Conditions.
The unfavorable net change in the schedule variance is due to construction schedule slips due to Differing Site Conditions.
Notes
Contract performance data is based solely on CLIN 0001 data from the contract.

## Table 32
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 1 | 0%
Production | 0 | 0 | 0 | --
Total Program Quantity Delivered | 0 | 0 | 1 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1502.9
744.4
49.53%
15
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
12
80%
1279
85.1%
The above data is current as of February 29, 2016.

## Table 33
Operating and Support Cost
Cost Estimate Details
Date of Estimate: May 01, 2014
Source of Estimate: CAPE ICE
Quantity to Sustain: 1
Unit of Measure: System
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2019 - FY 2039
Space Fence Inc 1 consists of one quantity that includes the control center and one radar site.
Sustainment Strategy
The Space Fence System will employ a two level maintenance and support concept (organizational and depot) similar to the current Space Surveillance Network (SSN) sensors. The development contractor will provide Interim Contractor Support (ICS), for both organizational and depot, for Increment 1 of the Space Fence system for up to two years after IOC for Kwajalein Atoll, Marshall Islands. During the ICS period, the contractor will perform both organizational and depot level maintenance on the Space Fence weapon system.
The Space Fence Depot Source of Report (DSOR) is complete and has indicated all Space Fence depot repairable workload (hardware and software) as well as cryptological equipment is considered core workload. Oklahoma City Air Logistics Center (OC-ALC) is designated as the depot for hardware and software and the Cryptologic Systems Group in San Antonio, TX is designated as the depot for cryptological equipment.
Planning activity for the depot maintenance with OC-ALC is underway to identify depot requirements and ensure proper activation of the sustainment capability at OC-ALC. As the activities progress, the information gained from the process, as well as the business case analysis, will influence sustainment support strategy after full operational capability. This will ensure the best mix of public and/or private capabilities will be used to sustain the system while meeting statutory requirements. Three essential areas are being addressed: (1) item management of parts (supply source), (2) depot repair, i.e., software/hardware maintenance, and (3) depot management type activities.
System logistics support for the Space Fence Inc 1 program will be performed over the life of the system, expected to be 20 years. This support includes maintenance and periodic technology refreshes to assure the system continues to meet required performance, and allows upgrades when mission requirements dictate as well as the government management of these processes.
The full product support package, including technical orders, support equipment, training, and initial spares, will be delivered by the development contractor prior to fielding, which will enable full sustainment of the system.
Antecedent Information
The Antecedent system is Air Force Space Surveillance System (AFSSS). AFSSS estimates are based on one unit with a service life of 15 years (FY 1998 to FY 2013). The AFSSS was closed October 1, 2013. Cost details were provided
by the Air Force Total Ownership Cost database.

## Table 34
Annual O&S Costs BY2014 $M
Cost Element |  | Space Fence Inc 1 Average Annual Cost Per System | [5 empty] | Air Force Space Surveillance System (AFSSS) (Antecedent) Average Annual Cost Per System
Unit-Level Manpower |  | 5.221 | [5 empty] | 0.705
Unit Operations |  | 16.99 | [5 empty] | 5.05
Maintenance |  | 2.422 | [5 empty] | 1.24
Sustaining Support |  | 11.262 | [5 empty] | 1.432
Continuing System Improvements |  | 14.224 | [5 empty] | 0.61
Indirect Support |  | 9.828 | [5 empty] | 1.595
Other |  | 0.274 | [5 empty] | 0
Total |  | 60.221 | [5 empty] | 10.632
Other costs include Depot Standup amortized over the 20 year design life.
Item | Total O&S Cost $M
| Space Fence Inc 1 | [7 empty] | Air Force Space Surveillance System (AFSSS) (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 1208.6 |  |  | 1329.5 |  |  | 1204.3 |  | 159.5
Then Year | 1554.1 |  |  | N/A |  |  | 1554.1 |  | 0
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
Total O&S Costs = Unitized cost * number of systems * service life per system
Total O&S Costs = $60.221M * 1 Space Fence Inc 1 system * 20 year design life = $1204M
O&S Cost Variance
Category |  |  | BY 2014 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
1204.3
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 1204.3

## Table 35
Disposal Estimate Details
Date of Estimate: May 01, 2014
Source of Estimate: CAPE ICE
Disposal/Demilitarization Total Cost (BY 2014 $M): Total costs for disposal of all System are 4.3