## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-437
AH-64E Apache New Build (AH-64E New Build)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 19
Foreign Military Sales 20
Nuclear Costs 20
Unit Cost 21
Cost Variance 24
Contracts 27
Deliveries and Expenditures 28
Operating and Support Cost 29

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
AH-64E Apache New Build (AH-64E New Build)
DoD Component
Army
Responsible Office
COL Jeffrey Hager Building 5307
Redstone Arsenal, AL 35898
jeffrey.hager@peoavn.army.mil
Phone: 256-313-4200
Fax: 256-313-4497
DSN Phone: 897-4200
DSN Fax:
Date Assigned: August 9, 2012
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acqusition Program Baseline (APB) dated December 16, 2010
Approved APB
Component Acquisition Executive (CAE) Approved Acquisition Program Baseline (APB) dated July 2, 2013

## Table 6
Mission and Description
The AH-64E Apache New Build (AH-64E New Build), hereinafter referred to as AH-64E, is the heavy attack helicopter of the current and future force. It is a twin engine, four-bladed, tandem seat, attack helicopter with 30-millimeter ammunition, 2.75- inch rockets, laser and radio frequency Hellfire missiles. The AH-64E is the Army's network-centric, multi-role weapon system within the Future Modular Force (FMF). It provides the capability to simultaneously conduct (or quickly transition between) close combat, mobile strike, armed reconnaissance, manned-unmanned teaming, security and vertical maneuver missions across the full spectrum of warfare from Stability and Support Operations to Major Combat Operations, when required, in day, night, obscured battlefield and adverse weather conditions. The AH-64E enables the Joint Air/Ground Maneuver Team to dominate the battle space by providing air-ground synergy through real-time Intelligence, Surveillance, and Reconnaissance (ISR) information and responsive precision fires. The AH-64E is linked to Joint and Combined Arms Air/Ground Maneuver Teams via Enhanced Digital Communications, Unmanned Aircraft Systems Data Links and Joint networking waveforms.
The AH-64E is an Apache Attack Helicopter modified as required to effectively and efficiently integrate the Longbow Apache well into the 21st century, by providing improvements to make it relevant in FMF operations. It provides a significantly enhanced warfighting capability over the AH-64A and AH-64D. It is capable of being employed day or night in adverse weather and obscurants, and can effectively engage and destroy advanced threat weapon systems on the air-land battlefield. Tactically, the AH-64E provides significant war fighting advantages over the original AH-64D and multiplies the combat effectiveness of the entire fleet. It will be fully capable of employing the Longbow Fire Control Radar mission kit, the Modernized Target Acquisition Designation System/Modernized Pilot Night Vision System, the Longbow Hellfire missiles, and future improved munitions in addition to the normal complement of AH-64D munitions. Additionally, the AH-64E includes upgraded engines, debuts evolutionary transmission technology, and incorporates significant improvements to its main rotor system, which increases power and provides substantial performance gains.
The AH-64E is fully network-centric capable with current digitized forces and FMF-equipped forces. This enables interoperability with current and future Tactical Operations Center and Army Battle Command System forces. In addition, this reduces the logistics footprint, enhances its deployability, reduces O&S costs, improves AH-64D flight performance and provides a means to effectively utilize already funded technology insertions. The AH-64E has a fully compatible and rapidly re-configurable open system architecture mission processor design, enabling rapid integration of future communication systems, and minimizing obsolescence.
The AH-64E operates within the future force system-of-systems environment where maximum combat power is delivered to units only in coherent packages of systems with synergistic interdependence. The FMF concept drives the demand for network-centric interdependence and Joint integration across the force to new levels. The AH-64E meets these challenges by providing and integrating Command and Control, ISR, and communications connectivity for attack/reconnaissance aviation within Brigade Combat Teams, Divisions, and Corps.

## Table 7
Executive Summary
Program Highlights Since Last Report:
In August 2015, Manned/Unmanned Teaming Expanded capabilities competition was completed and contract awarded. Meanwhile, Fire Control Radar Maritime Mode Testing occurred form August through September 2015 at Joint Base Little Creek, Virginia.
In September 2015, PM Apache completed fielding to the 2-17 Calvary (3-101 Attack Reconnaissance Battalion (ARB)), the Army’s 4th Unit Equipped with the E-model Apaches. PM Apache also assisted and managed transfer of 20 AH-64D aircraft from Germany and Forces Command to a new AH-64 unit, the 1-25 ARB in Fort Wainwright, Alaska. PM Apache identified and provided a materiel solution to support Apache AH-64D and AH-64E helicopters for first time stationing in an arctic environment.
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation:
June 30, 2014: The Boeing Company FRP contract for Lots 3 and 4 was definitized and awarded. This contract supports production of ten AH-64E Apache New Build helicopters. This production activity supported completion of fielding the second and third units equipped, as well as augmentation of the training fleet.
August 14, 2014: AH-64E Capability Version 4 Follow-on Operational Test & Evaluation was successfully concluded on time at Eglin Air Force Base, Florida. This capability is scheduled to be in production Lot 5 in FY 2015.
September 15, 2014: Seven additional New Build aircraft were awarded as an undefinitized contract awared modification.
November 2014: The First Unit Equipped, 1-229 Attack Reconnaissance Battalion, successfully completed the first operational combat deployment of the AH-64E.
December 23, 2014: Apache PM initiated the required processes and is seeking necessary approvals to enter a multi-year contract to support production from FY 2017 to FY 2021. The Army Acquisition Executive signed the justification and approval.
December 31, 2014: Apache program delivered ten AH-64E New Build Attack Helicopters of the 56 Army Acquisition Objective.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone C | Jul 2010 | Jul 2010 | Jan 2011 | Sep 2010
Initial Operational Test and Evaluation (IOT&E) | Mar 2012 | N/A | N/A | Mar 2012
Full Rate Production (FRP) | Jul 2012 | Jul 2012 | Mar 2013 | Mar 2013
First Unit Equipped (FUE) | Nov 2012 | N/A | N/A | May 2013
Initial Operational Capability (IOC) | May 2013 | N/A | N/A | Nov 2013
Change Explanations

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net Ready
Fully support execution of all operational activities. | Fully support execution of all operational activities. | Fully support execution of joint critical operational activities | Met Threshold | Fully support execution of all operational activities.
Performance
6000' PA, 95F OGE Hover (lbs/payload)
4100 | 4100 | 3400 | Met Threshold | 3400
Mission Reliability
MTBF (M) hrs
Lot 1
22 | 22 | 15.3 | Met Objective | 15.3
Lot 4
22 | 22 | 17 | Met Objective | 17
MR for 3.5 hr. Flight (%)
85 | 85 | 80 | Met Objective | 80
Survivability
Safe operation (minutes)
30 | 30 | 30 | Met Objective | 30
Survive Band IV MANPADS IR Missile Engagement
IAW JROCM 086-10 | IAW JROCM 086-10 | IAW JROCM 086-10 | Met Objective | IAW JROCM 086-10
Force Protection
Crewstation armor Survivability (mm)
IAW JROCM 086-10 | IAW JROCM 086-10 | IAW JROCM 086-10 | Met Objective | IAW JROCM 086-10
Crewstation armor barrier survivability
IAW JROCM 086-10 | IAW JROCM 086-10 | IAW JROCM 086-10 | Met Objective | IAW JROCM 086-10
Requirements Reference
Capability Production Document (CPD) dated June 1, 2010
Change Explanations
None

## Table 11
Notes
Net Ready KPP compliance is achieved by meeting the information exchange capabilities required by the Integrated Architectures Operational View-1 and is demonstrated by achieving Joint Interoperability Certification, Army Interoperability Certification, and DoD Information Assurance and Accreditation Process accreditation.
Demonstrated Performance based upon Director, Operational Test and Evaluation assessment of AH-64E Initial Operational Test and Evaluation.
Acronyms and Abbreviations
% - Percent ' - feet
F - Fahrenheit hr - hour
hrs - hours
IAW - In Accordance With IR - Infrared
JROCM - Joint Requirements Oversight Council Memorandum lbs - pounds
MANPADS - Man Portable Air Defense Systems mm - millimeter
MR - Mission Reliability
MTBF (M) - Mean Time Between Failure (Mission) OGE - Out of Ground Effect
PA - Pressure Altitude

## Table 12
Track to Budget
Procurement
Army | 2031 01 |  | 0210100A
| Line Item |  | Name
| A05133 |  | AH-64 Apache Block IIIB New Build
Appn |  | BA | PE

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2010 $M |  |  |  |  | BY 2010 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Flyaway |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Recurring |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Non Recurring |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Procurement |  | 2307 |  | 2003.3 | 2203.6 |  | 2031.9 |  | 2510.4 |  | 2562.6 |  | 2522.7
Flyaway |  | -- |  | -- | -- |  | 1864 |  | -- |  | -- |  | 2311.2
Recurring |  | -- |  | -- | -- |  | 1824.7 |  | -- |  | -- |  | 2261.2
Non Recurring |  | -- |  | -- | -- |  | 39.3 |  | -- |  | -- |  | 50
Support |  | -- |  | -- | -- |  | 167.9 |  | -- |  | -- |  | 211.5
Other Support |  | -- |  | -- | -- |  | 111.8 |  | -- |  | -- |  | 140.4
Initial Spares |  | -- |  | -- | -- |  | 56.1 |  | -- |  | -- |  | 71.1
MILCON |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total |  | 2307 |  | 2003.3 | N/A |  | 2031.9 |  | 2510.4 |  | 2562.6 |  | 2522.7
Confidence Level
Confidence Level of cost estimate for current APB: 50%
This estimate, like all previous Cost Analysis Improvement Group (CAIG) and Cost Assessment and Program Evaluation (CAPE) estimates, is built upon a product-oriented work breakdown structure; is based on historical actual cost information to the maximum extent possible; and, most importantly, is based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 14
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 56 | 56 | 63
Total | 56 | 56 | 63

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Procurement | 538.8 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 1983.9 |  | 2522.7
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 538.8 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 1983.9 |  | 2522.7
PB 2016 Total | 538.8 | 0 |  |  | 0 | 0 | 0 |  | 432.7 |  | 350.3 |  |  | 1297.2 |  | 2619
Delta | 0 | 0 |  |  | 0 | 0 | 0 |  | -432.7 |  | -350.3 |  |  | 686.7 |  | -96.3
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 17 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 46 |  | 63
PB 2017 Total | 0 |  | 17 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 46 |  | 63
PB 2016 Total | 0 |  | 17 |  | 0 | 0 | 0 | 0 |  |  | 7 | 7 |  | 32 |  | 63
Delta | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | -7 | -7 |  | 14 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | 71.6 |  | -- |  | -- |  | 71.6 |  | -- |  | 71.6
2013 |  | 13 | 294.6 |  | -- |  | -- |  | 294.6 |  | 30.6 |  | 325.2
2014 |  | 4 | 142 |  | -- |  | -- |  | 142 |  | -- |  | 142
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2022 |  | 16 | 710.8 |  | -- |  | 50 |  | 760.8 |  | 64 |  | 824.8
2023 |  | 15 | 575.1 |  | -- |  | -- |  | 575.1 |  | 57.9 |  | 633
2024 |  | 15 | 467.1 |  | -- |  | -- |  | 467.1 |  | 59 |  | 526.1
Subtotal |  | 63 | 2261.2 |  | -- |  | 50 |  | 2311.2 |  | 211.5 |  | 2522.7

## Table 17
Annual Funding 2031 ¦ Procurement ¦ Aircraft Procurement, Army
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | 67.3 |  | -- |  | -- |  | 67.3 |  | -- |  | 67.3
2013 |  | 13 | 272.2 |  | -- |  | -- |  | 272.2 |  | 28.3 |  | 300.5
2014 |  | 4 | 129.2 |  | -- |  | -- |  | 129.2 |  | -- |  | 129.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2022 |  | 16 | 559.2 |  | -- |  | 39.3 |  | 598.5 |  | 50.4 |  | 648.9
2023 |  | 15 | 443.6 |  | -- |  | -- |  | 443.6 |  | 44.6 |  | 488.2
2024 |  | 15 | 353.2 |  | -- |  | -- |  | 353.2 |  | 44.6 |  | 397.8
Subtotal |  | 63 | 1824.7 |  | -- |  | 39.3 |  | 1864 |  | 167.9 |  | 2031.9

## Table 18
Cost Quantity Information 2031 ¦ Procurement ¦ Aircraft Procurement, Army
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2010 $M
2012 | -- | --
2013 | 13 | 338.5
2014 | 4 | 128.4
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
2022 | 16 | 497.6
2023 | 15 | 471.9
2024 | 15 | 388.3
Subtotal | 63 | 1824.7

## Table 19
Low Rate Initial Production
There is no LRIP for this program.

## Table 20
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Saudi Arabia | 2015-09-15 | 12 | 408.3
Saudi Arabia | 2015-09-15 | 12 | 496.8
Qatar | 2014-08-10 | 24 | 877.7 | Fully Implemented.
Indonesia | 2013-08-26 | 8 | 345.3 | Fully Implemented.
Korea | 2013-05-02 | 36 | 1075.1 | Fully Implemented.
Saudi Arabia | 2011-11-29 | 12 | 420.6 | Fully Implemented.
Saudi Arabia | 2011-10-17 | 24 | 855.7 | Fully Implemented.
Saudi Arabia | 2009-12-30 | 12 | 510 | Fully Implemented.
Taiwan | 2008-12-22 | 30 | 1912 | Fully Implemented.
Notes
Nuclear Costs
None

## Table 21
Unit Cost
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  |  |  | % Change
|  | Current UCR Baseline (Jul 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2003.3 |  |  |  | 2031.9
Quantity | 56 |  |  |  | 63
Unit Cost | 35.773 |  |  |  | 32.252 |  |  | -9.84
Average Procurement Unit Cost
Cost | 2003.3 |  |  |  | 2031.9
Quantity | 56 |  |  |  | 63
Unit Cost | 35.773 |  |  |  | 32.252 |  |  | -9.84
Item |  | BY 2010 $M |  | BY 2010 $M |  |  | % Change
|  | Original UCR Baseline (Dec 2010 APB) |  | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2134.6 |  |  |  |  | 2031.9
Quantity | 56 |  |  |  |  | 63
Unit Cost | 38.118 |  |  |  |  | 32.252 |  | -15.39
Average Procurement Unit Cost
Cost | 2134.6 |  |  |  |  | 2031.9
Quantity | 56 |  |  |  |  | 63
Unit Cost | 38.118 |  |  |  |  | 32.252 |  | -15.39

## Table 22
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2010 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Dec 2010 |  |  |  |  | 38.118 |  |  | 38.118 |  |  | 41.539 |  |  | 41.539
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Dec 2010 |  |  |  |  | 38.118 |  |  | 38.118 |  |  | 41.539 |  |  | 41.539
Current APB |  |  | Jul 2013 |  |  |  |  | 35.773 |  |  | 35.773 |  |  | 45.761 |  |  | 45.761
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 33.4 |  |  | 33.4 |  |  | 41.571 |  |  | 41.571
Current Estimate |  |  | Dec 2015 |  |  |  |  | 32.252 |  |  | 32.252 |  |  | 40.043 |  |  | 40.043
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
44.829 0.135 1.872 4.649 0.000 -10.348 0.000 -1.094 -4.786 40.043
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
44.829 0.135 1.872 4.649 0.000 -10.348 0.000 -1.094 -4.786 40.043

## Table 23
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | N/A | N/A
Milestone C | N/A | N/A | Jul 2010 | Sep 2010
IOC | N/A | N/A | May 2013 | Nov 2013
Total Cost (TY $M) | N/A | N/A | 2510.4 | 2522.7
Total Quantity | N/A | N/A | 56 | 63
PAUC | N/A | N/A | 44.829 | 40.043

## Table 24
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
-- 2510.4 -- 2510.4
Economic |  | -- |  | 26.3 |  | -- |  | 26.3
Quantity |  | -- |  | 431.7 |  | -- |  | 431.7
Schedule |  | -- |  | 287.6 |  | -- |  | 287.6
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | -646.6 |  | -- |  | -646.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 9.6 |  | -- |  | 9.6
Subtotal |  | -- |  | 108.6 |  | -- |  | 108.6
Current Changes Economic |  | -- |  | -17.8 |  | -- |  | -17.8
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 5.3 |  | -- |  | 5.3
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | -5.3 |  | -- |  | -5.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -78.5 |  | -- |  | -78.5
Subtotal |  | -- |  | -96.3 |  | -- |  | -96.3
Total Changes |  | -- |  | 12.3 |  | -- |  | 12.3
CE - Cost Variance |  | -- |  | 2522.7 |  | -- |  | 2522.7
CE - Cost & Funding |  | -- |  | 2522.7 |  | -- |  | 2522.7

## Table 25
Summary BY 2010 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | -- | 2307 | -- | 2307
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | 313.5 | -- | 313.5
Schedule | -- | 72.8 | -- | 72.8
Engineering | -- | -- | -- | --
Estimating | -- | -563.9 | -- | -563.9
Other | -- | -- | -- | --
Support | -- | -25.2 | -- | -25.2
Subtotal | -- | -202.8 | -- | -202.8
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -12.4 | -- | -12.4
Other | -- | -- | -- | --
Support | -- | -59.9 | -- | -59.9
Subtotal | -- | -72.3 | -- | -72.3
Total Changes | -- | -275.1 | -- | -275.1
CE - Cost Variance | -- | 2031.9 | -- | 2031.9
CE - Cost & Funding | -- | 2031.9 | -- | 2031.9
Previous Estimate: December 2014

## Table 26
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -17.8
Adjustment for current and prior escalation. (Estimating) +1.3 +1.6
Stretch-out of procurement buy profile from FY 2022 to FY 2024 due to funding constraints. (Schedule)
0.0 +5.3
Revised estimate due to changes in estimating methodology. (Estimating) | -13.7 |  |  | -6.9
Adjustment for current and prior escalation. (Support) | 0.1 |  |  | 0
Decrease in Other Support due to updated estimating methodology. (Support) | -58.9 |  |  | -77.4
Decrease in Initial Spares due to updated estimating methodology. (Support) | -1.1 |  |  | -1.1
Procurement Subtotal | -72.3 |  |  | -96.3

## Table 27
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: FRP
Contractor: The Boeing Company
Contractor Location: 5000 E McDowell Road
Mesa, AZ 85215-9707
Contract Number: W58RGZ-12-C-0055
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 29, 2012
Definitization Date: May 26, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
35.5 35.5 10 288.9 291.4 17 288.9 288.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the Original Target Price was based on a quantity of ten aircraft. The Current Target Price is based on a quantity of 17 aircraft.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because an EVM waiver was granted by the Army Acquisition Executive on December 6, 2015 due to the program being a mature production or non-developmental services program.
Notes
An undefinitized contract action for seven additional New Build aircraft was awarded as a contract modification on September 15, 2014.
The Initial Contract Quantity was incorrectly reported as nine in prior reports. The Initial Contract Quantity is updated to reflect the correct quantity of 10 in the December 2015 SAR.

## Table 28
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 10 | 10 | 63 | 15.87%
Total Program Quantity Delivered | 10 | 10 | 63 | 15.87%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2522.7
294
11.65%
13
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
5
38.46%
538.8
21.36%
The above data is current as of March 01, 2016.

## Table 29
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 14, 2016
Source of Estimate: POE
Quantity to Sustain: 56
Unit of Measure: Aircraft
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2013 - FY 2046
The O&S cost estimate is based upon the OSD CAPE ICE dated August 15, 2012. The estimate was updated on September 17, 2013; February 24, 2014; January 16, 2015; and January 14, 2016 for fact-of-life changes.
The sustainment quantity of 56 aircraft differs from the acquisition quantity of 63 aircraft by seven aircraft. Those seven aircraft are replacements for battlefield losses.
Sustainment Strategy
The AH-64E Apache is maintained by a mix of soldier and civilian maintainers. The strategy assumes the fielding of 56 New Build aircraft, each flying 203.4 hours per year. The Mean Time Between Failure goal for the aircraft system is 22 hours at maturity once total program reaches 50,000 operational hours.
Antecedent Information
The antecedent to the AH-64E Apache is the AH-64D Longbow. The AH-64D Longbow will be in service until 2046. There are currently 633 AH-64D Longbow aircraft in operation. The AH-64D Longbow will have a total of 14,847 Fleet Years of Operational Tempo. Longbow antecedent data is derived from the Milestone C estimate, updated January 15, 2013.
14,847 Fleet Years x $3,420K per operation hour = $50,776.7M (BY 2010 $M); $58,146.7M (TY)
Annual O&S Costs BY2010 $K
Cost Element | AH-64E New Build Average Annual Cost Per Aircraft | Longbow Apache (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower | 1538 | 1538
Unit Operations | 206 | 205
Maintenance | 938 | 1148
Sustaining Support | 358 | 355
Continuing System Improvements | 73 | 73
Indirect Support | 102 | 101
Other | 0 | 0
Total | 3215 | 3420

## Table 30
Item | Total O&S Cost $M
| AH-64E New Build | [5 empty] | Longbow Apache (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 3538.1 |  | 3891.9 |  |  | 3601.6 | 50776.7
Then Year | 0 |  | N/A |  |  | 5066 | N/A
The AH-64E New Build estimate updated to reflect changes in the planned operational fleet schedule resulting from recent contract changes with the program's prime contractor as of January 14, 2016.
Equation to Translate Annual Cost to Total Cost
56 Helicopters * 20 Years Operational Life * $3215.0M Unitized Cost = $3601.6M (BY 2010 $M) The discrepancy in the reported cost and the equation is due to rounding.
O&S Cost Variance
Category |  | BY 2010 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
3543.1
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 54.1 Depot Level Overhaul and Depot Level Spares re- estimated.
Cost Data Update 0.0
Labor Rate 3.1 Army Military-Civilian Costing System Manpower Cost Factors increased.
Energy Rate 1.3 Updated Cost of Petroleum, Oil, and Lubricants.
Technical Input 0.0
Other 0.0
Total Changes 58.5
Current Estimate 3601.6
Disposal Estimate Details
Date of Estimate: August 15, 2012
Source of Estimate: CAPE ICE
Disposal/Demilitarization Total Cost (BY 2010 $M): Total costs for disposal of all Aircraft are 46.0
Total Disposal Costs for both the AH-64E Remanufacture and AH-64E New Build aircraft is $46.03M (BY 2010 $M) in accordance with the OSD CAPE ICE dated August 15, 2012.