## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-260
Guided Multiple Launch Rocket System/Guided Multiple Launch Rocket System Alternative Warhead (GMLRS/GMLRS AW)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 22
Unit Cost 23
Cost Variance 27
Contracts 30
Deliveries and Expenditures 36
Operating and Support Cost 37

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Guided Multiple Launch Rocket System/Guided Multiple Launch Rocket System Alternative Warhead (GMLRS/GMLRS AW)
DoD Component
Army
Responsible Office
COL James Mills
Presion Fires Rocket and Missile Systems Project Office 5250 Martin Road
Redstone Arsenal, AL 35898-8000
james.c.mills18.mil@mail.mil
Phone: | 256-876-1195
Fax: | 256-955-7958
DSN Phone: | 746-1195
DSN Fax: Date Assigned: | July 17, 2015
References
SAR Baseline (Production Estimate)
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated May 30, 2003
Approved APB
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated May 20, 2015

## Table 6
Mission and Description
The mission of the Guided Multiple Launch Rocket System/Guided Multiple Launch Rocket System Alternative Warhead (GMLRS/GMLRS AW) is to attack/neutralize/suppress/destroy targets using indirect precision fires. GMLRS provides Field Artillery units with medium- and long-range (70+ kilometers (Km)) fires while supporting brigade, division, corps, army, theater, Joint/Coalition Forces, and Marine Air-Ground Task Forces in full, limited, or expeditionary operations. GMLRS rocket is a solid propellant artillery rocket deployed from the M270A1 and the High Mobility Artillery Rocket System mobile launch vehicles. GMLRS/GMLRS AW uses an Inertial Measuring Unit with Global Positioning System assistance to guide the rocket to a specific point to deliver effects on target. GMLRS/GMLRS AW is transported and fired in a Rocket Pod Container that consists of six rockets. GMLRS family of munitions consists of three increments: Dual-Purpose Improved Conventional Munition (DPICM), Unitary (U), and Alternative Warhead (AW).
GMLRS DPICM (Increment 1)
The GMLRS DPICM (Increment 1) has a range of 70+ Km, contains 404 DPICM, and is used to provide precision fires on area targets including personnel and thinly armored vehicles. The GMLRS DPICM was an international cooperative development program with five nations (United States, United Kingdom, France, Germany, and Italy).
GMLRS-U (Increment 2)
The GMLRS-U (Increment 2) is equipped with a 200-pound Unitary high explosive warhead, has a range of 70+ Km, and is effective against multiple targets. The single warhead also limits collateral damage to areas surrounding the designated target.
GMLRS AW (Increment 3)
The GMLRS AW (Increment 3) is currently designed to replace the DPICM, provide similar effects at comparable range, and eliminate the probability of Unexploded Ordnance (UXO). The GMLRS AW will satisfy the UXO requirements as defined in the June 19, 2008 Department of Defense Policy on Cluster Munitions and Unintended Harm to Civilians.

## Table 7
Executive Summary
GMLRS Unitary
The Precision Fires Rocket and Missile Systems Project Office executed a GMLRS Unitary Reliability Scoring Conference on July 15, 2015 and assessed the continuous reliability of the GMLRS Unitary at 0.94 (149 Flight Successes of 158 Attempts).
United Arab Emirates (UAE) signed a Letter of Offer and Acceptance (LOA) in March 2015 for 65 GMLRS Unitary Rocket Pods.
GMLRS AW
The Physical Configuration Audit for the GMLRS AW was completed at the system level in March 2015.
Director of Operational Test and Evaluation Assessment recommended the Army revise the Tactics, Techniques, and Procedures (TTP) large area targets for GMLRS AW. Test and Evaluation Command revised the TTP, and the Project Office conducted two successful fire missions in May 2015. The lethality was significantly improved.
The GMLRS AW program successfully completed the combined Milestone C and FRP Decision Review on April 8, 2015. The GMLRS AW Cost Position was approved on April 15, 2015. The ADM to enter into the Production and Deployment Phase and begin FRP and the revised APB were approved by the Army Acquisition Executive on May 20, 2015.
GMLRS FRP X Contract was awarded on June 4, 2015, as an Undefinitized Contract Action change order in the Not to Exceed (NTE) amount of $226.9M. The NTE was awarded for GMLRS AW plus Low Cost Reduced Range Practice Rocket requirements and depot spares for the Army, U.S. Marine Corps, Bahrain, and UAE.
The annual Army Configuration Steering Board was completed on September 15, 2015; the board recommended no descoping actions.
GMLRS AW completed Initial Operational Test and Evaluation with an assessed reliability of 0.97 (29 Flight Success of 30 attempts). GMLRS AW test program achieved an overall reliability of 0.99 (98 Flight Success of 99 Attempts). The JROC was briefed in September 2015. This completes the GMLRS AW test phase.
Jordan signed a LOA on January 14, 2016 for 24 GMLRS AW rocket pods. Finland signed a LOA on February 20, 2016 for 25 GMLRS AW and 15 GMLRS Unitary rocket pods.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
GMLRS Milestone II EMD | Mar 1998 | Mar 1998 | Sep 1998 | Jul 1998
DPICM
Milestone C | Mar 2003 | Mar 2003 | Sep 2003 | Mar 2003
Full Rate Production Decision | Mar 2005 | Jun 2005 | Dec 2005 | Jun 2005
Initial Operational Capability | Nov 2006 | Dec 2005 | Jun 2006 | Dec 2005
UNITARY
Milestone B | Mar 2003 | Mar 2003 | Sep 2003 | Mar 2003
Milestone C | Sep 2006 | May 2007 | Nov 2007 | May 2007
Full Rate Production Decision | Sep 2008 | Sep 2008 | Mar 2009 | Dec 2008
Initial Operational Capability | Mar 2008 | Aug 2008 | Feb 2009 | Dec 2008
Alternative Warhead
Milestone B | N/A | Dec 2011 | Jun 2012 | Feb 2012
Milestone C | N/A | May 2015 | May 2015 | May 2015
Full Rate Production Decision | N/A | May 2015 | May 2015 | May 2015
Initial Operational Capability | N/A | Dec 2016 | Jun 2017 | Sep 2016
(Ch-1)
(Ch-1)
(Ch-2)
Change Explanations
(Ch-1) The Current Estimate for GMLRS AW Milestone C and FRP Decision changed from April 2015 to May 2015 to reflect the approved GMLRS AW ADM dated May 20, 2015 to enter into the Production and Deployment Phase and begin FRP.
(Ch-2) The Current Estimate for GMLRS AW IOC was changed from June 2016 to September 2016 to combine the GMLRS production contract award with a substantial FMS buy. The synergy of this contract action results in unit cost benefits, increasing U.S. Army rocket quantities by 40% for the same total budget. This allows the Army to achieve IOC with required quantities three months prior to the objective IOC date.
Acronyms and Abbreviations
DPICM - Dual Purpose Improved Conventional Munition

## Table 11
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
DPICM
Range
Max (Km)
70 | 70 | 60 | 73 | 70
Min (Km)
10 | 10 | 15 | 15 | 10
Effectiveness
(Expected Fractional Damage [EFD])
30% | 30% | 30% | 30% | 30%
Reliability
0.95 | 0.95 | 0.92 | 0.88 | 0.92
Hazardous Dud Rate
0 | 0% | 2%/4% | 1.71%/3.75% | 1.71%/3.75%
UNITARY
Range
Max (Km)
70 | 70 | 60 | 70 | 70
Min (Km)
10 | 10 | 15 | 15 | 15
Effectiveness
30% | 30% | Functional Kill | Meets Threshold | 30%
Reliability
0.95 | 0.95 | 0.92 | 0.94 | 0.92
Alternative Warhead
Range
Max (Km)
N/A | 70 | 60 | 70 | 70
Min (Km)
N/A | 10 | 15 | 15 | 15
Effectiveness
N/A | 30% | Functional Kill | Meets Threshold | Meets Threshold
(Ch-1)

## Table 12
Reliability
N/A | 0.95 | 0.92 | 0.99 | 0.99
Hazardous Dud Rate
N/A | 0% | <1% | 0% | 0%
Requirements Reference
ORD dated November 14, 2003 (includes Dual Purpose Improved Conventional Munitions), Multiple Launch Rocket System Guided Unitary Rocket ORD dated May 16, 2007 (in lieu of CPD), and GMLRS System Alternative Warhead Increment III CDD dated November 8, 2011
Change Explanations
(Ch-1) The Current Estimate for GMLRS AW Effectiveness changed from 30% to Meets Threshold due to demonstrated results achieved during EMD.
Notes
The GMLRS DPICM Demonstrated Performance in Reliability is 0.88. The GMLRS Reliability Working Group conducted a GMLRS DPICM Reliability Scoring Conference on August 18, 2014. The GMLRS DPICM Reliability was assessed at 0.88 (120 Flight Successes of 137 Attempts).
The GMLRS Unitary Demonstrated Performance in Reliability is 0.94. The GMLRS Reliability Working Group conducted a GMLRS Unitary Reliability Scoring Conference on July 15, 2015. The GMLRS Unitary Reliability was assessed at 0.94 (149 Flight Successes of 158 Attempts).
The GMLRS AW PQT Phase I Reliability was assessed at 1.0 (17 Flight Successes of 17 Attempts). The
program completed PQT Phase II - Developmental Test/Operational Test Ground, flight phase and the assessed reliability is 1.0 (15 Flight Successes of 15 Attempts), the GMLRS AW Production Verification Test flight phase and the assessed reliability is 1.0 (six Flight Successes of six Attempts). The program has completed the Initial Operational Test and Evaluation with an assessed reliability of 0.97 (29 Flight Successes of 30 Attempts). GMLRS AW test program achieved an overall reliability of 0.99 (74 flight successes of 75 attempts). This completes the GMLRS AW test phase.
Acronyms and Abbreviations
DPICM - Dual Purpose Improved Conventional Munitions Max (Km) - Maximum Kilometers
Min (Km) - Minimum Kilometers PQT - Production Qualification Test

## Table 13
Track to Budget
RDT&E
Appn |  | BA | PE
Army | 2040 07 |  | 0205778A
| Project |  |  | Name
| EG2 EG3 |  | GMLRS AW GMLRS |  | (Shared) | (Sunk)
Army | 2040 07 |  | 0603778A
| Project |  |  | Name
| 784 78G |  | GMLRS GMLRS AW |  |  | (Sunk) (Sunk)
Procurement
Appn |  | BA | PE
Army | 2032 07 |  | 0210602A
| Line Item |  | Name
| C65404 C65406 |  | GMLRS (Army) GMLRS (Army)
Notes
Line Item C64400 is the parent line for Line Items C65404 and C65406.

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2003 $M | [5 empty] | BY 2003 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 485.4 |  |  | 826.7 | 909.4 |  |  | 844.8 |  | 500.5 |  |  | 957.1 |  | 979.4
Procurement | 9294.8 |  |  | 4367.1 | 4803.8 |  |  | 4435.5 |  | 11348.4 |  |  | 5796.3 |  | 5854.6
Flyaway | -- |  |  | -- | -- |  |  | 4404.7 |  | -- |  |  | -- |  | 5818.8
Recurring | -- |  |  | -- | -- |  |  | 4244.9 |  | -- |  |  | -- |  | 5604.3
Non Recurring | -- |  |  | -- | -- |  |  | 159.8 |  | -- |  |  | -- |  | 214.5
Support | -- |  |  | -- | -- |  |  | 30.8 |  | -- |  |  | -- |  | 35.8
Other Support | -- |  |  | -- | -- |  |  | 28.6 |  | -- |  |  | -- |  | 33
Initial Spares | -- |  |  | -- | -- |  |  | 2.2 |  | -- |  |  | -- |  | 2.8
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 9780.2 |  |  | 5193.8 | N/A |  |  | 5280.3 |  | 11848.9 |  |  | 6753.4 |  | 6834
Current APB Cost Estimate Reference
GMLRS Alternative Warhead (AW) Army Cost Position dated April 14, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The confidence level used in establishing the cost estimate for GMLRS/GMLRS AW is 50% based on standard Department of the Army costing policy.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 235 |  |  |  | 376 |  |  |  |  | 376
Procurement |  | 140004 |  |  |  | 43560 |  |  |  |  | 43560
Total |  | 140239 |  |  |  | 43936 |  |  |  |  | 43936

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 778.1 | 36.7 |  |  | 22 | 30.2 | 29.7 |  | 28 |  |  | 27 |  | 27.7 |  | 979.4
Procurement | 2745.7 | 251 |  |  | 248.1 | 260.7 | 205.4 |  | 287.3 |  |  | 266 |  | 1590.4 |  | 5854.6
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0
PB 2017 Total | 3523.8 | 287.7 |  |  | 270.1 | 290.9 | 235.1 |  | 315.3 |  |  | 293 |  | 1618.1 |  | 6834
PB 2016 Total | 3525.5 | 268.5 |  |  | 183.2 | 200.5 | 234.4 |  | 256.6 |  |  | 387.3 |  | 1961.3 |  | 7017.3
Delta | -1.7 | 19.2 |  |  | 86.9 | 90.4 | 0.7 |  | 58.7 |  |  | -94.3 |  | -343.2 |  | -183.3
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 376 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 376
Production | 0 |  | 22458 |  | 1866 | 1766 | 1836 |  | 1296 | 1998 |  | 1776 |  | 10564 |  | 43560
PB 2017 Total | 376 |  | 22458 |  | 1866 | 1766 | 1836 |  | 1296 | 1998 |  | 1776 |  | 10564 |  | 43936
PB 2016 Total | 376 |  | 22338 |  | 1746 | 888 | 1002 |  | 1278 | 1470 |  | 2622 |  | 12216 |  | 43936
Delta | 0 |  | 120 |  | 120 | 878 | 834 |  | 18 | 528 |  | -846 |  | -1652 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.6
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.7
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.8
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.6
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.4
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 90
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 98.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.7
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.7
Subtotal |  | 376 | -- |  | -- |  | -- |  | -- |  | -- |  | 979.4

## Table 17
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.3
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.4
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.6
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.8
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.9
Subtotal |  | 376 | -- |  | -- |  | -- |  | -- |  | -- |  | 844.8

## Table 18
Annual Funding 2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | 822 | 110.4 |  | -- |  | 13.1 |  | 123.5 |  | 6.6 |  | 130.1
2004 |  | 683 | 97.2 |  | -- |  | 7 |  | 104.2 |  | 4.8 |  | 109
2005 |  | 954 | 96.9 |  | -- |  | 3.7 |  | 100.6 |  | 11.3 |  | 111.9
2006 |  | 984 | 119.8 |  | -- |  | 0.3 |  | 120.1 |  | 1.5 |  | 121.6
2007 |  | 925 | 123.4 |  | -- |  | 0.9 |  | 124.3 |  | 0.7 |  | 125
2008 |  | 2070 | 241.8 |  | -- |  | 20.8 |  | 262.6 |  | 1.1 |  | 263.7
2009 |  | 2646 | 298.7 |  | -- |  | 10.1 |  | 308.8 |  | 0.4 |  | 309.2
2010 |  | 3228 | 343.7 |  | -- |  | -- |  | 343.7 |  | 0.4 |  | 344.1
2011 |  | 2442 | 264.1 |  | -- |  | -- |  | 264.1 |  | 0.4 |  | 264.5
2012 |  | 2940 | 332.8 |  | -- |  | -- |  | 332.8 |  | 0.4 |  | 333.2
2013 |  | 1824 | 232.9 |  | -- |  | -- |  | 232.9 |  | 0.4 |  | 233.3
2014 |  | 2166 | 269.6 |  | -- |  | 3 |  | 272.6 |  | 0.4 |  | 273
2015 |  | 774 | 120 |  | -- |  | 6.7 |  | 126.7 |  | 0.4 |  | 127.1
2016 |  | 1866 | 232.8 |  | -- |  | 16.2 |  | 249 |  | 2 |  | 251
2017 |  | 1766 | 239.8 |  | -- |  | 7.8 |  | 247.6 |  | 0.5 |  | 248.1
2018 |  | 1836 | 251.7 |  | -- |  | 8.5 |  | 260.2 |  | 0.5 |  | 260.7
2019 |  | 1296 | 194.9 |  | -- |  | 10 |  | 204.9 |  | 0.5 |  | 205.4
2020 |  | 1998 | 275.6 |  | -- |  | 11.2 |  | 286.8 |  | 0.5 |  | 287.3
2021 |  | 1776 | 248.8 |  | -- |  | 16.7 |  | 265.5 |  | 0.5 |  | 266
2022 |  | 1794 | 254.1 |  | -- |  | 17.8 |  | 271.9 |  | 0.5 |  | 272.4
2023 |  | 2646 | 357.6 |  | -- |  | 17.3 |  | 374.9 |  | 0.5 |  | 375.4
2024 |  | 2568 | 356.3 |  | -- |  | 17.3 |  | 373.6 |  | 0.5 |  | 374.1
2025 |  | 1986 | 296.9 |  | -- |  | 14.6 |  | 311.5 |  | 0.5 |  | 312
2026 |  | 1570 | 240.9 |  | -- |  | 11.5 |  | 252.4 |  | 0.5 |  | 252.9
2027 |  | -- | -- |  | 3.6 |  | -- |  | 3.6 |  | -- |  | 3.6
Subtotal |  | 43560 | 5600.7 |  | 3.6 |  | 214.5 |  | 5818.8 |  | 35.8 |  | 5854.6

## Table 19
Annual Funding 2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2003 |  | 822 | 106.1 |  | -- |  | 12.6 |  | 118.7 |  | 6.3 |  | 125
2004 |  | 683 | 90.9 |  | -- |  | 6.6 |  | 97.5 |  | 4.5 |  | 102
2005 |  | 954 | 88.2 |  | -- |  | 3.4 |  | 91.6 |  | 10.2 |  | 101.8
2006 |  | 984 | 106.7 |  | -- |  | 0.3 |  | 107 |  | 1.3 |  | 108.3
2007 |  | 925 | 107.8 |  | -- |  | 0.8 |  | 108.6 |  | 0.6 |  | 109.2
2008 |  | 2070 | 208 |  | -- |  | 17.9 |  | 225.9 |  | 0.9 |  | 226.8
2009 |  | 2646 | 253.7 |  | -- |  | 8.6 |  | 262.3 |  | 0.3 |  | 262.6
2010 |  | 3228 | 287 |  | -- |  | -- |  | 287 |  | 0.3 |  | 287.3
2011 |  | 2442 | 216.7 |  | -- |  | -- |  | 216.7 |  | 0.3 |  | 217
2012 |  | 2940 | 269.1 |  | -- |  | -- |  | 269.1 |  | 0.3 |  | 269.4
2013 |  | 1824 | 184.3 |  | -- |  | -- |  | 184.3 |  | 0.3 |  | 184.6
2014 |  | 2166 | 211.3 |  | -- |  | 2.4 |  | 213.7 |  | 0.3 |  | 214
2015 |  | 774 | 92.8 |  | -- |  | 5.1 |  | 97.9 |  | 0.3 |  | 98.2
2016 |  | 1866 | 176.6 |  | -- |  | 12.3 |  | 188.9 |  | 1.5 |  | 190.4
2017 |  | 1766 | 178.5 |  | -- |  | 5.8 |  | 184.3 |  | 0.4 |  | 184.7
2018 |  | 1836 | 183.7 |  | -- |  | 6.2 |  | 189.9 |  | 0.4 |  | 190.3
2019 |  | 1296 | 139.5 |  | -- |  | 7.1 |  | 146.6 |  | 0.4 |  | 147
2020 |  | 1998 | 193.3 |  | -- |  | 7.9 |  | 201.2 |  | 0.4 |  | 201.6
2021 |  | 1776 | 171.1 |  | -- |  | 11.6 |  | 182.7 |  | 0.3 |  | 183
2022 |  | 1794 | 171.3 |  | -- |  | 12.1 |  | 183.4 |  | 0.3 |  | 183.7
2023 |  | 2646 | 236.4 |  | -- |  | 11.5 |  | 247.9 |  | 0.3 |  | 248.2
2024 |  | 2568 | 230.9 |  | -- |  | 11.3 |  | 242.2 |  | 0.3 |  | 242.5
2025 |  | 1986 | 188.7 |  | -- |  | 9.2 |  | 197.9 |  | 0.3 |  | 198.2
2026 |  | 1570 | 150.1 |  | -- |  | 7.1 |  | 157.2 |  | 0.3 |  | 157.5
2027 |  | -- | -- |  | 2.2 |  | -- |  | 2.2 |  | -- |  | 2.2
Subtotal |  | 43560 | 4242.7 |  | 2.2 |  | 159.8 |  | 4404.7 |  | 30.8 |  | 4435.5

## Table 20
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2003-03-24 | 2013-01-07
Approved Quantity | 13998 | 4445
Reference | Milestone C ADM (DPICM) | Acquisition Strategy (AW)
Start Year | 2003 | 2003
End Year | 2005 | 2015
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the summation of 1,961 GMLRS Dual Purpose Improved Conventional Munition (DPICM) Rockets plus 2,484 GMLRS Unitary Rockets.
The GMLRS DPICM Milestone C ADM, approved on March 24, 2003, authorized LRIP quantity not to exceed 13,998 rockets.
This quantity was based on the Army Acquisition Objective of 140,004 rockets. The actual GMLRS DPICM LRIP quantity is 1,961 rockets.
The GMLRS Unitary Milestone C ADM, signed May 2, 2007, authorized the LRIP quantity not to exceed 3,480 rockets based on the total expected procurement quantity of 34,848. The actual GMLRS LRIP quantity is 2,484 rockets.
The GMLRS AW Milestone B ADM was signed on February 19, 2012, and approved an LRIP quantity of 498 rockets. However, the Aquisition Strategy for GMLRS AW, signed on January 7, 2013, states the program will conduct the Inital Operational Test and Evaluation (IOT&E) during the EMD phase and combine Milestone C with the FRP Decision Review. Therefore, no LRIP is needed. Necessary assets will be procured to support IOT&E during EMD.

## Table 21
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Finland | 2016-02-10 | 25 | 28.7 | GMLRS AW rockets. Case ID FI-B-VAP
Finland | 2016-02-10 | 15 | 17.7 | Case ID FI-B-VAQ
Jordan | 2016-01-14 | 24 | 28.9 | GMLRS AW rockets. Case ID JO-B-YAY
United Arab Emirates | 2015-03-12 | 65 | 83.5 | Case ID AE-B-ZVE
Bahrain | 2014-06-30 | 4 | 5.3 | Case ID BA-B-UIW
Singapore | 2014-02-28 | 58 | 54.8 | Case ID SN-B-VFM
Italy | 2012-12-05 | 25 | 18.6 | International Cooperative Program. Agreement Number GIPR004IT
Singapore | 2012-03-26 | 12 | 10.1 | Case ID SN-B-VET
Italy | 2011-11-30 | 11 | 7.8 | International Cooperative Program. Agreement Number GIPR001IT
Japan | 2011-05-01 | 28 | 22.5 | Case ID JA-B-XIJ
Singapore | 2011-02-25 | 14 | 10.2 | Case ID SN-N-VEN
Germany | 2010-11-24 | 2 | 1.3 | International Cooperative Program. Agreement Number GIPR010GE
United Kingdom | 2010-02-01 | 72 | 48.9 | International Cooperative Program. Agreement Number GIPR011UK
Jordan | 2010-01-27 | 72 | 58.8 | Case ID JO-B-WYB
France | 2009-12-04 | 43 | 33.8 | International Cooperative Program. Agreement Number GIPR004FR
Germany | 2009-06-01 | 20 | 13.6 | International Cooperative Program. Agreement Number GIPR009GE
Japan | 2009-02-01 | 30 | 22.7 | Case ID JA-B-XGH
United Kingdom | 2009-01-12 | 50 | 31.5 | International Cooperative Program. Agreement Number GIPR008UK
France | 2008-12-18 | 2 | 1.4 | International Cooperative Program. Agreement Number GIPR002FR
United Kingdom | 2008-12-05 | 168 | 105.8 | International Cooperative Program. Agreement Number GIPR007UK
Germany | 2008-10-15 | 35 | 24.5 | International Cooperative Program. Agreement Number GIPR006GE
United Kingdom | 2008-07-25 | 75 | 48.5 | International Cooperative Program. Agreement Number GIPR003UK
Germany | 2007-12-31 | 13 | 9.4 | International Cooperative Program. Agreement Number GIPR001GE
Singapore | 2007-12-05 | 18 | 15 | Case ID SN-B-VDO
United Arab Emirates | 2007-08-01 | 130 | 98.6 | DPICM and Unitary rockets. Case ID AE-B-ZUD
United Kingdom | 2005-08-15 | 109 | 67.7 | International Cooperative Program. Agreement Number GIPR001UK
Notes
All quantities are listed as rocket pods. The rocket pod refers to the Rocket Pod Container that consists of six guided

## Table 22
rockets.
The Multiple Launch Rocket System (MLRS) was cooperatively developed under a Memorandum of Understanding (MOU) partnership between France, Germany, Italy, the United Kingdom (UK), and the U.S. The baseline design for the GMLRS rocket was developed under the terms and conditions of the MLRS MOU.
The baseline design was the M30 GMLRS Dual Purpose Improved Conventional Munition (DPICM) rocket pod. Only the
U.S. and the United Arab Emirates (UAE) have procured and continue to maintain stockpiles of M30 GMLRS DPICM pods. Two variants of the M30 GMLRS DPICM pod have since been developed by the U.S. Army, the M31A1 GMLRS Unitary and M30E1 GMLRS AW. The following nations have procured and continue to maintain stockpiles of M31A1 GMLRS Unitary pods: Bahrain, France, Germany, Italy, Japan, Jordan, Singapore, UAE, and UK.
Jordan and Finland will procure and maintain stockpiles of M30E1 GMLRS AW.
Nuclear Costs
None

## Table 23
Unit Cost
Unit Cost Report
Item |  | BY 2003 $M | BY 2003 $M |  | % Change
|  | Current UCR Baseline (May 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 5193.8 |  |  | 5280.3
Quantity | 43936 |  |  | 43936
Unit Cost | 0.118 |  |  | 0.12 |  |  | 1.69
Average Procurement Unit Cost
Cost | 4367.1 |  |  | 4435.5
Quantity | 43560 |  |  | 43560
Unit Cost | 0.1 |  |  | 0.102 |  |  | 2
Item |  | BY 2003 $M | BY 2003 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Jun 2007 APB)
Program Acquisition Unit Cost
Cost | 4578.4 |  |  | 5280.3
Quantity | 43795 |  |  | 43936
Unit Cost | 0.105 |  |  | 0.12 |  | 14.29
Average Procurement Unit Cost
Cost | 3966.7 |  |  | 4435.5
Quantity | 43560 |  |  | 43560
Unit Cost | 0.091 |  |  | 0.102 |  | 12.09
The GMLRS hardware will maintain approximately 80 percent commonality, regardless of which warhead is integrated into the systems. Consequently, changes in cost of any variant will directly affect the APUCs and PAUCs of the others.
The split-out APUC and PAUC of the GMLRS variants are:
GMLRS DPICM APUC ($0.133M (BY$ 2003); Quantity (Qty) = 2,472) GMLRS UNITARY APUC ($0 .098M (BY$ 2003); Qty = 22,506) GMLRS AW APUC ($0.102M (BY$ 2003); Qty = 18,582)
GMLRS DPICM PAUC ($0.189M (BY$ 2003); Qty = 2,565) GMLRS UNITARY PAUC ($0.112M (BY$ 2003); Qty = 22,684) GMLRS AW PAUC ($0.110M (BY$ 2003); Qty = 18,723)
All GMLRS variants benefit from the RDT&E future system enhancements (insensitive munitions, obsolescence, cost reduction initiatives), therefore an artificial pro-rating would have to be made to include them in the split-out PAUCs
above. The split-out PAUCs exclude the funding for these future enhancements; these dollars are included in the composite

## Table 24
PAUC shown in the Unit Cost section.

## Table 25
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2003 $M | [7 empty] | TY $M
[12 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Mar 1998 | [6 empty] | 0.034 |  |  |  |  | 0.032 |  |  |  | 0.039 |  |  |  | 0.037
APB as of January 2006 |  |  |  |  | May 2003 | [6 empty] | 0.07 |  |  |  |  | 0.066 |  |  |  | 0.084 |  |  |  | 0.081
Revised Original APB |  |  |  |  | Jun 2007 | [6 empty] | 0.105 |  |  |  |  | 0.091 |  |  |  | 0.133 |  |  |  | 0.119
Prior APB |  |  |  |  | Feb 2012 | [6 empty] | 0.116 |  |  |  |  | 0.099 |  |  |  | 0.146 |  |  |  | 0.127
Current APB |  |  |  |  | May 2015 | [6 empty] | 0.118 |  |  |  |  | 0.1 |  |  |  | 0.154 |  |  |  | 0.133
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 0.122 |  |  |  |  | 0.104 |  |  |  | 0.16 |  |  |  | 0.139
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 0.12 |  |  |  |  | 0.102 |  |  |  | 0.156 |  |  |  | 0.134
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  | Spt |  |  | Total
0.039 -0.003 0.001 0.001 0.009 0.037 0.000 0.000 0.045 0.084
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth |  | Spt |  |  | Total
0.084 0.012 -0.012 0.034 0.000 0.038 0.000 0.000 0.072 0.156

## Table 26
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [10 empty] | APUC Production Estimate
| Econ |  | Qty |  | Sch | Eng |  | Est | Oth | Spt | Total
0.037 -0.003 0.004 0.001 0.006 0.036 0.000 0.000 0.044 0.081
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch | Eng |  | Est | Oth | Spt | Total
0.081 0.012 -0.025 0.035 0.000 0.031 0.000 0.000 0.053 0.134
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone II |  |  |  | N/A |  |  | Mar 1998 |  |  | Mar 1998 |  |  | Jul 1998
Milestone C |  |  |  | N/A |  |  | Oct 2003 |  |  | Mar 2003 |  |  | Mar 2003
IOC |  |  |  | N/A |  |  | Apr 2004 |  |  | Nov 2006 |  |  | Dec 2005
Total Cost (TY $M) |  |  |  | N/A |  |  | 1688.6 |  |  | 11848.9 |  |  | 6834
Total Quantity |  |  |  | N/A |  |  | 43182 |  |  | 140239 |  |  | 43936
PAUC |  |  |  | N/A |  |  | 0.039 |  |  | 0.084 |  |  | 0.156
The Milestone C and IOC reported above reflect the GMLRS Dual Purpose Improved Conventional Munition
variant. Milestone C for the GMLRS Unitary variant was approved May 2007. Milestone C for the GMLRS AW variant was approved May 2015.

## Table 27
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 500.5 | 11348.4 | -- | 11848.9
Previous Changes
Economic | 6.6 | 545.9 | -- | 552.5
Quantity | 196 | -8922.7 | -- | -8726.7
Schedule | -9.1 | 1558.8 | -- | 1549.7
Engineering | -- | 10.8 | -- | 10.8
Estimating | 263.1 | 1507.8 | -- | 1770.9
Other | -- | -- | -- | --
Support | -- | 11.2 | -- | 11.2
Subtotal | 456.6 | -5288.2 | -- | -4831.6
Current Changes
Economic | -2.2 | -29.2 | -- | -31.4
Quantity | -- | -- | -- | --
Schedule | -- | -38.5 | -- | -38.5
Engineering | -- | -- | -- | --
Estimating | 24.5 | -138.6 | -- | -114.1
Other | -- | -- | -- | --
Support | -- | 0.7 | -- | 0.7
Subtotal | 22.3 | -205.6 | -- | -183.3
Total Changes | 478.9 | -5493.8 | -- | -5014.9
CE - Cost Variance | 979.4 | 5854.6 | -- | 6834
CE - Cost & Funding | 979.4 | 5854.6 | -- | 6834

## Table 28
Summary BY 2003 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 485.4 | 9294.8 | -- | 9780.2
Previous Changes
Economic | -- | -- | -- | --
Quantity | 159 | -5929.7 | -- | -5770.7
Schedule | -5.1 | 241.7 | -- | 236.6
Engineering | -- | 8.5 | -- | 8.5
Estimating | 187.4 | 902.3 | -- | 1089.7
Other | -- | -- | -- | --
Support | -- | 9.8 | -- | 9.8
Subtotal | 341.3 | -4767.4 | -- | -4426.1
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 18.1 | -92.2 | -- | -74.1
Other | -- | -- | -- | --
Support | -- | 0.3 | -- | 0.3
Subtotal | 18.1 | -91.9 | -- | -73.8
Total Changes | 359.4 | -4859.3 | -- | -4499.9
CE - Cost Variance | 844.8 | 4435.5 | -- | 5280.3
CE - Cost & Funding | 844.8 | 4435.5 | -- | 5280.3
Previous Estimate: December 2014

## Table 29
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -2.2
Adjustment for current and prior escalation. (Estimating) +0.6 +0.8
Contract award delay for Insensitve Munitions (IM) resulted in adjustment to funding. (Estimating)
-5.7 -7.5
Revised funding to adjust for IM activities that were previously delayed. (Estimating) +23.2 +31.2
RDT&E Subtotal +18.1 +22.3
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -29.2
Adjustment for current and prior escalation. (Estimating) +3.9 +4.8
Acceleration of procurement buy profile from FY 2015 to FY 2020 due to funding realignment which has provided resources needed to procure rockets at a more economic rate. (Schedule)
0.0 -38.5
Adjusted funding to align with the Milestone C/FRP APB. (Estimating) -71.5 -108.3
Due to additional Overseas Contingency Operations funding and quantities in FY 2017, the production schedule will be shortened by one year from FY 2027 to FY 2026, and the total non-end item recurring flyaway costs will be reduced. (Estimating)
-24.6 -35.1
Adjustment for current and prior escalation. (Support) -0.1 +0.1
Increase in Other Support for additional engineering support costs associated with the second IM vendor. (Support)
+0.6 +1.0
Decrease in Initial Spares due to revised cost estimate. (Support) | -0.2 |  |  | -0.4
Procurement Subtotal | -91.9 |  |  | -205.6

## Table 30
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: GMLRS FRP VI
Contractor: Lockheed Martin Missiles and Fire Control - Dallas
Contractor Location: 1701 W Marshall Drive
Grand Prairie, TX 75051-0000
Contract Number: W31P4Q-11-C-0166
Contract Type: Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF)
Award Date: June 10, 2011
Definitization Date: June 10, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
445.4 N/A 4440 483.7 N/A 4704 483.7 483.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to options exercised, change order incorporations, and negotiated reopener clauses.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP/CPFF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost or incentive portion does not meet the threshold requirements for earned value management reporting. The CPFF portion of this contract has a total value of
$9.599M.

## Table 31
Contract Identification
Appropriation: Procurement
Contract Name: GMLRS FRP VII
Contractor: Lockheed Martin Missiles and Fire Control - Dallas
Contractor Location: 1701 W Marshall Drive
Grand Prairie, TX 75051-0000
Contract Number: W31P4Q-12-C-0151
Contract Type: Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF)
Award Date: June 29, 2012
Definitization Date: June 29, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
353.2 N/A 3306 553.6 N/A 5550 553.6 553.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to option exercises, change order incorporations, and negotiated reopener clauses.
Contract Variance
Item |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances 0.0 0.0
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost or incentive portion does not meet the threshold requirements for earned value management reporting. The CPFF portion of this contract had a total value of
$13.6M.
Notes
FRP VIII is an option modification to FRP VII, which was awarded December 2012.

## Table 32
Contract Identification
Appropriation: RDT&E
Contract Name: AW EMD
Contractor: Lockheed Martin Missiles and Fire Control - Dallas
Contractor Location: 1701 W Marshal Drive
Grand Prairie, TX 75051-0000
Contract Number: W31P4Q-12-C-0121
Contract Type: Firm Fixed Price (FFP)
Award Date: March 30, 2012
Definitization Date: March 30, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
25.0 N/A N/A 105.9 N/A N/A 105.9 104.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to option exercises, change order incorporations, and negotiated reopener clauses.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 33
Contract Identification
Appropriation: Procurement
Contract Name: GMLRS FRP IX
Contractor: Lockheed Martin Missiles and Fire Control - Dallas
Contractor Location: 1701 W Marshall Drive
Grand Prairie, TX 75051-0000
Contract Number: W31P4Q-14-C-0066
Contract Type: Cost Plus Fixed Fee (CPFF), Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 20, 2013
Definitization Date: December 01, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor |  | Program Manager
255.1 N/A 1824 296.5 303.9 2922 296.5 296.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to to the increase in quantities, adding Singapore FMS requirements and adding additional scope.
Contract Variance
Item |  |  |  | Cost Variance |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances 0.0 0.0
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost or incentive portion does not meet the threshold requirements for earned value management reporting. The CPFF portion of this contract has a total value
of $5.2M.
An EVM wavier was signed on February 6, 2015 by the Army Acquisition Executive for FRP IX and FRP X.

## Table 34
Notes
Originally, the GMLRS FRP IX contract was executed on December 20, 2013, as an Undefinitized Contract Action in the Not to Exceed (NTE) amount of $255.1M and awarded for GMLRS Unitary plus Low Cost Reduced Range Practice Rocket requirements for the Army, Marine Corps, and Italy. The new NTE includes increased quantities, Singapore requirements and additional scope.
Delays in the definitization of FRP IX contract was due to OSD and Army policy changes, OSD/ Army Peer Reviews, change in contract type from FFP to FPIF, Army Contracting Command personnel shortages, and contractors taking longer to respond to contract changes. Negotiations started in April 2015 and issues with the contractor actuals and sub- contractor’s price increased the timeline. Negotiations were settled in October 2015 and definitization was accomplished in December 2015.

## Table 35
Contract Identification
Appropriation: Procurement
Contract Name: GMLRS FRP X
Contractor: Lockheed Martin Missiles and Fire Control - Dallas
Contractor Location: 1701 W Marshall Drive
Grand Prairie, TX 75051-0000
Contract Number: W31P4Q-15-C-0103
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Cost Plus Fixed Fee (CPFF)
Award Date: June 04, 2015
Definitization Date:
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
226.9 N/A 924 230.6 N/A 924 230.6 230.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to to the increase in Low Cost Reduced Range Practice Rocket pod quantities for the Army.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF/CPFF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost or incentive portion does not meet the threshold requirements for earned value management reporting. The CPFF portion of this contract has a value of $7.6M.
An EVM wavier was signed on February 6, 2015 by the Army Acquisition Executive for FRP IX and FRP X.
Notes
This is the first time this contract is being reported.
The contract was executed June 4, 2015, as an Undefinitized Contract Action change order in the Not to Exceed (NTE) amount of $226.9M. The NTE was awarded for GMLRS AW plus Low Cost Reduced Range Practice Rocket requirements and Depot Spares for the Army, Marine Corps, Bahrain, and United Arab Emirates.
FRP X was originally combined with FRP IX and was de-coupled during OSD Peer Review. Additional delays in defintization were caused by changing contract type from Firm Fixed Price to Fixed Price Incentive Fee, Army Peer Reviews requirements, and Army Contracting Command personnel shortages. Definitization is scheduled for 2016.

## Table 36
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 376 | 376 | 376 | 100%
Production | 21060 | 21060 | 43560 | 48.35%
Total Program Quantity Delivered | 21436 | 21436 | 43936 | 48.79%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
6834
2775
40.61%
30
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
19
63.33%
3811.5
55.77%
The above data is current as of February 26, 2016.
The Expended to Date amount was inadvertently overstated in the 2014 SAR; it is correctly reported above.

## Table 37
Operating and Support Cost
Cost Estimate Details
Date of Estimate: November 06, 2015
Source of Estimate: POE
Quantity to Sustain: 7260
Unit of Measure: Rocket Pod
Service Life per Unit: 10.00 Years
Fiscal Years in Service: FY 2005 - FY 2036
The O&S Costs include all variants (GMLRS Dual Purpose Improved Conventional Munition (DPICM), Unitary, and AW). The rocket pod refers to the Rocket Pod Container that consists of six guided rockets with an expected service life of ten- years and procurement of 7,260 rocket pods (total of 43,560 rockets). The 376 RDT&E rockets are test articles and were consumed.
Sustainment Strategy
The Sustainment Strategy is two-level maintenance - field and sustainment. An organic depot capability was established for GMLRS DPICM and Unitary variants in 2nd Quarter FY 2009. This capability will be upgraded to incorporate GMLRS AW in 3rd Quarter FY 2016.
Antecedent Information
No Antecedent
Annual O&S Costs BY2003 $K
Cost Element | GMLRS/GMLRS AW Average Annual Cost Per Rocket Pod | No GMLRS Antecedent (Antecedent)
Unit-Level Manpower | 0.024 | --
Unit Operations | 0.021 | --
Maintenance | 0.859 | --
Sustaining Support | 1.943 | --
Continuing System Improvements | 0.116 | --
Indirect Support | 0 | --
Other | 0 | --
Total | 2.963 | --
The Cost Element Sustaining Support includes Missile Stockpile Reliability Certification, base operations, second destination transportation, System Engineering Program Management, and training. The Continuing System Improvements consists of software maintenance.

## Table 38
Item | Total O&S Cost $M
| GMLRS/GMLRS AW | [5 empty] | No GMLRS Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 204.8 |  | 225.3 |  |  | 215.1 | N/A
Then Year | 337 |  | N/A |  |  | 354.6 | N/A
Equation to Translate Annual Cost to Total Cost
Total O&S Cost = Average Annual Cost per Rocket Pod x Number of Rocket Pods x Life per Rocket Pod = $2.963K x 7260 Rocket Pods x 10 Years = $215.1M (BY 2003 $M)
O&S Cost Variance
Category |  | BY 2003 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
177.5
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 37.6 Cost were reallocated based on funding guidance interpretation during the Cost Review Board process regarding the Program Executive Group (PEG) for Stockpile reliability and training devices. (Previously these were costed under the Equipping PEG now moved to the Sustaining PEG).
Total Changes 37.6
Current Estimate 215.1
Disposal Estimate Details
Date of Estimate: November 06, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2003 $M): Total costs for disposal of all Rocket Pod are 41.3