## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-355
Joint Air-to-Ground Missile (JAGM)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 11
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 27
Foreign Military Sales 28
Nuclear Costs 28
Unit Cost 29
Cost Variance 32
Contracts 35
Deliveries and Expenditures 36
Operating and Support Cost 37

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Joint Air-to-Ground Missile (JAGM)
DoD Component
Army
Joint Participants
Navy
Responsible Office
COL James Romero
Joint Attack Munition Systems Project Office Building 5250 Martin Road
Redstone Arsenal, AL 35898
james.s.romero2.mil@mail.mil
Phone: | 256-876-1141
Fax: | 256-876-0865
DSN Phone: | 746-1141
DSN Fax: | 746-0865
Date Assigned: | July 12, 2012
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 29, 2015
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 29, 2015

## Table 6
Mission and Description
The Joint Air-to-Ground Missile (JAGM) program is an Army led MDAP with Joint interest with the U.S. Marine Corps and
U.S. Navy. The JAGM mission is to develop the next generation of aviation launched fire and forget missiles to replace the HELLFIRE laser and Longbow radar missiles. JAGM will be used by Joint service aircraft for destruction of high value stationary, moving and relocatable land and maritime targets from standoff range in day, night, adverse weather and obscured battlefield conditions.

## Table 7
Executive Summary
Program Highlights Since Last Report:
JAGM EMD phase activities include: qualifying the all-up round, qualifying the production line, qualifying JAGM on threshold platforms and completing operational test.
On January 26-28, 2016, the Joint Attack Munition Systems Project Office conducted a successful JAGM System Critical Design Review (CDR) / Initial Production Readiness Review. The JAGM CDR confirmed the system design is stable and is able to meet system performance requirements as evidenced by the detailed design documentation. The CDR also demonstrated the program is on track to achieve affordability, should cost goals, and establish the system’s initial product baseline. A Post-CDR Assessment Report is being developed by OSD which will provide an overall assessment of the review and technical risk.
On July 29, 2015, the USD(AT&L) signed the Milestone B ADM for the JAGM program and authorized entry into EMD as an ACAT ID program. The associated 2366b certification statement waived three certification components, namely 2366b(1) (B), 2366b(1)(D), and 2366b(2), having determined that the DoD would be unable to meet critical national security objectives without these waivers.
Waived Provision (1) 2366b(1)(B): Appropriate trade-offs among cost, schedule, and performance objectives have been made to ensure that the program is affordable when considering the per unit cost and the total acquisition cost in the context of the total resources available during the period covered by the FYDP submitted during the fiscal year in which
the certification is made; and
Waived Provision (2) 2366b(1)(D): Funding is available to execute the product development and production plan under the program, through the period covered by the FYDP submitted during the fiscal year in which the certification is made, consistent with the estimates described in paragraph (a)(1)(C) of the 2366b certification for the program.
The waivers of these two components were necessary because the FYDP submitted during the fiscal year in which the certification is made will not be submitted until February 2016 for this fiscal year.
Waived Provision (3) 2366b(2): The program received a preliminary design review and conducted a formal post-preliminary design review assessment and certifies on the basis of such assessment that the program demonstrates a high likelihood of accomplishing its intended mission.
Based on the maturity of the technology required for the JAGM, it is expected that the requisite technologies are sufficiently mature to proceed to EMD. A JAGM preliminary design review was not conducted prior to Milestone B. However, a critical design review is planned within six months of contract award, followed by the formal post review assessment. Based on this assessment, the final determination as to the program's likelihood of accomplishing its intended mission will be made.
The Department will continue to review the JAGM program at least annually until all waived certification provisions are satisfied.
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation:
On October 17, 2014, USD(AT&L) authorized the release of the final request for proposal for the JAGM EMD contract and LRIP options to include LRIP long lead items.
On July 31, 2015, Lockheed Martin was awarded the competitive JAGM EMD contract to develop the next generation of aviation launched missiles to replace the HELLFIRE laser and Longbow radar missiles.

## Table 8
On August 25, 2015, the Joint Attack Munition Systems Project Office, with support from the U.S. Army Aviation and Missile Research, Development and Engineering Center and Lockheed Martin, successfully conducted the third JAGM flight test at Eglin Air Force Base, Florida. The missile had a nominal launch and impacted and destroyed the target. The missile executed a Doppler Beam Sharpening trajectory, increasing the probability of hit against a difficult stationary target using the Active Fire and Forget. Among many firsts, this was the first test of JAGM using the Active Fire and Forget engagement mode and the first engagement of an armored vehicle.

## Table 9
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule
None
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | Jul 2015 | Jul 2015 | Jul 2015 | Jul 2015
CDR | Jan 2016 | Jan 2016 | Jul 2016 | Jan 2016
Milestone C | Jul 2017 | Jul 2017 | Jan 2018 | Jul 2017
Army IOC | Sep 2018 | Sep 2018 | Mar 2019 | Sep 2018
FRP Decision | Mar 2019 | Mar 2019 | Sep 2019 | Mar 2019
Navy IOC | Sep 2019 | Sep 2019 | Mar 2020 | Sep 2019
Change Explanations
Acronyms and Abbreviations
CDR - Critical Design Review

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Combat Effectiveness/Reliability
In-Flight Reliability (Post P-BIT Check)
0.92 (Initial fielding) 0.94 (System Maturity) | 0.92 (Initial fielding) 0.94 (System Maturity) | (T=O) 0.92 (Initial fielding) 0.94 (System Maturity) | TBD | 0.92 (Initial fielding) 0.94 (System Maturity)
Range
Minimum Engagement Range Rotary Wing (RW)
500 m | 500 m | (T=O) 500 m | TBD | 500 m
Maximum Range (RW)
Greater Than 8 km | Greater Than 8 km | 8 km | TBD | Greater Than 8 km
Interoperability
Interoperable with joint rotary and fixed wing (manned and unmanned) aircraft
AH-64D, AH-1Z | AH-64D, AH-1Z | (T=O) AH-64D, AH-1Z | TBD | AH-64D, AH-1Z
Laser Designation
Compatible with standard Joint aviation platform laser designation systems, including PRF and PIM codes | Compatible with standard Joint aviation platform laser designation systems, including PRF and PIM codes | (T=O) Compatible with standard Joint aviation platform laser designation systems, including PRF and PIM codes | TBD | Compatible with standard Joint aviation platform laser designation systems, including PRF and PIM codes
Carrier/Shipboard Operability
Compatible with carrier/shipboard operations without degrading other Naval operations
Yes | Yes | (T=O) Yes | TBD | Yes
Sustainability (Materiel Availability)
Percentage of missiles operationally capable of performing an assigned mission at a given time, based on materiel condition
0.90 (At initial fielding) 0.95 (At system maturity) | 0.90 (At initial fielding) 0.95 (At system maturity) | (T=O) 0.90 (At initial fielding) 0.95 (At system maturity) | TBD | 0.90 (At initial fielding) 0.95 (At system maturity)
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
JAGM CDD version 2.5, dated October 1, 2012 and approved January 17, 2013

## Table 12
Change Explanations
None
Notes
The JAGM Life Cycle Sustainment Plan defines system maturity as IOC plus two years.
Acronyms and Abbreviations
km - kilometer m - meter
P-BIT - Power-On Built In Test PIM - Pulse Interval Modulation PRF - Pulse Repetition Frequency T=O - Threshold equals Objective

## Table 13
Track to Budget
RDT&E
Appn | BA | PE
Navy 1319 05 0605450N
Project Name
2211 Joint Air-to-Ground Missile (JAGM) Army 2040 05 0605450A
Project Name
JA6 Joint Air-to-Ground Missile (JAGM)
Procurement
Appn | BA | PE
Navy 1507 02 0206138M
Line Item Name
2248 Joint Air-to-Ground Missile (JAGM) Army 2032 02
Line Item Name
C70302 Joint Air-to-Ground Missile (JAGM)

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2015 $M |  |  |  | BY 2015 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 978.5 |  | 978.5 | 1076.4 |  | 967.1 |  | 952.8 |  | 952.8 |  | 941.5
Procurement | 4691.4 |  | 4691.4 | 5160.5 |  | 4715.7 |  | 6371.7 |  | 6371.7 |  | 6195.4
Flyaway | -- |  | -- | -- |  | 4645.6 |  | -- |  | -- |  | 6106.8
Recurring | -- |  | -- | -- |  | 4627.5 |  | -- |  | -- |  | 6085.6
Non Recurring | -- |  | -- | -- |  | 18.1 |  | -- |  | -- |  | 21.2
Support | -- |  | -- | -- |  | 70.1 |  | -- |  | -- |  | 88.6
Other Support | -- |  | -- | -- |  | 69.8 |  | -- |  | -- |  | 88.3
Initial Spares | -- |  | -- | -- |  | 0.3 |  | -- |  | -- |  | 0.3
MILCON | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 5669.9 |  | 5669.9 | N/A |  | 5682.8 |  | 7324.5 |  | 7324.5 |  | 7136.9
Current APB Cost Estimate Reference
Director of CAPE (DCAPE) ICE dated July 17, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 50%
This estimate, like all previous OSD CAPE estimates, is built upon a product-oriented work breakdown structure; is based on historical actual cost information to the maximum extent possible; and, most importantly, is based on conservative assumptions that are consistent with actual demonstrated contractor and Government performance for a series of acquisition programs in which the Department was successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 15
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 118 | 118 | 118
Procurement | 26319 | 26319 | 26319
Total | 26437 | 26437 | 26437

## Table 16
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M | [14 empty] | )
Appropriation | Prior | FY | 2016 |  |  | FY 2017 | FY 2018 |  | FY 2019 |  |  | FY 2020 |  | FY | 2021 | To Complete |  |  |  | Total
RDT&E | 734 | 109 |  |  | 60.9 |  | 24.3 |  | 12.9 |  |  | 0.2 |  | 0.2 |  |  |  | 0 |  | 941.5
Procurement | 0 | 27.7 |  |  | 128.1 |  | 216.7 |  | 283.4 |  |  | 251.8 |  | 357.1 |  |  |  | 4930.6 |  | 6195.4
MILCON | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
PB 2017 Total | 734 | 136.7 |  |  | 189 |  | 241 |  | 296.3 |  |  | 252 |  | 357.3 |  |  |  | 4930.6 |  | 7136.9
| -- | -- |  |  | -- |  | -- |  | -- |  |  | -- |  | -- |  |  |  | -- |  | --
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [12 empty] | R (TY$ M)
Quantity | Undistribu | ted | P | rior |  | FY 2016 | FY 2017 | 2 |  | FY 018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 118 |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 118
Production | 0 |  | 0 |  |  | 0 | 420 |  |  | 600 |  | 1376 |  | 970 | 1565 |  | 21388 |  | 26319
PB 2017 Total | 118 |  | 0 |  |  | 0 | 420 |  |  | 600 |  | 1376 |  | 970 | 1565 |  | 21388 |  | 26437
| -- |  | -- |  |  | -- | -- |  |  | -- |  | -- |  | -- | -- |  | -- |  | --

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 51.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 114.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 86.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.5
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.9
Subtotal |  | 74 | -- |  | -- |  | -- |  | -- |  | -- |  | 687

## Table 18
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 123.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 126.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 78.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.4
Subtotal |  | 74 | -- |  | -- |  | -- |  | -- |  | -- |  | 704.4

## Table 19
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.8
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
Subtotal |  | 44 | -- |  | -- |  | -- |  | -- |  | -- |  | 254.5

## Table 20
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.8
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
Subtotal |  | 44 | -- |  | -- |  | -- |  | -- |  | -- |  | 262.7

## Table 21
Annual Funding 2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | 27.7 |  | -- |  | -- |  | 27.7 |  | -- |  | 27.7
2017 |  | 324 | 100.8 |  | -- |  | 1.1 |  | 101.9 |  | -- |  | 101.9
2018 |  | 496 | 186.5 |  | -- |  | 0.2 |  | 186.7 |  | 3.7 |  | 190.4
2019 |  | 1266 | 248 |  | -- |  | 4.6 |  | 252.6 |  | 6.5 |  | 259.1
2020 |  | 860 | 222.6 |  | -- |  | -- |  | 222.6 |  | 5 |  | 227.6
2021 |  | 1344 | 297.5 |  | -- |  | 4.8 |  | 302.3 |  | 5.1 |  | 307.4
2022 |  | 1000 | 219.1 |  | -- |  | -- |  | 219.1 |  | 3.9 |  | 223
2023 |  | 1000 | 214.2 |  | -- |  | -- |  | 214.2 |  | 3.6 |  | 217.8
2024 |  | 1000 | 213.3 |  | -- |  | -- |  | 213.3 |  | 3.7 |  | 217
2025 |  | 1000 | 212.1 |  | -- |  | -- |  | 212.1 |  | 3.7 |  | 215.8
2026 |  | 1000 | 211.3 |  | -- |  | 0.8 |  | 212.1 |  | 3.8 |  | 215.9
2027 |  | 1000 | 212.2 |  | -- |  | -- |  | 212.2 |  | 3.8 |  | 216
2028 |  | 1000 | 213.9 |  | -- |  | -- |  | 213.9 |  | 3.9 |  | 217.8
2029 |  | 1000 | 215 |  | -- |  | -- |  | 215 |  | 3.9 |  | 218.9
2030 |  | 1000 | 216.2 |  | -- |  | -- |  | 216.2 |  | 4 |  | 220.2
2031 |  | 1000 | 217.5 |  | -- |  | 0.9 |  | 218.4 |  | 4.1 |  | 222.5
2032 |  | 1000 | 221.3 |  | -- |  | -- |  | 221.3 |  | 4.1 |  | 225.4
2033 |  | 1000 | 223.6 |  | -- |  | -- |  | 223.6 |  | 0.7 |  | 224.3
2034 |  | 1000 | 226.7 |  | -- |  | -- |  | 226.7 |  | 0.7 |  | 227.4
2035 |  | 1000 | 230.5 |  | -- |  | 1 |  | 231.5 |  | 0.7 |  | 232.2
2036 |  | 1000 | 232.6 |  | -- |  | 0.4 |  | 233 |  | 0.7 |  | 233.7
2037 |  | 1013 | 234.3 |  | -- |  | 0.2 |  | 234.5 |  | 0.7 |  | 235.2
2038 |  | -- | 13.6 |  | -- |  | -- |  | 13.6 |  | -- |  | 13.6
Subtotal |  | 20303 | 4610.5 |  | -- |  | 14 |  | 4624.5 |  | 66.3 |  | 4690.8

## Table 22
Annual Funding 2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | 26.4 |  | -- |  | -- |  | 26.4 |  | -- |  | 26.4
2017 |  | 324 | 94.4 |  | -- |  | 1 |  | 95.4 |  | -- |  | 95.4
2018 |  | 496 | 171.2 |  | -- |  | 0.2 |  | 171.4 |  | 3.4 |  | 174.8
2019 |  | 1266 | 223.2 |  | -- |  | 4.1 |  | 227.3 |  | 5.9 |  | 233.2
2020 |  | 860 | 196.5 |  | -- |  | -- |  | 196.5 |  | 4.4 |  | 200.9
2021 |  | 1344 | 257.4 |  | -- |  | 4.2 |  | 261.6 |  | 4.4 |  | 266
2022 |  | 1000 | 185.9 |  | -- |  | -- |  | 185.9 |  | 3.3 |  | 189.2
2023 |  | 1000 | 178.1 |  | -- |  | -- |  | 178.1 |  | 3 |  | 181.1
2024 |  | 1000 | 173.9 |  | -- |  | -- |  | 173.9 |  | 3 |  | 176.9
2025 |  | 1000 | 169.5 |  | -- |  | -- |  | 169.5 |  | 3 |  | 172.5
2026 |  | 1000 | 165.6 |  | -- |  | 0.6 |  | 166.2 |  | 3 |  | 169.2
2027 |  | 1000 | 163 |  | -- |  | -- |  | 163 |  | 3 |  | 166
2028 |  | 1000 | 161.1 |  | -- |  | -- |  | 161.1 |  | 3 |  | 164.1
2029 |  | 1000 | 158.8 |  | -- |  | -- |  | 158.8 |  | 2.9 |  | 161.7
2030 |  | 1000 | 156.5 |  | -- |  | -- |  | 156.5 |  | 2.9 |  | 159.4
2031 |  | 1000 | 154.4 |  | -- |  | 0.6 |  | 155 |  | 2.9 |  | 157.9
2032 |  | 1000 | 154 |  | -- |  | -- |  | 154 |  | 2.9 |  | 156.9
2033 |  | 1000 | 152.5 |  | -- |  | -- |  | 152.5 |  | 0.5 |  | 153
2034 |  | 1000 | 151.6 |  | -- |  | -- |  | 151.6 |  | 0.5 |  | 152.1
2035 |  | 1000 | 151.1 |  | -- |  | 0.7 |  | 151.8 |  | 0.5 |  | 152.3
2036 |  | 1000 | 149.5 |  | -- |  | 0.3 |  | 149.8 |  | 0.4 |  | 150.2
2037 |  | 1013 | 147.7 |  | -- |  | 0.1 |  | 147.8 |  | 0.4 |  | 148.2
2038 |  | -- | 8.4 |  | -- |  | -- |  | 8.4 |  | -- |  | 8.4
Subtotal |  | 20303 | 3550.7 |  | -- |  | 11.8 |  | 3562.5 |  | 53.3 |  | 3615.8

## Table 23
The source for procurement quantity profile is the JAGM OSD CAPE ICE.
Cost Quantity Information 2032 ¦ Procurement ¦ Missile Procurement, Army
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2015 $M
2016 | -- | --
2017 | 324 | 120.8
2018 | 496 | 171.2
2019 | 1266 | 223.2
2020 | 860 | 196.5
2021 | 1344 | 257.4
2022 | 1000 | 185.9
2023 | 1000 | 178.1
2024 | 1000 | 173.9
2025 | 1000 | 169.5
2026 | 1000 | 165.6
2027 | 1000 | 163
2028 | 1000 | 161.1
2029 | 1000 | 158.8
2030 | 1000 | 156.5
2031 | 1000 | 154.4
2032 | 1000 | 154
2033 | 1000 | 152.5
2034 | 1000 | 151.6
2035 | 1000 | 151.1
2036 | 1000 | 149.5
2037 | 1013 | 156.1
2038 | -- | --
Subtotal | 20303 | 3550.7

## Table 24
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2017 |  | 96 | 24.8 |  | -- |  | 0.7 |  | 25.5 |  | 0.7 |  | 26.2
2018 |  | 104 | 24.7 |  | -- |  | 0.4 |  | 25.1 |  | 1.2 |  | 26.3
2019 |  | 110 | 22.6 |  | -- |  | 0.4 |  | 23 |  | 1.3 |  | 24.3
2020 |  | 110 | 22.8 |  | -- |  | 0.3 |  | 23.1 |  | 1.1 |  | 24.2
2021 |  | 221 | 45.9 |  | -- |  | 3.2 |  | 49.1 |  | 0.6 |  | 49.7
2022 |  | 200 | 48.9 |  | -- |  | 0.4 |  | 49.3 |  | 0.7 |  | 50
2023 |  | 210 | 50.3 |  | -- |  | 0.3 |  | 50.6 |  | 0.6 |  | 51.2
2024 |  | 219 | 51.8 |  | -- |  | 0.3 |  | 52.1 |  | 0.6 |  | 52.7
2025 |  | 330 | 73.8 |  | -- |  | 0.3 |  | 74.1 |  | 0.9 |  | 75
2026 |  | 330 | 73.6 |  | -- |  | 0.3 |  | 73.9 |  | 0.9 |  | 74.8
2027 |  | 330 | 74.1 |  | -- |  | 0.2 |  | 74.3 |  | 1 |  | 75.3
2028 |  | 330 | 74.7 |  | -- |  | 0.2 |  | 74.9 |  | 1 |  | 75.9
2029 |  | 330 | 75.4 |  | -- |  | 0.1 |  | 75.5 |  | 1 |  | 76.5
2030 |  | 330 | 76.2 |  | -- |  | 0.1 |  | 76.3 |  | 1 |  | 77.3
2031 |  | 330 | 77.1 |  | -- |  | -- |  | 77.1 |  | 1 |  | 78.1
2032 |  | 330 | 78.1 |  | -- |  | -- |  | 78.1 |  | 1 |  | 79.1
2033 |  | 330 | 79.2 |  | -- |  | -- |  | 79.2 |  | 1 |  | 80.2
2034 |  | 330 | 80.3 |  | -- |  | -- |  | 80.3 |  | 1.1 |  | 81.4
2035 |  | 330 | 81.5 |  | -- |  | -- |  | 81.5 |  | 1.1 |  | 82.6
2036 |  | 330 | 82.7 |  | -- |  | -- |  | 82.7 |  | 1.1 |  | 83.8
2037 |  | 330 | 83.9 |  | -- |  | -- |  | 83.9 |  | 1.1 |  | 85
2038 |  | 330 | 85 |  | -- |  | -- |  | 85 |  | 1.1 |  | 86.1
2039 |  | 126 | 86.5 |  | -- |  | -- |  | 86.5 |  | 1.2 |  | 87.7
2040 |  | -- | 1.2 |  | -- |  | -- |  | 1.2 |  | -- |  | 1.2
Subtotal |  | 6016 | 1475.1 |  | -- |  | 7.2 |  | 1482.3 |  | 22.3 |  | 1504.6

## Table 25
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 2015 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2017 |  | 96 | 23.3 |  | -- |  | 0.6 |  | 23.9 |  | 0.7 |  | 24.6
2018 |  | 104 | 22.7 |  | -- |  | 0.4 |  | 23.1 |  | 1.1 |  | 24.2
2019 |  | 110 | 20.4 |  | -- |  | 0.4 |  | 20.8 |  | 1.1 |  | 21.9
2020 |  | 110 | 20.2 |  | -- |  | 0.3 |  | 20.5 |  | 0.9 |  | 21.4
2021 |  | 221 | 39.8 |  | -- |  | 2.8 |  | 42.6 |  | 0.5 |  | 43.1
2022 |  | 200 | 41.6 |  | -- |  | 0.3 |  | 41.9 |  | 0.6 |  | 42.5
2023 |  | 210 | 41.9 |  | -- |  | 0.3 |  | 42.2 |  | 0.5 |  | 42.7
2024 |  | 219 | 42.3 |  | -- |  | 0.2 |  | 42.5 |  | 0.6 |  | 43.1
2025 |  | 330 | 59.1 |  | -- |  | 0.2 |  | 59.3 |  | 0.8 |  | 60.1
2026 |  | 330 | 57.8 |  | -- |  | 0.2 |  | 58 |  | 0.8 |  | 58.8
2027 |  | 330 | 57.1 |  | -- |  | 0.2 |  | 57.3 |  | 0.7 |  | 58
2028 |  | 330 | 56.4 |  | -- |  | 0.2 |  | 56.6 |  | 0.7 |  | 57.3
2029 |  | 330 | 55.8 |  | -- |  | 0.1 |  | 55.9 |  | 0.7 |  | 56.6
2030 |  | 330 | 55.3 |  | -- |  | 0.1 |  | 55.4 |  | 0.7 |  | 56.1
2031 |  | 330 | 54.9 |  | -- |  | -- |  | 54.9 |  | 0.7 |  | 55.6
2032 |  | 330 | 54.5 |  | -- |  | -- |  | 54.5 |  | 0.7 |  | 55.2
2033 |  | 330 | 54.2 |  | -- |  | -- |  | 54.2 |  | 0.6 |  | 54.8
2034 |  | 330 | 53.8 |  | -- |  | -- |  | 53.8 |  | 0.8 |  | 54.6
2035 |  | 330 | 53.6 |  | -- |  | -- |  | 53.6 |  | 0.7 |  | 54.3
2036 |  | 330 | 53.3 |  | -- |  | -- |  | 53.3 |  | 0.7 |  | 54
2037 |  | 330 | 53 |  | -- |  | -- |  | 53 |  | 0.7 |  | 53.7
2038 |  | 330 | 52.6 |  | -- |  | -- |  | 52.6 |  | 0.7 |  | 53.3
2039 |  | 126 | 52.5 |  | -- |  | -- |  | 52.5 |  | 0.8 |  | 53.3
2040 |  | -- | 0.7 |  | -- |  | -- |  | 0.7 |  | -- |  | 0.7
Subtotal |  | 6016 | 1076.8 |  | -- |  | 6.3 |  | 1083.1 |  | 16.8 |  | 1099.9

## Table 26
Cost Quantity Information 1507 ¦ Procurement ¦ Weapons Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2015 $M
2017 | 96 | 23.3
2018 | 104 | 22.7
2019 | 110 | 20.4
2020 | 110 | 20.2
2021 | 221 | 39.8
2022 | 200 | 41.6
2023 | 210 | 41.9
2024 | 219 | 42.3
2025 | 330 | 59.1
2026 | 330 | 57.8
2027 | 330 | 57.1
2028 | 330 | 56.4
2029 | 330 | 55.8
2030 | 330 | 55.3
2031 | 330 | 54.9
2032 | 330 | 54.5
2033 | 330 | 54.2
2034 | 330 | 53.8
2035 | 330 | 53.6
2036 | 330 | 53.3
2037 | 330 | 53
2038 | 330 | 52.6
2039 | 126 | 53.2
2040 | -- | --
Subtotal | 6016 | 1076.8

## Table 27
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2015-07-29 | 2015-07-29
Approved Quantity | 2631 | 2631
Reference | JAGM Milestone B ADM | JAGM Milestone B ADM
Start Year | 2017 | 2017
End Year | 2018 | 2018

## Table 28
Foreign Military Sales
None
Nuclear Costs
None

## Table 29
Unit Cost
Unit Cost Report
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Current UCR Baseline (Sep 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 5669.9 |  |  | 5682.8
Quantity | 26437 |  |  | 26437
Unit Cost | 0.214 |  |  | 0.215 |  | 0.47
Average Procurement Unit Cost
Cost | 4691.4 |  |  | 4715.7
Quantity | 26319 |  |  | 26319
Unit Cost | 0.178 |  |  | 0.179 |  | 0.56
Item |  | BY 2015 $M | BY 2015 $M |  | % Change
|  | Original UCR Baseline (Sep 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 5669.9 |  |  | 5682.8
Quantity | 26437 |  |  | 26437
Unit Cost | 0.214 |  |  | 0.215 |  | 0.47
Average Procurement Unit Cost
Cost | 4691.4 |  |  | 4715.7
Quantity | 26319 |  |  | 26319
Unit Cost | 0.178 |  |  | 0.179 |  | 0.56

## Table 30
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2015 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Sep 2015 |  |  |  |  | 0.214 |  |  | 0.178 |  |  | 0.277 |  |  | 0.242
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Sep 2015 |  |  |  |  | 0.214 |  |  | 0.178 |  |  | 0.277 |  |  | 0.242
Prior Annual SAR |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current Estimate |  |  | Dec 2015 |  |  |  |  | 0.215 |  |  | 0.179 |  |  | 0.27 |  |  | 0.235
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
0.277 -0.001 0.000 -0.008 0.000 0.001 0.000 0.001 -0.007 0.270
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
0.242 -0.001 0.000 -0.007 0.000 0.001 0.000 0.001 -0.006 0.235

## Table 31
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Jul 2015 | N/A | Jul 2015
Milestone C | N/A | Jul 2017 | N/A | Jul 2017
IOC | N/A | Sep 2018 | N/A | Sep 2018
Total Cost (TY $M) | N/A | 7324.5 | N/A | 7136.9
Total Quantity | N/A | 26437 | N/A | 26437
PAUC | N/A | 0.277 | N/A | 0.27

## Table 32
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 952.8 | 6371.7 | -- | 7324.5
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -- | -- | --
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -- | -- | --
Current Changes
Economic | 0.4 | -31.8 | -- | -31.4
Quantity | -- | -- | -- | --
Schedule | -- | -190.7 | -- | -190.7
Engineering | -- | -- | -- | --
Estimating | -11.7 | 30.8 | -- | 19.1
Other | -- | -- | -- | --
Support | -- | 15.4 | -- | 15.4
Subtotal | -11.3 | -176.3 | -- | -187.6
Total Changes | -11.3 | -176.3 | -- | -187.6
CE - Cost Variance | 941.5 | 6195.4 | -- | 7136.9
CE - Cost & Funding | 941.5 | 6195.4 | -- | 7136.9

## Table 33
Summary BY 2015 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 978.5 | 4691.4 | -- | 5669.9
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -- | -- | --
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -- | -- | --
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -13 | -- | -13
Engineering | -- | -- | -- | --
Estimating | -11.4 | 22.9 | -- | 11.5
Other | -- | -- | -- | --
Support | -- | 14.4 | -- | 14.4
Subtotal | -11.4 | 24.3 | -- | 12.9
Total Changes | -11.4 | 24.3 | -- | 12.9
CE - Cost Variance | 967.1 | 4715.7 | -- | 5682.8
CE - Cost & Funding | 967.1 | 4715.7 | -- | 5682.8
Previous Estimate: September 2015

## Table 34
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 0.4
Revised estimate to reflect prior year actuals and program reductions. Prior year actual reductions equals $3.2M and program reductions equals $6.4M (Army). (Estimating) | -9.3 | -9.6
Revised estimate to account for current and prior inflation adjustments (Army). (Estimating) | 0.4 | 0.4
Adjustment for current and prior escalation. (Estimating) | -1 | -1
Revised estimate to reflect prior year actuals and program adjustments. Prior year actual reduction equals -$7.1M and program adjustments equals +$5.4M (Navy). (Estimating) | -1.7 | -1.7
Revised estimate to account for current and prior inflation adjustments (Navy). (Estimating) | 0.2 | 0.2
RDT&E Subtotal | -11.4 | -11.3
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -31.8
Adjustment for current and prior escalation. (Estimating) +0.1 +0.1
Acceleration of the procurement buy profile FY 2019 - FY 2021 due to increased funding (Army). (Schedule)
Acceleration of the procurement buy profile FY 2019 - FY2021 due to increased funding, shortens the procurement phase (Navy). (Schedule)
0.0 -194.1
0.0 -18.7
Revised estimate to account for current and prior inflation adjustments (Army). (Estimating) +17.6 +23.8 Revised estimate to account for current and prior inflation adjustments (Navy). (Estimating) +5.2 +6.9 Additional schedule variance due to accelerated buy profile (Navy). (Schedule) 0.0 +19.2
Additional schedule variance due to accelerated buy profile. Army (Schedule) -13.0 +2.9
Increase in Other Support is due to the accelerated procurement buy profile (Army). (Support)
+14.4 +15.4
Procurement Subtotal +24.3 -176.3

## Table 35
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: EMD and LRIP and Deployment
Contractor: Lockheed Martin Corporation
Contractor Location: 5600 W Sand lake Rd MP-265
Orlando, FL 32819
Contract Number: W31P4Q-15-C-0102
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: July 31, 2015
Definitization Date: July 31, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
195.2 201.3 1155 195.2 201.3 1155 195.2 195.2
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because an EVM was waived by the DAE on October 17, 2014 due to the short two-year length of the contract.

## Table 36
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 118 | 0%
Production | 0 | 0 | 26319 | 0%
Total Program Quantity Delivered | 0 | 0 | 26437 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
7136.9
652.7
9.15%
33
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
9
27.27%
870.7
12.2%
The above data is current as of February 09, 2016.

## Table 37
Operating and Support Cost
Cost Estimate Details
Date of Estimate: July 17, 2015
Source of Estimate: CAPE ICE
Quantity to Sustain: 26319
Unit of Measure: Missile
Service Life per Unit: 25.00 Years
Fiscal Years in Service: FY 2018 - FY 2065
The 118 developmental missiles will not be sustained.
Sustainment Strategy
Sustainment Approach
• Current: Three years Initial Interim Contractor Support
• Future: Integrated Product Support based sustainment beginning 1st Quarter FY 2022
• Obtain data rights to enable organic depot/partnering as required
• High Materiel Availability through design
• Leverage existing sustainment infrastructure
Antecedent Information
No Antecedent Program
Annual O&S Costs BY2015 $K
Cost Element | JAGM Average Annual Cost Per Missile | No Antecedent Program (Antecedent) N/A
Unit-Level Manpower | -- | --
Unit Operations | -- | --
Maintenance | 0.177 | --
Sustaining Support | 0.396 | --
Continuing System Improvements | 0.016 | --
Indirect Support | -- | --
Other | -- | --
Total | 0.589 | --

## Table 38
Item | Total O&S Cost $M
| JAGM | [5 empty] | No Antecedent Program (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 396.5 |  | 436.2 |  |  | 387.2 | 0
Then Year | 678.1 |  | N/A |  |  | 668.5 | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
Total Missile O&S = $0.5885K (average annual O&S cost per missile) * 25 (years of service life) * 26,319 (total missile quantity) = $387.2M
O&S Cost Variance
Category |  | BY 2015 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Sep 2015 SAR
392.6
Programmatic/Planning Factors -5.4 Accelerated production shortens sustainment years therefore decreasing sustainment cost.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes -5.4
Current Estimate 387.2
Disposal Estimate Details
Date of Estimate: February 04, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2015 $M): Total costs for disposal of all Missile are 2.6
The JAGM disposal costs changed from $3.9M to $2.6M due to a change from using the methodology in the ICE to using HELLFIRE disposal cost actuals. The disposal cost is calculated using the HELLFIRE actuals multiplied by the JAGM disposal quantity (JAGM Procurement quantity less missiles consumed during Stockpile Reliability Program) plus transportation to disposal site.