## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-385
Joint Tactical Radio System Handheld, Manpack, and Small Form Fit Radios (JTRS HMS)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 16
Cost and Funding 18
Low Rate Initial Production 33
Foreign Military Sales 34
Nuclear Costs 34
Unit Cost 35
Cost Variance 38
Contracts 42
Deliveries and Expenditures 44
Operating and Support Cost 45

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Joint Tactical Radio System Handheld, Manpack, and Small Form Fit Radios (JTRS HMS)
DoD Component
Army
Joint Participants
US Navy; US Marine Corps; US Air Force
Army is the lead Acquisition Executive per memo dated July 11, 2012.
Responsible Office
COL James Ross 6007 Combat Drive
Aberdeen Proving Ground, MD 21005
james.p.ross2.mil@mail.mil
Phone: | 443-395-2669
Fax: | 443-395-7680
DSN Phone: | 648-2669
DSN Fax: | 648-7680
Date Assigned: | August 19, 2014
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 20, 2011
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 20, 2011

## Table 6
Mission and Description
The Handheld, Manpack, and Small Form Fit (HMS) radio program is a materiel solution meeting the requirements for a Software Communications Architecture (SCA) compliant hardware system hosting SCA-compliant Government purpose rights software waveforms (applications). HMS is an ACAT ID program that encompasses specific requirements to support the U.S. Army, Air Force, Navy, Marine Corps and Special Operations Command communication needs.
HMS provides voice and data communications to the tactical edge/most disadvantaged warfighter with an on the move, at the halt, and stationary Line of Sight / Beyond Line of Sight capability for both dismounted personnel and platforms. HMS radios are software reprogrammable, networkable, multi-mode system (of systems) capable of simultaneous voice, data and video communication.
HMS encompasses the Rifleman Radio, Manpack Radio, and Small Form Fit radios. The Rifleman Radio is a secret and below capable radio and ports the Soldier Radio Waveform (SRW). It is the primary squad level communication system. The Manpack Radio is for use in a classified environment and ports the following waveforms: SRW, Single Channel Ground and Airborne Radio System, satellite communication, and Mobile-User Objective System. The Manpack Radio is utilized by the company and below. The embedded Small Form Fit radios may be used for Unmanned Vehicles and other platform applications.

## Table 7
Executive Summary
HMS is structured as a single acquisition program. The program completed the EMD Phase and received Milestone C approval on June 17, 2011 with LRIP configured radios. HMS is currently executing to a May 1, 2014 approved acquisition strategy to procure modified non-developmental items (NDI) through two full and open competition contracts available to all potential industry partners. The first contract will procure NDI Rifleman Radios (RR) for use in a classified environment. The RR ports the Soldier Radio Waveform (SRW) (Army managed waveform). The second contract will procure NDI Manpack Radios (MP) for use in a classified environment. Waveforms to be ported to HMS MP include: SRW, Single Channel Ground and Airborne Radio System (Army managed waveform), Satellite Communications (Army managed waveform), and Mobile- User Objective System (Navy managed waveform).
The RR Full and Open Competition contract was awarded on April 29, 2015 to two vendors, Thales Group and Harris Corporation. Qualification Testing was completed on August 13, 2015. Both vendors met the requirements to proceed to further Customer Testing which will be completed in May 2016. Operational Testing is planned for qualified vendors in 4th Quarter FY 2016.
The MP Full and Open Competition contract Request for Proposal was released to industry on August 3, 2015, proposals were received on October 2, 2015, and the contract is currently in source selection.
As of February 9, 2016, the Government received 19,327 LRIP RR and 5,326 LRIP MP radios as well as 200 FOC RR (100 per vendor) to support competition testing and eventual fielding. In addition, the Government received all 2,052 LRIP SFF-B (v)1 Radios for Nett Warrior. Nett Warrior Radios are not a part of the HMS program and are procured for PEO
Soldier; however, they are a part of the RR Army Acquisition Objective.
As of February 2016, the Army continues to evaluate a 2-channel handheld radio to meet the developing needs of the Nett Warrior and the Warfighter community.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Schedule breaches were previously reported in the December 2014 SAR. A Joint Requirements Oversight
Council memorandum signed August 5, 2015 acknowledges these breaches. As a result, the program office is preparing an APB
that reflects the new program schedule.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B Decision | Apr 2004 | Apr 2004 | Jun 2004 | Apr 2004
Contract Award | Jul 2004 | Jul 2004 | Jul 2004 | Jul 2004
Milestone C Decision: HMS | May 2011 | May 2011 | May 2011 | May 2011
IOT&E: AN/PRC-154 Rifleman Radio | Nov 2011 | Nov 2011 | May 2012 | Nov 2011
MOT&E: AN/PRC-155 Manpack | May 2012 | May 2012 | Nov 2012 | May 2012
IOC: AN/PRC-154 Rifleman Radio | Jan 2012 | Jan 2012 | Jul 2012 | Jul 2012
IPR: AN/PRC-155 Manpack | Feb 2012 | Feb 2012 | Aug 2012 | Jul 2012
IOC: AN/PRC-155 Manpack | Mar 2013 | Mar 2013 | Sep 2013 | Aug 20141
FOT&E: AN/PRC-155 Manpack with MUOS | Jun 2013 | Jun 2013 | Jun 2014 | Oct 20161
Fielding: AN/PRC-155 Manpack with MUOS | Jun 2014 | Jun 2014 | Jun 2015 | Apr 20171
FRP Decision Review: AN/PRC-154 Rifleman Radio | May 2012 | May 2012 | Nov 2012 | Feb 20181
FRP Decision Review: AN/PRC-155 Manpack | Dec 2012 | Dec 2012 | Jun 2013 | Aug 20181
1 APB Breach
(Ch-1)
(Ch-1)
(Ch-2)
(Ch-3)

## Table 10
Change Explanations
(Ch-1) FOT&E: Manpack with MUOS changed from June 2016 to October 2016. Fielding: Manpack with MUOS changed from September 2016 to April 2017. These changes are due to delays in the development of the MUOS system.
(Ch-2) The FRP Decision Review date for the Rifleman Radio changed from March 2017 to February 2018. A Customer Test was added to the testing schedule to provide risk reduction prior to the Operational Test, as well as inform an LRIP delivery order prior to FRP decision.
(Ch-3) The FRP Decision Review for the Manpack Radio changed from September 2017 to August 2018 due to industry timelines for delivering NDI MP radios that meet threshold requirements. Additionally, a Customer Test was added to the testing schedule to provide risk reduction prior to the Operational Test, as well as inform an LRIP delivery order prior to FRP decision.
Notes
HMS procured the AN/PRC-154 and AN/PRC-154A RR, and the AN/PRC-155 MP during the LRIP phase. These nomenclatures will not be applicable to the FRP Decision Review events above. The Full and Open Competition contracts for RR (awarded April 29, 2015) and MP (with award anticipated 3rd Quarter FY 2016) allowed new vendors and/or products to enter, each with unique nomenclature.
Acronyms and Abbreviations
FOT&E - Follow-On Test and Evaluation IOT&E - Initial Operational Test and Evaluation IPR - In-Process Review
MOT&E - Multi-Service Operational Test and Evaluation MP - Manpack
MUOS - Mobile User Objective System NDI - Non-Developmental Item
RR - Rifleman Radio SFF - Small Form Fit

## Table 11
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Intra-Squad Communication: AN/PRC-154 Rifleman Radio
Voice | Voice | Voice | Voice | Voice
Soldier Location: AN/PRC-154 Rifleman Radio
Automatic PLI | Automatic PLI | Automatic PLI | Automatic PLI | Automatic PLI
Net Ready (NR) Capability: AN/PRC-154 Rifleman Radio
The capability, | The system must fully | The system must fully | Threshold | The capability, system,
system, and/or | support execution of | support execution of | demonstrated at | and/or service must fully
service must fully | all operational | joint critical | NIE 15.1 | support execution of joint
support execution of | activities identified in | operational activities |  | critical operational
all operational | the applicable joint | identified in the |  | activities and information
activities and | and system integrated | applicable joint and |  | exchanges identified in
information | architectures and the | system integrated |  | the DoD Enterprise
exchanges identified | system must satisfy | architectures and the |  | Architecture and solution
in DoD Enterprise | the technical | system must satisfy |  | architectures based on
Architecture and | requirements for Net- | the technical |  | integrated DoDAF
solution architectures | Centric military | requirements for |  | content, and must satisfy
based on integrated | operations to include | transition to Net- |  | the technical
DoDAF content, and | 1) DISR mandated | Centric military |  | requirements for
must satisfy the | GIG IT standards and | operations to include |  | transition to Net-Centric
technical | profiles identified in | 1) DISR mandated |  | military operations to
requirements for | the TV-1, 2) DISR | GIG IT standards and |  | include: 1) Solution
transition to Net- | mandated GIG KIPs | profiles identified in |  | architecture products
Centric military | identified in the KIP | the TV-1, 2) DISR |  | compliant with DoD
operations to include 1 | declaration table, 3) | mandated GIG KIPs |  | Enterprise Architecture
Solution architecture | NCOW RM Enterprise | identified in the KIP |  | based on integrated
products compliant | Services 4) IA | declaration table, 3) |  | DoDAF content, including
with DoD Enterprise | requirements | NCOW RM Enterprise |  | specified operationally
Architecture based on | including availability, | Services 4) IA |  | effective information
integrated DoDAF | integrity, authentica- | requirements |  | exchanges 2) Compliant
content, including | tion, confident-iality, | including availability, |  | with Net-Centric Data
specified operationally | and nonrepudia-tion, | integrity, authentica- |  | Strategy and Net-Centric
effective information | and issuance of an | tion, confident-iality, |  | Services Strategy, and
exchanges 2) | ATO by the DAA, and | and nonrepudia-tion, |  | the principles and rules
Compliant with Net - | 5) Operationally | and issuance of an |  | identified in the DoD IEA,
Centric Data Strategy | effective information | IATO by the DAA, and |  | except tactical and non-IP
and Net-Centric | exchanges; and | 5) Operationally |  | communications 3)
Services Strategy, | mission critical | effective information |  | Compliant with GIG
and the principles and | performance and IA | exchanges; and |  | Technical Guidance to
rules identified in the | attributes, data | mission critical |  | include IT Standards
DoD IEA, excepting | correctness, data | performance and IA |  | identified in the TV-1 and
tactical and non-IP | availability, and | attributes, data |  | implementation guidance
communicat-ions 3) | consistent data | correctness, data |  | of GESPs necessary to
Compliant with GIG | processing specified | availability, and |  | meet all operational

## Table 12
Technical Guidance to | in the applicable joint | consistent data |  | requirements specified in
include IT Standards | and system integrated | processing specified |  | the DoD Enterprise
identified in the TV-1 | architecture views. | in the applicable joint |  | Architecture and solution
and implementa-tion |  | and system integrated |  | architecture views 4) IA
guidance of GESPs, |  | architecture views. |  | requirements including
necessary to meet all |  |  |  | availability, integrity,
operational |  |  |  | authentication,
requirements |  |  |  | confidentiality, and non-
specified in the DoD |  |  |  | repudiation, and issuance
Enterprise |  |  |  | of an IATO or ATO by the
Architecture and |  |  |  | DAA, and 5)
solution architecture |  |  |  | Supportability
views 4) IA |  |  |  | requirements to include
requirements |  |  |  | SAASM, Spectrum and
including availability, |  |  |  | JTRS requirements.
integrity, authenticat-
ion, confidential-ity,
and non-repudiation,
and issuance of an
ATO by the DAA, and
5) Supportabil-ity
requirements to
include SAASM,
Spectrum and JTRS
requirements
Sustainment (Operational Availability (Ao)): AN/PRC-154 Rifleman Radio
0.99 (Channel) | 0.99 (Channel) | 0.96 (Channel) | 0.999 (Channel) | 0.999 (Channel)
Voice and Data Communication: AN/PRC-155 Manpack
Must provide | Must provide | Must provide | MP | Must provide networked
networked voice and | networked voice and | networked voice and | demonstrated | voice and data exchange
data exchange to | data exchange to | data exchange to | networked voice | to support timely tactical
support timely tactical | support timely tactical | support timely tactical | and data | actions while dispersed
actions while | actions while | actions while | exchange (i.e., | across the battlefield.
dispersed across the | dispersed across the | dispersed across the | mission
battlefield. | battlefield. | battlefield. | command
information)
supporting timely
tactical actions
while dispersed
across the
battlefield using
gateways.
Net Ready (NR) Capability: AN/PRC-155 Manpack
The capability, | The capability, | The capability, | TBD | The capability, system,
system, and/or | system, and/or | system, and/or |  | and/or service must fully
service must fully | service must fully | service must fully |  | support execution of joint
support execution of | support execution of | support execution of |  | critical operational
all operational | all operational | joint critical |  | activities and information
activities and | activities and | operational activities |  | exchanges identified in
information | information | and information |  | DoD Enterprise
exchanges identified | exchanges identified | exchanges identified |  | Architecture and solution
in DoD Enterprise | in DoD Enterprise | in DoD Enterprise |  | architectures based on

## Table 13
Architecture and solution architectures based on integrated DoDAF content, and must satisfy the technical requirements for transition to Net- Centric military
Architecture and solution architectures based on integrated DoDAF content, and must satisfy the technical requirements for transition to Net- Centric military
Architecture and solution architectures based on integrated DoDAF content, and must satisfy the technical requirements for transition to Net- Centric military
integrated DoDAF content, and must satisfy the technical requirements for transition to Net-Centric military operations to include 1) Solution architecture products compliant with DoD
operations to include 1 operations to include
operations to include
Enterprise Architecture
Solution architecture products compliant with DoD Enterprise Architecture based on integrated DoDAF content, including specified operationally effective information exchanges 2) Compliant with Net - Centric Data Strategy and Net-Centric Services Strategy, and the principles and rules identified in the DoD IEA, excepting tactical and non-IP communica-tions 3) Compliant with GIG Technical Guidance to include IT Standards identified in the TV-1 and implementat-ion guidance of GESPs, necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views 4) IA requirements including availability, integrity, authenticat- ion, confident-iality, and nonrepudia-tion, and issuance of an ATO by the DAA, and
5) Supportabi-lity requirements to include SAASM, Spectrum and JTRS requirements
1) Solution architecture products compliant with DoD Enterprise Architecture based on integrated DoDAF content, including specified operationally effective information exchanges 2) Compliant with Net - Centric Data Strategy and Net-Centric Services Strategy, and the principles and rules identified in the DoD IEA, excepting tactical and non-IP communica-tions 3) Compliant with GIG Technical Guidance to include IT Standards identified in the TV-1 and implementa-tion guidance of GESPs, necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views 4) IA requirements including availability, integrity, authenticat- ion, confidential-ity, and non-repudiation, and issuance of an ATO by the DAA, and
5) Supportabil-ity requirements to include SAASM, Spectrum and JTRS
1) Solution architecture products compliant with DoD Enterprise Architecture based on integrated DoDAF content, including specified operationally effective information exchanges 2) Compliant with Net - Centric Data Strategy and Net-Centric Services Strategy, and the principles and rules identified in the DoD IEA, excepting tactical and non-IP communicat-ions 3) Compliant with GIG Technical Guidance to include IT Standards identified in the TV-1 and implementa-tion guidance of GESPs, necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views 4) IA requirements including availability, integrity, authenticat- ion, confidential-ity, and non-repudiation, and issuance of an ATO by the DAA, and
5) Supportabil-ity requirements to include SAASM, Spectrum and JTRS
based on integrated DoDAF content, including specified operationally effective information exchanges 2) Compliant with Net-Centric Data Strategy and Net-Centric Services Strategy, and the principles and rules identified in the DoD IEA, except tactical and non-IP communications 3) Compliant with GIG Technical Guidance to include IT Standards identified in the TV-1 and implementation guidance of GESPs, necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views 4) IA requirements including availability, integrity, authentication, confidentiality, and non- repudiation, and issuance of an ATO by the DAA, and 5) Supportability requirements to include SAASM, Spectrum and JTRS requirements.

## Table 14
| requirements | requirements
Sustainment (Operational Availability (Ao)): AN/PRC-155 Manpack
0.99 (Channel) | 0.99 (Channel) | 0.96 (Channel) | 0.86 (Channel) | 0.97 (Channel)
Multi-Channel Operations: AN/PRC-155 Manpack
To enable Warfighters | To enable Warfighters | To enable Warfighters | The radio | To enable Warfighters to
to conduct combat | to conduct combat | to conduct combat | enables | conduct combat missions
missions across the | missions across the | missions across the | Warfighters to | across the battlefield, any
battlefield, any | battlefield, any | battlefield, any | conduct combat | channel of the MP must
channel of the MP | channel of the MP | channel of the MP | missions across | have ability to operate any
must have ability to | must have ability to | must have ability to | the battlefield | of the waveforms listed
operate any of the | operate any of the | operate any of the | using the SRW, | as Thresholds in Table
waveforms listed as | waveforms listed as | waveforms listed as | basic modes of | EE-2 of the CPD. The MP
Objective in Table EE- | Objective in Table EE- | Thresholds in Table | SINCGARS and | must also allow
2 of the CPD. The MP | 2 of the CPD. The MP | EE-2 of the CPD. The | basic modes of | simultaneous operations
must also allow | must also allow | MP must also allow | UHF SATCOM. | using waveform
simultaneous | simultaneous | simultaneous | The MP has | combinations identified in
operations using | operations using | operations using | demonstrated | Table EE-3 of the CPD. In
waveform | waveform | waveform | simultaneous | addition the MP must
combinations listed as | combinations listed in | combinations listed in | operations using | have the ability to route
Objective identified in | Table EE-3.2 of the | Table EE-3 of the | combinations of | and retransmit threshold
Table EE-3.2 of the | CPD. In addition the | CPD. In addition the | these | waveforms listed in Table
CPD. In addition the | MP must have the | MP must have the | waveforms. | EE-4 of the CPD.
MP must have the | ability to route and | ability to route and
ability to route and | retransimit threshold | retransimit threshold
retransimit threshold | waveforms listed as | waveforms listed in
waveforms listed as | Objective in Table EE- | Table EE-4 of the
Objective in Table EE- | 4 of the CPD. | CPD.
4 of the CPD.
Requirements Reference
Rifleman Radio CPD dated March 7, 2011 and Manpack CPD dated May 10, 2012
Change Explanations
None
Notes
In order to address soldier and stakeholder concerns with regard to excessive heat and weight of the LRIP MP,
HMS coordinated with the U.S. Army Natick Soldier Research, Development and Engineering Center to design an enhanced rucksack that will improve the performance of the MP. The redesigned rucksack provides improved weight distribution and heat dissipation. Additionally, this rucksack is airborne operation certified through testing conducted by the Army Test and Evaluation Command.

## Table 15
Acronyms and Abbreviations
ATO - Approval to Operate
DAA - Designated Approval Authority
DISR - Department of Defense Information Technology Standards Registry DoDAF - Department of Defense Architecture Framework
GESP - Global Information Grid Enterprise Service Profile GIG - Global Information Grid
IA - Information Assurance
IATO - Interim Approval to Operate
IEA - Information Environment Architecture IP - Internet Protocol
IT - Information Technology KIP - Key Interface Profiles MP - Manpack
NCOW RM - Net-Centric Operations and Warfare Reference Model NIE - Network Integration Evaluation
NR - Net Ready
PLI - Position Location Information
SAASM - Selective Availability Anti-Spoofing Module SATCOM - Satellite Communications
SINCGARS - Single Channel Ground and Airborne Radio System SRW - Soldier Radio Waveform
TV - Technical View
UHF - Ultra High Frequency

## Table 16
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy |  | 1319 05 |  | 0604280N
|  | Project |  | Name
|  | 3075 |  | Joint Tactical Radio System (JTRS) / HMS JTRS | (Sunk)
Army |  | 2040 05 |  | 0604280A
|  | Project |  | Name
|  | 162 |  | Joint Tactical Radio / Network Enterprise Domain (NED) | (Sunk)
|  | DZ5 |  | Joint Tactical Radio
Army |  | 2040 05 |  | 0604805A
|  | Project |  | Name
|  | 615 |  | JTRS - Ground Domain Integration | (Sunk)
|  | 61A |  | JTRS Cluster 5 Development | (Sunk)
Army |  | 2040 05 |  | 0605042A
|  | Project |  | Name
|  | FA1 |  | Manpack Radio
|  | FA2 |  | Rifleman Radio
Procurement
Appn |  |  | BA | PE
Navy 1109 04 0206313M
Line Item | Name
4633 Radio Systems (Shared)
Navy 1810 02 0204163N
Line Item | Name
3057 Communication Items Under $5M (Shared)
Army 2035 02 0604280A
|  | Line Item |  | Name
|  | B90210 B90215 |  | JTRS Cluster 5 (Handheld) JTRS (Manpack) |  | (Sunk) (Sunk)
Army |  | 2035 02 |  | 0605042A
|  | Line Item |  | Name
|  | B95006 B95007 |  | Handheld Radio Manpack Radio
Army |  | 2035 03
|  | Line Item |  | Name
R80501 Ground Soldier System (Sunk)
Air Force 3080 03 0207423F

## Table 17
Line Item | Name
837100 Tactical C-E Equipment (Shared)
Notes
The parent line for B90210, JTRS Cluster 5 (Handheld), and B90215, JTRS (Manpack), is B90000.
The parent line for B95006, Handheld Radio, and B95007, Manpack Radio, is B95004.

## Table 18
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2011 $M |  |  |  |  | BY 2011 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 1254.7 |  | 1254.7 | 1380.2 |  | 1313.1 |  | 1238.5 |  | 1238.5 |  | 1326.1
Procurement |  | 6987.9 |  | 6987.9 | 7686.7 |  | 7442.5 |  | 7962.5 |  | 7962.5 |  | 9580.9
Flyaway |  | -- |  | -- | -- |  | 5406 |  | -- |  | -- |  | 7015.2
Recurring |  | -- |  | -- | -- |  | 5242.9 |  | -- |  | -- |  | 6832.6
Non Recurring |  | -- |  | -- | -- |  | 163.1 |  | -- |  | -- |  | 182.6
Support |  | -- |  | -- | -- |  | 2036.5 |  | -- |  | -- |  | 2565.7
Other Support |  | -- |  | -- | -- |  | 1834.1 |  | -- |  | -- |  | 2301.9
Initial Spares |  | -- |  | -- | -- |  | 202.4 |  | -- |  | -- |  | 263.8
MILCON |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total |  | 8242.6 |  | 8242.6 | N/A |  | 8755.6 |  | 9201 |  | 9201 |  | 10907
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The ICE to support JTRS HMS Milestone C decision, like all lifecycle cost estimates previously performed by the CAPE office, is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 19
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 582 | 582 | 833
Procurement | 270369 | 270369 | 270369
Total | 270951 | 270951 | 271202
Quantity Notes
Unit of measure is an HMS radio, which includes multiple variants (Rifleman Radio, Manpack, or various Small Form Fit).
Rifleman Radio (Army) - 193,279: Dismounted - 170,735
Mounted - 22,544
Manpack (Army) 65,622:
Dismounted - 23,358
Single Vehicle Mounted - 24,580 Dual Vehicle Mounted - 17,684
Small Form Fit-B - 950
Small Form Fit-D - 3,076
Manpack (Other Services): 7,442: Dismounted - 3,357
Single Vehicle Mounted - 4,085

## Table 20
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 1140.5 | 4.5 |  |  | 18.8 | 5.4 | 7 |  | 9.6 |  |  | 21.5 |  | 118.8 |  | 1326.1
Procurement | 965.2 | 54.6 |  |  | 273.7 | 404.9 | 413.8 |  | 415.2 |  |  | 435.8 |  | 6617.7 |  | 9580.9
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0
PB 2017 Total | 2105.7 | 59.1 |  |  | 292.5 | 410.3 | 420.8 |  | 424.8 |  |  | 457.3 |  | 6736.5 |  | 10907
PB 2016 Total | 2126 | 74.6 |  |  | 297.1 | 475 | 480.7 |  | 490.1 |  |  | 506.7 |  | 6036.5 |  | 10486.7
Delta | -20.3 | -15.5 |  |  | -4.6 | -64.7 | -59.9 |  | -65.3 |  |  | -49.4 |  | 700 |  | 420.3
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 833 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 833
Production | 0 |  | 26905 |  | 0 | 5656 | 8367 |  | 8480 | 8596 |  | 8357 |  | 204008 |  | 270369
PB 2017 Total | 833 |  | 26905 |  | 0 | 5656 | 8367 |  | 8480 | 8596 |  | 8357 |  | 204008 |  | 271202
PB 2016 Total | 833 |  | 26709 |  | 540 | 8134 | 12021 12336 |  |  | 13142 |  | 15555 |  | 181932 |  | 271202
Delta | 0 |  | 196 |  | -540 | -2478 | -3654 |  | -3856 | -4546 |  | -7198 |  | 22076 |  | 0

## Table 21
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 132.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 150.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 127.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 178.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 117.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.5
Subtotal |  | 271 | -- |  | -- |  | -- |  | -- |  | -- |  | 855.7

## Table 22
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 139.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 155.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 129.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 179.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 79.7
Subtotal |  | 271 | -- |  | -- |  | -- |  | -- |  | -- |  | 861.5

## Table 23
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 96.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 124.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.4
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.6
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.5
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.3
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.9
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.3
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.1
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.7
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.4
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.3
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4
Subtotal |  | 562 | -- |  | -- |  | -- |  | -- |  | -- |  | 470.4

## Table 24
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 106.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 133.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.1
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.7
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.9
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.8
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.2
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
Subtotal |  | 562 | -- |  | -- |  | -- |  | -- |  | -- |  | 451.6

## Table 25
Annual Funding 1109 ¦ Procurement ¦ Procurement, Marine Corps
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2023 |  | 245 | 16.2 |  | -- |  | -- |  | 16.2 |  | 2.4 |  | 18.6
2024 |  | 239 | 15.8 |  | -- |  | -- |  | 15.8 |  | 2.3 |  | 18.1
2025 |  | 239 | 15.9 |  | -- |  | -- |  | 15.9 |  | 2.3 |  | 18.2
2026 |  | 239 | 16 |  | -- |  | -- |  | 16 |  | 2.3 |  | 18.3
2027 |  | 239 | 16.1 |  | -- |  | -- |  | 16.1 |  | 2.3 |  | 18.4
2028 |  | 239 | 16.2 |  | -- |  | -- |  | 16.2 |  | 2.3 |  | 18.5
2029 |  | 239 | 16.4 |  | -- |  | -- |  | 16.4 |  | 2.4 |  | 18.8
2030 |  | 238 | 16.5 |  | -- |  | -- |  | 16.5 |  | 2.4 |  | 18.9
2031 |  | 238 | 16.7 |  | -- |  | -- |  | 16.7 |  | 2.4 |  | 19.1
2032 |  | 238 | 16.9 |  | -- |  | -- |  | 16.9 |  | 2.4 |  | 19.3
Subtotal |  | 2393 | 162.7 |  | -- |  | -- |  | 162.7 |  | 23.5 |  | 186.2

## Table 26
Annual Funding 1109 ¦ Procurement ¦ Procurement, Marine Corps
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2023 |  | 245 | 12.8 |  | -- |  | -- |  | 12.8 |  | 1.9 |  | 14.7
2024 |  | 239 | 12.2 |  | -- |  | -- |  | 12.2 |  | 1.8 |  | 14
2025 |  | 239 | 12.1 |  | -- |  | -- |  | 12.1 |  | 1.7 |  | 13.8
2026 |  | 239 | 11.9 |  | -- |  | -- |  | 11.9 |  | 1.7 |  | 13.6
2027 |  | 239 | 11.7 |  | -- |  | -- |  | 11.7 |  | 1.7 |  | 13.4
2028 |  | 239 | 11.6 |  | -- |  | -- |  | 11.6 |  | 1.6 |  | 13.2
2029 |  | 239 | 11.5 |  | -- |  | -- |  | 11.5 |  | 1.7 |  | 13.2
2030 |  | 238 | 11.3 |  | -- |  | -- |  | 11.3 |  | 1.7 |  | 13
2031 |  | 238 | 11.2 |  | -- |  | -- |  | 11.2 |  | 1.7 |  | 12.9
2032 |  | 238 | 11.2 |  | -- |  | -- |  | 11.2 |  | 1.5 |  | 12.7
Subtotal |  | 2393 | 117.5 |  | -- |  | -- |  | 117.5 |  | 17 |  | 134.5

## Table 27
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | 50 | 3.4 |  | -- |  | -- |  | 3.4 |  | -- |  | 3.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2023 |  | 20 | 1.3 |  | -- |  | -- |  | 1.3 |  | 0.2 |  | 1.5
2024 |  | 20 | 1.3 |  | -- |  | -- |  | 1.3 |  | 0.2 |  | 1.5
2025 |  | 20 | 1.3 |  | -- |  | -- |  | 1.3 |  | 0.2 |  | 1.5
2026 |  | 20 | 1.3 |  | -- |  | -- |  | 1.3 |  | 0.2 |  | 1.5
2027 |  | 20 | 1.4 |  | -- |  | -- |  | 1.4 |  | 0.2 |  | 1.6
2028 |  | 20 | 1.4 |  | -- |  | -- |  | 1.4 |  | 0.3 |  | 1.7
2029 |  | 20 | 1.4 |  | -- |  | -- |  | 1.4 |  | 0.3 |  | 1.7
2030 |  | 20 | 1.4 |  | -- |  | -- |  | 1.4 |  | 0.3 |  | 1.7
2031 |  | 20 | 1.4 |  | -- |  | -- |  | 1.4 |  | 0.3 |  | 1.7
2032 |  | 20 | 1.4 |  | -- |  | -- |  | 1.4 |  | 0.3 |  | 1.7
Subtotal |  | 250 | 17 |  | -- |  | -- |  | 17 |  | 2.5 |  | 19.5

## Table 28
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | 50 | 3.3 |  | -- |  | -- |  | 3.3 |  | -- |  | 3.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2023 |  | 20 | 1 |  | -- |  | -- |  | 1 |  | 0.2 |  | 1.2
2024 |  | 20 | 1 |  | -- |  | -- |  | 1 |  | 0.2 |  | 1.2
2025 |  | 20 | 1 |  | -- |  | -- |  | 1 |  | 0.1 |  | 1.1
2026 |  | 20 | 1 |  | -- |  | -- |  | 1 |  | 0.1 |  | 1.1
2027 |  | 20 | 1 |  | -- |  | -- |  | 1 |  | 0.2 |  | 1.2
2028 |  | 20 | 1 |  | -- |  | -- |  | 1 |  | 0.2 |  | 1.2
2029 |  | 20 | 1 |  | -- |  | -- |  | 1 |  | 0.2 |  | 1.2
2030 |  | 20 | 1 |  | -- |  | -- |  | 1 |  | 0.2 |  | 1.2
2031 |  | 20 | 0.9 |  | -- |  | -- |  | 0.9 |  | 0.2 |  | 1.1
2032 |  | 20 | 0.9 |  | -- |  | -- |  | 0.9 |  | 0.2 |  | 1.1
Subtotal |  | 250 | 13.1 |  | -- |  | -- |  | 13.1 |  | 1.8 |  | 14.9

## Table 29
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | 5297 | 33.3 |  | -- |  | 6.9 |  | 40.2 |  | 0.1 |  | 40.3
2012 |  | 19858 | 357.6 |  | -- |  | 6 |  | 363.6 |  | 85.4 |  | 449
2013 |  | 1500 | 144 |  | -- |  | 0.2 |  | 144.2 |  | 60.6 |  | 204.8
2014 |  | -- | -- |  | -- |  | 47.7 |  | 47.7 |  | 199.3 |  | 247
2015 |  | 200 | 1.4 |  | -- |  | -- |  | 1.4 |  | 19.3 |  | 20.7
2016 |  | -- | -- |  | -- |  | 2 |  | 2 |  | 52.6 |  | 54.6
2017 |  | 5656 | 142.7 |  | -- |  | 59.1 |  | 201.8 |  | 71.9 |  | 273.7
2018 |  | 8367 | 260.8 |  | -- |  | 33.4 |  | 294.2 |  | 110.7 |  | 404.9
2019 |  | 8480 | 267.1 |  | -- |  | 11 |  | 278.1 |  | 135.7 |  | 413.8
2020 |  | 8596 | 269.7 |  | -- |  | 6.3 |  | 276 |  | 139.2 |  | 415.2
2021 |  | 8357 | 285.9 |  | -- |  | 4.9 |  | 290.8 |  | 145 |  | 435.8
2022 |  | 8410 | 279.2 |  | -- |  | 5.1 |  | 284.3 |  | 153.8 |  | 438.1
2023 |  | 19201 | 425.5 |  | -- |  | -- |  | 425.5 |  | 146.4 |  | 571.9
2024 |  | 19201 | 425.9 |  | -- |  | -- |  | 425.9 |  | 155.5 |  | 581.4
2025 |  | 18726 | 406.4 |  | -- |  | -- |  | 406.4 |  | 154.8 |  | 561.2
2026 |  | 18726 | 409.5 |  | -- |  | -- |  | 409.5 |  | 148.4 |  | 557.9
2027 |  | 18726 | 413.2 |  | -- |  | -- |  | 413.2 |  | 139.3 |  | 552.5
2028 |  | 18726 | 417.5 |  | -- |  | -- |  | 417.5 |  | 115.9 |  | 533.4
2029 |  | 18724 | 422.3 |  | -- |  | -- |  | 422.3 |  | 112.1 |  | 534.4
2030 |  | 18724 | 427.4 |  | -- |  | -- |  | 427.4 |  | 112.7 |  | 540.1
2031 |  | 18724 | 432.9 |  | -- |  | -- |  | 432.9 |  | 114.1 |  | 547
2032 |  | 18728 | 438.7 |  | -- |  | -- |  | 438.7 |  | 113.4 |  | 552.1
Subtotal |  | 262927 | 6261 |  | -- |  | 182.6 |  | 6443.6 |  | 2486.2 |  | 8929.8

## Table 30
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2011 |  | 5297 | 32.6 |  | -- |  | 6.7 |  | 39.3 |  | 0.1 |  | 39.4
2012 |  | 19858 | 344.4 |  | -- |  | 5.8 |  | 350.2 |  | 82.2 |  | 432.4
2013 |  | 1500 | 136 |  | -- |  | 0.2 |  | 136.2 |  | 57.2 |  | 193.4
2014 |  | -- | -- |  | -- |  | 44.3 |  | 44.3 |  | 185.1 |  | 229.4
2015 |  | 200 | 1.3 |  | -- |  | -- |  | 1.3 |  | 17.7 |  | 19
2016 |  | -- | -- |  | -- |  | 1.8 |  | 1.8 |  | 47.6 |  | 49.4
2017 |  | 5656 | 126.6 |  | -- |  | 52.4 |  | 179 |  | 63.8 |  | 242.8
2018 |  | 8367 | 226.9 |  | -- |  | 29.1 |  | 256 |  | 96.2 |  | 352.2
2019 |  | 8480 | 227.8 |  | -- |  | 9.4 |  | 237.2 |  | 115.7 |  | 352.9
2020 |  | 8596 | 225.5 |  | -- |  | 5.3 |  | 230.8 |  | 116.4 |  | 347.2
2021 |  | 8357 | 234.4 |  | -- |  | 4 |  | 238.4 |  | 118.8 |  | 357.2
2022 |  | 8410 | 224.4 |  | -- |  | 4.1 |  | 228.5 |  | 123.6 |  | 352.1
2023 |  | 19201 | 335.3 |  | -- |  | -- |  | 335.3 |  | 115.3 |  | 450.6
2024 |  | 19201 | 329 |  | -- |  | -- |  | 329 |  | 120.1 |  | 449.1
2025 |  | 18726 | 307.8 |  | -- |  | -- |  | 307.8 |  | 117.2 |  | 425
2026 |  | 18726 | 304 |  | -- |  | -- |  | 304 |  | 110.2 |  | 414.2
2027 |  | 18726 | 300.8 |  | -- |  | -- |  | 300.8 |  | 101.4 |  | 402.2
2028 |  | 18726 | 297.9 |  | -- |  | -- |  | 297.9 |  | 82.8 |  | 380.7
2029 |  | 18724 | 295.5 |  | -- |  | -- |  | 295.5 |  | 78.4 |  | 373.9
2030 |  | 18724 | 293.2 |  | -- |  | -- |  | 293.2 |  | 77.3 |  | 370.5
2031 |  | 18724 | 291.1 |  | -- |  | -- |  | 291.1 |  | 76.7 |  | 367.8
2032 |  | 18728 | 289.2 |  | -- |  | -- |  | 289.2 |  | 74.8 |  | 364
Subtotal |  | 262927 | 4823.7 |  | -- |  | 163.1 |  | 4986.8 |  | 1978.6 |  | 6965.4

## Table 31
Annual Funding 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2023 |  | 481 | 37.8 |  | -- |  | -- |  | 37.8 |  | 5.1 |  | 42.9
2024 |  | 481 | 37.9 |  | -- |  | -- |  | 37.9 |  | 5.1 |  | 43
2025 |  | 480 | 38.1 |  | -- |  | -- |  | 38.1 |  | 5.2 |  | 43.3
2026 |  | 480 | 38.5 |  | -- |  | -- |  | 38.5 |  | 5.2 |  | 43.7
2027 |  | 480 | 38.8 |  | -- |  | -- |  | 38.8 |  | 5.3 |  | 44.1
2028 |  | 480 | 39.2 |  | -- |  | -- |  | 39.2 |  | 5.4 |  | 44.6
2029 |  | 480 | 39.7 |  | -- |  | -- |  | 39.7 |  | 5.5 |  | 45.2
2030 |  | 480 | 40.2 |  | -- |  | -- |  | 40.2 |  | 5.5 |  | 45.7
2031 |  | 479 | 40.6 |  | -- |  | -- |  | 40.6 |  | 5.6 |  | 46.2
2032 |  | 478 | 41.1 |  | -- |  | -- |  | 41.1 |  | 5.6 |  | 46.7
Subtotal |  | 4799 | 391.9 |  | -- |  | -- |  | 391.9 |  | 53.5 |  | 445.4

## Table 32
Annual Funding 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2023 |  | 481 | 30.4 |  | -- |  | -- |  | 30.4 |  | 4.1 |  | 34.5
2024 |  | 481 | 29.9 |  | -- |  | -- |  | 29.9 |  | 4 |  | 33.9
2025 |  | 480 | 29.5 |  | -- |  | -- |  | 29.5 |  | 4 |  | 33.5
2026 |  | 480 | 29.2 |  | -- |  | -- |  | 29.2 |  | 3.9 |  | 33.1
2027 |  | 480 | 28.8 |  | -- |  | -- |  | 28.8 |  | 4 |  | 32.8
2028 |  | 480 | 28.6 |  | -- |  | -- |  | 28.6 |  | 3.9 |  | 32.5
2029 |  | 480 | 28.4 |  | -- |  | -- |  | 28.4 |  | 3.9 |  | 32.3
2030 |  | 480 | 28.2 |  | -- |  | -- |  | 28.2 |  | 3.8 |  | 32
2031 |  | 479 | 27.9 |  | -- |  | -- |  | 27.9 |  | 3.8 |  | 31.7
2032 |  | 478 | 27.7 |  | -- |  | -- |  | 27.7 |  | 3.7 |  | 31.4
Subtotal |  | 4799 | 288.6 |  | -- |  | -- |  | 288.6 |  | 39.1 |  | 327.7

## Table 33
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2011-06-17 | 2013-12-12
Approved Quantity | 6350 | 26905
Reference | Milestone C ADM | LRIP ADM
Start Year | 2011 | 2011
End Year | 2012 | 2015
The Milestone C ADM signed on June 17, 2011 approved entry into Production and Deployment and authorized the Army to contract for an initial LRIP procurement of 6,250 Rifleman Radios (RR) (AN/PRC-154) and 100 Manpack (MP) radios (AN/PRC-155). The ADM directed the Services to fund to the Independent Cost Estimate position. A follow-on ADM signed July 11, 2012 approved the procurement of an additional LRIP of 13,077 RR. An October 11, 2012 ADM authorized an additional LRIP procurement of up to 3,726 MP. A December 12, 2013 ADM authorized LRIP procurement of an
additional 1,500 MP. In accordance with the program's May 1, 2014 approved Acquisition Strategy, HMS procured 200 Full and Open Competition RR (100 per vendor).
In addition, the Government received all 2,052 LRIP SFF-B(v)1 Radios for Nett Warrior. Nett Warrior Radios are not a part of the HMS program and are procured for PEO Soldier; however, they are a part of the Rifleman Radio Army Acquisition Objective.

## Table 34
Foreign Military Sales
Notes
There are no FMS for the HMS program at this time.
HMS Tactical Radio products are categorized as "Major Defense Equipment" under the International Traffic in Arms Regulations. Export of Significant Military Equipment such as HMS must be approved by U.S. Department of State when embedded with Type 1 encryption. Coalition partners may purchase HMS tactical radios via FMS or possibly Direct Commercial Sales after the HMS radios successfully complete operational test and satisfy all certification requirements. In all cases, export of HMS products is subject to the following considerations: a previous export for a legacy capability does not constitute automatic approval for that legacy capability instantiated; due to embedded Type 1 encryption, all requests for sales will be adjudicated on a case-by-case basis and approved by the National Security Agency (NSA); tactical radios with waveforms installed must be certified by NSA; tactical radio waveforms, as individual products, are not authorized for sale or export.
Nuclear Costs
None

## Table 35
Unit Cost
Unit Cost Report
Item |  | BY 2011 $M | BY 2011 $M |  | % Change
|  | Current UCR Baseline (Oct 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 8242.6 |  |  | 8755.6
Quantity | 270951 |  |  | 271202
Unit Cost | 0.03 |  |  | 0.032 |  | 6.67
Average Procurement Unit Cost
Cost | 6987.9 |  |  | 7442.5
Quantity | 270369 |  |  | 270369
Unit Cost | 0.026 |  |  | 0.028 |  | 7.69
Item |  | BY 2011 $M | BY 2011 $M |  | % Change
|  | Original UCR Baseline (May 2004 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 9889.2 |  |  | 8755.6
Quantity | 329574 |  |  | 271202
Unit Cost | 0.03 |  |  | 0.032 |  | 6.67
Average Procurement Unit Cost
Cost | 9352.6 |  |  | 7442.5
Quantity | 328514 |  |  | 270369
Unit Cost | 0.028 |  |  | 0.028 |  | 0

## Table 36
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2011 $M | [7 empty] | TY $M
[12 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | May 2004 | [6 empty] | 0.03 |  |  |  |  | 0.028 |  |  |  | 0.033 |  |  |  | 0.031
APB as of January 2006 |  |  |  |  | May 2004 | [6 empty] | 0.03 |  |  |  |  | 0.028 |  |  |  | 0.033 |  |  |  | 0.031
Revised Original APB |  |  |  |  | N/A | [6 empty] | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Jan 2008 | [6 empty] | 0.032 |  |  |  |  | 0.023 |  |  |  | 0.036 |  |  |  | 0.027
Current APB |  |  |  |  | Oct 2011 | [6 empty] | 0.03 |  |  |  |  | 0.026 |  |  |  | 0.034 |  |  |  | 0.029
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 0.031 |  |  |  |  | 0.026 |  |  |  | 0.039 |  |  |  | 0.034
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 0.032 |  |  |  |  | 0.028 |  |  |  | 0.04 |  |  |  | 0.035
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  | Spt |  |  | Total
0.033 0.002 0.012 0.003 0.000 -0.018 0.000 0.002 0.001 0.034
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  | Oth |  | Spt |  |  | Total
0.034 0.000 0.000 0.004 0.000 0.000 0.000 0.002 0.006 0.040

## Table 37
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [10 empty] | APUC Production Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt | Total
0.031 0.002 0.013 0.003 0.000 -0.022 0.000 0.002 -0.002 0.029
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
0.029 0.000 0.000 0.004 0.000 -0.001 0.000 0.002 0.005 0.035
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  | N/A |  |  |  | N/A
Milestone B |  |  | N/A |  |  | Apr 2004 |  |  | Apr 2004 |  |  |  | Apr 2004
Milestone C |  |  | N/A |  |  | Mar 2008 |  |  | May 2011 |  |  |  | May 2011
IOC |  |  | N/A |  |  | Feb 2007 |  |  | Jan 2012 |  |  |  | Jul 2012
Total Cost (TY $M) |  |  | N/A |  |  | 10717 |  |  | 9201 |  |  |  | 10907
Total Quantity |  |  | N/A |  |  | 328674 |  |  | 270951 |  |  |  | 271202
PAUC |  |  | N/A |  |  | 0.033 |  |  | 0.034 |  |  |  | 0.04

## Table 38
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1238.5 7962.5 -- 9201.0
Economic |  | -3.5 |  | 71.7 |  | -- |  | 68.2
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 850.7 |  | -- |  | 850.7
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 65.8 |  | 30 |  | -- |  | 95.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 271 |  | -- |  | 271
Subtotal |  | 62.3 |  | 1223.4 |  | -- |  | 1285.7
Current Changes Economic |  | -2.1 |  | -66.2 |  | -- |  | -68.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 299.1 |  | -- |  | 299.1
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 27.4 |  | -168 |  | -- |  | -140.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 330.1 |  | -- |  | 330.1
Subtotal |  | 25.3 |  | 395 |  | -- |  | 420.3
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 87.6 |  | 1618.4 |  | -- |  | 1706
CE - Cost Variance |  | 1326.1 |  | 9580.9 |  | -- |  | 10907
CE - Cost & Funding |  | 1326.1 |  | 9580.9 |  | -- |  | 10907

## Table 39
Summary BY 2011 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1254.7 6987.9 -- 8242.6
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 36.6 |  | 103.6 |  | -- |  | 140.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 66.8 |  | -- |  | 66.8
Subtotal |  | 36.6 |  | 170.4 |  | -- |  | 207
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 154.8 |  | -- |  | 154.8
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 21.8 |  | -134 |  | -- |  | -112.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 263.4 |  | -- |  | 263.4
Subtotal |  | 21.8 |  | 284.2 |  | -- |  | 306
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 58.4 |  | 454.6 |  | -- |  | 513
CE - Cost Variance |  | 1313.1 |  | 7442.5 |  | -- |  | 8755.6
CE - Cost & Funding |  | 1313.1 |  | 7442.5 |  | -- |  | 8755.6
Previous Estimate: December 2014

## Table 40
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -2.1
Revised estimate as a result of Full and Open Competition testing strategy in FY 2015-2032 (Army). (Estimating)
+20.9 +26.5
Adjustment for current and prior escalation. (Estimating) +0.9 +0.9
RDT&E Subtotal +21.8 +25.3
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -66.2
Stretch-out of procurement buy profile from FY 2017 to FY 2032 to align with FY 2017 President's Budget (Army). (Schedule)
Stretch-out of procurement buy profile from FY 2031 to FY 2032 to align with FY 2017 President's Budget (Marine Corps). (Schedule)
Stretch-out of procurement buy profile from FY 2031 to FY 2032 to align with FY 2017 President's Budget (Navy). (Schedule)
Stretch-out of procurement buy profile from FY 2031 to FY 2032 to align with FY 2017 President's Budget (Air Force). (Schedule)
Additional schedule variance due to procurement buy profile shifting quantity in FY 2016 - FY 2032 to align with FY 2017 PB (Army). (Schedule)
Additional schedule variance due to procurement buy profile shifting quantity from FY 2022 - FY 2031 to FY 2023 - FY 2032 to align with FY 2017 PB (Marine Corps). (Schedule)
Additional schedule variance due to procurement buy profile shifting quantity from FY 2022 - FY 2031 to FY 2023 - FY 2032 to align with FY 2017 PB (Navy). (Schedule)
Additional schedule variance due to procurement buy profile shifting quantity from FY 2022 - FY 2031 to FY 2023 - FY 2032 to align with FY 2017 PB (Air Force). (Schedule)
0.0 +177.3
0.0 +1.8
0.0 +0.2
0.0 +3.2
+161.6 +120.0
-2.0 -1.3
-0.2 -0.1
-4.6 -2.0
Revised estimate to reflect actuals. (Estimating) -68.3 -73.7
Adjustment for current and prior escalation. (Estimating) +1.2 +1.1
Revised estimate to reflect current programmatic plans (Army). (Estimating) -70.9 -100.6 Revised estimate to reflect current programmatic plans (Marine Corps). (Estimating) +1.0 +1.1 Revised estimate to reflect current programmatic plans (Navy). (Estimating) 0.0 0.0
Revised estimate to reflect current programmatic plans (Air Force). (Estimating) +3.0 +4.1 Adjustment for current and prior escalation. (Support) +1.3 +1.5
Increase in Other Support costs to reflect current programmatic and fielding plans (Marine Corps). (Support)
Decrease in Other Support costs to reflect current programmatic and fielding plans (Navy). (Support)
Increase in Other Support costs to reflect current programmatic and fielding plans (Army). (Support)
Increase in Other Support costs to reflect current programmatic and fielding plans (Air Force). (Support)
Increase in Initial Spares costs to reflect LRIP actuals and current programmatic plans (Army). (Support)
+4.4 +5.7
-0.2 -0.2
+238.1 +293.7
+10.8 +15.3
+9.1 +14.0
Decrease in Initial Spares costs to reflect LRIP actuals and current programmatic plans (Air -0.1 0.0

## Table 41
Force). (Support)
Increase in Initial Spares costs to reflect LRIP actuals and current programmatic plans (Navy). (Support)
0.0 +0.1
Procurement Subtotal +284.2 +395.0

## Table 42
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Thales - Rifleman Radio FOC
Contractor: Thales Defense & Security, Inc.
Contractor Location: 22605 Gateway Center Dr.
Clarksburg, MD 20871
Contract Number: W15P7T-15-D-0015/1
Contract Type: Firm Fixed Price (FFP), Indefinite Delivery Indefinite Quantity (IDIQ)
Award Date: April 29, 2015
Definitization Date: April 29, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
2.3 N/A 0 2.6 N/A 100 2.6 2.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of field service representative support for testing.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP/IDIQ) contract.
General Contract Variance Explanation
Cost variance is not reported for this contract, because it is not required for FFP contracts.
Notes
This is the first time this contract is being reported.
This is a Firm Fixed Price contract that will be administered on an Indefinite Delivery Indefinite Quantity basis as task orders are awarded.

## Table 43
Contract Identification
Appropriation: Procurement
Contract Name: Harris - Rifleman Radio FOC
Contractor: Harris Corporation
Contractor Location: 1680 University Ave
Rochester, NY 14610
Contract Number: W15P7T-15-D-0016/1
Contract Type: Firm Fixed Price (FFP), Indefinite Delivery Indefinite Quantity (IDIQ)
Award Date: April 29, 2015
Definitization Date: April 29, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
2.0 N/A 0 2.2 N/A 100 2.2 2.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of field service representative support for testing.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP/IDIQ) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because it is not required for FFP contracts.
Notes
This is the first time this contract is being reported.
This is a Firm Fixed Price contract that will be administered on an Indefinite Delivery Indefinite Quantity basis as task orders are awarded.

## Table 44
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 833 | 833 | 833 | 100%
Production | 26905 | 26905 | 270369 | 9.95%
Total Program Quantity Delivered | 27738 | 27738 | 271202 | 10.23%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
10907
2016.7
18.49%
29
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
13
44.83%
2164.8
19.85%
The above data is current as of February 09, 2016.
As of February 9, 2016, the Government received 19,327 LRIP Rifleman Radios and 5,326 LRIP Manpack radios as well as 200 Full and Open Competition Rifleman Radios (100 per vendor) to support competition testing and eventual fielding. In addition, the Government received all 2,052 LRIP SFF-B(v)1 Radios for Nett Warrior. Nett Warrior Radios are not a part of the HMS program and are procured for Program Executive Office Soldier; however, they are a part of the Rifleman
Radio Army Acquisition Objective.

## Table 45
Operating and Support Cost
Cost Estimate Details
Date of Estimate: December 01, 2015
Source of Estimate: POE
Quantity to Sustain: 266343
Unit of Measure: Total Quantity
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2012 - FY 2052
Sustainment Life Breakdown:
Manpack Radio total quantity is 73,064, Sustainment Life is 20 years. Rifleman Radio total quantity is 193,279, Sustainment Life is 20 years.
Small Form Fit-B (quantity of 950) and Small Form Fit-D (quantity of 3,076) are sustained by the host platform, and therefore not included in this estimate.
Developmental units (quantity of 833) will not be sustained.
Sustainment Strategy
Rifleman Radio:
All LRIP radios procured under the development contract were initially sustained by the prime contractor until expiration of the contract on February 28, 2015. A follow-on Cost Plus Fixed Fee (CPFF) LRIP Sustainment Contract was awarded to the LRIP vendor on March 29, 2015 with one base year and one option year period of performance to maintain the software baseline, deliver updated logistics support documentation, provide Field Service Representative (FSR) support, and furnish technical support to address field/operational issues. Unserviceable radios will be returned to Tobyhanna Army Depot (TYAD) for inspection and testing. Field sustainment of LRIP radios and ancillary components will be accomplished through spares requisitions through the Standard Army Supply System (SASS).
All radios procured under Full and Open Competition that become unserviceable will be turned-in to TYAD through the SASS. Radios will be returned to the original equipment manufacturer for warranty repair or replacement. Full Rate Production radios may come with a standard and/or additional warranty based on the cost and value to the Government. Upon expiration of the warranty period, there is no current plan to perform depot-level repair of the radio. Final disposition of all unserviceable radios will be accomplished at TYAD. All Full and Open Competition contracts will contain provisions to procure sustainment spares to replace unserviceable radios and ancillary items requisitioned through SASS, operations, maintenance, training documentation, and the ability to procure the software development environment and data to maintain the software baseline.
Manpack (MP):
The development contract for LRIP radios included fixed-price options for the manufacturing of production ready MP radios for operational test to establish an initial production base, development of logistics support documentation, and sustainment support. A follow-on CPFF LRIP Sustainment Contract was awarded to the LRIP vendor on March 24, 2015 to the LRIP vendor to provide continued support of LRIP radios following the development contract. Contractor repair of unserviceable LRIP radios is planned to transition to organic repair at TYAD upon the expiration of the MP radio LRIP sustainment contract.

## Table 46
For Full and Open Competition, MP radios will be procured through a multiple award, Firm Fixed-Price, Indefinite Delivery/Indefinite Quantity contract. The contract provides for sustainment services, which includes: warranties, radio repairs, spares, delivery and update of training material, delivery and update of technical manuals/bulletins, training, FSR support, and the management and updates to the software and hardware baselines.
Antecedent Information
No Antecedent. By the nature of the waveforms used, Soldier Radio Waveform, in current HMS products and the tactical implementation of where the waveforms are found in the formations, there are no analogous current or legacy radios to the Manpack (LRIP AN/PRC-155 and future FOC variants) or the Rifleman Radio (LRIP AN/PRC-154A and future FOC variants - initial FOC variants AN/PRC-154B and AN/PRC-159).
Annual O&S Costs BY2011 $K
Cost Element |  | JTRS HMS Average Annual Cost Per Total Quantity | [5 empty] | No Antecedent (Antecedent) N/A
Unit-Level Manpower |  | 0 | [5 empty] | 0
Unit Operations |  | 0 | [5 empty] | 0
Maintenance |  | 1.965 | [5 empty] | 0
Sustaining Support |  | 0.047 | [5 empty] | 0
Continuing System Improvements |  | 0.135 | [5 empty] | 0
Indirect Support |  | 0 | [5 empty] | 0
Other |  | 0 | [5 empty] | 0
Total |  | 2.147 | [5 empty] | --
Item | Total O&S Cost $M
| JTRS HMS | [7 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 14710.4 |  |  | 16181.4 |  |  | 11439.1 |  | 0
Then Year | 20019.2 |  |  | N/A |  |  | 19112.6 |  | N/A
Equation to Translate Annual Cost to Total Cost
The Total O&S cost is the Average Annual Cost ($2.147K) * Total Number of Radios (266,343) * 20-year sustainment life / 1000.
O&S Cost Variance
Category |  |  | BY 2011 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
10683
Programmatic/Planning Factors 756.1 Revised estimate due to an update to reflect current
programmatic and fielding plans.
Cost Estimating Methodology 0.0

## Table 47
Cost Data Update | 0
Labor Rate | 0
Energy Rate | 0
Technical Input | 0
Other | 0
Total Changes | 756.1
Current Estimate | 11439.1
Disposal Estimate Details
Date of Estimate: December 01, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2011 $M): Total costs for disposal of all Total Quantity are 1209.2
The O&S estimate does not include Disposal costs in the amount of $1.209B (BY$ 2011).