## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-492
Patriot Advanced Capability-3 Missile Segment Enhancement (PAC-3 MSE)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 24
Foreign Military Sales 25
Nuclear Costs 25
Unit Cost 26
Cost Variance 29
Contracts 32
Deliveries and Expenditures 38
Operating and Support Cost 39

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Patriot Advanced Capability-3 Missile Segment Enhancement (PAC-3 MSE)
DoD Component
Army
Responsible Office
COL John M. Eggert Lower Tier Project Office Building 5250, Martin Road
Redstone Arsenal, AL 35898-8000
john.m.eggert2.mil@mail.mil
Phone: | 256-955-3240
Fax: | 256-955-3108
DSN Phone: | 645-3240
DSN Fax: | 645-4656
Date Assigned: | July 24, 2013
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated January 16, 2015
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated January 16, 2015

## Table 6
Mission and Description
The Patriot Advanced Capability-3 Missile Segment Enhancement (PAC-3 MSE) is a high velocity, hit-to-kill, surface-to-air missile capable of intercepting and destroying Tactical Ballistic Missiles (TBM) and air-breathing threats. The PAC-3 MSE is the follow-on variant of the PAC-3 missile. The PAC-3 MSE’s improved capability is achieved through a higher performance solid rocket motor, modified lethality enhancer, more responsive control surfaces, upgraded guidance software, and insensitive munitions improvements. The PAC-3 MSE employs kinetic energy to destroy targets through a hit-to-kill capability and provides the range, accuracy, and lethality to effectively defend against TBMs armed with weapons of mass destruction as well as providing expanded battlespace performance against complex threats. The PAC-3 MSE is
being integrated into the Patriot system requiring minor modifications to the launching station and using currently fielded system software, Post Deployment Build (PDB)-7. Additional system improvements, Radar Digital Processor and PDB-8 software are in process and, when fielded, enable the system to fully utilize the PAC-3 MSE kinematic capabilities.

## Table 7
Executive Summary
Since the prior SAR, the FY 2014 and FY 2015 PAC-3 MSE production contract undefinitized contract actions were definitized on October 28, 2015 (with the exception of tooling, obsolescence, and FMS unique contract line items to be definitized no later than 4th Quarter FY 2016). The FY 2016 PAC-3 MSE production priced option was also added to the FY 2014 and FY 2015 production contracts and partially exercised December 14, 2015 with final exercise expected August 2016.
PAC-3 MSE First Unit Equipped was established with 3-2 Air Defense Artillery on October 23, 2015. The Army Conditional Material Release was also approved on October 23, 2015.
On November 19, 2015, the Lower Tier Project Office successfully completed the first of four developmental flight tests for Post Deployment Build (PDB)-8 software using PAC-3 and Guidance Enhanced Missiles. On December 10, 2015, another successful flight test was conducted to demonstrate the capability of the Patriot system, using PDB-8 to detect, track, engage and kill a threat representative Tactical Ballistic Missile (TBM) with PAC-3 MSE missiles. The test demonstrated proper Patriot PDB-8 Battalion interaction (across and within the Information and Coordination Central and Firing Units) before, during and after engagement of a TBM.
The FY 2017 PB includes a program increase of $100.0M in FY 2016 for procurement of additional MSE missiles to support combatant commanders.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Acquisition Increment 2
MSE First Intercept | Feb 2010 | Feb 2010 | Feb 2010 | Feb 2010
MSE FUE | Dec 2015 | Dec 2015 | Jun 2016 | Oct 2015
MSE Milestone C | Mar 2014 | Mar 2014 | Mar 2014 | Mar 2014
MSE IOC | Dec 2016 | Dec 2016 | Jun 2017 | Dec 2016
MSE FRP | Dec 2017 | Dec 2017 | Jun 2018 | Dec 2017
Change Explanations
(Ch-1) MSE FUE Current Estimate changed from December 2015 to Octotober 2015 based on actual achievement. MSE FUE was established with the 3-2 Air Defense Artillery on October 23, 2015.
Notes
MSE FUE is considered achieved when the first Patriot Fire Unit is equipped with 12 MSE missiles.
MSE IOC is considered achieved when a Patriot Battalion, consisting of four Fire Units, is equipped with 12 MSE missiles per Fire Unit.
Acronyms and Abbreviations
FUE - First Unit Equipped

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
System Training
Proficiency Level
Soldiers (Operators, | Soldiers (Operators, | (T=O) Soldiers | Soldiers (Operators, | Soldiers (Operators,
Maintainers, and | Maintainers, and | (Operators, | Maintainers, and | Maintainers, and
Leaders) are able to | Leaders) are able to | Maintainers, and | Leaders) were able to | Leaders) are able to
perform critical tasks | perform critical tasks | Leaders) are able to | perform critical tasks | perform critical tasks
to standard 95% of | to standard 95% of | perform critical tasks | to standard 95% of | to standard 95% of
the time after training. | the time after training. | to standard 95% of | the time after training | the time after training.
|  | the time after training. | during logistics
demonstration and
test unit training.
Time to Train
Duration of | Duration of | (T=O) Duration of | Fire Centers of | Duration of
institutional training | institutional training | institutional training | Excellence currently | institutional training
shall be no more than | shall be no more than | shall be no more than | conducts AOC 14A in | shall be no more than
20 weeks for AOC | 20 weeks for AOC | 20 weeks for AOC | 18 weeks 3 days, 14E | 20 weeks for AOC
14A and MOSs 14E, | 14A and MOSs 14E, | 14A and MOSs 14E, | in 19 weeks 4 days, | 14A and MOSs 14E,
H, T, 140A, 35 weeks | H, T, 140A, 35 weeks | H, T, 140A, 35 weeks | 14H in 11 weeks 3 | H, T, 140A, 35 weeks
for MOS 140E to train | for MOS 140E to train | for MOS 140E to train | days, 14T in 10 | for MOS 140E to train
to use the system | to use the system | to use the system | weeks, 140A in 19 | to use the system
capabilities properly. | capabilities properly. | capabilities properly. | weeks 2 days and | capabilities properly.
140E in 35 weeks and
4 days.
Training Retention
Soldier sustainment | Soldier sustainment | (T=O) Soldier | Soldier sustainment | Soldier sustainment
training to maintain | training to maintain | sustainment training | training to maintain | training to maintain
proficiency shall be | proficiency shall be | to maintain | proficiency shall be | proficiency shall be
required quarterly, | required quarterly, | proficiency shall be | required quarterly, | required quarterly,
semi-annually, and | semi-annually, and | required quarterly, | semi-annually, and | semi-annually, and
annually. | annually. | semi-annually, and | annually in | annually.
|  | annually. | accordance with FM 3
-01.86, Air Defense
Artillery Patriot
Brigade Gunnery
Program.
Training Support
Training resources | Training resources | Training resources | All training support | Training resources
shall be capable of | shall be capable of | shall be capable of | materials to include | shall be capable of
providing 95% of | providing 95% of | providing 90% of | preliminary technical | providing 95% of
training individual and | training individual and | training individual and | manuals, New | training individual and
collective critical | collective critical | collective critical | Equipment Training | collective critical

## Table 11
tasks (march-order and emplacement, operations, maintenance, force operations, and engagement operations) related to tactically deployed systems while missiles are loaded. | tasks (march-order and emplacement, operations, maintenance, force operations, and engagement operations) related to tactically deployed systems while missiles are loaded. | tasks (march-order and emplacement, operations, maintenance, force operations, and engagement operations) related to tactically deployed systems while missiles are loaded. | Plans, Task Analysis', and Doctrine Impact Reports were provided to Fires Center of Excellence Directorate of Training Development and Doctrine. | tasks (march-order and emplacement, operations, maintenance, force operations, and engagement operations) related to tactically deployed systems while missiles are loaded.
Training Interoperability
System specific | System specific | (T=O) System | The Patriot weapons | System specific
training capabilities | training capabilities | specific training | system supports live, | training capabilities
shall interoperate with | shall interoperate with | capabilities shall | virtual and | shall interoperate with
and support collective | and support collective | interoperate with and | constructive training | and support collective
training with existing | training with existing | support collective | environments by | training with existing
live, virtual, and | live, virtual, and | training with existing | using TADSS to | live, virtual, and
constructive training | constructive training | live, virtual, and | conduct multi-level | constructive training
environments | environments | constructive training | training for both | environments
throughout the | throughout the | environments | operators and | throughout the
system lifecycle. | system lifecycle. | throughout the | maintenance | system lifecycle.
|  | system lifecycle. | personnel. With the
addition of DIS and
TADiL-J
demonstrated the
ability to participate in
a virtual environment
in both AC-12 and JC-
14. The constructive
environment was
demonstrated during
PoP Test 1
(connected two
PCOFT labs in
different states) and
PoP Test 2
(connected two
PCOFT labs in
different countries.)
Net Ready
The PAC-3 Increment | The PAC-3 Increment | The PAC-3 Increment | TBD | The PAC-3 Increment
2 system must fully | 2 system must fully | 2 system must fully |  | 2 system must fully
support execution of | support execution of | support execution of |  | support execution of
all operational | all operational | joint critical |  | all operational
activitives and | activitives and | operational activitives |  | activitives and
information | information | and information |  | information
exchanges identified | exchanges identified | exchanges identified |  | exchanges identified
in the DoD Enterprise | in the DoD Enterprise | in the DoD Enterprise |  | in the DoD Enterprise
Architecture and | Architecture and | Architecture and |  | Architecture and
solution architectures | solution architectures | solution architectures |  | solution architectures
based on integrated | based on integrated | based on integrated |  | based on integrated
DoDAF content, and | DoDAF content, and | DoDAF content, and |  | DoDAF content, and

## Table 12
must satisfy the | must satisfy the | must satisfy the |  | must satisfy the
technical | technical | technical |  | technical
requirements for | requirements for | requirements for |  | requirements for
transition to Net- | transition to Net- | transition to Net- |  | transition to Net-
Centric military | Centric military | Centric military |  | Centric military
operations to include: | operations to include: | operations to include: |  | operations to include:
(1) Solution | (1) Solution | (1) Solution |  | (1) Solution
architecture products; | architecture products; | architecture products; |  | architecture products;
(2) Compliant with | (2) Compliant with | (2) Compliant with Net |  | (2) Compliant with
Net-Centric data | Net-Centric data | -Centric data strategy |  | Net-Centric data
strategy and Net- | strategy and Net- | and Net-Centric |  | strategy and Net-
Centric Services | Centric Services | Services strategy; (3) |  | Centric Services
strategy; (3) | strategy; (3) | Compliant with GIG |  | strategy; (3)
Compliant with GIG | Compliant with GIG | Technical Guidance; |  | Compliant with GIG
Technical Guidance; | Technical Guidance; | (4) Information |  | Technical Guidance;
(4) Information | (4) Information | assurance |  | (4) Information
assurance | assurance | requirements; (5) |  | assurance
requirements; (5) | requirements; (5) | Supportability |  | requirements; (5)
Supportability | Supportability | requirements. |  | Supportability
requirements. | requirements. |  |  | requirements.
Sustainment Reliability
The material | The material | The material | Will be demonstrated | The material
sustainment reliability | sustainment reliability | sustainment reliability | during Post | sustainment reliability
will exceed 41 hours | will exceed 41 hours | will exceed 20 hours | Deployment Build-8 | will exceed 20 hours
MTBCMF. | MTBCMF. | MTBCMF. | and Radar Digital | MTBCMF.
Processor-
Configuration
Operational testing.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Patriot Advanced Capability-3 (PAC-3) Increment 2 CPD dated January 24, 2013
Change Explanations
None
Notes

## Table 13
Acronyms and Abbreviations
AC-12 - Austere Challenge 2012 AOC - Area of Concentration
DIS - Distributive Interactive Simulation
DoDAF - Department of Defense Architecture Format FM - Field Manual
GIG - Global Information Grid JC-14 - Juniper Cobra 2014
MOS - Military Occupational Specialty
MTBCMF - Mean Time Between Critical Mission Failure O - Objective
PCOFT - Patriot Conduct of Fire Trainer PoP - Proof of Principle
T - Threshold
TADiL-J - Tactical Digital Information Link-Joint
TADSS - Training Aids, Devices, Simulators, and Simulations

## Table 14
Track to Budget
RDT&E
Appn |  | BA | PE
Army | 2040 05 |  | 0605456A
| Project |  | Name
| PA3 |  | PATRIOT PAC-3/Missile Segment Enhancement | (S | hared)
Procurement
Army | 2032 02 |  | 0605456A
| Line Item |  | Name
| C53101 |  | MSE Missile
MILCON
Army | 2050
| Project |  | Name
Notes
Appn |  | BA | PE
Appn |  | BA | PE
A budget activity code for MILCON is not yet established.

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2014 $M |  |  |  | BY 2014 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 940.8 |  | 940.8 | 1034.9 |  | 932.8 |  | 871.1 |  | 871.1 |  | 869.8
Procurement | 5087.2 |  | 5087.2 | 5595.9 |  | 5334.9 |  | 5840.7 |  | 5840.7 |  | 6020
Flyaway | -- |  | -- | -- |  | 4883.5 |  | -- |  | -- |  | 5507.4
Recurring | -- |  | -- | -- |  | 4802.1 |  | -- |  | -- |  | 5426.2
Non Recurring | -- |  | -- | -- |  | 81.4 |  | -- |  | -- |  | 81.2
Support | -- |  | -- | -- |  | 451.4 |  | -- |  | -- |  | 512.6
Other Support | -- |  | -- | -- |  | 451.4 |  | -- |  | -- |  | 512.6
Initial Spares | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON | 9 |  | 9 | 9.9 |  | 9.2 |  | 10.5 |  | 10.5 |  | 10.5
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 6037 |  | 6037 | N/A |  | 6276.9 |  | 6722.3 |  | 6722.3 |  | 6900.3
Current APB Cost Estimate Reference
Army Cost Position dated February 28, 2014
Confidence Level
Confidence Level of cost estimate for current APB: 85%
The PAC-3 MSE missile Program Office Estimate is estimated at a confidence level of 85%. Over 90% of the RDT&E nbsp;costs are sunk; however, there are still Initial Operational Test and Evaluation flight tests remaining that are planned through FY 2017. The PAC-3 MSE missile is a variation of the current PAC-3 missile; therefore, there was substantial PAC
-3 cost data available to support the PAC-3 MSE missile cost estimate. There are design changes to several components of the missile, which prevent using a higher confidence level.
Cost Notes
The PAC-3 MSE APB objective Cost and Quantity represent total Army requirements with planned procurement from FY 2014 to FY 2025. The Army will continue to assess complex threats, technology improvements, and material obsolescence for impacts and implementation to the current product configuration baseline.

## Table 16
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 1057 | 1057 | 1125
Total | 1057 | 1057 | 1125

## Table 17
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 867.5 | 2.3 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 869.8
Procurement | 1161.8 | 514.9 |  |  | 423.2 | 459.1 | 497 |  | 529.8 |  | 520.5 |  |  | 1913.7 |  | 6020
MILCON | 0 | 0 |  |  | 0 | 0 | 10.5 |  | 0 |  | 0 |  |  | 0 |  | 10.5
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 2029.3 | 517.2 |  |  | 423.2 | 459.1 | 507.5 |  | 529.8 |  | 520.5 |  |  | 1913.7 |  | 6900.3
PB 2016 Total | 2030.6 | 417.2 |  |  | 430.6 | 462.7 | 504.1 |  | 569.5 |  | 519.4 |  |  | 1892.1 |  | 6826.2
Delta | -1.3 | 100 |  |  | -7.4 | -3.6 | 3.4 |  | -39.7 |  | 1.1 |  |  | 21.6 |  | 74.1
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 200 |  | 112 | 85 | 93 |  | 95 |  | 95 | 95 |  | 350 |  | 1125
PB 2017 Total | 0 |  | 200 |  | 112 | 85 | 93 |  | 95 |  | 95 | 95 |  | 350 |  | 1125
PB 2016 Total | 0 |  | 200 |  | 80 | 85 | 93 |  | 95 |  | 104 | 90 |  | 346 |  | 1093
Delta | 0 |  | 0 |  | 32 | 0 | 0 |  | 0 |  | -9 | 5 |  | 4 |  | 32

## Table 18
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 101.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 75.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 115.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 125.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 869.8

## Table 19
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 74.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 114.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 125.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 121.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 128.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 68.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 932.8

## Table 20
Annual Funding 2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | 70.4 |  | 70.4 |  | -- |  | 70.4
2013 |  | -- | -- |  | -- |  | 10.8 |  | 10.8 |  | -- |  | 10.8
2014 |  | 92 | 508.9 |  | -- |  | -- |  | 508.9 |  | 39.1 |  | 548
2015 |  | 108 | 492.7 |  | -- |  | -- |  | 492.7 |  | 39.9 |  | 532.6
2016 |  | 112 | 474.3 |  | -- |  | -- |  | 474.3 |  | 40.6 |  | 514.9
2017 |  | 85 | 381.8 |  | -- |  | -- |  | 381.8 |  | 41.4 |  | 423.2
2018 |  | 93 | 416.9 |  | -- |  | -- |  | 416.9 |  | 42.2 |  | 459.1
2019 |  | 95 | 454 |  | -- |  | -- |  | 454 |  | 43 |  | 497
2020 |  | 95 | 486 |  | -- |  | -- |  | 486 |  | 43.8 |  | 529.8
2021 |  | 95 | 475.9 |  | -- |  | -- |  | 475.9 |  | 44.6 |  | 520.5
2022 |  | 90 | 468.9 |  | -- |  | -- |  | 468.9 |  | 45.5 |  | 514.4
2023 |  | 90 | 448.2 |  | -- |  | -- |  | 448.2 |  | 46.4 |  | 494.6
2024 |  | 90 | 424.9 |  | -- |  | -- |  | 424.9 |  | 47.2 |  | 472.1
2025 |  | 80 | 393.7 |  | -- |  | -- |  | 393.7 |  | 38.9 |  | 432.6
Subtotal |  | 1125 | 5426.2 |  | -- |  | 81.2 |  | 5507.4 |  | 512.6 |  | 6020

## Table 21
Annual Funding 2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | -- | -- |  | -- |  | 70.8 |  | 70.8 |  | -- |  | 70.8
2013 |  | -- | -- |  | -- |  | 10.6 |  | 10.6 |  | -- |  | 10.6
2014 |  | 92 | 496.4 |  | -- |  | -- |  | 496.4 |  | 38.1 |  | 534.5
2015 |  | 108 | 473.9 |  | -- |  | -- |  | 473.9 |  | 38.3 |  | 512.2
2016 |  | 112 | 447.7 |  | -- |  | -- |  | 447.7 |  | 38.4 |  | 486.1
2017 |  | 85 | 353.6 |  | -- |  | -- |  | 353.6 |  | 38.4 |  | 392
2018 |  | 93 | 378.6 |  | -- |  | -- |  | 378.6 |  | 38.4 |  | 417
2019 |  | 95 | 404.2 |  | -- |  | -- |  | 404.2 |  | 38.3 |  | 442.5
2020 |  | 95 | 424.3 |  | -- |  | -- |  | 424.3 |  | 38.2 |  | 462.5
2021 |  | 95 | 407.3 |  | -- |  | -- |  | 407.3 |  | 38.2 |  | 445.5
2022 |  | 90 | 393.4 |  | -- |  | -- |  | 393.4 |  | 38.2 |  | 431.6
2023 |  | 90 | 368.7 |  | -- |  | -- |  | 368.7 |  | 38.2 |  | 406.9
2024 |  | 90 | 342.7 |  | -- |  | -- |  | 342.7 |  | 38 |  | 380.7
2025 |  | 80 | 311.3 |  | -- |  | -- |  | 311.3 |  | 30.7 |  | 342
Subtotal |  | 1125 | 4802.1 |  | -- |  | 81.4 |  | 4883.5 |  | 451.4 |  | 5334.9

## Table 22
Annual Funding 2050 ¦ MILCON ¦ Military Construction, Army
Fiscal Year | TY $M
Total Program
2019 10.5
Subtotal 10.5

## Table 23
Annual Funding 2050 ¦ MILCON ¦ Military Construction, Army
Fiscal Year | BY 2014 $M
Total Program
2019 9.2
Subtotal 9.2

## Table 24
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2004-08-06 | 2014-03-27
Approved Quantity | 148 | 330
Reference | Milestone B ADM | Milestone C ADM
Start Year | 2010 | 2014
End Year | 2011 | 2018
The Current Total LRIP Quantity is more than 10% of the total production quantity in accordance with the March 27, 2014 ADM which approved a PAC-3 MSE LRIP quantity of 330 based on an Army Acquisition Objective (AAO) of 3,376 missiles. Procurement is expected to continue beyond the approved program with current or future MSE variants to meet the AAO.

## Table 25
Foreign Military Sales
None
Nuclear Costs
None

## Table 26
Unit Cost
Unit Cost Report
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Current UCR Baseline (Jan 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 6037 |  |  | 6276.9
Quantity | 1057 |  |  | 1125
Unit Cost | 5.711 |  |  | 5.579 |  |  | -2.32
Average Procurement Unit Cost
Cost | 5087.2 |  |  | 5334.9
Quantity | 1057 |  |  | 1125
Unit Cost | 4.813 |  |  | 4.742 |  |  | -1.47
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Original UCR Baseline (Aug 2004 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 7664 |  |  | 6276.9
Quantity | 1528 |  |  | 1125
Unit Cost | 5.016 |  |  | 5.579 |  | 11.23
Average Procurement Unit Cost
Cost | 7096.2 |  |  | 5334.9
Quantity | 1528 |  |  | 1125
Unit Cost | 4.644 |  |  | 4.742 |  | 2.11

## Table 27
Unit Cost History
Item | [7 empty] | Date |  |  |  |  | BY 2014 $M | [6 empty] | TY $M
[13 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Aug 2004 | [7 empty] | 5.016 |  |  |  | 4.644 |  |  |  | 5.272 |  |  |  | 4.957
APB as of January 2006 |  |  |  |  | Aug 2004 | [7 empty] | 5.016 |  |  |  | 4.644 |  |  |  | 5.272 |  |  |  | 4.957
Revised Original APB |  |  |  |  | N/A | [7 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Aug 2004 | [7 empty] | 5.016 |  |  |  | 4.644 |  |  |  | 5.272 |  |  |  | 4.957
Current APB |  |  |  |  | Jan 2015 | [7 empty] | 5.711 |  |  |  | 4.813 |  |  |  | 6.36 |  |  |  | 5.526
Prior Annual SAR |  |  |  |  | Dec 2014 | [7 empty] | 5.643 |  |  |  | 4.781 |  |  |  | 6.245 |  |  |  | 5.439
Current Estimate |  |  |  |  | Dec 2015 | [7 empty] | 5.579 |  |  |  | 4.742 |  |  |  | 6.134 |  |  |  | 5.351
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  | Spt |  |  | Total
5.272 0.311 0.411 0.398 0.000 0.126 0.000 -0.158 1.088 6.360
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth | Spt |  |  | Total
6.360 -0.040 -0.240 -0.022 0.000 0.072 0.000 0.004 -0.226 6.134

## Table 28
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [12 empty] | APUC Production Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  | Oth |  | Spt | Total
4.957 0.287 0.286 0.398 0.000 -0.244 0.000 -0.158 0.569 5.526
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [12 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth | Spt | Total
5.526 -0.039 -0.191 -0.022 0.000 0.073 0.000 0.004 -0.175 5.351
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  |  | Mar 2014 |  |  |  |  | Mar 2014 |  |  | Mar 2014
IOC |  |  | N/A |  |  |  | Dec 2016 |  |  |  |  | Dec 2016 |  |  | Dec 2016
Total Cost (TY $M) |  |  | N/A |  |  |  | 8056 |  |  |  |  | 6722.3 |  |  | 6900.3
Total Quantity |  |  | N/A |  |  |  | 1528 |  |  |  |  | 1057 |  |  | 1125
PAUC |  |  | N/A |  |  |  | 5.272 |  |  |  |  | 6.36 |  |  | 6.134

## Table 29
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 871.1 | 5840.7 | 10.5 | 6722.3
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | 114.6 | -- | 114.6
Other | -- | -- | -- | --
Support | -- | -10.7 | -- | -10.7
Subtotal | -- | 103.9 | -- | 103.9
Current Changes
Economic | -0.6 | -43.8 | -0.1 | -44.5
Quantity | -- | 161.1 | -- | 161.1
Schedule | -- | -24.9 | -- | -24.9
Engineering | -- | -- | -- | --
Estimating | -0.7 | -32.7 | 0.1 | -33.3
Other | -- | -- | -- | --
Support | -- | 15.7 | -- | 15.7
Subtotal | -1.3 | 75.4 | -- | 74.1
Adjustments | -- | -- | -- | --
Total Changes | -1.3 | 179.3 | -- | 178
CE - Cost Variance | 869.8 | 6020 | 10.5 | 6900.3
CE - Cost & Funding | 869.8 | 6020 | 10.5 | 6900.3

## Table 30
Summary BY 2014 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 940.8 | 5087.2 | 9 | 6037
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -7.3 | 152.6 | 0.1 | 145.4
Other | -- | -- | -- | --
Support | -- | -14.2 | -- | -14.2
Subtotal | -7.3 | 138.4 | 0.1 | 131.2
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | 127.4 | -- | 127.4
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -0.7 | -30.9 | 0.1 | -31.5
Other | -- | -- | -- | --
Support | -- | 12.8 | -- | 12.8
Subtotal | -0.7 | 109.3 | 0.1 | 108.7
Adjustments | -- | -- | -- | --
Total Changes | -8 | 247.7 | 0.2 | 239.9
CE - Cost Variance | 932.8 | 5334.9 | 9.2 | 6276.9
CE - Cost & Funding | 932.8 | 5334.9 | 9.2 | 6276.9
Previous Estimate: December 2014

## Table 31
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -0.6
Change in estimating assumptions due to application of new escalation indices. (Estimating)
-1.3 -1.3
Adjustment for current and prior escalation. (Estimating) +0.6 +0.6
RDT&E Subtotal -0.7 -1.3
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -43.8
Quantity variance resulting from an increase of 32 missiles from 1,093 to 1,125. (Subtotal) +127.9 +161.8
Quantity variance resulting from an increase of 32 missiles from 1,093 to 1,125. (Quantity)
(+127.4) (+161.1)
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (+0.5) (+0.7)
Acceleration of procurement buy profile to reflect increase in missile quantity in FY 2016. (Schedule) (QR)
Allocation to Estimating resulting from program quantity increase in FY 2016. (Estimating) (QR)
0.0 -24.9
-39.9 -42.1
Adjustment for current and prior escalation. (Estimating) +8.5 +8.7
Adjustment for current and prior escalation. (Support) +0.6 +0.8
Increase in Other Support due to revised estimate to reflect program quantity increase in FY 2016. (Support) (QR)
+12.2 +14.9
Procurement Subtotal +109.3 +75.4
(QR) Quantity Related
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.1
Change in estimating assumptions due to application of new escalation indices. (Estimating) | 0.1 | 0.1
MILCON Subtotal | 0.1 | 0

## Table 32
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: MSE IPF
Contractor: Lockheed Martin Missiles and Fire Control
Contractor Location: P.O. Box 650003
Dallas, TX 75265-0003
Contract Number: W31P4Q-12-C-0001
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: July 02, 2012
Definitization Date: July 02, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
69.0 N/A 0 76.3 N/A 0 77.9 79.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a contract modification to extend the period of performance to fabricate four missile assemblies and purchase several major subcontractor components (ignition safety devices, lethality enhancers, batteries, and thermally initiated venting systems).
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (8/31/2015) -4.3 +0.4
Previous Cumulative Variances -3.9 +0.4
Net Change -0.4 +0.0
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to delay in receipt of replacement thermal batteries.
Notes
The purpose of the effort is to set forth the requirements for the manufacture, modification, and/or procurement of production special tooling, special test equipment, and special inspection equipment to support the PAC-3 MSE missile program. The Initial Production Facilities (IPF) equipment is to be proven out and in place 24 months following contract award. The PAC-3 MSE IPF contract stresses production of MSE missiles at the lowest feasible life cycle cost. The objective of the PAC-3 MSE IPF is to establish and sustain the capability to produce PAC-3 MSE missiles at a rate of up to 20 per month. The contract was awarded and definitized on July 2, 2012, with a total contract value of $69.0M. The contract was completed on August 31, 2015.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 33
Contract Identification
Appropriation: Procurement
Contract Name: FY 2014 PAC-3/MSE Production
Contractor: Lockheed Martin Missiles and Fire Control
Contractor Location: P.O. Box 650003
Dallas, TX 75265-0003
Contract Number: W31P4Q-14-C-0034
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 31, 2013
Definitization Date: December 28, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
263.4 N/A 56 1305.7 1379.2 300 1305.7 1305.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications to add U.S. PAC-3 MSE missiles, PAC-3 FMS missile quantities, and FMS ground support equipment.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +2.1 -2.1
Previous Cumulative Variances 0.0 0.0
Net Change +2.1 -2.1
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to less than planned expenditure dependent on the return of reworked MSE actuators by the subcontractor.
The unfavorable cumulative schedule variance is due to all MSE actuators being returned to the subcontractor for rework because of a component qualification failure; continuation of efforts to develop a path for compliant MSE batteries from both subcontractors; and a Lot Acceptance Test failure of thermally initiated venting system units to determine root cause of failure and corrective action.

## Table 34
Notes
The FY 2014 PAC-3 Cost Reduction Initiative (CRI) missile and PAC-3 MSE Production contract was awarded on December 31, 2013 to Lockheed Martin Missiles and Fire Control, Dallas, Texas, as a Not to Exceed letter contract valued at $263.4M ($203.9M U.S. and $59.5M FMS). The original effort includes 56 PAC-3 CRI missiles for the U.S.
Army, seven Launcher Modification Kits (LMK), one portable four-pack test set and FMS initial spares, and missile/LMK production tooling.
On March 28, 2014, the contract was modified to change the contract type from Firm Fixed Price to FPIF. The modification added 92 PAC-3 MSE missiles, 50 LMKs, associated hardware, and initial spares. The PAC-3 CRI and PAC-3 MSE missiles share a high degree of commonality, therefore, combining requirements on a single production contract yields cost synergies.
On October 14, 2014, the contract was modified to add FMS case requirements for 152 PAC-3 CRI missiles, 15 LMKs, and other associated ground support equipment.
On October 28, 2015, the FY 2014 PAC-3 MSE production contract was modified to definitize all FY 2014 requirements. PAC-3 MSE deliveries began in 4th Quarter FY 2015.

## Table 35
Contract Identification
Appropriation: Procurement
Contract Name: FY 2015 PAC-3/MSE Production
Contractor: Lockheed Martin Missiles and Fire Control
Contractor Location: P.O. Box 650003
Dallas, TX 75265-0003
Contract Number: W31P4Q-14-C-0034/2
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: July 23, 2015
Definitization Date:
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1314.1 N/A 108 1314.1 1467.7 330 1314.1 1314.1
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances -- --
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract because EVM reporting has not commenced due to on-going negotiations. The majority of the contract requirements were definitized on October 28, 2015; however, the remaining Not to Exceed (NTE) requirements remain in negotiation and are projected to be complete in 4th Quarter FY 2016. EVM reporting on the contract will begin when all contract requirements are definitized.
Notes
This is the first time this contract is being reported.
On July 23, 2015, the contract was modified to add the FY 2015 production requirements. The modification added the following requirements: 108 U.S. PAC-3 MSE missiles (to include four test missiles) and other associated ground support equipment,16 U.S. PAC-3 Cost Reduction Initiative (CRI) missiles, 206 FMS PAC-3 CRI missiles, other associated ground support equipment, and 36 FMS Launcher Modification Kits. This modification also included NTEs for tooling and obsolescence requirements.
FY 2015 PAC-3 MSE deliveries are scheduled to begin in 2nd Quarter FY 2017.

## Table 36
Contract Identification
Appropriation: Procurement
Contract Name: FY 2016 PAC-3/MSE Production
Contractor: Lockheed Martin Missiles and Fire Control
Contractor Location: P.O. Box 650003
Dallas, TX 75265-0003
Contract Number: W31P4Q-14-C-0034/3
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 16, 2015
Definitization Date:
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1210.0 N/A 336 1210.0 1455.7 336 1210.0 1210.0
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances -- --
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because EVM reporting has not commenced due to on- going negotiations. The majority of the contract requirements were definitized on December 16, 2015; however, the remaining Not to Exceed requirements remain in negotiation and are projected to be complete in 4th Quarter FY 2016. EVM reporting on the contract will begin when all contract requirements are definitized.
Notes
This is the first time this contract is being reported.
On December 16, 2015, the contract was modified to exercise the FY 2016 option production requirements. The modification added only a part of total requirements due to being under continuing resolution at the time of the modification. Contract requirements include: 48 U.S. PAC-3 MSE missiles (to include four test missiles) and other associated ground support equipment, 288 FMS PAC-3 Cost Reduction Iniative missiles and associated ground support equipment, and 37 FMS PAC-3 Launcher Modification Kits.
PAC-3 MSE deliveries are scheduled to begin in 3rd Quarter FY 2018.

## Table 37
Contract Identification
Appropriation: Procurement
Contract Name: PAC-3 MSE MRT/ERT
Contractor: Lockheed Martin Missiles and Fire Control
Contractor Location: 1401 West Marshall Drive
Grand Prairie, TX 75051-2806
Contract Number: W31P4Q-15-C-0039
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 03, 2014
Definitization Date: October 30, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
46.2 48.8 132 46.2 48.8 132 46.9 48.8
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/20/2015) -4.5 -2.1
Previous Cumulative Variances -- --
Net Change -4.5 -2.1
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to to hardware requirements costing more than originally budgeted, issues with tube vendor requiring development of testing procedures and fixtures, issues with machined skid support casting vendor requiring tooling rework, engineering redesign efforts, and tooling issues.
The unfavorable cumulative schedule variance is due to design engineering, supplier parts, tooling issues and planning, programming, and control efforts being behind schedule due to fabrication of tactical Missile Round Trainers (MRT) and Empty Round Trainers (ERT) being behind schedule.
Notes
This is the first time this contract is being reported.
The PAC-3 MSE MRT and ERT production effort was awarded with a Not to Exceed value of $49.96M on December 3, 2014 to Lockheed Martin Missiles and Fire Control. The contract was definitized on October 30, 2015. The MRT/ERT program objective is to provide MSE canister training capability by delivering 132 total units. This effort also includes production rate tooling and test equipment.

## Table 38
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 15 | 27 | 1125 | 2.4%
Total Program Quantity Delivered | 15 | 27 | 1125 | 2.4%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
6900.3
1207.5
17.5%
22
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
13
59.09%
2546.5
36.9%
The above data is current as of February 09, 2016.

## Table 39
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 19, 2016
Source of Estimate: POE
Quantity to Sustain: 1125
Unit of Measure: Total Quantity
Service Life per Unit: 30.00 Years
Fiscal Years in Service: FY 2015 - FY 2057
The PAC-3 MSE approved APB procurement quantity is 1,057 missiles; however, the program received Congressional plus-ups in FY 2015 and FY 2016 to buy additional missiles and the program's current estimate is now 1,125 missiles.
The current O&S cost estimate for the PAC-3 MSE missile was updated since APB approval to reflect the program procurement quantity current estimate. The estimate includes the repair and recertification of PAC-3 MSE missiles. In addition, it includes all sustainment tasks needed to maintain the missile.
Sustainment Strategy
The missile is transported and operates in a sealed container as a self-contained major end item and does not require sustainment in the field. The missile will be certified twice, at ten-year intervals, within its 30-year planned service
life. Interim Contractor Support will be the sustainment strategy until an organic capability is established in FY 2021 (IOC plus four years). Once established, missiles will be shipped to Letterkenny Army Depot for diagnosis/testing, de-canning, repair and return of faulty or degraded missile subassemblies, reassembly, re-coating, and re-canning. Checkout and fault detection/isolation will be accomplished using depot test, measurement, and diagnostic equipment and peculiar test/support equipment. Missile sub-assemblies (five major sections) are returned to the original equipment manufacturer for repair. After the missile is repaired, an inspection will be performed prior to inserting the missile back into its tube to verify that current tactical software was uploaded as required.
Antecedent Information
No Antecedent
Annual O&S Costs BY2014 $M
Cost Element | PAC-3 MSE Average Annual Cost Per Total Quantity | No Antecedent (Antecedent)
Unit-Level Manpower | -- | --
Unit Operations | -- | --
Maintenance | 35.744 | --
Sustaining Support | 14.66 | --
Continuing System Improvements | 14.058 | --
Indirect Support | -- | --
Other | -- | --
Total | 64.462 | --

## Table 40
Item | Total O&S Cost $M
| PAC-3 MSE | [5 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 2660.6 |  | 2926.7 |  |  | 2771.9 | N/A
Then Year | 4354.3 |  | N/A |  |  | 4574.7 | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
Total Missile O&S = $64.462 (Average Annual O&S Cost) x 43 (years of service life) = $2771.9M
O&S Cost Variance
Category |  | BY 2014 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
2702.5
Programmatic/Planning Factors 69.4 O&S cost estimate revised to reflect program increase of 32 missiles from 1,093 to 1,125.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 69.4
Current Estimate 2771.9
Disposal Estimate Details
Date of Estimate: January 19, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2014 $M): Total costs for disposal of all Total Quantity are 13.8
Demilitarization costs were provided by Army Environmental Command.