## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-466
Paladin Integrated Management (PIM)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 23
Foreign Military Sales 24
Nuclear Costs 24
Unit Cost 25
Cost Variance 28
Contracts 31
Deliveries and Expenditures 33
Operating and Support Cost 34

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Paladin Integrated Management (PIM)
DoD Component
Army
Responsible Office
COL James Schirmer
6501 East Eleven Mile Road Warren, MI 48397
james.w.schirmer.mil@mail.mil
Phone: | 586-282-5927
Fax: | 586-282-8892
DSN Phone: | 786-5927
DSN Fax: | 786-8892
Date Assigned: | July 10, 2014
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 09, 2014
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 9, 2014

## Table 6
Mission and Description
The M109 Family of Vehicles (FOV) 155-millimeter / 39-caliber Self-Propelled Howitzer (SPH) provides the primary indirect fire support for full spectrum operations. It has the ability to support Armored Brigade Combat Teams, Infantry Brigade Combat Teams, and Stryker Brigade Combat Teams. The M109 FOV Carrier Ammunition Tracked (CAT) provides armored ammunition supply support to the SPH operating in support of full spectrum operations. Together, the M109 FOV is also referred to as Paladin Integrated Management (PIM) weapon (vehicle) system.
The M109A6 Paladin and the M992A2 Field Artillery Ammunition Support Vehicle (FAASV) are the currently fielded versions of the Army’s SPH and CAT. The PIM SPH and CAT will replace the M109A6 Paladin and M992A2 FAASV. Together, the M109A6 and M992A2 are also referred to as Paladin/FAASV weapon (vehicle) system.
The PIM program allows growth for improved force protection and technology insertion. PIM regains lost performance in the M109 FOV by addressing size, weight, and power issues. The program helps to ensure greater vehicle supportability, maintainability, and interoperability by leveraging fleet commonality for key components, replacing aging and obsolete components, and leveraging Bradley and Non-Line-of-Sight Cannon technology.

## Table 7
Executive Summary
PIM is a post-Milestone C program in Production and Deployment. The second option of an LRIP contract (Fixed Price Incentive Firm Target) was awarded to BAE Systems on October 30, 2015. The program received an ADM dated September 11, 2015 delegating program management of the M109A7 FOV from OSD to the Secretary of the Army.
Production is underway at both the York, Pennsylvania and Elgin, Oklahoma facilities. RDT&E-funded work supporting LRIP continues under the EMD contract modification and Production Qualification Testing (PQT) began as scheduled in April 2015. FRP remains on schedule to start 2nd Quarter FY 2017. The original equipment manufacturer delivered all Technical and Operator Manuals needed to begin Logistics Demonstration (LOGDEMO) and Technical Manual Verification.
Despite quality control issues with the engine which forced the program to adjust the test schedule, the program is on track to achieve FRP in 2nd Quarter FY 2017. Testing continues at Aberdeen Proving Ground, Yuma Proving Ground, White Sands Missile Range, and Cold Region Test Center and preliminary results have been positive. However, we identified technical issues on some components that caused some delays in test events. As an example, some, but not all, vehicles demonstrate an overheating condition. The team determined the root cause and is in the process of making corrections on the vehicles.
Based on the above test delays, the program office and the Army Test and Evaluation Command are determining those test events that must be completed in order to enter Initial Operational Test and Evaluation (IOT&E). Those events will be
our focus and used to set component replacement priority. The program is now meeting or exceeding all OSD goals for Obligations and Disbursements. The program is fully funded for FY 2016 in both RDT&E and Procurement to support PQT, IOT&E, and LOGDEMO.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Developmental Test Start | May 2011 | May 2011 | May 2011 | May 2011
Milestone C | Oct 2013 | Oct 2013 | Oct 2013 | Oct 2013
First Production Delivery | Jun 2015 | Jun 2015 | Dec 2015 | Mar 2015
Operational Test Start | Jun 2016 | Jun 2016 | Dec 2016 | Oct 2016
First Unit Equipped | Jan 2017 | Jan 2017 | Jul 2017 | Mar 2017
Full Rate Production | Jan 2017 | Jan 2017 | Jul 2017 | Mar 2017
IOC | Apr 2017 | Apr 2017 | Oct 2017 | Jun 2017
FOC | Mar 2020 | Mar 2020 | Sep 2020 | May 2020
Change Explanations
(Ch-1) The Current Estimates for IOT&E, FUE, FRP, IOC and FOC changed from June 2016, January 2017, January 2017, April 2017 and March 2020 to October 2016, March 2017, March 2017, June 2017 and May 2020, respectively, as risk reduction responses to fact-of-life budgetary and programmatic changes.

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
KPP 1: Net-Ready
The capability, system, | The capability, system, | The capability, system, | To be | PIM
and/or service must fully | and/or service must fully | and/or service must fully | determined | management
support execution of all | support execution of all | support execution of joint | during IA Cyber | estimates
operational activities and | operational activities and | critical operational | Security | that the
information exchanges | information exchanges | activities and information | Testing. | program will
identified in DoD | identified in DoD | exchanges identified in the |  | achieve the
Enterprise Architecture | Enterprise Architecture | DoD Enterprise |  | Threshold
and solution architectures | and solution architectures | Architecture and solution |  | requirement.
based on integrated | based on integrated | architectures based on
DoDAF content, and must | DoDAF content, and must | integrated DoDAF content,
satisfy the technical | satisfy the technical | and must satisfy the
requirements for transition | requirements for transition | technical requirements for
to Net-Centric military | to Net-Centric military | transition to Net-Centric
operations to include: 1) | operations to include: 1) | military operations to
Solution architecture | Solution architecture | include: 1) Solution
products compliant with | products compliant with | architecture products
DoD Enterprise | DoD Enterprise | compliant with DoD
Architecture based on | Architecture based on | Enterprise Architecture
integrated DoDAF content, | integrated DoDAF content, | based on integrated
including specified | including specified | DoDAF content, including
operationally effective | operationally effective | specified operationally
information exchanges 2) | information exchanges 2) | effective information
Compliant with Net-Centric | Compliant with Net-Centric | exchanges 2) Compliant
Data Strategy and Net- | Data Strategy and Net- | with Net-Centric Data
Centric Services Strategy, | Centric Services Strategy, | Strategy and Net-Centric
and the principles and | and the principles and | Services Strategy, and the
rules identified in the DoD | rules identified in the DoD | principles and rules
lEA, excepting tactical and | lEA, excepting tactical and | identified in the DoD lEA,
non-IP communications 3) | non-IP communications 3) | excepting tactical and non-
Compliant with GIG | Compliant with GIG | IP communications 3)
Technical Guidance to | Technical Guidance to | Compliant with GIG
include IT Standards | include IT Standards | Technical Guidance to
identified in the TV-I and | identified in the TV-I and | include IT Standards
implementation guidance | implementation guidance | identified in the TV-I and
of GESPs, necessary to | of GESPs, necessary to | implementation guidance
meet all operational | meet all operational | of GESPs necessary to
requirements specified in | requirements specified in | meet all operational
the DoD Enterprise | the DoD Enterprise | requirements specified in
Architecture and solution | Architecture and solution | the DoD Enterprise
architecture views 4) | architecture views 4) | Architecture and solution
Information assurance | Information assurance | architecture views 4)
requirements including | requirements including | Information assurance
availability, integrity, | availability, integrity, | requirements including
authentica-tion, | authentica-tion, | availability, integrity,

## Table 11
confidentiality, and non- repudiation, and issuance of an ATO by the DAA, and 5) Support-ability requirements to include SAASM, Spectrum and JTRS requirements. | confidentiality, and non- repudiation, and issuance of an ATO by the DAA, and 5) Support-ability requirements to include SAASM, Spectrum and JTRS requirements. | authentica-tion, confidentiality, and non- repudiation, and issuance of an IATO or ATO by the DAA, and 5) Support-ability requirements to include SAASM, Spectrum and JTRS requirements.
KPP 4: Digital Fire Control System (DFCS)
Must be able to | Must be able to | Receive, process, | Threshold | PIM
independently compute | independently compute | compute and transmit | achieved. | management
and execute precision fire | and execute precision fire | technical fire control data |  | estimates
missions. | missions. | from/to AFATDS to |  | that the
|  | execute fire missions. |  | program will
|  | Must be able to host |  | continue to
|  | current and future software |  | achieve the
|  | upgrades. |  | Threshold
requirement.
KPP 5: Rate of Fire
6 rpm un-guided, 3 rpm | 6 rpm un-guided, 3 rpm | For un-guided projectiles, | On track to | PIM
guided | guided | max rate of fire 4 rpm for 3 | achieve | management
|  | minutes with a sustained | Threshold. | estimates
|  | rate of fire of 1 rpm until |  | that the
|  | limited by tube temperature |  | program will
|  | sensor. |  | achieve the
Threshold
requirement.
KPP 6: Range
Maximum range when | Maximum range when | Minimum indirect fire range | Threshold | PIM
firing guided munitions | firing guided munitions | using the M107 projectile | achieved. | management
shall be no less than 40 | shall be no less than 40 | and MACS propellant shall |  | estimates
km. | km. | be no more than 4 km. |  | that the
|  | Maximum range when |  | program will
|  | firing the M795 projectile |  | continue to
|  | and MACS propellant shall |  | achieve the
|  | be no less than 22 km. |  | Threshold
|  | Maximum range when |  | requirement.
firing assisted (i.e. rocket
assisted) projectile
M549A1 shall be no less
than 30 km IAW ICAO
standard conditions.
KPP 7: Self-Propelled Howitzer Reliability
84 percent | 84 percent | Will have a reliability of 75 | Threshold | PIM
|  | percent probability of | achieved. | management
|  | completing an 18-hour |  | estimates
|  | combat mission. |  | that the
program will
continue to
achieve the
Threshold

## Table 12
requirement.
KPP 8: Self-Propelled Howitzer Availability (Materiel Availability/Operational Availability)
Howitzer Am 83% and Ao | Howitzer Am 83% and Ao | The Howitzer shall | To be updated | PIM
95%. | 95%. | demonstrate a Am of 81% | after IOT. | management
|  | and an Ao of 78%. |  | estimates
that the
program will
achieve the
Threshold
requirement.
KPP 9: Carrier Ammunition Tracked Reliability
90 percent | 90 percent | Will have a reliability of 84 | Threshold | PIM
|  | percent probability of | achieved. | management
|  | completing an 18-hour |  | estimates
|  | combat mission. |  | that the
program will
continue to
achieve the
Threshold
requirement.
KPP 10: Carrier Ammunition Tracked Availability (Materiel Availability / Operational Availability)
CAT Am 72% and Ao 95%. | CAT Am 72% and Ao 95%. | The CAT shall | To be updated | PIM
|  | demonstrate a Am of 66% | after IOT. | management
|  | and an Ao of 85%. |  | estimates
that the
program will
achieve the
Threshold
requirement.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Production Document (CPD) v3.3 dated August 19, 2012
Change Explanations
None

## Table 13
Acronyms and Abbreviations
AFATDS - Advanced Field Artillery Tactical Data System Am - Materiel Availability
Ao - Operational Availability ATO - Approval to Operate
CAT - Carrier Ammunition Tracked DAA - Designated Accrediting Authority
DoDAF - Department of Defense Architecture Framework GESP - GIG Enterprise Service Profile
GIG - Global Information Grid
i.e. - id est, "that is"
IA - Information Assurance
IATO - Interim Approval to Operate IAW - In Accordance With
ICAO - International Civil Aviation Organization IEA - Information Enterprise Architecture
IOT - Initial Operational Test IP - Internet Protocol
IT - Information Technology
JTRS - Joint Tactical Radio System km - Kilometers
MACS - Modular Artillery Charge System rpm - Rounds per Minute
SAASM - Selective Availability Anti-Spoofing Module TV - Technical View

## Table 14
Track to Budget
RDT&E
Appn |  | BA | PE
Army 2040 05 0210609A
Project | Name
ED8 Paladin Integrated Management (PIM)
Army 2040 05 0604854A
Project | Name
516 Paladin/Faasv (Sunk)
Procurement
Appn |  | BA | PE
Army 2033 01 0210609A
Line Item | Name
2073GZ0410 Paladin Integrated
Management (PIM)
Notes: Standard Study Number GZ0410

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2013 $M |  |  |  |  | BY 2013 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 1084.3 |  | 1084.3 | 1192.7 |  | 1087.3 |  | 1102 |  | 1102 |  | 1098.6
Procurement |  | 5759.3 |  | 5759.3 | 6335.2 |  | 5916.8 |  | 6850.5 |  | 6850.5 |  | 6934.3
Flyaway |  | -- |  | -- | -- |  | 5457.8 |  | -- |  | -- |  | 6390.7
Recurring |  | -- |  | -- | -- |  | 5399.1 |  | -- |  | -- |  | 6328.4
Non Recurring |  | -- |  | -- | -- |  | 58.7 |  | -- |  | -- |  | 62.3
Support |  | -- |  | -- | -- |  | 459 |  | -- |  | -- |  | 543.6
Other Support |  | -- |  | -- | -- |  | 330.7 |  | -- |  | -- |  | 393.4
Initial Spares |  | -- |  | -- | -- |  | 128.3 |  | -- |  | -- |  | 150.2
MILCON |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total |  | 6843.6 |  | 6843.6 | N/A |  | 7004.1 |  | 7952.5 |  | 7952.5 |  | 8032.9
Confidence Level
Confidence Level of cost estimate for current APB: 50%
This estimate, like all previous Cost Assessment and Program Evaluation (CAPE) estimates, is built upon a product- oriented work breakdown structure; is based on historical actual cost information to the maximum extent possible; and, most importantly, is based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Program (MDAPs) programs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 16
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 2 | 2 | 2
Procurement | 556 | 556 | 568
Total | 558 | 558 | 570
Quantity Notes
A quantity of two PIM systems are the RDT&E-funded quantity. One and one-half PIM systems are RDT&E-funded LRIP which were procured in FY 2014 for Full Up System Live Fire Testing. The remaining one-half System represents a prototype Self-Propelled Howitzer 5A considered to be production-representative for PAUC calculation purposes.
The procurement quantity represents 568 PIM systems. This includes 12 PIM systems funded with FY 2017 Overseas Contingency Operations dollars.

## Table 17
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 898.7 | 152.3 |  |  | 41.5 | 6.1 | 0 |  | 0 |  | 0 |  |  | 0 |  | 1098.6
Procurement | 594 | 273.9 |  |  | 594.4 | 662.4 | 656.6 |  | 653.5 |  | 663.2 |  |  | 2836.3 |  | 6934.3
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 1492.7 | 426.2 |  |  | 635.9 | 668.5 | 656.6 |  | 653.5 |  | 663.2 |  |  | 2836.3 |  | 8032.9
PB 2016 Total | 1534.2 | 426.2 |  |  | 515.2 | 673.6 | 661.8 |  | 658.7 |  | 685.5 |  |  | 2794.7 |  | 7949.9
Delta | -41.5 | 0 |  |  | 120.7 | -5.1 | -5.2 |  | -5.2 |  | -22.3 |  |  | 41.6 |  | 83
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 2
Production | 0 |  | 35 |  | 30 | 48 | 60 |  | 60 |  | 60 | 60 |  | 215 |  | 568
PB 2017 Total | 2 |  | 35 |  | 30 | 48 | 60 |  | 60 |  | 60 | 60 |  | 215 |  | 570
PB 2016 Total | 2 |  | 35 |  | 30 | 36 | 60 |  | 60 |  | 60 | 60 |  | 215 |  | 558
Delta | 0 |  | 0 |  | 0 | 12 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 12

## Table 18
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 147.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 176.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 126.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 149.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 121.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 152.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 1098.6

## Table 19
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2013 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 152.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 178.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 126.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 147.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 116.9
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 76.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 142.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.2
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.5
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 1087.3

## Table 20
Annual Funding 2033 ¦ Procurement ¦ Procurement of Weapons and Tracked Combat Vehicles, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2013 |  | -- | 123.5 |  | 28.9 |  | 17.2 |  | 169.6 |  | 19 |  | 188.6
2014 |  | 17 | 101.3 |  | 28.5 |  | 16.9 |  | 146.7 |  | 18.8 |  | 165.5
2015 |  | 18 | 163.7 |  | 71.4 |  | -- |  | 235.1 |  | 4.8 |  | 239.9
2016 |  | 30 | 188.5 |  | 55.6 |  | 7.2 |  | 251.3 |  | 22.6 |  | 273.9
2017 |  | 48 | 425.9 |  | 107.4 |  | 21 |  | 554.3 |  | 40.1 |  | 594.4
2018 |  | 60 | 502.5 |  | 119.5 |  | -- |  | 622 |  | 40.4 |  | 662.4
2019 |  | 60 | 496.5 |  | 116.5 |  | -- |  | 613 |  | 43.6 |  | 656.6
2020 |  | 60 | 486 |  | 119.1 |  | -- |  | 605.1 |  | 48.4 |  | 653.5
2021 |  | 60 | 490.3 |  | 122 |  | -- |  | 612.3 |  | 50.9 |  | 663.2
2022 |  | 60 | 520.9 |  | 134.8 |  | -- |  | 655.7 |  | 50.7 |  | 706.4
2023 |  | 60 | 528.7 |  | 138.5 |  | -- |  | 667.2 |  | 50.5 |  | 717.7
2024 |  | 60 | 537.3 |  | 145.9 |  | -- |  | 683.2 |  | 53.3 |  | 736.5
2025 |  | 35 | 324 |  | 111.6 |  | -- |  | 435.6 |  | 43.4 |  | 479
2026 |  | -- | -- |  | 70.3 |  | -- |  | 70.3 |  | 32.4 |  | 102.7
2027 |  | -- | -- |  | 69.3 |  | -- |  | 69.3 |  | 24.7 |  | 94
Subtotal |  | 568 | 4889.1 |  | 1439.3 |  | 62.3 |  | 6390.7 |  | 543.6 |  | 6934.3

## Table 21
Annual Funding 2033 ¦ Procurement ¦ Procurement of Weapons and Tracked Combat Vehicles, Army
Fiscal Year | Quantity |  | BY 2013 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2013 |  | -- | 119.8 |  | 28.1 |  | 16.7 |  | 164.6 |  | 18.4 |  | 183
2014 |  | 17 | 97.3 |  | 27.4 |  | 16.2 |  | 140.9 |  | 18.1 |  | 159
2015 |  | 18 | 155 |  | 67.6 |  | -- |  | 222.6 |  | 4.5 |  | 227.1
2016 |  | 30 | 174.9 |  | 51.6 |  | 6.7 |  | 233.2 |  | 21 |  | 254.2
2017 |  | 48 | 387.8 |  | 97.8 |  | 19.1 |  | 504.7 |  | 36.5 |  | 541.2
2018 |  | 60 | 448.6 |  | 106.8 |  | -- |  | 555.4 |  | 36 |  | 591.4
2019 |  | 60 | 434.6 |  | 101.9 |  | -- |  | 536.5 |  | 38.2 |  | 574.7
2020 |  | 60 | 417 |  | 102.2 |  | -- |  | 519.2 |  | 41.6 |  | 560.8
2021 |  | 60 | 412.5 |  | 102.6 |  | -- |  | 515.1 |  | 42.8 |  | 557.9
2022 |  | 60 | 429.6 |  | 111.1 |  | -- |  | 540.7 |  | 41.9 |  | 582.6
2023 |  | 60 | 427.5 |  | 111.9 |  | -- |  | 539.4 |  | 40.9 |  | 580.3
2024 |  | 60 | 425.9 |  | 115.7 |  | -- |  | 541.6 |  | 42.2 |  | 583.8
2025 |  | 35 | 251.8 |  | 86.8 |  | -- |  | 338.6 |  | 33.7 |  | 372.3
2026 |  | -- | -- |  | 53.6 |  | -- |  | 53.6 |  | 24.7 |  | 78.3
2027 |  | -- | -- |  | 51.7 |  | -- |  | 51.7 |  | 18.5 |  | 70.2
Subtotal |  | 568 | 4182.3 |  | 1216.8 |  | 58.7 |  | 5457.8 |  | 459 |  | 5916.8

## Table 22
Cost Quantity Information 2033 ¦ Procurement ¦ Procurement of Weapons and Tracked Combat Vehicles, Army
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2013 $M
2013 | -- | --
2014 | 17 | 196.6
2015 | 18 | 163.2
2016 | 30 | 260.2
2017 | 48 | 296
2018 | 60 | 455
2019 | 60 | 446.5
2020 | 60 | 428.9
2021 | 60 | 425
2022 | 60 | 422.4
2023 | 60 | 420.6
2024 | 60 | 419.5
2025 | 35 | 248.4
2026 | -- | --
2027 | -- | --
Subtotal | 568 | 4182.3

## Table 23
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2013-10-21 | 2013-10-21
Approved Quantity | 67 | 67
Reference | Milestone C ADM | Milestone C ADM
Start Year | 2014 | 2014
End Year | 2017 | 2017
The Current Total LRIP Quantity is more than 10% of the total production quantity as authorized in the Milestone C ADM to provide enough test assets to complete all required tests and to provide a gradual ramp-up to FRP.
The planned LRIP buy is 66.5 PIM systems. One and one-half PIM systems are RDT&E-funded LRIP assets procured in FY 2014 for Full Up System Live Fire Testing. The remaining 65 PIM systems are Procurement-funded.

## Table 24
Foreign Military Sales
None
Nuclear Costs
None

## Table 25
Unit Cost
Unit Cost Report
Item |  | BY 2013 $M | BY 2013 $M |  | % Change
|  | Current UCR Baseline (Mar 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 6843.6 |  |  | 7004.1
Quantity | 558 |  |  | 570
Unit Cost | 12.265 |  |  | 12.288 |  | 0.19
Average Procurement Unit Cost
Cost | 5759.3 |  |  | 5916.8
Quantity | 556 |  |  | 568
Unit Cost | 10.358 |  |  | 10.417 |  | 0.57
Item |  | BY 2013 $M | BY 2013 $M |  | % Change
|  | Original UCR Baseline (Mar 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 6902.6 |  |  | 7004.1
Quantity | 582 |  |  | 570
Unit Cost | 11.86 |  |  | 12.288 |  | 3.61
Average Procurement Unit Cost
Cost | 5862.3 |  |  | 5916.8
Quantity | 580 |  |  | 568
Unit Cost | 10.107 |  |  | 10.417 |  | 3.07
The FY 2017 PB includes 12 vehicle systems funded with FY 2017 Overseas Contingency Operations dollars.

## Table 26
Unit Cost History
Item | [7 empty] | Date |  |  |  |  | BY 2013 $M | [6 empty] | TY $M
[13 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Mar 2012 | [7 empty] | 11.86 |  |  |  | 10.107 |  |  |  | 13.449 |  |  |  | 11.699
APB as of January 2006 |  |  |  |  | N/A | [7 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Revised Original APB |  |  |  |  | N/A | [7 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Mar 2012 | [7 empty] | 11.86 |  |  |  | 10.107 |  |  |  | 13.449 |  |  |  | 11.699
Current APB |  |  |  |  | Mar 2014 | [7 empty] | 12.265 |  |  |  | 10.358 |  |  |  | 14.252 |  |  |  | 12.321
Prior Annual SAR |  |  |  |  | Dec 2014 | [7 empty] | 12.341 |  |  |  | 10.433 |  |  |  | 14.247 |  |  |  | 12.321
Current Estimate |  |  |  |  | Dec 2015 | [7 empty] | 12.288 |  |  |  | 10.417 |  |  |  | 14.093 |  |  |  | 12.208
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  |  | Oth |  | Spt |  | Total
13.449 0.365 0.238 0.027 0.000 -0.085 0.000 0.258 0.803 14.252
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  | Spt |  | Total
14.252 -0.189 -0.122 -0.028 0.000 0.308 0.000 -0.128 -0.159 14.093

## Table 27
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [12 empty] | APUC Production Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  | Oth |  | Spt | Total
11.699 0.343 0.163 0.027 0.000 -0.169 0.000 0.258 0.622 12.321
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [12 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est | Oth | Spt |  | Total
12.321 -0.177 -0.083 -0.028 0.000 0.303 0.000 -0.128 -0.113 12.208
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  |  | Jun 2013 |  |  |  |  | Oct 2013 |  |  | Oct 2013
IOC |  |  | N/A |  |  |  | Apr 2017 |  |  |  |  | Apr 2017 |  |  | Jun 2017
Total Cost (TY $M) |  |  | N/A |  |  |  | 7827.1 |  |  |  |  | 7952.5 |  |  | 8032.9
Total Quantity |  |  | N/A |  |  |  | 582 |  |  |  |  | 558 |  |  | 570
PAUC |  |  | N/A |  |  |  | 13.449 |  |  |  |  | 14.252 |  |  | 14.093

## Table 28
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1102 | 6850.5 | -- | 7952.5
Previous Changes
Economic | -4 | -48.6 | -- | -52.6
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 1.2 | 130.9 | -- | 132.1
Other | -- | -- | -- | --
Support | -- | -82.1 | -- | -82.1
Subtotal | -2.8 | 0.2 | -- | -2.6
Current Changes
Economic | -2.7 | -52.2 | -- | -54.9
Quantity | -- | 100.9 | -- | 100.9
Schedule | -- | -15.9 | -- | -15.9
Engineering | -- | -- | -- | --
Estimating | 2.1 | 41.4 | -- | 43.5
Other | -- | -- | -- | --
Support | -- | 9.4 | -- | 9.4
Subtotal | -0.6 | 83.6 | -- | 83
Adjustments | -- | -- | -- | --
Total Changes | -3.4 | 83.8 | -- | 80.4
CE - Cost Variance | 1098.6 | 6934.3 | -- | 8032.9
CE - Cost & Funding | 1098.6 | 6934.3 | -- | 8032.9

## Table 29
Summary BY 2013 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1084.3 5759.3 -- 6843.6
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 1 |  | 109.9 |  | -- |  | 110.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -68.3 |  | -- |  | -68.3
Subtotal |  | 1 |  | 41.6 |  | -- |  | 42.6
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 78.4 |  | -- |  | 78.4
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 2 |  | 29.3 |  | -- |  | 31.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 8.2 |  | -- |  | 8.2
Subtotal |  | 2 |  | 115.9 |  | -- |  | 117.9
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 3 |  | 157.5 |  | -- |  | 160.5
CE - Cost Variance |  | 1087.3 |  | 5916.8 |  | -- |  | 7004.1
CE - Cost & Funding |  | 1087.3 |  | 5916.8 |  | -- |  | 7004.1
Previous Estimate: December 2014

## Table 30
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -2.7
Revised estimate to align with the FY 2017 PB. (Estimating) |  | -0.3 | -0.3
Adjustment for current and prior escalation. (Estimating) |  | 2.3 | 2.4
RDT&E Subtotal |  | 2 | -0.6
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -52.2
Acceleration of procurement buy profile due to 12 additional PIM vehicle systems in FY 2017. (Schedule) (QR)
Quantity variance resulting from an increase of 12 PIM vehicle systems from 556 to 568. (Subtotal)
Quantity variance resulting from an increase of 12 PIM vehicle systems from 556 to
568. (Quantity)
0.0 -15.9
+79.1 +101.8
(+78.4) (+100.9)
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (+0.7) (+0.9)
Revised FY 2014 estimate to reflect the FY 2017 PB Above Threshold Reprogramming to M109A6 Paladin/Field Artillery Ammunition Support Vehicle program. (Estimating)
-32.7 -34.0
Revised estimate to align with the FY 2017 PB. (Estimating) +34.9 +44.5
Congressional reduction of FY 2015 funds per FY 2016 Consolidated Appropriations Bill
H.R. 2029. (Estimating)
Additional allocation to Estimating resulting from procurement of 12 additional PIM vehicle systems in FY 2017. (Estimating) (QR)
-7.1 -7.5
+28.8 +32.6
Adjustment for current and prior escalation. (Estimating) | 4.7 |  |  | 4.9
Adjustment for current and prior escalation. (Support) | 0.4 |  |  | 0.4
Increase in Other Support to align Procurement estimate with the FY 2017 PB. (Support) | 3.9 |  |  | 4.9
Increase in Initial Spares to align Procurement estimate with the FY 2017 PB. (Support) | 3.9 |  |  | 4.1
Procurement Subtotal | 115.9 |  |  | 83.6
(QR) Quantity Related

## Table 31
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: Comprehensive Contract Modification (CCM)
Contractor: BAE Systems Land & Armaments L.P.
Contractor Location: 1100 Bairs Road
York, PA 17408
Contract Number: W56HZV-09-C-0550/38 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: January 06, 2012
Definitization Date: January 06, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
311.6 N/A N/A 407.9 N/A N/A 389.5 389.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to awarding the EMD extension contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +9.3 -8.1
Previous Cumulative Variances +12.1 -3.2
Net Change -2.8 -4.9
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to additional labor for technical manuals/publications. The cumulative cost variance is positive and program Variance at Completion remains positive.
The unfavorable net change in the schedule variance is due to delays driven by Test and Evaluation. Planned material was delayed due to supplier conformance issues and quality inspections. The test schedule and recovery plans continue to be reviewed by the program office and BAE Systems. The recovery of schedule is expected through March 2016. The program is on track for an FRP decision in 2nd Quarter FY 2017.

## Table 32
Contract Identification
Appropriation: Procurement
Contract Name: PIM-LRIP BASE
Contractor: BAE Systems Land & Armaments L.P.
Contractor Location: 1100 Bairs Road
York, PA 17408
Contract Number: W56HZV-14-C-0002
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: October 30, 2013
Definitization Date: October 30, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
217.5 197.5 19 362.0 347.0 55 362.0 362.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to awarding the LRIP Option 1 contract.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because an EVM waiver was granted by the Army Acquisition Executive on December 24, 2015 due to incompatibility of using MIL STD 881C Work Breakdown Structure (WBS) for the PIM/M109A7 FOV LRIP contract. MIL STD 881C WBS structure is significantly different than the process- driven structure used by the contractor to capture cost, schedule and performance metrics in production. In order to remain compliant with EVM guidelines, the contractor would need to make significant changes to their Lean Manufacturing Process. These changes would increase cost to meet programmatic compliance requirements and create risk deficiencies with the recently approved EVM system.
Notes
Thirty-five percent of the Performance Measurement Baseline remains in Undistributed Budget (UB) for LRIP Option 1. The balance of the UB will continue to be detail planned in future reporting periods.
The Target Price includes data for all exercised FPIF and Cost Plus Fixed Fee Contract Line Items (CLIN); however, the contract Ceiling Price represents only FPIF CLINs.

## Table 33
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 2 | 0%
Production | 17 | 15 | 568 | 2.64%
Total Program Quantity Delivered | 17 | 15 | 570 | 2.63%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
8032.9
946.9
11.79%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
10
47.62%
1918.9
23.89%
The above data is current as of February 09, 2016.

## Table 34
Operating and Support Cost
Cost Estimate Details
Date of Estimate: October 21, 2013
Source of Estimate: CAPE ICE
Quantity to Sustain: 568
Unit of Measure: System
Service Life per Unit: 26.00 Years
Fiscal Years in Service: FY 2015 - FY 2053
System = PIM weapon system or vehicle set (one Self-Propelled Howitzer and one Carrier Ammunition Tracked)
A quantity of two PIM systems are RDT&E-funded and will not be sustained. One and one-half PIM systems are RDT&E- funded LRIP which were procured in FY 2014 for Full Up System Live Fire Testing. The remaining one-half system represents a prototype Self-Propelled Howitzer 5A considered to be production representative for PAUC calculation purposes.
Sustainment Strategy
The PIM product support concept will consist of Operational/Field and Sustainment support. Operation/Field support will be through the use of Brigade Support Battalions using the Fires Forward Support Company and the Supply Support Activity. Maintenance support will consist of the Army two-level maintenance strategy:
• Field Maintenance - Remove, replace, or repair in the field
• Sustainment Maintenance - Repair and return to supply
Antecedent Information
O&S costs for the M109A6 Paladin / M992A2 Field Artillery Ammunition Support Vehicle (antecedent system) are based on various sources including the O&S Management Information System, the Army Manpower Allocation Requirements Criteria Database, and historical actuals from the program office. Operational Tempos are based on the Army G-3/5/7 Forces Command model. The antecedent system assumes the same quantities and Economic Useful Life (EUL) as the PIM system.
Annual O&S Costs BY2013 $K
Cost Element | PIM Average Annual Cost Per System | M109A6 Paladin / M992A2 FAASV (Antecedent) Average Annual Cost Per System
Unit-Level Manpower | 625.363 | 638.86
Unit Operations | 130.412 | 133.11
Maintenance | 125.764 | 98.377
Sustaining Support | 106.241 | 108.544
Continuing System Improvements | 80.932 | 56.08
Indirect Support | 245.212 | 250.319
Other | 0 | 0
Total | 1313.924 | 1285.29

## Table 35
Item | Total O&S Cost $M
| PIM | [5 empty] | M109A6 Paladin / M992A2 FAASV (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 19911.1 |  | 21902.2 |  |  | 19404 | 18580.2
Then Year | 30867.8 |  | N/A |  |  | 29417.3 | N/A
Equation to Translate Annual Cost to Total Cost
PIM Total O&S Cost = Average Annual O&S Cost Per System * Number of Systems * EUL = $1313.924K * 568 systems * 26 years = $19404.0M (BY 2013 $M)
Paladin/FAASV Total O&S Cost = Average Annual O&S Cost Per System * Number of Systems * EUL = $1285.290K * 556 systems * 26 years = $18580.2M (BY 2013 $M)
O&S Cost Variance
Category |  | BY 2013 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
19374.5
Programmatic/Planning Factors 29.5 An additional 12 PIM systems to be procured in FY 2017 with Overseas Contingency Operations funds will be sustained as Army Prepositioned Stock.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 29.5
Current Estimate 19404.0
Disposal Estimate Details
Date of Estimate: October 21, 2013
Source of Estimate: CAPE ICE
Disposal/Demilitarization Total Cost (BY 2013 $M): Total costs for disposal of all System are 63.8