## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-279
Joint Light Tactical Vehicle (JLTV)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 17
Cost and Funding 18
Low Rate Initial Production 29
Foreign Military Sales 30
Nuclear Costs 30
Unit Cost 31
Cost Variance 34
Contracts 37
Deliveries and Expenditures 38
Operating and Support Cost 39

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Joint Light Tactical Vehicle (JLTV)
DoD Component
Army
Joint Participants
United States Marine Corps
Responsible Office
COL Shane Fullmer 43087 Lake Street
Building 301 NE
Harrison Township, MI 48045-4941
shane.n.fullmer.mil@mail.mil
Phone: 586-239-2984
Fax:
DSN Phone: 273-2984
DSN Fax:
Date Assigned: July 8, 2015
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 23, 2012
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 23, 2012

## Table 6
Mission and Description
The primary mission of the Joint Light Tactical Vehicle (JLTV) is to provide protected, sustained, and networked light tactical mobility to the Joint forces, capable of worldwide deployment across the full spectrum of military operations and mission profiles under all weather and terrain conditions.
The JLTV will be transportable over long distances within any theater of operations through numerous lift assets and options, from sealift and amphibious shipping to airlift (both fixed and rotary wing) and low velocity aerial delivery. It will provide mobility to reconnaissance units and direct fire in support of combat maneuver, with substantial payload for personnel, equipment, and supplies.
The JLTV will support command, control, and communication in both stationary and on-the-move modes, enabling interoperability with Joint and coalition forces in decentralized operations over extended ranges in complex and dynamic operational environments.
System Description: the JLTV Family of Vehicles is comprised of two variants based upon a common automotive platform, a two-seat Combat Support Vehicle (CSV) and a four-seat Combat Tactical Vehicle (CTV), as well as a companion trailer. The two-seat CSV variant has a payload capacity of 5,100-pounds. The four-seat CTV variant has a payload capacity of 3,500-pounds. Variant may be further equipped with multiple mission package configurations, such as the CSV Shelter Carrier and the CTV Heavy Guns Carrier.

## Table 7
Executive Summary
Program Highlights Since Last Report:
The JLTV is a Joint Army/ Marine Corps program, for which the Army is the lead service.
The LRIP/FRP Request for Proposal was released on December 12, 2014 and the solicitation closed on February 10, 2015. Proposals from each of the three prior EMD vendors were submitted on time and evaluated.
On August 25, 2015, the Milestone C DAB was successfully held and the DAE signed the ADM authorizing entrance into the Production and Deployment Phase. The contract was awarded on the same day to Oshkosh Defense LLC.
On September 8, 2015 a Stop Work Order was issued to Oshkosh after a Lockheed Martin protest was filed with the Government Accountability Office (GAO). On December 15, 2015 the GAO dismissed the protest due to Lockheed Martin's notice of intent to file a Post-Award Bid Protest with the U.S. Court of Federal Claims (COFC). The Stop Work Order was officially cancelled and Oshkosh resumed work. On December 17, 2015 Lockheed Martin officially filed a complaint with the COFC. On February 12, 2016 the COFC denied their request for a preliminary injunction and shortly after on February 17, 2016 Lockheed Martin officially withdrew their protest of the JLTV contract award decision.
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation:
Note: JLTV is one of the first programs to fully implement the OSD September 2007 Competitive Prototyping policy which calls for two or more competing teams producing prototypes through Milestone B, with the goal of reducing risk and synchronizing requirements.
December 22, 2007: JLTV had an approved Milestone A decision initiating the Technology Development (TD) phase.
October 2008: Three cost reimbursable contracts with a total value of $239.8M were awarded under full and open competition to BAE Systems Land & Armaments, General Tactical Vehicles, LLC and Lockheed Martin Corporation. TD efforts included the design, development, modeling, simulation, fabrication, test, and test support of 24 prototype JLTVs and companion trailers. The initial requirements proved very challenging for the TD prototypes; consequently, the requirements evolved to incorporate lessons learned, and were closely aligned with the capabilities and performance demonstrated by the TD vendors.
January 26, 2012: A full and open competition solicitation was issued, using a best value tradeoff source selection process. August 9, 2012: The Milestone B decision authorized entry into the EMD phase.
August 22, 2012 to November 30, 2014: Three firm-fixed price contracts with a total value of $184.8M were awarded to the AM General LLC, Lockheed Martin Corporation, and Oshkosh Defense LLC for a 27-month period of performance. The EMD phase included 14-months of performance, reliability, and ballistic testing in order to validate that JLTV prototype vehicles achieve KPP and Key System Attribute thresholds and to support the source selection process for the Production and Deployment phase. Each EMD vendor fabricated, assembled, tested, and delivered a total of 66 prototype vehicles and 18 trailers (22-vehicles and six-trailers from each vendor), along with ballistic structures, armor coupons and other test assets, vendor-furnished kits, trailers, and data requirements. In November 2014, the period of performance for all three contracts ended and all EMD phase testing was successfully completed.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
The 98 day Government Accountability Office (GAO) contract protest filed by Lockheed Martin and the associated stop work caused a day for day slip in contract execution and a greater than a day for day slip in the overall program schedule due to Multiservice Operational Test and Evaluation scheduling issues.
The proposed Milestone C Production APB incorporates the schedule impacts caused by the contract protest. Per the direction of the Milestone C ADM dated August 25, 2015, the APB was due for review and approval within 60 days. Due to the GAO protest and the associated stop work, the APB due date was extended. The APB is in staffing and on track for approval by the DAE in 2nd Quarter of FY 2016. When approved, the appearance of an APB breach will be eliminated as the program will report against the Milestone C APB.
Nunn-McCurdy Breaches

## Table 9
Schedule
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | Aug 2012 | Aug 2012 | Feb 2013 | Aug 2012
Milestone C | May 2015 | May 2015 | Nov 2015 | Aug 2015
Begin MOT&E | Feb 2017 | Feb 2017 | Aug 2017 | Feb 20181
Complete MOT&E | Jun 2017 | Jun 2017 | Dec 2017 | May 20181
FRP Decision | Feb 2018 | Feb 2018 | Aug 2018 | Dec 20181
IOC | May 2018 | May 2018 | Nov 2018 | Dec 20191
FOC | May 2025 | May 2025 | Nov 2025 | Nov 20391
1 APB Breach
(Ch-1)
(Ch-2)
(Ch-3)
(Ch-4)
(Ch-5)
(Ch-6)

## Table 10
Change Explanations
(Ch-1) On August 25, 2015, the Milestone C DAB was successfully held and the DAE signed the ADM authorizing entrance into the Production and Deployment Phase
(Ch-2) The current scheduled start of MOT&E changed from July 2017 to February 2018 due to the ramifications of the 98 day Government Accountability Office (GAO) contract protest. The day for day schedule slip pushed the start of MOT&E to November 2017 and was further shifted to avoid performing Operational Testing over the holiday time period.
(Ch-3) The current estimate for MOT&E completion changed from October 2017 to May 2018 due to the schedule impacts caused by the GAO contract protest. (See Note 1)
(Ch-4) The current estimate for FRP Decision changed from May 2018 to December 2018 due to the schedule impacts caused by the GAO contract protest which delayed MOT&E.
(Ch-5) The current estimate for IOC changed from August 2018 to December 2019 due to the schedule impacts caused by the GAO contract protest which delayed MOT&E and FRP Decision. This additional time allows the fielded brigade to conduct a certification exercise at a maneuver training facility.
(Ch-6) The current estimate for FOC changed from May 2025 to November 2039 due to the difference in interpretation of the FOC definition at the time the Capability Development Document was written compared to the current approved Capability Production Document.
Notes
The proposed Milestone C Production APB incorporates the schedule impacts caused by the 98 day contract protest and is on track for approval by the DAE in the 2nd Quarter of FY 2016. When approved, the appearance of an APB schedule breach will be eliminated as the program will report against the Milestone C APB.
The above IOC is for the Army. The U.S. Marine Corps (USMC) IOC is aligned with the Army IOC. The above FOC is for the Army. The USMC FOC is scheduled for September 2022.
Acronyms and Abbreviations
MOT&E - Multiservice Operational Test and Evaluation

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Survivability KPP
The JLTV FoV (at | The JLTV FoV (at | The JLTV FoV (at | TBD | The JLTV FoV (at GVW)
GVW) should provide a | GVW) should provide a | GVW) shall provide a |  | should provide a
crashworthy vehicle | crashworthy vehicle | crashworthy vehicle |  | crashworthy vehicle
structure capable of | structure capable of | structure capable of |  | structure capable of
maintaining structural | maintaining structural | maintaining structural |  | maintaining structural
integrity in a rollover; | integrity in a rollover; | integrity in a rollover; |  | integrity in a rollover;
quantified as a crush | quantified as a crush | quantified as a crush |  | quantified as a crush
resistant roof structure | resistant roof structure | resistant roof structure |  | resistant roof structure
capable of supporting | capable of supporting | capable of supporting |  | capable of supporting
150% of its own GVW | 150% of its own GVW | 100% of its own GVW |  | 150% of its own GVW
after a dynamically | after a dynamically | after a dynamically |  | after a dynamically
applied impact load. | applied impact load. | applied impact load. |  | applied impact load.
Net-Ready KPP
The capability, system, | The capability, system, | The capability, | TBD | The capability, system,
and/or service must | and/or service must | system, and/or service |  | and/or service must fully
fully support execution | fully support execution | must fully support |  | support execution of all
of all operational | of all operational | execution of joint |  | operational activities and
activities and | activities and | critical operational |  | information exchanges
information exchanges | information exchanges | activities and |  | identified in DoD
identified in DoD | identified in DoD | information exchanges |  | Enterprise Architecture
Enterprise Architecture | Enterprise Architecture | identified in the DoD |  | and solution
and solution | and solution | Enterprise |  | architectures based on
architectures based on | architectures based on | Architecture and |  | integrated DoDAF
integrated DoDAF | integrated DoDAF | solution architectures |  | content, and must
content, and must | content, and must | based on integrated |  | satisfy the technical
satisfy the technical | satisfy the technical | DoDAF content, and |  | requirements for
requirements for | requirements for | must satisfy the |  | transition to Net-Centric
transition to Net-Centric | transition to Net-Centric | technical requirements |  | military operations to
military operations to | military operations to | for transition to Net- |  | include: 1) Solution
include: 1) Solution | include: 1) Solution | Centric military |  | architecture products
architecture products | architecture products | operations to include: |  | compliant with DoD
compliant with DoD | compliant with DoD | 1) Solution |  | Enterprise Architecture
Enterprise Architecture | Enterprise Architecture | architecture products |  | based on integrated
based on integrated | based on integrated | compliant with DoD |  | DoDAF content,
DoDAF content, | DoDAF content, | Enterprise |  | including specified
including specified | including specified | Architecture based on |  | operationally effective
operationally effective | operationally effective | integrated DoDAF |  | information exchanges,
information exchanges, | information exchanges, | content, including |  | 2) Compliant with Net-
2) Compliant with Net- | 2) Compliant with Net- | specified operationally |  | Centric Data Strategy
Centric Data Strategy | Centric Data Strategy | effective information |  | and Net-Centric
and Net-Centric | and Net-Centric | exchanges, 2) |  | Services Strategy, and
Services Strategy, and | Services Strategy, and | Compliant with Net- |  | the principles and rules
the principles and rules | the principles and rules | Centric Data Strategy |  | identified in the DoD IEA,

## Table 12
identified in the DoD | identified in the DoD | and Net-Centric |  | excepting tactical and
IEA, excepting tactical | IEA, excepting tactical | Services Strategy, and |  | non-IP communica-
and non-IP communica | and non-IP communica | the principles and |  | tions, 3) Compliant with
-tions, 3) Compliant | -tions, 3) Compliant | rules identified in the |  | GIG Technical Guidance
with GIG Technical | with GIG Technical | DoD IEA, excepting |  | to include IT Standards
Guidance to include IT | Guidance to include IT | tactical and non-IP |  | identified in the TV-1 and
Standards identified in | Standards identified in | communica-tions, 3) |  | implementation
the TV-1 and | the TV-1 and | Compliant with GIG |  | guidance of GESPs,
implementation | implementation | Technical Guidance to |  | necessary to meet all
guidance of GESPs, | guidance of GESPs, | include IT Standards |  | operational
necessary to meet all | necessary to meet all | identified in the TV-1 |  | requirements specified
operational | operational | and implementation |  | in the DoD Enterprise
requirements specified | requirements specified | guidance of GESPs |  | Architecture and solution
in the DoD Enterprise | in the DoD Enterprise | necessary to meet all |  | architecture views, 4)
Architecture and | Architecture and | operational |  | Information assurance
solution architecture | solution architecture | requirements specified |  | requirements including
views, 4) Information | views, 4) Information | in the DoD Enterprise |  | availability, integrity,
assurance | assurance | Architecture and |  | authentication,
requirements including | requirements including | solution architecture |  | confidentiality, and non-
availability, integrity, | availability, integrity, | views, 4) Information |  | repudiation, and
authenticat-ion, | authenticat-ion, | assurance |  | issuance of an ATO by
confidential-ity, and non | confidential-ity, and non | requirements including |  | the DAA, and 5)
-repudiation, and | -repudiation, and | availability, integrity, |  | Supportability
issuance of an ATO by | issuance of an ATO by | authenticat-ion, |  | requirements to include
the DAA, and 5) | the DAA, and 5) | confidential-ity, and |  | SAASM, Spectrum and
Supportabil-ity | Supportabil-ity | non-repudiation, and |  | JTRS requirements.
requirements to include | requirements to include | issuance of an IATO
SAASM, Spectrum and | SAASM, Spectrum and | or ATO by the DAA,
JTRS require-ments. | JTRS require-ments. | and 5) Supportabil-ity
requirements to
include SAASM,
Spectrum and JTRS
require-ments.
Sustainment KPP
JLTV FoV (vehicle only) | JLTV FoV (vehicle only) | JLTV FoV (vehicle | TBD | JLTV FoV (vehicle only)
should have an Ao | should have an Ao | only) shall have an Ao |  | should have an Ao 98%.
98%. JLTV FoV (vehicle | 98%. JLTV FoV (vehicle | of 95%. JLTV FoV |  | JLTV FoV (vehicle only)
only) should have a Am | only) should have a Am | (vehicle only) shall |  | should have a Am of
of 85%. | of 85%. | have a Am of 80%. |  | 85%.
System Training KPP
The JLTV shall have | The JLTV shall have | The JLTV shall have | TBD | The JLTV shall have
training for operators | training for operators | training for operators |  | training for operators
and maintainers that | and maintainers that | and maintainers that |  | and maintainers that
incorporates and | incorporates and | incorporates and |  | incorporates and
leverages existing | leverages existing | leverages existing |  | leverages existing
training techniques, | training techniques, | training techniques, |  | training techniques,
methods, resources | methods, resources | methods, resources |  | methods, resources and
and licensing | and licensing | and licensing |  | licensing requirements
requirements of each | requirements of each | requirements of each |  | of each Service. JLTV
Service. JLTV training | Service. JLTV training | Service. JLTV training |  | training shall include in-
shall include in-vehicle | shall include in-vehicle | shall include in-vehicle |  | vehicle training to
training to encompass | training to encompass | training to encompass |  | encompass

## Table 13
demonstrat-ing a capability to negotiate operationally relevant terrain profiles, which include basic organic vehicle instrumenta- tion, controls and crew drills. | demonstrat-ing a capability to negotiate operationally relevant terrain profiles, which include basic organic vehicle instrumenta- tion, controls and crew drills. | demonstrat-ing a capability to negotiate operationally relevant terrain profiles, which include basic organic vehicle instrumenta- tion, controls and crew drills. |  | demonstrating a capability to negotiate operationally relevant terrain profiles, which include basic organic vehicle instrumentation, controls and crew drills.
Mobility KPP
The JLTV mobility shall | The JLTV mobility shall | The JLTV mobility | TBD | The JLTV mobility shall
support continuous | support continuous | shall support |  | support continuous
operation across | operation across | continuous operation |  | operation across
worldwide terrains, | worldwide terrains, | across worldwide |  | worldwide terrains,
climatic conditions, and | climatic conditions, and | terrains, climatic |  | climatic conditions, and
soil types at speeds | soil types at speeds | conditions, and soil |  | soil types at speeds
consistent with | consistent with | types at speeds |  | consistent with
conducting fast-paced | conducting fast-paced | consistent with |  | conducting fast-paced
military operations. This | military operations. This | conducting fast-paced |  | military operations. This
includes paved primary | includes paved primary | military operations. |  | includes paved primary
road networks, | road networks, | This includes paved |  | road networks,
gravel/dirt secondary | gravel/dirt secondary | primary road |  | gravel/dirt secondary
roadways, single track | roadways, single track | networks, gravel/dirt |  | roadways, single track
trails with no manmade | trails with no manmade | secondary roadways, |  | trails with no manmade
improve-ments, & | improve-ments, & | single track trails with |  | improve-ments, & cross
cross-country terrain | cross-country terrain | no manmade improve- |  | -country terrain with no
with no roads, routes, | with no roads, routes, | ments, & cross- |  | roads, routes, or well-
or well-worn trails. The | or well-worn trails. The | country terrain with no |  | worn trails. The JLTV at
JLTV at GVW should be | JLTV at GVW should be | roads, routes, or well- |  | GVW should be capable
capable of traversing | capable of traversing | worn trails. The JLTV |  | of traversing fine grain
fine grain soils with an | fine grain soils with an | at GVW shall be |  | soils with an RCI of 22 in
RCI of 22 in a single | RCI of 22 in a single | capable of traversing |  | a single pass and also
pass and also ascend | pass and also ascend | fine grain soils with an |  | ascend and descend
and descend coarse | and descend coarse | RCI of 25 in a single |  | coarse grained, dry
grained, dry sand (less | grained, dry sand (less | pass and also ascend |  | sand (less than 1%
than 1% moisture | than 1% moisture | and descend coarse |  | moisture content) 40%
content) 40% | content) 40% | grained, dry sand (less |  | longitudinal slopes. The
longitudinal slopes. The | longitudinal slopes. The | than 1% moisture |  | threshold applies within
threshold applies within | threshold applies within | content) 30% |  | the confidence bounds
the confidence bounds | the confidence bounds | longitudinal slopes. |  | of established soft soil
of established soft soil | of established soft soil | The threshold applies |  | test procedures.
test procedures. | test procedures. | within the confidence
bounds of established
soft soil test
procedures.
Transportability KPP
The JLTV FoV shall be | The JLTV FoV shall be | The JLTV FoV shall be | TBD | The JLTV FoV shall be
transportable worldwide | transportable worldwide | transportable |  | transportable worldwide
by air and sea modes | by air and sea modes | worldwide by air and |  | by air and sea modes to
to support strategic | to support strategic | sea modes to support |  | support strategic
deployment and | deployment and | strategic deployment |  | deployment and
operational maneuver in | operational maneuver in | and operational |  | operational maneuver in
accordance with | accordance with | maneuver in |  | accordance with service

## Table 14
service concepts and programs. Rotary Wing: General Purpose
– USMC: 2x CH-53K
service concepts and programs. Rotary Wing: General Purpose
– USMC: 2x CH-53K
accordance with service concepts and programs. Rotary Wing: General
concepts and programs. Rotary Wing: General Purpose – USMC: 2x CH-53K 40nm high-hot
40nm high-hot @ GVW, 40nm high-hot @ GVW,
Purpose – USMC: 2x
@ GVW, USA: 1x CH-
USA: 1x CH-47F 50nm 4k/95F @ GVW, USA:
1x MH-47 30nm IAT
4k/95F @ ECC Heavy Guns Carrier – USMC: 2x CH-53K 40nm high- hot @ GVW, USA: 1x CH-47F 50nm 4k/95F
@ GVW, USA: 1x MH-
47 30nm IAT 4k/95F @ ECC Close Combat Weapons Carrier – USMC: 2x CH-53K
USA: 1x CH-47F 50nm 4k/95F @ GVW, USA:
1x MH-47 30nm IAT
4k/95F @ ECC Heavy Guns Carrier – USMC: 2x CH-53K 40nm high- hot @ GVW, USA: 1x CH-47F 50nm 4k/95F
@ GVW, USA: 1x MH-
47 30nm IAT 4k/95F @ ECC Close Combat Weapons Carrier – USMC: 2x CH-53K
CH-53K 40nm high- hot @ ECC, USA: 1x CH-47F 50nm SL/SD
@ ECC Heavy Guns Carrier – USMC: 2x CH-53K 40nm high- hot @ ECC, USA: 1x CH-47F 50nm SL/SD
@ ECC Close Combat Weapons Carrier – USMC: 2x CH-53K 40nm high- hot @ ECC, USA: 1x
47F 50nm 4k/95F @ GVW, USA: 1x MH-47
30nm IAT 4k/95F @ ECC Heavy Guns Carrier – USMC: 2x CH- 53K 40nm high-hot @ GVW, USA: 1x CH-47F
50nm 4k/95F @ GVW, USA: 1x MH-47 30nm IAT 4k/95F @ ECC
Close Combat Weapons Carrier – USMC: 2x CH-53K
40nm high-hot @ GVW, 40nm high-hot @ GVW,
CH-47F 50nm SL/SD
40nm high-hot @ GVW,
USA: 1x CH-47F 50nm 4k/95F @ GVW, USA:
1x MH-47 30nm IAT
4k/95F @ ECC Utility (2 Seat) – USMC: 2x CH-
53K 40nm high-hot @ GVW, USA: 1x CH-47F
50nm 4k/95F @ GVW, USA: 1x MH-47 30nm IAT 4k/95F @ ECC
Shelter Carrier – Not a KPP Note: Range, Temperature, and Pressure Data: 1) CH- 53K: Navy High Hot:
91.5 deg F/33 deg C,
USA: 1x CH-47F 50nm 4k/95F @ GVW, USA:
1x MH-47 30nm IAT
4k/95F @ ECC Utility (2 Seat) – USMC: 2x CH-
53K 40nm high-hot @ GVW, USA: 1x CH-47F
50nm 4k/95F @ GVW, USA: 1x MH-47 30nm IAT 4k/95F @ ECC
Shelter Carrier – Not a KPP Note: Range, Temperature, and Pressure Data: 1) CH- 53K: Navy High Hot:
91.5 deg F/33 deg C,
@ ECC Utility (2 Seat)
– USMC: 2x CH-53K
40nm high-hot @ ECC, USA: 1x CH-47F
50nm SL/SD @ ECC Shelter Carrier – Not a KPP Note: Range, Temperature, and Pressure Data: 1) CH- 53K: Navy High Hot:
91.5 deg F/33 deg C, 3000ft. 40 nm; sea- level take off & landing
2) CH-47F high hot: 95 F / 35 deg C, 4,000 ft, 50nm 3) CH-47F
USA: 1x CH-47F 50nm 4k/95F @ GVW, USA:
1x MH-47 30nm IAT
4k/95F @ ECC Utility (2 Seat) – USMC: 2x CH-
53K 40nm high-hot @ GVW, USA: 1x CH-47F
50nm 4k/95F @ GVW, USA: 1x MH-47 30nm IAT 4k/95F @ ECC
Shelter Carrier – Not a KPP Note: Range, Temperature, and Pressure Data: 1) CH- 53K: Navy High Hot:
91.5 deg F/33 deg C,
3000ft. 40 nm; sea-level 3000ft. 40 nm; sea-level
SL/SD: Sea Level /
3000ft. 40 nm; sea-level
take off & landing 2) CH
-47F high hot: 95 F / 35 deg C, 4,000 ft, 50nm
3) CH-47F SL/SD: Sea Level / Standard Day (70 F), 50 nm Sealift: Transport by sea is an essential part of force deployment and a hallmark aspect of USMC Expedi-tionary capabilities. The USMC JLTV (CTV variants and the CSV Utility) shall be capable of being loaded into all deck spaces of the preposition-ing and amphibious ships force
take off & landing 2) CH
-47F high hot: 95 F / 35 deg C, 4,000 ft, 50nm
3) CH-47F SL/SD: Sea Level / Standard Day (70 F), 50 nm Sealift: Transport by sea is an essential part of force deployment and a hallmark aspect of USMC Expedi-tionary capabilities. The USMC JLTV (CTV variants and the CSV Utility) shall be capable of being loaded into all deck spaces of the preposition-ing and amphibious ships force
Standard Day (70 F), 50 nm Sealift: Transport by sea is an essential part of force deployment and a hallmark aspect of USMC Expedi-tionary capabilities. The USMC JLTV (CTV
variants and the CSV Utility) shall be capable of being loaded into all deck spaces of the preposition-ing and amphibious ships force projection naval ships where current HMMWVs are loaded,
take off & landing 2) CH- 47F high hot: 95 F / 35 deg C, 4,000 ft, 50nm 3) CH-47F SL/SD: Sea
Level / Standard Day (70 F), 50 nm Sealift: Transport by sea is an essential part of force deployment and a hallmark aspect of USMC Expeditionary capabilities. The USMC JLTV (CTV variants and the CSV Utility) shall be capable of being loaded into all deck spaces of the preposition-ing and amphibious ships force

## Table 15
projection naval ships where current HMMWVs are loaded, including height restricted deck spaces of the MPF MPS and amphibious class ships. | projection naval ships where current HMMWVs are loaded, including height restricted deck spaces of the MPF MPS and amphibious class ships. | including height restricted deck spaces of the MPF MPS and amphibious class ships. |  | projection naval ships where current HMMWVs are loaded, including height restricted deck spaces of the MPF MPS and amphibious class ships.
Payload KPP
Combat Tactical | Combat Tactical | Combat Tactical | TBD | Combat Tactical
Vehicles (CTVs | Vehicles (CTVs | Vehicles (CTVs |  | Vehicles (CTVs
including GP, HGC, and | including GP, HGC, and | including GP, HGC, |  | including GP, HGC, and
CCWC) should have an | CCWC) should have an | and CCWC) shall |  | CCWC) should have an
on vehicle payload of | on vehicle payload of | have an on vehicle |  | on vehicle payload of
5100. CSVs including | 5100. CSVs including | payload of 3500lbs. |  | 5100. CSVs including
Utility/Prime Movers | Utility/Prime Movers | CSVs including |  | Utility/Prime Movers and
and Shelter Carriers: | and Shelter Carriers: | Utility/Prime Movers |  | Shelter Carriers: 11,000;
11,000; Trailers: 6,000. | 11,000; Trailers: 6,000. | and Shelter Carriers: |  | Trailers: 6,000. Shelter
Shelter carrier variants | Shelter carrier variants | 5100; Trailers: 3500 |  | carrier variants shall
shall transport the S250 | shall transport the S250 | for CTV variants; 5100 |  | transport the S250
LWMS, S-788 SICPS | LWMS, S-788 SICPS | for CSV variants. |  | LWMS, S-788 SICPS
RWS, SECM, and other | RWS, SECM, and other | Shelter carrier variants |  | RWS, SECM, and other
Data Interchange | Data Interchange | shall transport the |  | Data Interchange
shelters within the | shelters within the | S250 LWMS, S-788 |  | shelters within the
payload capabilities of | payload capabilities of | SICPS RWS, SECM, |  | payload capabilities of
the variant, current as | the variant, current as | and other Data |  | the variant, current as of
of June 2011. | of June 2011. | Interchange shelters |  | June 2011.
within the payload
capabilities of the
variant, current as of
June 2011.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Development Document (CDD) dated March 15, 2012
Change Explanations
None
Notes
Joint Program Office JLTV will begin reporting demonstrated performance after completion of LRIP testing.
JROC approved CPD, dated November 21, 2014.

## Table 16
Acronyms and Abbreviations
@ - at
Am - Materiel Availability Ao - Operational Availability ATO - Approval to Operate C - Celsius
CCWC - Close Combat Weapons Carrier CSV - Combat Support Vehicle
CTV - Combat Tactical Vehicle
DAA - Designated Approval Authority Deg - Degree
DoD IEA - DoD Information Enterprise Architecture DoDAF - DoD Architecture Framework
ECC - Essential Combat Configuration F - Fahrenheit
FoV - Family of Vehicles ft - Feet
GESP - GIG Enterprise Service Profiles GIG - Global Information Grid
GP - General Purpose
GVW - Gross Vehicle Weight HGC - Heavy Guns Carrier
HMMWV - High Mobility Multi-Purpose Wheeled Vehicle IAT - Internal Air Transport
IATO - Interim Authorization to Operate IP - Internet Protocol
IT - Information Technology
JROC - Joint Requirements Oversight Council JTRS - Joint Tactical Radio System
k - Thousand lbs - Pounds
LWMS - Light Weight Multipurpose Shelter MPF - Maritime Pre-positioning Force MPS - Maritime Pre-Positioning Squadron nm - Nautical Miles
RCI - Rating Cone Index
SAASM - Selective Availability Anti-Spoofing Module SECM - Shop Equipment Contact Maintenance
SICPS RWS - Standardized Integrated Command Post System Rigid Wall Shelter SL/SD - Sea Level / Standard Day
TV-1 - Technical Standards Profile USA - U.S. Army
USMC - U.S. Marine Corps

## Table 17
Track to Budget
RDT&E
Appn |  | BA | PE
Navy | 1319 04 |  | 0603635M
| Project |  | Name
| 3209 |  | Marine Corps Grnd Cmbt/Supt (Shared) (Sunk) Sys
| Notes: |  | Funding line used through FY 2012
Navy | 1319 04 |  | 0605812M
| Project |  | Name
| 3209 |  | Joint Light Tactical Vehicle
| Notes: |  | Funding line FY 2013 and beyond
Army | 2040 04 |  | 0603804A
| Project |  | Name
| L04 |  | Joint Light Tactical Vehicle (Shared) (Sunk) (JLTV) - Advanced Development (AD)
| Notes: |  | Funding line used from FY 2008 - FY 2011
Army | 2040 05 |  | 0604804A
| Project |  | Name
| L50 |  | Joint Light Tactical Vehicle (Shared) (Sunk) (JLTV) - System Development and Demonstration (SDD)
| Notes: |  | Funding line used FY 2012
Army | 2040 05 |  | 0605812A
| Project |  | Name
| VU9 |  | Joint Light Tactical Vehicle - Engineering and Manufacturing Development (EMD)
| Notes: |  | Funding line FY 2013 and beyond
Procurement
Appn |  | BA | PE
Navy | 1109 05 |  | 0206211M
| Line Item |  | Name
| 5095 |  | Joint Light Tactical Vehicle
| Notes: |  | Funding starts FY 2015
Army | 2035 01 |  | 0216300A
| Line Item |  | Name
| D15603 |  | Joint Light Tactical Vehicle
| Notes: |  | Funding starts FY 2015

## Table 18
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2012 $M |  |  |  |  | BY 2012 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 962.3 |  | 962.3 | 1058.5 |  | 911.6 |  | 1009.8 |  | 1009.8 |  | 948.9
Procurement |  | 21782 |  | 21782 | 23960.2 |  | 18161.8 |  | 29359.4 |  | 29359.4 |  | 23718.9
Flyaway |  | -- |  | -- | -- |  | 17107.1 |  | -- |  | -- |  | 22419.7
Recurring |  | -- |  | -- | -- |  | 15591.9 |  | -- |  | -- |  | 20452.7
Non Recurring |  | -- |  | -- | -- |  | 1515.2 |  | -- |  | -- |  | 1967
Support |  | -- |  | -- | -- |  | 1054.7 |  | -- |  | -- |  | 1299.2
Other Support |  | -- |  | -- | -- |  | 863.3 |  | -- |  | -- |  | 1063.4
Initial Spares |  | -- |  | -- | -- |  | 191.4 |  | -- |  | -- |  | 235.8
MILCON |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 35.9 |  | 35.9 | 39.5 |  | 0 |  | 39.5 |  | 39.5 |  | 0
Total |  | 22780.2 |  | 22780.2 | N/A |  | 19073.4 |  | 30408.7 |  | 30408.7 |  | 24667.8
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The JLTV Joint Cost Position (JCP), approved July 12, 2012 by Assistant Secretary of the Army for Financial Management & Comptroller (ASA FM&C), was used to establish the APB. Costs are reflected at the 50% Confidence Level in accordance with Army Cost Guidance, Army Regulation 11-18.
Procurement does not include recurring production for government furnished equipment and non-Program Manager (PM) funded modifications.
Operations and Support includes training ammunition, non-PM funded modifications (Procurement), Military Personnel, and all Operations and Maintenance (minus demilitarization / demilitarization second destination tranportation repairable and consumerable parts associated with government furnished equipment / end-item supply and maintenance of government furnished equipment).
Cost Notes
For the JLTV program, the unit of measure for APUC and PAUC calculations is one vehicle.

## Table 19
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 131 | 131 | 115
Procurement | 54599 | 54599 | 54599
Total | 54730 | 54730 | 54714
Quantity Notes
The estimate is updated to reflect the latest test plan. EMD testing results determine that fewer Live Fire Tests were required, therefore RDT&E quantities were reduced.
Due to the effects of the 98 day slip (GAO Protest) to the program, methodology updates to fielding costs and reductions to the Army Procurement dollars at the end of the budget process, quantities throughout the FYDP years differ for both Army and U.S. Marine Corps from the program's FY 2017 PB budget documents.

## Table 20
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 741.7 | 64.6 |  |  | 34.7 | 10.9 | 5.8 |  | 5.1 |  |  | 2 |  | 84.1 |  | 948.9
Procurement | 172 | 309.9 |  |  | 700.7 | 1249.6 | 1751.3 |  | 1784.5 |  |  | 1238.4 |  | 16512.5 |  | 23718.9
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0
PB 2017 Total | 913.7 | 374.5 |  |  | 735.4 | 1260.5 | 1757.1 |  | 1789.6 |  |  | 1240.4 |  | 16596.6 |  | 24667.8
PB 2016 Total | 914 | 456.9 |  |  | 803 | 1383.1 | 1713.8 |  | 1796.8 |  |  | 1645.5 |  | 21860.9 |  | 30574
Delta | -0.3 | -82.4 |  |  | -67.6 | -122.6 | 43.3 |  | -7.2 |  |  | -405.1 |  | -5264.3 |  | -5906.2
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 115 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 115
Production | 0 |  | 406 |  | 821 | 1896 | 3435 |  | 4584 | 5004 |  | 2769 |  | 35684 |  | 54599
PB 2017 Total | 115 |  | 406 |  | 821 | 1896 | 3435 |  | 4584 | 5004 |  | 2769 |  | 35684 |  | 54714
PB 2016 Total | 121 |  | 191 |  | 570 | 1111 | 2678 |  | 3270 | 3360 |  | 3164 |  | 40255 |  | 54720
Delta | -6 |  | 215 |  | 251 | 785 | 757 |  | 1314 | 1644 |  | -395 |  | -4571 |  | -6

## Table 21
Cost and Funding
Annual Funding By Appropriation
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 84.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.1
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.6
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.7
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.8
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.2
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.3
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.8
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.6
Subtotal |  | 66 | -- |  | -- |  | -- |  | -- |  | -- |  | 592.8

## Table 22
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 110.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.3
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.4
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.7
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.7
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.6
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.3
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
Subtotal |  | 66 | -- |  | -- |  | -- |  | -- |  | -- |  | 561

## Table 23
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.9
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.2
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
Subtotal |  | 49 | -- |  | -- |  | -- |  | -- |  | -- |  | 356.1

## Table 24
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.2
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
Subtotal |  | 49 | -- |  | -- |  | -- |  | -- |  | -- |  | 350.6

## Table 25
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | 400 | 126.1 |  | -- |  | 26.2 |  | 152.3 |  | 12.3 |  | 164.6
2016 |  | 697 | 186.3 |  | -- |  | 57.4 |  | 243.7 |  | 6.2 |  | 249.9
2017 |  | 1694 | 439.9 |  | -- |  | 97.3 |  | 537.2 |  | 50.3 |  | 587.5
2018 |  | 2268 | 696.6 |  | -- |  | 72.1 |  | 768.7 |  | 59.2 |  | 827.9
2019 |  | 2781 | 829.2 |  | -- |  | 76.8 |  | 906 |  | 176.5 |  | 1082.5
2020 |  | 3093 | 904.2 |  | -- |  | 54.5 |  | 958.7 |  | 144.6 |  | 1103.3
2021 |  | 2745 | 919.5 |  | -- |  | 55.9 |  | 975.4 |  | 164 |  | 1139.4
2022 |  | 2851 | 1067 |  | -- |  | 69.5 |  | 1136.5 |  | 32.4 |  | 1168.9
2023 |  | 2809 | 1034.5 |  | -- |  | 111.3 |  | 1145.8 |  | 37 |  | 1182.8
2024 |  | 2638 | 1062.1 |  | -- |  | 93.2 |  | 1155.3 |  | 34.6 |  | 1189.9
2025 |  | 2471 | 1016.1 |  | -- |  | 84.9 |  | 1101 |  | 37 |  | 1138
2026 |  | 2556 | 1012.1 |  | -- |  | 86.6 |  | 1098.7 |  | 31.2 |  | 1129.9
2027 |  | 2363 | 964.5 |  | -- |  | 90 |  | 1054.5 |  | 29.4 |  | 1083.9
2028 |  | 2333 | 944 |  | -- |  | 117.7 |  | 1061.7 |  | 29.4 |  | 1091.1
2029 |  | 2385 | 981.2 |  | -- |  | 101.8 |  | 1083 |  | 27.9 |  | 1110.9
2030 |  | 2373 | 1011.2 |  | -- |  | 92.7 |  | 1103.9 |  | 28.3 |  | 1132.2
2031 |  | 2230 | 1042.4 |  | -- |  | 85 |  | 1127.4 |  | 27.4 |  | 1154.8
2032 |  | 2483 | 1068.2 |  | -- |  | 78.8 |  | 1147 |  | 30.7 |  | 1177.7
2033 |  | 2466 | 1071.4 |  | -- |  | 99.1 |  | 1170.5 |  | 31.1 |  | 1201.6
2034 |  | 2684 | 1134.7 |  | -- |  | 70.8 |  | 1205.5 |  | 34.2 |  | 1239.7
2035 |  | 2779 | 1179.5 |  | -- |  | 51.1 |  | 1230.6 |  | 36 |  | 1266.6
2036 |  | -- | -- |  | -- |  | 46.7 |  | 46.7 |  | 2.3 |  | 49
2037 |  | -- | -- |  | -- |  | 47.6 |  | 47.6 |  | 2.2 |  | 49.8
Subtotal |  | 49099 | 18690.7 |  | -- |  | 1767 |  | 20457.7 |  | 1064.2 |  | 21521.9

## Table 26
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | 400 | 117.6 |  | -- |  | 24.4 |  | 142 |  | 11.5 |  | 153.5
2016 |  | 697 | 171.4 |  | -- |  | 52.8 |  | 224.2 |  | 5.7 |  | 229.9
2017 |  | 1694 | 397.3 |  | -- |  | 87.8 |  | 485.1 |  | 45.5 |  | 530.6
2018 |  | 2268 | 616.9 |  | -- |  | 63.9 |  | 680.8 |  | 52.4 |  | 733.2
2019 |  | 2781 | 719.9 |  | -- |  | 66.7 |  | 786.6 |  | 153.2 |  | 939.8
2020 |  | 3093 | 769.6 |  | -- |  | 46.4 |  | 816 |  | 123.1 |  | 939.1
2021 |  | 2745 | 767.3 |  | -- |  | 46.6 |  | 813.9 |  | 136.9 |  | 950.8
2022 |  | 2851 | 873 |  | -- |  | 56.8 |  | 929.8 |  | 26.5 |  | 956.3
2023 |  | 2809 | 829.8 |  | -- |  | 89.2 |  | 919 |  | 29.7 |  | 948.7
2024 |  | 2638 | 835.2 |  | -- |  | 73.3 |  | 908.5 |  | 27.2 |  | 935.7
2025 |  | 2471 | 783.4 |  | -- |  | 65.3 |  | 848.7 |  | 28.6 |  | 877.3
2026 |  | 2556 | 765 |  | -- |  | 65.5 |  | 830.5 |  | 23.5 |  | 854
2027 |  | 2363 | 714.7 |  | -- |  | 66.7 |  | 781.4 |  | 21.8 |  | 803.2
2028 |  | 2333 | 685.8 |  | -- |  | 85.5 |  | 771.3 |  | 21.4 |  | 792.7
2029 |  | 2385 | 698.8 |  | -- |  | 72.5 |  | 771.3 |  | 19.9 |  | 791.2
2030 |  | 2373 | 706.1 |  | -- |  | 64.7 |  | 770.8 |  | 19.8 |  | 790.6
2031 |  | 2230 | 713.6 |  | -- |  | 58.3 |  | 771.9 |  | 18.7 |  | 790.6
2032 |  | 2483 | 716.9 |  | -- |  | 52.9 |  | 769.8 |  | 20.6 |  | 790.4
2033 |  | 2466 | 705 |  | -- |  | 65.1 |  | 770.1 |  | 20.5 |  | 790.6
2034 |  | 2684 | 732 |  | -- |  | 45.7 |  | 777.7 |  | 22 |  | 799.7
2035 |  | 2779 | 746 |  | -- |  | 32.4 |  | 778.4 |  | 22.7 |  | 801.1
2036 |  | -- | -- |  | -- |  | 29 |  | 29 |  | 1.4 |  | 30.4
2037 |  | -- | -- |  | -- |  | 29 |  | 29 |  | 1.3 |  | 30.3
Subtotal |  | 49099 | 14065.3 |  | -- |  | 1340.5 |  | 15405.8 |  | 853.9 |  | 16259.7

## Table 27
Annual Funding 1109 ¦ Procurement ¦ Procurement, Marine Corps
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | 6 | 2.2 |  | -- |  | 4.2 |  | 6.4 |  | 1 |  | 7.4
2016 |  | 124 | 41 |  | -- |  | 19 |  | 60 |  | -- |  | 60
2017 |  | 202 | 60.8 |  | -- |  | 52.3 |  | 113.1 |  | 0.1 |  | 113.2
2018 |  | 1167 | 361.2 |  | -- |  | 27.6 |  | 388.8 |  | 32.9 |  | 421.7
2019 |  | 1803 | 582.5 |  | -- |  | 27.3 |  | 609.8 |  | 59 |  | 668.8
2020 |  | 1911 | 602.1 |  | -- |  | 19.1 |  | 621.2 |  | 60 |  | 681.2
2021 |  | 24 | 7.6 |  | -- |  | 19.2 |  | 26.8 |  | 72.2 |  | 99
2022 |  | 263 | 104.6 |  | -- |  | 24.6 |  | 129.2 |  | 4.3 |  | 133.5
2023 |  | -- | -- |  | -- |  | 6.6 |  | 6.6 |  | 3.9 |  | 10.5
2024 |  | -- | -- |  | -- |  | 0.1 |  | 0.1 |  | 1.6 |  | 1.7
Subtotal |  | 5500 | 1762 |  | -- |  | 200 |  | 1962 |  | 235 |  | 2197

## Table 28
Annual Funding 1109 ¦ Procurement ¦ Procurement, Marine Corps
Fiscal Year | Quantity |  | BY 2012 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2015 |  | 6 | 2.1 |  | -- |  | 3.9 |  | 6 |  | 0.9 |  | 6.9
2016 |  | 124 | 37.8 |  | -- |  | 17.5 |  | 55.3 |  | -- |  | 55.3
2017 |  | 202 | 55 |  | -- |  | 47.2 |  | 102.2 |  | 0.1 |  | 102.3
2018 |  | 1167 | 320.3 |  | -- |  | 24.5 |  | 344.8 |  | 29.1 |  | 373.9
2019 |  | 1803 | 506.3 |  | -- |  | 23.7 |  | 530 |  | 51.4 |  | 581.4
2020 |  | 1911 | 513.1 |  | -- |  | 16.3 |  | 529.4 |  | 51.1 |  | 580.5
2021 |  | 24 | 6.3 |  | -- |  | 16 |  | 22.3 |  | 60.4 |  | 82.7
2022 |  | 263 | 85.7 |  | -- |  | 20.2 |  | 105.9 |  | 3.5 |  | 109.4
2023 |  | -- | -- |  | -- |  | 5.3 |  | 5.3 |  | 3.1 |  | 8.4
2024 |  | -- | -- |  | -- |  | 0.1 |  | 0.1 |  | 1.2 |  | 1.3
Subtotal |  | 5500 | 1526.6 |  | -- |  | 174.7 |  | 1701.3 |  | 200.8 |  | 1902.1

## Table 29
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2012-08-20 | 2015-08-25
Approved Quantity | 3100 | 4990
Reference | Milestone B ADM | Milestone C ADM
Start Year | 2015 | 2015
End Year | 2017 | 2018

## Table 30
Foreign Military Sales
None
Nuclear Costs
None

## Table 31
Unit Cost
Unit Cost Report
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Current UCR Baseline (Oct 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 22780.2 |  |  | 19073.4
Quantity | 54730 |  |  | 54714
Unit Cost | 0.416 |  |  | 0.349 |  | -16.11
Average Procurement Unit Cost
Cost | 21782 |  |  | 18161.8
Quantity | 54599 |  |  | 54599
Unit Cost | 0.399 |  |  | 0.333 |  | -16.54
Item |  | BY 2012 $M | BY 2012 $M |  | % Change
|  | Original UCR Baseline (Oct 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 22780.2 |  |  | 19073.4
Quantity | 54730 |  |  | 54714
Unit Cost | 0.416 |  |  | 0.349 |  | -16.11
Average Procurement Unit Cost
Cost | 21782 |  |  | 18161.8
Quantity | 54599 |  |  | 54599
Unit Cost | 0.399 |  |  | 0.333 |  | -16.54

## Table 32
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2012 $M | [5 empty] | TY $M
[8 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Oct 2012 |  |  |  |  | 0.416 |  |  |  | 0.399 |  |  | 0.556 |  |  | 0.538
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Oct 2012 |  |  |  |  | 0.416 |  |  |  | 0.399 |  |  | 0.556 |  |  | 0.538
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 0.412 |  |  |  | 0.396 |  |  | 0.559 |  |  | 0.542
Current Estimate |  |  | Dec 2015 |  |  |  |  | 0.349 |  |  |  | 0.333 |  |  | 0.451 |  |  | 0.434
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [14 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  |  | Total
0.556 0.002 0.000 -0.026 0.000 -0.080 0.000 -0.001 -0.105 0.451
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  |  | Total
0.538 0.002 0.000 -0.026 0.000 -0.079 0.000 -0.001 -0.104 0.434

## Table 33
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Aug 2012 | N/A | Aug 2012
Milestone C | N/A | May 2015 | N/A | Aug 2015
IOC | N/A | May 2018 | N/A | Dec 2019
Total Cost (TY $M) | N/A | 30408.7 | N/A | 24667.8
Total Quantity | N/A | 54730 | N/A | 54714
PAUC | N/A | 0.556 | N/A | 0.451

## Table 34
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Acq O&M |  | Total
SAR Baseline (Development Estimate)
Previous Changes
1009.8 29359.4 -- 39.5 30408.7
Economic |  | 1.9 |  | 344.7 |  | -- |  | 0.4 |  | 347
Quantity |  | -7.3 |  | -- |  | -- |  | -- |  | -7.3
Schedule |  | -12.7 |  | -120.1 |  | -- |  | -- |  | -132.8
Engineering |  | -- |  | -- |  | -- |  | -- |  | --
Estimating |  | -5.3 |  | -26.1 |  | -- |  | -39.9 |  | -71.3
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 29.7 |  | -- |  | -- |  | 29.7
Subtotal |  | -23.4 |  | 228.2 |  | -- |  | -39.5 |  | 165.3
Current Changes Economic |  | -2.9 |  | -232.2 |  | -- |  | -- |  | -235.1
Quantity |  | -4.5 |  | -- |  | -- |  | -- |  | -4.5
Schedule |  | -- |  | -1280.8 |  | -- |  | -- |  | -1280.8
Engineering |  | -- |  | -- |  | -- |  | -- |  | --
Estimating |  | -30.1 |  | -4274.2 |  | -- |  | -- |  | -4304.3
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -81.5 |  | -- |  | -- |  | -81.5
Subtotal |  | -37.5 |  | -5868.7 |  | -- |  | -- |  | -5906.2
Total Changes |  | -60.9 |  | -5640.5 |  | -- |  | -39.5 |  | -5740.9
CE - Cost Variance |  | 948.9 |  | 23718.9 |  | -- |  | -- |  | 24667.8
CE - Cost & Funding |  | 948.9 |  | 23718.9 |  | -- |  | -- |  | 24667.8

## Table 35
Summary BY 2012 $M
Item | RDT&E | Procurement | MILCON | Acq O&M | Total
SAR Baseline (Development Estimate) | 962.3 | 21782 | -- | 35.9 | 22780.2
Previous Changes
Economic | -- | -- | -- | -- | --
Quantity | -6.9 | -- | -- | -- | -6.9
Schedule | -13.1 | -144.8 | -- | -- | -157.9
Engineering | -- | -- | -- | -- | --
Estimating | -6.4 | -25.7 | -- | -35.9 | -68
Other | -- | -- | -- | -- | --
Support | -- | 24 | -- | -- | 24
Subtotal | -26.4 | -146.5 | -- | -35.9 | -208.8
Current Changes
Economic | -- | -- | -- | -- | --
Quantity | -4.1 | -- | -- | -- | -4.1
Schedule | -- | -- | -- | -- | --
Engineering | -- | -- | -- | -- | --
Estimating | -20.2 | -3455.7 | -- | -- | -3475.9
Other | -- | -- | -- | -- | --
Support | -- | -18 | -- | -- | -18
Subtotal | -24.3 | -3473.7 | -- | -- | -3498
Total Changes | -50.7 | -3620.2 | -- | -35.9 | -3706.8
CE - Cost Variance | 911.6 | 18161.8 | -- | -- | 19073.4
CE - Cost & Funding | 911.6 | 18161.8 | -- | -- | 19073.4
Previous Estimate: December 2014

## Table 36
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -2.9
Reduction of RDT&E funded test vehicles (Army). (Quantity) | -2.2 | -2.4
Reduction of RDT&E funded test vehicles (Navy). (Quantity) | -1.9 | -2.1
Revised estimate for updated test plans and asset requirements for LRIP and FRP (Army). | -14.2 | -23.6
(Estimating)
Revised estimate for updated test plans and asset requirements for LRIP and FRP (Navy). (Estimating)
Reduction of Government Systems Engineering and Program Management (SEPM) due to methodology change (Army). (Estimating)
+13.7 +14.5
-10.4 -11.1
Reduction of Government SEPM due to methodology change (Navy). (Estimating) -10.6 -11.2 Adjustment for current and prior escalation. (Estimating) +1.3 +1.3
RDT&E Subtotal -24.3 -37.5
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -232.2
Stretch out of procurement buy profile due to budget adjustments and revised assumptions regarding maximum buy profile by year (Army). (Schedule)
0.0 -1276.5
Stretch out of procurement buy profile due to budget adjustments (Navy). (Schedule) 0.0 -4.3
Revised estimates for unit costs of vehicles and kits based on realized savings (Army). (Estimating)
Revised estimates for unit costs of vehicles and kits based on realized savings (Navy). (Estimating)
Realized program efficiencies as a result of contractor SEPM down select (Army). (Estimating)
Realized program efficiencies as a result of contractor SEPM down select (Navy). (Estimating)
-2577.8 -3101.1
-522.1 -602.8
-17.7 -81.3
+49.0 +57.4
Methodology change in estimating Technical Data Package costs (Army). (Estimating) -390.6 -550.1 Adjustment for current and prior escalation. (Estimating) +3.5 +3.7
Adjustment for current and prior escalation. (Support) +0.2 +0.3
Decrease in Other Support due to a change in estimating methodology, updated cost data in fielding, and New Equipment Training (Army). (Support)
Increase in Other Support due to a change in estimating methodology, updated cost data in fielding, and New Equipment Training (Navy). (Support)
Decrease in Initial Spares due to a change in estimating methodology and updated cost data in initial spares (Army). (Support)
Increase in Initial Spares due to a change in estimating methodology and updated cost data in initial spares (Navy). (Support)
-172.5 -252.4
+116.5 +137.0
+7.3 -1.4
+30.5 +35.0
Procurement Subtotal -3473.7 -5868.7

## Table 37
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: LRIP & FRP contract
Contractor: Oshkosh Defense LLC
Contractor Location: 2307 Oregon St
Oshkosh, WI 54902
Contract Number: W56HZV-15-C-0095
Contract Type: Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF)
Award Date: August 25, 2015
Definitization Date:
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
114.7 N/A 201 114.7 N/A 201 114.7 114.7
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances -- --
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract since an EVM waiver was granted by the Army Acquisition Executive on July 1, 2015 due to the Cost Plus Fixed Fee Contract Line Items containing Level of Effort (LOE) type
work. There is a possibility that a System Technical Support work directive could exceed the $20M threshold, represent work of a discrete, non-LOE nature, and reflect a period of performance long enough to warrant application of EVM. Should such a case arise, JLTV will invoke EVM requirements on any individual or combination of related work directives that reflect such characteristics.
Notes
This is the first time this contract is being reported.
This contract is comprised of a basic performance period plus eight option periods.

## Table 38
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 90 | 90 | 115 | 78.26%
Production | 0 | 0 | 54599 | 0%
Total Program Quantity Delivered | 90 | 90 | 54714 | 0.16%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
24667.8
694.8
2.82%
30
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
9
30%
1288.2
5.22%
The above data is current as of January 31, 2016.

## Table 39
Operating and Support Cost
Cost Estimate Details
Date of Estimate: December 31, 2015
Source of Estimate: POE
Quantity to Sustain: 54599
Unit of Measure: Vehicle
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2019 - FY 2056
Total JLTV vehicle quantity of 54,714 includes 115 RDT&E funded vehicles and 54,599 Procurement funded vehicles. RDT&E vehicles represent prototypes from the Technology Development and EMD phases and vehicles for Live Fire and Destructive Testing during the Production phase. Prototypes, Live Fire and Destructive Test assets will not be fielded.
Sustainment quantity is the Procurement quantity of 54,599
Procurement Quantity: 49,099 (Army) / 5,500 (U.S. Marine Corps (USMC))
Sustainment Strategy
Reflects peacetime Operational Tempo (OPTEMPO) as identified by sub-configuration by the Army G-3/5/7 (Training) and in JLTV Operation Mode Summary & Mission Profile for the USMC. Reduced OPTEMPO used for Army Training and Army Prepositioned Stock units and inactive USMC units.
Interim Contractor Support will occur beginning in FY 2019 for Army and USMC fielding and will not exceed three years; it will then transition to organic maintenance support. USMC Supply Support is required from IOC (FY 2020) until fielding is complete (FY2023).
Army maintenance concept will be two levels of maintenance: Field and Sustainment maintenance. USMC maintenance concept will be three levels of maintenance: Operator/Crew, Field, and Sustainment.
The JLTV will incur a condition-based overhaul, starting at ten years. Of the operational vehicles that are older than ten years, 2.4 percent per year will undergo condition-based overhaul.
Antecedent Information
Total and annual per vehicle O&S costs for High Mobility Multipurpose Wheeled Vehicle (HMMWV) were provided by Army Product Manager Light Tactical Vehicles (PM LTV). This estimate is based on an operating schedule from FY 2015 to FY 2045 and includes actual HMMWV costs as available.
The HMMWV costs provided by PM LTV are for Army only.

## Table 40
Annual O&S Costs BY2012 $K
Cost Element |  | JLTV Average Annual Cost Per Vehicle | [5 empty] | HMMWV (Antecedent) Average Annual $ Per Vehicle
Unit-Level Manpower |  | 4.804 | [5 empty] | 7.7
Unit Operations |  | 3.365 | [5 empty] | 1.6
Maintenance |  | 10.13 | [5 empty] | 4.3
Sustaining Support |  | 2.41 | [5 empty] | 5.3
Continuing System Improvements |  | 1.485 | [5 empty] | 0.5
Indirect Support |  | 1.603 | [5 empty] | 2.9
Other |  | 0 | [5 empty] | 0
Total |  | 23.797 | [5 empty] | 22.3
The JLTV O&S costs reflect peacetime operations.
The cost excludes Government Furnished Equipment (GFE) and Consumable and Reparable costs as it was decided at the Joint Cost Review Board on May 15, 2012 to exclude GFE procurement & sustainment from program costs in the Joint Cost Position and APB.
Item | Total O&S Cost $M
| JLTV | [7 empty] | HMMWV (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 31728.7 |  |  | 34901.6 |  |  | 25985.8 |  | 55472.7
Then Year | 50630.5 |  |  | N/A |  |  | 40150 |  | N/A
Equation to Translate Annual Cost to Total Cost
Unitized O&S Cost = Total O&S Costs / Total Operational Vehicle Years where Total Operational Vehicle Years = Total Operating Vehicles * Economic Useful Life
Total O&S Costs: $25,985.8M (BY$ 2012)
Total Operational Vehicle Years: 1,091,980
Total Operating Vehicles: 54,599
Economic Useful Life: 20 Years
O&S Cost Variance
Category |  |  | BY 2012 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
32516.6
Programmatic/Planning Factors 0.0
Cost Estimating Methodology -2210.8 Updated methodology to exclude training ammunition and
to include base ops environmental estimate.

## Table 41
Cost Data Update -739.3 Updated Cost Estimating Relationship (CER) based on current O&S Management Information System data for Consumable/Reparables. Reflects updated vehicle manufacturing costs as input to O&S CERs (for Consumable/Reparables cost, civilian maintenance, overhaul). Updated cost data for transportation costs.
Labor Rate -3619.7 Updated Army Military-Civilian Cost System Military Pay rates.
Energy Rate Technical Input | 39.0 Updated cost of fuel. 0.0
Other | 0
Total Changes | -6530.8
Current Estimate | 25985.8
Disposal Estimate Details
Date of Estimate: December 31, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2012 $M): Total costs for disposal of all Vehicle are 191.5
Total Demilitarization Cost includes costs for disposal and transportation associated with disposal of JLTVs. The costs have increased from the previous year due to the inclusion of disposal costs for armor kits and an updated assumption of a higher quantity of vehicles to be disposed of for USMC and Army.