## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-384
Air and Missile Defense Radar (AMDR)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 14
Low Rate Initial Production 22
Foreign Military Sales 23
Nuclear Costs 23
Unit Cost 24
Cost Variance 27
Contracts 30
Deliveries and Expenditures 32
Operating and Support Cost 33

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Air and Missile Defense Radar (AMDR)
DoD Component
Navy
Responsible Office
CAPT Seiko Okano 1333 Isaac Hull Ave, SE
Washington, DC 20376-7101
seiko.okano@navy.mil
Phone: 202-781-0461
Fax:
DSN Phone: DSN Fax:
Date Assigned: April 6, 2015
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 03, 2013
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 3, 2013

## Table 6
Mission and Description
The Air and Missile Defense Radar (AMDR) is the Navy's next generation radar system that will address Ballistic Missile Defense and Air Defense capability gaps identified in the Maritime Air and Missile Defense of Joint Forces (MAMDJF) Initial Capabilities Document. The AMDR suite consists of an S-band radar (AMDR-S), X-band radar, and a Radar Suite Controller (RSC). AMDR-S is a new development Integrated Air and Missile Defense radar providing sensitivity for long range detection and engagement of advanced threats. The X-band radar is a horizon-search radar based on existing technology. The RSC provides S and X band radar resource management, coordination, and interface to the combat system. AMDR will be deployed on the Guided Missile Destroyer (DDG) 51 Flight III.

## Table 7
Executive Summary
After completing Concept Studies (CS) and Technology Development (TD) phase contracts with Raytheon, Northrop Grumman, and Lockheed Martin, the AMDR program achieved Milestone B in September 2013 and received a signed ADM on October 4, 2013. After a full and open competition, a 48 month EMD phase contract was awarded to Raytheon on October 10, 2013. The EMD phase focuses on the design of the system and development of an affordable and executable manufacturing process leading to a Production Readiness Review. Additional activities during the EMD phase include a hardware and a system Critical Design Review (CDR) to assess the completeness of the detailed design and how it supports the performance requirements. The AMDR hardware CDR was completed December 3, 2014 and the System CDR was completed on April 29, 2015. EMD will also include integration and test of a single-faced AMDR-S/RSC Engineering Development Model with an AN/SPQ-9B asset at the land- based test site at the Pacific Missile Range Facility (PMRF) in Kauai, HI. The EMD phase will conclude in an AMDR Milestone C decision.
Program testing began following a successful Developmental Test (DT-2) Test Readiness Review (TRR), which completed on June 9, 2015. Testing will continue through EMD phase with the DT-3 Test Readiness Review scheduled for Q4 FY 2016. Software Baseline Review (SBR) 2 was completed on June 10, 2015.
The FY 2016 budget included a $9M reduction for program execution. There are currently no schedule or technical issues for the program.
The program required one waiver to Section 2366b criteria. The provision requiring that a program "...has received a Preliminary Design Review (PDR) and conducted a formal post-PDR assessment" was deferred until the EMD phase. The delta hardware PDR was completed on May 21, 2014 and the system delta PDR was completed on August 27, 2014. The post-PDR Assessment was signed on June 22, 2015.
USD(AT&L) also approved proceeding into EMD without Director, Operational Test & Evaluation approval of the AMDR Test and Evaluation Master Plan, "... because of an unresolved issue regarding the need for an unmanned test asset for close-in Aegis ship self defense engagement testing." The PB 2017 budget includes $175M, added in FY2019-2021, to support long lead hardware procurement for unmanned Self-Defense Test Ship (SDTS) at-sea testing in support of DDG-51 Flight III and Aegis Advanced Capability Build (ACB) 20 requirements.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | Jul 2013 | Jul 2013 | Jan 2014 | Sep 2013
System CDR | Jan 2015 | Jan 2015 | Jul 2015 | Apr 2015
DT-3 Complete | Apr 2017 | Apr 2017 | Oct 2017 | Aug 2017
Milestone C | Jul 2017 | Jul 2017 | Jan 2018 | Sep 2017
IYND | Sep 2019 | Sep 2019 | Mar 2020 | Jan 2020
IOT&E Complete | Jun 2023 | Jun 2023 | Dec 2023 | Jun 2023
IOC | Sep 2023 | Sep 2023 | Mar 2024 | Sep 2023
Change Explanations
(Ch-1) The current estimate for DT-3 Complete has changed from September 2017 to August 2017 to reflect current planned DT-3 completion date.
Acronyms and Abbreviations
CDR - Critical Design Review
DT&E - Developmental Test and Evaluation DT-3 - Developmental Test-3
IOT&E - Initial Operational Test and Evaluation IYND - In Yard Need Date

## Table 10
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Availability
Ao ≥0.99 | Ao ≥0.99 | Ao ≥0.98 | TBD | Ao ≥0.99
System Training
Maintenance technicians | Maintenance | Maintenance | TBD | Maintenance
correctly perform ≥ 99% | technicians correctly | technicians correctly |  | technicians correctly
of critical tasks and ≥ | perform ≥ 99% of | perform ≥ 99% of |  | perform ≥ 99% of
99% of non-critical tasks | critical tasks and ≥ 99% | critical tasks and ≥ 80% |  | critical tasks and ≥
as defined in the TTL. | of non-critical tasks as | of non-critical tasks as |  | 80% of non-critical
| defined in the TTL. | defined in the TTL. |  | tasks as defined in
the TTL.
Net Ready
Will satisfy applicable Net | Will satisfy applicable | Will satisfy applicable | TBD | Will satisfy applicable
Ready KPP elements for | Net Ready KPP | Net Ready KPP |  | Net Ready KPP
all operational activities | elements for all | elements for joint |  | elements for joint
and information | operational activities | critical operational |  | critical operational
exchanges. | and information | activities and |  | activities and
| exchanges. | information exchanges. |  | information
exchanges.
Energy Efficiency
Two reduced power | Two reduced power | Two reduced power | TBD | Reduced Power
states for AMDR-S, when | states for AMDR-S, | states for AMDR-S, |  | Substate 1
commanded by the | when commanded by | when commanded by |  | consumes 1110kW
platform CMS: State 1 | the platform CMS: State | the platform CMS: State |  | total power; Reduced
consumes no more than | 1 consumes no more | 1 consumes no more |  | power Substate 2
1100 kW total prime | than 1100 kW total | than 1230 kW total |  | consumes 860kW
power; State 2 consumes | prime power; State 2 | prime power; State 2 |  | total power
no more than 850 kW | consumes no more | consumes no more
total prime power | than 850 kW total prime | than 950 kW total prime
| power | power
Survivability
(Objective = Threshold) | (Objective = Threshold) | Exemption - AMDR will | TBD | Exemption - AMDR
Exemption - AMDR will | Exemption - AMDR will | be integrated into the |  | will be integrated into
be integrated into the | be integrated into the | DDG 51 hull with no |  | the DDG 51 hull with
DDG 51 hull with no | DDG 51 hull with no | decrease in survivability |  | no decrease in
decrease in survivability | decrease in survivability | of the hull based on |  | survivability of the hull
of the hull based on DDG | of the hull based on | DDG 51 live fire |  | based on DDG 51
51 live fire equivalent | DDG 51 live fire | equivalent testing (DDG |  | live fire equivalent
testing (DDG 81 shock | equivalent testing (DDG | 81 shock trial) |  | testing (DDG 81
trial) | 81 shock trial) |  |  | shock trial)
Force Protection

## Table 11
(Objective = Threshold) | (Objective = Threshold) | Exemption - Will | TBD | Exemption - Will
Exemption - Will support | Exemption - Will | support host platform |  | support host platform
host platform requirement | support host platform | requirement |  | requirement
requirement
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
The AMDR CDD was signed by the Chief of Naval Operations on April 20, 2013 (JROC Memo) signed June 27, 2013). Specific KPP values have been established in the CDD and those requirements have been flowed down to the Top Level Radar Performance (TLRP) and Top Level Requirements (TLR) documents developed by the program. AMDR capability will be codified in a CPD in support of Milestone C.
The Pre-EMD DAB's ADM, dated May 21, 2012, directed a change to the program structure so that it includes only the AMDR S-band array and the Radar Suite Controller (RSC). This APB represents only the S-band and RSC capabilities from the AMDR CDD. The X-band capabilities in the AMDR CDD will be addressed in a separate future Program of Record.
Change Explanations
None
Acronyms and Abbreviations
Ao - Operational Availability
CMS - Combat Management System DDG - Guided Missile Destroyer
kW - Kilowatt
TTL - Training Task List

## Table 12
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy 1319 04 0603513N
Project | Name
4019 Shipboard System Component (Shared) (Sunk) Development - Radar
Upgrades
Notes: Applies to FY 2006 - 2007
Navy 1319 05 0604307N
Project | Name
3044 AEGIS Combat System Engineering - Solid State SPY Radar
(Shared) (Sunk)
|  | Notes: |  | Applies to FY 2006 - 2007
Navy |  | 1319 05 |  | 0604501N
|  | Project |  | Name
|  | 3186 |  | Advanced Above Water (Shared) (Sunk) Sensors - Air and Missile Defense Radar
|  | Notes: |  | Applies to FY 2008 - 2014
Navy |  | 1319 05 |  | 0604522N
|  | Project |  | Name
|  | 3186 |  | Air and Missile Defense Radar (AMDR) System - Air and Missile Defense Radar
|  | Notes: |  | Applies to FY 2015 - 2023 (program transitioned from PE0604501N to PE0604522N in FY 2015).
Procurement
Appn |  |  | BA | PE
Navy |  | 1611 02 |  | 0204222N
|  | Line Item |  | Name
|  | 2122 |  | DDG 51 (Shared)
|  | Notes: |  | Applies to FY 2016 – 2026
MILCON
Appn |  |  | BA | PE
Navy |  | 1205 01 |  | 0805376N
|  | Project |  | Name
|  | P422 |  | Advanced Radar Detection (Sunk) Laboratory

## Table 13
Notes: Applies to FY 2009

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2013 $M | [6 empty] | BY 2013 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 1860 |  |  | 1860 | 2046 |  |  | 1849.4 |  | 1911.1 |  |  | 1911.1 |  | 1901.9
Procurement |  | 3846.9 |  |  | 3846.9 | 4231.6 |  |  | 3254.1 |  | 4724 |  |  | 4724 |  | 4016.3
Flyaway |  | -- |  |  | -- | -- |  |  | 2637.7 |  | -- |  |  | -- |  | 3258.7
Recurring |  | -- |  |  | -- | -- |  |  | 2619.8 |  | -- |  |  | -- |  | 3238.7
Non Recurring |  | -- |  |  | -- | -- |  |  | 17.9 |  | -- |  |  | -- |  | 20
Support |  | -- |  |  | -- | -- |  |  | 616.4 |  | -- |  |  | -- |  | 757.6
Other Support |  | -- |  |  | -- | -- |  |  | 519.9 |  | -- |  |  | -- |  | 638.3
Initial Spares |  | -- |  |  | -- | -- |  |  | 96.5 |  | -- |  |  | -- |  | 119.3
MILCON |  | 28.8 |  |  | 28.8 | 31.7 |  |  | 28.6 |  | 27.5 |  |  | 27.5 |  | 27.5
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 5735.7 |  |  | 5735.7 | N/A |  |  | 5132.1 |  | 6662.6 |  |  | 6662.6 |  | 5945.7
Confidence Level
Confidence Level of cost estimate for current APB: 50%
Based on the AMDR Independent Cost Estimate (ICE) prepared for the Milestone B Defense Acquisition Board (DAB) review (memo dated May 29, 2013), it is about equally likely that the estimate will prove too low or too high.
Cost Notes
Procurement funding for AMDR is also included in the DDG 51 SAR under Program Element: 0204222N. Total Acquisition Cost includes RDT&E, Procurement, and MILCON. FY 2015 - 2021 RDT&E totals reflect PB 2017 controls and include
$175M to support long lead hardware procurement for unmanned Self-Defense Test Ship (SDTS) at-sea testing in support of DDG 51 Flight III and Aegis Advanced Capability Build 20 requirements. Procurement and MILCON are unchanged from PB 2016.
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  |  | 22 |  |  |  | 22 |  |  |  |  | 22
Total |  |  | 22 |  |  |  | 22 |  |  |  |  | 22

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 1172.6 | 232.7 |  | 144.4 |  | 31.9 | 172.2 |  | 47 |  | 37.8 |  | 63.3 |  |  | 1901.9
Procurement | 0 | 262.3 |  | 351.6 |  | 340.1 | 337.8 |  | 344.2 |  | 352.2 |  | 2028.1 |  |  | 4016.3
MILCON | 27.5 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 27.5
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
PB 2017 Total | 1200.1 | 495 |  | 496 |  | 372 | 510 |  | 391.2 |  | 390 |  | 2091.4 |  |  | 5945.7
PB 2016 Total | 1203.3 | 504.1 |  | 503.5 |  | 372.8 | 366.7 |  | 374.1 |  | 382.8 |  | 2091.4 |  |  | 5798.7
Delta | -3.2 | -9.1 |  | -7.5 |  | -0.8 | 143.3 |  | 17.1 |  | 7.2 |  | 0 |  |  | 147
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 0 |  | 1 | 2 | 2 |  | 2 |  | 2 | 2 |  | 11 |  | 22
PB 2017 Total | 0 |  | 0 |  | 1 | 2 | 2 |  | 2 |  | 2 | 2 |  | 11 |  | 22
PB 2016 Total | 0 |  | 0 |  | 1 | 2 | 2 |  | 2 |  | 2 | 2 |  | 11 |  | 22
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 92.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 92.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 164.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 204.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 193.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 112.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 126.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 232.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 144.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 172.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.8
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.9
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.4
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1901.9

## Table 17
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2013 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 97.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 171.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 207
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 191.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 109.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 121.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 220
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 134.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 153.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.1
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.4
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.7
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1849.4

## Table 18
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | 1 | 178.7 |  | -- |  | 20 |  | 198.7 |  | 63.6 |  | 262.3
2017 |  | 2 | 282.5 |  | -- |  | -- |  | 282.5 |  | 69.1 |  | 351.6
2018 |  | 2 | 273.1 |  | -- |  | -- |  | 273.1 |  | 67 |  | 340.1
2019 |  | 2 | 272.3 |  | -- |  | -- |  | 272.3 |  | 65.5 |  | 337.8
2020 |  | 2 | 278.7 |  | -- |  | -- |  | 278.7 |  | 65.5 |  | 344.2
2021 |  | 2 | 287.2 |  | -- |  | -- |  | 287.2 |  | 65 |  | 352.2
2022 |  | 2 | 292.7 |  | -- |  | -- |  | 292.7 |  | 66.1 |  | 358.8
2023 |  | 3 | 447.3 |  | -- |  | -- |  | 447.3 |  | 96.6 |  | 543.9
2024 |  | 2 | 303.9 |  | -- |  | -- |  | 303.9 |  | 67 |  | 370.9
2025 |  | 3 | 464.5 |  | -- |  | -- |  | 464.5 |  | 97.3 |  | 561.8
2026 |  | 1 | 157.8 |  | -- |  | -- |  | 157.8 |  | 34.9 |  | 192.7
Subtotal |  | 22 | 3238.7 |  | -- |  | 20 |  | 3258.7 |  | 757.6 |  | 4016.3

## Table 19
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 2013 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | 1 | 160.2 |  | -- |  | 17.9 |  | 178.1 |  | 57.1 |  | 235.2
2017 |  | 2 | 248.5 |  | -- |  | -- |  | 248.5 |  | 60.8 |  | 309.3
2018 |  | 2 | 235.6 |  | -- |  | -- |  | 235.6 |  | 57.8 |  | 293.4
2019 |  | 2 | 230.3 |  | -- |  | -- |  | 230.3 |  | 55.4 |  | 285.7
2020 |  | 2 | 231.1 |  | -- |  | -- |  | 231.1 |  | 54.3 |  | 285.4
2021 |  | 2 | 233.5 |  | -- |  | -- |  | 233.5 |  | 52.8 |  | 286.3
2022 |  | 2 | 233.3 |  | -- |  | -- |  | 233.3 |  | 52.6 |  | 285.9
2023 |  | 3 | 349.5 |  | -- |  | -- |  | 349.5 |  | 75.5 |  | 425
2024 |  | 2 | 232.8 |  | -- |  | -- |  | 232.8 |  | 51.3 |  | 284.1
2025 |  | 3 | 348.8 |  | -- |  | -- |  | 348.8 |  | 73.1 |  | 421.9
2026 |  | 1 | 116.2 |  | -- |  | -- |  | 116.2 |  | 25.7 |  | 141.9
Subtotal |  | 22 | 2619.8 |  | -- |  | 17.9 |  | 2637.7 |  | 616.4 |  | 3254.1

## Table 20
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2009 27.5
Subtotal 27.5

## Table 21
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2013 $M
Total Program
2009 28.6
Subtotal 28.6

## Table 22
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2013-10-04 | 2013-10-04
Approved Quantity | 16 | 16
Reference | Milestone B ADM | Milestone B ADM
Start Year | 2016 | 2016
End Year | 2023 | 2023
The Current Total LRIP Quantity is more than 10% of the total production quantity due to timing of Initial Operational Test and Evaluation, IOC, and the need to meet the shipbuilding plan. The Milestone B ADM dated October 4, 2013 included approval for a planned LRIP quantity not to exceed 16 units.

## Table 23
Foreign Military Sales
None
Nuclear Costs
None

## Table 24
Unit Cost
Unit Cost Report
Item |  | BY 2013 $M | BY 2013 $M |  | % Change
|  | Current UCR Baseline (Oct 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 5735.7 |  |  | 5132.1
Quantity | 22 |  |  | 22
Unit Cost | 260.714 |  |  | 233.277 |  | -10.52
Average Procurement Unit Cost
Cost | 3846.9 |  |  | 3254.1
Quantity | 22 |  |  | 22
Unit Cost | 174.859 |  |  | 147.914 |  | -15.41
Item |  | BY 2013 $M | BY 2013 $M |  | % Change
|  | Original UCR Baseline (Oct 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 5735.7 |  |  | 5132.1
Quantity | 22 |  |  | 22
Unit Cost | 260.714 |  |  | 233.277 |  | -10.52
Average Procurement Unit Cost
Cost | 3846.9 |  |  | 3254.1
Quantity | 22 |  |  | 22
Unit Cost | 174.859 |  |  | 147.914 |  | -15.41

## Table 25
Unit Cost History
Item |  |  |  |  | Date |  |  |  | BY 2013 $M | [6 empty] | TY $M
[9 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Oct 2013 | [5 empty] | 260.714 |  |  |  |  | 174.859 |  |  | 302.845 |  |  | 214.727
APB as of January 2006 |  |  | N/A | [5 empty] | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A | [5 empty] | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A | [5 empty] | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Oct 2013 | [5 empty] | 260.714 |  |  |  |  | 174.859 |  |  | 302.845 |  |  | 214.727
Prior Annual SAR |  |  | Dec 2014 | [5 empty] | 227.409 |  |  |  |  | 148.173 |  |  | 263.577 |  |  | 182.559
Current Estimate |  |  | Dec 2015 | [5 empty] | 233.277 |  |  |  |  | 147.914 |  |  | 270.259 |  |  | 182.559
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [16 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  |  |  | Oth |  | Spt |  | Total
302.845 0.418 0.000 0.000 7.955 -13.668 0.000 -27.291 -32.586 270.259
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [16 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  |  | Total
214.727 1.123 0.000 0.000 0.000 -6.000 0.000 -27.291 -32.168 182.559

## Table 26
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Jul 2013 | N/A | Sep 2013
Milestone C | N/A | Jul 2017 | N/A | Sep 2017
IOC | N/A | Sep 2023 | N/A | Sep 2023
Total Cost (TY $M) | N/A | 6662.6 | N/A | 5945.7
Total Quantity | N/A | 22 | N/A | 22
PAUC | N/A | 302.845 | N/A | 270.259

## Table 27
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1911.1 | 4724 | 27.5 | 6662.6
Previous Changes
Economic | -10.4 | 17.6 | 0.2 | 7.4
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -145.8 | -125.8 | -0.2 | -271.8
Other | -- | -- | -- | --
Support | -- | -599.5 | -- | -599.5
Subtotal | -156.2 | -707.7 | -- | -863.9
Current Changes
Economic | -5.3 | 7.1 | -- | 1.8
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | 175 | -- | -- | 175
Estimating | -22.7 | -6.2 | -- | -28.9
Other | -- | -- | -- | --
Support | -- | -0.9 | -- | -0.9
Subtotal | 147 | -- | -- | 147
Total Changes | -9.2 | -707.7 | -- | -716.9
CE - Cost Variance | 1901.9 | 4016.3 | 27.5 | 5945.7
CE - Cost & Funding | 1901.9 | 4016.3 | 27.5 | 5945.7

## Table 28
Summary BY 2013 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 1860 | 3846.9 | 28.8 | 5735.7
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -145.4 | -103.2 | -0.2 | -248.8
Other | -- | -- | -- | --
Support | -- | -483.9 | -- | -483.9
Subtotal | -145.4 | -587.1 | -0.2 | -732.7
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | 155.5 | -- | -- | 155.5
Estimating | -20.7 | -4.8 | -- | -25.5
Other | -- | -- | -- | --
Support | -- | -0.9 | -- | -0.9
Subtotal | 134.8 | -5.7 | -- | 129.1
Total Changes | -10.6 | -592.8 | -0.2 | -603.6
CE - Cost Variance | 1849.4 | 3254.1 | 28.6 | 5132.1
CE - Cost & Funding | 1849.4 | 3254.1 | 28.6 | 5132.1
Previous Estimate: December 2014

## Table 29
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -5.3
Funding increase to support long lead hardware procurement for unmanned Self-Defense Test Ship at-sea testing in support of the Guided Missile Destroyer (DDG) 51 Flight III and Aegis Advanced Capability Build (ACB) 20 requirements (Engineering)
Revised estimate to align funding to POE and to reflect implementation of cost reduction initiatives (Estimating)
+155.5 +175.0
-23.8 -25.9
Adjustment for current and prior escalation. (Estimating) | 3.1 | 3.2
RDT&E Subtotal | 134.8 | 147
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 7.1
Adjustment for current and prior escalation. (Estimating) | -0.5 | -0.4
Revised estimate to align funding to POE (Estimating) | -4.3 | -5.8
Adjustment for current and prior escalation. (Support) | 0 | -0.2
Decrease in Other Support. (Support) | -0.8 | -0.7
Decrease in Initial Spares. (Support) | -0.1 | 0
Procurement Subtotal | -5.7 | 0

## Table 30
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: AMDR Engineering and Manufacturing Development
Contractor: Raytheon Company
Contractor Location: 528 Boston Post Road
Sudbury, MA 01776
Contract Number: N00024-14-C-5315
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: October 10, 2013
Definitization Date: October 10, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
385.7 N/A 0 388.5 N/A 0 422.2 436.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a Request for Equitable Adjustment (REA) contract modification that addressed the delay due to a bid protest. The bid protest was subsequently withdrawn.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -45.1 -6.3
Previous Cumulative Variances -9.2 -2.9
Net Change -35.9 -3.4
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to design issues with the Digital Receiver/Exciters, but is also impacted by complexities due to ship fit issues with the mechanical structure. In order to maintain schedule, Raytheon and subcontractor General Dynamics have both provided additional Systems Engineering and Program Management Support on site at the subcontractor’s facility. The majority of this cost variance is not expected to be recovered.
The unfavorable net change in the schedule variance is due to design issues with the digital receivers/exciters resulting in a significantly late delivery to the near field range. Raytheon took several actions to mitigate this schedule slip as much as possible but this still caused a delay in the start of the array test for Developmental Test-2. There remains a schedule margin of about a month for the delivery of the array to Pacific Missile Range Facility and the majority of this schedule variance is expected to recover by April 2016.
EVM data based on Integrated Program Management Report delivered by Raytheon on January 21, 2016 and reflects data through December 31, 2015.

## Table 31
Notes
The difference between the current contract price and the current Estimate at Completion is due to cost growth described in the "Cost and Schedule Variance Explanations" section and adding a requirement for procurement, installation, and test of diesel generators to be used at the Advanced Radar Detection Laboratory for radar developmental testing.

## Table 32
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 22 | 0%
Total Program Quantity Delivered | 0 | 0 | 22 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
5945.7
1181
19.86%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
11
52.38%
1695.1
28.51%
The above data is current as of February 09, 2016.

## Table 33
Operating and Support Cost
Cost Estimate Details
Date of Estimate: May 29, 2013
Source of Estimate: CAPE ICE
Quantity to Sustain: 22
Unit of Measure: System
Service Life per Unit: 40.00 Years
Fiscal Years in Service: FY 2021 - FY 2070
Each AMDR System includes four fully populated AMDR-S array faces and a Radar Suite Controller (RSC).
Sustainment Strategy
In order to meet Operational Availability (Ao) KPP and O&S Cost Key System Attribute requirements AMDR will implement a performance-based product support strategy involving Naval Surface Warfare Center Crane Division, NSWC Port Hueneme Division, and NSWC Dahlgren Division, Defense Logistics Agency, Naval Supply Systems Command, and Center for Surface Combat Systems Dahlgren.
The AMDR system employs a two level maintenance philosophy (organizational to depot) with onboard maintenance performed by the ship’s crew. The ship’s operational tempo is assumed to be 180 days on station. Maintenance (preventative and corrective) can occur anytime during the 180 days on station as long as the system is not degraded by the maintenance activity. Commercial Off The Shelf (COTS) processing equipment refresh and upgrades will be implemented using a 'refresh by attrition' approach combined with an eight year refresh cycle. The planned software sustainment strategy for AMDR includes post-delivery routine software maintenance and software updates every two years to address new threats and other emergent capability requirements.
Antecedent Information
The antecedent system is AN/SPY-1D(V). AN/SPY-1D(V) has fielded 32 systems, each with a planned service life of 35 years. The source of the cost estimate is the Naval Sea Systems Command Systems Engineering Directorate - Cost Engineering and Industrial Analysis Division AN/SPY-1D(V) Full Rate Production ICE dated November 14, 2011. The AN/SPY-1D(V) Sustaining Support cost element does not include costs for Operating Equipment Replacement, whereas AMDR does.

## Table 34
Annual O&S Costs BY2013 $M
Cost Element |  | AMDR Average Annual Cost Per System | [5 empty] | AN/SPY-1D(V) (Antecedent) Average Annual Cost Per System
Unit-Level Manpower |  | -- | [5 empty] | 0.192
Unit Operations |  | -- | [5 empty] | --
Maintenance |  | 1.177 | [5 empty] | 2.047
Sustaining Support |  | 2.722 | [5 empty] | 1.047
Continuing System Improvements |  | 0.852 | [5 empty] | 0.204
Indirect Support |  | -- | [5 empty] | 0.086
Other |  | -- | [5 empty] | --
Total |  | 4.751 | [5 empty] | 3.576
Costs above reflect average annual cost per system. For AMDR, Unit-Level Manpower, Unit Operations, and Indirect Support are not reported because they are considered Ship Level Costs. The antecedent column for AN/SPY-1D(V) includes Unit Level Manpower and Indirect Support costs since manpower costs were included in the AN/SPY-1D(V) cost estimate, while for AMDR these costs were captured in the DDG 51 costs.
Item | Total O&S Cost $M
| AMDR | [7 empty] | AN/SPY-1D(V) (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 4181.3 |  |  | 4599.4 |  |  | 4181.3 |  | 4005.6
Then Year | 7857.3 |  |  | N/A |  |  | 7857.3 |  | N/A
Objective O&S costs include System Operations and Maintenance, Navy (OMN) (TY $6,415.1M, BY 2013 $3,385.7M) and Fleet OMN (TY $1,442.1M, BY 2013 $795.6M).
Equation to Translate Annual Cost to Total Cost
Total System O&S [BY 2013 $4,181.3M] = unitized cost [BY 2013 $4.751M] * number of systems [22] * service life per system [40].
O&S Cost Variance
Category |  |  | BY 2013 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
4181.3
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0

## Table 35
Current Estimate 4181.3
Disposal Estimate Details
Date of Estimate: May 29, 2013
Source of Estimate: CAPE ICE
Disposal/Demilitarization Total Cost (BY 2013 $M): Total costs for disposal of all System are 30.2
.