## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-390
CH-53K Heavy Lift Replacement Helicopter (CH-53K)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 23
Foreign Military Sales 24
Nuclear Costs 24
Unit Cost 25
Cost Variance 28
Contracts 31
Deliveries and Expenditures 35
Operating and Support Cost 36

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
CH-53K Heavy Lift Replacement Helicopter (CH-53K)
DoD Component
Navy
Responsible Office
Col Henry Vanderborght
PMA-261 Heavy Lift Helicopters
Program Executive Office - Air, Anti-Submarine Warfare, Assault & Special Mission Programs
22595 Saufley Road, Bldg. 3259 Patuxent River, MD 20670-1547
hank.vanderborght@navy.mil
Phone: 301-757-5780
Fax: 301-757-5109
DSN Phone: 757-5780
DSN Fax: 757-5109
Date Assigned: May 29, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 22, 2005
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 24, 2013

## Table 6
Mission and Description
The CH-53K Heavy Lift Replacement Helicopter (CH-53K) program mission is to generate and support a robust United States Marine Corps heavy-lift capability. The primary mission is vertical heavy lift. The Program includes improvements in lift and range capabilities, commonality, reliability, maintainability, interoperability, ship integration, survivability, and force protection. The CH-53K helicopter will be a replacement for the CH-53E.

## Table 7
Executive Summary
The CH-53K Program has breached the APB for Milestone C. A Program Deviation Report was submitted to the MDA and accepted in August 2015. As a result of the breach, an Exception SAR was completed in September 2015.
First Flight was executed on Engineering Development Model (EDM) October 27, 2015 which commenced the CH-53K Systems Development and Demonstration Test Program. Currently two of the four required test EDMs are in a test flight status.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
The program has breached the APB for Milestone C as a result of discoveries during test on the Ground Test Vehicle and qualification testing. The discoveries have driven component re-designs, re- qualifications, and re-test, thereby delaying First Flight and subsequent milestones. The Program Deviation Report was accepted by the MDA in August 2015.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
(Ch-1)
(Ch-1)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B DAB Review | Oct 2005 | Dec 2005 | Dec 2005 | Dec 2005
CDR | Mar 2009 | Jul 2010 | Jul 2010 | Jul 2010
MDA Design Readiness Review | Apr 2009 | N/A | N/A | Jun 2011
Milestone C | Dec 2012 | Feb 2016 | Aug 2016 | Feb 20171
TECHEVAL Complete | Oct 2014 | Feb 2018 | Aug 2018 | Jan 20191
IOT&E (OPEVAL) Complete | Jun 2015 | Sep 2018 | Mar 2019 | Aug 20191
IOC | Sep 2015 | Jan 2019 | Jul 2019 | Dec 20191
FRP Decision Review | Dec 2015 | Sep 2019 | Mar 2020 | Mar 2020
1 APB Breach
Change Explanations
(Ch-1) The following milestones dates for TECHEVAL Complete, IOT&E (OPEVAL) Complete and IOC have changed from August 2018, March 2019, July 2019 to January 2019, August 2019 and December 2019 respectively. This is a result of discoveries during test on the Ground Test Vehicle and qualification testing. The discoveries have driven component re- designs, re-qualifications, and re-test, thereby delaying First Flight and subsequent milestones. The Program is awaiting direction from the MDA for an APB rebaseline.

## Table 10
Acronyms and Abbreviations
CDR - Critical Design Review
IOT&E - Initial Operational Test and Evaluation. Used interchangeably with Operational Evaluation (OPEVAL). OPEVAL - Operational Evaluation. Used interchangeably with Initial Operational Test and Evaluation (IOT&E). PDR - Program Deviation Report
SDD - Systems Design and Demonstration TECHEVAL - Technical Evaluation

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net Ready (NR)
Satisfy 100% of NR reqts in Joint Integrated Architecture (JIA) | Satisfy 100% of NR reqts in JIA | Satisfy 100% of NR reqts designated as enterprise- level or critical in JIA | TBD | Satisfy 100% of NR reqts in JIA
Range and Payload (nm)
110 w/30,000 lbs external load, no refuel | 110 w/30,000 lbs external load, no refuel | 110 w/27,000 lbs external load, no refuel | TBD | 110 w/27,000 lbs external load, no refuel
Mission Reliability (MR)
90% | 90% | 89% | TBD | 89%
Logistics Footprint
10% reduction from current CH-53E | 10% reduction from current CH- 53E | <= current CH-53E | TBD | <= current CH- 53E
Sortie Generation Rate (SGR)/Average Sortie Duration (ASD)
2.6 sorties/ 2.25 hrs | 2.6 sorties/ 2.25 hrs | 2.6 sorties/ 2.25 hrs | TBD | 2.6 sorties/ 2.25 hrs
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Operational Requirements Document (ORD) Change 4 dated July 15, 2010
Change Explanations
None
Notes
Net Ready KPP: JVMF, Link-16, and Mode 5 capabilities were approved for deferral by JROCM 142-10 of September 10, 2010 until IOC + 6 months for Mode 5 and IOC + 2 years for JVMF and Link-16.

## Table 12
Acronyms and Abbreviations
<= - Less Than or Equal To hrs - Hours
JROCM - Joint Requirements Oversight Council Memorandum JVMF - Joint Variable Message Format
lbs - Pounds
nm - Nautical Miles reqts - Requirements

## Table 13
Track to Budget
RDT&E
Appn |  | BA | PE
Navy 1319 05 0605212N
Project | Name
3059 CH-53K Development
Procurement
Appn |  | BA | PE
Navy 1506 01 0206122M
Line Item Name
0158 CH-53K (Heavy Lift) Navy 1506 06 0206122M
Line Item Name
0605 Spares and Repair Parts
MILCON
Appn |  | BA | PE
Navy 1205 01 0202176M
Project | Name
VARIOUS VARIOUS

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2006 $M | [6 empty] | BY 2006 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 3962 |  |  | 5535.9 | 6089.5 |  |  | 5786.6 |  | 4366.4 |  |  | 6273.7 |  | 6598.3
Procurement |  | 11018.9 |  |  | 16118.3 | 17730 |  |  | 16077.6 |  | 14399.9 |  |  | 22178.8 |  | 22563.4
Flyaway |  | -- |  |  | -- | -- |  |  | 13819.4 |  | -- |  |  | -- |  | 19441.6
Recurring |  | -- |  |  | -- | -- |  |  | 13394 |  | -- |  |  | -- |  | 18851.3
Non Recurring |  | -- |  |  | -- | -- |  |  | 425.4 |  | -- |  |  | -- |  | 590.3
Support |  | -- |  |  | -- | -- |  |  | 2258.2 |  | -- |  |  | -- |  | 3121.8
Other Support |  | -- |  |  | -- | -- |  |  | 1751.9 |  | -- |  |  | -- |  | 2423.9
Initial Spares |  | -- |  |  | -- | -- |  |  | 506.3 |  | -- |  |  | -- |  | 697.9
MILCON |  | 0 |  |  | 39.6 | 43.6 |  |  | 35.1 |  | 0 |  |  | 48.1 |  | 44.4
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 14980.9 |  |  | 21693.8 | N/A |  |  | 21899.3 |  | 18766.3 |  |  | 28500.6 |  | 29206.1
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The cost estimate recommendation aims to provide sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule, and programmatic risk and external interference. It is consistent with average resource expenditures on historical efforts of similar size, scope, and complexity.
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 4 |  |  |  | 4 |  |  |  |  | 6
Procurement |  |  | 152 |  |  |  | 196 |  |  |  |  | 194
Total |  |  | 156 |  |  |  | 200 |  |  |  |  | 200

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 4818.6 | 592.3 |  | 404.8 |  | 233.9 | 175.7 |  | 184.6 |  | 188.4 |  |  | 0 |  | 6598.3
Procurement | 0 | 41.3 |  | 488 |  | 754 | 1222.1 |  | 1751.5 |  | 1807.4 |  |  | 16499.1 |  | 22563.4
MILCON | 13.2 | 3.3 |  | 0 |  | 0 | 27.9 |  | 0 |  | 0 |  |  | 0 |  | 44.4
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 4831.8 | 636.9 |  | 892.8 |  | 987.9 | 1425.7 |  | 1936.1 |  | 1995.8 |  |  | 16499.1 |  | 29206.1
PB 2016 Total | 4853.3 | 673.4 |  | 947.5 |  | 937.7 | 1407.6 |  | 1902.7 |  | 1949.3 |  |  | 16432.4 |  | 29103.9
Delta | -21.5 | -36.5 |  | -54.7 |  | 50.2 | 18.1 |  | 33.4 |  | 46.5 |  |  | 66.7 |  | 102.2
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 6 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 6
Production | 0 |  | 0 |  | 0 | 2 | 4 |  | 7 |  | 13 | 14 |  | 154 |  | 194
PB 2017 Total | 6 |  | 0 |  | 0 | 2 | 4 |  | 7 |  | 13 | 14 |  | 154 |  | 200
PB 2016 Total | 6 |  | 0 |  | 0 | 2 | 4 |  | 7 |  | 13 | 14 |  | 154 |  | 200
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 252
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 338.1
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 386.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 543.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 503.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 558.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 606.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 535.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 447.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 538.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 592.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 404.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 233.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 175.7
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 184.6
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 188.4
Subtotal |  | 6 | -- |  | -- |  | -- |  | -- |  | -- |  | 6598.3

## Table 17
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2006 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100.5
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 247.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 323.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 363.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 505.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 461.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 498.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 533.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 466.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 384
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 456
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 493.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 331.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 187.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 142.5
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 142.6
Subtotal |  | 6 | -- |  | -- |  | -- |  | -- |  | -- |  | 5786.6

## Table 18
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | 41.3 |  | -- |  | -- |  | 41.3 |  | -- |  | 41.3
2017 |  | 2 | 299.1 |  | -- |  | 1.7 |  | 300.8 |  | 187.2 |  | 488
2018 |  | 4 | 528.5 |  | -- |  | 12.8 |  | 541.3 |  | 212.7 |  | 754
2019 |  | 7 | 891.2 |  | -- |  | 73.2 |  | 964.4 |  | 257.7 |  | 1222.1
2020 |  | 13 | 1324.5 |  | -- |  | 75.6 |  | 1400.1 |  | 351.4 |  | 1751.5
2021 |  | 14 | 1452 |  | -- |  | 101.3 |  | 1553.3 |  | 254.1 |  | 1807.4
2022 |  | 21 | 2078.9 |  | -- |  | 87.9 |  | 2166.8 |  | 264.1 |  | 2430.9
2023 |  | 24 | 2226.1 |  | -- |  | 20.8 |  | 2246.9 |  | 298.6 |  | 2545.5
2024 |  | 24 | 2242.5 |  | -- |  | 20.5 |  | 2263 |  | 281.4 |  | 2544.4
2025 |  | 24 | 2270.2 |  | -- |  | 20.4 |  | 2290.6 |  | 263.5 |  | 2554.1
2026 |  | 24 | 2315.6 |  | -- |  | 49.6 |  | 2365.2 |  | 252 |  | 2617.2
2027 |  | 24 | 2120.2 |  | -- |  | 50.3 |  | 2170.5 |  | 218 |  | 2388.5
2028 |  | 13 | 1061.2 |  | -- |  | 76.2 |  | 1137.4 |  | 154.8 |  | 1292.2
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | 63.8 |  | 63.8
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | 62.5 |  | 62.5
Subtotal |  | 194 | 18851.3 |  | -- |  | 590.3 |  | 19441.6 |  | 3121.8 |  | 22563.4

## Table 19
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2006 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | 34 |  | -- |  | -- |  | 34 |  | -- |  | 34
2017 |  | 2 | 241.5 |  | -- |  | 1.4 |  | 242.9 |  | 151.1 |  | 394
2018 |  | 4 | 418.4 |  | -- |  | 10.1 |  | 428.5 |  | 168.5 |  | 597
2019 |  | 7 | 691.8 |  | -- |  | 56.8 |  | 748.6 |  | 200 |  | 948.6
2020 |  | 13 | 1007.9 |  | -- |  | 57.5 |  | 1065.4 |  | 267.5 |  | 1332.9
2021 |  | 14 | 1083.3 |  | -- |  | 75.6 |  | 1158.9 |  | 189.6 |  | 1348.5
2022 |  | 21 | 1520.6 |  | -- |  | 64.3 |  | 1584.9 |  | 193.2 |  | 1778.1
2023 |  | 24 | 1596.4 |  | -- |  | 14.9 |  | 1611.3 |  | 214.1 |  | 1825.4
2024 |  | 24 | 1576.6 |  | -- |  | 14.4 |  | 1591 |  | 197.8 |  | 1788.8
2025 |  | 24 | 1564.8 |  | -- |  | 14.1 |  | 1578.9 |  | 181.5 |  | 1760.4
2026 |  | 24 | 1564.8 |  | -- |  | 33.5 |  | 1598.3 |  | 170.3 |  | 1768.6
2027 |  | 24 | 1404.6 |  | -- |  | 33.3 |  | 1437.9 |  | 144.5 |  | 1582.4
2028 |  | 13 | 689.3 |  | -- |  | 49.5 |  | 738.8 |  | 100.5 |  | 839.3
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | 40.6 |  | 40.6
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | 39 |  | 39
Subtotal |  | 194 | 13394 |  | -- |  | 425.4 |  | 13819.4 |  | 2258.2 |  | 16077.6

## Table 20
Cost Quantity Information 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2006 $M
2016 | -- | --
2017 | 2 | 204.1
2018 | 4 | 373.7
2019 | 7 | 596.6
2020 | 13 | 994.5
2021 | 14 | 1026.7
2022 | 21 | 1447.9
2023 | 24 | 1597.7
2024 | 24 | 1577
2025 | 24 | 1563.7
2026 | 24 | 1563.4
2027 | 24 | 1564.9
2028 | 13 | 883.8
2029 | -- | --
2030 | -- | --
Subtotal | 194 | 13394

## Table 21
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2014 13.2
2015 --
2016 3.3
2017 --
2018 --
2019 27.9
Subtotal 44.4

## Table 22
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2006 $M
Total Program
2014 11.1
2015 --
2016 2.7
2017 --
2018 --
2019 21.3
Subtotal 35.1

## Table 23
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2005-11-22 | 2014-02-05
Approved Quantity | 29 | 29
Reference | Milestone B Acquisition Strategy (AS) | Milestone B AS Revision 2
Start Year | 2012 | 2017
End Year | 2015 | 2020
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the need to plan for an efficient production ramp-up.
The current total LRIP-approved quantity value has been updated to reflect the initial LRIP decision approved quantity of 29 which has not changed since 2006. The CH-53K currently has 26 LRIP aircraft within the FY 2017 PB. LRIP is expected to begin in 2017.

## Table 24
Foreign Military Sales
None
Nuclear Costs
None

## Table 25
Unit Cost
Unit Cost Report
Item |  | BY 2006 $M | BY 2006 $M |  | % Change
|  | Current UCR Baseline (Apr 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 21693.8 |  |  | 21899.3
Quantity | 200 |  |  | 200
Unit Cost | 108.469 |  |  | 109.496 |  | 0.95
Average Procurement Unit Cost
Cost | 16118.3 |  |  | 16077.6
Quantity | 196 |  |  | 194
Unit Cost | 82.236 |  |  | 82.874 |  | 0.78
Item |  | BY 2006 $M | BY 2006 $M |  | % Change
|  | Original UCR Baseline (Dec 2005 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 14980.9 |  |  | 21899.3
Quantity | 156 |  |  | 200
Unit Cost | 96.031 |  |  | 109.496 |  | 14.02
Average Procurement Unit Cost
Cost | 11018.9 |  |  | 16077.6
Quantity | 152 |  |  | 194
Unit Cost | 72.493 |  |  | 82.874 |  | 14.32

## Table 26
Unit Cost History
Item |  |  |  |  | Date |  |  |  | BY 2006 $M | [5 empty] | TY $M
[9 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Dec 2005 | [5 empty] | 96.031 |  |  | 72.493 |  |  |  | 120.297 |  |  | 94.736
APB as of January 2006 |  |  | Dec 2005 | [5 empty] | 96.031 |  |  | 72.493 |  |  |  | 120.297 |  |  | 94.736
Revised Original APB |  |  | N/A | [5 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  | Dec 2005 | [5 empty] | 96.031 |  |  | 72.493 |  |  |  | 120.297 |  |  | 94.736
Current APB |  |  | Apr 2013 | [5 empty] | 108.469 |  |  | 82.236 |  |  |  | 142.503 |  |  | 113.157
Prior Annual SAR |  |  | Dec 2014 | [5 empty] | 108.398 |  |  | 82.311 |  |  |  | 145.52 |  |  | 116.483
Current Estimate |  |  | Dec 2015 | [5 empty] | 109.496 |  |  | 82.874 |  |  |  | 146.03 |  |  | 116.306
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [15 empty] | PAUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est | Oth |  |  | Spt | Total
120.297 -2.004 -10.579 16.312 0.140 20.460 0.000 1.404 25.733 146.030
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [15 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
94.736 -1.903 -5.411 12.062 0.000 15.710 0.000 1.112 21.570 116.306

## Table 27
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Oct 2005 | N/A | Dec 2005
Milestone C | N/A | Dec 2012 | N/A | Feb 2017
IOC | N/A | Sep 2015 | N/A | Dec 2019
Total Cost (TY $M) | N/A | 18766.3 | N/A | 29206.1
Total Quantity | N/A | 156 | N/A | 200
PAUC | N/A | 120.297 | N/A | 146.03

## Table 28
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
4366.4 14399.9 -- 18766.3
Economic |  | -14.8 |  | -178.2 |  | -0.5 |  | -193.5
Quantity |  | 248 |  | 2929.1 |  | -- |  | 3177.1
Schedule |  | 806 |  | 2340 |  | -- |  | 3146
Engineering |  | -- |  | -- |  | 28.1 |  | 28.1
Estimating |  | 1017.5 |  | 2905.2 |  | -9.4 |  | 3913.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | 64.9 |  | 201.7 |  | -- |  | 266.6
Subtotal |  | 2121.6 |  | 8197.8 |  | 18.2 |  | 10337.6
Current Changes Economic |  | -16.2 |  | -190.9 |  | -0.1 |  | -207.2
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | 116.5 |  | -- |  | -- |  | 116.5
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 10 |  | 142.5 |  | 26.3 |  | 178.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 14.1 |  | -- |  | 14.1
Subtotal |  | 110.3 |  | -34.3 |  | 26.2 |  | 102.2
Total Changes |  | 2231.9 |  | 8163.5 |  | 44.4 |  | 10439.8
CE - Cost Variance |  | 6598.3 |  | 22563.4 |  | 44.4 |  | 29206.1
CE - Cost & Funding |  | 6598.3 |  | 22563.4 |  | 44.4 |  | 29206.1

## Table 29
Summary BY 2006 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
3962.0 11018.9 -- 14980.9
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | 201.7 |  | 2209.9 |  | -- |  | 2411.6
Schedule |  | 603.9 |  | 591.9 |  | -- |  | 1195.8
Engineering |  | -- |  | -- |  | 21.5 |  | 21.5
Estimating |  | 875.3 |  | 2165.6 |  | -6.7 |  | 3034.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | 53.6 |  | -17.9 |  | -- |  | 35.7
Subtotal |  | 1734.5 |  | 4949.5 |  | 14.8 |  | 6698.8
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | 81.7 |  | -- |  | -- |  | 81.7
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 8.4 |  | 100.9 |  | 20.3 |  | 129.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 8.3 |  | -- |  | 8.3
Subtotal |  | 90.1 |  | 109.2 |  | 20.3 |  | 219.6
Total Changes |  | 1824.6 |  | 5058.7 |  | 35.1 |  | 6918.4
CE - Cost Variance |  | 5786.6 |  | 16077.6 |  | 35.1 |  | 21899.3
CE - Cost & Funding |  | 5786.6 |  | 16077.6 |  | 35.1 |  | 21899.3
Previous Estimate: September 2015

## Table 30
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -16.2
Adjustment for current and prior escalation. (Estimating) +8.4 +10.0
Stretch-out of development effort between FY 2015 and FY 2020 due to Contractor schedule delays. (Schedule)
+81.7 +116.5
RDT&E Subtotal +90.1 +110.3
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -190.9
Adjustment for current and prior escalation. (Estimating) | 0.3 | 0.4
Revised estimate to reflect the application of new outyear inflation indices. (Estimating) | 100.6 | 142.1
Increase in Other Support due to refined cost estimate. (Support) | 1.8 | 11.1
Increase in Initial Spares due to funding realignment beginning in FY 2017. (Support) | 6.5 | 3
Procurement Subtotal | 109.2 | -34.3
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.1
Increase due to refined cost estimate. (Estimating) | 20.2 | 26.2
Adjustment for current and prior escalation. (Estimating) | 0.1 | 0.1
MILCON Subtotal | 20.3 | 26.2

## Table 31
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: System Development and Demonstration
Contractor: Sikorsky Aircraft Corporation
Contractor Location: 6900 Main Street
Stratford, CT 06615-9129
Contract Number: N00019-06-C-0081
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: January 03, 2006
Definitization Date: January 03, 2006
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
3052.2 N/A 5 3012.3 N/A 5 4002.7 4185.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a reduction in target fee associated with contract type conversion from Cost Plus Award Fee to Cost Plus Incentive Fee and scope adjustments. Program Manager's Estimated Price is equal to the current Estimate at Completion plus scope changes, profit and fee.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -189.3 -117.6
Previous Cumulative Variances -175.6 -122.0
Net Change -13.7 +4.4
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to Test & Evaluation for Gearbox Engineering Support for Engineering Design Model (EDM) 1 First Flight and for Ground Test Vehicle (GTV) Op-tempo delays, as well as preparations in support of EDM3 First Flight; to include, final special inspection and aircraft ground run activities and support for test conduct. Support of GTV activities during remaining envelope expansion/Preliminary Flight Acceptance Testing and Dynamics added to the unfavorable net cost variance due to overruns on the Main Rotor Blades for EDM2 and EDM4.
The favorable net change in the schedule variance is due to the receipt of late parts within the Supportability IPT, as well as final acceptance of supplier data in support of maintenance plan development, receipt of materials to build up dynamic component spares and receipt of materials to fabricate the maintenance training device main rotor head.

## Table 32
Notes
The definitization date above reflects the definitization of the Interim System Development and Demonstration (iSDD) contract for $7.63M. On April 5, 2006 the System Development and Demonstration (SDD) contract was signed for the negotiated cost of $2.73B.
Initial Contract Price Quantity was updated to correct previous submissions. The iSDD contract had a quantity of 0. This quantity was later negotiated to 5 when the full SDD contract was initialized.
Initial quantity has been updated to reflect the number of aircraft procured.

## Table 33
Contract Identification
Appropriation: RDT&E
Contract Name: System Demonstration Test Articles
Contractor: Sikorsky Aircraft Corporation
Contractor Location: 6900 Main Street
Stratford, CT 06614
Contract Number: N00019-06-C-0081/2 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: May 30, 2013
Definitization Date: May 30, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
435.3 N/A 4 477.8 N/A 4 486.9 485.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to increase in scope to the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +3.4 -55.7
Previous Cumulative Variances +3.9 -40.9
Net Change -0.5 -14.8
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to the higher part cost of transmission shafts assemblies than originally planned by the Transmissions & Drives Integrated Product Team.
The unfavorable net change in the schedule variance is due to Final Assembly delays associated with Advanced Change Notices (ACNs) as well as late part deliveries and/or late starts of Air Vehicle and Dynamics components.
Notes
Program Manager's estimates provided for this submission reflect the November 2015 Estimate At Completion. Program Manager's estimated price is equal to the current estimate plus scope changes, profit and fee.
In addition, critical parts for System Demonstration Test Articles 5&6 were added to the contract.

## Table 34
Contract Identification
Appropriation: RDT&E
Contract Name: SDTA Engines
Contractor: General Electric
Contractor Location: 1000 Western Avenue
Lynn, MA 01905
Contract Number: N00013-13-C-0132/3
Contract Type: Firm Fixed Price (FFP)
Award Date: July 18, 2013
Definitization Date: July 31, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
15.7 N/A 0 114.2 N/A 22 114.2 114.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to exercising options to procure engines.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
Initial contract target price of $15.7M was awarded on July 18, 2013 for critical parts, systems engineering, and program management related to engine procurement. On July 31, 2014, the Government added FFP CLINs to procure 16 engines and the associated technical data and tooling. On July 15, 2015, the Government exercised an option to procure an additional six engines. PM's estimated price is equal to the current estimate plus scope changes, profit, and fee.
An administrative change to Initial contract quantity has been changed from the previous SAR to reflect zero quantities associated with the initial award for critical parts, systems engineering, and program Management.

## Table 35
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 6 | 0%
Production | 0 | 0 | 194 | 0%
Total Program Quantity Delivered | 0 | 0 | 200 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
29206.1
4457.4
15.26%
29
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
15
51.72%
5468.7
18.72%
The above data is current as of February 09, 2016.

## Table 36
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 08, 2016
Source of Estimate: POE
Quantity to Sustain: 200
Unit of Measure: Aircraft
Service Life per Unit: 30.00 Years
Fiscal Years in Service: FY 2017 - FY 2059
- Aircraft Attrition Rate: 0.5% of Total Aircraft Inventory (TAI) per year.
- Aircraft Pipeline Factor: 15.5% of TAI.
- Squadrons: 10 Marine Heavy Helicopter (HMH) squadrons (8 active / 1 reserve) / 1 Marine Training (HMHT) squadron.
- Helicopters per HMH (active) squadron: 16.
- Helicopters per HMH (reserve) squadron: 16.
- Helicopters per HMHT squadron: 21.
- Monthly Flight Hours per Helicopter (TAI): 17.9.
- Aircraft reliability projections per NAVAIR-4.1.10 input.
- Total Operating Helicopter Years: 5,035.
Sustainment Strategy
The CH-53K will be sustained utilizing Organizational, Intermediate, and Depot levels of maintenance. Repair and Overhaul capability establishment will be phased in over five years and will be based on component maturity, operational readiness and affordability factors. Product Support analyses are being matured and will be compared to data obtained during flight test and initial operations to establish sustainment baselines at the component level. A Fleet Common Operating Environment (FCOE) has been established to fuse information from operations and sustainment activities across the Naval Aviation Enterprise and provide near real-time comparisons of actual environmental, reliability, cost and sustainment infrastructure performance against the established baselines. Current sustainment planning activities are facilitating engagement with both public and private industrial support services in the development of performance-based product support arrangements as well as utilizing the FCOE to enable more agile and effective product support packages during CH-53K sustainment operations.
Antecedent Information
- The antecedent system is CH-53E.
- Antecedent CH-53E data representative of FY 2012 to FY 2014 average of Naval Visibility And Management of Operating and Support Cost (VAMOSC) reported cost data.
- CH-53E is not capable of meeting Joint Requirements Oversight Council Key Performance Parameter requirements established for the CH-53K (CH-53K provides three times the lift capability compared to CH-53E).
- CH-53E Total O&S Cost (Base Year 2006$) = CH-53E Annual O&S Cost per Helicopter * CH-53K Total Operating Helicopter Years. As historical data is unavailable for all years of the Antecedent System's life cycle, the calculation is supplemented with CH-53K data.

## Table 37
Annual O&S Costs BY2006 $M
Cost Element |  | CH-53K Average Annual Cost Per Aircraft | [5 empty] | CH-53E (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  | 1.215 | [5 empty] | 1.324
Unit Operations |  | 0.407 | [5 empty] | 0.294
Maintenance |  | 4.486 | [5 empty] | 3.148
Sustaining Support |  | 0.24 | [5 empty] | 0.103
Continuing System Improvements |  | 0.576 | [5 empty] | 0.517
Indirect Support |  | 0.469 | [5 empty] | 0.606
Other |  | 0 | [5 empty] | 0
Total |  | 7.393 | [5 empty] | 5.992
Item | Total O&S Cost $M
| CH-53K | [7 empty] | CH-53E (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 37520.3 |  |  | 41272.3 |  |  | 37224.7 |  | 30173.3
Then Year | 78156.7 |  |  | N/A |  |  | 75255.4 |  | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
- CH-53K Average Annual Cost per Helicopter = Total O&S Cost (Base Year) / Total Operating Helicopter Years.
- $37,224.7M / 5,035 Total Operating Helicopter Years = $7.393M per Year per Helicopter.
O&S Cost Variance
Category |  |  | BY 2006 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Sep 2015 SAR
37221.6
Programmatic/Planning Factors -74.1 FY 2017 PB Flight Hours for FYDP
Cost Estimating Methodology -901.4 Full Lifecycle engineering approach for Aviation Depot Level Repairable (AVDLR)
Cost Data Update 732.8 Updated VAMOSC data and FY 2016 inflation rates
Labor Rate 56.8 2016 Military Composite Pay Rates
Energy Rate -82.9 Fuel pricing per guidance
Technical Input 271.9 Updated Training Device refresh Other 0.0
Total Changes 3.1
Current Estimate 37224.7
The updated estimate is <1% increase from the 2014 SAR O&S estimate, from $37,221.6 to $37,224.7 (BY2006$M). O&S Cost decrease is due to updated methodology, rates, and FY 2017 PB flight hours.

## Table 38
Disposal Estimate Details
Date of Estimate: January 30, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2006 $M): Total costs for disposal of all Aircraft are 23.9
Estimate to be refined at Milestone C based on the System Disposal Plan Annex to the Life Cycle Sustainment Plan.