## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-223
CVN 78 Gerald R. Ford Class Nuclear Aircraft Carrier (CVN 78)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 11
Performance 15
Track to Budget 18
Cost and Funding 21
Low Rate Initial Production 46
Foreign Military Sales 47
Nuclear Costs 48
Unit Cost 49
Cost Variance 55
Contracts 62
Deliveries and Expenditures 67
Operating and Support Cost 68

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
CVN 78 Gerald R. Ford Class Nuclear Aircraft Carrier (CVN 78)
DoD Component
Navy
Responsible Office
CAPT Chris Meyer
Program Executive Office (PEO) Aircraft Carriers PMS 378
614 Sicard Street SE Stop 7007
Washington, DC 20376-7007
chris.meyer@navy.mil
Phone: | 202-781-3969
Fax: | 202-781-4684
DSN Phone: | 326-3969
DSN Fax: | 326-4684
Date Assigned: | June 9, 2011
References
CVN 78
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 23, 2004
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 2, 2013
EMALS
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 23, 2004
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 2, 2013

## Table 6
Mission and Description
The CVN 78 Gerald R. Ford Class Nuclear Aircraft Carrier (CVN 78) is the planned successor to the NIMITZ-class (CVN 68) aircraft carrier. The CVN 78 mission is to provide credible, sustainable, independent forward presence during peacetime without access to land bases; operate as the cornerstone of a joint and/or allied maritime expeditionary force in response to crisis; and carry the war to the enemy through joint multi-mission offensive operations by: (a) being able to operate and support aircraft in attacks on enemy forces ashore, afloat, or submerged independent of forward-based land facilities, (b) protecting friendly forces from enemy attack through the establishment and maintenance of battle space dominance independent of forward-based land facilities, and (c) engaging in sustained operations in support of the United States and its allies independent of forward-based land facilities.
The CVN 78 Class Aircraft Carrier program includes major efforts for Nuclear Propulsion/Electric Plant
Design, Electromagnetic Aircraft Launching System (EMALS) and all electric auxiliary systems. Additional design features and new technologies have been added, including a new/enlarged flight deck, improved weapons handling capabilities, and improved survivability.

## Table 7
Executive Summary
As of February 2016, the CVN 78 Class design is complete and on the lead ship, GERALD R. FORD (CVN 78), production is 97% complete. The Navy and shipbuilder are focused on activity necessary to finish construction, complete the test program, and deliver the ship. During this past year, the Initial Light Off of Dual Band Radar (DBR) began in May 2015.
Electromagnetic Aircraft Launching System (EMALS) shipboard catapult testing commenced on schedule in June 2015 and has completed 109 dead-load launches on the two bow catapults. The Advanced Arresting Gear (AAG) shipboard test program commenced July 18, 2015. The crew moved aboard as scheduled in August 2015. As of February 1, 2016, the shipbuilder has turned over 93% of compartments to the crew, and 80% of the overall shipboard testing has been completed.
With 3% of the production effort to go on CVN 78, the principal risk remains completing the shipboard test program and in particular, the test programs for concurrently developed systems, including EMALS, AAG and DBR. During EMALS testing in October 2015, the EMALS Prime Power Interface Sub System Transformer/Rectifier (T/R) #3 failed. The Navy has replaced the T/R with a spare, and dead-load testing has resumed. As of late February 2016, nine dead-load tests are complete. DBR testing is progressing. All three Multi-Function Radar arrays have been successfully energized at high power. The shipboard construction and test efforts for AAG are behind schedule due to delays in system development.
Performance Testing was suspended at the AAG land based test site for approximately two years to investigate and correct critical design issues with major AAG components. System level installation and checkout testing is projected to complete in time to support first aircraft operations in Fall 2016. The Navy is monitoring the land based testing and software development efforts closely to ensure system level installation and checkout testing is complete in time to support first aircraft operations in Fall 2016.
Just as we have experienced learning on the design and construction of this first of class carrier, we are also experiencing learning during the testing phase. Reasonable time frames were allocated to complete the initial testing, but the compounding problems of first of class systems with first of class integration testing have taken longer than originally planned. Shipboard testing progress to date has been slower than anticipated. As a result, sea trials are expected to commence June 2016, and delivery is expected in late August/early September 2016. The Navy expects no schedule delay to CVN 78 deployability due to the sea trials delay and is managing these schedule delays within the $12,887M cost cap.
CVN 78 is the numerical replacement for USS ENTERPRISE (CVN 65), inactivated on December 1, 2012. Upon delivery of CVN 78, the Navy carrier force will return to 11 ships as required by 10 U.S.C. 5062(b).
The Navy will conduct Full Ship Shock Trials (FSST) on CVN 78 prior to deployment in accordance with the ADM signed by USD(AT&L) on August 7, 2015. FSST will be conducted in FY 2019 following the completion of CVN 78 component shock qualification in FY 2016-FY 2018. Following FSST, CVN 78 will enter its scheduled maintenance availability and required training workups prior to being deployment ready in 2021.
On June 5, 2015, the Navy awarded to Huntington Ingalls Industries - Newport News Shipbuilding a Fixed Price Incentive Firm target contract in the amount of $3.35B for the JOHN F. KENNEDY (CVN 79) Detail Design & Construction effort. Additionally, a $941M modification to the Construction Preparation contract was awarded the same day. This modification included the remaining component and steel fabrication and selected construction unit assemblies already underway where proven performance results were available. Keeping like work on one contract reduces the cost of contract administration, enables better procurement oversight, and avoids potential errors in tracking workers' time charges for similar work scope on two separate contracts. An Integrated Baseline Review was conducted in January 2016.
The keel for CVN 79 was laid into the graving dock on August 22, 2015. CVN 79 is the force structure replacement for USS NIMITZ (CVN 68), which is scheduled for inactivation in 2025.
With 16.8% constructed based on total production hours, the shipbuilder is on track to achieve the negotiated 18% production hour reduction on CVN 79.

## Table 8
For CVN 79, the Navy has implemented a two-phase acquisition plan which will allow the basic ship to be constructed and tested in the most efficient manner by the shipbuilder (Phase I) while enabling select ship systems and compartments to be completed in Phase II, where the work can be completed more affordably through competition or the use of skilled installation teams. The two-phase strategy for CVN 79 capitalizes on schedule flexibility to deliver the ship at the lowest cost and enables the Navy to procure and install at the latest date possible shipboard electronics systems which otherwise would be subject to obsolescence prior to CVN 79's first deployment in 2027. All costs for both Phase I and Phase II are included within the CVN 79 end cost and are accounted for within the cost cap.
The FY 2017 PB submission for ENTERPRISE (CVN 80) is $12.9B, $572M below the FY 2016 PB submission, and $974M below the FY 2015 PB submission. The Navy continues to seek out and implement cost reduction opportunities. To that end, Navy has established a Ford Class Design for Affordability RDT&E investment for the identification and development of initiatives to reduce construction costs.
As documented in the April 28, 2015 ADM, the USD(AT&L) will conduct annual in-process review DABs of the CVN 78 Class Program. The Navy and USD(AT&L) remain in discussions about the optimum timing for the program's Milestone C review.
Development and ship integration efforts for EMALS continue as planned. The System Development and Demonstration program is 99% complete. Land-based aircraft compatibility testing in Lakehurst, NJ completed in April 2014 and shipboard testing with dead-loads started in June 2015. The Lakehurst site will remain operational through 2017 to support shipboard testing, the correction of deficiencies, CVN 78 crew training, a maintainability demonstration, and logistics product development which is currently 81.5% complete. The delivery of EMALS hardware to CVN 78 is 100% complete. Shipboard commissioning began in August 2014 and will continue through 2016.
The EMALS CVN 79 production shipset contract was awarded as an Undefinitized Contract Action on June 12, 2015. Final contract definitization is planned for 3Q FY 2016.
There are no significant software-related issues with this program at this time.

## Table 9
Threshold Breaches
CVN 78
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
Shipboard testing progress to date has been slower than anticipated. As a result sea trials are expected to commence on June 30, 2016. The shipboard testing delay has resulted in a delay to Combat Systems Trial Rehearsal which is now planned for May 2016. The delay in sea trials has resulted in a subsequent delay to CVN 78 Delivery and IOC, which are now planned for September 2016 and October 2017, respectively.
Further, as the Navy has addressed concerns expressed by the Government Accountability Office and the Director of Operational Test and Evaluation (D,OT&E) regarding the amount of overlap between Developmental Testing (DT) and Operational Testing, a realignment of the post-delivery test and trial period has resulted in a delay to Initial Operational Test and Evaluation (IOT&E) and Platform- Level Integration DT Period Complete. IOT&E Start, Platform-Level Integration DT Period Complete, and IOT&E Complete have been rescheduled to May 2018, November 2018, and April 2020, respectively.
CVN 79 DAB Program Review and Start Construction event breaches were previously reported in the December 2014 SAR.
The Program Office is currently developing a Program Deviation Report (PDR) to address these changes and an APB update will be submitted at a future date.
Nunn-McCurdy Breaches
EMALS
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
EMALS will deliver and complete IOC as a component to the ship. The ship delivery and IOC have shifted to September 2016 and October 2017, respectively.
Additionally, EMALS will reach IOT&E Start, Platform-Level Integration DT Period Complete, and IOT&E Complete with the ship and have been rescheduled to May 2018, November 2018, and April 2020, respectively.
The cost breach to RDT&E was previously reported in the December 2014 SAR for EMALS in the amount of $5.5M. The program anticipates this breach to increase to approximately $61.6M. This cost breach is the result of additional costs associated with maintaining the EMALS shore based test site and continued land
Nunn-McCurdy Breaches

## Table 10
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
based testing efforts.
The Program Office is currently developing a PDR to address these changes and an APB update will be submitted at a future date.

## Table 11
Schedule

## Table 12
CVN 78
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
CVN 78
Early Operational Assessment | Mar 2004 | Mar 2004 | Sep 2004 | Mar 2004
Milestone B | Apr 2004 | Apr 2004 | Oct 2004 | Apr 2004
DAB Program Review (PR) | Jan 2006 | Jan 2008 | Jul 2008 | Jul 2008
Start Construction | Jan 2007 | Mar 2008 | Sep 2008 | Sep 2008
Launch | Nov 2012 | Nov 2013 | May 2014 | Nov 2013
Delivery | Sep 2014 | Sep 2015 | Mar 2016 | Sep 20161
OPEVAL
Start | Oct 2014 | N/A | N/A | N/A
Complete | Sep 2017 | N/A | N/A | N/A
TECHEVAL | Feb 2015 | N/A | N/A | N/A
Combat Systems Trial Rehearsal (CSTR) | Jul 2014 | Jul 2015 | Jan 2016 | May 20161
Initial Operational Capability (IOC) | Sep 2015 | Sep 2016 | Mar 2017 | Oct 20171
Follow-on Ship (CVN 79)
DAB Program Review | Jan 2010 | Apr 2013 | Oct 2013 | Apr 20151
Start Construction | Jan 2011 | Aug 2013 | Feb 2014 | Jun 20151
Delivery | Sep 2018 | Sep 2022 | Mar 2023 | Jun 2022
Follow-on Ship (CVN 80)
DAB Program Review | Jan 2015 | Sep 2017 | Mar 2018 | Oct 2017
IOT&E
IOT&E Start | N/A | Feb 2017 | Aug 2017 | May 20181
IOT&E Complete | N/A | Aug 2019 | Feb 2020 | Apr 20201
Milestone C | Mar 2017 | Sep 2019 | Mar 2020 | Oct 2017
Platform-Level Integration DT Period Complete | N/A | Sep 2017 | Mar 2018 | Nov 20181
(Ch-1)
(Ch-2)
(Ch-3)
(Ch-4)
1 APB Breach
(Ch-5)
(Ch-6)
(Ch-7)
(Ch-8)

## Table 13
Change Explanations
(Ch-1) The current estimate for CVN 78 Delivery is revised from March 2016 to September 2016 to reflect delays associated with the shipboard testing and integration schedule.
(Ch-2) The current estimate for CSTR is rescheduled from November 2015 to May 2016 to reflect delays associated with the shipboard testing and integration schedule.
(Ch-3) The current estimate for IOC is rescheduled from March 2017 to October 2017 to reflect a shift in PSA start and completion dates resulting from the delay to delivery.
(Ch-4) The current estimate for CVN 79 Start Construction was revised from May 2015 to June 2015 to reflect actual date of contract award.
(Ch-5) The current estimate for IOT&E Start is revised from September 2017 to May 2018 to reflect shift in the PSA dates and partially to provide sufficient time for crew familiarization training and Platform Level DT integration testing with the new systems installed during PSA before commencing operational testing.
(Ch-6) The current estimate for IOT&E Complete is revised from February 2020 to April 2020 to reflect shift in the PSA dates and partially to provide sufficient time for crew familiarization training and Platform Level DT integration testing with the new systems installed during PSA before commencing operational testing.
(Ch-7) The current estimate for Milestone C is rescheduled from April 2015 to October 2017 to align with CVN 80 DAB Program Review.
(Ch-8) The current estimate for Platform-Level Integration DT Period Complete is rescheduled from April 2018 to November 2018 to reflect a shift in PSA start and completion dates resulting from the delay to delivery.
Acronyms and Abbreviations
CSTR - Combat Systems Trial Rehersal DT - Developmental Testing
IOT&E - Initial Operational Test & Evaluation OPEVAL - Operational Evaluation
PSA - Post Shakedown Availability TECHEVAL - Technical Evaluation

## Table 14
EMALS
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
EMALS
Delivery (with Ship) | Sep 2015 | Sep 2015 | Mar 2016 | Sep 20161
IOC | Sep 2016 | Sep 2016 | Mar 2017 | Oct 20171
IOT&E
IOT&E Start | Feb 2017 | Feb 2017 | Aug 2017 | May 20181
IOT&E Complete | Aug 2019 | Aug 2019 | Feb 2020 | Apr 20201
Platform-Level Integration DT Period Complete | Sep 2017 | Sep 2017 | Mar 2018 | Nov 20181
(Ch-1)
(Ch-2)
1 APB Breach
(Ch-3)
(Ch-4)
(Ch-5)
Change Explanations
(Ch-1) The current estimate for CVN 78 Delivery is revised from March 2016 to September 2016 to reflect delays associated with the shipboard testing and integration schedule.
(Ch-2) The current estimate for IOC is rescheduled from March 2017 to October 2017 to reflect a shift in PSA start and completion dates resulting from the delay to delivery.
(Ch-3) The current estimate for IOT&E Start is revised from September 2017 to May 2018 to reflect shift in the PSA dates and partially to provide sufficient time for crew familiarization training and Platform Level DT integration testing with the new systems installed during PSA before commencing operational testing.
(Ch-4) The current estimate for IOT&E Complete is revised from February 2020 to April 2020 to reflect a shift in the PSA dates and partially to provide sufficient time for crew familiarization training and Platform Level DT integration testing with the new systems installed during PSA before commencing operational testing.
(Ch-5) The current estimate for Platform-Level Integration DT Period Complete is rescheduled from April 2018 to November 2018 to reflect a shift in PSA start and completion dates resulting from the delay to delivery.
Acronyms and Abbreviations
DT - Developmental Test
IOT&E - Initial Operational Test & Evaluation PSA - Post Shakedown Availability

## Table 15
Performance
CVN 78
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
CVN 78
Interoperability
Note 2 | N/A | N/A | TBD | N/A
Sustained Sortie Rate
220 | 220 | 160 | TBD | 172
Surge Sortie Rate
310 | 310 | 270 | TBD | 284
Ship Service Electrical Generating Capacity (times NIMITZ Class capacity in MW)
3 | 3 | 2.5 | TBD | 2.7
Weight Service Life Allowance (% of full load displacement in long tons)
7.5 | 7.5 | 5 | TBD | 5.9
Stability Service Life Allowance (feet)
2.5 | 2.5 | 1.5 | TBD | 1.5
Ship's Force Manpower (billets)
2391 | 2391 | 2791 | TBD | 2628
Follow-on Ship
Interoperability
Note 2 | N/A | N/A | N/A | N/A
Sustained Sortie Rate
220 | N/A | N/A | N/A | N/A
Surge Sortie Rate
310 | N/A | N/A | N/A | N/A
Service Electrical Generating Capacity (times NIMITZ Class capacity in MW)
3 | N/A | N/A | N/A | N/A
Weight Service Life Allowance (% of full load displacement in long tons)
7.5 | N/A | N/A | N/A | N/A
Stability Service Life Allowance (feet)
2.5 | N/A | N/A | N/A | N/A
Ship's Force Manpower (billets)

## Table 16
2391 | N/A | N/A | N/A | N/A
Force Protection and Survivability in an Asymmetric Threat Environment
Survivability
N/A | Level III as defined by OPNAV Instruction 9070.1 | Level II as defined by OPNAV Instruction 9070.1 with the exception of Collective Protection System | TBD | Level II as defined by OPNAV Instruction 9070.1 with the exception of Collective Protection System
Net-Ready
N/A | Meets 100% of top level IERs | Meets 100% of top level IERs designated as critical | TBD | Meets 100% of top level IERs designated as critical
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Operational Requirements Document (ORD) Change 2 dated June 22, 2007
Change Explanations
None
Notes
CVN 78 performance Threshold and Objectives apply to all ships in the class. Current estimates for the follow-on ship will be updated, if different from the lead ship, when they become available.
For additional description regarding CVN 78 and Follow-on Ship Interoperability and other Performance Characteristics, see Table 4.4, KPPs, contained in the Future Aircraft Carrier (CVN 21) ORD dated June 22, 2007.
Acronyms and Abbreviations
CBR - Chemical, Biological, Radiological IER - Interoperability Exchange Requirement MW - Megawatt
OPNAV - Chief of Naval Operations

## Table 17
EMALS
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
See Note
N/A | N/A | N/A | TBD | N/A
Requirements Reference
Operational Requirements Document (ORD) Change 2 dated June 22, 2007
Change Explanations
None
Notes
The JROC has not established KPPs specific to the EMALS subprogram. All existing CVN 78 Class KPPs will be managed in the CVN 78 Class ship subprogram section.

## Table 18
Track to Budget
CVN 78
RDT&E
Appn |  |  | BA | PE
Navy |  | 1319 04 |  | 0603512N
|  | Project |  |  | Name
|  | 10C098 |  | Composite Mast for CVN's |  |  | (Sunk)
|  | 2208 |  | CVN 21 |  | (Shared) | (Sunk)
|  | 2678 |  | Tech Insertion |  |  | (Sunk)
|  | 2693 |  | Ship System Definition |  |  | (Sunk)
|  | 4006 |  | CVN 79 |  |  | (Sunk)
|  | 9181 |  | Adv Battlestations/DSS |  |  | (Sunk)
|  | 9349 |  | Aviation Ship Integration Center |  |  | (Sunk)
|  | 9516 |  | Surface Ship Composite Moisture Separators |  |  | (Sunk)
|  | 9B57A |  | Carrier Plant Automation and Manning Reduction |  |  | (Sunk)
Navy |  | 1319 | 4 | 0603564N
|  | Project |  | Name
|  | 2230 |  | CV Feasibility Studies |  | (Sunk)
|  | 4230 |  | CVNX 1 |  | (Sunk)
Navy |  | 1319 | 4 | 0603570N
|  | Project |  | Name
|  | 2692 |  | Advance Nuclear Power System/CVN 21 Propulsion Plant Development
Navy |  | 1319 | 4 | 0604112N
|  | Project |  | Name
|  | 2208 |  | CVN 21
|  | 9999 |  | CVN-78 Shock Trials
Navy |  | 1319 | 5 | 0604567N
|  | Project |  | Name
2301 Contract Design (Sunk)
3108 CVN 80 Total Ship Integration
3179 CVN 79 Total Ship Integration
4007 CVN 21 LFT&E
4008 CVN 21 Total Ship Integration (Sunk) 9C20A Automated Fiber Optic Manufacturing Initiative (Sunk)
Procurement
Appn |  |  | BA | PE
Navy 1611 02 07029898N
Line Item | Name

## Table 19
2001 Carrier Replacement Program (Shared) Navy 1611 02 0204112N
Line Item Name
2001 Carrier Replacement Program (Shared) Navy 1611 05 0204112N
Line Item Name
5110 Outfitting (Shared)
5300 Completion of Prior Year Shipbuilding (Shared) (Sunk) Navy 1810 01 0204112N
Line Item Name
0981 Surface Training Equipment (Shared)
MILCON
Appn BA PE
Navy 1205 01 0203176N
Project Name
62688500 Pier 11 CVN-78 Power Booms (Sunk) Navy 1205 01 0702776N
Project Name
32443998 Drydock 8 Electrical Distribution Upgrade (Sunk)
Acq O&M
Appn BA PE
Navy 1804 01 0702827N
Project Name
1B2B Ship Operational Support and Training (Shared)
EMALS
RDT&E
Appn |  | BA | PE
Navy | 1319 04 |  | 0603512N
| Project |  | Name
| 2208 |  | CVN 21 | (Shared) | (Sunk)
| 4004 9B58A 9D24A |  | EMALS Improved Corrosion Protection for EMALS EMALS Congressional Add |  | (Sunk) (Sunk) (Sunk)
Navy | 1319 04 |  | 0604112N
| Project |  | Name
| 4004 |  | EMALS
Procurement
Navy | 1611 02 |  | 0204112N
| Line Item |  | Name
Appn |  | BA | PE

## Table 20
2001 Carrier Replacement Program (Shared)
MILCON
Appn |  | BA | PE
Navy 1205 01 0212176N
Project | Name
N0400024 EMALS Facility (Sunk)

## Table 21
Cost and Funding
Cost Summary - Total Program
Total Acquisition Cost - Total Program
Appropriation | BY 2000 $M |  |  |  | BY 2000 $M |  | TY $M
| SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E | 3875.3 |  | 4123.4 | -- |  | 4080.7 |  | 4333.4 |  | 4744.6 |  | 4794.3
Procurement | 24825.9 |  | 24357.7 | -- |  | 23740.7 |  | 31748.7 |  | 33258.8 |  | 38897.5
Flyaway | -- |  | -- | -- |  | 23734.3 |  | -- |  | -- |  | 38888.8
Recurring | -- |  | -- | -- |  | 20540.6 |  | -- |  | -- |  | 34184.6
Non Recurring | -- |  | -- | -- |  | 3193.7 |  | -- |  | -- |  | 4704.2
Support | -- |  | -- | -- |  | 6.4 |  | -- |  | -- |  | 8.7
Other Support | -- |  | -- | -- |  | 6.4 |  | -- |  | -- |  | 8.7
Initial Spares | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON | 0 |  | 152 | -- |  | 46.2 |  | 0 |  | 208.5 |  | 56.9
Acq O&M | 0 |  | 0 | -- |  | 54.4 |  | 0 |  | 0 |  | 73.8
Total | 28701.2 |  | 28633.1 | N/A |  | 27922 |  | 36082.1 |  | 38211.9 |  | 43822.5

## Table 22
Cost and Funding
Cost Summary - CVN 78
Total Acquisition Cost - CVN 78
Appropriation | BY 2000 $M | [6 empty] | BY 2000 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 3490.6 |  |  | 3472.2 | 3819.4 |  |  | 3269.5 |  | 3923 |  |  | 3999.8 |  | 3835.4
Procurement |  | 24235 |  |  | 22764.3 | 25040.7 |  |  | 22478 |  | 30977.4 |  |  | 30808.7 |  | 36750.1
Flyaway |  | -- |  |  | -- | -- |  |  | 22471.6 |  | -- |  |  | -- |  | 36741.4
Recurring |  | -- |  |  | -- | -- |  |  | 19277.9 |  | -- |  |  | -- |  | 32037.2
Non Recurring |  | -- |  |  | -- | -- |  |  | 3193.7 |  | -- |  |  | -- |  | 4704.2
Support |  | -- |  |  | -- | -- |  |  | 6.4 |  | -- |  |  | -- |  | 8.7
Other Support |  | -- |  |  | -- | -- |  |  | 6.4 |  | -- |  |  | -- |  | 8.7
Initial Spares |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON |  | 0 |  |  | 133.2 | 146.5 |  |  | 27.4 |  | 0 |  |  | 187.8 |  | 36.2
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 54.4 |  | 0 |  |  | 0 |  | 73.8
Total |  | 27725.6 |  |  | 26369.7 | N/A |  |  | 25829.3 |  | 34900.4 |  |  | 34996.3 |  | 40695.5
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The estimate to support this program, like most cost estimates, is built upon a product-oriented work breakdown structure based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which we have been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about as likely the estimate will prove too low or too high for the program as described.
Total Quantity - CVN 78
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  |  | 3 |  |  |  | 3 |  |  |  |  | 3
Total |  |  | 3 |  |  |  | 3 |  |  |  |  | 3

## Table 23
Cost Summary - EMALS
Total Acquisition Cost - EMALS
Appropriation | BY 2000 $M | [5 empty] | BY 2000 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E | 384.7 |  |  | 651.2 | 748.9 |  |  | 811.21 |  | 410.4 |  |  | 744.8 |  | 958.9
Procurement | 590.9 |  |  | 1593.4 | 1752.7 |  |  | 1262.7 |  | 771.3 |  |  | 2450.1 |  | 2147.4
Flyaway | -- |  |  | -- | -- |  |  | 1262.7 |  | -- |  |  | -- |  | 2147.4
Recurring | -- |  |  | -- | -- |  |  | 1262.7 |  | -- |  |  | -- |  | 2147.4
Non Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON | 0 |  |  | 18.8 | 20.7 |  |  | 18.8 |  | 0 |  |  | 20.7 |  | 20.7
Acq O&M | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 975.6 |  |  | 2263.4 | N/A |  |  | 2092.7 |  | 1181.7 |  |  | 3215.6 |  | 3127
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The estimate to support this program, like most cost estimates, is built upon a product-oriented work breakdown structure based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which we have been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for major complex systems. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about as likely the estimate will prove too low or too high for the program as described.
Total Quantity - EMALS
Quantity |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  | 3 |  |  |  | 3 |  |  |  |  | 3
Total |  | 3 |  |  |  | 3 |  |  |  |  | 3

## Table 24
Cost and Funding
Funding Summary - Total Program
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | To Complete | Total
RDT&E | 4011.7 | 116.7 | 121.5 | 150 | 134.2 | 90.5 | 72.2 | 97.5 | 4794.3
Procurement | 18832.9 | 2659.9 | 2668.9 | 4361.2 | 1650.2 | 1736.5 | 3097.1 | 3890.8 | 38897.5
MILCON | 56.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.9
Acq O&M | 4.8 | 38.4 | 14.1 | 4.8 | 3.8 | 3.9 | 4 | 0 | 73.8
PB 2017 Total | 22906.3 | 2815 | 2804.5 | 4516 | 1788.2 | 1830.9 | 3173.3 | 3988.3 | 43822.5
PB 2016 Total | 22868.8 | 2846.9 | 3068.4 | 3598.8 | 2133 | 931.1 | 2339.6 | 5174.6 | 42961.2
Delta | 37.5 | -31.9 | -263.9 | 917.2 | -344.8 | 899.8 | 833.7 | -1186.3 | 861.3

## Table 25
Cost and Funding
Funding Summary - CVN 78
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 3145.1 | 104.2 |  | 83.8 |  | 124 | 118.1 |  | 90.5 |  | 72.2 |  | 97.5 |  | 3835.4
Procurement | 17946.7 | 2386 |  | 2434.5 |  | 4183.4 | 1472.3 |  | 1609.6 |  | 2984.5 |  | 3733.1 |  | 36750.1
MILCON | 36.2 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 36.2
Acq O&M | 4.8 | 38.4 |  | 14.1 |  | 4.8 | 3.8 |  | 3.9 |  | 4 |  | 0 |  | 73.8
PB 2017 Total | 21132.8 | 2528.6 |  | 2532.4 |  | 4312.2 | 1594.2 |  | 1704 |  | 3060.7 |  | 3830.6 |  | 40695.5
PB 2016 Total | 21107.3 | 2645.1 |  | 2913.1 |  | 3318 | 1983 |  | 866.1 |  | 2189.6 |  | 4645.6 |  | 39667.8
Delta | 25.5 | -116.5 |  | -380.7 |  | 994.2 | -388.8 |  | 837.9 |  | 871.1 |  | -815 |  | 1027.7
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 2 |  | 0 | 0 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 3
PB 2017 Total | 0 |  | 2 |  | 0 | 0 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 3
PB 2016 Total | 0 |  | 2 |  | 0 | 0 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 3
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0

## Table 26
Funding Summary - EMALS
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 866.6 | 12.5 |  | 37.7 |  | 26 | 16.1 |  | 0 |  | 0 |  | 0 |  | 958.9
Procurement | 886.2 | 273.9 |  | 234.4 |  | 177.8 | 177.9 |  | 126.9 |  | 112.6 |  | 157.7 |  | 2147.4
MILCON | 20.7 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 20.7
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 1773.5 | 286.4 |  | 272.1 |  | 203.8 | 194 |  | 126.9 |  | 112.6 |  | 157.7 |  | 3127
PB 2016 Total | 1761.5 | 201.8 |  | 155.3 |  | 280.8 | 150 |  | 65 |  | 150 |  | 529 |  | 3293.4
Delta | 12 | 84.6 |  | 116.8 |  | -77 | 44 |  | 61.9 |  | -37.4 |  | -371.3 |  | -166.4
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 2 |  | 0 | 0 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 3
PB 2017 Total | 0 |  | 2 |  | 0 | 0 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 3
PB 2016 Total | 0 |  | 2 |  | 0 | 0 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 3
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0

## Table 27
Cost and Funding
Annual Funding By Appropriation - CVN 78
Annual Funding - CVN 78 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.1
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.3
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 136.8
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 189.5
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 240.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 272.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 268.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 300.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 245.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 229.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 191.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 201.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 179.6
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 119.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 104.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 103.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 117.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 104.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 124
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.1
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 90.5
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.2
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.3
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.6
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3835.4

## Table 28
Annual Funding - CVN 78 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2000 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.9
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.7
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 135.5
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 185.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 232.6
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 259.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 249.2
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 271.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 215.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 196.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 160.8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 167.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 146.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 79.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.2
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.8
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.2
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.1
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3269.5

## Table 29
Annual Funding - CVN 78 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | 21.7 |  | -- |  | -- |  | 21.7 |  | -- |  | 21.7
2002 |  | -- | 135.3 |  | -- |  | -- |  | 135.3 |  | -- |  | 135.3
2003 |  | -- | 243.7 |  | -- |  | 151.8 |  | 395.5 |  | -- |  | 395.5
2004 |  | -- | 955.2 |  | -- |  | 207.7 |  | 1162.9 |  | -- |  | 1162.9
2005 |  | -- | 274.4 |  | -- |  | 348.7 |  | 623.1 |  | -- |  | 623.1
2006 |  | -- | 241.6 |  | -- |  | 377.3 |  | 618.9 |  | -- |  | 618.9
2007 |  | -- | 358.3 |  | -- |  | 424.5 |  | 782.8 |  | -- |  | 782.8
2008 |  | 1 | 1772.3 |  | -- |  | 1010.7 |  | 2783 |  | -- |  | 2783
2009 |  | -- | 3663 |  | -- |  | 54.9 |  | 3717.9 |  | -- |  | 3717.9
2010 |  | -- | 830.3 |  | -- |  | 251 |  | 1081.3 |  | -- |  | 1081.3
2011 |  | -- | 1811 |  | -- |  | 546.3 |  | 2357.3 |  | -- |  | 2357.3
2012 |  | -- | 453.6 |  | -- |  | 101.2 |  | 554.8 |  | -- |  | 554.8
2013 |  | 1 | 393.7 |  | -- |  | 82.7 |  | 476.4 |  | -- |  | 476.4
2014 |  | -- | 1214.8 |  | -- |  | 267.3 |  | 1482.1 |  | -- |  | 1482.1
2015 |  | -- | 1643.8 |  | -- |  | 109.9 |  | 1753.7 |  | -- |  | 1753.7
2016 |  | -- | 2232.7 |  | -- |  | 148.6 |  | 2381.3 |  | -- |  | 2381.3
2017 |  | -- | 2325.3 |  | -- |  | 105.2 |  | 2430.5 |  | -- |  | 2430.5
2018 |  | 1 | 4105.4 |  | -- |  | 78 |  | 4183.4 |  | -- |  | 4183.4
2019 |  | -- | 1374.9 |  | -- |  | 97.4 |  | 1472.3 |  | -- |  | 1472.3
2020 |  | -- | 1514.4 |  | -- |  | 95.2 |  | 1609.6 |  | -- |  | 1609.6
2021 |  | -- | 1925.1 |  | 968.4 |  | 91 |  | 2984.5 |  | -- |  | 2984.5
2022 |  | -- | 1560.3 |  | -- |  | 85.5 |  | 1645.8 |  | -- |  | 1645.8
2023 |  | -- | 1651.4 |  | -- |  | 69.3 |  | 1720.7 |  | -- |  | 1720.7
2024 |  | -- | 69.4 |  | -- |  | -- |  | 69.4 |  | -- |  | 69.4
2025 |  | -- | 61.6 |  | -- |  | -- |  | 61.6 |  | -- |  | 61.6
2026 |  | -- | 77.7 |  | -- |  | -- |  | 77.7 |  | -- |  | 77.7
2027 |  | -- | 140.2 |  | -- |  | -- |  | 140.2 |  | -- |  | 140.2
2028 |  | -- | 17.7 |  | -- |  | -- |  | 17.7 |  | -- |  | 17.7
Subtotal |  | 3 | 31068.8 |  | 968.4 |  | 4704.2 |  | 36741.4 |  | -- |  | 36741.4

## Table 30
Annual Funding - CVN 78 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 2000 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | 19.7 |  | -- |  | -- |  | 19.7 |  | -- |  | 19.7
2002 |  | -- | 122 |  | -- |  | -- |  | 122 |  | -- |  | 122
2003 |  | -- | 207.7 |  | -- |  | 129.4 |  | 337.1 |  | -- |  | 337.1
2004 |  | -- | 785.7 |  | -- |  | 170.9 |  | 956.6 |  | -- |  | 956.6
2005 |  | -- | 216.1 |  | -- |  | 274.7 |  | 490.8 |  | -- |  | 490.8
2006 |  | -- | 183.8 |  | -- |  | 287.1 |  | 470.9 |  | -- |  | 470.9
2007 |  | -- | 260.6 |  | -- |  | 308.8 |  | 569.4 |  | -- |  | 569.4
2008 |  | 1 | 1246.8 |  | -- |  | 710.9 |  | 1957.7 |  | -- |  | 1957.7
2009 |  | -- | 2499.9 |  | -- |  | 37.5 |  | 2537.4 |  | -- |  | 2537.4
2010 |  | -- | 547.4 |  | -- |  | 165.5 |  | 712.9 |  | -- |  | 712.9
2011 |  | -- | 1156.3 |  | -- |  | 348.8 |  | 1505.1 |  | -- |  | 1505.1
2012 |  | -- | 283.2 |  | -- |  | 63.2 |  | 346.4 |  | -- |  | 346.4
2013 |  | 1 | 241 |  | -- |  | 50.6 |  | 291.6 |  | -- |  | 291.6
2014 |  | -- | 729.9 |  | -- |  | 160.7 |  | 890.6 |  | -- |  | 890.6
2015 |  | -- | 970.8 |  | -- |  | 64.9 |  | 1035.7 |  | -- |  | 1035.7
2016 |  | -- | 1294.8 |  | -- |  | 86.2 |  | 1381 |  | -- |  | 1381
2017 |  | -- | 1323 |  | -- |  | 59.8 |  | 1382.8 |  | -- |  | 1382.8
2018 |  | 1 | 2290.4 |  | -- |  | 43.5 |  | 2333.9 |  | -- |  | 2333.9
2019 |  | -- | 752 |  | -- |  | 53.3 |  | 805.3 |  | -- |  | 805.3
2020 |  | -- | 812.1 |  | -- |  | 51 |  | 863.1 |  | -- |  | 863.1
2021 |  | -- | 1012 |  | 509.2 |  | 47.8 |  | 1569 |  | -- |  | 1569
2022 |  | -- | 804.2 |  | -- |  | 44.1 |  | 848.3 |  | -- |  | 848.3
2023 |  | -- | 834.5 |  | -- |  | 35 |  | 869.5 |  | -- |  | 869.5
2024 |  | -- | 34.4 |  | -- |  | -- |  | 34.4 |  | -- |  | 34.4
2025 |  | -- | 29.9 |  | -- |  | -- |  | 29.9 |  | -- |  | 29.9
2026 |  | -- | 37 |  | -- |  | -- |  | 37 |  | -- |  | 37
2027 |  | -- | 65.4 |  | -- |  | -- |  | 65.4 |  | -- |  | 65.4
2028 |  | -- | 8.1 |  | -- |  | -- |  | 8.1 |  | -- |  | 8.1
Subtotal |  | 3 | 18768.7 |  | 509.2 |  | 3193.7 |  | 22471.6 |  | -- |  | 22471.6

## Table 31
Navy plans to build 11 CVN 78 Class ships to replace CVN 65 and CVN 68 Class ships.
Cost Quantity Information
The Navy and shipbuilder have made fundamental changes in the manner in which the CVN 79 will be built to incorporate lessons learned from CVN 78 and eliminate the key contributors to cost performance challenges realized in the construction of CVN 78. Further improvements are planned for CVN 80 and have been incorporated into the CVN 80 cost estimates and budgets. The FY 2017 PB for CVN 80 is $572.0M in TY$ ($279.2M in BY$) less than the FY 2016 PB, and $974M less than the FY 2015 PB.
The FY 2017 PB introduces the first year of funding for CVN 81; however, it is not in the current APB. An update to the APB will be needed at a later to date to add CVN 81 to the program baseline. With the addition of CVN 81 into the FYDP, unit costs will appear to have increased until CVN 81 is added to the APB and the unit cost is adjusted to reflect four ships.

## Table 32
Cost Quantity Information - CVN 78 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2000 $M
2001 | -- | --
2002 | -- | --
2003 | -- | --
2004 | -- | --
2005 | -- | --
2006 | -- | --
2007 | -- | --
2008 | 1 | 6344.1
2009 | -- | --
2010 | -- | --
2011 | -- | --
2012 | -- | --
2013 | 1 | 6011.3
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | 1 | 6413.3
2019 | -- | --
2020 | -- | --
2021 | -- | --
2022 | -- | --
2023 | -- | --
2024 | -- | --
2025 | -- | --
2026 | -- | --
2027 | -- | --
2028 | -- | --
Subtotal | 3 | 18768.7

## Table 33
Annual Funding - CVN 78 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | 4.7 |  | 4.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | 4 |  | 4
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 8.7 |  | 8.7

## Table 34
Annual Funding - CVN 78 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2000 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | 3.5 |  | 3.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | 2.9 |  | 2.9
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 6.4 |  | 6.4

## Table 35
Annual Funding - CVN 78 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2013 | 32.8
2014 | 3.4
Subtotal | 36.2

## Table 36
Annual Funding - CVN 78 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2000 $M
Total Program
2013 | 24.9
2014 | 2.5
Subtotal | 27.4

## Table 37
Annual Funding - CVN 78 1804 ¦ Acq O&M ¦ Operation and Maintenance, Navy
Fiscal Year | TY $M
Total Program
2015 | 4.8
2016 | 38.4
2017 | 14.1
2018 | 4.8
2019 | 3.8
2020 | 3.9
2021 | 4
Subtotal | 73.8

## Table 38
Annual Funding - CVN 78 1804 ¦ Acq O&M ¦ Operation and Maintenance, Navy
Fiscal Year | BY 2000 $M
Total Program
2015 | 3.6
2016 | 28.8
2017 | 10.4
2018 | 3.5
2019 | 2.7
2020 | 2.7
2021 | 2.7
Subtotal | 54.4

## Table 39
Annual Funding By Appropriation - EMALS
Annual Funding - EMALS 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.2
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.2
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 90.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.9
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 958.9

## Table 40
Annual Funding - EMALS 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2000 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.6
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.6
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 92.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 93.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 74.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.9
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.6
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 811.2

## Table 41
Annual Funding - EMALS 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | 5.8 |  | -- |  | -- |  | 5.8 |  | -- |  | 5.8
2008 |  | 1 | 25.6 |  | -- |  | -- |  | 25.6 |  | -- |  | 25.6
2009 |  | -- | 177.2 |  | -- |  | -- |  | 177.2 |  | -- |  | 177.2
2010 |  | -- | 138.6 |  | -- |  | -- |  | 138.6 |  | -- |  | 138.6
2011 |  | -- | 257.5 |  | -- |  | -- |  | 257.5 |  | -- |  | 257.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | 1 | 17.8 |  | -- |  | -- |  | 17.8 |  | -- |  | 17.8
2014 |  | -- | 65.3 |  | -- |  | -- |  | 65.3 |  | -- |  | 65.3
2015 |  | -- | 198.4 |  | -- |  | -- |  | 198.4 |  | -- |  | 198.4
2016 |  | -- | 273.9 |  | -- |  | -- |  | 273.9 |  | -- |  | 273.9
2017 |  | -- | 234.4 |  | -- |  | -- |  | 234.4 |  | -- |  | 234.4
2018 |  | 1 | 177.8 |  | -- |  | -- |  | 177.8 |  | -- |  | 177.8
2019 |  | -- | 177.9 |  | -- |  | -- |  | 177.9 |  | -- |  | 177.9
2020 |  | -- | 126.9 |  | -- |  | -- |  | 126.9 |  | -- |  | 126.9
2021 |  | -- | 112.6 |  | -- |  | -- |  | 112.6 |  | -- |  | 112.6
2022 |  | -- | 87.8 |  | -- |  | -- |  | 87.8 |  | -- |  | 87.8
2023 |  | -- | 69.9 |  | -- |  | -- |  | 69.9 |  | -- |  | 69.9
Subtotal |  | 3 | 2147.4 |  | -- |  | -- |  | 2147.4 |  | -- |  | 2147.4

## Table 42
Annual Funding - EMALS 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 2000 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2007 |  | -- | 4.2 |  | -- |  | -- |  | 4.2 |  | -- |  | 4.2
2008 |  | 1 | 18 |  | -- |  | -- |  | 18 |  | -- |  | 18
2009 |  | -- | 120.9 |  | -- |  | -- |  | 120.9 |  | -- |  | 120.9
2010 |  | -- | 91.4 |  | -- |  | -- |  | 91.4 |  | -- |  | 91.4
2011 |  | -- | 164.4 |  | -- |  | -- |  | 164.4 |  | -- |  | 164.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | 1 | 10.9 |  | -- |  | -- |  | 10.9 |  | -- |  | 10.9
2014 |  | -- | 39.2 |  | -- |  | -- |  | 39.2 |  | -- |  | 39.2
2015 |  | -- | 117.2 |  | -- |  | -- |  | 117.2 |  | -- |  | 117.2
2016 |  | -- | 158.8 |  | -- |  | -- |  | 158.8 |  | -- |  | 158.8
2017 |  | -- | 133.4 |  | -- |  | -- |  | 133.4 |  | -- |  | 133.4
2018 |  | 1 | 99.2 |  | -- |  | -- |  | 99.2 |  | -- |  | 99.2
2019 |  | -- | 97.3 |  | -- |  | -- |  | 97.3 |  | -- |  | 97.3
2020 |  | -- | 68 |  | -- |  | -- |  | 68 |  | -- |  | 68
2021 |  | -- | 59.2 |  | -- |  | -- |  | 59.2 |  | -- |  | 59.2
2022 |  | -- | 45.3 |  | -- |  | -- |  | 45.3 |  | -- |  | 45.3
2023 |  | -- | 35.3 |  | -- |  | -- |  | 35.3 |  | -- |  | 35.3
Subtotal |  | 3 | 1262.7 |  | -- |  | -- |  | 1262.7 |  | -- |  | 1262.7

## Table 43
Cost Quantity Information
The Navy was successful in using Firm Fixed Price (FFP) Contracting for EMALS on the CVN 78 to control costs and has utilized the same contracting approach on the CVN 79.
Cost Quantity Information - EMALS 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2000 $M
2007 | -- | --
2008 | 1 | 438.2
2009 | -- | --
2010 | -- | --
2011 | -- | --
2012 | -- | --
2013 | 1 | 424
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | 1 | 400.5
2019 | -- | --
2020 | -- | --
2021 | -- | --
2022 | -- | --
2023 | -- | --
Subtotal | 3 | 1262.7

## Table 44
Annual Funding - EMALS 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2004 20.7
Subtotal 20.7

## Table 45
Annual Funding - EMALS 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2000 $M
Total Program
2004 18.8
Subtotal 18.8

## Table 46
Low Rate Initial Production
CVN 78
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2004-04-26 | 2004-04-26
Approved Quantity | 3 | 3
Reference | Milestone B ADM | Milestone B ADM
Start Year | 2004 | 2004
End Year | 2018 | 2018
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the ADM dated April 26, 2004 approving three ships.
EMALS
EMALS has no LRIP quantities because the current LRIP decision occurred prior to the establishment of EMALS as a major subprogram.

## Table 47
Foreign Military Sales
CVN 78
Notes
The Navy has initiated discussions with the Government of India under the DTTI through the JWGACTC about assistance in the construction of an indigenous 65,000 ton aircraft carrier. The discussions are in the early stages and are coordinated through USD(AT&L) International Cooperation and the NIPO. The Program is determining disclosure and other exportability considerations that may impact cooperation/sales. A Critical Program Information assessment has been completed and the Program Office is working with NIPO to develop the necessary documentation to complete a Technology Transfer and Security Assistance Review Board in CY 2016.
EMALS
Notes
The Navy has initiated discussions with the Government of India under the DTTI through the JWGACTC about assistance in the construction of an indigenous 65,000 ton aircraft carrier. The discussions are in the early stages and are coordinated through USD(AT&L) International Cooperation and the NIPO. The Program is determining disclosure and other exportability considerations that may impact cooperation/sales. A Critical Program Information assessment has been completed and the Program Office is working with NIPO to develop the necessary documentation to complete a Technology Transfer and Security Assistance Review Board in CY 2016.
Acronyms and Abbreviations
DTTI - Defense Technology and Trade Initiative
JWGACTC - Joint Working Group on Aircraft Carrier Technology Cooperation NIPO - Navy International Progams Office

## Table 48
Nuclear Costs
CVN 78
Nuclear Research and Development and Reactor Plant Government Furnished Equipment costs are included within the program costs in this report; however, Department of Energy nuclear costs are not included in this report.
Shipbuilding & Conversion Navy Nuclear Propulsion Equipment Cost is $6,221.0M in TY dollars for the CVN 78 Class Aircraft Carriers (CVN 78-80).
EMALS
None

## Table 49
Unit Cost
CVN 78
Unit Cost Report
Item |  | BY 2000 $M | BY 2000 $M |  | % Change
|  | Current UCR Baseline (Apr 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 26369.7 |  |  | 25829.3
Quantity | 3 |  |  | 3
Unit Cost | 8789.9 |  |  | 8609.767 |  | -2.05
Average Procurement Unit Cost
Cost | 22764.3 |  |  | 22478
Quantity | 3 |  |  | 3
Unit Cost | 7588.1 |  |  | 7492.667 |  | -1.26
Item |  | BY 2000 $M | BY 2000 $M |  | % Change
|  | Original UCR Baseline (Apr 2004 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 28701.2 |  |  | 25829.3
Quantity | 3 |  |  | 3
Unit Cost | 9567.067 |  |  | 8609.767 |  | -10.01
Average Procurement Unit Cost
Cost | 24825.9 |  |  | 22478
Quantity | 3 |  |  | 3
Unit Cost | 8275.3 |  |  | 7492.667 |  | -9.46

## Table 50
CVN 78
Unit Cost History
Item |  |  |  | Date |  |  | BY 2000 $M |  |  |  |  | TY $M
[7 empty] | PAUC |  | APUC |  |  | PAUC |  |  |  | APUC
Original APB |  | Apr 2004 |  |  |  |  | 9567.067 |  |  | 8275.3 |  |  |  | 12027.367 |  |  | 10582.9
APB as of January 2006 |  | Aug 2005 |  |  |  |  | 9068.8 |  |  | 7778 |  |  |  | 12004.4 |  |  | 10526.633
Revised Original APB |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  | Nov 2007 |  |  |  |  | 9068.8 |  |  | 7778 |  |  |  | 12004.4 |  |  | 10526.633
Current APB |  | Apr 2013 |  |  |  |  | 8789.9 |  |  | 7588.1 |  |  |  | 11665.433 |  |  | 10269.567
Prior Annual SAR |  | Dec 2014 |  |  |  |  | 8414.567 |  |  | 7366.8 |  |  |  | 13222.6 |  |  | 12005.733
Current Estimate |  | Dec 2015 |  |  |  |  | 8609.767 |  |  | 7492.667 |  |  |  | 13565.167 |  |  | 12250.033
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ |  | Qty |  | Sch | Eng |  | Est |  | Oth | Spt |  | Total
11633.467 2145.467 0.000 279.833 -27.067 -469.433 0.000 2.900 1931.700 13565.167

## Table 51
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [9 empty] | APUC Current Estimate
| Econ | Qty | Sch | Eng |  | Est | Oth |  | Spt | Total
10325.800 2113.300 0.000 222.467 132.967 -547.400 0.000 2.900 1924.234 12250.033
SAR Baseline History
Item |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  | N/A |  |  | N/A |  |  | N/A |  |  |  | N/A
Milestone B |  | N/A |  |  | Apr 2004 |  |  | N/A |  |  |  | Apr 2004
Milestone C |  | N/A |  |  | Mar 2017 |  |  | N/A |  |  |  | Oct 2017
IOC |  | N/A |  |  | Sep 2015 |  |  | N/A |  |  |  | Oct 2017
Total Cost (TY $M) |  | N/A |  |  | 34900.4 |  |  | N/A |  |  |  | 40695.5
Total Quantity |  | N/A |  |  | 3 |  |  | N/A |  |  |  | 3
PAUC |  | N/A |  |  | 11633.467 |  |  | N/A |  |  |  | 13565.167

## Table 52
Unit Cost Report
Item |  | BY 2000 $M | BY 2000 $M |  | % Change
|  | Current UCR Baseline (Apr 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2263.4 |  |  | 2092.7
Quantity | 3 |  |  | 3
Unit Cost | 754.467 |  |  | 697.567 |  | -7.54
Average Procurement Unit Cost
Cost | 1593.4 |  |  | 1262.7
Quantity | 3 |  |  | 3
Unit Cost | 531.133 |  |  | 420.9 |  | -20.75
Item |  | BY 2000 $M | BY 2000 $M |  | % Change
|  | Original UCR Baseline (Apr 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2263.4 |  |  | 2092.7
Quantity | 3 |  |  | 3
Unit Cost | 754.467 |  |  | 697.567 |  | -7.54
Average Procurement Unit Cost
Cost | 1593.4 |  |  | 1262.7
Quantity | 3 |  |  | 3
Unit Cost | 531.133 |  |  | 420.9 |  | -20.75

## Table 53
Unit Cost History
Item |  |  | Date |  | BY 2000 $M | [5 empty] | TY $M
[5 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  | Apr 2013 |  |  | 754.467 |  |  | 531.133 |  |  |  | 1071.867 |  |  | 816.7
APB as of January 2006 |  | N/A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Revised Original APB |  | N/A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  | N/A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Current APB |  | Apr 2013 |  |  | 754.467 |  |  | 531.133 |  |  |  | 1071.867 |  |  | 816.7
Prior Annual SAR |  | Dec 2014 |  |  | 718 |  |  | 460.267 |  |  |  | 1097.8 |  |  | 797.3
Current Estimate |  | Dec 2015 |  |  | 697.567 |  |  | 420.9 |  |  |  | 1042.333 |  |  | 715.8
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [11 empty] | PAUC Current Estimate
| Econ | Qty | Sch | Eng | Est | Oth |  |  | Spt | Total
393.900 164.967 0.000 0.000 0.000 483.466 0.000 0.000 648.433 1042.333

## Table 54
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [10 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt |  | Total
257.100 156.400 0.000 0.000 0.000 302.300 0.000 0.000 458.700 715.800
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  | Sep 2016 |  |  |  | N/A |  |  | Oct 2017
Total Cost (TY $M) |  |  | N/A |  |  | 1181.7 |  |  |  | N/A |  |  | 3127
Total Quantity |  |  | N/A |  |  | 3 |  |  |  | N/A |  |  | 3
PAUC |  |  | N/A |  |  | 393.9 |  |  |  | N/A |  |  | 1042.333

## Table 55
Cost Variance
CVN 78
Summary TY $M
Item | RDT&E | Procurement | MILCON | Acq O&M | Total
SAR Baseline (Development Estimate) | 3923 | 30977.4 | -- | -- | 34900.4
Previous Changes
Economic | 100.7 | 6291 | 0.3 | -0.2 | 6391.8
Quantity | -- | -- | -- | -- | --
Schedule | 172.1 | 667.4 | -- | -- | 839.5
Engineering | -480.1 | 398.9 | -- | -- | -81.2
Estimating | -192 | -2317.5 | 35.9 | 90.9 | -2382.7
Other | -- | -- | -- | -- | --
Support | -- | -- | -- | -- | --
Subtotal | -399.3 | 5039.8 | 36.2 | 90.7 | 4767.4
Current Changes
Economic | -3.4 | 48.9 | -0.1 | -0.8 | 44.6
Quantity | -- | -- | -- | -- | --
Schedule | -- | -- | -- | -- | --
Engineering | -- | -- | -- | -- | --
Estimating | 315.1 | 675.3 | 0.1 | -16.1 | 974.4
Other | -- | -- | -- | -- | --
Support | -- | 8.7 | -- | -- | 8.7
Subtotal | 311.7 | 732.9 | -- | -16.9 | 1027.7
Total Changes | -87.6 | 5772.7 | 36.2 | 73.8 | 5795.1
CE - Cost Variance | 3835.4 | 36750.1 | 36.2 | 73.8 | 40695.5
CE - Cost & Funding | 3835.4 | 36750.1 | 36.2 | 73.8 | 40695.5

## Table 56
Summary BY 2000 $M
Item | RDT&E | Procurement | MILCON | Acq O&M | Total
SAR Baseline (Development Estimate) | 3490.6 | 24235 | -- | -- | 27725.6
Previous Changes
Economic | -- | -- | -- | -- | --
Quantity | -- | -- | -- | -- | --
Schedule | 120.2 | -- | -- | -- | 120.2
Engineering | -352.4 | 187.7 | -- | -- | -164.7
Estimating | -208.9 | -2322.3 | 27.3 | 66.5 | -2437.4
Other | -- | -- | -- | -- | --
Support | -- | -- | -- | -- | --
Subtotal | -441.1 | -2134.6 | 27.3 | 66.5 | -2481.9
Current Changes
Economic | -- | -- | -- | -- | --
Quantity | -- | -- | -- | -- | --
Schedule | -- | -- | -- | -- | --
Engineering | -- | -- | -- | -- | --
Estimating | 220 | 371.2 | 0.1 | -12.1 | 579.2
Other | -- | -- | -- | -- | --
Support | -- | 6.4 | -- | -- | 6.4
Subtotal | 220 | 377.6 | 0.1 | -12.1 | 585.6
Total Changes | -221.1 | -1757 | 27.4 | 54.4 | -1896.3
CE - Cost Variance | 3269.5 | 22478 | 27.4 | 54.4 | 25829.3
CE - Cost & Funding | 3269.5 | 22478 | 27.4 | 54.4 | 25829.3
Previous Estimate: December 2014

## Table 57
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -3.4
Adjustment for current and prior escalation. (Estimating) +1.2 +1.5
Revised estimate for CVN 78 Class (Ford Class Design) for the identification and development of initiatives to reduce construction costs. (Estimating)
+110.8 +161.7
Revised estimate for CVN 78 shock testing. (Estimating) +68.7 +97.2
Congressional increase in FY 2016 for CVN 78 shock testing. (Estimating) +37.2 +50.0
Congressional reduction in FY 2016 for CVN 78 due to program under-execution. (Estimating)
Congressional reduction in FY 2016 for CVN 79 due to program under-execution. (Estimating)
Congressional reduction in FY 2016 to CVN 80 for radar integration ahead of need.
-0.4 -0.5
-1.2 -1.6
-5.2 -7.0
(Estimating)
Revised estimate for CVN 78 non-pay, non-fuel purchase rate adjustments. (Estimating) | -1.9 | -2.6
Revised estimate for CVN 79 non-pay, non-fuel purchase rate adjustments. (Estimating) | -0.5 | -0.8
Revised estimate for CVN 80 non-pay, non-fuel purchase rate adjustments. (Estimating) | -1.6 | -2.2
Revised estimate for CVN 78 as a result of miscellaneous adjustments. (Estimating) | -1.2 | -1.4
Revised estimate for CVN 79 as a result of miscellaneous adjustments. (Estimating) | -0.3 | -0.4
Revised estimate for CVN 80 as a result of miscellaneous adjustments. (Estimating) | -0.5 | -0.6
Revised estimates in the outyears for Operational Test & Evaluation and Live Fire Test & | 13.6 | 19.9
Evaluation due to CVN 78 Delivery effort shift. (Estimating)
Revised estimate due to application of new outyear escalation indices. (Estimating) | 1.3 | 1.9
RDT&E Subtotal | 220 | 311.7
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 48.9
Adjustment for current and prior escalation. (Estimating) | -12.5 | -20.8
Revised estimate for CVN 78 Outfitting/Post Delivery (OF/PD). (Estimating) | 15.5 | 26.5
Revised estimate for CVN 79 OF/PD. (Estimating) | 3.1 | 6.2
Revised estimate for CVN 79 to fund to the PM's Estimate at Completion of $11.498B. | 83.9 | 150.4
(Estimating)
Revised estimate for CVN 79 to align with revised cost cap of $11.398B. (Estimating) -31.2 -38.4
Congressional Reduction in FY 2016 for CVN 79 for Ship's Signal Exploitation Equipment hardware and tech services cost growth. (Estimating)
Congressional reduction in FY 2016 for CVN 79 for High Frequency Radio cost growth. (Estimating)
Congressional reduction in FY 2016 for CVN 79 due to other electronics cost growth. (Estimating)
Congressional reduction in FY 2016 for CVN 79 for MK-29 launching system hardware cost growth. (Estimating)
Congressional reduction in FY 2016 for CVN 79 for Hull Mechnical & Engineering (HM&E) engineering services growth. (Estimating)
-0.9 -1.6
-1.6 -2.8
-2.5 -4.3
-1.7 -3.0
-2.0 -3.5

## Table 58
Congressional reduction in FY 2016 for CVN 79 due to program cost growth. (Estimating) -2.0 -3.5
Congressional reduction in FY 2016 for CVN 80 to defer non-nuclear long lead material. (Estimating)
-7.1 -12.3
Revised estimate for CVN 79 due to miscellaneous adjustments. (Estimating) +0.2 +0.2
Revised estimate for CVN 80 due to miscellaneous adjustments. (Estimating) +5.1 +9.4
Decrease to CVN 80 due to realized efficiencies from optimizing the build sequence and re- phasing funding into earlier years of execution. (Estimating)
-105.7 -252.0
Revised estimate for CVN 80 non-pay, non-fuel purchase rate adjustments. (Estimating) -63.4 -115.5
Revised estimate due to the addition of first year of Advance Procurement for CVN 81. (Estimating)
+509.1 +968.4
Revised estimate due to application of new outyear escalation indices. (Estimating) -15.1 -28.1
Increase in Other Support to procure CVN 78 classroom training equipment for new Contractor Furnished Equipment Systems. (Support)
+6.4 +8.7
Procurement Subtotal +377.6 +732.9
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.1
Adjustment for current and prior escalation. (Estimating) | 0.1 | 0.1
MILCON Subtotal | 0.1 | 0
Acq O&M | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.8
Adjustment for current and prior escalation. (Estimating) | 0.3 | 0.4
Revised estimate for CVN 78 Life Cycle training system development. (Estimating) | 2.9 | 3.9
Revised estimate for CVN 78 sustainment funding. (Estimating) | -13.3 | -18
Revised estimate due to miscellaneous adjustments. (Estimating) | -5 | -6.8
Revised estimate for CVN 78 outyear estimates. (Estimating) | 2.7 | 4
Revised estimate due to application of new outyear escalation indices. (Estimating) | 0.3 | 0.4
Acq O&M Subtotal | -12.1 | -16.9

## Table 59
Cost Variance
EMALS
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
410.4 771.3 -- 1181.7
Economic |  | 26.1 |  | 465.8 |  | -- |  | 491.9
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 444.3 |  | 1154.8 |  | 20.7 |  | 1619.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 470.4 |  | 1620.6 |  | 20.7 |  | 2111.7
Current Changes Economic |  | -0.4 |  | 3.4 |  | -- |  | 3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 78.5 |  | -247.9 |  | -- |  | -169.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 78.1 |  | -244.5 |  | -- |  | -166.4
Total Changes |  | 548.5 |  | 1376.1 |  | 20.7 |  | 1945.3
CE - Cost Variance |  | 958.9 |  | 2147.4 |  | 20.7 |  | 3127
CE - Cost & Funding |  | 958.9 |  | 2147.4 |  | 20.7 |  | 3127

## Table 60
Summary BY 2000 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
384.7 590.9 -- 975.6
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 369.7 |  | 789.9 |  | 18.8 |  | 1178.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 369.7 |  | 789.9 |  | 18.8 |  | 1178.4
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 56.8 |  | -118.1 |  | -- |  | -61.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 56.8 |  | -118.1 |  | -- |  | -61.3
Total Changes |  | 426.5 |  | 671.8 |  | 18.8 |  | 1117.1
CE - Cost Variance |  | 811.2 |  | 1262.7 |  | 18.8 |  | 2092.7
CE - Cost & Funding |  | 811.2 |  | 1262.7 |  | 18.8 |  | 2092.7
Previous Estimate: December 2014

## Table 61
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -0.4
Adjustment for current and prior escalation. (Estimating) |  | 0.3 | 0.4
Revised estimate to support Integrated Test & Evaluation efforts. (Estimating) |  | 53 | 73.3
Revised estimate to support land based testing efforts. (Estimating) |  | 2.5 | 3.3
Revised estimate due to miscellaneous adjustments. (Estimating) |  | 1 | 1.5
RDT&E Subtotal |  | 56.8 | 78.1
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A +3.4
Adjustment for current and prior escalation. (Estimating) -0.9 -1.4
Congressional reduction in FY 2016 due to CVN 79 EMALS program cost growth. (Estimating)
-23.1 -46.5
Revised estimate for CVN 80 EMALS. (Estimating) | -93.1 |  |  | -198
Revised estimate due to application of new outyear escalation indices. (Estimating) | -1 |  |  | -2
Procurement Subtotal | -118.1 |  |  | -244.5

## Table 62
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: CVN 78 DETAIL DESIGN & CONSTRUCTION (DD&C)
Contractor: Huntington Ingalls Industries (HII) Newport News Shipbuilding (NNS)
Contractor Location: 4101 Washington Avenue
Newport News, VA 23607-2734
Contract Number: N00024-08-C-2110
Contract Type: Cost Plus Award Fee (CPAF), Cost Plus Incentive Fee (CPIF), Cost Plus Fixed Fee (CPFF)
Award Date: September 10, 2008
Definitization Date: September 10, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
4910.5 N/A 1 6063.0 N/A 1 6928.3 6911.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the award of a new contract structure for Non-Recurring Engineering (NRE) and adjudicated change orders, procurement of special tooling and test equipment, and NRE associated with design and integration of developmental systems.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) |  |  |  | -1063.1 |  |  |  | -79.5
Previous Cumulative Variances |  |  |  | -876.7 |  |  |  | -67.2
Net Change |  |  |  | -186.4 |  |  |  | -12.3

## Table 63
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to material cost growth (21%), labor inefficiencies (32%), Overhead degradation (49%), and Facilities Capital Cost of Money (FCCM) improvement (-2%). The material variances are attributed to impacts associated with a "first of class" specification on contractor furnished direct material costs (e.g. valves, electrical components), and increases in vendor services cost for supporting completion of new developmental systems (e.g. advanced weapons elevators, plasma arc waste disposal system). Labor inefficiencies are the result of unanticipated challenges with vendor equipment (e.g. advanced weapons elevators, oxygen plant), design changes (e.g. advanced weapons elevator, EMALS), and producibility issues (e.g. thin plate steel, JP-5 corrosion resistant steel piping, weld distortion, and the increased use of temporary structures and rigging). Additionally, increased supervision and additional recurring engineering costs have been required to manage the above challenges. Contributing to the Cost Variance (CV) are schedule impacts due to planning/budgeting integration efforts to accurately apply distributed budgets to both current and future work.
The unfavorable net change in the schedule variance is due to unanticipated challenges with completing developmental systems, and the complexity of managing and integrating a large volume of work. Although shipbuilder actions to resolve “first of class” issues have retired some technical and schedule risk, HII-NNS was unable to retire all schedule risk, resulting in a four month delay to the launch of CVN 78, with associated impact to delivery. The Navy agreed to delay the delivery date accordingly while HII-NNS has increased material funds to facilitate additional Leased Labor for system and compartment finalization. Contributing to the Schedule Variance (SV) are schedule impacts due to planning/budgeting integration efforts to accurately apply distributed budgets to both current and future work.
Notes
The Program Manager's Estimated Price at Completion (PMEPAC) of $6,911M exceeds the current Target Price of
$6,063M by $848M. This total includes $740M of contractor performance based variance and $108M of authorized work that has not yet been adjudicated. Both the PMEPAC and the current cumulative cost variance include this $108M of authorized unadjudicated work. Upon adjudication, this work will be moved to target leaving a Price Variance at Completion of $740M. The Cost VAC has increased to $1,018M for the reasons described above. The government liability for this cost variance is $740M based on share line ratios which reduce the contractor's target fee as cost increases.

## Table 64
Contract Identification
Appropriation: Procurement
Contract Name: CVN 79 Construction Preparation (CP)
Contractor: Huntington Ingalls Industries (HII) Newport News Shipbuilding (NNS)
Contractor Location: 4101 Washington Avenue
Newport News, VA 23607-2734
Contract Number: N00024-09-C-2116
Contract Type: Cost Plus Fixed Fee (CPFF), Cost Plus Incentive Fee (CPIF)
Award Date: January 15, 2009
Definitization Date: December 08, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
373.5 N/A N/A 4237.0 N/A N/A 4298.6 4295.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to award of CVN 79 CP contract extensions for FY 2011 through FY 2014 efforts, a modification awarded on June 5, 2015 which includes the remaining component and steel fabrication and, multiple modifications for procurement of additional material to support the CVN 79 procurement strategy.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +57.3 +3.5
Previous Cumulative Variances +12.2 +0.4
Net Change +45.1 +3.1
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to meeting performance challenges in the manufacturing and assembly process areas that were achieved through improvement initiatives.
The favorable net change in the schedule variance is due to the shipbuilder's execution of the material procurement plan focused on shipset procurements where possible. There was a slight degradation associated with labor performance as the shipbuilder's primary focus has been on achieving cost challenges. Mitigation plans are in place to address schedule variances in fabrication, assembly, and engineering.
Notes
A $941M modification was awarded on June 5, 2015 which includes the remaining component and steel fabrication, and selected construction unit assemblies already underway where proven performance results were available. As of December 31, 2015, the CP contract is 59.1% complete based on dollars.

## Table 65
Contract Identification
Appropriation: Procurement
Contract Name: CVN 79 Detail Design & Construction
Contractor: Huntington Ingalls Industries (HII) Newport News Shipbuilding (NNS)
Contractor Location: 4101 Washington Ave
Newport News, VA 23607
Contract Number: N00024-15-C-2114
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 05, 2015
Definitization Date: June 05, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
3352.6 N/A 1 3352.6 N/A 1 3352.6 3296.7
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -4.9 +13.1
Previous Cumulative Variances -- --
Net Change -4.9 +13.1
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to initial challenges in ship integration and engineering, and material charges for support, maintenance and facilities with only 2.6% of contract complete.
The favorable cumulative schedule variance is due to efficient performance in planning and engineering, with only 2.6% of contract complete.
Notes
This is the first time this contract is being reported.
The Navy awarded a FPIF contract in the amount of $3.35B for the CVN 79 Detail Design & Construction effort. As of December 31, 2015, the DD&C contract is 2.6% complete based on dollars.

## Table 66
Contract Identification
Appropriation: RDT&E
Contract Name: EMALS Basic Ordering Agreement Logistics Development Order
Contractor: General Atomics Electromagnetic Systems Group
Contractor Location: San Diego, CA 92121-1122 Contract Number: N68335-11-G-0003 Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: August 12, 2012
Definitization Date: August 12, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
44.5 N/A 1 44.6 N/A 1 46.8 51.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications to incorporate changes to logistics products due to two EMALS specification change notices.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -1.6 -1.5
Previous Cumulative Variances +0.6 -1.8
Net Change -2.2 +0.3
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to technical manual development which experienced reduced efficiency due to newly hired, inexperienced personnel. Rework of maintenance task analyses and technical manuals due to engineering changes were also contributors.
The favorable net change in the schedule variance is due to technical manual development. Past due fault isolation data module development tasks were completed.
Notes
The Program Manager's Estimated Price at Completion (PMEPAC) currently exceeds the Current Contract Price by $6.6M. An Integrated Baseline Review (IBR) was conducted in December 2013 that yielded 27 findings. A PMEPAC of $63.3M was established based on the cost and schedule risks associated with the IBR findings. General Atomics took corrective action to address all IBR findings and the IBR was closed in December 2014. Naval Air Systems Command subsequently conducted a Schedule Risk Assessment and an updated Estimate at Completion the results of which represent a $12.1M reduction in the PMEPAC to $51.2M. This order is currently 81.5% complete.

## Table 67
Deliveries and Expenditures
CVN 78
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 3 | 0%
Total Program Quantity Delivered | 0 | 0 | 3 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
40695.5
19132.8
47.01%
32
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
20
62.5%
23661.4
58.14%
The above data is current as of February 25, 2016.
EMALS
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 3 | 0%
Total Program Quantity Delivered | 0 | 0 | 3 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
3127
1215
38.86%
24
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
17
70.83%
2059.9
65.87%
The above data is current as of February 25, 2016.

## Table 68
Operating and Support Cost
CVN 78
Cost Estimate Details
Date of Estimate: March 02, 2016
Source of Estimate: POE
Quantity to Sustain: 3
Unit of Measure: Ship
Service Life per Unit: 50.00 Years
Fiscal Years in Service: FY 2017 - FY 2077
The current APB Objective/Threshold values and current estimate reflects Total O&S costs for three ships in accordance with the current Program of Record. The CVN 78 Class Program is planned for a total of 11 ships over a 50 year service life.
O&S costs are developed at the ship level, on an annual cost per ship basis by cost category and appropriation, with total and annual average cost over the ship's expected service life. Costs are estimated for all categories listed in the CAPE Operating and Support Cost Estimating Guide using historical data from operating carrier classes and the Chief of Naval Operations (OPNAV) "Maintenance" Notices. Maintenance and Personnel costs are the major contributors to the total O&S Program.
Sustainment Strategy
Sustainment strategy includes nuclear aircraft carrier certified Naval Shipyards (Newport News Shipyard (NNSY), Puget Sound Naval Shipyard (PSNSY) & Intermediate Maintenance Facility (IMF)) and/or Huntington-Ingalls, Inc - Newport News Shipyard (HII-NNS) for Depot-level Maintenance in concert with regional multi-ship/multi-option (MSMO) contractors, Intermediate-level activities (e.g., Mid-Atlantic Regional Maintenance Center (MARMC), Southwest Regional Maintenance Center (SWRMC)), Organizational-level maintenance strategies, and the employment of existing shore support to the maximum extent possible.
Antecedent Information
The CVN 68 O&S costs were derived from requirements, actual returns, and the Naval Visibility and Management of Operating and Support Costs (VAMOSC) database, with the primary focus using requirements. Unit Level Manpower (1.0) was based on authorized billets (3,291) as detailed in the CVN 68 Ship Manpower Document (SMD); the billets were multiplied against the OSD composite rates for calculating the unit level manpower. Indirect Support (6.0) was based on authorized billets (3,291) as detailed in the CVN 68 SMD; the billets were multiplied against the Naval Center for Cost Analysis (NCCA) Manpower Cost Estimating Tool for Enhanced Online Reporting (METEOR) rates for calculating the indirect support cost. Depot Maintenance (3.3) was derived from OPNAV Note 4700 (dated June 8, 2015).
Unit Operations (2.0), Intermediate Maintenance (3.2), Sustaining Support (4.0), and Continuing System Improvements (5.0) were derived from VAMOSC, with data pulled from FY 2000 through FY 2010; using full year data and excluding CVN 73 which was a forward deployed ship starting in 2008.

## Table 69
Annual O&S Costs BY2000 $M
Cost Element |  | CVN 78 Average Annual Cost Per Ship | [5 empty] | CVN 68 Class (Antecedent) Average Annual Cost Per Ship
Unit-Level Manpower |  | 129.02 | [5 empty] | 162.738
Unit Operations |  | 10.13 | [5 empty] | 10.241
Maintenance |  | 101.286 | [5 empty] | 130.099
Sustaining Support |  | 10.853 | [5 empty] | 11.818
Continuing System Improvements |  | 20.163 | [5 empty] | 23.6
Indirect Support |  | 119.52 | [5 empty] | 151.083
Other |  | 0 | [5 empty] | 0
Total |  | 390.972 | [5 empty] | 489.579
Item | Total O&S Cost $M
| CVN 78 | [7 empty] | CVN 68 Class (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 55600 |  |  | 61160 |  |  | 58645.8 |  | 244789.7
Then Year | 251600 |  |  | N/A |  |  | 180995 |  | N/A
Total O&S cost for 11 ships would be $215,034.69M BY dollars/$1,041,643.00M in TY dollars.
Equation to Translate Annual Cost to Total Cost
Total Cost = Average Annual Cost Per Ship * Number of Ships * Service Life = $390.972 * 3 * 50 = $58,645.83M
O&S Cost Variance
Category |  |  | BY 2000 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
48009.8
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 1425.0 Updated to reflect updated OPNAV 4700 Note dated June 08, 2015.
Cost Data Update 321.2 Update to reflect updated VAMOSC data from FY 2000-FY 2014.
Labor Rate 7539.8 Updated to reflect revised labor and health benefit rates. Energy Rate 0.0
Technical Input 1350.0 Added software maintenance costs for Advanced Arresting Gear (AAG), Ship Self Defense System (SSDS), Enterprise Air Surveillance Radar (EASR), and Machinery Control and Monitoring System (MCMS).
Other 0.0
Total Changes 10636.0

## Table 70
Current Estimate 58645.8
Disposal Estimate Details
Date of Estimate: July 18, 2007
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2000 $M): Total costs for disposal of all Ship are 1612.2
The current estimate for disposal costs for the CVN 78 Class ships is $5,911.4M for eleven ships in BY 2000 dollars. Disposal costs include disposal of EMALS.

## Table 71
EMALS
Cost Estimate Details
Date of Estimate: March 02, 2016
Source of Estimate: POE
Quantity to Sustain: 3
Unit of Measure: Ship
Service Life per Unit: 50.00 Years
Fiscal Years in Service: FY 2017 - FY 2077
The current APB Objective/Threshold values and current estimate reflects Total O&S costs for three shipsets in accordance with the current Program of Record. The CVN 78 Class Program is planned for a total of 11 shipsets over a 50 year service life.
O&S Costs are developed at the ship level, on an annual cost per ship basis by cost category and appropriation, with total and annual average cost over the ship's expected service life. Costs are estimated for all categories listed in the CAPE Operating and Support Cost Estimating Guide using historical data from operating carrier classes and
the OPNAV "Maintenance" Notices. Maintenance and Personnel costs are the major contributors to the total O&S Program.
Sustainment Strategy
EMALS will be under a blended support and sustainment scenario by the Original Equipment Manufacturer (OEM), General Atomics (GA), and Navy support from Naval Air Systems Command (NAVAIR) PMA 251 as is applicable. The intention is for GA to provide support and have the shipyards and the Navy to provide the both industrial level support, (i.e. cranes, lifts, power (including step down backup) and air) as well as shop modifications, equipment to support motor repairs, equipment storage areas and temperature controls.
The final EMALS System Maintenance Plan review was conducted in November 2015. The delivery of final maintenance planning information is currently projected to be 3rd quarter FY 2016 as part of the submission of Provisioning Technical Data. Depot Planning to support out year requirements is slated to begin during FY 2018 with an estimated completion date of FY 2019/2020.
Antecedent Information
EMALS is specifically designed to meet the requirements of the CVN 78 class. The advanced technologies and capabilities, and unique ship interface requirements of EMALS do not exist in any legacy launcher systems. As such, there are no comparable antecedent systems.

## Table 72
Annual O&S Costs BY2000 $M
Cost Element |  | EMALS Average Annual Cost Per Ship | [5 empty] | No Antecedent (Antecedent)
Unit-Level Manpower |  | 4.453 | [5 empty] | 0
Unit Operations |  | 0 | [5 empty] | 0
Maintenance |  | 5.995 | [5 empty] | 0
Sustaining Support |  | 1.494 | [5 empty] | 0
Continuing System Improvements |  | 3.658 | [5 empty] | 0
Indirect Support |  | 1.704 | [5 empty] | 0
Other |  | 0 | [5 empty] | 0
Total |  | 17.304 | [5 empty] | --
Item | Total O&S Cost $M
| EMALS | [7 empty] | No Antecedent (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 2574.3 |  |  | 2831.7 |  |  | 2595.6 |  | 0
Then Year | 6422.6 |  |  | N/A |  |  | 7832 |  | N/A
Total O&S cost for 11 Shipsets would be $9,517.0M in BY dollars/$44,956.0M in TY dollars.
Equation to Translate Annual Cost to Total Cost
Total Cost = Average Annual Cost Per Shipset * number of Shipsets * Service Life = $17.304M * 3 * 50 = $2,595.6M
O&S Cost Variance
Category |  |  | BY 2000 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
2574.3
Programmatic/Planning Factors 21.3 Revised to reflect movement of depot stand-up from FY 2017 to FY 2021.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 21.3
Current Estimate 2595.6

## Table 73
Disposal Estimate Details
Date of Estimate: July 18, 2007
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2000 $M): Total costs for disposal of all Ship are 0.0
EMALS disposal costs are included in the CVN 78 Class Disposal Cost.