## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-101
H-1 Upgrades (4BW/4BN) (H-1 Upgrades)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 16
Cost and Funding 17
Low Rate Initial Production 26
Foreign Military Sales 27
Nuclear Costs 27
Unit Cost 28
Cost Variance 31
Contracts 34
Deliveries and Expenditures 39
Operating and Support Cost 40

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
H-1 Upgrades (4BW/4BN) (H-1 Upgrades)
DoD Component
Navy
Responsible Office
Col Steven Girard
PMA-276 USMC Light/Attack Helicopter
Program Executive Officer - Air, Anti-Submarine Warfare, Assault & Special Mission
48202 Bronson Road, 2nd Floor Patuxent River, MD 20670-1547
steven.girard@navy.mil
Phone: 301-757-5534
Fax: 301-342-3788
DSN Phone: 757-5534
DSN Fax: 342-3788
Date Assigned: January 31, 2013
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 22, 2008
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated February 11, 2011

## Table 6
Mission and Description
The mission of the AH-1Z attack helicopter is to provide rotary wing close air support, anti-armor, armed escort, armed/visual reconnaissance and fire support coordination capabilities under day/night and adverse weather conditions for the United States Marine Corps. The mission of the UH-1Y utility helicopter is to provide command, control and assault support under day/night and adverse weather conditions. Both the AH-1Z and UH-1Y aircraft incorporate state-of-the-art designs, which serve to improve capability, lethality, and survivability. Major modifications include a new four-bladed rotor system with semi-automatic blade fold of the new composite rotor blades, new performance matched transmissions, a new four-bladed tail rotor and drive system, upgraded landing gear, and pylon structural modifications. The H-1 Upgrades aircraft have increased maneuverability, speed, and payload capability. Both aircraft have fully integrated common cockpits/avionics that reduce operator workload and improve situational awareness, thus increasing safety.

## Table 7
Executive Summary
Both the UH-1Y and AH-1Z continue to meet all KPPs. The UH-1Y has completed Operation Enduring
Freedom deployments, amassing over 162,000 flight hours. All West coast Marine Expeditionary Units (MEU) deploy with UH-1Y and AH-1Z aircraft. East coast MEUs deploy with UH-1Y and AH-1W aircraft.
Production of H-1 Upgrades aircraft continues at Bell Helicopter with final assembly and delivery occurring in Amarillo, Texas. There are 243 aircraft (Lots 1-12) on contract, which includes 148 UH-1Y, 37 AH-1Z remanufactured and 58 AH-1Z Build New (ZBN) aircraft. Lot 12 (FY 2015) also includes the first three of 12 AH-1Z Build New aircraft for Pakistan under FMS case PK-P-SBO. As of January 25, 2016, 174 production aircraft (127 UH-1Ys, 37 remanufactured AH-1Zs, and 10 ZBNs) have been delivered to the Fleet. All remaining AH-1Z deliveries are Build New aircraft.
The program office continues to make progress on improving material availability, reliability, as well as depot capability. Corrective action plans for readiness degraders are maturing & progressing towards fielding, or fielded & being validated for effectiveness. Depot capability continues to increase across the Fleet Readiness Centers.
A Letter of Offer and Acceptance (LOA) was signed by Pakistan on July 10, 2015 for 12 AH-1Z helicopters, initial support, and training. The LOA value is $681M, which includes the total package approach.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone II | Sep 1996 | Sep 1996 | Mar 1997 | Oct 1996
Preliminary Design Review Complete | Jul 1997 | Jul 1997 | Jan 1998 | Jun 1997
Critical Design Review Complete | Jul 1998 | Jul 1998 | Jan 1999 | Sep 1998
DAB LRIP Review | Aug 2003 | Aug 2003 | Feb 2004 | Oct 2003
CAE LRIP #2 Review | Feb 2005 | Feb 2005 | Aug 2005 | Mar 2005
Integrated Testing Complete | Jul 2005 | Jul 2005 | Jan 2006 | Jan 2006
CAE LRIP #3 Review | May 2006 | May 2006 | Nov 2006 | May 2006
OPEVAL Testing Complete (AH-1Z) | Nov 2006 | Nov 2006 | May 2007 | Jan 2007
OPEVAL Testing Complete (UH-1Y) | Nov 2006 | Nov 2006 | May 2007 | Jan 2007
DAE LRIP #4 Review | Feb 2007 | Feb 2007 | Aug 2007 | Jul 2007
OPEVAL Phase II Testing Complete (UH-1Y) | Mar 2008 | Mar 2008 | Sep 2008 | Apr 2008
IOC (UH-1Y) | Mar 2008 | Mar 2008 | Sep 2008 | Aug 2008
Milestone III | May 2008 | May 2008 | Nov 2008 | Sep 2008
DAE LRIP #5 Review (AH-1Z) | Sep 2008 | Sep 2008 | Mar 2009 | Sep 2008
LRIP #6 Review (AH-1Z) | Aug 2009 | Aug 2009 | Feb 2010 | Feb 2009
LRIP #7 Review (AH-1Z) | Mar 2010 | Mar 2010 | Sep 2010 | Apr 2010
OPEVAL Phase II Testing Complete (AH-1Z) | Jul 2010 | Jul 2010 | Jan 2011 | Jul 2010
Milestone III (AH-1Z) | Oct 2010 | Oct 2010 | Apr 2011 | Nov 2010
IOC (AH-1Z) | Mar 2011 | Mar 2011 | Sep 2011 | Feb 2011
Navy Support Date (AH-1Z) | Mar 2012 | Sep 2015 | Mar 2016 | Mar 2016
Navy Support Date (UH-1Y) | Mar 2012 | Sep 2015 | Mar 2016 | Mar 2016
(Ch-1)
(Ch-1)
Change Explanations
(Ch-1) The Navy Support Date (AH-1Z and UH-1Y) Current Estimate has changed from Sep 2015 to Mar 2016 to reflect the Threshold requirement.
Acronyms and Abbreviations
CAE - Component Acquisition Executive OPEVAL - Operational Evaluation

## Table 11
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
4BW (AH-1W/AH-1Z)
MFHBA (hrs)
35 | 35 | 24 | 63.8 | 63.8
MMH/FH (hrs)
3.6 | 3.6 | 4.3 | 2.5 | 2.5
Cruise Speed (kts)
165 | 165 | 135 | 139 | 139
Payload (Hot Day) (lbs)
3500 lbs | 3500 lbs | 2500 lbs 6 Wing Stations 4 Universal Under Wing Stations | 3429 | 3429
Weapon Stations
Universal Mounts
6 | 6 | 4 | 4 | 4
Precision Guided Munitions
16 | 16 | 12 | 16 | 16
Maneuverability/Agility (G's)
-0.5 to +2.5 | -0.5 to +2.5 | -0.5 to +2.5 | -0.5 to +2.5 | -0.5 to +2.5
Mission Radius (NM)
200 NM | 200 NM | 110 NM | 135 NM x 1 | 135 NM x 1
Shipboard Compatibility
Fully compatible to include blade fold. | Fully compatible to include blade fold. | Fully compatible to include blade fold. | Fully compatible to include blade fold. | Fully compatible to include blade fold.
Interoperability
The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net Centric military | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric military | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net Centric military | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net Centric military
(Ch-1)
(Ch-1)

## Table 12
operations to include: | operations to include: | transition to Net- | operations to include: | operations to include:
1) DISR mandated | 1) DISR-mandated | Centric military | 1) DISR mandated | 1) DISR mandated
GIG IT standards and | GIG IT standards and | operations to include: | GIG IT standards and | GIG IT standards and
profiles identified in | profiles identified in | 1) DISR-mandated | profiles identified in | profiles identified in
the TV-1, 2) DISR | the TV-1, 2) DISR- | GIG IT standards and | the TV-1, 2) DISR | the TV-1, 2) DISR
mandated GIG KIPs | mandated GIG KIPs | profiles identified in | mandated GIG KIPs | mandated GIG KIPs
identified in the KIP | identified in the KIP | the TV-1, 2) DISR- | identified in the KIP | identified in the KIP
declaration table, 3) | declaration table, 3) | mandated GIG KIPs | declaration table, 3) | declaration table, 3)
NCOW RM | NCOW RM | identified in the KIP | NCOW RM | NCOW RM
Enterprise Services | Enterprise Services | declaration table, 3) | Enterprise Services | Enterprise Services
4) Information | 4) Information | NCOW RM | 4) Information | 4) Information
assurance | assurance | Enterprise Services | assurance | assurance
requirements | requirements | 4) Information | requirements | requirements
including availability, | including availability, | assurance | including availability, | including availability,
integrity, authenticat- | integrity, authenticat- | requirements | integrity, | integrity,
ion, confidential-ity, | ion, confidenti-ality, | including availability, | authentication, | authentication,
and non-repudiation, | and non-repudiation, | integrity, authenticat- | confidentiality, and | confidentiality, and
and issuance of an | and issuance of an | ion, confidential-ity, | non-repudiation, and | non-repudiation, and
ATO by the DAA, and | ATO by the DAA, and | and non-repudiation, | issuance of an ATO | issuance of an ATO
5) Operationally | 5) Operationally | and issuance of an | by the DAA, and 5) | by the DAA, and 5)
effective information | effective information | IATO by the DAA, | Operationally | Operationally
exchanges; and | exchanges; and | and 5) Operationally | effective information | effective information
mission critical | mission critical | effective information | exchanges; and | exchanges; and
performance and | performance and | exchanges; and | mission critical | mission critical
information | information | mission critical | performance and | performance and
assurance attributes, | assurance attributes, | performance and | information | information
data correctness, | data correctness, | information | assurance attributes, | assurance attributes,
data availability, and | data availability, and | assurance attributes, | data correctness, | data correctness,
consistent data | consistent data | data correctness, | data availability, and | data availability, and
processing specified | processing specified | data availability, and | consistent data | consistent data
in the applicable joint | in the applicable joint | consistent data | processing specified | processing specified
and system | and system | processing specified | in the applicable joint | in the applicable joint
integrated | integrated | in the applicable joint | and system | and system
architecture views. | architecture views. | and system | integrated | integrated
|  | integrated | architecture views. | architecture views.
architecture views.
Force Protection (Seating)
Two AH-1Z pilot | Two AH-1Z pilot | Two AH-1Z pilot | Two AH-1Z pilot | Two AH-1Z pilot
seats that are | seats that are | seats that are | seats that are | seats that are
stroking, | stroking, | stroking, | stroking, | stroking,
crashworthy, and | crashworthy, and | crashworthy, and | crashworthy, and | crashworthy, and
capable of sustaining | capable of sustaining | capable of sustaining | capable of sustaining | capable of sustaining
20Gs longitudinal, | 20Gs longitudinal, | 20Gs longitudinal, | 20Gs longitudinal, | 20Gs longitudinal,
20Gs vertical, and 10 | 20Gs vertical, and 10 | 20Gs vertical, and 10 | 20Gs vertical, and | 20Gs vertical, and
Gs laterally. | Gs laterally. | Gs laterally. | 10Gs laterally. | 10Gs laterally.
Survivability (Ballistic Tolerance/Hardening)
Airframe structure | Airframe structure | Airframe structure | Airframe structure | Airframe structure
and flight critical | and flight critical | and flight critical | and flight critical | and flight critical
systems shall be | systems shall be | systems shall be | systems shall be | systems shall be
ballistic tolerant/ | ballistic tolerant/ | ballistic tolerant/ | ballistic | ballistic
hardened against 23 | hardened against 23 | hardened against | tolerant/hardened | tolerant/hardened
mm HEI. | mm HEI. | 12.7 mm API. | against 12.7 mm | against 12.7 mm

## Table 13
|  |  | API. | API.
4BN (UH-1N/UH-1Y)
MFHBA (hrs)
40.2 | 40.2 | 33.1 | 56.6 | 56.6
MMH/FH (hrs)
2.9 | 2.9 | 3.9 | 2 | 2
Cruise Speed (kts)
165 | 165 | 140 | 155 | 155
Payload (Hot Day) (lbs)
4500 | 4500 | 2800 | 2982 | 2982
Weapon Stations
2 Univ. Mounts | 2 Univ. Mounts | 2 Hard Mounts | 2 Hard Mounts | 2 Hard Mounts
Maneuverability/Agility (G's)
-0.5 to +2.5 | -0.5 to +2.5 | -0.5 to +2.3 | -0.5 to +2.3 | -0.5 to +2.3
Mission Radius (NM)
200 NM | 200 NM | 110 NM | 130 NM | 130 NM
Shipboard Compatibility
Fully compatible to include blade fold. | Fully compatible to include blade fold. | Fully compatible to include blade fold. | Fully compatible to include blade fold. | Fully compatible to include blade fold.
Interoperability
The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net Centric military operations to include: 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability, | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric military operations to include: 1) DISR-mandated GIG IT standards and profiles identified in the TV-1, 2) DISR- mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability, | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for transition to Net- Centric military operations to include: 1) DISR-mandated GIG IT standards and profiles identified in the TV-1, 2) DISR- mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net Centric military operations to include: 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability, | The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net Centric military operations to include: 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability,
(Ch-2)
(Ch-2)

## Table 14
integrity, authenticat- | integrity, | requirements | integrity, | integrity,
ion, confidenti-ality, | authentication, | including availability, | authentication, | authentication,
and non-repudiation, | confidentiality, and | integrity, | confidentiality, and | confidentiality, and
and issuance of an | non-repudiation, and | authentication, | non-repudiation, and | non-repudiation, and
ATO by the DAA, and | issuance of an ATO | confidentiality, and | issuance of an ATO | issuance of an ATO
5) Operationally | by the DAA, and 5) | non-repudiation, and | by the DAA, and 5) | by the DAA, and 5)
effective information | Operationally | issuance of an IATO | Operationally | Operationally
exchanges; and | effective information | by the DAA, and 5) | effective information | effective information
mission critical | exchanges; and | Operationally | exchanges; and | exchanges; and
performance and | mission critical | effective information | mission critical | mission critical
information | performance and | exchanges; and | performance and | performance and
assurance attributes, | information | mission critical | information | information
data correctness, | assurance attributes, | performance and | assurance attributes, | assurance attributes,
data availability, and | data correctness, | information | data correctness, | data correctness,
consistent data | data availability, and | assurance attributes, | data availability, and | data availability, and
processing specified | consistent data | data correctness, | consistent data | consistent data
in the applicable joint | processing specified | data availability, and | processing specified | processing specified
and system | in the applicable joint | consistent data | in the applicable joint | in the applicable joint
integrated | and system | processing specified | and system | and system
architecture views. | integrated | in the applicable joint | integrated | integrated
| architecture views. | and system | architecture views. | architecture views.
integrated
architecture views.
Force Protection (Seating)
Two UH-1Y pilot | Two UH-1Y pilot | Two UH-1Y pilot | Two UH-1Y pilot | Two UH-1Y pilot
seats and ten UH-1Y | seats and ten UH-1Y | seats and ten UH-1Y | seats and ten UH-1Y | seats and ten UH-1Y
cabin seats that are | cabin seats that are | cabin seats that are | cabin seats that are | cabin seats that are
stroking, crash- | stroking, crash- | stroking, crash- | stroking, | stroking,
worthy, and capable | worthy, and capable | worthy, and capable | crashworthy, and | crashworthy, and
of sustain-ing 20Gs | of sustaining 20Gs | of sustaining 20Gs | capable of sustaining | capable of sustaining
longitudinal, 20Gs | longitudinal, 20Gs | longitudinal, 20Gs | 20Gs longitudinal, | 20Gs longitudinal,
vertical, and 10 Gs | vertical, and 10 Gs | vertical, and 10 Gs | 20Gs vertical, and | 20Gs vertical, and
laterally. | laterally. | laterally. | 10Gs laterally. | 10Gs laterally.
Survivability (Ballistic Tolerance/Hardening)
Airframe structure | Airframe structure | Airframe structure | Airframe structure | Airframe structure
and flight critical | and flight critical | and flight critical | and flight critical | and flight critical
systems shall be | systems shall be | systems shall be | systems shall be | systems shall be
ballistic | ballistic | ballistic | ballistic | ballistic
tolerant/hardened | tolerant/hardened | tolerant/hardened | tolerant/hardened | tolerant/hardened
against 23 mm HEI. | against 23 mm HEI. | against 12.7 mm API. | against 12.7 mm | against 12.7 mm
|  |  | API. | API.
Requirements Reference
UH-1Y CPD and AH-1Z CPD dated June 11, 2007 as modified by JROC Memorandum 195-08 dated October 14, 2008

## Table 15
Change Explanations
(Ch-1) The current estimate values for R&M have changed as follows based on the Naval Air Systems Command R&M Review Board #106 in December 2015: 4BW (AH-1W/AH-1Z) MFHBA from 57.8 to 63.8 and MMH/FH from 1.9 to 2.5.
(Ch-2) The current estimate values for R&M have changed as follows based on the Naval Air Systems Command R&M Review Board #106 in December 2015: 4BN (UH-1N/UH-1Y) MFHBA from 61.5 to 56.6 and MMH/FH from 2.4 to 2.0.
Acronyms and Abbreviations
API - Armor Piercing Incendiary ATO - Authority to Operate
DAA - Designated Approving Authority
DISR - DoD Information Technology Standards Registry
FRACAS - Failure Reporting, Analysis and Corrective Action System G's - Gravitational forces
GIG - Global Information Grid HEI - High Explosive Incendiary hrs - Hours
IATO - Interim Authority to Operate IT - Information Technology
KIP - Key Interface Protocol kts - Knots
lbs - Pounds
MFHBA - Mean Flight Hours Between Abort mm - Millimeter
MMH/FH - Maintenance Man Hours per Flight Hours NCOW - Net-Centric Operation and Warfare
NM - Nautical Miles
R&M - Reliability and Maintainability RM - Reference Model
TV-1 - Technical Standards Profile Univ. - Universal

## Table 16
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy 1319 05 0604245N
Project | Name
2279 H-1 Upgrades (Sunk)
Procurement
Appn |  |  | BA | PE
Navy |  | 1506 01 |  | 0206131M
|  | Line Item |  | Name
|  | 178 |  | H-1 Upgrades (UH-1Y/AH-1Z)
Navy |  | 1506 06 |  | 0206131M
|  | Line Item |  | Name
|  | 605 |  | Spares and Repair Parts | (Sunk)
Notes
Aircraft Procurement, Navy - BA 05 for Line Item 0532, PE 0206131M, is incorporated into the program as a subset of total O&S.
MILCON
Appn |  |  | BA | PE
Navy 1205 01 0216496M
Project Name
991 H-1 Y/Z Helicopter Gearbox Repair & Test Facility
(Sunk)

## Table 17
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2008 $M | [6 empty] | BY 2008 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 1799.2 |  |  | 1848.3 | 2033.1 |  |  | 1704.1 |  | 1644.1 |  |  | 1696.2 |  | 1537.1
Procurement |  | 9404.2 |  |  | 10088.4 | 11097.2 |  |  | 9894.6 |  | 10542.7 |  |  | 11022.1 |  | 10871.2
Flyaway |  | -- |  |  | -- | -- |  |  | 8348 |  | -- |  |  | -- |  | 9234.3
Recurring |  | -- |  |  | -- | -- |  |  | 7853.2 |  | -- |  |  | -- |  | 8716.4
Non Recurring |  | -- |  |  | -- | -- |  |  | 494.8 |  | -- |  |  | -- |  | 517.9
Support |  | -- |  |  | -- | -- |  |  | 1546.6 |  | -- |  |  | -- |  | 1636.9
Other Support |  | -- |  |  | -- | -- |  |  | 1300.9 |  | -- |  |  | -- |  | 1389.2
Initial Spares |  | -- |  |  | -- | -- |  |  | 245.7 |  | -- |  |  | -- |  | 247.7
MILCON |  | 0 |  |  | 16.3 | 17.9 |  |  | 16 |  | 0 |  |  | 17.6 |  | 17.6
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 11203.4 |  |  | 11953 | N/A |  |  | 11614.7 |  | 12186.8 |  |  | 12735.9 |  | 12425.9
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The estimate recommendation aims to provide sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule, and programmatic risk and external interference. It is consistent with average resource expenditures on historical efforts of similar size, scope, and complexity and represents a 50% confidence level.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 4 |  |  |  | 4 |  |  |  |  | 4
Procurement |  |  | 349 |  |  |  | 349 |  |  |  |  | 347
Total |  |  | 353 |  |  |  | 353 |  |  |  |  | 351
Quantity Notes
The four RDT&E aircraft include two UH-1Ys and two AH-1Zs. The 347 Procurement aircraft include 37 AH-1W helicopters remanufactured into AH-1Zs, 149 AH-1Z Build New models, 10 UH-1N helicopters remanufactured into UH-1Ys, and 151 new UH-1Y models. Program currently funded to 347 aircraft; Program of Record remains 349.

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 1537.1 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1537.1
Procurement | 7404.9 | 840.8 |  |  | 817 | 887.7 | 908.8 |  | 6 |  | 6 |  | 0 |  | 10871.2
MILCON | 17.6 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 17.6
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 8959.6 | 840.8 |  |  | 817 | 887.7 | 908.8 |  | 6 |  | 6 |  | 0 |  | 12425.9
PB 2016 Total | 8963.1 | 857 |  |  | 917.7 | 899.5 | 921.6 |  | 16.9 |  | 16.3 |  | 0 |  | 12592.1
Delta | -3.5 | -16.2 |  |  | -100.7 | -11.8 | -12.8 |  | -10.9 |  | -10.3 |  | 0 |  | -166.2
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 4 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 4
Production | 0 |  | 240 |  | 29 | 24 | 27 |  | 27 | 0 |  | 0 |  | 0 |  | 347
PB 2017 Total | 4 |  | 240 |  | 29 | 24 | 27 |  | 27 | 0 |  | 0 |  | 0 |  | 351
PB 2016 Total | 4 |  | 240 |  | 28 | 27 | 27 |  | 27 | 0 |  | 0 |  | 0 |  | 353
Delta | 0 |  | 0 |  | 1 | -3 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | -2

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67.9
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.3
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 116.7
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 178.5
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.2
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 167.4
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 232.9
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 99.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.7
Subtotal |  | 4 | -- |  | -- |  | -- |  | -- |  | -- |  | 1537.1

## Table 20
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.3
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 82
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 97.4
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.1
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 208.3
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 159.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 190.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 261.5
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 179
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.6
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.4
Subtotal |  | 4 | -- |  | -- |  | -- |  | -- |  | -- |  | 1704.1

## Table 21
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | 6 |  | 6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2004 |  | 9 | 197.8 |  | -- |  | 23.8 |  | 221.6 |  | 105.9 |  | 327.5
2005 |  | 7 | 136.9 |  | -- |  | 18.7 |  | 155.6 |  | 78.3 |  | 233.9
2006 |  | 7 | 150.9 |  | -- |  | 42.2 |  | 193.1 |  | 162 |  | 355.1
2007 |  | 11 | 228.8 |  | -- |  | 136.5 |  | 365.3 |  | 170.1 |  | 535.4
2008 |  | 15 | 315.5 |  | -- |  | 25.2 |  | 340.7 |  | 154.3 |  | 495
2009 |  | 24 | 514 |  | -- |  | 42.6 |  | 556.6 |  | 80.5 |  | 637.1
2010 |  | 27 | 655.7 |  | -- |  | 34.8 |  | 690.5 |  | 70.7 |  | 761.2
2011 |  | 31 | 688.5 |  | -- |  | 77.6 |  | 766.1 |  | 127 |  | 893.1
2012 |  | 25 | 567.6 |  | -- |  | 46.3 |  | 613.9 |  | 120 |  | 733.9
2013 |  | 30 | 772.8 |  | -- |  | 3.8 |  | 776.6 |  | 89.6 |  | 866.2
2014 |  | 23 | 574.3 |  | -- |  | 1.6 |  | 575.9 |  | 85.6 |  | 661.5
2015 |  | 31 | 792.3 |  | -- |  | -- |  | 792.3 |  | 106.7 |  | 899
2016 |  | 29 | 780.5 |  | -- |  | -- |  | 780.5 |  | 60.3 |  | 840.8
2017 |  | 24 | 719.8 |  | -- |  | 6.4 |  | 726.2 |  | 90.8 |  | 817
2018 |  | 27 | 822.4 |  | -- |  | 2.3 |  | 824.7 |  | 63 |  | 887.7
2019 |  | 27 | 798.6 |  | -- |  | 56.1 |  | 854.7 |  | 54.1 |  | 908.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | 6 |  | 6
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | 6 |  | 6
Subtotal |  | 347 | 8716.4 |  | -- |  | 517.9 |  | 9234.3 |  | 1636.9 |  | 10871.2

## Table 22
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | 6.8 |  | 6.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2004 |  | 9 | 212.6 |  | -- |  | 25.6 |  | 238.2 |  | 113.8 |  | 352
2005 |  | 7 | 143.1 |  | -- |  | 19.6 |  | 162.7 |  | 81.8 |  | 244.5
2006 |  | 7 | 153.5 |  | -- |  | 42.9 |  | 196.4 |  | 164.8 |  | 361.2
2007 |  | 11 | 227.5 |  | -- |  | 135.7 |  | 363.2 |  | 169.1 |  | 532.3
2008 |  | 15 | 309 |  | -- |  | 24.7 |  | 333.7 |  | 151.1 |  | 484.8
2009 |  | 24 | 496.5 |  | -- |  | 41.2 |  | 537.7 |  | 77.7 |  | 615.4
2010 |  | 27 | 620.4 |  | -- |  | 32.9 |  | 653.3 |  | 66.9 |  | 720.2
2011 |  | 31 | 638.8 |  | -- |  | 72 |  | 710.8 |  | 117.8 |  | 828.6
2012 |  | 25 | 519.2 |  | -- |  | 42.3 |  | 561.5 |  | 109.8 |  | 671.3
2013 |  | 30 | 699.3 |  | -- |  | 3.4 |  | 702.7 |  | 81.2 |  | 783.9
2014 |  | 23 | 513 |  | -- |  | 1.4 |  | 514.4 |  | 76.5 |  | 590.9
2015 |  | 31 | 697.3 |  | -- |  | -- |  | 697.3 |  | 93.9 |  | 791.2
2016 |  | 29 | 675.2 |  | -- |  | -- |  | 675.2 |  | 52.2 |  | 727.4
2017 |  | 24 | 611.1 |  | -- |  | 5.4 |  | 616.5 |  | 77.1 |  | 693.6
2018 |  | 27 | 684.8 |  | -- |  | 1.9 |  | 686.7 |  | 52.4 |  | 739.1
2019 |  | 27 | 651.9 |  | -- |  | 45.8 |  | 697.7 |  | 44.2 |  | 741.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | 4.8 |  | 4.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | 4.7 |  | 4.7
Subtotal |  | 347 | 7853.2 |  | -- |  | 494.8 |  | 8348 |  | 1546.6 |  | 9894.6

## Table 23
Cost Quantity Information 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2008 $M
2001 | -- | --
2002 | -- | --
2003 | -- | --
2004 | 9 | 212.6
2005 | 7 | 143.1
2006 | 7 | 153.5
2007 | 11 | 227.5
2008 | 15 | 309
2009 | 24 | 496.5
2010 | 27 | 572.6
2011 | 31 | 632.5
2012 | 25 | 521.3
2013 | 30 | 693.1
2014 | 23 | 517.6
2015 | 31 | 695.1
2016 | 29 | 682.4
2017 | 24 | 611.1
2018 | 27 | 684.8
2019 | 27 | 700.5
2020 | -- | --
2021 | -- | --
Subtotal | 347 | 7853.2

## Table 24
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2012 17.6
Subtotal 17.6

## Table 25
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2008 $M
Total Program
2012 16.0
Subtotal 16.0

## Table 26
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2003-10-22 | 2010-06-07
Approved Quantity | 28 | 55
Reference | LRIP ADM | LRIP VII ADM
Start Year | 2004 | 2004
End Year | 2005 | 2010
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the need to permit an orderly increase in the production rate and efficiency until successful completion of operational testing.

## Table 27
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Pakistan 7/10/2015 12 57.9 FMS Case PK-P-BSO, AH-1Z helicopters, initial
support, and training.
Notes
Total Cost reflects the procurement of 3 out of 12 total aircraft. The Total Cost will increase upon Contract Award of the additional 9 aircraft.
PK-P-SBO is the only H-1 Upgrades active FMS case at this time.
Nuclear Costs
None

## Table 28
Unit Cost
Unit Cost Report
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Current UCR Baseline (Feb 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 11953 |  |  | 11614.7
Quantity | 353 |  |  | 351
Unit Cost | 33.861 |  |  | 33.09 |  |  | -2.28
Average Procurement Unit Cost
Cost | 10088.4 |  |  | 9894.6
Quantity | 349 |  |  | 347
Unit Cost | 28.907 |  |  | 28.515 |  |  | -1.36
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Apr 2005 APB)
Program Acquisition Unit Cost
Cost | 7852.2 |  |  | 11614.7
Quantity | 284 |  |  | 351
Unit Cost | 27.649 |  |  | 33.09 |  | 19.68
Average Procurement Unit Cost
Cost | 6352.9 |  |  | 9894.6
Quantity | 280 |  |  | 347
Unit Cost | 22.689 |  |  | 28.515 |  | 25.68

## Table 29
Unit Cost History
Item | [7 empty] | Date |  |  |  |  | BY 2008 $M | [7 empty] | TY $M
[13 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Oct 1996 | [7 empty] | 12.089 |  |  |  |  | 9.903 |  |  |  | 12.491 |  |  |  | 10.554
APB as of January 2006 |  |  |  |  | Apr 2005 | [7 empty] | 27.649 |  |  |  |  | 22.689 |  |  |  | 28.172 |  |  |  | 23.843
Revised Original APB |  |  |  |  | Apr 2005 | [7 empty] | 27.649 |  |  |  |  | 22.689 |  |  |  | 28.172 |  |  |  | 23.843
Prior APB |  |  |  |  | Dec 2008 | [7 empty] | 31.738 |  |  |  |  | 26.946 |  |  |  | 34.524 |  |  |  | 30.208
Current APB |  |  |  |  | Feb 2011 | [7 empty] | 33.861 |  |  |  |  | 28.907 |  |  |  | 36.079 |  |  |  | 31.582
Prior Annual SAR |  |  |  |  | Dec 2014 | [7 empty] | 33.192 |  |  |  |  | 28.644 |  |  |  | 35.672 |  |  |  | 31.626
Current Estimate |  |  |  |  | Dec 2015 | [7 empty] | 33.09 |  |  |  |  | 28.515 |  |  |  | 35.401 |  |  |  | 31.329
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [22 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  |  | Oth |  | Spt |  |  | Total
12.491 -0.078 -1.056 1.772 2.351 15.397 0.000 3.647 22.033 34.524
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [20 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth |  | Spt |  |  | Total
34.524 -0.710 0.071 -0.055 0.275 1.422 0.000 -0.126 0.877 35.401

## Table 30
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [12 empty] | APUC Production Estimate
| Econ | Qty |  | Sch | Eng |  |  | Est |  | Oth | Spt | Total
10.554 -0.003 -0.686 1.722 1.632 13.299 0.000 3.690 19.654 30.208
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [12 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  |  | Est | Oth | Spt |  | Total
30.208 -0.725 0.046 -0.055 0.000 1.982 0.000 -0.127 1.121 31.329
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Milestone II |  |  | N/A |  |  |  | Sep 1996 |  |  |  | Sep 1996 |  |  |  | Oct 1996
Milestone III |  |  | N/A |  |  |  | Feb 2004 |  |  |  | May 2008 |  |  |  | Sep 2008
IOC |  |  | N/A |  |  |  | Jun 2005 |  |  |  | Mar 2008 |  |  |  | Aug 2008
Total Cost (TY $M) |  |  | N/A |  |  |  | 3547.5 |  |  |  | 12186.8 |  |  |  | 12425.9
Total Quantity |  |  | N/A |  |  |  | 284 |  |  |  | 353 |  |  |  | 351
PAUC |  |  | N/A |  |  |  | 12.491 |  |  |  | 34.524 |  |  |  | 35.401

## Table 31
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1644.1 | 10542.7 | -- | 12186.8
Previous Changes
Economic | 2.5 | -208.2 | 0.4 | -205.3
Quantity | -- | -- | -- | --
Schedule | -- | -18.5 | -- | -18.5
Engineering | 96.7 | -- | -- | 96.7
Estimating | -206.2 | 643.1 | 17.2 | 454.1
Other | -- | -- | -- | --
Support | -- | 78.3 | -- | 78.3
Subtotal | -107 | 494.7 | 17.6 | 405.3
Current Changes
Economic | -0.2 | -43.5 | -0.1 | -43.8
Quantity | -- | -44.2 | -- | -44.2
Schedule | -- | -0.7 | -- | -0.7
Engineering | -- | -- | -- | --
Estimating | 0.2 | 44.7 | 0.1 | 45
Other | -- | -- | -- | --
Support | -- | -122.5 | -- | -122.5
Subtotal | -- | -166.2 | -- | -166.2
Total Changes | -107 | 328.5 | 17.6 | 239.1
CE - Cost Variance | 1537.1 | 10871.2 | 17.6 | 12425.9
CE - Cost & Funding | 1537.1 | 10871.2 | 17.6 | 12425.9

## Table 32
Summary BY 2008 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 1799.2 | 9404.2 | -- | 11203.4
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -20.9 | -- | -20.9
Engineering | 83.6 | -- | -- | 83.6
Estimating | -178.9 | 545.8 | 15.9 | 382.8
Other | -- | -- | -- | --
Support | -- | 67.8 | -- | 67.8
Subtotal | -95.3 | 592.7 | 15.9 | 513.3
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -34.6 | -- | -34.6
Schedule | -- | -3.3 | -- | -3.3
Engineering | -- | -- | -- | --
Estimating | 0.2 | 39.2 | 0.1 | 39.5
Other | -- | -- | -- | --
Support | -- | -103.6 | -- | -103.6
Subtotal | 0.2 | -102.3 | 0.1 | -102
Total Changes | -95.1 | 490.4 | 16 | 411.3
CE - Cost Variance | 1704.1 | 9894.6 | 16 | 11614.7
CE - Cost & Funding | 1704.1 | 9894.6 | 16 | 11614.7
Previous Estimate: December 2014

## Table 33
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.2
Adjustment for current and prior escalation. (Estimating) | 0.2 | 0.2
RDT&E Subtotal | 0.2 | 0
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -43.5
Adjustment for current and prior escalation. (Estimating) | 15.6 | 17.7
Revised estimate to reflect the application of new outyear inflation indices. (Estimating) | 19.2 | 23
Quantity variance resulting from a decrease of 2 helicopters from 349 to 347. (Subtotal) | -46.1 | -56.5
Quantity variance resulting from a decrease of 2 helicopters from 349 to 347. | -41.1 | -50.3
(Quantity)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+0.1) (+0.1)
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-5.1) (-6.3)
Additional quantity variance resulting from procurement profile adjustments in FY 2016 through FY 2019. (Quantity)
Realignment of funding resulting from procurement buy profile adjustments in FY 2016 through FY 2019. (Schedule)
Additional schedule variance resulting from procurement profile adjustments in FY 2016 through FY 2019. (Schedule)
+6.5 +6.1
0.0 +1.7
-3.4 -2.5
Revised cost estimate in FY 2014 for M-299 life of type buy for obsolescence. (Estimating) +14.3 +16.1
Revised cost estimate in FY 2016 for Target Sight System Engineering Change Orders and repair. (Estimating)
Revised cost estimate due to updated procurement strategy and unit prices for Government Furnished Equipment. (Estimating)
+8.0 +9.0
-12.8 -14.8
Adjustment for current and prior escalation. (Support) +2.4 +2.6
Decrease in Other Support due to updated support strategy and realignment of funds to accommodate the purchase of an additional aircraft in FY 2016. (Support)
-106.5 -125.7
Increase in Initial Spares due to revised cost estimate. (Support) | 0.5 | 0.6
Procurement Subtotal | -102.3 | -166.2
(QR) Quantity Related
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.1
Adjustment for current and prior escalation. (Estimating) | 0.1 | 0.1
MILCON Subtotal | 0.1 | 0

## Table 34
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: H-1 Upgrades Production Contract Lot 8
Contractor: Bell Helicopter Textron
Contractor Location: 600 Hurst Blvd
Hurst, TX 76053
Contract Number: N00019-10-C-0015
Contract Type: Firm Fixed Price (FFP)
Award Date: February 05, 2010
Definitization Date: July 25, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
50.3 N/A 33 600.4 N/A 33 600.4 600.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the contract award for the Lot 8 UH-1Y and AH-1Z aircraft. The current contract represents the definitization of the Advanced Acquisition Contract for long lead items and, as a result, the Initial Contract Price Target increased from $50.3M to the Current Contract Price Target of $600.4M.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 35
Contract Identification
Appropriation: Procurement
Contract Name: H-1 Upgrades Production Contract Lot 9
Contractor: Bell Helicopter Textron
Contractor Location: 600 Hurst Blvd
Hurst, TX 76053
Contract Number: N00019-11-C-0023
Contract Type: Firm Fixed Price (FFP)
Award Date: March 14, 2011
Definitization Date: October 16, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
56.3 N/A 26 474.7 N/A 25 474.7 474.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the contract award for the Lot 9 UH-1Y and AH-1Z aircraft. The Initial Contract Price Target was for the Advanced Acquisition Contract (AAC) for long lead items. The Initial Contract Price Target increased from $48.4M to $56.3M under a subsequent modification after the Continuing Resolution Authority expired to apply additional advanced procurement funding. The current contract represents the definitization of the AAC for long lead items, as well as other requirements in support of the Lot 9 production aircraft, resulting in a Current Contract Price Target of $474.7M.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 36
Contract Identification
Appropriation: Procurement
Contract Name: H-1 Upgrades Production Contract Lot 10
Contractor: Bell Helicopter Textron
Contractor Location: 600 Hurst Blvd
Hurst, TX 76053
Contract Number: N00019-12-C-0009
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: February 13, 2012
Definitization Date: December 27, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
56.7 N/A 25 570.1 586.0 28 570.1 570.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the contract award for the Lot 10 UH-1Y and AH-1Z aircraft. The current contract represents the definitization of the Advanced Acquisition Contract for long lead items and, as a result, the Initial Contract Price Target increased from $56.7M to the Current Contract Price Target of $570.1M.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +2.2 -119.0
Previous Cumulative Variances +8.3 -30.4
Net Change -6.1 -88.6
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to rework of Main Rotor Gearboxes driven by the need to inspect for, and replace as required, discrepant sub-assembly components, as well as higher than anticipated costs for cabin detail parts.
The unfavorable net change in the schedule variance is due to the impact of the poor quality of the Kaman cabin assembly component from previous ZBN Aircraft Production lots.

## Table 37
Contract Identification
Appropriation: Procurement
Contract Name: H-1 Upgrades Production Contract Lot 11
Contractor: Bell Helicopter Textron
Contractor Location: 600 Hurst Blvd
Hurst, TX 76053
Contract Number: N00019-13-C-0023
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: April 01, 2013
Definitization Date: May 16, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
13.1 N/A 25 543.7 551.4 24 543.7 543.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the contract award for the Lot 11 UH-1Y and AH-1Z aircraft. The current contract represents the reduction to the Lot 11 price associated with the Lot 12 Advanced Procurement of long lead items, resulting in a Current Contract Price Target of $543.7M.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances 0.0 0.0
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
Notes
Lot 11 includes two FY 2013-funded aircraft.
The contract modification to add Earned Value (EV) reporting awarded on September 30, 2015. Data will be available in the next reporting period.

## Table 38
Contract Identification
Appropriation: Procurement
Contract Name: H-1 Upgrades Production Contract Lot 12
Contractor: Bell Helicopter Textron Inc.
Contractor Location: 600 E Hurst Blvd
Hurst, TX 76053
Contract Number: N00019-13-C-0023/12
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: August 25, 2015
Definitization Date: August 25, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
59.7 59.7 26 623.4 635.0 34 623.4 623.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to receipt of additional funding in support of the Advanced Acquisition Contract (AAC) for long lead items and the subsequent definitization for 34 Lot 12 H-1 Upgrade Aircraft (15 UH-1Y and 19 AH-1Z (including 3 FMS Pakistan ZBN)) and Lot 13 AAC. FPI construct utilizes share ratios as follows: above target 50/50 and below target 50/50.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date 0.0 0.0
Previous Cumulative Variances -- --
Net Change +0.0 +0.0
Cost and Schedule Variance Explanations
None
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because earned value management reporting has not yet commenced due to an issue with the contract requirement for reporting and will be reported in the next available submission following receipt of data.
Notes
This is the first time this contract is being reported.

## Table 39
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 4 | 4 | 4 | 100%
Production | 184 | 174 | 347 | 50.14%
Total Program Quantity Delivered | 188 | 178 | 351 | 50.71%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
12425.9
7551
60.77%
26
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
21
80.77%
9800.4
78.87%
The above data is current as of February 09, 2016.

## Table 40
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 09, 2016
Source of Estimate: POE
Quantity to Sustain: 349
Unit of Measure: Aircraft
Service Life per Unit: 30.00 Years
Fiscal Years in Service: FY 2007 - FY 2051
Aircraft quantity is 349 (not including four EMD assets not inducted into the Fleet).
Program currently funded to 347 aircraft; program of record remains 349 aircraft.
2016 inflation rates are included in this estimate.
PB17 Flight Hour controls from document 3871 are used in this estimate.
Cost estimate updated to reflect recovery of AH-1Z delivery schedule through FY 2017. H-1 Procurement Profile: 189 AH-1Z, 160 UH-1Y.
H-1 Primary Authorized Aircraft profile: 149 AH-1Z, 125 UH-1Y. Combined squadrons are composed of 15 AH-1Z and 12 UH-1Y aircraft.
The life cycle includes a 30-year service life with an average annual usage of 239 flight hours per AH-1Z aircraft and an average annual usage of 296 flight hours per UH-1Y aircraft accumulating a total of 8,130 operating aircraft years.
Each aircraft has a designed fatigue life of 10,000 hours per aircraft. Attrition rates are 1% for AH-1Z and 0.7% for UH-1Y.
Pipeline rates are 10% for AH-1Z and 8.3% for UH-1Y.
Maintenance Costs consisting of Aviation Depot Level Repairable and Consumables are now estimated using a bottoms- up model, utilizing historical costs and reliability performance projections for both the UH-1Y and AH-1Z.
O&S cost estimate is based on three levels of organic maintenance with chargeable manning (fleet squadron) estimated at 100%.
Sustainment Strategy
The sustainment strategy for H-1 Upgrades has three major tenants: 1) ensuring Organizational, Intermediate, and Depot level maintenance capabilities are established and that the Program Office optimizes Fleet support based on a three level maintenance concept, 2) ensuring Intermediate level maintenance capability is established and expanded capability is implemented based on approved Business Case Analysis (BCAs) , and 3) establishing organic Depot level capability for core components using a direct approach that focuses on components that have the greatest impact on Fleet readiness to include ensuring the correct balance of government and original equipment manufacturer depot component

## Table 41
repair is maintained in support of Fleet readiness.
Antecedent Information
The H-1 antecedent estimate is a composite of AH-1W and UH-1N series aircraft. Cost per aircraft is the combined three- year (FY 2007 - FY 2009) average of Naval Visibility and Management of Operating and Support Costs Aviation Type Model Series Report database. Manpower for antecedent and upgrade aircraft are set equal as the table of organization is deemed to be equivalent. Antecedent aircraft have historically flown 21.7 flight hours per month and 260 flight hours annually.
Annual O&S Costs BY2008 $M
Cost Element |  |  | H-1 Upgrades Average Annual Cost Per Aircraft | [5 empty] | UH-1N/AH-1W (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  |  | 1.31 | [5 empty] | 1.31
Unit Operations |  |  | 0.37 | [5 empty] | 0.23
Maintenance |  |  | 1.43 | [5 empty] | 1.51
Sustaining Support |  |  | 0.09 | [5 empty] | 0.11
Continuing System Improvements |  |  | 0.19 | [5 empty] | 0.34
Indirect Support |  |  | 0.52 | [5 empty] | 0.53
Other |  |  | 0 | [5 empty] | 0
Total |  |  | 3.91 | [5 empty] | 4.03
.
Item | Total O&S Cost $M
| H-1 Upgrades | [8 empty] | UH-1N/AH-1W (Antecedent)
| Current Production APB Objective/Threshold | [5 empty] | Current Estimate
Base Year |  | 33301.8 |  |  | 36632 |  |  | 31711.7 |  |  | 32723.4
Then Year |  | 0 |  |  | N/A |  |  | 48904.4 |  |  | N/A
.
Equation to Translate Annual Cost to Total Cost
H-1 Upgrades Average Annual Cost Per Aircraft = Total O&S Cost (BY) / Total Operating Aircraft Years
$3.9 M Per Year Per Aircraft = $31,711.7M / 8,130 Total Operating Aircraft Years
O&S Cost Variance
Category |  |  |  | BY 2008 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
33929.8
Programmatic/Planning Factors -1937.9 Updated with Aircraft Program Data File (APDF) v119,
updated with PB17 flight hours, and changed the

## Table 42
calculation to reflect the APDF PAA until TAI cannot meet 50% of squadron’s PAA.
Cost Estimating Methodology 1862.8 Updated flight hours to reflect actuals and Planning Factors
Memo. Continued transitioning to a Y/Z actuals based estimate.
Cost Data Update -2085.4 Updated Flying Hour Program CPH based on latest Flying Hour Program data using FY 2015 prices and updated inflation to the 2016 indices.
Labor Rate 2.2 Incorporated update for depot labor rates.
Energy Rate -59.8 Updated Fuel cost /gal to FY 2015 rate for JP5.
Technical Input 0.0
Other 0.0
Total Changes -2218.1
Current Estimate 31711.7
.
Disposal Estimate Details
Date of Estimate: February 09, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2008 $M): Total costs for disposal of all Aircraft are 80.2
This Rough Order of Magnitude estimate will be refined as the System Disposal Plan Annex to the Life Cycle Sustainment Plan is developed.