## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-418
Integrated Defensive Electronic Countermeasures (IDECM)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 12
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 33
Foreign Military Sales 34
Nuclear Costs 34
Unit Cost 35
Cost Variance 41
Contracts 47
Deliveries and Expenditures 51
Operating and Support Cost 52

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Integrated Defensive Electronic Countermeasures (IDECM)
DoD Component
Navy
Responsible Office
CAPT Scott Porter, USN
Program Executive Office (Tactical Aircraft) Bldg. 2272, Suite 535
47123 Buse Rd
Patuxent River, MD 20670-1547
scott.d.porter@navy.mil
Phone: | 301-757-7951
Fax: | 301-757-7954
DSN Phone: | 757-7951
DSN Fax: | 757-7954
Date Assigned: | October 9, 2012
References
IDECM Blocks 2/3
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated June 16, 2008
Approved APB
Assistant Secretary of the Navy (Research, Development & Acquisition) (ASN(RDA)) Approved Acquisition Program Baseline (APB) dated April 13, 2012
IDECM Block 4
SAR Baseline (Development Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated June 16, 2008
Approved APB
Component Acquisition Executive (CAE) Approved Acquisition Program Baseline (APB) dated February 3, 2014

## Table 6
Mission and Description
The Integrated Defensive Electronic Countermeasures (IDECM) System is a Radio Frequency (RF), self-protection electronic countermeasure suite on the F/A-18 aircraft. IDECM improves the survivability of the F/A-18 aircraft against RF guided threats during Air-to-Ground/Surface and Air-to-Air missions. The system is comprised of onboard components, which receive and process radar signals, along with onboard and offboard jammer components that transmit appropriate RF jamming responses.
There are four IDECM variants in development, production, or sustainment. Blocks 1-3 are compatible with F/A-18E/F aircraft only. Block 4 is compatible with F/A-18C-F aircraft.
IDECM Block 1: A federated suite, consisting of the ALQ-165 On-Board Jammer (OBJ) and ALE-50 expendable decoy. IDECM Block 2: An integrated suite, consisting of the ALQ-214 OBJ and ALE-50 expendable decoy.
IDECM Block 3: An integrated suite, consisting of the ALQ-214 OBJ and ALE-55 Fiber Optic Towed Decoy.
IDECM Block 4: A Hardware Engineering Change Proposal to the ALQ-214 OBJ to render it suitable for operation on F/A-18C/D aircraft, while retaining all functionality, when installed on F/A-18E/F.
ALQ-214 Software Improvement Program (SWIP): ALQ-214 Software/Firmware updates that will enhance F/A-18 mission execution and improve mission survivability against modern air, land and naval threat systems by degrading (denying/delaying) threat ability to engage.

## Table 7
Executive Summary
IDECM Block-2 (IB-2) ALQ-214(V)3:
ALQ-214(V)3 deliveries are 100% complete and all systems were delivered at least one month ahead of the contracted schedule. Harris (formerly Exelis) delivered two hundred seventy-six (276) ALQ-214(V) 3 production systems under the LRIP 1 through FRP 8 contracts.
IDECM Block-3 (IB-3) ALE-55:
The ALE-55 is in FRP and all production contracts are performing well. As of February 9, 2016, BAE Systems has delivered 1,902 Fiber Optic Towed Decoys (FOTD) and 424 Electronic Frequency Converters (EFC) under the LRIP 4 through FRP 5 contracts. EFC deliveries are 100% complete. FRP 5 deliveries began in December 2015.
IB-2/3 current APB threshold deviation for APUC and procurement are due to reductions in the procurement rate of the ALE- 55 FOTD. Reduced rate of ALE-55 FOTD procurements caused by continual budget reductions and increased Forward Pricing Rate Agreements between DCMA and ALE-55 vendor BAE. A Program Deviation Report (PDR) has been drafted notifying Assistant Secretary of the Navy (Research, Development and Acquisition) (ASN(RD&A)) of the deviation.
IDECM Block-4 (IB-4) ALQ-214 Engineering Change Proposal (ECP) and Software Improvement Program (SWIP):
On March 10, 2015, PMA 272 submitted a PDR for IB-4 ECP schedule breach. As a result of delays to Operational Test (OT) execution, caused by the combined lack of test aircraft and threat simulators/range availability, the schedule could not be met for conduct of In-Process Review (IPR) 6. Based on IDECM maturity, ASN(RD&A) concurred with the IDECM program plan to award the FY 2015 ALQ-214 production contract and remove the requirement for IPR 6 via ADM signed on May 26, 2015. The FY 2015 production contract was awarded in 4th Quarter FY 2015 for a quantity of 46 systems and spares. A revised APB which reflects the current schedule estimate (removes IPR 6 (Production Transition)) is in signature routing. With respect to the IB-4 ECP OT which officially ended November 17, 2015, that test period has officially been changed to an Operational Assessment (OA) for SWIP. The data from that test period will be used to inform the effectiveness and suitability decision when SWIP is tested. SWIP OT is planned in 2nd Quarter FY 2017. IB-4 SWIP Build 4 delivered in October 2015. IB-4 SWIP Build 5 will deliver in March 2016.
IDECM Block-4 (IB-4) Production:
The FRP 9 through 11 contract was awarded on April 16, 2012. FRP 9 and 10 deliveries are complete. As of February 9, 2016, Harris has delivered 98 ALQ-214(V)4 production systems under the FRP 9 through 11 contracts. FRP 11 deliveries began in January 2016 and are currently one month ahead of contracted schedule. The FRP 12/13 contract was awarded on July 30, 2015. FRP 12 deliveries are planned to begin in January 2017. FRP 13 option award planned for 2nd Quarter FY 2016.
IB-4 current APB threshold deviation for procurement due to the addition of 134 ALQ-214(V)4 systems, documented in N98 memo Serial Number: N98/13U146134, dated February 4, 2013. A PDR has been drafted notifying ASN(RD&A) of the deviation. A revised APB will be submitted to ASN(RD&A) to reflect current/new objective and threshold for the affected cost parameters.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
IDECM Blocks 2/3
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
IB-2/3 current APB threshold deviations for APUC and procurement are due to reductions in the procurement rate of the ALE-55 Fiber Optic Towed Decoy (FOTD). The reduced rate of ALE-55 FOTD procurements was caused by continual budget reductions and increased Forward Pricing Rate Agreements between Defense Contract Management Agency (DCMA) and ALE-55 vendor BAE. A Program Deviation Report (PDR) has been drafted notifying Assistant Secretary of the Navy (Research, Development and Acquisition) (ASN RD&A) of the deviation.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
IDECM Block 4
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
IB-4 current APB threshold deviation for procurement and O&S due to the addition of 134 ALQ-214(V)4 systems, documented in N98 memo Serial Number: N98/13U146134, dated February 4, 2013. A PDR has been drafted notifying ASN(RD&A) of the deviation.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
IDECM Blocks 2/3
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
ALQ-214 (IB2) OPEVAL (Start) | Nov 2002 | Nov 2002 | May 2003 | Nov 2002
ALQ-214 (IB2) MS III | Nov 2003 | Nov 2003 | May 2004 | Nov 2003
ALQ-214 (IB2) FRP Contract Award | Sep 2004 | Sep 2004 | Mar 2005 | Sep 2004
ALQ-214 (IB2) IOC | Sep 2004 | Sep 2004 | Mar 2005 | Sep 2004
ALE-55 (IB3) OPEVAL (Start) | Feb 2008 | Feb 2008 | Aug 2008 | Feb 2008
ALE-55 (IB3) MS III | Jan 2009 | Jul 2011 | Jan 2012 | Jul 2011
ALE-55 (IB3) FRP Contract Award | Feb 2009 | Jan 2011 | Jul 2011 | Jul 2011
ALE-55 (IB3) IOC | Feb 2010 | Jan 2011 | Jul 2011 | Jul 2011
Change Explanations
None
Acronyms and Abbreviations
IB2 - IDECM Block 2 IB3 - IDECM Block 3
MS - Milestone
OPEVAL - Operational Evaluation

## Table 11
IDECM Block 4
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Production Objective/Threshold |  | Current Estimate
ALQ-214 (IB4) MS B | Mar 2009 | N/A | N/A | N/A
ALQ-214 (IB4) IPR (Post-PDR Assessment) | N/A | Jan 2010 | Jul 2010 | Mar 2010
ALQ-214 (IB4) IPR (Post-CDR Assessment) | N/A | Jul 2010 | Jan 2011 | Jul 2010
ALQ-214 (IB4) MS C | Mar 2012 | N/A | N/A | N/A
ALQ-214 (IB4) IPR (Production Cut-in Review 1) | N/A | Dec 2011 | Jun 2012 | Mar 2012
ALQ-214 (IB4) OPEVAL (Start) | Nov 2012 | N/A | N/A | N/A
ALQ-214 (IB4) IPR (Production Cut-in Review 2) | N/A | Feb 2013 | Aug 2013 | Apr 2013
ALQ-214 (IB4) FRP Decision | Aug 2013 | N/A | N/A | N/A
ALQ-214 (IB4) IPR (Production Cut-in Review 3) | N/A | Jan 2014 | Jul 2014 | Feb 2014
ALQ-214 (IB4) OT (Start) | N/A | Dec 2013 | Jun 2014 | Jun 2014
ALQ-214 (IB4) IPR (Production Transition) | N/A | Nov 2014 | May 2015 | Nov 20151
ALQ-214 (IB4) IOC | Feb 2014 | Nov 2014 | May 2015 | May 2015
(Ch-1)
1 APB Breach
Change Explanations
(Ch-1) ALQ-214 (IB4) IPR (Production Transition) current estimate changed from May 2015 to November 2015 due to delays in OT caused by lack of aircraft and threat simulator availability at the test range.
Acronyms and Abbreviations
CDR - Critical Design Review IB4 - IDECM Block 4
IPR - In-Process Review MS - Milestone
OPEVAL - Operational Evaluation OT - Operational Test
PDR - Preliminary Design Review

## Table 12
Performance
IDECM Blocks 2/3
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
ALQ-214 (IB2/3 On-Board Jammer) Ao
0.95 | 0.95 | 0.9 | 0.92 | 0.92
ALQ-214 (IB3 Off-Board Jammer) Ao
0.95 | 0.95 | 0.9 | 0.997 | 0.997
ALQ-214 (IB2) Operating Envelope
N/A | LBA | LBA | LBA | LBA
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Operational Requirements Document (ORD) (Block 2) dated November 2003 and Capability Production Document (CPD) (Block 3) dated November 13, 2007
Change Explanations
None
Acronyms and Abbreviations
Ao - Operational Availability IB-2 - IDECM Block 2
IB-3 - IDECM Block 3
LBA - Limits of Basic Airframe

## Table 13
IDECM Block 4
Performance Characteristics
SAR Baseline Development Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
ALQ-214 (IB2/3/4 On-Board Jammer) Ao
0.95 | 0.95 | 0.9 | 0.92 | 0.92
ALQ-214 (IB2) Operating Envelope
N/A | LBA | LBA | LBA | LBA
ALQ-214 (IB2/3/4 On-board Jammer) Operational Availability
Ao >= 0.95 | N/A | N/A | N/A | N/A
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Operational Requirements Document (ORD) (Block 4) dated November 2003 and Statement of Functionality (SOF) dated October 12, 2010
Change Explanations
None
Acronyms and Abbreviations
Ao - Operational Availability IB-2 - IDECM Block 2
IB-3 - IDECM Block 3 IB-4 - IDECM Block 4
LBA - Limits of Basic Airframe

## Table 14
Track to Budget
IDECM Blocks 2/3
RDT&E
Appn |  | BA | PE
Navy 1319 05 0604270N
Project | Name
2175 Tactical Air Electronic Warfare (Sunk)
Procurement
Appn |  | BA | PE
Navy 1506 05 0204161N
Line Item Name
0576 Common ECM Equipment (Shared) (Sunk) Navy 1506 06 0204161N
Line Item Name
0605 Spares and Repair Parts (Shared) (Sunk) Navy 1508 01 0204162N
Line Item Name
0182 Air Expendable Countermeasures (Shared)
IDECM Block 4
RDT&E
Appn |  | BA | PE
Navy 1319 05 0604270N
Project | Name
2175 Tactical Air Electronic Warfare
Procurement
Appn |  | BA | PE
Navy 1506 05 0204161N
Line Item Name
0576 Common ECM Equipment (Shared) Navy 1506 06 0204161N
Line Item Name
0605 Spares and Repair Parts (Shared)

## Table 15
Cost and Funding
Cost Summary - Total Program
Total Acquisition Cost - Total Program
Appropriation | BY 2008 $M |  |  |  | BY 2008 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 664.4 |  | 696.2 | -- |  | 694.3 |  | 615.2 |  | 645.1 |  | 646.2
Procurement | 1407.2 |  | 1579.4 | -- |  | 1964.7 |  | 1666.1 |  | 1885.5 |  | 2560.5
Flyaway | -- |  | -- | -- |  | 1582.1 |  | -- |  | -- |  | 2126.2
Recurring | -- |  | -- | -- |  | 1571.9 |  | -- |  | -- |  | 2115.6
Non Recurring | -- |  | -- | -- |  | 10.2 |  | -- |  | -- |  | 10.6
Support | -- |  | -- | -- |  | 382.6 |  | -- |  | -- |  | 434.3
Other Support | -- |  | -- | -- |  | 254 |  | -- |  | -- |  | 307.3
Initial Spares | -- |  | -- | -- |  | 128.6 |  | -- |  | -- |  | 127
MILCON | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total | 2071.6 |  | 2275.6 | N/A |  | 2659 |  | 2281.3 |  | 2530.6 |  | 3206.7

## Table 16
Cost and Funding
Cost Summary - IDECM Blocks 2/3
Total Acquisition Cost - IDECM Blocks 2/3
Appropriation | BY 2008 $M | [5 empty] | BY 2008 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 454.9 |  |  | 456.4 | 502 |  |  | 456.4 |  | 391 |  |  | 391 |  | 391
Procurement | 956 |  |  | 1037.5 | 1141.3 |  |  | 1154.11 |  | 1144.2 |  |  | 1276.4 |  | 1568.6
Flyaway | -- |  |  | -- | -- |  |  | 923.2 |  | -- |  |  | -- |  | 1319.3
Recurring | -- |  |  | -- | -- |  |  | 916.2 |  | -- |  |  | -- |  | 1312.2
Non Recurring | -- |  |  | -- | -- |  |  | 7 |  | -- |  |  | -- |  | 7.1
Support | -- |  |  | -- | -- |  |  | 230.9 |  | -- |  |  | -- |  | 249.3
Other Support | -- |  |  | -- | -- |  |  | 151.4 |  | -- |  |  | -- |  | 177.6
Initial Spares | -- |  |  | -- | -- |  |  | 79.5 |  | -- |  |  | -- |  | 71.7
MILCON | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 1410.9 |  |  | 1493.9 | N/A |  |  | 1610.5 |  | 1535.2 |  |  | 1667.4 |  | 1959.6
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current APB cost estimate provided sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk and external interference. It was consistent with average resource expenditures on historical efforts of similar size, scope, and complexity and represents a notional 50% confidence level when established.
Total Quantity - IDECM Blocks 2/3
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  | 12809 |  |  |  | 12805 |  |  |  |  | 12805
Total |  | 12809 |  |  |  | 12805 |  |  |  |  | 12805

## Table 17
Cost Summary - IDECM Block 4
Total Acquisition Cost - IDECM Block 4
Appropriation | BY 2008 $M | [5 empty] | BY 2008 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E | 209.5 |  |  | 239.8 | 263.8 |  |  | 237.9 |  | 224.2 |  |  | 254.1 |  | 255.2
Procurement | 451.2 |  |  | 541.9 | 596.1 |  |  | 810.61 |  | 521.9 |  |  | 609.1 |  | 991.9
Flyaway | -- |  |  | -- | -- |  |  | 658.9 |  | -- |  |  | -- |  | 806.9
Recurring | -- |  |  | -- | -- |  |  | 655.7 |  | -- |  |  | -- |  | 803.4
Non Recurring | -- |  |  | -- | -- |  |  | 3.2 |  | -- |  |  | -- |  | 3.5
Support | -- |  |  | -- | -- |  |  | 151.7 |  | -- |  |  | -- |  | 185
Other Support | -- |  |  | -- | -- |  |  | 102.6 |  | -- |  |  | -- |  | 129.7
Initial Spares | -- |  |  | -- | -- |  |  | 49.1 |  | -- |  |  | -- |  | 55.3
MILCON | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 660.7 |  |  | 781.7 | N/A |  |  | 1048.5 |  | 746.1 |  |  | 863.2 |  | 1247.1
1 APB Breach
Total Quantity - IDECM Block 4
Quantity |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  | 160 |  |  |  | 190 |  |  |  |  | 324
Total |  | 160 |  |  |  | 190 |  |  |  |  | 324

## Table 18
Cost and Funding
Funding Summary - Total Program
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020 | FY 2021 | To Complete | Total
RDT&E | 629.4 | 6.6 | 3.9 | 2.1 | 2.1 | 2.1 | 0 | 0 | 646.2
Procurement | 809.2 | 130.1 | 78.5 | 74.4 | 71.8 | 73.1 | 74.5 | 1248.9 | 2560.5
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2017 Total | 1438.6 | 136.7 | 82.4 | 76.5 | 73.9 | 75.2 | 74.5 | 1248.9 | 3206.7
PB 2016 Total | 1443.9 | 140.7 | 71.9 | 85.1 | 75.1 | 76.6 | 71.2 | 824.3 | 2788.8
Delta | -5.3 | -4 | 10.5 | -8.6 | -1.2 | -1.4 | 3.3 | 424.6 | 417.9

## Table 19
Cost and Funding
Funding Summary - IDECM Blocks 2/3
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 391 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 391
Procurement | 505.2 | 21.7 |  |  | 20.9 | 24.5 | 24.9 |  | 25.4 |  | 25.8 |  |  | 920.2 |  | 1568.6
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 896.2 | 21.7 |  |  | 20.9 | 24.5 | 24.9 |  | 25.4 |  | 25.8 |  |  | 920.2 |  | 1959.6
PB 2016 Total | 896.2 | 21.7 |  |  | 22.2 | 24.8 | 25.3 |  | 25.8 |  | 26.3 |  |  | 810 |  | 1852.3
Delta | 0 | 0 |  |  | -1.3 | -0.3 | -0.4 |  | -0.4 |  | -0.5 |  |  | 110.2 |  | 107.3
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 2190 |  | 284 | 261 | 319 |  | 317 | 317 |  | 316 |  | 8801 |  | 12805
PB 2017 Total | 0 |  | 2190 |  | 284 | 261 | 319 |  | 317 | 317 |  | 316 |  | 8801 |  | 12805
PB 2016 Total | 0 |  | 2190 |  | 285 | 289 | 330 |  | 332 | 336 |  | 339 |  | 8704 |  | 12805
Delta | 0 |  | 0 |  | -1 | -28 | -11 |  | -15 | -19 |  | -23 |  | 97 |  | 0

## Table 20
Funding Summary - IDECM Block 4
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 238.4 | 6.6 |  |  | 3.9 | 2.1 | 2.1 |  | 2.1 |  | 0 |  |  | 0 |  | 255.2
Procurement | 304 | 108.4 |  |  | 57.6 | 49.9 | 46.9 |  | 47.7 |  | 48.7 |  |  | 328.7 |  | 991.9
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 542.4 | 115 |  |  | 61.5 | 52 | 49 |  | 49.8 |  | 48.7 |  |  | 328.7 |  | 1247.1
PB 2016 Total | 547.7 | 119 |  |  | 49.7 | 60.3 | 49.8 |  | 50.8 |  | 44.9 |  |  | 14.3 |  | 936.5
Delta | -5.3 | -4 |  |  | 11.8 | -8.3 | -0.8 |  | -1 |  | 3.8 |  |  | 314.4 |  | 310.6
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 95 |  | 48 | 20 | 17 |  | 16 | 16 |  | 16 |  | 96 |  | 324
PB 2017 Total | 0 |  | 95 |  | 48 | 20 | 17 |  | 16 | 16 |  | 16 |  | 96 |  | 324
PB 2016 Total | 0 |  | 85 |  | 40 | 15 | 19 |  | 12 | 13 |  | 6 |  | 0 |  | 190
Delta | 0 |  | 10 |  | 8 | 5 | -2 |  | 4 | 3 |  | 10 |  | 96 |  | 134

## Table 21
Cost and Funding
Annual Funding By Appropriation - IDECM Blocks 2/3
Annual Funding - IDECM Blocks 2/3 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.8
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.6
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.7
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.2
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.5
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.3
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.9
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.6
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 391

## Table 22
Annual Funding - IDECM Blocks 2/3 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.7
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.5
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.9
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.9
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.7
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.3
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.5
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 456.4

## Table 23
Annual Funding - IDECM Blocks 2/3 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | 34.7 |  | 34.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | 25.9 |  | 25.9
2004 |  | 3 | 5.8 |  | -- |  | -- |  | 5.8 |  | 20 |  | 25.8
2005 |  | 12 | 21.6 |  | -- |  | -- |  | 21.6 |  | 14.4 |  | 36
2006 |  | 20 | 34.1 |  | -- |  | -- |  | 34.1 |  | 8.2 |  | 42.3
2007 |  | 14 | 26.5 |  | -- |  | -- |  | 26.5 |  | 8.4 |  | 34.9
2008 |  | 16 | 29.4 |  | -- |  | -- |  | 29.4 |  | 9.8 |  | 39.2
2009 |  | 9 | 20.8 |  | -- |  | 1.4 |  | 22.2 |  | 19.3 |  | 41.5
2010 |  | 10 | 28.9 |  | -- |  | -- |  | 28.9 |  | 13 |  | 41.9
2011 |  | 1 | 7.1 |  | -- |  | -- |  | 7.1 |  | 11.7 |  | 18.8
Subtotal |  | 85 | 174.2 |  | -- |  | 1.4 |  | 175.6 |  | 165.4 |  | 341

## Table 24
Annual Funding - IDECM Blocks 2/3 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | 39.1 |  | 39.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | 28.6 |  | 28.6
2004 |  | 3 | 6.2 |  | -- |  | -- |  | 6.2 |  | 21.5 |  | 27.7
2005 |  | 12 | 22.6 |  | -- |  | -- |  | 22.6 |  | 15 |  | 37.6
2006 |  | 20 | 34.7 |  | -- |  | -- |  | 34.7 |  | 8.3 |  | 43
2007 |  | 14 | 26.3 |  | -- |  | -- |  | 26.3 |  | 8.4 |  | 34.7
2008 |  | 16 | 28.8 |  | -- |  | -- |  | 28.8 |  | 9.6 |  | 38.4
2009 |  | 9 | 20.1 |  | -- |  | 1.4 |  | 21.5 |  | 18.6 |  | 40.1
2010 |  | 10 | 27.3 |  | -- |  | -- |  | 27.3 |  | 12.3 |  | 39.6
2011 |  | 1 | 6.6 |  | -- |  | -- |  | 6.6 |  | 10.8 |  | 17.4
Subtotal |  | 85 | 172.6 |  | -- |  | 1.4 |  | 174 |  | 172.2 |  | 346.2

## Table 25
Annual Funding - IDECM Blocks 2/3 1508 ¦ Procurement ¦ Procurement of Ammunition, Navy and Marine Corps
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | 3.8 |  | 3.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.4 |  | 0.4
2008 |  | 150 | 13.3 |  | -- |  | 4.3 |  | 17.6 |  | 1.7 |  | 19.3
2009 |  | 251 | 14 |  | -- |  | 1.4 |  | 15.4 |  | 1.5 |  | 16.9
2010 |  | 334 | 20.6 |  | -- |  | -- |  | 20.6 |  | 3.2 |  | 23.8
2011 |  | 282 | 17.2 |  | -- |  | -- |  | 17.2 |  | 1.8 |  | 19
2012 |  | 274 | 17.8 |  | -- |  | -- |  | 17.8 |  | 3 |  | 20.8
2013 |  | 269 | 17.5 |  | -- |  | -- |  | 17.5 |  | 1 |  | 18.5
2014 |  | 262 | 18.4 |  | -- |  | -- |  | 18.4 |  | 1.7 |  | 20.1
2015 |  | 283 | 19.9 |  | -- |  | -- |  | 19.9 |  | 1.7 |  | 21.6
2016 |  | 284 | 20.1 |  | -- |  | -- |  | 20.1 |  | 1.6 |  | 21.7
2017 |  | 261 | 19.2 |  | -- |  | -- |  | 19.2 |  | 1.7 |  | 20.9
2018 |  | 319 | 22.8 |  | -- |  | -- |  | 22.8 |  | 1.7 |  | 24.5
2019 |  | 317 | 23.2 |  | -- |  | -- |  | 23.2 |  | 1.7 |  | 24.9
2020 |  | 317 | 23.7 |  | -- |  | -- |  | 23.7 |  | 1.7 |  | 25.4
2021 |  | 316 | 24.1 |  | -- |  | -- |  | 24.1 |  | 1.7 |  | 25.8
2022 |  | 317 | 24.6 |  | -- |  | -- |  | 24.6 |  | 1.7 |  | 26.3
2023 |  | 318 | 25.1 |  | -- |  | -- |  | 25.1 |  | 1.8 |  | 26.9
2024 |  | 319 | 25.6 |  | -- |  | -- |  | 25.6 |  | 1.8 |  | 27.4
2025 |  | 320 | 26.1 |  | -- |  | -- |  | 26.1 |  | 1.8 |  | 27.9
2026 |  | 321 | 26.7 |  | -- |  | -- |  | 26.7 |  | 1.8 |  | 28.5
2027 |  | 322 | 27.2 |  | -- |  | -- |  | 27.2 |  | 1.8 |  | 29
2028 |  | 323 | 27.8 |  | -- |  | -- |  | 27.8 |  | 1.9 |  | 29.7
2029 |  | 324 | 28.4 |  | -- |  | -- |  | 28.4 |  | 1.9 |  | 30.3
2030 |  | 325 | 28.9 |  | -- |  | -- |  | 28.9 |  | 1.9 |  | 30.8
2031 |  | 326 | 29.5 |  | -- |  | -- |  | 29.5 |  | 1.9 |  | 31.4
2032 |  | 327 | 30.1 |  | -- |  | -- |  | 30.1 |  | 1.9 |  | 32
2033 |  | 328 | 30.8 |  | -- |  | -- |  | 30.8 |  | 2 |  | 32.8
2034 |  | 329 | 31.4 |  | -- |  | -- |  | 31.4 |  | 2 |  | 33.4
2035 |  | 330 | 32 |  | -- |  | -- |  | 32 |  | 2 |  | 34
2036 |  | 331 | 32.7 |  | -- |  | -- |  | 32.7 |  | 2 |  | 34.7
2037 |  | 332 | 33.4 |  | -- |  | -- |  | 33.4 |  | 2 |  | 35.4
2038 |  | 333 | 34.1 |  | -- |  | -- |  | 34.1 |  | 2.1 |  | 36.2
2039 |  | 334 | 34.8 |  | -- |  | -- |  | 34.8 |  | 2.1 |  | 36.9
2040 |  | 335 | 35.5 |  | -- |  | -- |  | 35.5 |  | 2.1 |  | 37.6
2041 |  | 336 | 36.2 |  | -- |  | -- |  | 36.2 |  | 2.1 |  | 38.3
2042 |  | 337 | 37 |  | -- |  | -- |  | 37 |  | 2.1 |  | 39.1
2043 |  | 338 | 37.7 |  | -- |  | -- |  | 37.7 |  | 2.2 |  | 39.9
2044 |  | 339 | 38.5 |  | -- |  | -- |  | 38.5 |  | 2.2 |  | 40.7
2045 |  | 340 | 39.3 |  | -- |  | -- |  | 39.3 |  | 2.2 |  | 41.5

## Table 26
2046 | 341 | 40.1 | -- | -- | 40.1 | 2.2 | 42.3
2047 | 342 | 40.9 | -- | -- | 40.9 | 2.2 | 43.1
2048 | 234 | 31.8 | -- | -- | 31.8 | 2.3 | 34.1
Subtotal | 12720 | 1138 | -- | 5.7 | 1143.7 | 83.9 | 1227.6

## Table 27
Annual Funding - IDECM Blocks 2/3 1508 ¦ Procurement ¦ Procurement of Ammunition, Navy and Marine Corps
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | 3.9 |  | 3.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.4 |  | 0.4
2008 |  | 150 | 13 |  | -- |  | 4.2 |  | 17.2 |  | 1.7 |  | 18.9
2009 |  | 251 | 13.5 |  | -- |  | 1.4 |  | 14.9 |  | 1.4 |  | 16.3
2010 |  | 334 | 19.5 |  | -- |  | -- |  | 19.5 |  | 3 |  | 22.5
2011 |  | 282 | 16 |  | -- |  | -- |  | 16 |  | 1.6 |  | 17.6
2012 |  | 274 | 16.3 |  | -- |  | -- |  | 16.3 |  | 2.7 |  | 19
2013 |  | 269 | 15.8 |  | -- |  | -- |  | 15.8 |  | 0.9 |  | 16.7
2014 |  | 262 | 16.4 |  | -- |  | -- |  | 16.4 |  | 1.5 |  | 17.9
2015 |  | 283 | 17.4 |  | -- |  | -- |  | 17.4 |  | 1.5 |  | 18.9
2016 |  | 284 | 17.3 |  | -- |  | -- |  | 17.3 |  | 1.4 |  | 18.7
2017 |  | 261 | 16.2 |  | -- |  | -- |  | 16.2 |  | 1.4 |  | 17.6
2018 |  | 319 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.4 |  | 20.3
2019 |  | 317 | 18.8 |  | -- |  | -- |  | 18.8 |  | 1.4 |  | 20.2
2020 |  | 317 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.3 |  | 20.2
2021 |  | 316 | 18.8 |  | -- |  | -- |  | 18.8 |  | 1.3 |  | 20.1
2022 |  | 317 | 18.8 |  | -- |  | -- |  | 18.8 |  | 1.3 |  | 20.1
2023 |  | 318 | 18.8 |  | -- |  | -- |  | 18.8 |  | 1.4 |  | 20.2
2024 |  | 319 | 18.8 |  | -- |  | -- |  | 18.8 |  | 1.3 |  | 20.1
2025 |  | 320 | 18.8 |  | -- |  | -- |  | 18.8 |  | 1.3 |  | 20.1
2026 |  | 321 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.2 |  | 20.1
2027 |  | 322 | 18.8 |  | -- |  | -- |  | 18.8 |  | 1.3 |  | 20.1
2028 |  | 323 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.3 |  | 20.2
2029 |  | 324 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.3 |  | 20.2
2030 |  | 325 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.2 |  | 20.1
2031 |  | 326 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.2 |  | 20.1
2032 |  | 327 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.2 |  | 20.1
2033 |  | 328 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.3 |  | 20.2
2034 |  | 329 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.2 |  | 20.1
2035 |  | 330 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.2 |  | 20.1
2036 |  | 331 | 18.9 |  | -- |  | -- |  | 18.9 |  | 1.2 |  | 20.1
2037 |  | 332 | 19 |  | -- |  | -- |  | 19 |  | 1.1 |  | 20.1
2038 |  | 333 | 19 |  | -- |  | -- |  | 19 |  | 1.2 |  | 20.2
2039 |  | 334 | 19 |  | -- |  | -- |  | 19 |  | 1.1 |  | 20.1
2040 |  | 335 | 19 |  | -- |  | -- |  | 19 |  | 1.1 |  | 20.1
2041 |  | 336 | 19 |  | -- |  | -- |  | 19 |  | 1.1 |  | 20.1
2042 |  | 337 | 19 |  | -- |  | -- |  | 19 |  | 1.1 |  | 20.1
2043 |  | 338 | 19 |  | -- |  | -- |  | 19 |  | 1.1 |  | 20.1
2044 |  | 339 | 19 |  | -- |  | -- |  | 19 |  | 1.1 |  | 20.1
2045 |  | 340 | 19.1 |  | -- |  | -- |  | 19.1 |  | 1 |  | 20.1

## Table 28
2046 | 341 | 19.1 | -- | -- | 19.1 | 1 | 20.1
2047 | 342 | 19.1 | -- | -- | 19.1 | 1 | 20.1
2048 | 234 | 14.5 | -- | -- | 14.5 | 1.1 | 15.6
Subtotal | 12720 | 743.6 | -- | 5.6 | 749.2 | 58.7 | 807.9

## Table 29
Annual Funding By Appropriation - IDECM Block 4
Annual Funding - IDECM Block 4 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.3
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 255.2

## Table 30
Annual Funding - IDECM Block 4 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.3
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.2
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.9
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 237.9

## Table 31
Annual Funding - IDECM Block 4 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | 7 | 33.1 |  | -- |  | 3.5 |  | 36.6 |  | 15.5 |  | 52.1
2013 |  | 17 | 42.7 |  | -- |  | -- |  | 42.7 |  | 21 |  | 63.7
2014 |  | 25 | 66.5 |  | -- |  | -- |  | 66.5 |  | 15 |  | 81.5
2015 |  | 46 | 87.3 |  | -- |  | -- |  | 87.3 |  | 19.4 |  | 106.7
2016 |  | 48 | 90.2 |  | -- |  | -- |  | 90.2 |  | 18.2 |  | 108.4
2017 |  | 20 | 50.5 |  | -- |  | -- |  | 50.5 |  | 7.1 |  | 57.6
2018 |  | 17 | 42.7 |  | -- |  | -- |  | 42.7 |  | 7.2 |  | 49.9
2019 |  | 16 | 39.7 |  | -- |  | -- |  | 39.7 |  | 7.2 |  | 46.9
2020 |  | 16 | 40.6 |  | -- |  | -- |  | 40.6 |  | 7.1 |  | 47.7
2021 |  | 16 | 41.5 |  | -- |  | -- |  | 41.5 |  | 7.2 |  | 48.7
2022 |  | 16 | 42.4 |  | -- |  | -- |  | 42.4 |  | 7.3 |  | 49.7
2023 |  | 16 | 43.3 |  | -- |  | -- |  | 43.3 |  | 7.3 |  | 50.6
2024 |  | 16 | 44.3 |  | -- |  | -- |  | 44.3 |  | 7.4 |  | 51.7
2025 |  | 16 | 45.2 |  | -- |  | -- |  | 45.2 |  | 7.5 |  | 52.7
2026 |  | 16 | 46.2 |  | -- |  | -- |  | 46.2 |  | 7.5 |  | 53.7
2027 |  | 16 | 47.2 |  | -- |  | -- |  | 47.2 |  | 7.6 |  | 54.8
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | 7.7 |  | 7.7
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | 7.8 |  | 7.8
Subtotal |  | 324 | 803.4 |  | -- |  | 3.5 |  | 806.9 |  | 185 |  | 991.9

## Table 32
Annual Funding - IDECM Block 4 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2012 |  | 7 | 30.3 |  | -- |  | 3.2 |  | 33.5 |  | 14.2 |  | 47.7
2013 |  | 17 | 38.6 |  | -- |  | -- |  | 38.6 |  | 19 |  | 57.6
2014 |  | 25 | 59.4 |  | -- |  | -- |  | 59.4 |  | 13.4 |  | 72.8
2015 |  | 46 | 76.8 |  | -- |  | -- |  | 76.8 |  | 17.1 |  | 93.9
2016 |  | 48 | 78 |  | -- |  | -- |  | 78 |  | 15.8 |  | 93.8
2017 |  | 20 | 42.9 |  | -- |  | -- |  | 42.9 |  | 6 |  | 48.9
2018 |  | 17 | 35.6 |  | -- |  | -- |  | 35.6 |  | 5.9 |  | 41.5
2019 |  | 16 | 32.4 |  | -- |  | -- |  | 32.4 |  | 5.9 |  | 38.3
2020 |  | 16 | 32.5 |  | -- |  | -- |  | 32.5 |  | 5.7 |  | 38.2
2021 |  | 16 | 32.6 |  | -- |  | -- |  | 32.6 |  | 5.6 |  | 38.2
2022 |  | 16 | 32.6 |  | -- |  | -- |  | 32.6 |  | 5.6 |  | 38.2
2023 |  | 16 | 32.7 |  | -- |  | -- |  | 32.7 |  | 5.5 |  | 38.2
2024 |  | 16 | 32.8 |  | -- |  | -- |  | 32.8 |  | 5.4 |  | 38.2
2025 |  | 16 | 32.8 |  | -- |  | -- |  | 32.8 |  | 5.4 |  | 38.2
2026 |  | 16 | 32.8 |  | -- |  | -- |  | 32.8 |  | 5.4 |  | 38.2
2027 |  | 16 | 32.9 |  | -- |  | -- |  | 32.9 |  | 5.3 |  | 38.2
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | 5.3 |  | 5.3
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | 5.2 |  | 5.2
Subtotal |  | 324 | 655.7 |  | -- |  | 3.2 |  | 658.9 |  | 151.7 |  | 810.6

## Table 33
Low Rate Initial Production
IDECM Blocks 2/3
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2000-12-01 | 2010-06-28
Approved Quantity | 1 | 735
Reference | Program Review ADM | Gate 6 Program Review ADM
Start Year | 2003 | 2003
End Year | 2004 | 2012
Total LRIP is a summation of six LRIP authorizations between CY 2000 and CY 2010.
IDECM Block 4
There is no LRIP for this program.

## Table 34
Foreign Military Sales
IDECM Blocks 2/3
Country | Date of Sale | Quantity | Total Cost $M | Description
Australia | 2011-07-21 | 9.9 |  | Australia procured IDECM Block 2/3 (ALE-55) systems as part of the Australian Super Hornet procurement, per Line 32, Amendment 2 of Case AT-P-SAF.
Australia | 2010-06-28 | 2.4 |  | Australia procured IDECM Block 2/3 (EFC) systems as part of the Australian Super Hornet procurement, per Line 32, Amendment 2 of Case AT-P-SAF.
Australia | 2009-04-17 | 4 |  | Australia procured IDECM Block 2/3 (ALE-55) systems as part of the Australian Super Hornet procurement, per Line 32, Amendment 2 of Case AT-P-SAF.
Australia | 2009-04-17 | 2.1 |  | Australia procured IDECM Block 2/3 (EFC) systems as part of the Australian Super Hornet procurement, per Line 32, Amendment 2 of Case AT-P-SAF.
Australia | 2008-02-07 | 43.5 |  | Australia procured IDECM Block 2/3 (ALQ-214) systems and spares as part of the Australian Super Hornet procurement, per Line 25, Amendment 1 of Case AT-P-SAF.
Notes
Australian quantities are considered sensitive by the country.
IDECM Block 4
None
Nuclear Costs
IDECM Blocks 2/3
None
IDECM Block 4
None

## Table 35
Unit Cost
IDECM Blocks 2/3
Unit Cost Report
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Current UCR Baseline (Apr 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1493.9 |  |  | 1610.5
Quantity | 12805 |  |  | 12805
Unit Cost | 0.117 |  |  | 0.126 |  | 7.69
Average Procurement Unit Cost
Cost | 1037.5 |  |  | 1154.1
Quantity | 12805 |  |  | 12805
Unit Cost | 0.081 |  |  | 0.0901 |  | 11.11
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Original UCR Baseline (Jun 2008 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1410.9 |  |  | 1610.5
Quantity | 12809 |  |  | 12805
Unit Cost | 0.11 |  |  | 0.126 |  | 14.55
Average Procurement Unit Cost
Cost | 956 |  |  | 1154.1
Quantity | 12809 |  |  | 12805
Unit Cost | 0.075 |  |  | 0.09 |  | 20
1
APB Unit Cost Breach

## Table 36
IDECM Blocks 2/3
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2008 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Jun 2008 |  |  |  |  | 0.11 |  |  | 0.075 |  |  | 0.12 |  |  | 0.089
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Jun 2011 |  |  |  |  | 0.11 |  |  | 0.075 |  |  | 0.12 |  |  | 0.089
Current APB |  |  | Feb 2014 |  |  |  |  | 0.117 |  |  | 0.081 |  |  | 0.13 |  |  | 0.1
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 0.122 |  |  | 0.086 |  |  | 0.145 |  |  | 0.114
Current Estimate |  |  | Dec 2015 |  |  |  |  | 0.126 |  |  | 0.09 |  |  | 0.153 |  |  | 0.122
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
0.120 -0.001 -0.001 0.021 0.000 0.010 0.000 0.004 0.033 0.153

## Table 37
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [8 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng | Est | Oth | Spt | Total
0.089 -0.001 -0.001 0.021 0.000 0.010 0.000 0.004 0.033 0.122
SAR Baseline History
Item |  |  | SAR Planning Estimate |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  | N/A |  | N/A |  |  | N/A |  |  | N/A
Milestone II |  |  | N/A |  | N/A |  |  | N/A |  |  | N/A
Milestone III |  |  | N/A |  | N/A |  |  | Nov 2003 |  |  | Nov 2003
IOC |  |  | N/A |  | N/A |  |  | Sep 2004 |  |  | Sep 2004
Total Cost (TY $M) |  |  | N/A |  | N/A |  |  | 1535.2 |  |  | 1959.6
Total Quantity |  |  | N/A |  | N/A |  |  | 12809 |  |  | 12805
PAUC |  |  | N/A |  | N/A |  |  | 0.12 |  |  | 0.153
Milestone III and IOC dates in the table above reflects IDECM Block 2 only.

## Table 38
Unit Cost Report
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Current UCR Baseline (Feb 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 781.7 |  |  | 1048.5
Quantity | 190 |  |  | 324
Unit Cost | 4.114 |  |  | 3.236 |  | -21.34
Average Procurement Unit Cost
Cost | 541.9 |  |  | 810.6
Quantity | 190 |  |  | 324
Unit Cost | 2.852 |  |  | 2.502 |  | -12.27
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Original UCR Baseline (Jun 2008 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 660.7 |  |  | 1048.5
Quantity | 160 |  |  | 324
Unit Cost | 4.129 |  |  | 3.236 |  | -21.63
Average Procurement Unit Cost
Cost | 451.2 |  |  | 810.6
Quantity | 160 |  |  | 324
Unit Cost | 2.82 |  |  | 2.502 |  | -11.28

## Table 39
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2008 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Jun 2008 |  |  |  |  | 4.129 |  |  | 2.82 |  |  | 4.663 |  |  | 3.262
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Apr 2012 |  |  |  |  | 4.114 |  |  | 2.852 |  |  | 4.543 |  |  | 3.206
Current APB |  |  | Feb 2014 |  |  |  |  | 4.114 |  |  | 2.852 |  |  | 4.543 |  |  | 3.206
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 4.311 |  |  | 3.062 |  |  | 4.929 |  |  | 3.588
Current Estimate |  |  | Dec 2015 |  |  |  |  | 3.236 |  |  | 2.502 |  |  | 3.849 |  |  | 3.061
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
4.663 -0.061 -1.668 0.689 0.195 -0.220 0.000 0.251 -0.814 3.849

## Table 40
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [9 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est | Oth | Spt | Total
3.262 -0.052 -0.960 0.689 0.000 -0.129 0.000 0.251 -0.201 3.061
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  | Mar 2009 |  |  | N/A |  |  | N/A
Milestone C |  |  | N/A |  |  | Mar 2012 |  |  | N/A |  |  | N/A
IOC |  |  | N/A |  |  | Feb 2014 |  |  | N/A |  |  | May 2015
Total Cost (TY $M) |  |  | N/A |  |  | 746.1 |  |  | N/A |  |  | 1247.1
Total Quantity |  |  | N/A |  |  | 160 |  |  | N/A |  |  | 324
PAUC |  |  | N/A |  |  | 4.663 |  |  | N/A |  |  | 3.849

## Table 41
Cost Variance
IDECM Blocks 2/3
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
391.0 1144.2 -- 1535.2
Economic |  | -1.3 |  | -0.7 |  | -- |  | -2
Quantity |  | -- |  | -11.2 |  | -- |  | -11.2
Schedule |  | -- |  | 239.6 |  | -- |  | 239.6
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 1.3 |  | 52.7 |  | -- |  | 54
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 36.7 |  | -- |  | 36.7
Subtotal |  | -- |  | 317.1 |  | -- |  | 317.1
Current Changes Economic |  | -- |  | -8.9 |  | -- |  | -8.9
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 29.7 |  | -- |  | 29.7
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | 76.1 |  | -- |  | 76.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 10.4 |  | -- |  | 10.4
Subtotal |  | -- |  | 107.3 |  | -- |  | 107.3
Total Changes |  | -- |  | 424.4 |  | -- |  | 424.4
CE - Cost Variance |  | 391 |  | 1568.6 |  | -- |  | 1959.6
CE - Cost & Funding |  | 391 |  | 1568.6 |  | -- |  | 1959.6

## Table 42
Summary BY 2008 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
454.9 956.0 -- 1410.9
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -10.5 |  | -- |  | -10.5
Schedule |  | -- |  | 90.4 |  | -- |  | 90.4
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 1.5 |  | 37.1 |  | -- |  | 38.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 28.5 |  | -- |  | 28.5
Subtotal |  | 1.5 |  | 145.5 |  | -- |  | 147
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 2 |  | -- |  | 2
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | 44.8 |  | -- |  | 44.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 5.8 |  | -- |  | 5.8
Subtotal |  | -- |  | 52.6 |  | -- |  | 52.6
Total Changes |  | 1.5 |  | 198.1 |  | -- |  | 199.6
CE - Cost Variance |  | 456.4 |  | 1154.1 |  | -- |  | 1610.5
CE - Cost & Funding |  | 456.4 |  | 1154.1 |  | -- |  | 1610.5
Previous Estimate: December 2014

## Table 43
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -8.9
Stretch-out of procurement buy profile of ALE-55 Fiber-Optic Towed Decoy (FOTD) from FY 2045 to FY 2048. (Schedule)
Additional schedule variance for stretch-out of procurement buy profile of ALE-55 FOTD from FY 2045 to FY2048. (Schedule)
0.0 +20.5
+2.0 +9.2
Adjustment for current and prior escalation. (Estimating) +0.6 +0.5
Estimate updated to reflect actuals. (Estimating) +44.2 +75.6
Adjustment for current and prior escalation. (Support) -0.1 0.0
Increase in Other Support to reflect revised Government in-house support due to extension of end of program from FY 2045 to FY 2048. (Support)
+5.9 +10.4
Procurement Subtotal +52.6 +107.3

## Table 44
Cost Variance
IDECM Block 4
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
224.2 521.9 -- 746.1
Economic |  | -2.4 |  | -12.7 |  | -- |  | -15.1
Quantity |  | -- |  | 69.8 |  | -- |  | 69.8
Schedule |  | -- |  | 63.1 |  | -- |  | 63.1
Engineering |  | 63.3 |  | -- |  | -- |  | 63.3
Estimating |  | -30.4 |  | -12.9 |  | -- |  | -43.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 52.6 |  | -- |  | 52.6
Subtotal |  | 30.5 |  | 159.9 |  | -- |  | 190.4
Current Changes Economic |  | -0.3 |  | -4.3 |  | -- |  | -4.6
Quantity |  | -- |  | 154.6 |  | -- |  | 154.6
Schedule |  | -- |  | 160 |  | -- |  | 160
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 0.8 |  | -28.9 |  | -- |  | -28.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 28.7 |  | -- |  | 28.7
Subtotal |  | 0.5 |  | 310.1 |  | -- |  | 310.6
Total Changes |  | 31 |  | 470 |  | -- |  | 501
CE - Cost Variance |  | 255.2 |  | 991.9 |  | -- |  | 1247.1
CE - Cost & Funding |  | 255.2 |  | 991.9 |  | -- |  | 1247.1

## Table 45
Summary BY 2008 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
209.5 451.2 -- 660.7
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 59.5 |  | -- |  | 59.5
Schedule |  | -- |  | 42 |  | -- |  | 42
Engineering |  | 57.9 |  | -- |  | -- |  | 57.9
Estimating |  | -30.2 |  | -10.9 |  | -- |  | -41.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 40 |  | -- |  | 40
Subtotal |  | 27.7 |  | 130.6 |  | -- |  | 158.3
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 108.1 |  | -- |  | 108.1
Schedule |  | -- |  | 123.7 |  | -- |  | 123.7
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 0.7 |  | -20.8 |  | -- |  | -20.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 17.8 |  | -- |  | 17.8
Subtotal |  | 0.7 |  | 228.8 |  | -- |  | 229.5
Total Changes |  | 28.4 |  | 359.4 |  | -- |  | 387.8
CE - Cost Variance |  | 237.9 |  | 810.6 |  | -- |  | 1048.5
CE - Cost & Funding |  | 237.9 |  | 810.6 |  | -- |  | 1048.5
Previous Estimate: December 2014

## Table 46
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.3
Adjustment for current and prior escalation. (Estimating) | 0.2 | 0.2
Revised estimate to reflect actuals (Estimating) | 0.5 | 0.6
RDT&E Subtotal | 0.7 | 0.5
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -4.3
Acceleration of procurement buy profile for ALQ-214(V)4/5s. (Schedule) 0.0 -5.4
Total Quantity variance resulting from an increase of 134 ALQ-214(V)4/5s from 190 to 324. (Subtotal)
Quantity variance resulting from an increase of 134 ALQ-214(V)4/5s from 190 to 324. (Quantity)
+324.8 +433.6
(+226.5) (+302.1)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+123.7) (+165.4) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-25.4) (-33.9)
Additional quantity variance resulting from an increase of 134 ALQ-214(V)4/5s from 190 to
324. (Quantity)
-118.4 -147.5
Adjustment for current and prior escalation. (Estimating) | 1.3 |  | 1.4
Revised estimate to reflect actuals. (Estimating) | 3.3 |  | 3.6
Adjustment for current and prior escalation. (Support) | 0.5 |  | 0.6
Increase in Other Support to reflect revised Government in-house support due to extension | 25.1 |  | 37.1
of end of program from FY 2023 to FY 2027. (Support)
Decrease in Initial Spares to reflect actuals. (Support) | -7.8 |  | -9
Procurement Subtotal | 228.8 |  | 310.1
(QR) Quantity Related

## Table 47
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: IDECM Block 3 (ALE-55/EFC) FRP 2, 3 & 4
Contractor: BAE Systems
Contractor Location: 66 Spit Brook Road
Nashua, NH 06060
Contract Number: N00019-13-C-0010
Contract Type: Firm Fixed Price (FFP)
Award Date: December 17, 2012
Definitization Date: July 01, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
50.8 N/A 660 80.8 N/A 1007 80.8 80.8
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the award of FRP 4.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 48
Contract Identification
Appropriation: Procurement
Contract Name: IDECM Block 3 (ALE-55 FOTD) FRP 6
Contractor: BAE Systems
Contractor Location: 65 Spit Brook Road
Nashua, NH 06060
Contract Number: N00019-16-C-0020
Contract Type: Firm Fixed Price (FFP)
Award Date: December 17, 2015
Definitization Date: December 17, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
20.9 N/A 284 20.9 N/A 284 20.9 20.9
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This is the first time this contract is being reported.

## Table 49
Contract Identification
Appropriation: Procurement
Contract Name: IDECM Block 4 (ALQ-214) FRP 9, 10 & 11
Contractor: ITT Exelis
Contractor Location: 77 River Road
Clifton, NJ 07014
Contract Number: N00019-12-C-0002
Contract Type: Firm Fixed Price (FFP)
Award Date: April 16, 2012
Definitization Date: December 03, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
64.3 N/A 23 291.6 N/A 131 291.6 291.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of two ALQ-214 systems, award of FRPs 10 and 11, and modification for FRP 9 test equipment.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 50
Contract Identification
Appropriation: Procurement
Contract Name: IDECM Block 4 (ALQ-214) FRP 12
Contractor: ITT Exelis
Contractor Location: 77 River Road
Clifton, NJ 07014
Contract Number: N00019-15-C-0104
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: July 30, 2015
Definitization Date: July 30, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
97.3 100.1 46 97.3 100.1 46 97.3 97.3
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
Notes
This is the first time this contract is being reported.
EVM waiver approved on July 23, 2015 by Deputy Assistant Secretary of the Navy (Acquisition and Procurement) (DASN (AP)).

## Table 51
Deliveries and Expenditures
IDECM Blocks 2/3
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 1987 | 1987 | 12805 | 15.52%
Total Program Quantity Delivered | 1987 | 1987 | 12805 | 15.52%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1959.6
847.1
43.23%
54
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
22
40.74%
917.9
46.84%
The above data is current as of February 09, 2016.
Deliveries reflect 85 ALQ-214s and 1,902 Fiber Optic Towed Decoys (FOTD). ALQ-214(V)3 deliveries are complete. Expenditures reflect IDECM Block 2/3 RDT&E, Aircraft Procurement, Navy (APN-5) and Procurement of Ammunition, Navy and Marine Corps.
IDECM Block 4
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 32 | 32 | 324 | 9.88%
Total Program Quantity Delivered | 32 | 32 | 324 | 9.88%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1247.1
339.7
27.24%
22
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
9
40.91%
657.4
52.71%
The above data is current as of February 09, 2016.

## Table 52
Operating and Support Cost
IDECM Blocks 2/3
Cost Estimate Details
Date of Estimate: February 01, 2015
Source of Estimate: POE
Quantity to Sustain: 85
Unit of Measure: System
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2006 - FY 2033
System - ALQ-214 (V)3 (quantity 85 ALQ-214(V)3 systems)
The ALE-55(V) is an expendable. The 12,720 ALE-55(V) systems are not included in the quantity of systems to sustain. Flight Hours per aircraft per month: 30
Number of Operating System Years: 1,770 Total Life Cycle Flight Hours: 63,720
Sustainment Strategy
The maintenance concept for the ALQ-214(V)2/3 and ALE-55(V) is two levels, Organizational to Depot. Organizational Level activities will include: removal and replacement of faulty Weapons Replacement Assemblies (WRAs) identified by Built In Test (BIT)/Maintenance Service Panel (MSP) Code; removal and replacement of the Magazine containing the faulty decoy identified by BIT/MSP Code; loading of Operational Flight Program/Mission Data File with Memory Loader Verifier System as required; retest by BIT to verify repair action; end-to-end testing with Organizational Support Equipment (OSE) as required; corrosion control and phase inspections. Maintenance Support for the IDECM Blocks 2/3 is performed by fleet personnel. There are presently no Contractor Engineering & Technical Services or United States Navy Engineering & Technical Services representatives. If additional support is required, the Type Commander can then request technical assistance for the IDECM Deputy Assistant Program Manager Logistics (DAPML). The DAPML will assess the issue and request support from the Fleet Support Team (FST) and/or Original Equipment Manufacturer (OEM).
Depot Level activities will include: removal and replacement of faulty modules/parts to the component or Shop Replaceable Assembly (SRA) level and verification of repair. Depot level maintenance consists of inspection, test, troubleshooting, repair, overhaul and disposal of WRAs/SRAs which are beyond repair. Depot support is provided by the OEMs managed by the Naval Supply System Command Weapons Systems Support, Philadelphia.
The ALQ-214(V)2/3 and ALE-55(V) will contain a BIT capability consisting of Periodic BIT (PBIT) and Initiated BIT (IBIT). IBIT will be used as a preflight and maintenance test on the ground when commanded by the mission computer or other controller. These BIT test determine if the ALQ-214(V)2/3 WRAs and the ALE-55(V) are operational. PBIT provides automatic and continuous monitoring of mission critical parameters on a background basis during normal system operation. PBIT will not fault isolate but will give clear indications of mission critical failures signaling that IBIT needs to be run. IBIT consists of a series of tests to assess the operational status of the system as well as fault isolate problem hardware. End-to-end testing with utilizing a combination of OSE and BIT as required. On the F/A-18E/F, the ALE-55(V) IBIT is run simultaneously with the ALQ-214(V)2/3.
A Maintenance Plan (MaPl) for IDECM Blocks 2/3 is currently available to support the logistics program. The MaPls are updated as necessary to reflect configuration changes. IDECM Blocks 2/3 MaPl is a deliverable from the Logistics Management Information database and contains all necessary information for interim supply support and development of

## Table 53
source data for the F/A-18 Interactive Electronic Technical Manual. The FST at Jacksonville presently manages the MaPls for the ALQ-214(V)2/3 and ALE-55(V).
Antecedent Information
• Antecedent program: Aircraft Self Protection Jammer (ASPJ)
• # of Aircraft Operating Years: 1,770 (Not actual, but used in order to provide a comparison between the ALQ-214(V) 3 Suite and its antecedent system)
The BY Antecedent Average Annual Cost per System is derived from total FY 2009 - FY 2011 cost from Naval Visibility and Management of Operating and Support Costs database Naval Aviation Maintenance Subsystem Report (NAMSR) divided by the total number of systems in NAMSR for FY 2009 - FY 2011. This value is then multiplied by the total number of operating system years associated with the ALQ-214(V)3 Suite to provide a point of comparison.
Annual O&S Costs BY2008 $K
Cost Element |  | IDECM Blocks 2/3 Average Annual Cost Per System | [5 empty] | Aircraft Self Protection Jammer (ASPJ) (Antecedent) Average Annual Cost Per ASPJ
Unit-Level Manpower |  | 0 | [5 empty] | 0
Unit Operations |  | 0 | [5 empty] | 0
Maintenance |  | 97.2 | [5 empty] | 91.883
Sustaining Support |  | 10.5 | [5 empty] | 8.307
Continuing System Improvements |  | 20.1 | [5 empty] | 7.692
Indirect Support |  | 0 | [5 empty] | 0
Other |  | 0 | [5 empty] | 0
Total |  | 127.8 | [5 empty] | 107.882
Item | Total O&S Cost $M
| IDECM Blocks 2/3 | [7 empty] | Aircraft Self Protection Jammer (ASPJ) (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 226.3 |  |  | 248.9 |  |  | 226.3 |  | 190.9
Then Year | 290.6 |  |  | N/A |  |  | 290.6 |  | N/A
Equation to Translate Annual Cost to Total Cost
The Average Annual Cost Per Aircraft for the ALQ-214(V)3 Suite is calculated by dividing the Total O&S Cost by the Total Operational System Years for the program.
ALQ-214(V)3 Total O&S Cost = ALQ-214(V)3 Annual O&S Cost per System * Total Operating System Years
$226.3M Total O&S Cost = $127.8K / System / Year * 1,770 Operating Years
O&S Cost Variance
Category |  |  | BY 2008 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 226.3

## Table 54
2014 SAR
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 226.3
Disposal Estimate Details
Date of Estimate: February 01, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2008 $M): Total costs for disposal of all System are 0.7
While these costs are not part of the CAPE 2007 O&S Cost Element Structure and hence are not included in the totals above, their Life Cycle Cost impact has been estimated at 0.680 BY 2008 $M and 1.059 TY $M.

## Table 55
IDECM Block 4
Cost Estimate Details
Date of Estimate: March 01, 2016
Source of Estimate: POE
Quantity to Sustain: 324
Unit of Measure: System
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2014 - FY 2038
System - ALQ-214
Flight Hours per aircraft per month: 30 Number of Operating System Years: 4,934 Total Life Cycle Flight Hours: 888,120
Sustainment Strategy
The IDECM Block 4 (IB-4), ALQ-214(V)4/5, is an Engineering Change Proposal to the ALQ-214(V)3 and as such will follow the same sustainment strategy and infrastructure established for the fielded ALQ-214(V)3.
The maintenance concept for the ALQ-214(V)4/5 is two levels, Organizational to Depot. Organizational Level activities will include: removal and replacement of faulty Weapons Replacement Assemblies (WRAs) identified by Built In Test (BIT)/Maintenance Service Panel Code; loading of Operational Flight Program/Mission Data File with Memory Loader Verifier System as required; retest by BIT to verify repair action; end-to-end testing with Organizational Support Equipment (OSE) as required; corrosion control and phase inspections. Maintenance Support for the IB-4 is performed by fleet personnel. There are presently no Contractor Engineering & Technical Services or Navy Engineering & Technical Services representatives. If additional support is required, the Type Commander can then request technical assistance for the IDECM Deputy Assistant Program Manager Logistics (DAPML). The DAPML will assess the issue and request support from the Fleet Support Team (FST) and/or Original Equipment Manfacturer (OEM).
Depot Level activities will include: removal and replacement of faulty modules/parts to the component or Shop Replaceable Assembly (SRA) level and verification of repair. Depot level maintenance consists of inspection, test, troubleshooting, repair, overhaul and disposal of WRAs/SRAs which are beyond repair. Depot support is provided by the OEMs managed by the Naval Supply Systems Command Weapon Systems Support, Philadelphia.
The ALQ-214(V)4/5 contain a BIT capability consisting of Periodic BIT (PBIT) and Initiated BIT (IBIT). IBIT is used as a preflight and maintenance test on the ground when commanded by the mission computer or other controller. These BIT determine if the ALQ-214(V)4/5 WRAs are operational. PBIT provides automatic and continuous monitoring of mission critical parameters on a background basis during normal system operation. PBIT will not fault isolate but will give clear indications of mission critical failures signaling that IBIT needs to be run. IBIT consists of a series of tests to assess the operational status of the system as well as fault isolate problem hardware. End-to-end testing utilizes a combination of OSE and BIT as required.
A preliminary Maintenance Plan (MaPl) for IB-4 is currently available to support the logistics program. The MaPls will be updated as necessary to reflect configuration changes. IB-4 MaPl is a deliverable from the Logistics Management Information database and contains all necessary information for interim supply support and development of source data for the F/A-18 Interactive Electronic Technical Manual. Following IOC, IB-4 MaPl management will transition to the FST at Fleet Readiness Center-Southeast, In-Service Support Center, Jacksonville, Florida.
Antecedent Information

## Table 56
• Antecedent program: Aircraft Self Protection Jammer (ASPJ)
• # of Aircraft Operating Years: 4,934 (Not actual, but used in order to provide a comparison between the ALQ-214(V) 4 Suite and its antecedent system)
The BY Antecedent Average Annual Cost per System is derived from total FY 2009 - FY 2011 cost from Naval Visibility and Management of Operating and Support Costs database Naval Aviation Maintenance Subsystem Report (NAMSR) divided by the total number of systems in NAMSR for FY 2009 - FY 2011. This value is then multiplied by the total number of operating system years associated with ALQ-214(V)4 Suite to provide a point of comparison.
Annual O&S Costs BY2008 $K
Cost Element |  |  | IDECM Block 4 Average Annual Cost Per System | [5 empty] | Aircraft Self Protection Jammer (ASPJ) (Antecedent) Average Annual Cost Per ASPJ
Unit-Level Manpower |  |  | 0 | [5 empty] | 0
Unit Operations |  |  | 0 | [5 empty] | 0
Maintenance |  |  | 63.268 | [5 empty] | 91.883
Sustaining Support |  |  | 3.906 | [5 empty] | 8.307
Continuing System Improvements |  |  | 8.243 | [5 empty] | 7.692
Indirect Support |  |  | 0 | [5 empty] | 0
Other |  |  | 0 | [5 empty] | 0
Total |  |  | 75.417 | [5 empty] | 107.882
Item | Total O&S Cost $M
| IDECM Block 4 | [8 empty] | Aircraft Self Protection Jammer (ASPJ) (Antecedent)
| Current Development APB Objective/Threshold | [5 empty] | Current Estimate
Base Year |  | 264.7 |  |  | 291.2 |  |  | 372.11 |  |  | 532.3
Then Year 1 APB O&S Cost Breach |  | 378.8 |  |  | N/A |  |  | 545.9 |  |  | N/A
Equation to Translate Annual Cost to Total Cost
The Average Annual Cost Per Aircraft for the ALQ-214(V)4 Suite is calculated by dividing the Total O&S Cost by the Total Operational System Years for the program.
ALQ-214(V)4 Total O&S Cost = ALQ-214(V)4 Annual O&S Cost per System * Total Operating System Years
$372.1M Total O&S Cost = $75.4K / System / Year * 4,934 Operating Years
O&S Cost Variance
Category |  |  |  | BY 2008 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
264.7
Programmatic/Planning Factors 107.4 Increase in O&S estimate to resulting from an increase of
134 ALQ-214(V)4/5 systems from 190 to 324.

## Table 57
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 107.4
Current Estimate 372.1
Disposal Estimate Details
Date of Estimate: February 01, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2008 $M): Total costs for disposal of all System are 1.5
While these costs are not part of the CAPE 2007 O&S Cost Element Structure and hence are not included in the totals above, their Life Cycle Cost impact has been estimated at 1.520 BY 2008 $M and 2.490 TY $M.