## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-238
Joint Precision Approach and Landing System Increment 1A (JPALS Inc 1A)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 24
Foreign Military Sales 25
Nuclear Costs 25
Unit Cost 26
Cost Variance 29
Contracts 32
Deliveries and Expenditures 33
Operating and Support Cost 34

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Joint Precision Approach and Landing System Increment 1A (JPALS Inc 1A)
DoD Component
Navy
Responsible Office
CAPT Joseph B. Hornbuckle, III
Program Executive Officer (T) (PMA-213) 46579 Expedition Drive
Expedition IV, 3rd Floor, Suite 301 Lexington Park, MD 20653
Joseph.Hornbuckle@navy.mil
Phone: 301-737-2091
Fax: 301-737-2100
DSN Phone: DSN Fax:
Date Assigned: July 23, 2015
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 19, 2008
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated December 19, 2008

## Table 6
Mission and Description
Precision approach and landing is a critical enabler for joint, coalition, combined, and inter-agency aviation assets to complete approaches and landings in limited visibility conditions. Today, the DoD relies heavily on a more expeditionary and agile joint force, which in turn places increased emphasis on aviation assets for deployment, employment, sustainment, and redeployment. To be readily available to the Joint Force Commander (JFC), aviation assets need to be able to operate into and out of all civil and military air facilities (airfields, landing areas, and air capable ships at sea) across the range of military operations in a fully automatic landing (auto-land) mode. A key to joint operational success is the ability of aviation assets to land anywhere, at any time. However, a standard precision approach and landing system with auto-land capability does not exist for joint forces, nor is there a standard system to fully support unmanned aircraft Precision Approach and Landing Capability (PALC) requirements.
Joint Precision Approach and Landing System (JPALS), in conjunction with the F-35B/C program, will provide precision guidance in support of coupled flight to 200 feet height above touchdown for the F-35B to Amphibious Assault (LH) type ships and precision guidance in support of auto-land for the F-35C and RAQ-25 to Nuclear Aircraft Carriers (CVN). JPALS will also support the F-35B/C and RAQ-25 interim PALC.
When delivered, the JPALS program will secure the minimum acceptable capability to support the joint military requirement and safeguard the future PALC requirements of any JPALS-equipped aircraft (e.g., F-35B/C and RAQ-25) during operations at sea in virtually any weather condition within platform limitations. These enhancements will support the JFC's vital sea- based combat capabilities across a broad range of military operations in an uncertain future.
JPALS is a Global Positioning System-based precision approach and landing system that will function in more operational environments, and support all DoD sea-based applications. The National Defense Strategy of the United States of America calls for highly mobile forces that can rapidly respond to crises worldwide. Success in meeting this challenge requires the ability to land aviation assets virtually anywhere, at any time. JPALS will provide this capability by being rapidly deployable, survivable, and interoperable with U.S. allies. JPALS will support manned and unmanned aircraft and will be able to operate during restricted emission control conditions.

## Table 7
Executive Summary
As reported in the December 2014 SAR, on January 28, 2014, the JPALS Inc 1A PM submitted a Program Deviation Report on a likely critical Nunn-McCurdy cost breach. On March 19, 2014, the Secretary of the Navy notified Congress and
the USD(AT&L) of the critical breach. Subsequently, USD(AT&L) initiated a Nunn-McCurdy review of the program, which resulted in certification of the restructured JPALS program on June 15, 2014. Accordingly, the July 2008 JPALS Milestone B decision was rescinded. The Navy was directed to continue auto-land trade studies and risk reduction efforts through third quarter FY 2016, develop a draft Technical Data Package (TDP) for the JPALS ship system (previously known as Increment 1A), complete Developmental Test (DT) with a Letter of Observation (LOO) from the Commander, Operational Test Force (COTF), and return to the Defense Acquisition Board (DAB) for Milestone B approval for the restructured JPALS program not later than third quarter FY 2016.
DT was completed and a LOO was signed by COTF on December 22, 2015; a draft TDP is scheduled for delivery
in second quarter FY 2016. The auto-land trade studies were completed, with the results defining the path forward to meet the auto-land requirements for manned and unmanned air vehicles. All JPALS ship system requirements have been developed, and a successful Government led System Requirements Review 1 and 2 was completed in March 2015. A Systems Functional Review (SFR) was conducted in November 2015. Remaining risk reduction trade studies to further refine the system's technical design are on track to complete in time to support the JPALS Preliminary Design Review (PDR) scheduled for second quarter FY 2016.
In support of the Nunn-McCurdy ADM and in preparation for returning to the DAB for Milestone B approval, a contract extension was awarded July 2015 to the existing EMD contract to enable the program to continue with requirements derivation and system development through PDR. The program completed a successful Navy Gate 4 Review in June 2015, followed by an Overarching Integrated Product Team (OIPT) review with Deputy Assistant Secretary of Defense (Tactical Warfare Systems) in July 2015. The Navy Gate 5 Review with Assistant Secretary, Navy (Research Development & Acquisition) was conducted October 26, 2015, followed by the DAB Readiness Meeting (DRM) on October 29, 2015. USD (AT&L) conducted a JPALS Development Request for Proposal (RFP) Release Decision Point (DRRDP) DAB review
on November 4, 2015, resulting in a signed ADM authorizing the release of the EMD RFP, which was released on November 23, 2015.
In anticipation of the post Milestone B contract for EMD, the program is on schedule for the planned Milestone B decision in third quarter FY 2016.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC Critical
APUC Critical
Original UCR Baseline
PAUC Critical
APUC Critical
The schedule breach, RDT&E and procurement cost breaches, and Nunn-McCurdy unit cost breaches were previously reported in
the December 2013 SAR.
As previously reported in the December 2013 SAR, JPALS Inc 1A experienced critical Nunn-McCurdy breaches. The June 2014 Nunn- McCurdy ADM certified the restructured JPALS program in lieu of termination. A revised APB for the restructured JPALS program will be approved in conjunction with Milestone B approval by the third quarter of FY 2016.
As previously reported in the December 2014 SAR, the O&S cost breach occurred as a result of the updated O&S cost estimate.
Nunn-McCurdy Breaches

## Table 9
Schedule
1 APB Breach
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
JPALS Increment 1A Milestone B | Jul 2008 | Jul 2008 | Jan 2009 | Jul 2008
SDD Contract Award | Jul 2008 | Jul 2008 | Jan 2009 | Jul 2008
Preliminary Design Review | Oct 2009 | Oct 2009 | Apr 2010 | Dec 2009
Critical Design Review | Oct 2010 | Oct 2010 | Apr 2011 | Dec 2010
EDM Delivery (LSTF Pax River) | Sep 2011 | Sep 2011 | Mar 2012 | Oct 2011
JPALS Increment 1A Milestone C | Feb 2013 | Feb 2013 | Aug 2013 | Mar 20191
IOT&E | Jan 2014 | Jan 2014 | Jul 2014 | Jul 20201
FRP | Jun 2015 | Jun 2015 | Dec 2015 | Sep 20211
IOC | Dec 2014 | Dec 2014 | Jun 2015 | Sep 20241
Change Explanations
None

## Table 10
Acronyms and Abbreviations
EDM - Engineering Development Model IOT&E - Initial Operational Test and Evaluation
JPALS - Joint Precision Approach and Landing System LSTF - Landing Systems Test Facility
Pax - Patuxent
SDD - System Development and Demonstration

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Network Ready: The system must support Net-Centric military operations. The system must be able to enter and be managed in the network, and exchange data in a secure manner to enhance mission effectiveness. The system must continuously provide survivable, interoperable, secure, and operationally effective information exchanges to enable a Net-Centric military capability.
The system must fully | The system must fully | The system must fully | TBD | The system must fully
support execution of | support execution of | support execution of |  | support execution of
operational activities | operational activities | joint critical operational |  | joint critical operational
identified in the | identified in the | activities identified in |  | activities identified in
applicable joint and | applicable joint and | the applicable joint and |  | the applicable joint and
system integrated | system integrated | system integrated |  | system integrated
architectures and the | architectures and the | architectures and the |  | architectures and the
system must satisfy the | system must satisfy | system must satisfy |  | system must satisfy
technical requirements | the technical | the technical |  | the technical
for Net-Centric military | requirements for Net- | requirements for |  | requirements for
operations to include: 1) | Centric military | transition to Net- |  | transition to Net-
DISR mandated GIG IT | operations to include: | Centric military |  | Centric military
standards and profiles | 1) DISR mandated GIG | operations to include: |  | operations to include:
identified in the TV-1, 2) | IT standards and | 1) DISR mandated GIG |  | 1) DISR mandated GIG
DISR mandated GIG | profiles identified in the | IT standards and |  | IT standards and
KIPs identified in the KIP | TV-1, 2) DISR | profiles identified in the |  | profiles identified in the
declaration table, 3) | mandated GIG KIPs | TV-1, 2) DISR |  | TV-1, 2) DISR
NCOW RM Enterprise | identified in the KIP | mandated GIG KIPs |  | mandated GIG KIPs
Services, 4) IA | declaration table, 3) | identified in the KIP |  | identified in the KIP
requirements including | NCOW RM Enterprise | declaration table, 3) |  | declaration table, 3)
availability, integrity, | Services, 4) IA | NCOW RM Enterprise |  | NCOW RM Enterprise
authenticat-ion, | requirements including | Services, 4) IA |  | Services, 4) IA
confidential-ity, and | availability, integrity, | requirements including |  | requirements including
nonrepudiat-ion, and | authenticat-ion, | availability, integrity, |  | availability, integrity,
issuance of an ATO by | confidential-ity, and | authenticat-ion, |  | authentica-tion,
the DAA, and 5) | nonrepudiat-ion, and | confidential-ity, and |  | confidential-ity, and
Operationally effective | issuance of an ATO by | nonrepudiat-ion, and |  | nonrepudiati-on, and
information exchanges; | the DAA, and 5) | issuance of an IATO by |  | issuance of an IATO by
mission critical | Operationally effective | the (DAA), and 5) |  | the (DAA), and 5)
performance and IA | information | Operationally effective |  | Operationally effective
attributes; data | exchanges; mission | information exchanges; |  | information exchanges;
correctness, data | critical performance | mission critical |  | mission critical
availability, and | and IA attributes; data | performance and IA |  | performance and IA
consistent data | correctness, data | attributes; data |  | attributes; data
processing specified in | availability, and | correctness, data |  | correctness, data
the applicable joint and | consistent data | availability, and |  | availability, and
system integrated | processing specified in | consistent data |  | consistent data
architecture views. | the applicable joint and | processing specified in |  | processing specified in
| system integrated | the applicable joint and |  | the applicable joint and
| architecture views. | system integrated |  | system integrated

## Table 12
|  | architecture views. |  | architecture views.
Guidance Quality
Certification for | Certification for | Sufficient quality to | Coupled | Meeting Threshold with
operations in 0 ft ceiling | operations in 0 ft | allow the Service to | approaches to | margin. Sufficient
and 0 NM visibility | ceiling and 0 NM | certify the sea-based | the deck were | quality to allow the
conditions. | visibility conditions. | system for use in 200 ft | demonstrated at | Service to certify the
|  | ceiling and ½ NM | -sea with test | sea-based system for
|  | visibility weather | aircraft under | use in 200 ft ceiling and
|  | conditions. | test conditions. | ½ NM visibility weather
conditions.
Manpower
Should reduce current | Should reduce current | The total number of | TBD | Current manning level
manning levels when | manning levels when | dedicated maintenance
currently fielded | currently fielded | and/or logistics
systems are phased | systems are phased | personnel needed to
out. Should require no | out. Should require no | support Sea-Based
dedicated personnel. | dedicated personnel. | JPALS per shift shall
Should be reduced to no | Should be reduced to | be no more than one
more than one qualified | no more than one | person. The number of
air traffic controller. | qualified air traffic | qualified final controller
| controller. | positions per shift on
CVN/LH ship classes
shall be no more than
two air traffic
controllers.
Operational Availability (Ao) in Clear Air
JPALS Ao requirement | JPALS Ao requirement | JPALS Ao requirement | TBD | 99.1%
in clear air for manned | in clear air for manned | in clear air for manned
aircraft to 200 ft - ½ NM | aircraft to 200 ft - ½ | aircraft to 200 ft - ½ NM
mins should be at least | NM mins should be at | mins shall be at least
99.7%. | least 99.7%. | 99.0%.
Requirements Reference
Capability Development Document (CDD) dated March 16, 2007
Change Explanations
None

## Table 13
Acronyms and Abbreviations
Ao - Operational Availability ATO - Approval to Operate CVN - Nuclear Aircraft Carrier
DAA - Designated Approval Authority
DISR - DOD Information Technology Standards and Profile Registry ft - feet
GIG - Global Information Grid IA - Information Assurance
IATO - Interim Approval to Operate IT - Information Technology
KIP - Key Interface Profile
LH - Amphibious Assault Ship mins - minimums
NCOW RM - Net Centric Operations and Warfare Reference Model NM - Nautical Mile
TV - Technical Standards View

## Table 14
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy 1319 04 0603860N
Project | Name
2329 JPALS
Procurement
Appn |  |  | BA | PE
Navy |  | 1810 02 |  | 0305014N
|  | Line Item |  | Name
|  | 2867 |  | Joint Precision Approach and Landing System
Navy |  | 1810 08 |  | 0305014N
|  | Line Item |  | Name
|  | 9020 |  | Spares and Repair Parts (Shared)
MILCON
Appn |  |  | BA | PE
Navy 1205 01 0805376N
Project | Name
P977 Facilities Restoration and Modification - RDT&E (Sunk)

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2008 $M | [5 empty] | BY 2008 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E | 753.7 |  |  | 753.7 | 829.1 |  |  | 1299.41 |  | 781.4 |  |  | 781.4 |  | 1433.3
Procurement | 202.9 |  |  | 202.9 | 223 |  |  | 418.11 |  | 243.7 |  |  | 243.7 |  | 540.1
Flyaway | -- |  |  | -- | -- |  |  | 317.3 |  | -- |  |  | -- |  | 409
Recurring | -- |  |  | -- | -- |  |  | 317.3 |  | -- |  |  | -- |  | 409
Non Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support | -- |  |  | -- | -- |  |  | 100.8 |  | -- |  |  | -- |  | 131.1
Other Support | -- |  |  | -- | -- |  |  | 83.8 |  | -- |  |  | -- |  | 108.9
Initial Spares | -- |  |  | -- | -- |  |  | 17 |  | -- |  |  | -- |  | 22.2
MILCON | 6.6 |  |  | 6.6 | 7.3 |  |  | 6.6 |  | 6.8 |  |  | 6.8 |  | 6.8
Acq O&M | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 963.2 |  |  | 963.2 | N/A |  |  | 1724.1 |  | 1031.9 |  |  | 1031.9 |  | 1980.2
1 APB Breach
Total Quantity
Quantity |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  | 12 |  |  |  | 12 |  |  |  |  | 10
Procurement |  | 25 |  |  |  | 25 |  |  |  |  | 17
Total |  | 37 |  |  |  | 37 |  |  |  |  | 27
Quantity Notes
Unit of Measure: The physical architecture of Joint Precision Approach and Landing System (JPALS) consists of multiple equipment racks, processing equipment, sensors, radios, and antennas.

## Table 16
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 849.9 | 81.5 |  | 104.1 |  | 105 | 102.6 |  | 50.7 |  | 39 |  | 100.5 |  |  | 1433.3
Procurement | 0 | 0 |  | 0 |  | 0 | 58.7 |  | 69.1 |  | 70.4 |  | 341.9 |  |  | 540.1
MILCON | 6.8 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 6.8
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
PB 2017 Total | 856.7 | 81.5 |  | 104.1 |  | 105 | 161.3 |  | 119.8 |  | 109.4 |  | 442.4 |  |  | 1980.2
PB 2016 Total | 854.1 | 91.5 |  | 76.4 |  | 28.7 | 60.5 |  | 70.5 |  | 91.4 |  | 325.1 |  |  | 1598.2
Delta | 2.6 | -10 |  | 27.7 |  | 76.3 | 100.8 |  | 49.3 |  | 18 |  | 117.3 |  |  | 382
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 10 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 10
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 4 |  | 3 | 3 |  | 7 |  | 17
PB 2017 Total | 10 |  | 0 |  | 0 | 0 | 0 |  | 4 |  | 3 | 3 |  | 7 |  | 27
PB 2016 Total | 10 |  | 0 |  | 0 | 0 | 0 |  | 2 |  | 3 | 3 |  | 9 |  | 27
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 2 |  | 0 | 0 |  | -2 |  | 0

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 74.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 134.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 75.5
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 126.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 104.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.7
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.6
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.8
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.8
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.4
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.9
Subtotal |  | 10 | -- |  | -- |  | -- |  | -- |  | -- |  | 1433.3

## Table 18
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.5
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.2
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 129.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 111.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 114.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 71.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.2
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.5
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.1
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.6
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.3
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.2
Subtotal |  | 10 | -- |  | -- |  | -- |  | -- |  | -- |  | 1299.4

## Table 19
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | 4 | 46.3 |  | -- |  | -- |  | 46.3 |  | 12.4 |  | 58.7
2020 |  | 3 | 55.7 |  | -- |  | -- |  | 55.7 |  | 13.4 |  | 69.1
2021 |  | 3 | 56.8 |  | -- |  | -- |  | 56.8 |  | 13.6 |  | 70.4
2022 |  | 4 | 91.9 |  | -- |  | -- |  | 91.9 |  | 30.4 |  | 122.3
2023 |  | 3 | 90.1 |  | -- |  | -- |  | 90.1 |  | 30 |  | 120.1
2024 |  | -- | 51.6 |  | -- |  | -- |  | 51.6 |  | 14.2 |  | 65.8
2025 |  | -- | 16.6 |  | -- |  | -- |  | 16.6 |  | 3.8 |  | 20.4
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | 13.3 |  | 13.3
Subtotal |  | 17 | 409 |  | -- |  | -- |  | 409 |  | 131.1 |  | 540.1

## Table 20
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2008 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | 4 | 38 |  | -- |  | -- |  | 38 |  | 10.2 |  | 48.2
2020 |  | 3 | 44.8 |  | -- |  | -- |  | 44.8 |  | 10.8 |  | 55.6
2021 |  | 3 | 44.8 |  | -- |  | -- |  | 44.8 |  | 10.7 |  | 55.5
2022 |  | 4 | 71 |  | -- |  | -- |  | 71 |  | 23.5 |  | 94.5
2023 |  | 3 | 68.3 |  | -- |  | -- |  | 68.3 |  | 22.7 |  | 91
2024 |  | -- | 38.3 |  | -- |  | -- |  | 38.3 |  | 10.6 |  | 48.9
2025 |  | -- | 12.1 |  | -- |  | -- |  | 12.1 |  | 2.8 |  | 14.9
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | 9.5 |  | 9.5
Subtotal |  | 17 | 317.3 |  | -- |  | -- |  | 317.3 |  | 100.8 |  | 418.1

## Table 21
Cost Quantity Information 1810 ¦ Procurement ¦ Other Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2008 $M
2019 | 4 | 78.3
2020 | 3 | 44.8
2021 | 3 | 44.8
2022 | 4 | 81.1
2023 | 3 | 68.3
2024 | -- | --
2025 | -- | --
2026 | -- | --
Subtotal | 17 | 317.3

## Table 22
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2008 6.8
Subtotal 6.8

## Table 23
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2008 $M
Total Program
2008 6.6
Subtotal 6.6

## Table 24
Low Rate Initial Production
There is no LRIP for this program.

## Table 25
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
United Kingdom 6/1/2012 1 3.9 This is a technical services case.
Notes
There is a technical services case with the United Kingdom (UK) which has been extended through the end of December 2016 to allow for the exchange of technical information and services for both the AN/SPN-41 instrument carrier landing system and the JPALS ship system. This technical service case also allows further discussions between the U.S. and UK in support of a JPALS procurement decision. There are no Technology Security/Foreign Disclosure issues related to the technical services case with the UK.
Nuclear Costs
None

## Table 26
Unit Cost
Unit Cost Report
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Current UCR Baseline (Dec 2008 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 963.2 |  |  | 1724.1
Quantity | 37 |  |  | 27
Unit Cost | 26.032 |  |  | 63.856 |  | +145.301
Average Procurement Unit Cost
Cost | 202.9 |  |  | 418.1
Quantity | 25 |  |  | 17
Unit Cost | 8.116 |  |  | 24.594 |  | +203.031
Item |  | BY 2008 $M | BY 2008 $M |  | % Change
|  | Original UCR Baseline (Dec 2008 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 963.2 |  |  | 1724.1
Quantity | 37 |  |  | 27
Unit Cost | 26.032 |  |  | 63.856 |  | +145.301
Average Procurement Unit Cost
Cost | 202.9 |  |  | 418.1
Quantity | 25 |  |  | 17
Unit Cost | 8.116 |  |  | 24.594 |  | +203.031
1
Nunn-McCurdy Breach
JPALS Inc 1A previously reported critical Nunn-McCurdy breaches and provided detailed Unit Cost reporting in the December 2013 SAR. The Department certified a restructured program to Congress on June 15, 2014. This section will be updated when an APB is approved at Milestone B.

## Table 27
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2008 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Dec 2008 |  |  |  |  | 26.032 |  |  | 8.116 |  |  | 27.889 |  |  | 9.748
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Dec 2008 |  |  |  |  | 26.032 |  |  | 8.116 |  |  | 27.889 |  |  | 9.748
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 52.237 |  |  | 24.865 |  |  | 59.193 |  |  | 32.324
Current Estimate |  |  | Dec 2015 |  |  |  |  | 63.856 |  |  | 24.594 |  |  | 73.341 |  |  | 31.771
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
27.889 -0.659 7.878 9.881 8.148 17.441 0.000 2.763 45.452 73.341
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
9.748 -0.871 1.018 1.412 0.000 16.076 0.000 4.388 22.023 31.771

## Table 28
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Jul 2008 | N/A | Jul 2008
Milestone C | N/A | Feb 2013 | N/A | Mar 2019
IOC | N/A | Dec 2014 | N/A | Sep 2024
Total Cost (TY $M) | N/A | 1031.9 | N/A | 1980.2
Total Quantity | N/A | 37 | N/A | 27
PAUC | N/A | 27.889 | N/A | 73.341

## Table 29
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
781.4 243.7 6.8 1031.9
Economic |  | -1.2 |  | -10.3 |  | -- |  | -11.5
Quantity |  | -5.5 |  | -60.7 |  | -- |  | -66.2
Schedule |  | 242.8 |  | 28.6 |  | -- |  | 271.4
Engineering |  | 220 |  | -- |  | -- |  | 220
Estimating |  | -195.6 |  | 273 |  | -- |  | 77.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 75.2 |  | -- |  | 75.2
Subtotal |  | 260.5 |  | 305.8 |  | -- |  | 566.3
Current Changes Economic |  | -1.8 |  | -4.5 |  | -- |  | -6.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -4.6 |  | -- |  | -4.6
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 393.2 |  | 0.3 |  | -- |  | 393.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -0.6 |  | -- |  | -0.6
Subtotal |  | 391.4 |  | -9.4 |  | -- |  | 382
Total Changes |  | 651.9 |  | 296.4 |  | -- |  | 948.3
CE - Cost Variance |  | 1433.3 |  | 540.1 |  | 6.8 |  | 1980.2
CE - Cost & Funding |  | 1433.3 |  | 540.1 |  | 6.8 |  | 1980.2

## Table 30
Summary BY 2008 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
753.7 202.9 6.6 963.2
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -5.1 |  | -49.1 |  | -- |  | -54.2
Schedule |  | 214.5 |  | 7.8 |  | -- |  | 222.3
Engineering |  | 191.6 |  | -- |  | -- |  | 191.6
Estimating |  | -173.6 |  | 208.6 |  | -- |  | 35
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 52.5 |  | -- |  | 52.5
Subtotal |  | 227.4 |  | 219.8 |  | -- |  | 447.2
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 318.3 |  | -3.9 |  | -- |  | 314.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -0.7 |  | -- |  | -0.7
Subtotal |  | 318.3 |  | -4.6 |  | -- |  | 313.7
Total Changes |  | 545.7 |  | 215.2 |  | -- |  | 760.9
CE - Cost Variance |  | 1299.4 |  | 418.1 |  | 6.6 |  | 1724.1
CE - Cost & Funding |  | 1299.4 |  | 418.1 |  | 6.6 |  | 1724.1
Previous Estimate: December 2014

## Table 31
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -1.8
Revised estimate to meet post Nunn-McCurdy certification. (Estimating) |  | 329.4 | 406.3
Revised estimate to reflect prior year actuals. (Estimating) |  | 2.7 | 2.9
Revised estimate due to Congressional budget adjustments. (Estimating) |  | -8.7 | -10
Revised estimate due to Service level budget adjustments. (Estimating) |  | -6.1 | -7.1
Adjustment for current and prior escalation. (Estimating) |  | 1 | 1.1
RDT&E Subtotal |  | 318.3 | 391.4
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -4.5
Acceleration of procurement buy-profile shifting two systems to FY 2019 from FY 2023 and FY 2024. (Schedule)
0.0 -4.6
Revised estimate based on government staffing plan updates. (Estimating) | -3.9 |  |  | 0.3
Decrease in Other Support due to training estimate changes. (Support) | -0.6 |  |  | -0.9
Increase in Initial Spares due to Service level budget adjustments. (Support) | -0.1 |  |  | 0.3
Procurement Subtotal | -4.6 |  |  | -9.4

## Table 32
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: JPALS Development Contract
Contractor: Raytheon Company
Contractor Location: 1801 Hughes Drive
Fullerton, CA 92833-2200
Contract Number: N00019-08-C-0034
Contract Type: Cost Plus Award Fee (CPAF), Cost Plus Incentive Fee (CPIF), Firm Fixed Price (FFP)
Award Date: September 15, 2008
Definitization Date: September 15, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
232.8 N/A 12 427.1 N/A 10 424.4 427.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to EMD contract completion and the Phase I 19-month and 11-month JPALS Inc 1A EMD contract extensions being awarded for risk reduction activities in support of manned and unmanned auto-land capability improvements. There was also a Technical Incentive Fee payout of $6.3M and a cost overrun of $1.3M.
Current Contract Price includes all CLINs. This includes FFP CLIN for proposal costs, award fee and schedule incentive payout out on separate CLINs, travel costs CLIN, and separate CLINs for the integration work and availability in Jamming.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -28.2 -0.8
Previous Cumulative Variances -27.0 +0.2
Net Change -1.2 -1.0
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to additional unplanned work developing the navigational sensor for the Global Positioning System/Intertial Navigation System and unplanned work upgrading from Windows 7 to Windows 10. Conversion from old Integrated Data Environment system to new system was complex with the inclusion of the subcontractor's system. Software efforts added to the cost variance with more rework than planned.
The unfavorable net change in the schedule variance is due to Systems Engineering requiring additional time to complete a planned trade study than originally estimated. Training was required for new resources for Technical Publications.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 33
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 8 | 8 | 10 | 80%
Production | 0 | 0 | 17 | 0%
Total Program Quantity Delivered | 8 | 8 | 27 | 29.63%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
1980.2
855.1
43.18%
26
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
16
61.54%
938.2
47.38%
The above data is current as of February 09, 2016.

## Table 34
Operating and Support Cost
Cost Estimate Details
Date of Estimate: December 31, 2015
Source of Estimate: POE
Quantity to Sustain: 25
Unit of Measure: System
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2020 - FY 2046
The December 2015 SAR estimate is for all JPALS ship systems and a single Naval Air Technical Training Center (NATTC) trainer from FY2020 - FY2046 with a system service life assumed to end in 2046. The service life is expected to be at least 20 years with no end of life defined at this time. The ramp up period is from FY2020-FY2026 with the last certification scheduled for FY2026.
The sustainment quantity of 25 systems is based on the 17 productions systems funded by Other Procurement, Navy (OPN); 2 of the development systems funded by Research, Development, Test, & Evaluation (RDT&E); and 6 systems being procured by the Naval Sea Systems command (NAVSEA) funded by Shipbuilding and Conversion, Navy (SCN). The JPALS Inc 1A program office is not responsible for the acquisition of the NAVSEA units and not included in the Deliveries and Expenditures section, but is responsible for the sustainment of these units. Eight of the developmental units are considered test assets and therefore not explicitly identified in the O&S estimate.
JPALS Systems: 24 Nuclear Aircraft Carriers (CVN)/Amphibious Assault (LH) Class Ships and 1 NATTC Trainer Life Cycle Cost Estimate: 20 years after the last install/certification
Total Operating Years: 608 years
Annual Operation Tempo: 4,000 hours per ship and 3,500 hours for NATTC No sundown period or disposal costs planned
Sustainment Strategy
The program is pre-Milestone B as a result of June 2014 Nunn-McCurdy decision. The program is scheduled for Milestone B in the third quarter of FY 2016.
The sustainment strategy is being analyzed. The current estimate assumes a 2-level Organizational - Depot (O-D) maintenace concept. The O-D maintenance concept will be evaluated during two planned Business Case Analysis addressing the Software Support Activity and Depot Source of Repair. Maintenance is based on a historical average of 4,000 annual operating hours for every ship beginning in the year of installation or certification and utilizes the predicted reliability and maintainabilty rates. Sustaining Engineering has been identified in the In-Service Engineering Activity support plan. The JPALS system is expected to be removed from a decommissioned ship and installed on a similar new type ship. The decommissioned schedule is based on a 50 year service life of the ship. Hardware and software improvements are based on comparable system historical percentages.
Antecedent Information
The antecedent system associated with this estimate is the AN/SPN-46(V)3. Legacy systems continue to experience service life adjustments and system modification that make Total O&S Costs compilation in a static service life (e.g., 25 years) to be not credible. In addition, the capture of O&S data in available reporting systems has changed significantly

## Table 35
over time. The Visibility and Management of Operating and Support Costs database, the Navy's official system for collecting and reporting O&S costs, provides costs from 1997-present. The cost data for platforms in existence prior to 1997 is either unavailable or incomplete. Sufficient historical data and resources do not exist to create comparable, credible Total O&S Costs.
The AN/SPN-46(V)3 is an analogous system to the JPALS system with the Precision Approach Landing Capability (PALC) Roadmap decision. The AN/SPN-46(V)3 will remain in service on the ships as the landing system for legacy aircraft.
Annual O&S Costs BY2008 $M
Cost Element |  |  | JPALS Inc 1A Average Annual Cost Per System |  |  |  | AN/SPN-46(V)3 (Antecedent) Average Annual Cost Per System
Unit-Level Manpower |  |  | 0 |  |  |  | 0.716
Unit Operations |  |  | 0 |  |  |  | 0
Maintenance |  |  | 0.524 |  |  |  | 0.051
Sustaining Support |  |  | 0.203 |  |  |  | 0.027
Continuing System Improvements |  |  | 0.131 |  |  |  | 0.408
Indirect Support |  |  | 0 |  |  |  | 0
Other |  |  | 0 |  |  |  | 0
Total |  |  | 0.858 |  |  |  | 1.202
Item | Total O&S Cost $M
| JPALS Inc 1A | [6 empty] | AN/SPN-46(V)3 (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year |  | 338.6 |  | 372.5 |  | 521.81 |  |  | 0
Then Year 1 APB O&S Cost Breach |  | 520.6 |  | N/A |  | 867.8 |  |  | N/A
The O&S cost estimate has been updated to reflect quantity, schedule, and scope changes as a result of the Nunn- McCurdy process. The O&S estimate will be updated for Milestone B to reflect quantity, schedule, and scope changes to reflect the Technical and Programmatic Baseline following the JPALS Engineering Technical Assurance Board review in January 2016.
Equation to Translate Annual Cost to Total Cost
JPALS Average Annual Unit O&S Cost * 608 operating system years = Total JPALS O&S Cost
The unitized costs are based on the 608 operating years. This is the cumulative total of the systems operating through FY2046. $521.7 = $0.858 * 608 operating years. The small delta between this calculated value and the total O&S cost shown is due to rounding. The unitized costs include the NATTC unit, OPN ships, and SCN ships.
O&S Cost Variance

## Table 36
Category | BY 2008 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
512
Programmatic/Planning Factors -2.7 Ship schedule updates and 2016 Inflation Indices
Cost Estimating Methodology 0.0
Cost Data Update 12.5 Updates to simulator annual cost and repair pricing changes
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 9.8
Current Estimate 521.8
The O&S Cost Variances are due to ship schedule updates, annual simulator costs, and repair pricing changes.
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2008 $M):
Disposal costs have not been identified at this time.