## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-443
Littoral Combat Ship Mission Modules (LCS MM)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 12
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 34
Foreign Military Sales 35
Nuclear Costs 35
Unit Cost 36
Cost Variance 39
Contracts 42
Deliveries and Expenditures 44
Operating and Support Cost 45

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Littoral Combat Ship Mission Modules (LCS MM)
DoD Component
Navy
Responsible Office
CAPT Casey Moton 1333 Isaac Hull Ave, SE
Washington Navy Yard, DC 20376
casey.moton@navy.mil
Phone: 202-781-2303
Fax: 202-781-4696
DSN Phone: DSN Fax:
Date Assigned: July 28, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated November 27, 2013
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated November 27, 2013

## Table 6
Mission and Description
The Littoral Combat Ship (LCS) is a fast, agile, and networked surface combatant optimized for operations close to shore, otherwise known as the littorals. The LCS Mission Modules (MM) provide a modular, focused mission capability to the Combatant Commanders to provide assured access against littoral threats. The primary missions for the LCS include countering littoral mine, submarine, and surface threats to assure maritime access for Joint Forces. The underlying strength of the LCS lies in its innovative design approach and the application of modularity for operational flexibility.
Fundamental to this approach is the capability to rapidly install interchangeable mission packages onto the ship.
A mission package consists of mission modules with mission crew and support aircraft. Mission modules combine mission systems (vehicles, sensors, weapons) and support equipment that install into the ship via standard interfaces.
Mission systems are added to the mission module baseline incrementally as they reach a level of maturity necessary for fielding. This approach provides for continuous improvement of warfighting capability through an evolutionary acquisition process. Misson modules' modular capability provides an open architecture environment that enables future rapid insertion of new technologies.

## Table 7
Executive Summary
The LCS MM Program continues to incrementally field additional capabilities to the Fleet as approved in the budget and in- phase with ship deliveries.
This SAR is based on the current program of record of 64 mission packages. Changes to the LCS/Frigate program of record likely will affect the number of Mine Countermeasures Mission Packages (MCM MP), Surface Warfare Mission Packages(SUW MP), and Anti-Submarine Warfare Mission Packages (ASW MP) to be procured by the LCS MM Program. The Navy is reviewing the numerical distribution of mission packages based on the LCS/Frigate program changes reflected in the PB 2017 submission, and expects to update the mission package quantity profile this year.
SUW MP:
• Successfully completed Phase 1 of Initial Operational Test & Evaluation (IOT&E) of SUW MP Increment 2 aboard USS Coronado (LCS 4) on September 25, 2015. Phase 2 will take place in Spring 2016.
• Successfully conducted Surface-to-Surface Missile Module Guided Test Vehicle (GTV) -2 test event from December 5-9, 2015. The test evaluated the performance of the launcher and missile system in a littoral environment. This built upon the successful completion of GTV-1 in June 2015.
MCM MP:
• Technical Evaluation (TECHEVAL) of the Increment 1 MCM MP was completed on August 30, 2015. TECHEVAL is the final developmental test prior to IOT&E. The MCM MP met the majority of its sustained area coverage rate test requirements, but significant reliability issues were noted with the Remote Multi-Mission Vehicle (RMMV) and associated subsystems. The other MCM MP systems evaluated during TECHEVAL, the sonar (AN/AQS-20) and the MH-60R helicopter-borne Airborne Laser Mine Detection System (ALMDS) and the Airborne Mine Neutralization System (AMNS), performed well. Based on TECHEVAL results, the Navy chartered an Independent Review Team (IRT) to assess the Remote Minehunting System (RMS).
• The Navy has elected to delay IOT&E of the Increment 1 MCM MP based on the RMS IRT recommendations. The MCM MP schedule will be updated further as part of the IRT implementation plan.
• The plan for fielding the remainder of the MCM MP systems, including COBRA for Beach Zone Mine Detection, CUSV
+ mine sweeping (Unmanned Influence Sweep System - UISS) for Influence Minesweeping, and Knifefish for buried/high clutter minehunting remains on schedule, with an acceleration of Knifefish being considered. These systems add capability in other portions of the water column or other portions of the MCM detect-to-engage sequence and are not dependent on RMMV to continue their efforts.
ASW MP:
• The Navy has canceled plans to conduct testing of the Advanced Development Model in the Pacific theater in FY 2016 due to a Congressional appropriations reduction. The Navy is reviewing other opportunities for testing. While the Congressional reduction increases program risk, it is not anticipated to affect schedule.
• The LCS MM program awarded contracts to three companies in July 2015 for the development and delivery of a weight-reduced Escort Mission Module (EMM). The objective is to reduce weight of the EMM by 15-25%, depending upon the LCS variant, while meeting established performance, reliability, safety, and operability requirements.
• The LCS MM program plans to downselect in 2nd Quarter FY 2016 for delivery and testing of the prototype EMM.

## Table 8
The Assistant Secretary of the Navy for Research, Development and Acquisition (ASN (RD&A)) approved Milestone B for the LCS MM program on January 7, 2014. ASN (RD&A), acting as the MDA, waived the following provisions of Section 2366b of Title 10, United States Code:
1. 2366b(a)(1)(D): That funding is available to execute the product development and production plan under the program, through the period covered by the FYDP submitted during the fiscal year in which the certification is made, consistent with the estimates described in subparagraph (1)(C) for the program, having determined that, but for such a waiver, the Department would be unable to meet critical national security objectives.
2. 2366b(2): That the MDA has received a Preliminary Design Review (PDR) and conducted a formal post-PDR assessment, and certifies on the basis of such assessment that the program demonstrates a high likelihood of accomplishing its intended mission, having determined that, but for such a waiver, the Department would be unable to meet critical national security objectives.
The Department will continue to review the LCS MM program at least annually until the certification components are satisfied.
There are no significant software-related issues with this program at this time.

## Table 9
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
IOC for the Anti-Submarine Warfare Mission Package (ASW MP) will be delayed until March 2018 due to the need to balance operational requirements and ship schedules to support deployment of LCS 1-4 and execution of Full Ship Shock Trials on LCS 5 and 6, while aligning the readiness of the weight-reduced Engineering Development Model for at-sea testing with projected ship availability. As a result, shipboard testing will begin in late FY 2017 and Initial Operational Test & Evaluation will occur in FY 2018. This schedule change will still support the Navy's planned first deployment of the ASW MP in FY 2019. The LCS MM program office will continue to coordinate with the LCS ship program and other stakeholders to balance priorities.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule
(Ch-1)
(Ch-2)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone A (Combined LCS program) | May 2004 | May 2004 | May 2004 | May 2004
Mission MP, Production, and Assembly contract award | Mar 2006 | Mar 2006 | Mar 2006 | Mar 2006
First MCM MP delivery | Sep 2007 | Sep 2007 | Sep 2007 | Sep 2007
First SUW MP delivery | Jul 2008 | Jul 2008 | Jul 2008 | Jul 2008
Milestone A Prime | Aug 2009 | Aug 2009 | Aug 2009 | Aug 2009
Milestone B | Aug 2013 | Aug 2013 | Aug 2014 | Aug 2013
SUW MP Increment I/II IOC | Aug 2014 | Aug 2014 | Aug 2015 | Nov 2014
MCM MP Increment I IOC | Sep 2015 | Sep 2015 | Sep 2016 | Apr 2016
ASW MP IOC | Sep 2016 | Sep 2016 | Sep 2017 | Mar 20181
MCM MP Increment IV IOC | Sep 2019 | Sep 2019 | Sep 2020 | Sep 2019
Milestone C | Mar 2020 | Mar 2020 | Mar 2021 | Mar 2020
SUW MP Increment IV IOC | Sep 2020 | Sep 2020 | Sep 2021 | Sep 2020
1 APB Breach

## Table 11
Change Explanations
(Ch-1) The current estimate for IOC for the MCM MP has been delayed from September 2015 to April 2016 due to reliability issues noted with the Remote Multi-Mission Vehicle and associated subsystems. The April 2016 date is tentative as the Navy's Independent Review Team is assessing the entire Remote Minehunting System. The Independent Review Team's findings will inform the way ahead for the MCM MP and a new IOC date will be officially established at that time.
(Ch-2) The current estimate for IOC for the ASW MP has been delayed from September 2017 to March 2018 due to the need to balance operational requirements and ship schedules to support deployment of LCS 1-4 and execution of Full Ship Shock Trials on LCS 5 and 6, while aligning the readiness of the weight-reduced Engineering Development Model for at-sea testing with projected ship availability. As a result, shipboard testing will begin in late FY 2017 and IOT&E will occur in FY 2018. This schedule change will still support the Navy's planned first deployment of the ASW MP in FY 2019. The LCS MM Program Office will continue to coordinate with the LCS ship program and other stakeholders to balance priorities.
Acronyms and Abbreviations
ASW - Anti-Submarine Warfare
IOT&E - Initial Operational Test & Evaluation MCM - Mine Countermeasures
MP - Mission Package SUW - Surface Warfare

## Table 12
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
MCM MP
Materiel Availability
0.712 | 0.712 | 0.64 | 0.673 | 0.712
Train to Certify: A trained crew is required for MP Billets / Watch Stations
Trained-to-Certify at all Team (Watch Section) levels | Trained-to-Certify at all Team (Watch Section) levels | Trained-to-Certify at all Team (Watch Section) levels | TBD | Trained-to-Certify at all Team (Watch Section) levels
SUW MP
Materiel Availability
0.712 | 0.712 | 0.64 | 0.814 | 0.712
Train-to-Certify: A trained crew is required for MP Billets / Watch Stations
Trained-to-Certify at all Team (Watch Section) levels | Trained-to-Certify at all Team (Watch Section) levels | Trained-to-Certify at all Team (Watch Section) levels | TBD | Trained-to-Certify at all Team (Watch Section) levels
ASW MP
Materiel Availability
0.712 | 0.712 | 0.64 | TBD | 0.712
Train-to-Certify: A trained crew is required for MP Billets / Watch Stations
Trained-to-Certify at all Team (Watch Section) levels | Trained-to-Certify at all Team (Watch Section) levels | Trained-to-Certify at all Team (Watch Section) levels | TBD | Trained-to-Certify at all Team (Watch Section) levels
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
LCS Flight 0 Capability Development Document (CDD) dated May 25, 2004 and LCS Flight 0+ CDD dated June 17, 2008
Change Explanations
None
Notes
Interoperability Information Exchange Requirement KPP replaced by Net Ready KPP.
No materiel availability projection is available for the ASW MP currently in development.

## Table 13
Acronyms and Abbreviations
ASW - Anti-Submarine Warfare MCM - Mine Countermeasures MP - Mission Package
SUW - Surface Warfare

## Table 14
Track to Budget
RDT&E
Appn BA PE
Navy 1319 04 0603581N
Project Name
3096 LCS Mission Package Development (Shared) (Sunk) 3129 LCS Mission Package Development (Shared) (Sunk)
Navy 1319 04 0603596N
Project Name
3129 LCS Mission Package Development
Procurement
Appn BA PE
Navy 1507 04 0204230N
Line Item Name
4221 LCS Module Weapons
Notes: For procurement of surface-to-surface missiles for the SUW MP.
Navy 1810 01 0204230N
Line Item Name
1600 LCS Common Mission Modules Equipment
1601 LCS MCM Mission Modules
1602 LCS ASW Mission Modules
1603 LCS SUW Mission Modules
1605 Remote Minehunting System
MILCON
Appn BA PE
Navy 1205 01 0212176N
Project Name
60201424 LCS Mission Module Readiness Center (MMRC)

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2010 $M |  |  |  |  | BY 2010 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 2233.7 |  | 2233.7 | 2457.1 |  | 2343.9 |  | 2415.6 |  | 2415.6 |  | 2513.5
Procurement |  | 4116.7 |  | 4116.7 | 4528.4 |  | 3999.5 |  | 4995 |  | 4995 |  | 5039.5
Flyaway |  | -- |  | -- | -- |  | 3999.5 |  | -- |  | -- |  | 5039.5
Recurring |  | -- |  | -- | -- |  | 3999.5 |  | -- |  | -- |  | 5039.5
Non Recurring |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Other Support |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON |  | 29.1 |  | 29.1 | 32 |  | 29.5 |  | 37.7 |  | 37.7 |  | 35.7
Acq O&M |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total |  | 6379.5 |  | 6379.5 | N/A |  | 6372.9 |  | 7448.3 |  | 7448.3 |  | 7588.7
Confidence Level
Confidence Level of cost estimate for current APB: 50%
Point estimates scaled to the 50/50 confidence level per the Program Life Cycle Cost Estimate (PLCCE) and Service Cost position (SCP).

## Table 16
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 5 | 5 | 5
Procurement | 59 | 59 | 59
Total | 64 | 64 | 64
Quantity Notes
The LCS MM Program uses Mission Packages (MP) as its quantity unit of measure. A MP consists of mission
modules, plus a mission crew detachment and supporting aircraft. This SAR is based on the current program of record of 64 MP. Changes to the LCS/Frigate program of record likely will affect the number of Mine Countermeasures, Surface Warfare (SUW), and Anti-Submarine Warfare MP to be procured by the LCS MM Program. The Navy is reviewing the numerical distribution of mission packages based on the LCS/Frigate program changes reflected in the PB 2017 submission, and expects to update the mission package quantity profile this year.
The program provides funding to other programs for the purpose of procuring Mission Systems (MS). These MS (offboard vehicles, sensors, and weapons) are then combined with common mission modules equipment. For the purposes of Congressional visibility into program execution, the annual PB submission breaks out these MS procurements in detail.
Once all MS and support equipment are procured for a given MP type (SUW, ASW, MCM), a MP is counted as a procured end item in the budget.

## Table 17
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 1724.2 | 203.1 |  |  | 160.1 | 72.8 | 54.9 |  | 43.2 |  | 31 |  |  | 224.2 |  | 2513.5
Procurement | 591.1 | 178.8 |  |  | 142.2 | 311.7 | 328.9 |  | 229.5 |  | 337.3 |  |  | 2920 |  | 5039.5
MILCON | 0 | 16.2 |  |  | 0 | 0 | 0 |  | 0 |  | 19.5 |  |  | 0 |  | 35.7
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 2315.3 | 398.1 |  |  | 302.3 | 384.5 | 383.8 |  | 272.7 |  | 387.8 |  |  | 3144.2 |  | 7588.7
PB 2016 Total | 2312.2 | 447.5 |  |  | 440 | 374.7 | 379.2 |  | 276 |  | 594.8 |  |  | 2652.6 |  | 7477
Delta | 3.1 | -49.4 |  |  | -137.7 | 9.8 | 4.6 |  | -3.3 |  | -207 |  |  | 491.6 |  | 111.7
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 5 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 5
Production | 0 |  | 11 |  | 5 | 3 | 6 |  | 5 |  | 4 | 5 |  | 20 |  | 59
PB 2017 Total | 5 |  | 11 |  | 5 | 3 | 6 |  | 5 |  | 4 | 5 |  | 20 |  | 64
PB 2016 Total | 5 |  | 11 |  | 4 | 4 | 5 |  | 5 |  | 4 | 6 |  | 20 |  | 64
Delta | 0 |  | 0 |  | 1 | -1 | 1 |  | 0 |  | 0 | -1 |  | 0 |  | 0

## Table 18
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.6
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 193.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 157.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 151
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 198.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 204.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 172.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 203.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 160.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.8
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.2
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.8
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.6
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.2
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.6
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.2
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.3
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.3
2035 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2036 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.8
2037 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
2038 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5

## Table 19
2039 | -- | -- | -- | -- | -- | -- | 2.6
2040 | -- | -- | -- | -- | -- | -- | 2.7
2041 | -- | -- | -- | -- | -- | -- | 3
2042 | -- | -- | -- | -- | -- | -- | 2.8
2043 | -- | -- | -- | -- | -- | -- | 2.6
2044 | -- | -- | -- | -- | -- | -- | 3
2045 | -- | -- | -- | -- | -- | -- | 2.7
2046 | -- | -- | -- | -- | -- | -- | 3.3
2047 | -- | -- | -- | -- | -- | -- | 2.8
2048 | -- | -- | -- | -- | -- | -- | 3.2
2049 | -- | -- | -- | -- | -- | -- | 3.2
2050 | -- | -- | -- | -- | -- | -- | 3.3
2051 | -- | -- | -- | -- | -- | -- | 3.2
2052 | -- | -- | -- | -- | -- | -- | 3.3
2053 | -- | -- | -- | -- | -- | -- | 3.2
2054 | -- | -- | -- | -- | -- | -- | 3.5
2055 | -- | -- | -- | -- | -- | -- | 3.5
Subtotal | 5 | -- | -- | -- | -- | -- | 2513.5

## Table 20
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.6
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.5
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 204.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 173.6
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 107.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 155.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 142.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 185.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 188.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 157.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 182.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 141
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.9
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.2
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.2
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.5
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.6
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.8
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.4
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2031 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
2032 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2033 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.3
2034 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4
2035 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2036 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.7
2037 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2038 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2039 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2040 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2041 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
2042 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2043 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4

## Table 21
2044 | -- | -- | -- | -- | -- | -- | 1.5
2045 | -- | -- | -- | -- | -- | -- | 1.4
2046 | -- | -- | -- | -- | -- | -- | 1.6
2047 | -- | -- | -- | -- | -- | -- | 1.4
2048 | -- | -- | -- | -- | -- | -- | 1.5
2049 | -- | -- | -- | -- | -- | -- | 1.5
2050 | -- | -- | -- | -- | -- | -- | 1.5
2051 | -- | -- | -- | -- | -- | -- | 1.4
2052 | -- | -- | -- | -- | -- | -- | 1.5
2053 | -- | -- | -- | -- | -- | -- | 1.4
2054 | -- | -- | -- | -- | -- | -- | 1.5
2055 | -- | -- | -- | -- | -- | -- | 1.5
Subtotal | 5 | -- | -- | -- | -- | -- | 2343.9

## Table 22
Only includes RDT&E, Navy costs associated with initial procurement. The LCS MM program will procure five Mission Packages with RDT&E, Navy as training and test assets. RDT&E, Navy costs associated with replacement, attrition, and technology refresh costs are accounted for in O&S per the SCP.

## Table 23
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2017 |  | -- | 2.8 |  | -- |  | -- |  | 2.8 |  | -- |  | 2.8
2018 |  | -- | 13.1 |  | -- |  | -- |  | 13.1 |  | -- |  | 13.1
2019 |  | -- | 13.7 |  | -- |  | -- |  | 13.7 |  | -- |  | 13.7
2020 |  | -- | 13.5 |  | -- |  | -- |  | 13.5 |  | -- |  | 13.5
2021 |  | -- | 13.7 |  | -- |  | -- |  | 13.7 |  | -- |  | 13.7
2022 |  | -- | 14 |  | -- |  | -- |  | 14 |  | -- |  | 14
2023 |  | -- | 14.3 |  | -- |  | -- |  | 14.3 |  | -- |  | 14.3
2024 |  | -- | 15.6 |  | -- |  | -- |  | 15.6 |  | -- |  | 15.6
2025 |  | -- | 17.1 |  | -- |  | -- |  | 17.1 |  | -- |  | 17.1
Subtotal |  | -- | 117.8 |  | -- |  | -- |  | 117.8 |  | -- |  | 117.8

## Table 24
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2017 |  | -- | 2.4 |  | -- |  | -- |  | 2.4 |  | -- |  | 2.4
2018 |  | -- | 11.1 |  | -- |  | -- |  | 11.1 |  | -- |  | 11.1
2019 |  | -- | 11.4 |  | -- |  | -- |  | 11.4 |  | -- |  | 11.4
2020 |  | -- | 11 |  | -- |  | -- |  | 11 |  | -- |  | 11
2021 |  | -- | 11 |  | -- |  | -- |  | 11 |  | -- |  | 11
2022 |  | -- | 11 |  | -- |  | -- |  | 11 |  | -- |  | 11
2023 |  | -- | 11 |  | -- |  | -- |  | 11 |  | -- |  | 11
2024 |  | -- | 11.8 |  | -- |  | -- |  | 11.8 |  | -- |  | 11.8
2025 |  | -- | 12.7 |  | -- |  | -- |  | 12.7 |  | -- |  | 12.7
Subtotal |  | -- | 93.4 |  | -- |  | -- |  | 93.4 |  | -- |  | 93.4

## Table 25
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | 2 | 220.3 |  | -- |  | -- |  | 220.3 |  | -- |  | 220.3
2011 |  | 2 | 42.6 |  | -- |  | -- |  | 42.6 |  | -- |  | 42.6
2012 |  | 2 | 67.7 |  | -- |  | -- |  | 67.7 |  | -- |  | 67.7
2013 |  | 3 | 109.2 |  | -- |  | -- |  | 109.2 |  | -- |  | 109.2
2014 |  | 2 | 90.3 |  | -- |  | -- |  | 90.3 |  | -- |  | 90.3
2015 |  | -- | 61 |  | -- |  | -- |  | 61 |  | -- |  | 61
2016 |  | 5 | 178.8 |  | -- |  | -- |  | 178.8 |  | -- |  | 178.8
2017 |  | 3 | 139.4 |  | -- |  | -- |  | 139.4 |  | -- |  | 139.4
2018 |  | 6 | 298.6 |  | -- |  | -- |  | 298.6 |  | -- |  | 298.6
2019 |  | 5 | 315.2 |  | -- |  | -- |  | 315.2 |  | -- |  | 315.2
2020 |  | 4 | 216 |  | -- |  | -- |  | 216 |  | -- |  | 216
2021 |  | 5 | 323.6 |  | -- |  | -- |  | 323.6 |  | -- |  | 323.6
2022 |  | 6 | 715.7 |  | -- |  | -- |  | 715.7 |  | -- |  | 715.7
2023 |  | 6 | 734 |  | -- |  | -- |  | 734 |  | -- |  | 734
2024 |  | 6 | 600.5 |  | -- |  | -- |  | 600.5 |  | -- |  | 600.5
2025 |  | 2 | 128.7 |  | -- |  | -- |  | 128.7 |  | -- |  | 128.7
2026 |  | -- | 76.3 |  | -- |  | -- |  | 76.3 |  | -- |  | 76.3
2027 |  | -- | 78 |  | -- |  | -- |  | 78 |  | -- |  | 78
2028 |  | -- | 80.6 |  | -- |  | -- |  | 80.6 |  | -- |  | 80.6
2029 |  | -- | 21.9 |  | -- |  | -- |  | 21.9 |  | -- |  | 21.9
2030 |  | -- | 21.6 |  | -- |  | -- |  | 21.6 |  | -- |  | 21.6
2031 |  | -- | 21.9 |  | -- |  | -- |  | 21.9 |  | -- |  | 21.9
2032 |  | -- | 22.7 |  | -- |  | -- |  | 22.7 |  | -- |  | 22.7
2033 |  | -- | 22.3 |  | -- |  | -- |  | 22.3 |  | -- |  | 22.3
2034 |  | -- | 20.5 |  | -- |  | -- |  | 20.5 |  | -- |  | 20.5
2035 |  | -- | 20.1 |  | -- |  | -- |  | 20.1 |  | -- |  | 20.1
2036 |  | -- | 20.7 |  | -- |  | -- |  | 20.7 |  | -- |  | 20.7
2037 |  | -- | 20.6 |  | -- |  | -- |  | 20.6 |  | -- |  | 20.6
2038 |  | -- | 19.9 |  | -- |  | -- |  | 19.9 |  | -- |  | 19.9
2039 |  | -- | 20.7 |  | -- |  | -- |  | 20.7 |  | -- |  | 20.7
2040 |  | -- | 20.7 |  | -- |  | -- |  | 20.7 |  | -- |  | 20.7
2041 |  | -- | 20.8 |  | -- |  | -- |  | 20.8 |  | -- |  | 20.8
2042 |  | -- | 20.4 |  | -- |  | -- |  | 20.4 |  | -- |  | 20.4
2043 |  | -- | 18.9 |  | -- |  | -- |  | 18.9 |  | -- |  | 18.9
2044 |  | -- | 18.7 |  | -- |  | -- |  | 18.7 |  | -- |  | 18.7
2045 |  | -- | 18.7 |  | -- |  | -- |  | 18.7 |  | -- |  | 18.7
2046 |  | -- | 17.4 |  | -- |  | -- |  | 17.4 |  | -- |  | 17.4
2047 |  | -- | 15.6 |  | -- |  | -- |  | 15.6 |  | -- |  | 15.6
2048 |  | -- | 14 |  | -- |  | -- |  | 14 |  | -- |  | 14
2049 |  | -- | 13 |  | -- |  | -- |  | 13 |  | -- |  | 13

## Table 26
2050 | -- | 11.2 | -- | -- | 11.2 | -- | 11.2
2051 | -- | 9.6 | -- | -- | 9.6 | -- | 9.6
2052 | -- | 6.3 | -- | -- | 6.3 | -- | 6.3
2053 | -- | 5.5 | -- | -- | 5.5 | -- | 5.5
2054 | -- | 1.5 | -- | -- | 1.5 | -- | 1.5
Subtotal | 59 | 4921.7 | -- | -- | 4921.7 | -- | 4921.7

## Table 27
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2010 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | 2 | 213.9 |  | -- |  | -- |  | 213.9 |  | -- |  | 213.9
2011 |  | 2 | 40.8 |  | -- |  | -- |  | 40.8 |  | -- |  | 40.8
2012 |  | 2 | 63.8 |  | -- |  | -- |  | 63.8 |  | -- |  | 63.8
2013 |  | 3 | 101.5 |  | -- |  | -- |  | 101.5 |  | -- |  | 101.5
2014 |  | 2 | 82.8 |  | -- |  | -- |  | 82.8 |  | -- |  | 82.8
2015 |  | -- | 55.2 |  | -- |  | -- |  | 55.2 |  | -- |  | 55.2
2016 |  | 5 | 159 |  | -- |  | -- |  | 159 |  | -- |  | 159
2017 |  | 3 | 121.7 |  | -- |  | -- |  | 121.7 |  | -- |  | 121.7
2018 |  | 6 | 255.6 |  | -- |  | -- |  | 255.6 |  | -- |  | 255.6
2019 |  | 5 | 264.6 |  | -- |  | -- |  | 264.6 |  | -- |  | 264.6
2020 |  | 4 | 177.7 |  | -- |  | -- |  | 177.7 |  | -- |  | 177.7
2021 |  | 5 | 261.1 |  | -- |  | -- |  | 261.1 |  | -- |  | 261.1
2022 |  | 6 | 566.1 |  | -- |  | -- |  | 566.1 |  | -- |  | 566.1
2023 |  | 6 | 569.2 |  | -- |  | -- |  | 569.2 |  | -- |  | 569.2
2024 |  | 6 | 456.5 |  | -- |  | -- |  | 456.5 |  | -- |  | 456.5
2025 |  | 2 | 95.9 |  | -- |  | -- |  | 95.9 |  | -- |  | 95.9
2026 |  | -- | 55.8 |  | -- |  | -- |  | 55.8 |  | -- |  | 55.8
2027 |  | -- | 55.9 |  | -- |  | -- |  | 55.9 |  | -- |  | 55.9
2028 |  | -- | 56.6 |  | -- |  | -- |  | 56.6 |  | -- |  | 56.6
2029 |  | -- | 15.1 |  | -- |  | -- |  | 15.1 |  | -- |  | 15.1
2030 |  | -- | 14.6 |  | -- |  | -- |  | 14.6 |  | -- |  | 14.6
2031 |  | -- | 14.5 |  | -- |  | -- |  | 14.5 |  | -- |  | 14.5
2032 |  | -- | 14.7 |  | -- |  | -- |  | 14.7 |  | -- |  | 14.7
2033 |  | -- | 14.2 |  | -- |  | -- |  | 14.2 |  | -- |  | 14.2
2034 |  | -- | 12.8 |  | -- |  | -- |  | 12.8 |  | -- |  | 12.8
2035 |  | -- | 12.3 |  | -- |  | -- |  | 12.3 |  | -- |  | 12.3
2036 |  | -- | 12.4 |  | -- |  | -- |  | 12.4 |  | -- |  | 12.4
2037 |  | -- | 12.1 |  | -- |  | -- |  | 12.1 |  | -- |  | 12.1
2038 |  | -- | 11.5 |  | -- |  | -- |  | 11.5 |  | -- |  | 11.5
2039 |  | -- | 11.7 |  | -- |  | -- |  | 11.7 |  | -- |  | 11.7
2040 |  | -- | 11.5 |  | -- |  | -- |  | 11.5 |  | -- |  | 11.5
2041 |  | -- | 11.3 |  | -- |  | -- |  | 11.3 |  | -- |  | 11.3
2042 |  | -- | 10.9 |  | -- |  | -- |  | 10.9 |  | -- |  | 10.9
2043 |  | -- | 9.9 |  | -- |  | -- |  | 9.9 |  | -- |  | 9.9
2044 |  | -- | 9.6 |  | -- |  | -- |  | 9.6 |  | -- |  | 9.6
2045 |  | -- | 9.4 |  | -- |  | -- |  | 9.4 |  | -- |  | 9.4
2046 |  | -- | 8.6 |  | -- |  | -- |  | 8.6 |  | -- |  | 8.6
2047 |  | -- | 7.5 |  | -- |  | -- |  | 7.5 |  | -- |  | 7.5
2048 |  | -- | 6.6 |  | -- |  | -- |  | 6.6 |  | -- |  | 6.6
2049 |  | -- | 6 |  | -- |  | -- |  | 6 |  | -- |  | 6

## Table 28
2050 | -- | 5.1 | -- | -- | 5.1 | -- | 5.1
2051 | -- | 4.3 | -- | -- | 4.3 | -- | 4.3
2052 | -- | 2.8 | -- | -- | 2.8 | -- | 2.8
2053 | -- | 2.4 | -- | -- | 2.4 | -- | 2.4
2054 | -- | 0.6 | -- | -- | 0.6 | -- | 0.6
Subtotal | 59 | 3906.1 | -- | -- | 3906.1 | -- | 3906.1

## Table 29
Other Procurement, Navy (OP,N) is split into separate PEs/Budget Line Items for Common Equipment, Mine Countermeasures Mission Package (MP) equipment, Surface Warfare MP equipment, Anti-Submarine Warfare MP equipment, the Remote Multi-Mission Vehicles, and spares. These are initial procurement costs only. OP,N costs for replacement mission systems, attrition, technology refresh, and spares are accounted for in O&S. Five MP were procured with RDT&E, Navy.
Cost Quantity Information 1810 ¦ Procurement ¦ Other Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2010 $M
2010 | 2 | 230.1
2011 | 2 | 57
2012 | 2 | 80
2013 | 3 | 125.8
2014 | 2 | 99
2015 | -- | --
2016 | 5 | 199.5
2017 | 3 | 146
2018 | 6 | 304.2
2019 | 5 | 305.1
2020 | 4 | 210.1
2021 | 5 | 301.6
2022 | 6 | 614.7
2023 | 6 | 617.8
2024 | 6 | 503.1
2025 | 2 | 112.1
2026 | -- | --
2027 | -- | --
2028 | -- | --
2029 | -- | --
2030 | -- | --
2031 | -- | --
2032 | -- | --
2033 | -- | --
2034 | -- | --
2035 | -- | --
2036 | -- | --
2037 | -- | --
2038 | -- | --
2039 | -- | --
2040 | -- | --

## Table 30
2041 | -- | --
2042 | -- | --
2043 | -- | --
2044 | -- | --
2045 | -- | --
2046 | -- | --
2047 | -- | --
2048 | -- | --
2049 | -- | --
2050 | -- | --
2051 | -- | --
2052 | -- | --
2053 | -- | --
2054 | -- | --
Subtotal | 59 | 3906.1

## Table 31
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2016 16.2
2017 --
2018 --
2019 --
2020 --
2021 19.5
Subtotal 35.7

## Table 32
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2010 $M
Total Program
2016 14.1
2017 --
2018 --
2019 --
2020 --
2021 15.4
Subtotal 29.5

## Table 33
The SCP assumed receipt of MILCON funds in FY 2021 for construction of four Mission Module Readiness Centers in various locations. One of the locations will be Mayport, FL. The FY 2016 PB submission moves the funds for the construction of the Mission Module Readiness Center in Mayport, FL to FY 2016. However, the Naval Facilities Command manages, executes, and reports on these funds.

## Table 34
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2014-01-07 | 2014-01-07
Approved Quantity | 27 | 27
Reference | Milestone B ADM | Milestone B ADM
Start Year | 2006 | 2006
End Year | 2018 | 2019
The Current Total LRIP Quantity is more than 10% of the total production quantity , due to the requirement to have enough mission packages to populate the 24 LCS delivered or under contract through FY 2015, and the units required to support development, testing, and training.
The LRIP quantities authorized at Milestone B were 12 surface warfare, 12 mine countermeasures, and three anti- submarine warfare mission packages. The LRIP decision did not specify a starting or ending FY for LRIP. The dates above are derived from program plans. The program procured the first production mission package in 2006, following written authorization by USD (AT&L), acting in his capacity as the MDA. Under the program's current procurement plan, the program will procure the 27th production mission package in FY 2019.
The MDA also authorized the procurement of up to five developmental mission packages for use as development, test, and training assets. These will consist of up to three surface warfare, one mine countermeasures, and one anti-submarine warfare mission package. The program already has procured the surface warfare and mine countermeasures mission packages using RDT&E, Navy. The program plans to procure the developmental anti-submarine warfare mission package in FY 2016.

## Table 35
Foreign Military Sales
None
Nuclear Costs
None

## Table 36
Unit Cost
Unit Cost Report
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Current UCR Baseline (Nov 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 6379.5 |  |  | 6372.9
Quantity | 64 |  |  | 64
Unit Cost | 99.68 |  |  | 99.577 |  | -0.1
Average Procurement Unit Cost
Cost | 4116.7 |  |  | 3999.5
Quantity | 59 |  |  | 59
Unit Cost | 69.775 |  |  | 67.788 |  | -2.85
Item |  | BY 2010 $M | BY 2010 $M |  | % Change
|  | Original UCR Baseline (Nov 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 6379.5 |  |  | 6372.9
Quantity | 64 |  |  | 64
Unit Cost | 99.68 |  |  | 99.577 |  | -0.1
Average Procurement Unit Cost
Cost | 4116.7 |  |  | 3999.5
Quantity | 59 |  |  | 59
Unit Cost | 69.775 |  |  | 67.788 |  | -2.85

## Table 37
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2010 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Nov 2013 |  |  |  |  | 99.68 |  |  | 69.775 |  |  | 116.38 |  |  | 84.661
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A |  |  | N/A
Current APB |  |  | Nov 2013 |  |  |  |  | 99.68 |  |  | 69.775 |  |  | 116.38 |  |  | 84.661
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 98.255 |  |  | 67.322 |  |  | 116.828 |  |  | 84.522
Current Estimate |  |  | Dec 2015 |  |  |  |  | 99.577 |  |  | 67.788 |  |  | 118.573 |  |  | 85.415
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth |  | Spt | Total
116.380 -2.097 0.000 10.072 -0.344 -5.438 0.000 0.000 2.193 118.573
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth |  | Spt | Total
84.661 -1.805 0.000 10.925 -0.373 -7.993 0.000 0.000 0.754 85.415

## Table 38
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | May 2004 | N/A | May 2004
Milestone B | N/A | Aug 2013 | N/A | Aug 2013
Milestone C | N/A | Mar 2020 | N/A | Mar 2020
IOC | N/A | Aug 2014 | N/A | Nov 2014
Total Cost (TY $M) | N/A | 7448.3 | N/A | 7588.7
Total Quantity | N/A | 64 | N/A | 64
PAUC | N/A | 116.38 | N/A | 118.573

## Table 39
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 2415.6 | 4995 | 37.7 | 7448.3
Previous Changes
Economic | -20.4 | -70.4 | -0.7 | -91.5
Quantity | -- | -- | -- | --
Schedule | -- | 433 | -- | 433
Engineering | -- | -22 | -- | -22
Estimating | 59.3 | -348.8 | -1.3 | -290.8
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 38.9 | -8.2 | -2 | 28.7
Current Changes
Economic | -6.4 | -36.1 | -0.2 | -42.7
Quantity | -- | -- | -- | --
Schedule | -- | 211.6 | -- | 211.6
Engineering | -- | -- | -- | --
Estimating | 65.4 | -122.8 | 0.2 | -57.2
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 59 | 52.7 | -- | 111.7
Total Changes | 97.9 | 44.5 | -2 | 140.4
CE - Cost Variance | 2513.5 | 5039.5 | 35.7 | 7588.7
CE - Cost & Funding | 2513.5 | 5039.5 | 35.7 | 7588.7

## Table 40
Summary BY 2010 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 2233.7 | 4116.7 | 29.1 | 6379.5
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | 277.5 | -- | 277.5
Engineering | -- | -18.7 | -- | -18.7
Estimating | 53.3 | -403.5 | 0.2 | -350
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 53.3 | -144.7 | 0.2 | -91.2
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | 147.6 | -- | 147.6
Engineering | -- | -- | -- | --
Estimating | 56.9 | -120.1 | 0.2 | -63
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | 56.9 | 27.5 | 0.2 | 84.6
Total Changes | 110.2 | -117.2 | 0.4 | -6.6
CE - Cost Variance | 2343.9 | 3999.5 | 29.5 | 6372.9
CE - Cost & Funding | 2343.9 | 3999.5 | 29.5 | 6372.9
Previous Estimate: December 2014

## Table 41
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -6.4
FY 2014 adjustments - Below threshold reprogramming to fund Mine Countermeasures +6.8 +7.4
(MCM) Mission Package (MP) testing. (Estimating)
Congressional and Navy budget adjustments. (Estimating) | -13.8 |  | -15.8
Reprogramming of MCM MP funding in FY2017 and FY 2018 from Other Procurement, Navy (OP,N) to RDT&E, Navy to support integration and testing efforts. (Estimating) | 23.8 |  | 27
Adjustment to FY 2021 Prior Estimate to align with PB 2017 FYDP controls. (Estimating) | 5 |  | 6.2
Fund Train to Qualify / Train to Certify Requirement and MCM MP Increment 3 (Unmanned | 32.1 |  | 37.3
Influence Sweep System) integration and development. (Estimating)
Adjustment for current and prior escalation. (Estimating) | 3 |  | 3.3
RDT&E Subtotal | 56.9 |  | 59
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -36.1
Adjustment for current and prior escalation. (Estimating) +2.5 +2.7
Stretch-out of procurement buy profile from FY 2017 - FY 2027; Mission Module equipment unit cost varies based on mission package types and increments (Navy). (Schedule)
+147.6 +211.6
Congressional and Navy budget adjustments. (Estimating) Reprogramming of MCM MP funding in FY 2017 and FY 2018 from Other Procurement, | +53.1 -23.4 | +87.3 -27.0
Navy (OP,N) to RDT&E, Navy to support integration and testing efforts. (Estimating)
Adjustment to FY 2021 Prior Estimate to align with PB 2017 FYDP controls. (Estimating) | -152.5 | -189.1
Revised estimate to reflect application of outyear inflation indices (Weapons Procurement, Navy). (Estimating) | 0.2 | 3.3
Procurement Subtotal | 27.5 | 52.7
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.2
Adjustment for current and prior escalation. (Estimating) | 0.1 | 0.1
Adjustment for current and prior escalation. (Estimating) | 0.1 | 0.1
MILCON Subtotal | 0.2 | 0

## Table 42
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Mission Package Integrator - PIO CLINs - MCM 7 and SUW 8
Contractor: Northrop Grumman Systems
Contractor Location: 600 Grumman Road West
Bethpage, NY 11714
Contract Number: N00024-06-C-6311/2
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: December 12, 2014
Definitization Date: December 12, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
21.6 N/A 2 21.6 N/A 2 21.6 21.2
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +0.4 -0.1
Previous Cumulative Variances -- --
Net Change +0.4 -0.1
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to learning curve effects.
The unfavorable cumulative schedule variance is due to delayed delivery of a gun mission module component from a subcontractor to the prime contractor in October 2015. Early delivery of other gun mission module components have brought schedule variance to near zero.
Notes
This is the first time this contract is being reported.
Contract N00024-06-C-6311, effort #1 ("Mission Package Integrator - PIO CLINs") concluded in September 2015. This was the production portion of the Northrop Grumman contract awarded in 2006. This effort encompassed procurement of the program's portion of MCM MP #3-6 and SUW MP #3-7, along with miscellaneous equipment and spares.
The program has separated out the production of MCM MP #7 and SUW MP #8 to allow greater visibility into the EVM performance of that procurement. The program is now reporting it as contract N00024-06-C-6311, effort #2 ("MCM 7 and SUW 8").

## Table 43
Contract Identification
Appropriation: RDT&E
Contract Name: Mission Package Integration Services
Contractor: Northrop Grumman Systems
Contractor Location: 600 Grumman Road West
Bethpage, NY 11714
Contract Number: N00024-15-C-6311/0
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: August 14, 2015
Definitization Date: August 14, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
38.5 N/A 0 38.5 N/A 0 38.5 38.5
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (CPFF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because an EVM waiver was granted by Deputy Assistant Secretary of the Navy - Management & Budget on August 10, 2015, due to the contract being for level-of-effort services.
Notes
This is the first time this contract is being reported.
Contract N00024-06-C-6311, effort #0 ("Mission Package Integrator - Core Services") concluded in September 2015. It was succeeded by contract N00024-15-C-6311 ("Mission Package Integration Services") in August 2015. This contract is for level-of-effort engineering services.

## Table 44
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 4 | 4 | 5 | 80%
Production | 9 | 9 | 59 | 15.25%
Total Program Quantity Delivered | 13 | 13 | 64 | 20.31%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
7588.7
2497.8
32.91%
52
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
13
25%
2713.4
35.76%
The above data is current as of December 31, 2015.

## Table 45
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 06, 2013
Source of Estimate: SCP
Quantity to Sustain: 64
Unit of Measure: Mission Package
Service Life per Unit: 30.00 Years
Fiscal Years in Service: FY 2009 - FY 2055
This SAR is based on the current program of record of 24 Mine Countermeasures (MCM), 24 Surface Warfare (SUW), and 16 Anti-Submarine Warfare (ASW) Mission Packages (MPs). Changes to the LCS/Frigate program of record likely will affect the number of MCM, SUW, and ASW MPs to be procured by the LCS MM Program. The Navy is reviewing the numerical distribution of MPs based on the LCS/Frigate program changes reflected in the PB 2017 submission, and expects to update the MP quantity profile this year. The LCS MM Program plans to update the O&S estimate to reflect new quantities by the end of calendar year 2016.
Each mission package consists of a number of warfare area-specific mission systems, the computing environment and computer programs permanently installed aboard each LCS, any needed aviation assets, and a crew detachment. The collected sensors, weapons, and offboard vehicles for a given warfare area are “mission systems.” The LCS MM Program Office combines these mission systems with support containers, support equipment, the Mission Package Computing Environment (MPCE), Mission Package Application Software (MPAS), and the Multiple Vehicle Communication System (MVCS) to create “mission modules (MMs).” The MPCE, MPAS, and MVCS are permanently installed aboard each LCS during construction. At the Mission Package Support Facility (MPSF) or a Mission Module Readiness Center (MMRC), multiple mission modules are combined with any needed aviation assets and the mission package crew detachment to create a “mission package.” The mission package is what is embarked on the ship. An example follows:
An SUW MP consists of:
• MPCE/MPAS/MVCS (permanently installed)
• Two Gun Mission Modules: Two 30 millimeter guns, containers, and support equipment
• One Maritime Security Module: Two Rigid Hull Inflatable Boats; Visit, Boarding, Search, and Seizure gear; containers; and support equipment
• One Surface-to-Surface Missile Module: Missiles, launcher, containers, and support equipment
• One Vertical Take-Off Unmanned Aerial Vehicle / Fire Scout
• One MH-60R helicopter
• Crew detachment
Sustainment Strategy
The Fleet Introduction and Sustainment Program Office, Program Manager, Ship (PMS) 505, is responsible for the sustainment of LCS MMs. The sustainment strategy closely couples the development and production role of the LCS MM Program Office (PMS 420) with that of PMS 505, particularly in the near term. LCS will carry limited onboard resources to maintain and repair mission systems. The assignment of significant maintenance and repair work to a dedicated off- ship, shore-based workforce with significant reliance on distance support is a new approach. Thus, product support of LCS requires a departure from the support approach seen in other surface combatants.

## Table 46
The mission modules will be maintained, stored, and centrally managed through the MPSF. The MPSF will be responsible for providing or coordinating maintenance, technical, and spares support as MMs, mission systems, or other equipment are delivered to and accepted by the MPSF. The MPSF was designed to receive requests from the deployed or embarked mission packages and to translate that into required actions for organic Navy, original equipment manufacturer, or other contractor effort, while maintaining a seamless process and a single interface to Fleet units.
PMS 505, through the MPSF, will coordinate all actions requiring shore-based personnel in support of maintenance and repair actions on an embarked mission package, particularly those that require travel to an Outside Continental United States (OCONUS)-deployed ship. Individual mission system maintenance plans describe specific mission system requirements and tasks to be accomplished to achieve, maintain, or restore operational capability. Maintenance is accomplished by the crew, by the MPSF, by organic Navy resources, or by a contractor, as appropriate. The MPSF will plan, arrange, schedule, coordinate, and manage the execution of all maintenance and modernization tasks. The permanent MPSF workforce will be augmented with government and contractor personnel to handle surge, low volume, and specialized tasks.
In addition to the MPSF, MMRCs will be established at other Continental United States sites and at forward OCONUS locations as deployed operations require. MMRCs are designed to have appropriate maintenance, administrative, and storage capabilities. To support significant maintenance or other events, MMRC staffing may be augmented from the MPSF and/or other Navy or contractor surge forces. MMRCs provide support forces a base for specific operations (e.g., embarkation/debarkation evolutions and major maintenance availabilities).
A hybrid Performance Based Logistics (PBL) system with a Program Support Integrator (PSI) arrangement will be adopted as a near-term solution for early support. The PSI will monitor and report failure of performance against Participating Activity Requirements Manager initiated support contracts requirements, assess existing contractual requirements against needs and experience, and seek alternatives where contractual adjustments are not possible or feasible to improve performance. The PSI will be responsible for data identification and collection and will analyze and correlate hardware and sustainment systems performance. This analysis will help determine which issues demand product improvement, which demand process improvement, what near-term mitigation is possible and affordable, and what long-term solutions are needed and recommended. During the early support phases of the program, PMS 505 will make use of support contracts arranged by mission system program offices, as well as In-Service Engineering
Agents and other organic Navy support to provide maintenance, technical, training, and spares support.
PMS 505 will pursue a long-range PBL strategy, with PMS 505 as lead and contractors in a supporting role. PMS 505 has initiated a formal process to transition support from interim support to full MPSF support. This process is designed to ensure that approved logistics products, which are critical to establishing and maintaining mission modules sustainment support, are complete, comprehensive, and current. Ultimately, PMS 505 will ensure that specific plans with firm delivery dates are in place and that approved draft products are available in the interim. Additionally, PMS 505 will ensure that version and configuration control is in place, configuration changes consider logistics impacts, and the costs of updates to applicable products are included in the costs of the change.
Antecedent Information
No Antecedent

## Table 47
Annual O&S Costs BY2010 $M
Cost Element |  | LCS MM Average Annual Cost Per Mission Package | [5 empty] | No Antecedent (Antecedent)
Unit-Level Manpower |  | 3.21 | [5 empty] | --
Unit Operations |  | 0.296 | [5 empty] | --
Maintenance |  | 2.658 | [5 empty] | --
Sustaining Support |  | 0.484 | [5 empty] | --
Continuing System Improvements |  | 3.691 | [5 empty] | --
Indirect Support |  | 0.905 | [5 empty] | --
Other |  | 0 | [5 empty] | --
Total |  | 11.244 | [5 empty] | --
Item | Total O&S Cost $M
| LCS MM | [7 empty] | No Antecedent (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 21589.2 |  |  | 23748.1 |  |  | 21589.2 |  | N/A
Then Year | 33040.2 |  |  | N/A |  |  | 33040.2 |  | N/A
Equation to Translate Annual Cost to Total Cost
Total Mission Package O&S = unitized cost (Unit Level Manpower + Unit Operations + Maintenance + Sustaining Support
+ Continuing System Improvements + Indirect Support) x 64 mission packages x 30-year service life per mission package.
The figure provided under the "Continuing System Improvements" cost element includes the projected average annual cost of replacing or refreshing individual mission systems. Generally, individual mission systems within the mission packages have a projected service life of less than 30 years.
O&S Cost Variance
Category |  |  | BY 2010 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
21589.2
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 21589.2

## Table 48
Disposal Estimate Details
Date of Estimate: February 06, 2013
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2010 $M): Total costs for disposal of all Mission Package are 177.8