## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-333
LHA 6 America Class Amphibious Assault Ship (LHA 6)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 14
Cost and Funding 15
Low Rate Initial Production 24
Foreign Military Sales 25
Nuclear Costs 25
Unit Cost 26
Cost Variance 29
Contracts 32
Deliveries and Expenditures 33
Operating and Support Cost 34

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
LHA 6 America Class Amphibious Assault Ship (LHA 6)
DoD Component
Navy
Responsible Office
Mr. Thomas Rivers
Program Executive Office, Ships Amphibious Warfare Program Office 1333 Isaac Hull Avenue
Washington, DC 20376-2101
thomas.m.rivers@navy.mil
Phone: | 202-781-0940
Fax: | 202-781-4567
DSN Phone: | 326-0940
DSN Fax: | 326-4596
Date Assigned: | September 28, 2015
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated January 12, 2006
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated May 8, 2012

## Table 6
Mission and Description
The LHA Replacement (LHA (R)) Program is planned to replace existing LHA 1 Class Amphibious Assault Ships, which reach the end of their extended service lives between 2011 and 2015.
The LHA (R) will be the key platform in the Expeditionary Strike Group (ESG)/Amphibious Ready Group (ARG) of the future and will provide the Joint Force Commander options to project expeditionary power. The LHA 6 America Class, the first ship of the LHA (R) Program, will embark and support all of the Short Take-off Vertical Landing (STOVL) and Vertical Take-off Landing Marine expeditionary aviation assets in the ESG/ARG, including the MV-22 and the F-35B, the STOVL model of the Joint Strike Fighter. The LHA 6 America Class is an LHD 8 gas turbine variant with enhanced aviation capability. The Flight 0 ship will embark over 1,600 Marines and transport them and their equipment ashore by rotary-wing aircraft when the situation requires. The Flight I ship maintains an aviation centric capability with the addition of a well deck that will accommodate two Landing Craft, Air Cushion. The Flight I ship will embark over 1,400 Marines and transport them and their equipment ashore by rotary-wing or surface connector.

## Table 7
Executive Summary
The LHA (R) program completed another successful year, with each of the three ships of the LHA (R) Program achieving significant milestones. Delivered to the Navy in April of 2014, the LHA 6 (USS AMERICA) Post Delivery Test and Trial test phase is currently in progress. The test phase has included the completion of signature measurements, Combat System Ship Qualification Trials events, Final Contract Trials, and will resume upon the completion of Post Shakedown Availability (PSA). PSA is currently underway in San Diego, CA. The 50% PSA conference was held on October 7, 2015 and the availability is scheduled to complete in March 2016.
The LHA 7 (TRIPOLI) continued sustained production at Huntington Ingalls Industries (HII), Ingalls Shipbuilding Division in Pascagoula, MS. At the end of 2015, the ship’s physical progress was 40% complete. A formal Program Manager's Estimate at Completion (PMEAC) for LHA 7 has commenced, as Earned Value progress for Vessel labor hours has reached 20% complete. The release of the PMEAC is currently forecasted for third quarter FY 2016.
LHA 8, the LHA (R) Flight 1 variant, has completed its contract design phase. Early industry involvement contracts with HII and National Steel and Shipbuilding Company (NASSCO) were initiated in November 2012 to allow industry participation in the design development for LHA 8. The contracts were modified in February 2014 to add Congressional plus-up funding for more in-depth Affordability Design initiatives. The period of performance for these efforts ended in August 2015. In February 2015, contract options were exercised under these base contracts for systems engineering and planning work with a period of performance through May 2016. These FY 2015 Procurement funded efforts are directly in support of the planned FY 2016 Detail Design and Construction (DD&C) contract award. The Request for Proposal for the Planning, Advanced Engineering and Procurement of Long Lead Time Material with option for DD&C was issued to HII and NASSCO in June 2015. Proposals were received on December 18, 2015 and are under evaluation. Contract award is currently planned for third quarter FY 2016.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Schedule breaches were previously reported in the December 2014 and June 2015 SARs.
Cost breaches were previously reported in the December 2009 and the December 2010 SARs.
A Program Deviation Report memorandum was issued by Assistant Secretary of the Navy for Research, Development and Acquisition on November 10, 2015 to USD(AT&L) documenting the noted breaches and the current program estimates. These deviations will be integrated into a revised APB in support of the LHA 8 contract award DAB program review in third quarter FY 2016.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
LHA (R) Milestone A | Jul 2001 | Jul 2001 | Jan 2002 | Jul 2001
LHA 6 Start Contract Design | May 2005 | May 2005 | Nov 2005 | May 2005
Advance Procurement Contract | Jul 2005 | Jul 2005 | Jan 2006 | Jul 2005
LHA 6 Milestone B | Jan 2006 | Jan 2006 | Jul 2006 | Jan 2006
Contract Award | Dec 2006 | Dec 2006 | Jun 2007 | Jun 2007
Start Fab | Nov 2007 | Nov 2007 | May 2008 | Jan 2008
LHA 7 Advance Procurement Contract Award | N/A | Jun 2010 | Dec 2010 | Jun 2010
LHA 7 DD&C Contract Award | N/A | Mar 2012 | Sep 2012 | May 2012
Float Off | Aug 2010 | Jun 2012 | Dec 2012 | Jun 2012
LHA 7 Start Fab | N/A | Apr 2013 | Oct 2013 | Jul 2013
Ship Delivery | Dec 2011 | Oct 2013 | Apr 2014 | Apr 2014
Operational Evaluation (OPEVAL) Start | Aug 2012 | Aug 2014 | Feb 2015 | Apr 20151
Initial Operational Capability (IOC) | Sep 2013 | Apr 2016 | Oct 2016 | Sep 2016
OPEVAL Complete | Sep 2013 | Apr 2016 | Oct 2016 | Jun 20171
LHA 7 Launch | N/A | Oct 2016 | Apr 2017 | Jul 20171
LHA 7 Ship Delivery | N/A | Mar 2018 | Sep 2018 | Dec 20181
1 APB Breach
Change Explanations
None
Acronyms and Abbreviations
DD&C - Detail Design and Construction Fab - Fabrication

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Net Ready
100% of interfaces; services; policy- enforcement controls; and data correctness, availability and processing requirements in the joint integrated architecture | 100% of interfaces; services; policy- enforcement controls; and data correctness, availability and processing requirements in the joint integrated architecture | 100% of interfaces; services; policy- enforcement controls; and data correctness, availability and processing requirements designated as enterprise level or critical in the joint integrated architecture | TBD | 100% of interfaces; services; policy- enforcement controls; and data correctness, availability and processing requirements designated as enterprise level or critical in the joint integrated architecture
Vertical Take Off and Landing land/launch spots
9 CH-53E/MV-22 | 9 CH-53E/MV-22 | 9 CH-53E/MV-22 | TBD | 9 CH-53E/MV-22
F-35B capacity
23 Aircraft | 23 Aircraft | 20 Aircraft | TBD | 23 Aircraft
Aviation operations
6 Spots 12 hrs/day (Sustained) 6 Spots 24 hrs/day for six consecutive days (Surge) | 6 Spots 12 hrs/day (Sustained) 6 Spots 24 hrs/day for six consecutive days (Surge) | 6 Spots 12 hrs/day (Sustained) 6 Spots 24 hrs/day for six consecutive days (Surge) | TBD | 6 spots 10 hours/day 12 hours/day of flight quarters to support 10 hours/day of flight operations
Vehicle space
12,000 sq. ft. | 12,000 sq. ft. | 10,000 sq. ft. | TBD | 11,760 sq. ft.
Total manpower (includes ship's force and all embarked elements such as troops, staffs, detachments, etc.)
2,891 Persons | 2,891 Persons | 2,891 Persons | TBD | 2,831 Persons
Cargo space
160,000 cu. ft. | 160,000 cu. ft. | 130,000 cu. ft. | TBD | 160,000 cu. ft.
Troop accomodations
1,686 Persons | 1,686 Persons | 1,626 Persons | TBD | 1,686 Persons
Survivability: Navy Survivability Policy for Surface Ships
Equals threshold, implement recommendat- | Equals threshold, implement recommendat- | Level II per OPNAV- INST 9070.1 of | TBD | Equals threshold, implement

## Table 12
ions of the NAVSEA USS COLE Survivability Review Group Phase II Analysis Report of Amphibious Ships, April 2003 | ions of the NAVSEA COLE Survivability Review Group Phase II Analysis Report of Amphibious Ships, April 2003 | September 23, 1988 (LHA(R) cargo magazine protection as stated in para. 6.b.17 of the CDD |  | recommend-ations of the NAVSEA COLE Survivability Review Group Phase II Analysis Report of Amphibious Ships, April 2003
Force Protection: Collective Protection System (CPS)
Expanded CBR protection | Expanded CBR protection | CBR protection that | TBD | CBR protection that
that provides a toxic-free | that provides a toxic-free | provides a toxic-free |  | provides a toxic-
environment (where it is | environment (where it is | environment (where it |  | free environment
not necessary to wear | not necessary to wear | is not necessary to |  | (where it is not
protective clothing or | protective clothing or | wear protective |  | necessary to wear
masks) for 40% of crew in | masks) for 40% of crew in | clothing or masks) for |  | protective clothing
berthing, messing, | berthing, messing, | 40% of crew in |  | or masks) for 40%
sanitary, and battle | sanitary, and battle | berthing, messing, |  | of crew in berthing,
dressing facilities as well | dressing facilities as well | sanitary, and battle |  | messing, sanitary,
as key operational spaces | as key operational spaces | dressing facilities |  | and battle dressing
that can be affordably | that can be affordably |  |  | facilities
integrated into ship design | integrated into ship design
Force Protection: Decontamination Stations
Four decontaminat-ion | Four decontaminat-ion | Four decontaminat-ion | TBD | Four decontamina-
stations (two CPS, one | stations (two CPS, one | stations (two CPS, |  | tion stations (two
casualty, and one | casualty, and one | one casualty, and one |  | CPS, one casualty,
conventional) providing a | conventional) providing a | conventional) providing |  | and one
capability of | capability of | a capability of |  | conventional)
decontamination an avg of | decontamination an avg of | decontamination an |  | providing a
ten people per hr per | ten people per hr per | avg of ten people per |  | capability of
station | station | hr per station |  | decontamin-ation
an avg of ten
people per hr per
station
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Development Document (CDD) dated December 17, 2009
Change Explanations
None

## Table 13
Acronyms and Abbreviations
avg - average
CBR - Chemical, Biological, and Radiological cu - cubic
etc. - etcetera ft. - feet
hrs - hours
INST. - Instruction
NAVSEA - Naval Sea Systems Command OPNAV - Office of the Chief of Naval Operations sq. - square

## Table 14
Track to Budget
RDT&E
Appn |  | BA | PE
Navy | 1319 04 |  | 0603564N
| Project |  | Name
| 408 |  | Ship Preliminary Design & Feasibility Studies/Ship Development |  |  | (Shared) | (Sunk)
Navy | 1319 05 |  | 0604567N
| Project |  | Name
| 2465 |  | Ship Contract Design/Live Fire T&E
| 9235 |  | Ship Contract Design/Live Fire Test & Evaluation/LHA (R) DESIGN |  |  | (Shared) | (Sunk)
| 9236 |  | Ship Contract Design/Live Fire Test & Evaluation/LHA(R) DESIGN |  |  | (Shared) | (Sunk)
| 9999 |  | Congressional Add |  |  |  | (Sunk)
Navy | 1611 03 |  | 0204411N
| Line Item |  | Name
| 3041 |  | LHA Replacement
| Notes: |  | LHA Replacement End Cost
Navy | 1611 05 |  | 0204411N
| Line Item |  | Name
| 5110 |  | Outfitting |  | (Shared)
| 5300 |  | Completion of Prior Year Shipbuilding Programs |  | (Shared) (Sunk)
Notes: Budget realigned to line item 3041 during year of execution.
Navy | 1804 01 |  | 0204411N
| Project |  |  | Name
| 1C6C |  | LHA(R) TADTAR
Procurement
Appn |  | BA | PE
Acq O&M
Appn |  | BA | PE

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2006 $M | [5 empty] | BY 2006 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E | 199.9 |  |  | 240.6 | 264.7 |  |  | 378.91 |  | 197.5 |  |  | 239.9 |  | 403.2
Procurement | 2677.5 |  |  | 5420.9 | 5963 |  |  | 7952.01 |  | 2896 |  |  | 6563.4 |  | 10421.9
Flyaway | -- |  |  | -- | -- |  |  | 7952 |  | -- |  |  | -- |  | 10421.9
Recurring | -- |  |  | -- | -- |  |  | 7952 |  | -- |  |  | -- |  | 10421.9
Non Recurring | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Other Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 1.6 | 1.8 |  |  | 2.21 |  | 0 |  |  | 1.6 |  | 2.2
Total | 2877.4 |  |  | 5663.1 | N/A |  |  | 8333.1 |  | 3093.5 |  |  | 6804.9 |  | 10827.3
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The estimate to support this program, like most cost estimates, is built upon a product-oriented work breakdown structure based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which we have been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for MDAPs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about as likely the estimate will prove too low or too high for the program as described.
Total Quantity
Quantity |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  | 1 |  |  |  | 2 |  |  |  |  | 3
Total |  | 1 |  |  |  | 2 |  |  |  |  | 3

## Table 16
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 354.1 | 8.5 |  | 9.5 |  | 8.1 | 14.6 |  | 2.4 |  | 6 |  | 0 |  | 403.2
Procurement | 6542.7 | 491.7 |  | 1638.8 |  | 1692 | 39.2 |  | 17.5 |  | 0 |  | 0 |  | 10421.9
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 1 | 0.2 |  | 0.2 |  | 0.2 | 0.2 |  | 0.2 |  | 0.2 |  | 0 |  | 2.2
PB 2017 Total | 6897.8 | 500.4 |  | 1648.5 |  | 1700.3 | 54 |  | 20.1 |  | 6.2 |  | 0 |  | 10827.3
PB 2016 Total | 6902 | 302.4 |  | 1547.1 |  | 2107.4 | 54.8 |  | 22.8 |  | 0 |  | 0 |  | 10936.5
Delta | -4.2 | 198 |  | 101.4 |  | -407.1 | -0.8 |  | -2.7 |  | 6.2 |  | 0 |  | -109.2
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0
Production | 0 |  | 2 |  | 0 | 1 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 3
PB 2017 Total | 0 |  | 2 |  | 0 | 1 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 3
PB 2016 Total | 0 |  | 2 |  | 0 | 1 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 3
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0

## Table 17
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.2
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.9
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 76.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.5
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 403.2

## Table 18
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2006 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.6
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.3
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.5
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.5
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 378.9

## Table 19
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | 149.2 |  | -- |  | -- |  | 149.2 |  | -- |  | 149.2
2006 |  | -- | 350.1 |  | -- |  | -- |  | 350.1 |  | -- |  | 350.1
2007 |  | 1 | 1131.1 |  | -- |  | -- |  | 1131.1 |  | -- |  | 1131.1
2008 |  | -- | 1365.8 |  | -- |  | -- |  | 1365.8 |  | -- |  | 1365.8
2009 |  | -- | 190.7 |  | -- |  | -- |  | 190.7 |  | -- |  | 190.7
2010 |  | -- | 169.5 |  | -- |  | -- |  | 169.5 |  | -- |  | 169.5
2011 |  | 1 | 937.6 |  | -- |  | -- |  | 937.6 |  | -- |  | 937.6
2012 |  | -- | 1942.1 |  | -- |  | -- |  | 1942.1 |  | -- |  | 1942.1
2013 |  | -- | 173.6 |  | -- |  | -- |  | 173.6 |  | -- |  | 173.6
2014 |  | -- | 68.3 |  | -- |  | -- |  | 68.3 |  | -- |  | 68.3
2015 |  | -- | 64.7 |  | -- |  | -- |  | 64.7 |  | -- |  | 64.7
2016 |  | -- | 491.7 |  | -- |  | -- |  | 491.7 |  | -- |  | 491.7
2017 |  | 1 | 1638.8 |  | -- |  | -- |  | 1638.8 |  | -- |  | 1638.8
2018 |  | -- | 1692 |  | -- |  | -- |  | 1692 |  | -- |  | 1692
2019 |  | -- | 39.2 |  | -- |  | -- |  | 39.2 |  | -- |  | 39.2
2020 |  | -- | 17.5 |  | -- |  | -- |  | 17.5 |  | -- |  | 17.5
Subtotal |  | 3 | 10421.9 |  | -- |  | -- |  | 10421.9 |  | -- |  | 10421.9

## Table 20
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 2006 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | 141.6 |  | -- |  | -- |  | 141.6 |  | -- |  | 141.6
2006 |  | -- | 321 |  | -- |  | -- |  | 321 |  | -- |  | 321
2007 |  | 1 | 991.6 |  | -- |  | -- |  | 991.6 |  | -- |  | 991.6
2008 |  | -- | 1157.9 |  | -- |  | -- |  | 1157.9 |  | -- |  | 1157.9
2009 |  | -- | 156.8 |  | -- |  | -- |  | 156.8 |  | -- |  | 156.8
2010 |  | -- | 134.7 |  | -- |  | -- |  | 134.7 |  | -- |  | 134.7
2011 |  | 1 | 721.4 |  | -- |  | -- |  | 721.4 |  | -- |  | 721.4
2012 |  | -- | 1461.4 |  | -- |  | -- |  | 1461.4 |  | -- |  | 1461.4
2013 |  | -- | 128.1 |  | -- |  | -- |  | 128.1 |  | -- |  | 128.1
2014 |  | -- | 49.5 |  | -- |  | -- |  | 49.5 |  | -- |  | 49.5
2015 |  | -- | 46.1 |  | -- |  | -- |  | 46.1 |  | -- |  | 46.1
2016 |  | -- | 343.6 |  | -- |  | -- |  | 343.6 |  | -- |  | 343.6
2017 |  | 1 | 1123.6 |  | -- |  | -- |  | 1123.6 |  | -- |  | 1123.6
2018 |  | -- | 1137.6 |  | -- |  | -- |  | 1137.6 |  | -- |  | 1137.6
2019 |  | -- | 25.8 |  | -- |  | -- |  | 25.8 |  | -- |  | 25.8
2020 |  | -- | 11.3 |  | -- |  | -- |  | 11.3 |  | -- |  | 11.3
Subtotal |  | 3 | 7952 |  | -- |  | -- |  | 7952 |  | -- |  | 7952

## Table 21
Cost Quantity Information 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2006 $M
2005 | -- | --
2006 | -- | --
2007 | 1 | 2836.8
2008 | -- | --
2009 | -- | --
2010 | -- | --
2011 | 1 | 2520.1
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | 1 | 2595.1
2018 | -- | --
2019 | -- | --
2020 | -- | --
Subtotal | 3 | 7952

## Table 22
Annual Funding 1804 ¦ Acq O&M ¦ Operation and Maintenance, Navy
Fiscal Year | TY $M
Total Program
2010 | 0.2
2011 | 0.2
2012 | 0.2
2013 | 0.1
2014 | 0.1
2015 | 0.2
2016 | 0.2
2017 | 0.2
2018 | 0.2
2019 | 0.2
2020 | 0.2
2021 | 0.2
Subtotal | 2.2

## Table 23
Annual Funding 1804 ¦ Acq O&M ¦ Operation and Maintenance, Navy
Fiscal Year | BY 2006 $M
Total Program
2010 | 0.2
2011 | 0.2
2012 | 0.2
2013 | 0.1
2014 | 0.1
2015 | 0.2
2016 | 0.2
2017 | 0.2
2018 | 0.2
2019 | 0.2
2020 | 0.2
2021 | 0.2
Subtotal | 2.2

## Table 24
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2006-02-14 | 2012-05-08
Approved Quantity | 1 | 2
Reference | LHA(R)/LHA 6 Milestone B ADM | LHA(R)/LHA 6/LHA 7 Milestone B ADM
Start Year | 2007 | 2007
End Year | 2013 | 2018
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the ADM dated February 14, 2006, which approved one ship, which is standard for shipbuilding programs.
An additional ADM authorized a second ship on May 8, 2012.

## Table 25
Foreign Military Sales
None
Nuclear Costs
None

## Table 26
Unit Cost
Unit Cost Report
Item |  | BY 2006 $M | BY 2006 $M |  | % Change
|  | Current UCR Baseline (May 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 5663.1 |  |  | 8333.1
Quantity | 2 |  |  | 3
Unit Cost | 2831.55 |  |  | 2777.7 |  | -1.9
Average Procurement Unit Cost
Cost | 5420.9 |  |  | 7952
Quantity | 2 |  |  | 3
Unit Cost | 2710.45 |  |  | 2650.667 |  | -2.21
Item |  | BY 2006 $M | BY 2006 $M |  | % Change
|  | Original UCR Baseline (Jan 2006 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 2877.4 |  |  | 8333.1
Quantity | 1 |  |  | 3
Unit Cost | 2877.4 |  |  | 2777.7 |  | -3.46
Average Procurement Unit Cost
Cost | 2677.5 |  |  | 7952
Quantity | 1 |  |  | 3
Unit Cost | 2677.5 |  |  | 2650.667 |  | -1

## Table 27
Unit Cost History
Item |  |  | Date |  |  | BY 2006 $M | [6 empty] | TY $M
[6 empty] | PAUC |  |  |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  | Jan 2006 |  |  |  | 2877.4 |  |  |  |  | 2677.5 |  |  | 3093.5 |  |  | 2896
APB as of January 2006 |  | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  | Jan 2006 |  |  |  | 2877.4 |  |  |  |  | 2677.5 |  |  | 3093.5 |  |  | 2896
Current APB |  | May 2012 |  |  |  | 2831.55 |  |  |  |  | 2710.45 |  |  | 3402.45 |  |  | 3281.7
Prior Annual SAR |  | Dec 2014 |  |  |  | 2802.733 |  |  |  |  | 2676.533 |  |  | 3645.5 |  |  | 3511.367
Current Estimate |  | Dec 2015 |  |  |  | 2777.7 |  |  |  |  | 2650.667 |  |  | 3609.1 |  |  | 3473.967
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch | Eng |  |  | Est | Oth |  |  | Spt | Total
3093.500 271.200 566.567 3.133 19.500 -435.467 90.667 0.000 515.600 3609.100
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch | Eng |  | Est |  | Oth |  |  | Spt | Total
2896.000 271.500 698.234 3.133 0.000 -485.567 90.667 0.000 577.967 3473.967

## Table 28
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | Jul 2001 | N/A | Jul 2001
Milestone B | N/A | Jan 2006 | N/A | Jan 2006
Milestone C | N/A | N/A | N/A | N/A
IOC | N/A | Sep 2013 | N/A | Sep 2016
Total Cost (TY $M) | N/A | 3093.5 | N/A | 10827.3
Total Quantity | N/A | 1 | N/A | 3
PAUC | N/A | 3093.5 | N/A | 3609.1

## Table 29
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Acq O&M |  | Total
SAR Baseline (Development Estimate)
Previous Changes
197.5 2896.0 -- -- 3093.5
Economic |  | -0.5 |  | 802.4 |  | -- |  | -- |  | 801.9
Quantity |  | -- |  | 7886.7 |  | -- |  | -- |  | 7886.7
Schedule |  | -- |  | 17.4 |  | -- |  | -- |  | 17.4
Engineering |  | 58.5 |  | -- |  | -- |  | -- |  | 58.5
Estimating |  | 144.9 |  | -1340.4 |  | -- |  | 2 |  | -1193.5
Other |  | -- |  | 272 |  | -- |  | -- |  | 272
Support |  | -- |  | -- |  | -- |  | -- |  | --
Subtotal |  | 202.9 |  | 7638.1 |  | -- |  | 2 |  | 7843
Current Changes Economic |  | -0.4 |  | 12.1 |  | -- |  | -- |  | 11.7
Quantity |  | -- |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -8 |  | -- |  | -- |  | -8
Engineering |  | -- |  | -- |  | -- |  | -- |  | --
Estimating |  | 3.2 |  | -116.3 |  | -- |  | 0.2 |  | -112.9
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | -- |  | --
Subtotal |  | 2.8 |  | -112.2 |  | -- |  | 0.2 |  | -109.2
Total Changes |  | 205.7 |  | 7525.9 |  | -- |  | 2.2 |  | 7733.8
CE - Cost Variance |  | 403.2 |  | 10421.9 |  | -- |  | 2.2 |  | 10827.3
CE - Cost & Funding |  | 403.2 |  | 10421.9 |  | -- |  | 2.2 |  | 10827.3

## Table 30
Summary BY 2006 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Acq O&M |  | Total
SAR Baseline (Development Estimate)
Previous Changes
199.9 2677.5 -- -- 2877.4
Economic |  | -- |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 6142.3 |  | -- |  | -- |  | 6142.3
Schedule |  | -- |  | -33.3 |  | -- |  | -- |  | -33.3
Engineering |  | 49.5 |  | -- |  | -- |  | -- |  | 49.5
Estimating |  | 127.2 |  | -1006.6 |  | -- |  | 2 |  | -877.4
Other |  | -- |  | 249.7 |  | -- |  | -- |  | 249.7
Support |  | -- |  | -- |  | -- |  | -- |  | --
Subtotal |  | 176.7 |  | 5352.1 |  | -- |  | 2 |  | 5530.8
Current Changes Economic |  | -- |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | -- |  | --
Estimating |  | 2.3 |  | -77.6 |  | -- |  | 0.2 |  | -75.1
Other |  | -- |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | -- |  | --
Subtotal |  | 2.3 |  | -77.6 |  | -- |  | 0.2 |  | -75.1
Total Changes |  | 179 |  | 5274.5 |  | -- |  | 2.2 |  | 5455.7
CE - Cost Variance |  | 378.9 |  | 7952 |  | -- |  | 2.2 |  | 8333.1
CE - Cost & Funding |  | 378.9 |  | 7952 |  | -- |  | 2.2 |  | 8333.1
Previous Estimate: June 2015

## Table 31
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -0.4
Revised estimate to reflect execution year realignments and Navy Working Capital Fund (NWCF) rate adjustments. (Estimating)
+2.0 +2.9
Adjustment for current and prior escalation. (Estimating) +0.3 +0.3
RDT&E Subtotal +2.3 +2.8
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A +12.1
Revised phasing of LHA 8 funding from FY 2018 to FY 2016 to support advance procurement lead time requirement. (Schedule)
0.0 -8.0
Revised estimate for LHA 8 procurement cost due to Service reductions. (Estimating) | -62.5 | -94.7
Revised estimate for NWCF rate adjustments. (Estimating) | 2.6 | 3.8
Revised estimate for inflation rates on Non-pay and Non Fuel Purchases. (Estimating) | -12.3 | -18
Revised estimate for LHA (R) Outfitting and Post Delivery requirements. (Estimating) | -1.3 | -2
Adjustment for current and prior escalation. (Estimating) | -4.1 | -5.4
Procurement Subtotal | -77.6 | -112.2
Acq O&M | $M
Current Change Explanations | Base Year | Then Year
LHA 8 acquisition requirement refinement for FY 2021. (Estimating) | 0.2 | 0.2
Acq O&M Subtotal | 0.2 | 0.2

## Table 32
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: LHA 7 Detail Design & Construction Contract (DD&C)
Contractor: Huntington Ingalls Incorporated
Contractor Location: 1000 Access Road
Pascagoula, MS 39567
Contract Number: N00024-10-C-2229
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 30, 2010
Definitization Date: May 31, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
2355.0 2664.9 1 2450.4 2772.4 1 2599.8 2450.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of scope for the incorporation of Flight Deck Strengthening and the Joint Strike Fighter modifications. Additional change is the result of expenses related to Pension Protection Act Harmonization and Katrina Depreciation settlements, and various engineering change proposals.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/24/2016) -107.2 -2.3
Previous Cumulative Variances -71.7 +7.5
Net Change -35.5 -9.8
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to continued labor inefficiencies in Hull departments. Additional variance is attributed to high indirect costs in General and Administrative (G&A) and Overhead accounts, well above what was established in the performance measurement baseline.
The unfavorable net change in the schedule variance is due to milestone payments for material items being achieved later than what was baselined.
Notes
The LHA 7 Advance Procurement Contract and Long Lead Time Material CLIN has been subsumed by the LHA 7 DD&C contract. The Program Manager Estimated Price at Completion (PMEAC) reflects the Current Target Price of the contract. A formal PMEAC for LHA 7 has commenced, as Earned Value progress for Vessel labor hours has reached 20% complete.

## Table 33
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 1 | 1 | 3 | 33.33%
Total Program Quantity Delivered | 1 | 1 | 3 | 33.33%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
10827.3
4916.8
45.41%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
16
76.19%
7398.2
68.33%
The above data is current as of February 09, 2016.
Total expenditures are representative of LHA 6 and LHA 7.

## Table 34
Operating and Support Cost
Cost Estimate Details
Date of Estimate: April 02, 2012
Source of Estimate: POE
Quantity to Sustain: 2
Unit of Measure: Ship
Service Life per Unit: 40.00 Years
Fiscal Years in Service: FY 2017 - FY 2062
Two ships currently in production, the LHA 6 and LHA 7, will be sustained over a 40 year life cycle. Sustainment requirements for a planned third ship, the LHA 8, will be included upon competition of the Program Life Cycle Cost Estimate, third quarter FY 2016. O&S costs for LHA 8 will be included in the next SAR.
The intent is to estimate the normal costs of operating and supporting the ship in typical peacetime operations. Additional costs that might be incurred under wartime operating scenarios are not included. Potential costs of currently unplanned and unknown future upgrades or configuration changes are assumed to occur in the same proportion as modernization work that has occurred on the LHD 1 ship classes. Operating & Support Cost Analysis Model (OSCAM) builds the O&S costs by month, and the results show the estimated cost by year based on the Operational Tempo (OPTEMPO) and maintenance cycle. In order to obtain a per year estimate, the total O&S cost as reported by OSCAM (without disposal costs included) is divided by the 40 year life expectancy. Nominal OPTEMPO is assumed to be 2700 hours steaming underway and 1200 hours steaming not underway, based on the fuel burn rates and time profiles provided by the LHA 6 design team (in section 6.0 of the CARD).
Sustainment Strategy
The LHA 6 sustainment strategy includes the use of commercial shipyards for depot maintenance in concert with Organizational and Intermediate level maintenance strategies. Existing shore support and infrastructure will be used to the maximum extent possible. Life cycle cost savings are anticipated from fuel savings realized from the propulsion system and Manpower savings expected from operations and maintenance of the Gas Turbine engines.
Antecedent Information
The antecedent system designated for LHA 6 is LHD 1. LHD 1 Unitized O&S Costs (BY 2006 $M) were developed in 2013 and also reflect the Operating and Support Cost Analysis Model (OSCAM) historical average dataset for LHD 1. Visibility and Management of Operating and Support Costs data reflects average O&S return data for active ships (LHD1-
7) between FY 1992 and FY 2011. Open Architectural Retrieval System Open Architectural Retrieval System 3-M data includes the years FY 2001 through FY 2011. Like the LHA 6 and LHA 7 Unitized O&S Costs, antecedent costs reflect a 40 year life cycle.
Projected manning on LHA 6 and LHA 7 includes approximately 24 fewer officer and 55 fewer enlisted personnel than the average historical manning on LHD 1-7. However, FY 2006 Military Pay Rates utilized to estimate LHA (R) Flight 0 Personnel are approximately 12 percent higher than the average LHD 1-7 historical rates, which were inflated to FY 2006. Therefore, Unit Level Personnel costs do not reflect expected savings due to reduction in crew size. If personnel rates were normalized, the LHA 6 and LHA 7 would show an approximate 10 percent savings when compared to the antecedent class. The discrepancy between historical rates and the FY 2006 set could be driven in part by actual crews being manned with lower ranking personnel than that assumed in the LHA 6 and LHA 7 baseline.
For comparative purposes, the FY 2006 cost per barrel of Diesel Fuel, Marine (DFM) was substituted for the historical average cost of DFM observed in LHD 1 class data. This methodology better aligns LHD 1 historical requirements for Unit Operations with estimated requirements for the LHA 6 and LHA 7.

## Table 35
In line with LHA 6 and LHA 7 Maintenance requirements, antecedent Maintenance costs reflect requirements laid out in the Office of the Chief of Naval Operations 4700 (2011).
The scope of LHD 1 Indirect Support costs, which were first mandated in the OSD, CAPE O&S Cost Estimating Guide (published October 2007), align with LHA 6 and LHA 7 requirements but reflect a larger average historical crew size than that projected for the LHA 6 and LHA 7.
Annual O&S Costs BY2006 $M
Cost Element |  | LHA 6 Average Annual Cost Per Ship | [5 empty] | LHD 1 (Antecedent) Average Annual Cost Per Ship
Unit-Level Manpower |  | 65.684 | [5 empty] | 63.895
Unit Operations |  | 11.953 | [5 empty] | 18.246
Maintenance |  | 27.936 | [5 empty] | 33.525
Sustaining Support |  | 4.44 | [5 empty] | 4.873
Continuing System Improvements |  | 7.692 | [5 empty] | 7.376
Indirect Support |  | 27.247 | [5 empty] | 31.094
Other |  | 0 | [5 empty] | 0
Total |  | 144.952 | [5 empty] | 159.009
Item | Total O&S Cost $M
| LHA 6 | [7 empty] | LHD 1 (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 12095.2 |  |  | 13304.7 |  |  | 11596.3 |  | 12720.7
Then Year | 24951 |  |  | N/A |  |  | 23788.5 |  | N/A
Equation to Translate Annual Cost to Total Cost
Total O&S Cost = 2 Ships x 40 Service Life x Unitized LHA 6 Cost or LHD 1 Antecedent Cost
O&S Cost Variance
Category |  |  | BY 2006 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Jun 2015 SAR
11596.3
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 11596.3

## Table 36
Disposal Estimate Details
Date of Estimate: April 02, 2012
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2006 $M): Total costs for disposal of all Ship are 19.8
The CG class of ship was determined by the Naval Sea Systems Command (NAVSEA) Inactive Ships Program Office (PMS 333) as most comparable to the LHA 7 out of those vessels historically disposed of by NAVSEA. The decision to use the CG class of ships was based upon the comparison of warship compartmentalization, hazardous materials to remove and hull weight, influenced by scrap metal commodity prices.