## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-516
SSN 774 Virginia Class Submarine (SSN 774)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 13
Track to Budget 14
Cost and Funding 16
Low Rate Initial Production 27
Foreign Military Sales 28
Nuclear Costs 28
Unit Cost 29
Cost Variance 32
Contracts 35
Deliveries and Expenditures 42
Operating and Support Cost 43

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
SSN 774 Virginia Class Submarine (SSN 774)
DoD Component
Navy
Responsible Office
CAPT Michael Stevens
VIRGINIA Submarine Program Office PEO Submarines
614 Sicard Street, SE
Washington Navy Yard, DC 20376-7022
michael.j.stevens@navy.mil
Phone: | 202-781-1294
Fax: | 202-781-4678
DSN Phone: | 326-1294
DSN Fax: | 326-4678
Date Assigned: | June 16, 2015
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 3, 2010
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 3, 2010

## Table 6
Mission and Description
The VIRGINIA Class (SSN 774) Submarine Program is bringing forward a critical national security asset designed to flexibly address the unique multi-mission requirements of the post-Cold War era. Capable of performing traditional submarine missions, dominating the littoral battle space and adapting to future requirements, the VIRGINIA Class Submarine satisfies any assigned role well into the Twenty-First Century. Intended to replace the fleet of SSN 688 Class submarines, the VIRGINIA Class Submarine is characterized by state-of-the-art stealth, enhanced features for special operations forces, and cost effective Command, Control, Communication and Intelligence capability. With an array of armament including the MK48 Advanced Capability torpedo and cruise missile vertical launch capability, the VIRGINIA Class Submarine maintains total undersea superiority at an affordable cost.

## Table 7
Executive Summary
Program Highlights Since Last Report:
The VIRGINIA Class Submarine Program continues to deliver submarines within cost, ahead of schedule, with improved quality and with increasing performance capabilities more than eleven years after lead ship delivery in October 2004. With the delivery to the Navy of USS JOHN WARNER (SSN 785) in June 2015, 12 VIRGINIAs are in service today.
The program is restructuring to increase the number of submarines in the class from 30 to 48. A Component Cost Position is being developed to support an update to the APB, which, in addition to VIRGINIA Payload Module (VPM) will also include Acoustic Superiority (AS) on Block V and follow-on ships.
The VPM design is progressing on schedule. An initial Integrated Master Schedule (IMS) was submitted in December 2014 with an IMS for final module configuration submitted in December 2015. VPM prototyping is underway for an FY 2019 construction start which is supported by Detailed Design and contractor furnished equipment long lead time material in the President’s Budget for 2017 (PB17). SOUTH DAKOTA Insertion Program (SDIP) is a near-term AS concept demonstration on a VIRGINIA Class platform to be installed during SOUTH DAKOTA (SSN 790) Post Shakedown Availability. PB17 includes RDT&E funding for SDIP and AS for Block V.
Recent milestones in the construction and testing of VIRGINIA Class Submarines are highlighted by the Commissioning of USS JOHN WARNER (SSN 785) at Norfolk Naval Shipyard on August 1, 2015 and the Christening of ILLINOIS (SSN 786) on October 10, 2015 by the First Lady, Michelle Obama, the ship’s sponsor. WASHINGTON (SSN 787) achieved a significant production milestone with the completion of her pressure hull on August 29, 2015.
Other near term VIRGINIA Class program events include Pre-Commissioning Unit (PCU) COLORADO (SSN 788) completion of her Pressure Hull in February 2016. PCU ILLINOIS (SSN 786) is projected to deliver in May 2016, marking a 62 month construction span. PCU WASHINGTON (SSN 787) is projected to deliver in September 2016 with a 60.5 month production period.
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation:
August 1992: Milestone 0 for Centurion Submarine, “the first submarine designed with affordability considerations paramount”. Conceptualized as a lower cost alternative to SEAWOLF Class.
August 1994: Milestone I was approved for the New Attack Submarine (NSSN) following two years of extensive review of requirements and rigorous systems definition effort.
December 1994: Milestone I APB established.
June 30, 1995: The New Attack Submarine Program successfully passed Milestone II with the signing of an ADM.
June 1995: A waiver from full-up, system-level live fire testing was approved jointly by USD(A&T) and Director, Operational Test & Evaluation with notification letters sent to Congressional Defense Committees on June 29, 1995.
April 24, 1996: Contract award for the NSSN Command, Control, Communications and Intelligence (C3I) System was executed to Lockheed Martin Federal Systems.
May 9, 1996: The Integrated Process and Product Development 1996 Design/Build Contract with Electric Boat (EB) Corporation was definitized.
October 27, 1997: The revised APB (Change 1 to the Development Baseline of June 30, 1995) was signed to reflect the co-

## Table 8
construction teaming arrangement between EB) and Newport News Shipbuilding (NNS) as mandated in the FY98 Authorization and Appropriations Acts.
September 30, 1998: The IPPD 96 Design Build contract with EB was modified to include construction of the first four VIRGINIA Class Submarines.
January 2001: Systems testing and integration started on the first Command and Control Systems Module (CCSM) at the Off-hull Assembly and Test Site (COATS). The COATS facility is used to test VIRGINIA Class CCSM units prior to shipyard delivery.
August 2003: The Navy awarded the Block II construction contract with clauses to transition to a multi-year contract in FY2004 in pursuit of the lowest possible future program costs.
January 2004: The transition to multi-year procurement for hulls six through ten was completed in January 2004 following approval by Congress in the FY04 Defense Appropriations and Authorization Acts.
October 12, 2004: Lead Ship delivery (USS VIRGINIA SSN 774). Delivery occurred within the original baseline schedule threshold set ten years earlier, in 1994.
June 20, 2006: USS TEXAS, which was essentially the second lead ship of the class, is the first submarine delivered at Northrop Grumman, Newport News in nearly ten years.
March 5, 2007: The program achieves IOC although USS VIRGINIA first deployed operationally in the fall of 2005 in support of the Global War on Terror.
December 2008: The Navy awards the Block III construction contract to General Dynamics Electric Boat (and Northrop Grumman Newport News) for the construction of eight VIRGINIA Class submarines from FY 2009 through FY 2013.
September 2010: The program achieves Milestone III. The ADM was signed by USD(AT&L) and included a declaration of Full Operational Capability and authorization of Full Rate Production.
October 2010: The program accelerates to Full Rate Production of two ships per year.
April 2014: The Navy, with General Dynamics Electric Boat and Huntington Ingalls Industries-Newport News, signed a Block IV Construction Contract to build ten VIRGINIA Class Submarines. Under the five-year agreement, Electric Boat and Newport News Shipbuilding will jointly build two ships per year from FY 2014 - FY 2018.

## Table 9
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Schedule -- This schedule breach was previously reported in the December 2006 SAR.
Nunn McCurdy Unit Cost -- This program reflects a significant Nunn- McCurdy breach to the original baseline that was first reported in the December 2005 SAR.
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC Significant APUC Significant

## Table 10
Schedule

## Table 11
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone 0 | Aug 1992 | Aug 1992 | Feb 1993 | Aug 1992
Milestone I | Aug 1994 | Aug 1994 | Feb 1995 | Aug 1994
Milestone II | Jun 1995 | Jun 1995 | Dec 1995 | Jun 1995
New Attack Submarine Integrated Product and Process Development Contract Award | Oct 1995 | Oct 1995 | Apr 1996 | Jan 1996
Program Review (LRIP) | Sep 1997 | Sep 1997 | Mar 1998 | Jan 1997
Organizational Support (by Fast Cruise) | Apr 2004 | Apr 2004 | Oct 2004 | Apr 2004
Lead Ship Delivery | Jun 2004 | Jun 2004 | Dec 2004 | Oct 2004
LFT&E Shock Tests | Jun 2006 | Jun 2006 | Dec 2006 | N/A1
Intermediate Support (by IOC) | Jan 2006 | Jan 2006 | Jul 2006 | Jun 2006
IOC (Lead Ship) | Nov 2006 | Nov 2006 | May 2007 | Mar 2007
Initial Operational Test & Evaluation
Start | Feb 2008 | Feb 2008 | Aug 2008 | Jan 2008
Complete | Sep 2008 | Sep 2008 | Mar 2009 | Mar 2009
Milestone III | Jul 2010 | Jul 2010 | Jan 2011 | Sep 2010
Depot Shipyard Support | Aug 2015 | Aug 2015 | Feb 2016 | Jun 2013
Related Programs
NSSN COMMAND AND CONTROL SYSTEM
FY 1995 Open Architecture Demo Complete | Oct 1995 | Oct 1995 | Apr 1996 | Sep 1995
C&CS Module Start Fabrication | Jun 1999 | Jun 1999 | Dec 1999 | Jun 1999
GFE C&CS Delivered to Shipyard | Dec 2000 | Dec 2000 | Jun 2001 | Dec 2000
LBTS Integration and Test Complete | Apr 2002 | Apr 2002 | Oct 2002 | Apr 2002
C&CS Module delivered to ship | May 2002 | May 2002 | Nov 2002 | May 2002
1 APB Breach
Classified Schedule information is provided in the classified annex to this submission.
Change Explanations
None
Notes
On December 4, 2006, the USD(AT&L) notified Congress of the decision to eliminate the VIRGINIA Class Ship Shock Test from the Live Fire Test and Evaluation portion of the VIRGINIA Class Test and Evaluation Master Plan.

## Table 12
Acronyms and Abbreviations
C&CS - Command and Control System GFE - Government Furnished Equipment LBTS - Land Based Test Site
LFT&E - Live Fire Test and Evaluation NSSN - New Attack Submarine

## Table 13
Performance
Classified Performance information is provided in the classified annex to this submission.

## Table 14
Track to Budget
RDT&E
Appn |  |  |  |  | BA | PE
Navy 1319 03 0603561N
Project |  | Name
2177 NEW DESIGN SSN HM&E (NSSN UNIQUE)
Navy 1319 03 0603564N
(Sunk)
|  |  | Project |  |  | Name
|  |  | 2200 |  |  | Ship Preliminary Design |  | (Sunk)
Navy |  |  | 1319 | 3 |  | 0603570N
|  |  | Project |  |  | Name
|  |  | 2158 |  |  | NUCLEAR PROPULSION (Sunk)
Navy |  |  | 1319 | 5 |  | 0604558N
Project | [5 empty] | Name
1947 | [5 empty] | NEW DESIGN SSN HM&E and Combat Systems
1950 | [5 empty] | NEW DESIGN SSN HM&E and Combat Systems
2429 | [5 empty] | NEW DESIGN SSN HM&E and Combat Systems |  |  | (Sunk)
2430 | [5 empty] | NEW DESIGN SSN HM&E and Combat Systems |  |  | (Sunk)
2644 | [5 empty] | NEW DESIGN SSN HM&E and Combat Systems |  |  | (Sunk)
2645 | [5 empty] | NEW DESIGN SSN HM&E and Combat Systems |  |  | (Sunk)
2887 | [5 empty] | NEW DESIGN SSN HM&E and Combat Systems |  |  | (Sunk)
2888 | [5 empty] | NEW DESIGN SSN HM&E and Combat Systems |  |  | (Sunk)
3062 | [5 empty] | NEW DESIGN SSN HM&E and (Shared) Combat Systems |  |  | (Sunk)
4500 | [5 empty] | VIRGINIA Payload Module |  |  | (Sunk)
Notes: VIRGINIA Payload Module funding shifted to Program Element 0604580N beginning in FY 2014.
9231 | NEW DESIGN SSN HM&E and Combat Systems | [5 empty] | (Sunk)
9232 | NEW DESIGN SSN HM&E and Combat Systems | [5 empty] | (Sunk)
9386 | NEW DESIGN SSN HM&E and Combat Systems | [5 empty] | (Sunk)
9387 | NEW DESIGN SSN HM&E and Combat Systems | [5 empty] | (Sunk)
9999 | NEW DESIGN SSN HM&E and | [5 empty] | (Sunk)

## Table 15
Combat Systems
Navy | 1319 04 |  | 0604567N
| Project |  | Name
| 2199 |  | Ship Contract Design | (Sunk)
Navy | 1319 05 |  | 0604580N
| Project |  | Name
| 4500 |  | VIRGINIA Payload Module
Notes
FYDP funding includes the following projects from BA 05 PE 0604558: Project F1947 New Design Hull Mechanical & Electrical (HM&E) and Project F1950 New Design Combat Systems. PE 0604558, Project 3062, Multi-mission Team Trainer, is not included as part of the VIRGINIA Class baseline acquisition cost for RDT&E. Project F4500 VIRGINIA Payload Module shifted to PE 0604580 beginning in FY 2014.
Procurement
Navy | 1611 02 |  | 0204281N
| Line Item |  | Name
| 2013 |  | New SSN (NSSN-1)
Navy | 1611 05 |  | 0204281N
| Line Item |  | Name
| 5110 |  | Outfitting and Post Delivery |  | (Shared)
| 5300 |  | Completion of Prior Year Shipbuilding Programs |  | (Shared) (Sunk)
Navy | 1810 01 |  | 0204281N
| Line Item |  | Name
| 920 |  | Repair Parts |  | (Shared) (Sunk)
| 942 |  | VA Class Support Equipment |  | (Shared)
Notes
Appn |  | BA | PE
VIRGINIA Class program acquisition costs include a portion of the Other Procurement, Navy (OPN) budget Project Line Item 0942. Programs included in VIRGINIA Class acquisition costs are: VA Class Special Operations Forces Support, Test and Evaluation Measuring Equipment, Exterior Communication System Trainer, VIRGINIA Ship Control Operator Trainer and Major Shore Spares. The balance of the OPN budget is captured in program O&S Costs.

## Table 16
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 1995 $M |  |  |  |  | BY 1995 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 5420.4 |  | 5420.4 | 5962.4 |  | 5602.1 |  | 6351.2 |  | 6351.2 |  | 6610.1
Procurement |  | 58933.2 |  | 58933.2 | 64826.5 |  | 60925.2 |  | 86856.1 |  | 86856.1 |  | 97651.4
Flyaway |  | -- |  | -- | -- |  | 60416.9 |  | -- |  | -- |  | 96863.9
Recurring |  | -- |  | -- | -- |  | 58748.7 |  | -- |  | -- |  | 94931.6
Non Recurring |  | -- |  | -- | -- |  | 1668.2 |  | -- |  | -- |  | 1932.3
Support |  | -- |  | -- | -- |  | 508.3 |  | -- |  | -- |  | 787.5
Other Support |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares |  | -- |  | -- | -- |  | 508.3 |  | -- |  | -- |  | 787.5
MILCON |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total |  | 64353.6 |  | 64353.6 | N/A |  | 66527.3 |  | 93207.3 |  | 93207.3 |  | 104261.5
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Independent Cost Estimate (ICE) to support the VIRGINIA Class Submarine Program Milestone III decision, like all life- cycle cost estimates previously performed by Cost Assessment and Program Evaluation (CAPE), is built upon a product- oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 17
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 30 | 30 | 33
Total | 30 | 30 | 33
Quantity Notes
The Navy is planning for a class extension and has added Advance Procurement (FY 2018 - FY 2021) and Full Funding (two ships in FY 2020, one ship in FY 2021) accordingly. The Increase in the Current Estimate for cost from PB 2016 to PB 2017 is primarily due to additional funding in FY 2020 and FY 2021 for VIRGINIA Payload Module (VPM) and a class extension.

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 5355.4 | 317.2 |  |  | 208.5 | 220.2 | 85.6 |  | 75.4 |  | 85.3 |  | 262.5 |  | 6610.1
Procurement | 62194.7 | 5424.8 |  |  | 5106.8 | 5334.3 | 6894.9 |  | 7497.2 |  | 4569.9 |  | 628.8 |  | 97651.4
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 67550.1 | 5742 |  |  | 5315.3 | 5554.5 | 6980.5 |  | 7572.6 |  | 4655.2 |  | 891.3 |  | 104261.5
PB 2016 Total | 67605.7 | 5741.4 |  |  | 5544.1 | 5422.3 | 6901.9 |  | 7027 |  | 175.9 |  | 894.3 |  | 99312.6
Delta | -55.6 | 0.6 |  |  | -228.8 | 132.2 | 78.6 |  | 545.6 |  | 4479.3 |  | -3 |  | 4948.9
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 22 |  | 2 | 2 | 2 |  | 2 |  | 2 | 1 |  | 0 |  | 33
PB 2017 Total | 0 |  | 22 |  | 2 | 2 | 2 |  | 2 |  | 2 | 1 |  | 0 |  | 33
PB 2016 Total | 0 |  | 22 |  | 2 | 2 | 2 |  | 2 |  | 2 | 0 |  | 0 |  | 32
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 1 |  | 0 |  | 1

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.7
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.3
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 363.7
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 453.4
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 429
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 452.3
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 382.4
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 308.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 275.4
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 237.3
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 218.8
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 242.2
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 155.4
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 153.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 166.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 191.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 233.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 180.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 172.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 161.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 78.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 115.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 189.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 317.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 208.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 220.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 75.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.3
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.5
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.7
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.9
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.7
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.8

## Table 20
2027 | -- | -- | -- | -- | -- | -- | 22.9
Subtotal | -- | -- | -- | -- | -- | -- | 6610.1

## Table 21
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.8
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 68
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 365.9
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 447.5
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 416.4
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 433.7
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 363.7
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 289.9
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 255.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 216.9
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 198
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 216
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 134.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 129.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 136.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 153
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 183.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 140
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 132.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 120.6
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 82.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 134
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 220.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 142.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 147.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.3
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.6
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.9
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.7
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.5
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.8
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.1
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.9
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5602.1

## Table 22
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | 571 |  | -- |  | 219.3 |  | 790.3 |  | -- |  | 790.3
1997 |  | -- | 532.9 |  | -- |  | 242.5 |  | 775.4 |  | -- |  | 775.4
1998 |  | 1 | 1625 |  | -- |  | 840.9 |  | 2465.9 |  | -- |  | 2465.9
1999 |  | 1 | 1881.6 |  | -- |  | 165.6 |  | 2047.2 |  | -- |  | 2047.2
2000 |  | -- | 743.7 |  | -- |  | -- |  | 743.7 |  | -- |  | 743.7
2001 |  | 1 | 1589.8 |  | -- |  | 90.8 |  | 1680.6 |  | 0.2 |  | 1680.8
2002 |  | 1 | 2407.5 |  | -- |  | 60.8 |  | 2468.3 |  | 15.9 |  | 2484.2
2003 |  | 1 | 2402 |  | -- |  | 14.3 |  | 2416.3 |  | 8.3 |  | 2424.6
2004 |  | 1 | 2715.2 |  | -- |  | 6.9 |  | 2722.1 |  | 11 |  | 2733.1
2005 |  | 1 | 2601.5 |  | -- |  | -- |  | 2601.5 |  | 4.3 |  | 2605.8
2006 |  | 1 | 2563.9 |  | -- |  | -- |  | 2563.9 |  | 15.1 |  | 2579
2007 |  | 1 | 2580.8 |  | -- |  | -- |  | 2580.8 |  | 8.4 |  | 2589.2
2008 |  | 1 | 3157.6 |  | -- |  | -- |  | 3157.6 |  | 19.5 |  | 3177.1
2009 |  | 1 | 3652.5 |  | -- |  | -- |  | 3652.5 |  | 17.9 |  | 3670.4
2010 |  | 1 | 4034.3 |  | -- |  | -- |  | 4034.3 |  | 9.8 |  | 4044.1
2011 |  | 2 | 5164 |  | -- |  | -- |  | 5164 |  | 18.7 |  | 5182.7
2012 |  | 2 | 4735.8 |  | -- |  | -- |  | 4735.8 |  | 12.3 |  | 4748.1
2013 |  | 2 | 4686.1 |  | -- |  | -- |  | 4686.1 |  | 16.9 |  | 4703
2014 |  | 2 | 6523.4 |  | -- |  | -- |  | 6523.4 |  | 26.2 |  | 6549.6
2015 |  | 2 | 5913.2 |  | -- |  | -- |  | 5913.2 |  | 29.4 |  | 5942.6
2016 |  | 2 | 5388.2 |  | -- |  | -- |  | 5388.2 |  | 34.6 |  | 5422.8
2017 |  | 2 | 4974 |  | -- |  | 93.7 |  | 5067.7 |  | 30.1 |  | 5097.8
2018 |  | 2 | 5199.6 |  | -- |  | 90.5 |  | 5290.1 |  | 35.9 |  | 5326
2019 |  | 2 | 6459.8 |  | 267.4 |  | 107 |  | 6834.2 |  | 51.2 |  | 6885.4
2020 |  | 2 | 5818.5 |  | 1626.8 |  | -- |  | 7445.3 |  | 42.2 |  | 7487.5
2021 |  | 1 | 2536.6 |  | 1980.4 |  | -- |  | 4517 |  | 43.1 |  | 4560.1
2022 |  | -- | 122.8 |  | -- |  | -- |  | 122.8 |  | 14.2 |  | 137
2023 |  | -- | 123.6 |  | -- |  | -- |  | 123.6 |  | 11.4 |  | 135
2024 |  | -- | 105.2 |  | -- |  | -- |  | 105.2 |  | 4.7 |  | 109.9
2025 |  | -- | 102.7 |  | -- |  | -- |  | 102.7 |  | -- |  | 102.7
2026 |  | -- | 100.8 |  | -- |  | -- |  | 100.8 |  | -- |  | 100.8
2027 |  | -- | 43.4 |  | -- |  | -- |  | 43.4 |  | -- |  | 43.4
Subtotal |  | 33 | 91057 |  | 3874.6 |  | 1932.3 |  | 96863.9 |  | 481.3 |  | 97345.2

## Table 23
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | 548.1 |  | -- |  | 210.6 |  | 758.7 |  | -- |  | 758.7
1997 |  | -- | 503.9 |  | -- |  | 229.2 |  | 733.1 |  | -- |  | 733.1
1998 |  | 1 | 1502.6 |  | -- |  | 777.6 |  | 2280.2 |  | -- |  | 2280.2
1999 |  | 1 | 1712.7 |  | -- |  | 150.7 |  | 1863.4 |  | -- |  | 1863.4
2000 |  | -- | 660.2 |  | -- |  | -- |  | 660.2 |  | -- |  | 660.2
2001 |  | 1 | 1364.3 |  | -- |  | 77.9 |  | 1442.2 |  | 0.2 |  | 1442.4
2002 |  | 1 | 2054.3 |  | -- |  | 51.8 |  | 2106.1 |  | 13.6 |  | 2119.7
2003 |  | 1 | 1937.5 |  | -- |  | 11.5 |  | 1949 |  | 6.7 |  | 1955.7
2004 |  | 1 | 2113.5 |  | -- |  | 5.4 |  | 2118.9 |  | 8.5 |  | 2127.4
2005 |  | 1 | 1939 |  | -- |  | -- |  | 1939 |  | 3.2 |  | 1942.2
2006 |  | 1 | 1845.9 |  | -- |  | -- |  | 1845.9 |  | 10.9 |  | 1856.8
2007 |  | 1 | 1776.4 |  | -- |  | -- |  | 1776.4 |  | 5.8 |  | 1782.2
2008 |  | 1 | 2101.9 |  | -- |  | -- |  | 2101.9 |  | 13 |  | 2114.9
2009 |  | 1 | 2358.8 |  | -- |  | -- |  | 2358.8 |  | 11.5 |  | 2370.3
2010 |  | 1 | 2517 |  | -- |  | -- |  | 2517 |  | 6.1 |  | 2523.1
2011 |  | 2 | 3119.9 |  | -- |  | -- |  | 3119.9 |  | 11.3 |  | 3131.2
2012 |  | 2 | 2798.1 |  | -- |  | -- |  | 2798.1 |  | 7.3 |  | 2805.4
2013 |  | 2 | 2714.4 |  | -- |  | -- |  | 2714.4 |  | 9.7 |  | 2724.1
2014 |  | 2 | 3709.1 |  | -- |  | -- |  | 3709.1 |  | 14.9 |  | 3724
2015 |  | 2 | 3304.7 |  | -- |  | -- |  | 3304.7 |  | 16.4 |  | 3321.1
2016 |  | 2 | 2956.9 |  | -- |  | -- |  | 2956.9 |  | 19 |  | 2975.9
2017 |  | 2 | 2677.9 |  | -- |  | 50.4 |  | 2728.3 |  | 16.2 |  | 2744.5
2018 |  | 2 | 2744.9 |  | -- |  | 47.7 |  | 2792.6 |  | 19 |  | 2811.6
2019 |  | 2 | 3343.3 |  | 138.4 |  | 55.4 |  | 3537.1 |  | 26.5 |  | 3563.6
2020 |  | 2 | 2952.3 |  | 825.5 |  | -- |  | 3777.8 |  | 21.4 |  | 3799.2
2021 |  | 1 | 1261.9 |  | 985.2 |  | -- |  | 2247.1 |  | 21.4 |  | 2268.5
2022 |  | -- | 59.9 |  | -- |  | -- |  | 59.9 |  | 6.9 |  | 66.8
2023 |  | -- | 59.1 |  | -- |  | -- |  | 59.1 |  | 5.4 |  | 64.5
2024 |  | -- | 49.3 |  | -- |  | -- |  | 49.3 |  | 2.2 |  | 51.5
2025 |  | -- | 47.2 |  | -- |  | -- |  | 47.2 |  | -- |  | 47.2
2026 |  | -- | 45.4 |  | -- |  | -- |  | 45.4 |  | -- |  | 45.4
2027 |  | -- | 19.2 |  | -- |  | -- |  | 19.2 |  | -- |  | 19.2
Subtotal |  | 33 | 56799.6 |  | 1949.1 |  | 1668.2 |  | 60416.9 |  | 277.1 |  | 60694

## Table 24
The Navy is planning for a class extension and has added Advance Procurement (FY 2019 - FY 2021) and Full Funding (2 ships in FY 2020, 1 ship in FY 2021) accordingly. Funding in the Non End Item Recurring Flyaway column is associated with Advance Procurement for ships beyond the FYDP.
Cost Quantity Information 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 1995 $M
1996 | -- | --
1997 | -- | --
1998 | 1 | 2141.8
1999 | 1 | 2356.4
2000 | -- | --
2001 | 1 | 1910.7
2002 | 1 | 2021.3
2003 | 1 | 1824.4
2004 | 1 | 1813.2
2005 | 1 | 1745.2
2006 | 1 | 1771.4
2007 | 1 | 1836.1
2008 | 1 | 1781.3
2009 | 1 | 1899.5
2010 | 1 | 1773
2011 | 2 | 3355
2012 | 2 | 3155.7
2013 | 2 | 3076.6
2014 | 2 | 3166.7
2015 | 2 | 3033
2016 | 2 | 3044.2
2017 | 2 | 3015.5
2018 | 2 | 3023.6
2019 | 2 | 3701.2
2020 | 2 | 3519.9
2021 | 1 | 1833.9
2022 | -- | --
2023 | -- | --
2024 | -- | --
2025 | -- | --
2026 | -- | --
2027 | -- | --
Subtotal | 33 | 56799.6

## Table 25
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | 12.5 |  | 12.5
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | 44.1 |  | 44.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | 47 |  | 47
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | 39.7 |  | 39.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | 48 |  | 48
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | 13.8 |  | 13.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | 21.7 |  | 21.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | 5.3 |  | 5.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.8 |  | 1.8
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | 14.7 |  | 14.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | 9.3 |  | 9.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | 2 |  | 2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | 9 |  | 9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | 8.3 |  | 8.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | 9.5 |  | 9.5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | 9.7 |  | 9.7
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | 9.8 |  | 9.8
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 306.2 |  | 306.2

## Table 26
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 1995 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | 10.4 |  | 10.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | 35.6 |  | 35.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | 37.2 |  | 37.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | 30.9 |  | 30.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | 36.9 |  | 36.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | 10.4 |  | 10.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | 16.1 |  | 16.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | 3.9 |  | 3.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.3 |  | 1.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | 10.5 |  | 10.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | 6.5 |  | 6.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | 1.4 |  | 1.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | 6.1 |  | 6.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | 5.5 |  | 5.5
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | 6.2 |  | 6.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | 6.2 |  | 6.2
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | 6.1 |  | 6.1
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | 231.2 |  | 231.2

## Table 27
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1995-06-30 | 1995-06-30
Approved Quantity | 14 | 14
Reference | MS II ADM | MS II ADM
Start Year | 1998 | 1998
End Year | 2007 | 2011
The Current Total LRIP Quantity is more than 10% of the total production quantity due to this being a shipbuilding program for which this is standard practice.

## Table 28
Foreign Military Sales
None
Nuclear Costs
$17,940.0 (TY$). These costs are for reactor propulsion plant equipment. These costs are included in the Shipbuilding and Conversion, Navy costs in this report. Department of Energy costs are excluded from this report.

## Table 29
Unit Cost
Unit Cost Report
Item |  | BY 1995 $M | BY 1995 $M |  | % Change
|  | Current UCR Baseline (Sep 2010 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 64353.6 |  |  | 66527.3
Quantity | 30 |  |  | 33
Unit Cost | 2145.12 |  |  | 2015.979 |  |  | -6.02
Average Procurement Unit Cost
Cost | 58933.2 |  |  | 60925.2
Quantity | 30 |  |  | 33
Unit Cost | 1964.44 |  |  | 1846.218 |  |  | -6.02
Item |  | BY 1995 $M | BY 1995 $M |  | % Change
|  | Original UCR Baseline (Jun 1995 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 45633.1 |  |  | 66527.3
Quantity | 30 |  |  | 33
Unit Cost | 1521.103 |  |  | 2015.979 |  | +32.531
Average Procurement Unit Cost
Cost | 42228.1 |  |  | 60925.2
Quantity | 30 |  |  | 33
Unit Cost | 1407.603 |  |  | 1846.218 |  | +31.161
1
Nunn-McCurdy Breach
This program reflects a significant Nunn-McCurdy breach to the original baseline that was first reported in the December 2005 SAR. The supporting breach information and explanations can be found in the UCR section of that SAR.

## Table 30
Unit Cost History
Item |  |  |  |  | Date |  |  |  | BY 1995 $M | [5 empty] | TY $M
[9 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  |  |  | APUC
Original APB |  |  |  | Jun 1995 |  |  |  |  | 1521.103 |  |  |  | 1407.603 |  |  |  | 2369.36 |  |  |  | 2242.227
APB as of January 2006 |  |  |  | May 2005 |  |  |  |  | 2174.943 |  |  |  | 2021.43 |  |  |  | 2749.06 |  |  |  | 2578.85
Revised Original APB |  |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  | May 2005 |  |  |  |  | 2174.943 |  |  |  | 2021.43 |  |  |  | 2749.06 |  |  |  | 2578.85
Current APB |  |  |  | Sep 2010 |  |  |  |  | 2145.12 |  |  |  | 1964.44 |  |  |  | 3106.91 |  |  |  | 2895.203
Prior Annual SAR |  |  |  | Dec 2014 |  |  |  |  | 2004.028 |  |  |  | 1829.784 |  |  |  | 3103.519 |  |  |  | 2897.975
Current Estimate |  |  |  | Dec 2015 |  |  |  |  | 2015.979 |  |  |  | 1846.218 |  |  |  | 3159.439 |  |  |  | 2959.133
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [17 empty] | PAUC Production Estimate
| Econ |  | Qty |  | Sch |  | Eng |  |  | Est |  | Oth |  | Spt |  |  | Total
2369.360 -166.403 0.000 259.820 42.410 564.303 9.333 28.087 737.550 3106.910
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [15 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  | Sch |  | Eng |  |  | Est | Oth |  | Spt |  | Total
3106.910 174.012 -53.056 -50.218 59.545 -71.127 0.000 -6.627 52.529 3159.439

## Table 31
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [15 empty] | APUC Production Estimate
| Econ |  | Qty |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
2242.227 -160.064 0.000 259.820 36.360 479.440 9.333 28.087 652.976 2895.203
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [15 empty] | APUC Current Estimate
| Econ | Qty |  |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
2895.203 174.088 -33.810 -50.218 35.364 -54.867 0.000 -6.627 63.930 2959.133
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  |  |  | SAR Production Estimate |  |  |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  |  | Aug 1994 |  |  |  |  | Aug 1994 |  |  |  |  | Aug 1994
Milestone II |  |  |  | N/A |  |  |  | Jun 1995 |  |  |  |  | Jun 1995 |  |  |  |  | Jun 1995
Milestone III |  |  |  | N/A |  |  |  | Oct 2007 |  |  |  |  | Jul 2010 |  |  |  |  | Sep 2010
IOC |  |  |  | N/A |  |  |  | Oct 2005 |  |  |  |  | Nov 2006 |  |  |  |  | Jun 2006
Total Cost (TY $M) |  |  |  | N/A |  |  |  | 71080.8 |  |  |  |  | 93207.3 |  |  |  |  | 104261.5
Total Quantity |  |  |  | N/A |  |  |  | 30 |  |  |  |  | 30 |  |  |  |  | 33
PAUC |  |  |  | N/A |  |  |  | 2369.36 |  |  |  |  | 3106.91 |  |  |  |  | 3159.439

## Table 32
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
6351.2 86856.1 -- 93207.3
Economic |  | 6.1 |  | 5626.2 |  | -- |  | 5632.3
Quantity |  | -- |  | 4580 |  | -- |  | 4580
Schedule |  | -- |  | -1452.6 |  | -- |  | -1452.6
Engineering |  | 798 |  | -- |  | -- |  | 798
Estimating |  | -577.9 |  | -2646.4 |  | -- |  | -3224.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -228.1 |  | -- |  | -228.1
Subtotal |  | 226.2 |  | 5879.1 |  | -- |  | 6105.3
Current Changes Economic |  | -8.6 |  | 118.7 |  | -- |  | 110.1
Quantity |  | -- |  | 2989.9 |  | -- |  | 2989.9
Schedule |  | -- |  | -204.6 |  | -- |  | -204.6
Engineering |  | -- |  | 1167 |  | -- |  | 1167
Estimating |  | 41.3 |  | 835.8 |  | -- |  | 877.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 9.4 |  | -- |  | 9.4
Subtotal |  | 32.7 |  | 4916.2 |  | -- |  | 4948.9
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 258.9 |  | 10795.3 |  | -- |  | 11054.2
CE - Cost Variance |  | 6610.1 |  | 97651.4 |  | -- |  | 104261.5
CE - Cost & Funding |  | 6610.1 |  | 97651.4 |  | -- |  | 104261.5

## Table 33
Summary BY 1995 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
5420.4 58933.2 -- 64353.6
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 2327.8 |  | -- |  | 2327.8
Schedule |  | -- |  | -747.5 |  | -- |  | -747.5
Engineering |  | 556.6 |  | -- |  | -- |  | 556.6
Estimating |  | -401.2 |  | -1809.2 |  | -- |  | -2210.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -151.2 |  | -- |  | -151.2
Subtotal |  | 155.4 |  | -380.1 |  | -- |  | -224.7
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 1487.4 |  | -- |  | 1487.4
Schedule |  | -- |  | -101.8 |  | -- |  | -101.8
Engineering |  | -- |  | 594.8 |  | -- |  | 594.8
Estimating |  | 26.3 |  | 386.4 |  | -- |  | 412.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 5.3 |  | -- |  | 5.3
Subtotal |  | 26.3 |  | 2372.1 |  | -- |  | 2398.4
Adjustments |  | -- |  | -- |  | -- |  | --
Total Changes |  | 181.7 |  | 1992 |  | -- |  | 2173.7
CE - Cost Variance |  | 5602.1 |  | 60925.2 |  | -- |  | 66527.3
CE - Cost & Funding |  | 5602.1 |  | 60925.2 |  | -- |  | 66527.3
Previous Estimate: December 2014

## Table 34
RDT&E |  |  | $M
Current Change Explanations |  |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -8.6
Congressional adjustment to non-core Research and Development program in FY 2016. (Estimating)
+26.2 +37.5
Revised estimate for VIRGINIA Payload Module (VPM) development program. (Estimating) -9.6 -13.5
Revised estimate for core Hull, Mechanical and Electrical (HM&E) and Combat Systems RDT&E program. (Estimating)
+7.6 +14.5
Adjustment for current and prior escalation. (Estimating) +2.1 +2.8
RDT&E Subtotal +26.3 +32.7
Procurement |  |  | $M
Current Change Explanations |  |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A +118.7
Quantity variance resulting from an increase in the current estimate from 32 to 33 ships. (Subtotal)
Quantity variance resulting from an increase in the current estimate from 32 to 33 ships. (Quantity)
+1544.3 +3104.4
(+1831.5) (+3681.7)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -101.8 |  |  | -204.6
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -185.4 |  |  | -372.7
Additional Quantity variance associated with the 33rd ship to realign previously funded | -344.1 |  |  | -691.8
Advance Procurement. (Quantity)
Revised estimates for Advance Procurement to fund class restructuring. (Estimating) +857.4 +1734.0
Additional funding for Acoustic Superiority program in FY 2019 - FY 2021 to incorporate design changes to VIRGINIA Class Submarines. (Engineering)
Additional funding for the VPM program in FY 2018 - FY 2021 to incorporate the program on Block V and later submarines. (Engineering)
+316.6 +618.0
+278.2 +549.0
Revised estimate due to refinement of requirements. (Estimating) |  | -151.7 |  |  | -289.1
Revised estimate for Technology Insertion program in FY 2019 - FY 2021. (Estimating) |  | -69.6 |  |  | -136.2
Removal of expired funds. (Estimating) |  | -21.8 |  |  | -25.6
Adjustment for current and prior escalation. (Estimating) |  | -42.5 |  |  | -74.6
Adjustment for current and prior escalation. (Support) |  | -0.2 |  |  | 0
Increase in Initial Spares (Other Procurement Navy). (Support) |  | 5.8 |  |  | 9.4
Decrease in Initial Outfitting Spares (Shipbuilding and Conversion, Navy). (Support) |  | -0.3 |  |  | 0
Procurement Subtotal (QR) Quantity Related |  | 2372.1 |  |  | 4916.2

## Table 35
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: SSN 786
Contractor: General Dynamics, EB Corporation
Contractor Location: 75 Eastern Point Road
Groton, CT 06340
Contract Number: N00024-09-C-2104/3
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 22, 2008
Definitization Date: December 22, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1694.1 1825.9 1 1750.7 1888.8 1 1705.4 1707.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to authorized contract change orders.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) |  |  |  | 1.9 |  |  |  | -14.7
Previous Cumulative Variances |  |  |  | 7 |  |  |  | -11.2
Net Change |  |  |  | -5.1 |  |  |  | -3.5
Percent Variance Percent Complete |  |  |  | +0.14% +91.46% |  |  |  | -1.1%
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to final assembly and testing performance leading up to ship delivery in 2016.
The unfavorable net change in the schedule variance is due to attempting to hold an aggressive schedule to deliver ahead of the contract delivery date.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 36
Contract Identification
Appropriation: Procurement
Contract Name: SSN 787
Contractor: General Dynamics, EB Corporation
Contractor Location: 75 Eastern Point Road
Groton, CT 06340
Contract Number: N00024-09-C-2104/4
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 22, 2008
Definitization Date: December 22, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1773.6 1909.2 1 1814.9 1953.7 1 1756.3 1759.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to authorized contract change orders.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) |  |  |  | 75.3 |  |  |  | -69.6
Previous Cumulative Variances |  |  |  | 100.1 |  |  |  | -39.9
Net Change |  |  |  | -24.8 |  |  |  | -29.7
Percent Variance Percent Complete |  |  |  | +5.66% +88.23% |  |  |  | -4.97%
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to assembly performance moving toward Pressure Hull Complete in August 2015.
The unfavorable net change in the schedule variance is due to working toward an aggressive production schedule. The Contract Performance Report (CPR) baseline is set to the aggressive schedule targets - well before the contractual delivery dates, therefore the schedule variances generated are against the aggressive schedules.

## Table 37
Contract Identification
Appropriation: Procurement
Contract Name: SSN 788
Contractor: General Dynamics, EB Corporation
Contractor Location: 75 Eastern Point Road
Groton, CT 06340
Contract Number: N00024-09-C-2104/5
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 22, 2008
Definitization Date: December 22, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1650.0 1777.9 1 1710.4 1844.4 1 1664.6 1672.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to authorized contract change orders.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) |  |  |  | 33.2 |  |  |  | -11.5
Previous Cumulative Variances |  |  |  | 26.5 |  |  |  | -19.7
Net Change |  |  |  | 6.7 |  |  |  | 8.2
Percent Variance Percent Complete |  |  |  | +2.87% +80.77% |  |  |  | -0.98%
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to positive modular fabrication and assembly performance.
The favorable net change in the schedule variance is due to working towards and meeting aggressive module delivery dates.

## Table 38
Contract Identification
Appropriation: Procurement
Contract Name: SSN 789
Contractor: General Dynamics, EB Corporation
Contractor Location: 75 Eastern Point Road
Groton, CT 06340
Contract Number: N00024-09-C-2104/6
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 22, 2008
Definitization Date: December 22, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1688.8 1796.5 1 1715.4 1846.6 1 1663.1 1676.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to authorized contract change orders.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) |  |  |  | 68.5 |  |  |  | -54.3
Previous Cumulative Variances |  |  |  | 60.4 |  |  |  | -32.7
Net Change |  |  |  | 8.1 |  |  |  | -21.6
Percent Variance Percent Complete |  |  |  | +6.26% +75.60% |  |  |  | -4.73%
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to positive labor performance in module fabrication and assembly.
The unfavorable net change in the schedule variance is due to falling short on labor performance in the modular construction process. The Contract Performance Report baseline is set to aggressive schedule targets, well ahead of the contract delivery date. Therefore the schedule variance generated is against the aggressive schedule.

## Table 39
Contract Identification
Appropriation: Procurement
Contract Name: SSN 790
Contractor: General Dynamics, EB Corporation
Contractor Location: 75 Eastern Point Road
Groton, CT 06340
Contract Number: N00024-09-C-2104/7
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 22, 2008
Definitization Date: December 22, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1621.3 1738.5 1 1743.6 1879.1 1 1697.4 1699.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to authorized contract change orders.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) |  |  |  | 40.8 |  |  |  | -32.5
Previous Cumulative Variances |  |  |  | -- |  |  |  | --
Net Change |  |  |  | 40.8 |  |  |  | -32.5
Percent Variance Percent Complete |  |  |  | +4.26% +65.73% |  |  |  | -3.28%
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to positive labor performance on module fabrication and assembly.
The unfavorable cumulative schedule variance is due to falling short on labor performance in the modular construction process.
Notes
This is the first time this contract is being reported.

## Table 40
Contract Identification
Appropriation: Procurement
Contract Name: SSN 791
Contractor: General Dynamics, EB Corporation
Contractor Location: 75 Eastern Point Road
Groton, CT 06340
Contract Number: N00024-09-C-2104/8
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 22, 2008
Definitization Date: December 22, 2008
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1657.1 1776.9 1 1753.6 1887.1 1 1698.8 1711.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to authorized contract change orders.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) |  |  |  | 84.2 |  |  |  | -25.8
Previous Cumulative Variances |  |  |  | -- |  |  |  | --
Net Change |  |  |  | 84.2 |  |  |  | -25.8
Percent Variance Percent Complete |  |  |  | +9.39% +60.82% |  |  |  | -2.8%
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to positive labor performance on module fabrication and assembly.
The unfavorable cumulative schedule variance is due to falling short on labor performance in the modular construction process.
Notes
This is the first time this contract is being reported.

## Table 41
Contract Identification
Appropriation: RDT&E
Contract Name: Lead Yard Services
Contractor: General Dynamics, EB Corporation
Contractor Location: 75 Eastern Point Road
Groton, CT 06340
Contract Number: N00024-10-C-2118
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: July 02, 2010
Definitization Date: July 02, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
171.9 N/A N/A 1044.7 N/A N/A 1044.7 1044.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to tasking added to this incrementally funded contract.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (CPFF) contract.
Notes
The Lead Yard Services contract provides design studies, engineering, material and logistics support and research and development activities on the baseline VIRGINIA design. Cost and schedule variances are not reported for this contract because this service contract is Level Of Effort for which EVM was not deemed the most effective way to track performance.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 42
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 12 | 12 | 33 | 36.36%
Total Program Quantity Delivered | 12 | 12 | 33 | 36.36%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
104261.5
53475
51.29%
36
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
25
69.44%
73292.1
70.3%
The above data is current as of February 26, 2016.
The 12th ship of the VIRGINIA Class, USS JOHN WARNER (SSN 785), was delivered June 25, 2015.

## Table 43
Operating and Support Cost
Cost Estimate Details
Date of Estimate: June 01, 2010
Source of Estimate: SCP
Quantity to Sustain: 30
Unit of Measure: Ship
Service Life per Unit: 33.00 Years
Fiscal Years in Service: FY 2004 - FY 2058
The source of this data is the VIRGINIA Class Milestone III (MSIII) Program Life Cycle Cost Estimate dated June 2010, which uses the CAPE six element cost classification system. The analysis includes description of input data and detailed Cost Element Structure reporting in the format recommended by the OSD CAPE.
Naval Visibility and Management of Operating and Support Cost (VAMOSC) data for LOS ANGELES Class and VIRGINIA Class actuals were used to construct the estimate. The estimate includes costs for Unit Level Manpower, Unit Operations, Maintenance, Sustaining Support, Continuing System Improvements, and Indirect Support. Unit Level Manpower was estimated based on the crew description contained in the Manning Estimate Report (15 officers, 120 enlisted), and the direct personnel costs using VIRGINIA Class rates factored for VIRGINIA Class crew size. Unit Operations was based on historical LOS ANGELES Class data and factored by power, weight, and crew size.
Maintenance was estimated based on historical LOS ANGELES Class maintenance costs factored for the VIRGINIA Class based on weight. Public and private shipyard data was used, as well as the maintenance schedule provided in the CARD, Rev E dated May 2010, to appropriately phase maintenance costs over the service life of the submarines.
Sustaining Support was estimated based on historical LOS ANGELES Class data factored by weight or crew size, depending on the individual element. Continuing System Improvements were estimated based on historical LOS ANGELES Class data factored by weight. The Software Maintenance portion was based on the analysis of DDG 51 cost per line of code and factored by the total Source Lines of Code count contained in the CARD. Indirect Support was based on historical infrastructure costs from U.S. Naval Submarine Bases, as well as historical personnel costs from LOS ANGELES Class which were factored for the VIRGINIA Class crew size.
The difference between the sustainment quantity (30) and the acquisition quantity (33) reflected in other sections of this report is due to a class extension currently being planned by the Navy.
Sustainment Strategy
The baseline sustainment strategy is structured to achieve 14 deployments during the 33 year design life for each of the total force of 30 VIRGINIA Class submarines. The first deployment occurs after a Post Shakedown Availability (PSA) conducted at the private industry construction yard. The deployment rate is achieved through maintaining material readiness using maintenance periods including three Extended Drydocking Selected Restricted Availabilities (EDSRAs) and one Depot Maintenance Period (DMP) scheduled and planned according to the required maintenance periods for major equipments and systems. The EDRSAs and DMP are expected to be performed at Navy depot maintenance facilities such as the Naval shipyards. Additional routine maintenance and repair are conducted throughout the submarine’s life cycle at the homeport Navy intermediate maintenance facility.
Changes to the equipment and system design are considered and implemented on a case by case basis which may increase maintenance periodicities and support an increase to 15 deployments during the life cycle for later submarines of the class.
Antecedent Information

## Table 44
Assembly of an accurate compilation O&S cost estimate for the SSN 688 Class using actual cost data going back to 1976 when USS LOS ANGELES was commissioned and then projecting those costs out to Calendar Year 2029 is also problematic based on the availability and detail of the historic data. VIRGINIA Class O&S comparisons with the legacy class are hampered by changes in required attack submarine force size where the LOS ANGELES Class, at one time, had 62 submarines compared to the planned class size of 30 VIRGINIA Class submarines.
The source of antecedent data is VAMOSC data for LOS ANGELES Class submarines for the years 1984-2008, however, this data must be adjusted due to significant differences between the two classes, to achieve a comparable estimate. The LOS ANGELES Class was comprised of 62 ships with major design changes in blocks of ships that had an original planned life of 30 years. Some of these 62 ships were retired at mid-life and, therefore, did not incur normal life of ship maintenance and operating costs.
Annual O&S Costs BY1995 $M
Cost Element |  | SSN 774 Average Annual Cost Per Ship |  |  |  | LOS ANGELES CLASS (Antecedent) Average Annual Cost Per Ship
Unit-Level Manpower |  | 8.98 |  |  |  | 5.45
Unit Operations |  | 0.74 |  |  |  | 0.7
Maintenance |  | 13.98 |  |  |  | 15.03
Sustaining Support |  | 0.96 |  |  |  | 0.99
Continuing System Improvements |  | 6.37 |  |  |  | 4.24
Indirect Support |  | 4.37 |  |  |  | 4.11
Other |  | 0 |  |  |  | 0
Total |  | 35.4 |  |  |  | 30.52
There are several factors contributing to an apparent anomaly between VIRGINIA CLASS and LOS ANGELES Class (SSN 688) per ship Unit Level Manpower costs. The costs for SSN 688 are lower than SSN 774 despite a larger crew size for SSN 688 due to the source and timing of the data. SSN 688 costs are extracted from VAMOSC using class average data 1984 - 2008. Manpower costs for the first several years of the data were approximately 65% of the most recent costs for the SSN 688 Class indicating real growth in pay and allowances (i.e., above inflation) over the period. The overall average, however, is significantly influenced by the lower initial costs. Further, 688 VAMOSC data reflect the average annual cost of ships in the fleet. VIRGINIA estimates were built using a ramp up/ramp down methodology and reflect the total annual manpower costs for the program from assignment of the first pre-commissioning crew of the lead ship through decommissioning of the last ship.
The total O&S Cost referenced below for the SSN 688 Class was derived using the average annual cost per ship, 62 ships in the class and an expected service life of 33 years. The 33-year service life is used for comparative
purposes with the SSN 774 Class as SSN 688 ships were originally designed for 30 years and subsequently increased to 33 years. The O&S data will be updated in the next SAR.
Item | Total O&S Cost $M
| SSN 774 | [5 empty] | LOS ANGELES CLASS (Antecedent)
| Current Production APB Objective/Threshold |  |  | Current Estimate
Base Year | 36216.6 |  | 39838.3 |  | 35038.7 |  | 62443.9
Then Year | 98758.7 |  | N/A |  | 95627.9 |  | N/A
Equation to Translate Annual Cost to Total Cost

## Table 45
The average annual cost per ship is derived by dividing total O&S costs by 30 ships and service life of 33 years.
O&S Cost Variance
Category | BY 1995 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
35038.7
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 0.0
Current Estimate 35038.7
Disposal Estimate Details
Date of Estimate: June 01, 2010
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 1995 $M): Total costs for disposal of all Ship are 1177.9
Total program disposal costs are estimated to be $3,130.8M TY.