## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-178
Trident II (D-5) Sea-Launched Ballistic Missile UGM 133A (Trident II Missile)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 12
Cost and Funding 14
Low Rate Initial Production 28
Foreign Military Sales 29
Nuclear Costs 29
Unit Cost 30
Cost Variance 33
Contracts 36
Deliveries and Expenditures 48
Operating and Support Cost 49

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Trident II (D-5) Sea-Launched Ballistic Missile UGM 133A (Trident II Missile)
DoD Component
Navy
Responsible Office
VADM Terry Benedict Strategic Systems Programs 1250-10th Street, SE
Suite 3600; Washington Navy Yard Washington, DC 20374-5127
SP00@SSP.NAVY.MIL
Phone: | 202-433-7001
Fax: | 202-433-5326
DSN Phone: | 288-7001
DSN Fax: | 288-5326
Date Assigned: | May 7, 2010
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated July 15, 1987
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated September 10, 2011

## Table 6
Mission and Description
The TRIDENT II (D5) Sea-Launched Ballistic Missile UGM 133A (TRIDENT II (D5) missile) developed an improved Submarine Launched Ballistic Missile with greater accuracy and payload capability at equivalent ranges as compared to the TRIDENT I (C4) system. TRIDENT II (D5) enhances United States (U.S.) strategic deterrence by providing a survivable sea- based system capable of engaging the full spectrum of potential targets. It enhances the U.S. position in strategic arms negotiation by providing a weapon system with performance and payload flexibility that accommodates various treaty initiatives. The TRIDENT II (D5) missile's increased payload allows the deterrent mission to be achieved with fewer submarines.

## Table 7
Executive Summary
On November 2, 2015, SSP completed a Demonstration and Shakedown Operation flight operation with a fully configured D5 Life Extension (LE) missile involving all of the LE missile electronics packages and the Guidance LE subsystem. This flight test was a critical milestone as D5 LE remains on track for initial fleet introduction (IFI) in FY 2017. The operation was the first flight test for two fully configured D5 LE missiles with all LE missiles electronics packages and the Guidance LE subsystem.
In the area of rocket motors and post boost control system gas generators, the TRIDENT II (D5) missile program has maintained the solid rocket motor unit cost from FY 2014 PB, however, the Navy is actively engaged with Lockheed Martin and Orbital ATK to aggressively lower their respective overheads as the industrial base shrinks. The Navy is cautiously watching the industrial base as the decreasing demand is expected to continue and will accelerate downward as both the Air Force and the National Aeronautics and Space Administration (NASA) reduce their procurements,increasing the risk of future unit costs. NASA is expected to make a decision whether to switch from solid to liquid propulsion systems for the next generation Space Launch Vehicles in the coming years. If NASA were to decide upon the liquid propulsion options, costs could significantly increase for the TRIDENT II (D5) missile. The current budget maintains buying 12 rocket motor sets per year through FY 2017 and increases to 14 sets in FY 2018 in order to address age out concerns. Due to the high rate of TRIDENT II (D5) missile production in the early years of the program, a significant portion of the inventory will age out in the near term driving the quantities to increase in FY 2018.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
This schedule breach was previously reported in the December 2014 SAR.
Assistant Secretary of the Navy (Research, Development and Acquisition (RDA)) agreed at the November 2012 Program Executive Office Quarterly Review that no Program Deviation Report was required by the Program Manager as a result of the delay of Demonstration and Shakedown Operation-24.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
1 APB Breach
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone I (Initiate Concept Definition) | Oct 1977 | Oct 1977 | Apr 1978 | Oct 1977
Commence Advanced Dev Phase | Oct 1980 | Oct 1980 | Apr 1981 | Oct 1980
Milestone II (Commence FSD) | Oct 1983 | Oct 1983 | Apr 1984 | Oct 1983
First Development Flight Test | Jan 1987 | Jan 1987 | Jul 1987 | Jan 1987
Milestone III (Production Approval)/ Award Initial Missile Production | Apr 1987 | Apr 1987 | Oct 1987 | Apr 1987
IOC (may be less than full msl outload) | Dec 1989 | Dec 1989 | Jun 1990 | Mar 1990
D5 LE System CDR | N/A | Feb 2011 | Aug 2011 | Jan 2011
First Guidance Only Flight Test (DASO-23) | N/A | Feb 2012 | Aug 2012 | Feb 2012
Second Guidance Only Flight Test (DASO-24) | N/A | Aug 2012 | Feb 2013 | Apr 20131
First Missile Electronics Flight Test (PTM-1/DASO-25) | N/A | Sep 2013 | Mar 2014 | Apr 2013
IFI for FCEA/Interlocks | N/A | Apr 2017 | Oct 2017 | Apr 2017
EHW#2 at Bangor IOC | N/A | Oct 2017 | Apr 2018 | Oct 2017
First Operational Flight Test (CET) | N/A | Oct 2018 | Apr 2019 | Oct 2018

## Table 10
Change Explanations
None
Acronyms and Abbreviations
CDR - Critical Design Review
CET - Commander Evaluation Test D5 LE - D5 Life Extension
DASO - Demonstration and Shakedown Operation Dev - Development
EHW - Explosive Handling Wharf
FCEA - Flight Control Electronics Assembly FSD - Full Scale Development
IFI - Initial Fleet Introduction MSL - missile
PTM - Proofing Test Missile

## Table 11
Performance
Classified Performance information is provided in the classified annex to this submission.

## Table 12
Track to Budget
RDT&E
Appn |  |  |  | BA | PE
Navy 1319 07 0101221N
Project | Name
0951 JOINT WARHEAD FUZE SUSTAINMENT PROGRAM
Navy 1319 04 0603371N
|  | Project |  |  | Name
|  | 951 |  |  | TRIDENT II/TRIDENT II
Navy |  | 1319 | 4 |  | 0604327N
|  | Project |  |  | Name
|  | 9611 |  |  | HARD AND DEEPLY BURIED TARGET DEFEAT SYSTEM/Advanced Conventional Strike Capability Demonstration
Navy |  | 1319 | 4 |  | 0604363N
|  | Project |  |  | Name
(Sunk)
(Sunk)
0951 TRIDENT II/TRIDENT II (Sunk)
Procurement
Appn |  |  |  | BA | PE
Navy 1507 01 0101228N
Line Item | Name
1150 TRIDENT II (D-5) Missile (Sunk)
1250 TRIDENT MODS (Shared)
Notes
The funding profile for Proc (Weapons Proc, Navy (WPN)) does not match that found in the FY 2017 PB controls for WPN after FY 2011. Beginning in FY 2012, WPN funding is shared between Acquisition and O&S costs in the SAR and,
hence, the O&S costs are not reflected in the TRIDENT II (D5) missile acquisition.
MILCON
Appn |  |  |  | BA | PE
Navy 1205 01 0202576N
Project | Name
Facilities Restoration and MOD- Grounds (Shared) (Sunk)
Navy 1205 01 0203176N
Project | Name
Facilities Restoration and MOD- Fleet Ops (Shared) (Sunk)
Navy 1205 01 0212176N
Project | Name

## Table 13
68436990 Fleet Ballistic Missile
Navy 1205 01 0212576N
Project | Name
Facilities New Footprint (Shared) (Sunk)
Navy 1205 01 0703676N
|  | Project | Name
|  |  | Facility Restoration and MOD - Maint and Prod | (Shared) | (Sunk)
Navy |  | 1205 01 | 0712876N
|  | Project | Name
|  | 60495822 | Facilities - New Footprint- Main and Production
Navy |  | 1205 01 | 0805976N
|  | Project | Name
|  |  | Facility Restoration and MOD - Training | (Shared) | (Sunk)

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 1983 $M | [6 empty] | BY 1983 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 8434.9 |  |  | 8783.9 | 9662.3 |  |  | 8806.3 |  | 9453.2 |  |  | 10126 |  | 10184.7
Procurement |  | 17588.5 |  |  | 18406.7 | 20247.4 |  |  | 18261.7 |  | 25396.9 |  |  | 30643.5 |  | 30547.3
Flyaway |  | -- |  |  | -- | -- |  |  | 14077.6 |  | -- |  |  | -- |  | 23668.7
Recurring |  | -- |  |  | -- | -- |  |  | 14077.6 |  | -- |  |  | -- |  | 23668.7
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 4184.1 |  | -- |  |  | -- |  | 6878.6
Other Support |  | -- |  |  | -- | -- |  |  | 4160.5 |  | -- |  |  | -- |  | 6843.2
Initial Spares |  | -- |  |  | -- | -- |  |  | 23.6 |  | -- |  |  | -- |  | 35.4
MILCON |  | 532.9 |  |  | 757.6 | 833.4 |  |  | 636.3 |  | 668.4 |  |  | 1220.3 |  | 991.4
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 26556.3 |  |  | 27948.2 | N/A |  |  | 27704.3 |  | 35518.5 |  |  | 41989.8 |  | 41723.4
Confidence Level
Confidence Level of cost estimate for current APB: 50%
TRIDENT II D-5 is currently in the process of reconciling the program office estimate with our Internal Independent Cost Estimate (IICE). Costs are being compared at the point estimate which is approximately 17 to 18% and are making a comparison at the 50% estimate. The plan is to have this reconciliation completed in the near future.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 30 |  |  |  | 28 |  |  |  |  | 28
Procurement |  |  | 815 |  |  |  | 533 |  |  |  |  | 533
Total |  |  | 845 |  |  |  | 561 |  |  |  |  | 561

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 9729.6 | 84.8 |  |  | 111.9 | 108.8 | 63.6 |  | 65.2 |  | 20.8 |  | 0 |  | 10184.7
Procurement | 26214.6 | 603.1 |  |  | 614.1 | 615.7 | 658.4 |  | 704 |  | 616.1 |  | 521.3 |  | 30547.3
MILCON | 926.1 | 0 |  |  | 0 | 0 | 65.3 |  | 0 |  | 0 |  | 0 |  | 991.4
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 36870.3 | 687.9 |  |  | 726 | 724.5 | 787.3 |  | 769.2 |  | 636.9 |  | 521.3 |  | 41723.4
PB 2016 Total | 36868.7 | 708.5 |  |  | 769.5 | 739.8 | 804.1 |  | 784.4 |  | 462 |  | 521.3 |  | 41658.3
Delta | 1.6 | -20.6 |  |  | -43.5 | -15.3 | -16.8 |  | -15.2 |  | 174.9 |  | 0 |  | 65.1
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 28 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 28
Production | 0 |  | 533 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 533
PB 2017 Total | 28 |  | 533 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 561
PB 2016 Total | 28 |  | 533 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 561
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1978 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
1979 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
1980 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.6
1981 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 96.7
1982 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 198.4
1983 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 351
1984 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1447.3
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1982.6
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1942.3
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1565.3
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1029.7
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 546.5
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 169.5
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.4
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.5

## Table 17
2013 | -- | -- | -- | -- | -- | -- | 56.2
2014 | -- | -- | -- | -- | -- | -- | 83.8
2015 | -- | -- | -- | -- | -- | -- | 81.7
2016 | -- | -- | -- | -- | -- | -- | 84.8
2017 | -- | -- | -- | -- | -- | -- | 111.9
2018 | -- | -- | -- | -- | -- | -- | 108.8
2019 | -- | -- | -- | -- | -- | -- | 63.6
2020 | -- | -- | -- | -- | -- | -- | 65.2
2021 | -- | -- | -- | -- | -- | -- | 20.8
Subtotal | 28 | -- | -- | -- | -- | -- | 10184.7

## Table 18
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 1983 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1978 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.2
1979 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.5
1980 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.1
1981 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 104.2
1982 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 203.1
1983 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 343.9
1984 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1368.5
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1818.1
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1731.2
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1355.1
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 862.6
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 439.3
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 130.9
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.1
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.9
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.9

## Table 19
2018 | -- | -- | -- | -- | -- | -- | 50.4
2019 | -- | -- | -- | -- | -- | -- | 28.9
2020 | -- | -- | -- | -- | -- | -- | 29
2021 | -- | -- | -- | -- | -- | -- | 9.1
Subtotal | 28 | -- | -- | -- | -- | -- | 8806.3

## Table 20
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | 160.8 |  | 160.8
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | 508.4 |  | 508.4
1987 |  | 21 | 1051.6 |  | -- |  | -- |  | 1051.6 |  | 295.2 |  | 1346.8
1988 |  | 66 | 1710 |  | -- |  | -- |  | 1710 |  | 323.5 |  | 2033.5
1989 |  | 66 | 1586.8 |  | -- |  | -- |  | 1586.8 |  | 252.2 |  | 1839
1990 |  | 41 | 1114.2 |  | -- |  | -- |  | 1114.2 |  | 286.4 |  | 1400.6
1991 |  | 52 | 1242.9 |  | -- |  | -- |  | 1242.9 |  | 269.5 |  | 1512.4
1992 |  | 28 | 817.6 |  | -- |  | -- |  | 817.6 |  | 279.3 |  | 1096.9
1993 |  | 21 | 719.6 |  | -- |  | -- |  | 719.6 |  | 258.5 |  | 978.1
1994 |  | 24 | 989.2 |  | -- |  | -- |  | 989.2 |  | 111.5 |  | 1100.7
1995 |  | 18 | 606.5 |  | -- |  | -- |  | 606.5 |  | 58.9 |  | 665.4
1996 |  | 6 | 186.5 |  | -- |  | -- |  | 186.5 |  | 324.2 |  | 510.7
1997 |  | 7 | 209.1 |  | -- |  | -- |  | 209.1 |  | 108.1 |  | 317.2
1998 |  | 5 | 150.8 |  | -- |  | -- |  | 150.8 |  | 117.7 |  | 268.5
1999 |  | 5 | 189.3 |  | -- |  | -- |  | 189.3 |  | 126.4 |  | 315.7
2000 |  | 12 | 362.7 |  | -- |  | -- |  | 362.7 |  | 122.7 |  | 485.4
2001 |  | 12 | 355.2 |  | -- |  | -- |  | 355.2 |  | 81.9 |  | 437.1
2002 |  | 12 | 378.8 |  | -- |  | -- |  | 378.8 |  | 154 |  | 532.8
2003 |  | 12 | 553.5 |  | -- |  | -- |  | 553.5 |  | 19.5 |  | 573
2004 |  | 12 | 640 |  | -- |  | -- |  | 640 |  | 0.9 |  | 640.9
2005 |  | 5 | 612.9 |  | -- |  | -- |  | 612.9 |  | 102.4 |  | 715.3
2006 |  | -- | 708.9 |  | -- |  | -- |  | 708.9 |  | 196.3 |  | 905.2
2007 |  | -- | 766.7 |  | -- |  | -- |  | 766.7 |  | 147.4 |  | 914.1
2008 |  | 12 | 862.6 |  | -- |  | -- |  | 862.6 |  | 179.2 |  | 1041.8
2009 |  | 24 | 889.2 |  | -- |  | -- |  | 889.2 |  | 178.9 |  | 1068.1
2010 |  | 24 | 867.8 |  | -- |  | -- |  | 867.8 |  | 184.4 |  | 1052.2
2011 |  | 24 | 935.7 |  | -- |  | -- |  | 935.7 |  | 177.5 |  | 1113.2
2012 |  | 24 | 624.7 |  | -- |  | -- |  | 624.7 |  | 131.8 |  | 756.5
2013 |  | -- | 420.7 |  | -- |  | -- |  | 420.7 |  | 180.7 |  | 601.4
2014 |  | -- | 463.1 |  | -- |  | -- |  | 463.1 |  | 202.5 |  | 665.6
2015 |  | -- | 454 |  | -- |  | -- |  | 454 |  | 203.3 |  | 657.3
2016 |  | -- | 396.9 |  | -- |  | -- |  | 396.9 |  | 206.2 |  | 603.1
2017 |  | -- | 403.9 |  | -- |  | -- |  | 403.9 |  | 210.2 |  | 614.1
2018 |  | -- | 422.1 |  | -- |  | -- |  | 422.1 |  | 193.6 |  | 615.7
2019 |  | -- | 461.8 |  | -- |  | -- |  | 461.8 |  | 196.6 |  | 658.4
2020 |  | -- | 508.2 |  | -- |  | -- |  | 508.2 |  | 195.8 |  | 704
2021 |  | -- | 483.9 |  | -- |  | -- |  | 483.9 |  | 132.2 |  | 616.1
2022 |  | -- | 333.6 |  | -- |  | -- |  | 333.6 |  | -- |  | 333.6
2023 |  | -- | 150 |  | -- |  | -- |  | 150 |  | -- |  | 150
2024 |  | -- | 37.7 |  | -- |  | -- |  | 37.7 |  | -- |  | 37.7

## Table 21
Subtotal 533 23668.7 -- -- 23668.7 6878.6 30547.3

## Table 22
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 1983 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | 137.7 |  | 137.7
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | 420.7 |  | 420.7
1987 |  | 21 | 839.8 |  | -- |  | -- |  | 839.8 |  | 235.8 |  | 1075.6
1988 |  | 66 | 1314.1 |  | -- |  | -- |  | 1314.1 |  | 248.6 |  | 1562.7
1989 |  | 66 | 1173.3 |  | -- |  | -- |  | 1173.3 |  | 186.5 |  | 1359.8
1990 |  | 41 | 796.4 |  | -- |  | -- |  | 796.4 |  | 204.7 |  | 1001.1
1991 |  | 52 | 866.5 |  | -- |  | -- |  | 866.5 |  | 187.8 |  | 1054.3
1992 |  | 28 | 555.9 |  | -- |  | -- |  | 555.9 |  | 189.9 |  | 745.8
1993 |  | 21 | 480.5 |  | -- |  | -- |  | 480.5 |  | 172.6 |  | 653.1
1994 |  | 24 | 647.8 |  | -- |  | -- |  | 647.8 |  | 73 |  | 720.8
1995 |  | 18 | 390.9 |  | -- |  | -- |  | 390.9 |  | 38 |  | 428.9
1996 |  | 6 | 118.7 |  | -- |  | -- |  | 118.7 |  | 206.5 |  | 325.2
1997 |  | 7 | 131.8 |  | -- |  | -- |  | 131.8 |  | 68.2 |  | 200
1998 |  | 5 | 94 |  | -- |  | -- |  | 94 |  | 73.3 |  | 167.3
1999 |  | 5 | 116.5 |  | -- |  | -- |  | 116.5 |  | 77.8 |  | 194.3
2000 |  | 12 | 220.2 |  | -- |  | -- |  | 220.2 |  | 74.6 |  | 294.8
2001 |  | 12 | 213 |  | -- |  | -- |  | 213 |  | 49.1 |  | 262.1
2002 |  | 12 | 224.7 |  | -- |  | -- |  | 224.7 |  | 91.4 |  | 316.1
2003 |  | 12 | 321.8 |  | -- |  | -- |  | 321.8 |  | 11.3 |  | 333.1
2004 |  | 12 | 361.3 |  | -- |  | -- |  | 361.3 |  | 0.5 |  | 361.8
2005 |  | 5 | 336.7 |  | -- |  | -- |  | 336.7 |  | 56.3 |  | 393
2006 |  | -- | 379.9 |  | -- |  | -- |  | 379.9 |  | 105.2 |  | 485.1
2007 |  | -- | 402.2 |  | -- |  | -- |  | 402.2 |  | 77.3 |  | 479.5
2008 |  | 12 | 445.4 |  | -- |  | -- |  | 445.4 |  | 92.5 |  | 537.9
2009 |  | 24 | 452.6 |  | -- |  | -- |  | 452.6 |  | 91.1 |  | 543.7
2010 |  | 24 | 434.3 |  | -- |  | -- |  | 434.3 |  | 92.3 |  | 526.6
2011 |  | 24 | 459.5 |  | -- |  | -- |  | 459.5 |  | 87.2 |  | 546.7
2012 |  | 24 | 302.2 |  | -- |  | -- |  | 302.2 |  | 63.8 |  | 366
2013 |  | -- | 200.7 |  | -- |  | -- |  | 200.7 |  | 86.2 |  | 286.9
2014 |  | -- | 217.9 |  | -- |  | -- |  | 217.9 |  | 95.3 |  | 313.2
2015 |  | -- | 210.4 |  | -- |  | -- |  | 210.4 |  | 94.3 |  | 304.7
2016 |  | -- | 180.8 |  | -- |  | -- |  | 180.8 |  | 94 |  | 274.8
2017 |  | -- | 180.6 |  | -- |  | -- |  | 180.6 |  | 94 |  | 274.6
2018 |  | -- | 185.1 |  | -- |  | -- |  | 185.1 |  | 84.9 |  | 270
2019 |  | -- | 198.5 |  | -- |  | -- |  | 198.5 |  | 84.6 |  | 283.1
2020 |  | -- | 214.2 |  | -- |  | -- |  | 214.2 |  | 82.5 |  | 296.7
2021 |  | -- | 200 |  | -- |  | -- |  | 200 |  | 54.6 |  | 254.6
2022 |  | -- | 135.1 |  | -- |  | -- |  | 135.1 |  | -- |  | 135.1
2023 |  | -- | 59.6 |  | -- |  | -- |  | 59.6 |  | -- |  | 59.6
2024 |  | -- | 14.7 |  | -- |  | -- |  | 14.7 |  | -- |  | 14.7

## Table 23
Subtotal 533 14077.6 -- -- 14077.6 4184.1 18261.7

## Table 24
Cost Quantity Information 1507 ¦ Procurement ¦ Weapons Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 1983 $M
1985 | -- | --
1986 | -- | --
1987 | 21 | 737.5
1988 | 66 | 1068.2
1989 | 66 | 941.3
1990 | 41 | 796.4
1991 | 52 | 901.9
1992 | 28 | 541.8
1993 | 21 | 480.5
1994 | 24 | 647.8
1995 | 18 | 390.9
1996 | 6 | 118.7
1997 | 7 | 131.9
1998 | 5 | 94
1999 | 5 | 116.5
2000 | 12 | 220.4
2001 | 12 | 213.1
2002 | 12 | 224.7
2003 | 12 | 321.8
2004 | 12 | 779.6
2005 | 5 | 827.3
2006 | -- | --
2007 | -- | --
2008 | 12 | 628.9
2009 | 24 | 1015.2
2010 | 24 | 1163.1
2011 | 24 | 997.5
2012 | 24 | 718.6
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
2022 | -- | --
2023 | -- | --

## Table 25
2024 | -- | --
Subtotal | 533 | 14077.6

## Table 26
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
1984 79.3
1985 82.4
1986 126.3
1987 21.0
1988 18.1
1989 15.4
1990 7.6
1991 70.5
1992 --
1993 --
1994 --
1995 --
1996 --
1997 --
1998 --
1999 --
2000 5.7
2001 1.1
2002 4.2
2003 7.2
2004 --
2005 --
2006 2.8
2007 --
2008 28.7
2009 --
2010 --
2011 --
2012 78.0
2013 264.4
2014 24.9
2015 88.5
2016 --
2017 --
2018 --
2019 65.3
Subtotal 991.4

## Table 27
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 1983 $M
Total Program
1984 72.8
1985 73.4
1986 109.3
1987 17.6
1988 14.6
1989 12.0
1990 5.7
1991 51.3
1992 --
1993 --
1994 --
1995 --
1996 --
1997 --
1998 --
1999 --
2000 3.6
2001 0.7
2002 2.6
2003 4.3
2004 --
2005 --
2006 1.6
2007 --
2008 15.4
2009 --
2010 --
2011 --
2012 38.8
2013 129.7
2014 12.0
2015 42.1
2016 --
2017 --
2018 --
2019 28.8
Subtotal 636.3

## Table 28
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1983-10-30 | 1983-10-30
Approved Quantity | 21 | 21
Reference | Milestone II ADM | Milestone II ADM
Start Year | 1983 | 1983
End Year | 1987 | 1987

## Table 29
Foreign Military Sales
None
Nuclear Costs
Classified Nuclear Cost information is provided in the classified annex to this submission.

## Table 30
Unit Cost
Unit Cost Report
Item |  | BY 1983 $M | BY 1983 $M |  | % Change
|  | Current UCR Baseline (Sep 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 27948.2 |  |  | 27704.3
Quantity | 561 |  |  | 561
Unit Cost | 49.819 |  |  | 49.384 |  | -0.87
Average Procurement Unit Cost
Cost | 18406.7 |  |  | 18261.7
Quantity | 533 |  |  | 533
Unit Cost | 34.534 |  |  | 34.262 |  | -0.79
Item |  | BY 1983 $M | BY 1983 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Jun 2002 APB)
Program Acquisition Unit Cost
Cost | 25943.7 |  |  | 27704.3
Quantity | 568 |  |  | 561
Unit Cost | 45.676 |  |  | 49.384 |  | 8.12
Average Procurement Unit Cost
Cost | 17155.2 |  |  | 18261.7
Quantity | 540 |  |  | 533
Unit Cost | 31.769 |  |  | 34.262 |  | 7.85

## Table 31
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 1983 $M |  |  |  |  | TY $M
[8 empty] | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Jul 1987 |  |  |  |  | 31.428 |  |  | 21.581 |  |  | 42.034 |  |  | 31.162
APB as of January 2006 |  |  | Jun 2002 |  |  |  |  | 45.676 |  |  | 31.769 |  |  | 66.098 |  |  | 51.266
Revised Original APB |  |  | Jun 2002 |  |  |  |  | 45.676 |  |  | 31.769 |  |  | 66.098 |  |  | 51.266
Prior APB |  |  | Jun 2002 |  |  |  |  | 45.676 |  |  | 31.769 |  |  | 66.098 |  |  | 51.266
Current APB |  |  | Sep 2011 |  |  |  |  | 49.819 |  |  | 34.534 |  |  | 74.848 |  |  | 57.492
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 49.303 |  |  | 34.166 |  |  | 74.257 |  |  | 57.156
Current Estimate |  |  | Dec 2015 |  |  |  |  | 49.384 |  |  | 34.262 |  |  | 74.373 |  |  | 57.312
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
42.034 -0.760 9.301 3.381 0.180 15.663 0.000 4.574 32.339 74.373
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  | Total
31.162 -0.733 3.971 3.215 0.175 14.708 0.000 4.814 26.150 57.312

## Table 32
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone I | N/A | Oct 1977 | Oct 1977 | Oct 1977
Milestone II | N/A | Oct 1983 | Oct 1983 | Oct 1983
Milestone III | N/A | Mar 1987 | Apr 1987 | Apr 1987
IOC | N/A | Dec 1989 | Dec 1989 | Mar 1990
Total Cost (TY $M) | N/A | 37645.1 | 35518.5 | 41723.4
Total Quantity | N/A | 740 | 845 | 561
PAUC | N/A | 50.872 | 42.034 | 74.373

## Table 33
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
9453.2 25396.9 668.4 35518.5
Economic |  | -34.6 |  | -347.3 |  | 4.5 |  | -377.4
Quantity |  | -48 |  | -6671.1 |  | -- |  | -6719.1
Schedule |  | 75.3 |  | 1713.6 |  | 108 |  | 1896.9
Engineering |  | -0.8 |  | 93.1 |  | 8.5 |  | 100.8
Estimating |  | 761.4 |  | 7681.9 |  | 198.3 |  | 8641.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 2597 |  | -- |  | 2597
Subtotal |  | 753.3 |  | 5067.2 |  | 319.3 |  | 6139.8
Current Changes Economic |  | -3.7 |  | -43.2 |  | -2.3 |  | -49.2
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -18.1 |  | 157.4 |  | 6 |  | 145.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -31 |  | -- |  | -31
Subtotal |  | -21.8 |  | 83.2 |  | 3.7 |  | 65.1
Total Changes |  | 731.5 |  | 5150.4 |  | 323 |  | 6204.9
CE - Cost Variance |  | 10184.7 |  | 30547.3 |  | 991.4 |  | 41723.4
CE - Cost & Funding |  | 10184.7 |  | 30547.3 |  | 991.4 |  | 41723.4

## Table 34
Summary BY 1983 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
8434.9 17588.5 532.9 26556.3
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -40 |  | -3930.8 |  | -- |  | -3970.8
Schedule |  | 32.7 |  | -32.2 |  | 35.1 |  | 35.6
Engineering |  | 1.3 |  | 50.4 |  | 4.2 |  | 55.9
Estimating |  | 385.9 |  | 3453.6 |  | 61.2 |  | 3900.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 1081.1 |  | -- |  | 1081.1
Subtotal |  | 379.9 |  | 622.1 |  | 100.5 |  | 1102.5
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -8.5 |  | 65.4 |  | 2.9 |  | 59.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -14.3 |  | -- |  | -14.3
Subtotal |  | -8.5 |  | 51.1 |  | 2.9 |  | 45.5
Total Changes |  | 371.4 |  | 673.2 |  | 103.4 |  | 1148
CE - Cost Variance |  | 8806.3 |  | 18261.7 |  | 636.3 |  | 27704.3
CE - Cost & Funding |  | 8806.3 |  | 18261.7 |  | 636.3 |  | 27704.3
Previous Estimate: December 2014

## Table 35
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -3.7
Congressional reductions FY 2016 which resulted in Mk5A funding decreases. (Estimating) | -6.7 | -13.9
Adjustment for current and prior escalation. (Estimating) | 0.7 | 1.4
Decreases due to revised estimates. (Estimating) | -2.5 | -5.6
RDT&E Subtotal | -8.5 | -21.8
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -43.2
Congressional reductions FY 2016 which resulted in Mk5A funding decrease. (Estimating) | -4.4 | -10
Revised funding due to the Balanced Budget Amendment. (Estimating) | -2.7 | -6
Increases due to revised estimates for Strategic Programs Alteration Kits (Flight Control | 67.8 | 162.9
Electronics Assembly, Interlocks, Command Sequencer, and Missile Inverter). (Estimating)
Adjustment for current and prior escalation. (Estimating) | 4.7 | 10.5
Adjustment for current and prior escalation. (Support) | 2.3 | 4.5
Decrease in Other Support due to realignment from Other Weapons Support to O&S for refresh and replacement of Extended Navy Test Beds necessary to support life of the program. (Support) | -16.6 | -35.5
Procurement Subtotal | 51.1 | 83.2
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -2.3
Revised Project Estimates for the Motor Transfer Facility project at the Utah Test and Training Range. (Estimating)
+2.0 +4.2
Adjustment for current and prior escalation. (Estimating) +0.9 +1.8
MILCON Subtotal +2.9 +3.7

## Table 36
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Guidance FY 11 Production
Contractor: Charles Stark Draper Laboratory
Contractor Location: 55 Technology Square
Cambridge, MA 02139
Contract Number: N00030-11-C-0014
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Firm Fixed Price (FFP), Cost Plus Incentive Fee (CPIF)
Award Date: February 10, 2011
Definitization Date: June 22, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
178.5 181.9 N/A 178.5 181.9 N/A 178.5 178.5
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +1.5 -1.4
Previous Cumulative Variances +1.8 -1.3
Net Change -0.3 -0.1
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to greater than planned Program Management activities required to address a delay in parts deliveries. The cumulative cost variance remains favorable and is comparable to the slightly unfavorable schedule variance, which it will be used to recover.
The unfavorable net change in the schedule variance is due to completion of deliverables as this contract comes to a close, but for which performance has not yet been recorded.
Notes
Current Contract Ceiling Price contains the CPIF, FFP efforts and FPIF. FFP efforts are not included in the variance data reported above.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 37
Contract Identification
Appropriation: Procurement
Contract Name: Guidance FY11 Omnibus
Contractor: Charles Stark Draper Laboratory
Contractor Location: 55 Technology Square
Cambridge, MA 02139
Contract Number: N00030-11-C-0005
Contract Type: Cost Plus Incentive Fee (CPIF)
Award Date: December 28, 2010
Definitization Date: December 28, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
142.9 N/A N/A 494.3 N/A N/A 476.6 476.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications which exercised the FY 2012, FY 2013, and FY 2014 option CLINs.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +3.5 -2.9
Previous Cumulative Variances +5.7 -1.5
Net Change -2.2 -1.4
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to technical issues with the Interferometric Fiber-Optic Gyro and Alternate Pendulous Integrating Gyro Accelerometer. The cumulative cost variance remains favorable and is greater than the slightly unfavorable schedule variance, which it will be used to recover.
The unfavorable net change in the schedule variance is due to completion of deliverables as this contract comes to a close, but for which performance has not yet been recorded.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 38
Contract Identification
Appropriation: Procurement
Contract Name: Guidance FY12 Production
Contractor: Charles Stark Draper Laboratory
Contractor Location: 55 Technology Square
Cambridge, MA 02139
Contract Number: N00030-12-C-0005
Contract Type: Fixed Price Incentive(Firm Target) (FPIF), Firm Fixed Price (FFP)
Award Date: May 04, 2012
Definitization Date: May 04, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
236.7 35.7 651 236.7 35.7 651 236.7 236.7
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) 0.0 -2.7
Previous Cumulative Variances -1.1 -7.4
Net Change +1.1 +4.7
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to
The favorable net change in the schedule variance is due to accelerometer sensor production and corrections to performance data with minimal impact to performance analysis. Materials that were originally delayed in receipt at the time of the last SAR submission were delivered over the course of FY 2015 leading to a large positive change in schedule variance.
Notes
Initial Target Price and Current Target Price represent the total contract values. Ceiling prices reflect the value of the FFP CLINs, which are the only CLINs with ceilings. Therefore, Ceiling price will be lower than Target Price for this contract.
Ceiling Price change due to correction of data.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 39
Contract Identification
Appropriation: Procurement
Contract Name: TRIDENT II FY12 P&DSS
Contractor: Lockheed Martin Space Systems
Contractor Location: 1111 Lockheed Martin Way
Sunnyvale, CA 94089
Contract Number: N00030-12-C-0100
Contract Type: Cost Plus Incentive Fee (CPIF), Cost Plus Fixed Fee (CPFF), Fixed Price Incentive(Firm Target) (FPIF)
Award Date: October 01, 2011
Definitization Date: December 16, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
334.7 590.7 N/A 1134.9 590.7 N/A 1134.9 1134.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract definitization and the exercising of options.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +23.9 -11.8
Previous Cumulative Variances +34.1 -13.5
Net Change -10.2 +1.7
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to 1) Increased labor volume resulting from quality surveillance activities for the first stage, second stage, and common stage motor areas; 2) Missile Body production final year efforts, and
3) More support than planned for several key electronics packages. The cumulative cost variance remains very favorable and is expected to be sufficient to achieve schedule recovery.
The favorable net change in the schedule variance is due to 1) Schedule recovery for a Circuit Card Assembly milestone; 2) Partial schedule recovery on the Flight Control and Interlocks Chassis builds at the Missile Integrated Support Facility; and
3) Schedule recovery for the delivery of Thruster Assemblies and Thruster Cartridges.
Notes
Initial Target Price and Current Target Price represent the total contract values. Ceiling Prices reflect the value of the FFP CLINs, which are the only CLINs with ceilings. Therefore, Ceiling Price will be lower than Target Price for this contract.
Production and Deployed System Support = P&DSS
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 40
Contract Identification
Appropriation: Procurement
Contract Name: Guidance FY13 SPALT
Contractor: Charles Stark Draper Laboratory
Contractor Location: 55 Technology Square
Cambridge, MA 02139
Contract Number: N00030-13-C-0007
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: March 08, 2013
Definitization Date: March 08, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
252.8 28.9 651 257.8 28.9 651 257.8 257.8
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to last year's data only reflected only Cost for all CLINs when, in fact, the data should have reflected Cost plus Fee. This year the data is reflecting Cost plus Fee.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +0.3 -3.6
Previous Cumulative Variances -0.3 -1.9
Net Change +0.6 -1.7
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to work associated with the builds which was pushed back to focus on quality assurance of needed production parts. Since many of these pushed tasks were level of effort, performance was taken on quality assurance time spent and not actual builds.
The unfavorable net change in the schedule variance is due to delays caused by the late receipt of SPALT materials. These materials used to produce accelerometers have seen ongoing delays for over a year which is an issue affecting Guidance subsystem contracts in multiple fiscal years. Another issue has been delays in circuit card assemblies and component production due to a brief factory shutdown due to quality management issues are also contributing to the variance. The factory is now functioning at full capacity with maximum efficiency.
Notes
Initial Target Price and Current Target Price represent the total contract values. Ceiling Prices reflect the value of the FFP CLINs, which are the only CLINs with ceilings. Therefore, Ceiling Price will be lower than Target Price for this contract.
Ceiling Price change due to correction of data.
Strategic Programs Alteration = SPALT

## Table 41
Contract Identification
Appropriation: Procurement
Contract Name: TRIDENT II FY13 P&DSS
Contractor: Lockheed Martin Space Systems
Contractor Location: 1111 Lockheed Martin Way
Sunnyvale, CA 94089
Contract Number: N00030-12-C-0101
Contract Type: Cost Plus Incentive Fee (CPIF), Cost Plus Fixed Fee (CPFF), Fixed Price Incentive(Firm Target) (FPIF)
Award Date: October 01, 2012
Definitization Date: December 20, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
592.2 516.7 N/A 1661.9 516.7 N/A 1661.9 1661.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract definitization and the exercising of options.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +20.7 -13.5
Previous Cumulative Variances +32.0 -9.3
Net Change -11.3 -4.2
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to 1) Power Supply Modules labor ramp up to recover schedule and sub-contractor rework of accelerometers along with increased shifts to support a revised schedule; 2) Survivability Efforts-
a) hardware deliveries were delayed for components needed for the cable builds, which extended the overall time required for build/test, and b) unplanned work was required during the Burn-In Console Critical Design Review; and 3) Increased System Engineering support for the First Article Compatibility Testing on Missile Railcar Support Equipment along with Loading Tube pads. The cumulative variance remains favorable and is expected to be sufficient to recover the schedule variance.
The unfavorable net change in the schedule variance is due to 1) Schedule delay in second tier subcontractors for circuit card assembly; 2) Re-test and rework of accelerometer components due to subcontractor quality control, and 3) First, Second, and Third Stage rocket motors production delays due to focus on quality training and unscheduled down time on the rocket motor precision drilling machine.

## Table 42
Notes
Initial Target Price and Current Target Price represent the total contract values. Ceiling Prices reflect the value of the FFP CLINs, which are the only CLINs with ceilings. Therefore, Ceiling Prices will be lower than Target Price for this contract.
Production and Deployed System Support = P&DSS

## Table 43
Contract Identification
Appropriation: Procurement
Contract Name: TRIDENT II FY14 P&DSS
Contractor: Lockheed Martin Space Systems
Contractor Location: 1111 Lockheed Martin Way
Sunnyvale, CA 94089
Contract Number: N00030-13-C-0100
Contract Type: Cost Plus Fixed Fee (CPFF), Fixed Price Incentive(Firm Target) (FPIF)
Award Date: September 17, 2013
Definitization Date: November 05, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
98.0 529.5 N/A 756.2 529.5 N/A 756.2 756.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract definitization and the exercising of options.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +23.0 -9.2
Previous Cumulative Variances +17.7 -6.3
Net Change +5.3 -2.9
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to 1) Life Extension (LE) Production - Program Management Integrator Disciplines personnel are being leveraged across multiple open production contracts, reducing labor costs; 2) Production - Planned material deliveries are delayed; however, when material deliveries are made this will reduce the cost variance; 3) Lower support required for the procurement and receipt of non-LE electronic parts material; and 4) The Test Missile Kit antenna manufacturing area improvements due to process efficiencies utilizing batch assembly and test.
The unfavorable net change in the schedule variance is due to 1) First article inspection quality management activities and reprioritization to meet Strategic Weapons Facility, Atlantic cable demand; and 2) Delay in delivery of second stage igniter Strategic Systems Program Alteration conversions. Schedule recovery is expected without program impacts.
Notes
Initial Target Price and Current Target Price represent the total contract values. Ceiling Prices reflect the value of the FFP CLINs, which are the only CLINs with ceilings. Therefore, Ceiling Price will be lower than Target Price for this contract.
Production and Deployed System Support = P&DSS

## Table 44
Contract Identification
Appropriation: Procurement
Contract Name: TRIDENT II FY 15 P&DSS
Contractor: Lockheed Martin and Space
Contractor Location: 1111 Lockheed Martin Way
Sunnyvale, CA 94089
Contract Number: N00030-14-C-0100
Contract Type: Cost Plus Incentive Fee (CPIF), Fixed Price Incentive(Firm Target) (FPIF)
Award Date: July 07, 2014
Definitization Date: August 19, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
146.3 549.6 N/A 786.7 549.6 N/A 786.7 786.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract definitization and the exercise of options as funding becomes available.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +14.9 +3.4
Previous Cumulative Variances -- --
Net Change +14.9 +3.4
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to 1) Labor efficiencies across multiple engineering and program management disciplines resulting from a) less system engineering support than planned; b) successful integration testing led to less trouble shooting on the Simulated Flight Test Equipment; and c) favorable rates resulting from hiring of junior personnel to replenish personnel retiring; and 2) Delays in low dollar value material deliveries, however when material deliveries are made this will reduce the cost variance.
The favorable cumulative schedule variance is due to 1) Supplier is ahead of schedule on producing the First Stage and Second Stage motor chocks, Third Stage (TS) dollies and TS Motor Supports and completion of machining and welding for Aerospike Protective Caps; 2) Early delivery of Integrated Valve Assembly Current Monitor Assembly, Preamplifier L Band, and Source Controlled Drawing Low Cost Test Missile Kit Telemetry Transmitter; and 3) Early delivery of Source Controlled Drawings of a required Pressure Transducer.
Notes
This is the first time this contract is being reported.
Initial Target Price and Current Target Price represent the total contract values. Ceiling Prices reflect the value of the FFP CLINs, which are the only CLINs with ceilings. Therefore, Ceiling Price will be lower than Target Price for this contract.
Production and Deployed System Support = P&DSS

## Table 45
Contract Identification
Appropriation: Procurement
Contract Name: FY 14 Guidance SPALT
Contractor: Charles Stark Draper Laboratory
Contractor Location: 55 Technology Square
Cambridge, MA 02139
Contract Number: N00030-14-C-0001
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: March 01, 2014
Definitization Date: April 28, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
283.2 40.0 750 283.2 40.0 750 283.2 283.2
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +2.7 -8.0
Previous Cumulative Variances -- --
Net Change +2.7 -8.0
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to delayed contractor billing which is expected to recover.
The unfavorable cumulative schedule variance is due to 1) Delayed receipt of accelerometer materials. This slip in delivery will not affect the timeline of the overall guidance system; 2) Delays on sensors on previous contracts contributing to delays in gyroscope production; and 3) Delays in circuit card assemblies and component production due to a brief factory shutdown due to quality management issues. The factory is now functioning at full capacity with maximum efficiency.
Notes
This is the first time this contract is being reported.
Initial Target Price and Current Target Price represent the total contract values. Ceiling Prices reflect the value of the FFP CLINs, which are the only CLINs with ceilings. Therefore, Ceiling Price will be lower than Target Price for this contract.
Strategic Programs Alterations = SPALT

## Table 46
Contract Identification
Appropriation: Procurement
Contract Name: FY 15 Guidance SPALT
Contractor: Charles Stark Draper Laboratory
Contractor Location: 55 Technology Square
Cambridge, MA 02139
Contract Number: N00030-15-C-0003
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: February 02, 2015
Definitization Date: February 02, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
302.4 41.0 869 302.4 41.0 869 302.4 302.4
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +0.9 -2.2
Previous Cumulative Variances -- --
Net Change +0.9 -2.2
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to delays on the FY 2014 Guidance SPALT contract which delayed the start of FY 2015 SPALT work. Now that production is back to full capacity this variance will start to erode once prior year work is completed. The current delays on this contract are in the areas of production, infrastructure support, and program management.
The unfavorable cumulative schedule variance is due to an extended delay in subcontractor billing receipts that has prevented the recording of performance. This variance will correct once invoiced are received.
Notes
This is the first time this contract is being reported.
Initial Target Price and Current Target Price represent the total contract values. Ceiling Prices reflect the value of the FFP CLINs, which are the only CLINs with ceilings. Therefore, Ceiling Price will be lower than Target Price for this contract.
Strategic Programs Alteration = SPALT

## Table 47
Contract Identification
Appropriation: Procurement
Contract Name: FY 15 Guidance Omnibus Life Extension
Contractor: Charles Stark Draper Laboratory
Contractor Location: 55 Technology Square
Cambridge, MA 02139
Contract Number: N00030-14-C-0054
Contract Type: Cost Plus Incentive Fee (CPIF), Cost Plus Fixed Fee (CPFF)
Award Date: September 30, 2014
Definitization Date: September 30, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
10.0 N/A 1 49.7 N/A 1 49.7 49.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications which exercised and funded the FY 2015 option CLINs.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +2.5 -0.6
Previous Cumulative Variances -- --
Net Change +2.5 -0.6
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to technical system performance utilizing fewer hours than planned.
The unfavorable cumulative schedule variance is due to delays in completing system qualification testing due to system test issues.
Notes
This is the first time this contract is being reported.
Initial Target Price and Current Target Price represent the total contract value. Ceiling Prices reflect the value of the FFP CLINs, which are the only CLINs with ceilings. Therefore, Ceiling Price will be lower than Target Price for this contract.

## Table 48
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 28 | 28 | 28 | 100%
Production | 425 | 425 | 533 | 79.74%
Total Program Quantity Delivered | 453 | 453 | 561 | 80.75%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
41723.4
35732.8
85.64%
47
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
39
82.98%
37558.2
90.02%
The above data is current as of February 09, 2016.

## Table 49
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 11, 2016
Source of Estimate: POE
Quantity to Sustain: 533
Unit of Measure: Missile
Service Life per Unit: 43.00 Years
Fiscal Years in Service: FY 2000 - FY 2042
Total missiles procured for the TRIDENT II (D5) missile program is 561. Of that number, 28 of those missiles were RDT&E missiles, with the remainder of 533 to be procured using Weapons Procurement, Navy (WPN) funding. Strategic Systems Programs (SSP) uses the number of 533 as O&S costs began in FY 2000 and end in FY 2042. That time period would only cover the 533 procured missiles and would not support the 28 RDT&E missiles which were procured in the late 1980s prior to IOC in 1990.
The costs reflected in this section are for FYs 2000-2042. This is due to the fact that TRIDENT II (D5) missile did not have to establish an O&S APB or report O&S costs. FY 2000 was the first year that SSP was required to begin showing O&S costs for TRIDENT II (D5) missile in its SAR.
Sustainment Strategy
With the collaboration of SSP and its industry partners, life cycle sustainment is the basic premise of the TRIDENT II (D5) missile program and its life extension. The strategy is to reduce O&S costs, provide a full range of logistics support, maintain critical reliability and accuracy requirements and implement the Shipboard Systems Integration (SSI) refresh schedule. A total of 533 TRIDENT II (D5) missiles will be procured for this program that will support the OHIO-Class submarine through FY 2042. The TRIDENT II (D5) missile will be the initial strategic weapon system (SWS) for the OHIO
-Class Replacement Program (ORP).
The TRIDENT II (D5) missile SWS is completing its 26th year of deployment and has reached its original design life goal. Like any other aging weapon system, increased maintenance and repair will be required to sustain a safe, reliable, and accurate SWS. SSP's "Cradle to Grave" responsibility requires a broad range of engineering knowledge and unique skill sets to support the Navy's primary nuclear deterrent system. As such, engineering support spanning all phases of the weapon system life cycle is provided by one organization (SSP). Operational Engineering Support (OES) is required for the establishment of a "closed loop" system which includes the following: 1) collecting data from the Fleet; 2) measuring weapons system performance; 3) analyzing the data collected to identify performance deficiencies; 4) investigating problems identified; 5) developing solutions to resolve the deficiencies and problems; and 6) implementing corrective actions to the Fleet. The SSP life cycle budget maintains the industrial base and expertise in the workforce and ensures that those skill sets will be available for the follow-on ORP.
The TRIDENT II (D5) missile SWS achieved Milestone I in October 1977; Milestone II in October 1983; and Milestone III in April 1987. At that time, program life cycle cost estimates and service cost positions were not required. At the request of the Assistant Secretary of the Navy (ASN) (Research, Development & Acquisition (RDA)), SSP submitted an Internal ICE for only the acquisition portion of the TRIDENT II (D5) Life Extension Program, therefore no O&S cost estimate is available. ASN (RDA) has determined that the current APB is to remain open.
Antecedent Information
The TRIDENT II (D5) weapon system replaced the TRIDENT I (C4) weapon system. O&S costs and assumptions for the TRIDENT I (C4) system are not available.

## Table 50
Annual O&S Costs BY1983 $M
Cost Element |  | Trident II Missile Average Annual Cost Per Missile |  |  |  | TRIDENT I (C-4) (Antecedent) N/A
Unit-Level Manpower |  | -- |  |  |  | --
Unit Operations |  | -- |  |  |  | --
Maintenance |  | 0.231 |  |  |  | --
Sustaining Support |  | 0.94 |  |  |  | --
Continuing System Improvements |  | -- |  |  |  | --
Indirect Support |  | 0.003 |  |  |  | --
Other |  | -- |  |  |  | --
Total |  | 1.174 |  |  |  | --
Item | Total O&S Cost $M
| Trident II Missile | [5 empty] | TRIDENT I (C-4) (Antecedent)
| Current Production APB Objective/Threshold |  |  | Current Estimate
Base Year | N/A |  | N/A |  | 26909 |  | 0
Then Year | N/A |  | N/A |  | 65446 |  | N/A
While the TRIDENT II (D5) missile program will procure 533 WPN missiles there will never be a time when SSP will support a total of 533 missiles in a given year. This is due to the flight test program as ever year a certain number of missiles are tested for reliability and accuracy.
Annual O&S Costs are broken down into these categories:
Maintenance: Provides for the repair, overhaul, and missile processing of the TRIDENT II (D5) missiles' SWS at the Strategic Weapons Facilities (SWFs).
Sustaining Support: Provides for the sustainment of the TRIDENT II (D5) missiles' SWS to include SSI efforts, replacement of aging rocket motors, tooling and test equipment, modifications required for treaty obligations, SWS training at the SWFs, and salaries and benefits for the SSP employees.
Indirect Support: Provides for real property maintenance including funding for recurring maintenance, major repair projects, and minor construction in support of the Fleet Ballistic Missiles and TRIDENT II (D5) facilities. The last year of funding for these efforts was FY 2003.
Equation to Translate Annual Cost to Total Cost
$1.1741M is the average O&S cost per missile per year (in BY $).
$1.1741M x 533 missiles = $625.795M as the average O&S costs for all missiles per year (in BY $).
$625.795M x 43 years = $26,909M as the cost of O&S costs for all missiles from FY 2000-FY 2042 (in BY $).

## Table 51
O&S Cost Variance
Category | BY 1983 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
26769
Programmatic/Planning Factors 140.0 Procurement, Navy O&S sustaining support increases due
to keeping Ship Submersible Ballistic Navy (SSBN) 730 and SSBN 731 in operational service, and a technical correction to the SSI program as well as a realignment of the refresh and replacement of Extended Navy Test Beds which are necessary to support life of the program.
Operations and Maintenance, Navy sustaining support and maintenance increases are due to OES increases in the areas of performance evaluation, reliability maintenance, and accuracy thus ensuring the necessary technical expertise and industrial base in order to maintain the sea based strategic deterrent demonstrated safety, reliability, and accuracy and its unique technologies through the entire life of the OHIO Class and as the initial payload for the ORP. Missile Processing operations also increased as a result of the National Threat Capability Assessment, Force Restructure, and New Strategic Arms Reduction Treaty implementation.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 140.0
Current Estimate 26909.0
Disposal Estimate Details
Date of Estimate: February 04, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 1983 $M): Total costs for disposal of all Missile are 124.7
O&S Costs for TRIDENT II (D5) missile include 1st, 2nd, and 3rd stage rocket motor disposal. At this time, these are the only disposal/demilitarization costs anticipated for the TRIDENT II (D5) missile. Any further disposal/demilitarization costs will be determined once final decisions have been made in regards to the OHIO-Class Replacement
Program. The costs displayed in this section reflect infrastructure costs required for maintaining a disposal program.