## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-212
V-22 Osprey Joint Services Advanced Vertical Lift Aircraft (V-22)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 13
Track to Budget 17
Cost and Funding 19
Low Rate Initial Production 45
Foreign Military Sales 46
Nuclear Costs 46
Unit Cost 47
Cost Variance 50
Contracts 54
Deliveries and Expenditures 60
Operating and Support Cost 61

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
V-22 Osprey Joint Services Advanced Vertical Lift Aircraft (V-22)
DoD Component
Navy
Joint Participants
United States Marine Corps; United States Navy; United States Special Operations Command; United States Air Force
Responsible Office
Col Dan Robinson
PMA-275 (V-22 Osprey Joint Services Advanced Vertical Lift Aircraft (V-22))
Program Executive Office - Air, Anti-Submarine Warfare, Assault & Special Mission Programs
47123 Buse Road Bldg 2272 Patuxent River, MD 20670-1547
dan.robinson@navy.mil
Phone: | 301-757-5161
Fax: | 301-757-7558
DSN Phone: | 757-5161
DSN Fax: | 757-7558
Date Assigned: | July 9, 2013
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated September 28, 2005
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 31, 2011

## Table 6
Mission and Description
The V-22 Osprey Joint Services Advanced Vertical Lift Aircraft (V-22) Program was established by the DoD to develop, test, evaluate, procure, field and support a tilt rotor, Vertical/Short Takeoff and Landing aircraft for Joint Service application. The Navy was designated the Executive Agent with support from the United States Air Force (USAF) in the V-22 Joint Program Office located at the Naval Air Systems Command Headquarters, Naval Air Station Patuxent River, MD. The V-22 Program is designed to provide an aircraft to meet the amphibious/vertical assault needs of the United States Marine Corps (USMC), the Carrier-On Board Delivery/fleet logistics needs of the Navy, and the special operations needs of the USAF and United States Special Operations Command (USSOCOM). The MV-22 variant replaces the CH-46E and CH-53D in the USMC. The CV-22 variant replaces the MH-53-J/M, but also provides a new capability and augments the MC-130 in the USAF/USSOCOM inventory for special operations infiltration, exfiltration, and resupply missions. The Navy CMV-22 will be replacing the C-2A in the Navy inventory. The V-22 is capable of flying over 2,100 nautical miles with a single refueling, giving the Services the advantage of a V/STOL aircraft able to rapidly self-deploy to any location in the world.
Block Descriptions:
V-22 capability is being increased and fielded over time via a Block upgrade acquisition strategy. MV-22 Block A provides a “Safe and Operational Test and Training Asset” configuration that supports developmental and operational flight tests, as well as fleet training. MV-22 Block B provides for correction of previously identified deficiencies and suitability improvements. MV-22 Block C provides mission enhancements, primarily in the areas of environmental control systems upgrades and mission systems improvements. Block 0/10 is a CV-unique configuration including radar and electronic countermeasures upgrades. Block 20 provides an enhanced CV-unique configuration with communications and aircraft system performance upgrades. The Navy CMV-22 is an MV-22 Block C configuration with enhancements including extended range fuel tanks, high frequency radio and a cabin intercom system.

## Table 7
Executive Summary
The V-22 Program focus is on improving aircraft readiness, sustaining Fleet aircraft, delivery of Multi-Year 2 production aircraft, reducing operating costs, and expanding our business base, both domestically and internationally. Both the MV-22 and CV-22 continue to meet all Key Performance Parameters. APB cost performance remains within established thresholds.
Production has completed on 17 of 27 planned aircraft production lots. As of February 26, 2016, 329 (281 MV/48 CV) aircraft have been delivered. To support program affordability, the Program is currently pursuing a third Multi-Year Procurement (MYP) contract for FY 2018-FY 2022. On the V-22 MYP 2 Contract with Bell-Boeing, the Lot 20 full-funding modification was awarded for $1.184B on October 26, 2015 and $38.6M of Advance Procurement funding for Lot 21 was awarded on November 24, 2015.
The Navy variant of the V-22 in support of the Carrier Onboard Delivery mission will begin development in FY 2016. The initial Navy Non-Recurring Engineering/Engineering Change Proposal delivery order is expected to award in second quarter FY 2016. Production of the Navy variant V-22 will begin in FY 2018.
The Program Office awarded a $332M modification to the MYP 2 Contract with Bell-Boeing in July 2015 to provide for the manufacture and delivery of five MV-22 tilt rotor aircraft in support of the Government of Japan. On September 25, 2015, a delivery order was awarded with Bell-Boeing for $20.9M to complete Non-Recurring Engineering for Japan-specific aircraft modifications. It is expected that a second Letter of Offer and Acceptance (LOA) will be in place by June 2016 for up to 12 additional aircraft, for a total of 17 aircraft for Japan.
The Operational Utility Evaluation (OUE) of the new Mission Computer and Color Helmet Mounted Display systems on the CV-22 began on December 8, 2015, and was completed on February 11, 2016.
There are no significant software-related issues with the program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone 0 (DEPSECDEF MEMO) | Dec 1981 | Dec 1981 | Jun 1982 | Dec 1981
Milestone I (DSARC I) | Dec 1982 | Dec 1982 | Jun 1983 | Dec 1982
Preliminary Design Contract Award | Apr 1993 | Apr 1993 | Oct 1993 | Apr 1983
Milestone II (DSARC II) | Apr 1986 | Apr 1986 | Oct 1986 | Apr 1986
FSD Contract Award | May 1986 | May 1986 | Nov 1986 | May 1986
Production Contract Award (Long Lead AAC) | Jan 1989 | Jan 1989 | Jul 1989 | Mar 1989
EMD Airframe Contract Award | Oct 1992 | Oct 1992 | Apr 1993 | Oct 1992
EMD Engine Contract Award | Dec 1992 | Dec 1992 | Jun 1993 | Dec 1992
SRR Complete | Aug 1993 | Aug 1993 | Feb 1994 | Aug 1993
PDR Complete | Apr 1994 | Apr 1994 | Oct 1994 | Apr 1994
MS II Plus Program Review | Sep 1994 | Sep 1994 | Mar 1995 | Sep 1994
CDR Complete | Dec 1994 | Dec 1994 | Jun 1995 | Dec 1994
Modification to EMD Contract to Include CV-22 Efforts | Aug 1995 | Aug 1995 | Feb 1996 | Aug 1995
LRIP 1 Contract Award (Long lead $) | Jun 1996 | Jun 1996 | Dec 1996 | Jun 1996
CV-22 SRR | Aug 1996 | Aug 1996 | Feb 1997 | Aug 1996
DAB LRIP REVIEW | Apr 1997 | Apr 1997 | Oct 1997 | Apr 1997
LRIP 2 Contract Award (Long lead $) | Apr 1997 | Apr 1997 | Oct 1997 | Apr 1997
CV-22 PDR | Dec 1997 | Dec 1997 | Jun 1998 | Dec 1997
LRIP 3 Contract Award (Long Lead $) | Feb 1998 | Feb 1998 | Aug 1998 | Mar 1998
CV-22 CDR | Dec 1998 | Dec 1998 | Jun 1999 | Dec 1998
LRIP 4 Contract Award (Long Lead $) | Mar 1999 | Mar 1999 | Sep 1999 | Mar 1999
LRIP 1 First Delivery | May 1999 | May 1999 | Nov 1999 | May 1999
MV-22 TECHEVAL
Start | Jul 1999 | Jul 1999 | Jan 2000 | Jul 1999
Complete | Sep 1999 | Sep 1999 | Mar 2000 | Sep 1999
MV-22 OPEVAL
Start | Nov 1999 | Nov 1999 | May 2000 | Nov 1999
Complete | Jul 2000 | Jul 2000 | Jan 2001 | Jul 2000
PCA | Dec 1999 | Dec 1999 | Jun 2000 | Dec 1999
CV-22 Flight Test
Start | Feb 2000 | Feb 2000 | Aug 2000 | Feb 2000
Complete | Oct 2007 | Oct 2007 | Apr 2008 | Oct 2007

## Table 11
LRIP 5 Contract Award (Long Lead $) | Jun 2000 | Jun 2000 | Dec 2000 | Jun 2000
LRIP 6 Contract Award (Long Lead $) | Jun 2000 | Jun 2000 | Dec 2000 | Jun 2000
CV-22 Production Contract Award (Long lead $) | Jun 2000 | Jun 2000 | Dec 2000 | Jun 2000
LRIP 2 First Delivery | Apr 2000 | Apr 2000 | Oct 2000 | Jul 2000
LRIP 7 Contract Award (Long Lead $) | Mar 2002 | Mar 2002 | Sep 2002 | Mar 2002
LRIP 3 First Delivery | Apr 2003 | Apr 2003 | Oct 2003 | Apr 2003
LRIP 8 Contract Award (Long Lead $) | May 2003 | May 2003 | Nov 2003 | May 2003
LRIP 4 First Delivery | Aug 2003 | Aug 2003 | Feb 2004 | Aug 2003
LRIP 5 First Delivery | Oct 2003 | Oct 2003 | Apr 2004 | Oct 2003
LRIP 6 First Delivery | Jan 2004 | Jan 2004 | Jul 2004 | Jan 2004
LRIP 9 Contract Award (Long Lead $) | Jan 2004 | Jan 2004 | Jul 2004 | Feb 2004
MV-22 Operational Test-2F
Start | May 2004 | May 2004 | Nov 2004 | May 2004
Complete | Jul 2004 | Jul 2004 | Jan 2005 | Jul 2004
Full Rate Production Contract Award (Long lead $) | Jan 2005 | Jan 2005 | Jul 2005 | Jan 2005
MV-22 OPEVAL Phase II
Start | Nov 2004 | Nov 2004 | May 2005 | Mar 2005
Complete | May 2005 | May 2005 | Nov 2005 | Jun 2005
LRIP 7 First Delivery | Feb 2005 | Feb 2005 | Aug 2005 | Apr 2005
CV-22 First PRTV Delivery | Jul 2005 | Jul 2005 | Jan 2006 | Sep 2005
MS III | Oct 2005 | Oct 2005 | Apr 2006 | Oct 2005
LRIP 8 First Delivery | Dec 2005 | Dec 2005 | Jun 2006 | Dec 2005
CV-22 First Production Delivery | Feb 2006 | Feb 2006 | Aug 2006 | Mar 2006
CV-22 IOT&E
Start | Jun 2006 | Jun 2006 | Dec 2006 | Jun 2006
Complete | Dec 2007 | Dec 2007 | Jun 2008 | Jun 2008
LRIP 9 First Delivery | Nov 2006 | Nov 2006 | May 2007 | Dec 2006
MV-22 IOC | Mar 2007 | Mar 2007 | Sep 2007 | Jun 2007
CV IOC | Oct 2009 | Oct 2009 | Apr 2010 | Mar 2009
GSD | Dec 2010 | Dec 2010 | Jun 2011 | Apr 2010
Change Explanations
None

## Table 12
Acronyms and Abbreviations
AAC - Advanced Acquisition Contract CDR - Critical Design Review
DEPSECDEF - Deputy Secretary of Defense
DSARC - Defense Systems Acquisition Review Council FSD - Full Scale Development
GSD - Government Support Date
IOT&E - Initial Operational Test and Evaluation MS - Milestone
OPEVAL - Operational Evaluation PCA - Physical Configuration Audit PDR - Preliminary Design Review
PRTV - Production Representative Test Vehicle SRR - System Requirements Review TECHEVAL - Technical Evaluation

## Table 13
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
MV-22
Interoperability
Satisfy all top level IERs | Satisfy all top level IERs | Satisfy all top level IERs designated as critical | Satisfy all top level IERs designated as critical | Satisfy all top level IERs designated as critical
Cruise Speed (kts)
270 | 270 | 240 | 255 | 285
Mission Radius (nm)
Land Trooplift
200X1 | 200X1 | 200X1 | 210x1 | 216X1
Land External
110X1 | 110X1 | 50X1 | 69x1 | 51x1
Sea Trooplift
110X2 | 110X2 | 50X2 | 53x2 | 90X2
Sea External
110X1 | 110X1 | 50X1 | 89x1 | 84X1
Amphibious Pre-Assault/Raid Ops (nm)
200X1 | 200X1 | 200X1 | 230x1 | 319x1
Payload
Troops
24 | 24 | 24 | 24 | 24
External Lift (lbs)
15000 | 15000 | 10000 | 10000 | 12500
Aerial Refuel Capable
yes | yes | yes | yes | yes
Self-Deployment (nm)
2100 w/no refuel | 2100 w/no refuel | 2100 w/1 refuel | 2660 w/1 aeriel refuel | 2294 w/1 aerial refuel
Shipboard Compatible
yes | yes | yes | yes | yes
V/STOL Capable
yes | yes | yes | yes | yes
Reliability
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)

## Table 14
MFHBF (log)
>=1.2 | >=1.2 | >=0.9 | 1.3 | 1.24
MFHBA
17 Hrs | 17 Hrs | 17 Hrs | 31.2 | 33.1
CV-22
Interoperability
Satisfy all top level IERs | Satisfy all top level IERs | Satisfy all top level IERs designated as critical | Satisfy all top level IERs designated as critical | Satisfy all top level IERs designated as critical
Cruise Speed (kts)
270 | 270 | 230 | 264 | 261
Mission Radius (nm)
750 | 750 | 500 | 538 | 567
Payload - Troops
24 | 24 | 18 | 18 | 18
Aerial Refuel Capable
yes | yes | yes | yes | yes
Self-Deployment (nm)
2100 w/0 aerial refuel | 2100 w/0 aerial refuel | 2100 w/1 aerial refuel | 2144 w/1 aerial refuel | 2161 w/1 aerial refuel
Shipboard Compatible
yes | yes | yes | yes | yes
Operational Environment
100' TF/TA, Day/Night, VMC/IMC | 100' TF/TA, Day/Night, VMC/IMC | 300' TF/TA, Day/Night, VMC/IMC | 100' TF/TA, Day/Night, VMC/IMC | 100' TF/TA, Day/Night, VMC/IMC
Precision Navigation (diameter @ MAX Combat Radius)
Locate LZ W/IN 1 Rotor | Locate LZ W/IN 1 Rotor | Locate LZ W/IN 2X Rotor | Locate LZ W/IN 2X Rotor | Locate LZ W/IN 2X Rotor
Operational Enviroment
DECM
SIRFC w/RF Jamming DIRCM | SIRFC w/RF Jamming DIRCM | SIRFC w/RWR, MW, CMDS | SIRFC w/RF, Jamming DIRCM | SIRFC w/RF, Jamming DIRCM
MMR (TF/TA)
100 FT | 100 FT | 300 FT | 100FT | 100 FT
Reliability
MFHBF (LOG)
>=1.2 | >=1.2 | >=0.9 | 1.6 | 1.5
MFHBA
15 Hrs | 15 Hrs | 15 Hrs | 29.2 | 29
(Ch-2)
(Ch-3)
(Ch-4)
(Ch-4)
(Ch-4)
(Ch-5)
(Ch-6)

## Table 15
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
CPD dated September 1, 2010
Change Explanations
(Ch-1) The current performance estimates for MV-22 have been updated to reflect Lot 18 (current production lot) aircraft specification weight. Changes to the specification weight, drag and assumptions associated with calculating performance values have resulted in minor adjustments to performance predictions.
(Ch-2) The current estimate for MV-22 MFHBF has changed slightly from 1.25 hrs to 1.24 hrs. These values reflect the updated calculations from the V-22 Failure Reporting, Analysis and Corrective Action System database. This data is based on the Block B and C Aircraft operating in the Vertical Marine Medium Tilt-Rotor Squadrons through October 2015 with 176,688 flight hours.
(Ch-3) The current estimate for MV-22 MFHBA has improved from 32.1 hrs to 33.1 hrs. These values reflect the updated calculations from the V-22 Failure Reporting, Analysis and Corrective Action System database. This data is based on the Block B and C Aircraft operating in the Vertical Marine Medium Tilt-Rotor Squadrons through October 2015 with 176,688 flight hours.
(Ch-4) The current estimate for CV-22 Cruise Speed (kts), Mission Radius (nm) and Self-Deployment (nm) is based on Lot 18 aircraft specification weights with slight adjustment to SOF mission weights used in modeling the performance. These changes generally resulted in improvements to current estimates for calculated aircraft performance.
(Ch-5) The current estimate for CV-22 MFHBF has changed slightly from 1.6 hrs to 1.5 hrs. These values reflect the updated calculations from the V-22 Failure Reporting, Analysis and Corrective Action System database. This data is based on the Block 10 and 20 Aircraft operating at Hurlburt, Cannon, and Mildenhall through October 2015 with 36,019 flight hours. (Ch-6) The current estimate for CV-22 MFHBA has changed slightly from 29.9 hrs to 29.0 hrs. These values reflect the updated calculations from the V-22 Failure Reporting, Analysis and Corrective Action System database. This data is based on the Block 10 and 20 Aircraft operating at Hurlburt, Cannon, and Mildenhall through October 2015 with 36,019 flight hours.

## Table 16
Acronyms and Abbreviations
CMDS - Counter-Measures Dispenser System DECM - Defensive Electronic Countermeasure DIRCM - Directed Infrared Countermeasures Ft - Feet
Hrs - Hours
IERs - Information Exchange Requirements kts - knots
lbs - Pounds LOG - Logistics
LZ w/IN - Landing Zone Within MAX - Maximum
MFHBA - Mean Flight Hours Between Aborts MFHBF - Mean Flight Hours Between Failures MW - Missile Warning
nm - nautical miles
SIRFC - Suite of Integrated Radio Frequency Countermeasures TF/TA - Terrain Following/Terrain Avoidance
V/STOL - Vertical/Short Takeoff and Landing
VMC/IMC - Visual Meteorological Conditions/Instrument Meteorological Conditions w/RF - with Radio Frequency
w/RWR - with Radar Warning Receiver

## Table 17
Track to Budget
RDT&E
Appn |  |  | BA | PE
Navy 1319 05 0604262N
Project | Name
1425 V-22
Air Force 3600 05 0401318F
Project | Name
654103 CV-22 (Sunk)
Air Force 3600 07 0401318F
Project | Name
676033 CV-22 RDT&E Post
Production Support
Defense-Wide 0400 07 1160403BB
Project | Name
SF200 CV-22 Development (Shared)
Defense-Wide 0400 07 1160404BB
Project | Name
SF200 SO Tactical Systems
(Automation)
Notes: 1985 Sunk (funded in prior years only)
Defense-Wide 0400 07 1160421BB
(Sunk)
Project | Name
SF200 CV-22 (Sunk)
Procurement
Appn |  |  | BA | PE
Navy |  | 1506 01 |  | 0206121M
|  | Line Item |  | Name
|  | 0164 Notes: |  | V-22 (Medium Lift) Spares are separately entered.
Navy |  | 1506 06 |  | 0206121M
|  | Line Item |  | Name
|  | 605 |  | Spares and Repair Parts | (Shared)
Air Force |  | 3010 06 |  | 0401318F
|  | Line Item |  | Name
|  | 999 |  | Initial Spares/Repair Parts | (Shared)
Air Force |  | 3010 04 |  | 0401318F
|  | Line Item |  | Name
|  | V022A0 |  | CV-22 (MYP)

## Table 18
Notes: Spares are separately entered.
Defense-Wide 0300 02 1160421BB
Line Item | Name
1000CV22 CV-22 Modification
Notes: Does not include retrofit funding.
MILCON
Appn |  | BA | PE
Navy 1205 01 0216496M
Project | Name
00318887 LHD Pad Conversion and MV-22 LZ Improvements
Defense-Wide 0500 01 1140494BB
Project | Name
QFQE0530 Special Operations Command Simulator Facility
Notes
Multiple MILCON projects are associated with each program element and are too numerous to list. Projects that are identified are either ongoing or to be completed.

## Table 19
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2005 $M | [6 empty] | BY 2005 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 11446.5 |  |  | 11446.5 | 12591.2 |  |  | 12487.1 |  | 9891.7 |  |  | 9891.7 |  | 11176.6
Procurement |  | 38562.8 |  |  | 38562.8 | 42419.1 |  |  | 38812.8 |  | 43099.3 |  |  | 43099.3 |  | 44570
Flyaway |  | -- |  |  | -- | -- |  |  | 31704.5 |  | -- |  |  | -- |  | 36653.1
Recurring |  | -- |  |  | -- | -- |  |  | 30138.5 |  | -- |  |  | -- |  | 34937.3
Non Recurring |  | -- |  |  | -- | -- |  |  | 1566 |  | -- |  |  | -- |  | 1715.8
Support |  | -- |  |  | -- | -- |  |  | 7108.3 |  | -- |  |  | -- |  | 7916.9
Other Support |  | -- |  |  | -- | -- |  |  | 5203.2 |  | -- |  |  | -- |  | 5786.9
Initial Spares |  | -- |  |  | -- | -- |  |  | 1905.1 |  | -- |  |  | -- |  | 2130
MILCON |  | 241.1 |  |  | 241.1 | 265.2 |  |  | 105.1 |  | 262.4 |  |  | 262.4 |  | 115.7
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 50250.4 |  |  | 50250.4 | N/A |  |  | 51405 |  | 53253.4 |  |  | 53253.4 |  | 55862.3
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current APB/SAR cost estimate provides sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk and external interference. It was consistent with average resource expenditures on historical efforts of similar size, scope, and complexity and represents a notional 50% confidence level when established.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 2 |  |  |  | 2 |  |  |  |  | 2
Procurement |  |  | 456 |  |  |  | 456 |  |  |  |  | 459
Total |  |  | 458 |  |  |  | 458 |  |  |  |  | 461

## Table 20
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 10102.6 | 104.3 |  |  | 206.7 | 177.1 | 135.8 |  | 83.9 |  | 82.5 |  |  | 283.7 |  | 11176.6
Procurement | 33049.6 | 1526 |  |  | 1284.7 | 663.9 | 731 |  | 664.1 |  | 1532.5 |  |  | 5118.2 |  | 44570
MILCON | 103.3 | 0 |  |  | 12.4 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 115.7
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 43255.5 | 1630.3 |  |  | 1503.8 | 841 | 866.8 |  | 748 |  | 1615 |  |  | 5401.9 |  | 55862.3
PB 2016 Total | 43254 | 1608 |  |  | 1707.1 | 1048.4 | 936.2 |  | 959.8 |  | 1860.1 |  |  | 3384.4 |  | 54758
Delta | 1.5 | 22.3 |  |  | -203.3 | -207.4 | -69.4 |  | -211.8 |  | -245.1 |  |  | 2017.5 |  | 1104.3
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 2
Production | 0 |  | 351 |  | 20 | 16 | 6 |  | 6 |  | 6 | 14 |  | 40 |  | 459
PB 2017 Total | 2 |  | 351 |  | 20 | 16 | 6 |  | 6 |  | 6 | 14 |  | 40 |  | 461
PB 2016 Total | 2 |  | 351 |  | 19 | 18 | 8 |  | 8 |  | 8 | 16 |  | 30 |  | 460
Delta | 0 |  | 0 |  | 1 | -2 | -2 |  | -2 |  | -2 | -2 |  | 10 |  | 1

## Table 21
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1982 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
1983 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.4
1984 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.1
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 169.5
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 525.1
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 421.7
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 404.8
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 269.9
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 204.2
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 212.2
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 758
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 713.3
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 451.8
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 716.4
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 605.5
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 487.5
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 335.8
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 175.9
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 217.9
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 391.6
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 387.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 357.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 246.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 192.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 251.6
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 76.9
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.3
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 76.5

## Table 22
2017 | -- | -- | -- | -- | -- | -- | 174.4
2018 | -- | -- | -- | -- | -- | -- | 145.3
2019 | -- | -- | -- | -- | -- | -- | 97.6
2020 | -- | -- | -- | -- | -- | -- | 64.2
2021 | -- | -- | -- | -- | -- | -- | 67.5
2022 | -- | -- | -- | -- | -- | -- | 55.5
2023 | -- | -- | -- | -- | -- | -- | 56.5
2024 | -- | -- | -- | -- | -- | -- | 45.2
2025 | -- | -- | -- | -- | -- | -- | 27.1
2026 | -- | -- | -- | -- | -- | -- | 10.9
2027 | -- | -- | -- | -- | -- | -- | 14.5
Subtotal | -- | -- | -- | -- | -- | -- | 9963.5

## Table 23
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1982 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
1983 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.7
1984 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 132.1
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 261.3
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 786.9
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 613.8
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 570.1
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 364.7
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 265.1
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 266
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 923.2
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 849.1
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.2
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 517.9
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 807.6
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 674.3
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 538.5
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 366.6
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 189.3
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 231.3
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 411.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 401.2
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 360
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 242.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 183
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 233.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 107.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.2
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 68.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113.2
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 74.5
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.1
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.6

## Table 24
2022 | -- | -- | -- | -- | -- | -- | 39.9
2023 | -- | -- | -- | -- | -- | -- | 39.9
2024 | -- | -- | -- | -- | -- | -- | 31.3
2025 | -- | -- | -- | -- | -- | -- | 18.4
2026 | -- | -- | -- | -- | -- | -- | 7.2
2027 | -- | -- | -- | -- | -- | -- | 9.5
Subtotal | -- | -- | -- | -- | -- | -- | 11331.1

## Table 25
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.3
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 145.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.9
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.1
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.9
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.7
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.5
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.6
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.7
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.3
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.6
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.9

## Table 26
2025 | -- | -- | -- | -- | -- | -- | 16.2
2026 | -- | -- | -- | -- | -- | -- | 11
Subtotal | 2 | -- | -- | -- | -- | -- | 633.2

## Table 27
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.5
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 153
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.4
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1

## Table 28
2025 | -- | -- | -- | -- | -- | -- | 11.1
2026 | -- | -- | -- | -- | -- | -- | 7.4
Subtotal | 2 | -- | -- | -- | -- | -- | 570.7

## Table 29
The FY 2002 Appropriation Act provided funding for two CV-22 Production Representative Test Vehicles.

## Table 30
Annual Funding 0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1990 |  | -- | 36.1 |  | -- |  | -- |  | 36.1 |  | -- |  | 36.1
1991 |  | -- | 8 |  | -- |  | -- |  | 8 |  | -- |  | 8
1992 |  | -- | 15 |  | -- |  | -- |  | 15 |  | -- |  | 15
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1994 |  | -- | 14.7 |  | -- |  | -- |  | 14.7 |  | -- |  | 14.7
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2000 |  | -- | 33.5 |  | -- |  | -- |  | 33.5 |  | -- |  | 33.5
2001 |  | -- | 40.1 |  | -- |  | -- |  | 40.1 |  | -- |  | 40.1
2002 |  | -- | 104.1 |  | -- |  | -- |  | 104.1 |  | -- |  | 104.1
2003 |  | -- | 32.2 |  | -- |  | -- |  | 32.2 |  | -- |  | 32.2
2004 |  | -- | 68.4 |  | -- |  | -- |  | 68.4 |  | -- |  | 68.4
2005 |  | -- | 53.1 |  | -- |  | -- |  | 53.1 |  | -- |  | 53.1
2006 |  | -- | 23.7 |  | -- |  | -- |  | 23.7 |  | -- |  | 23.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | 21.9 |  | -- |  | -- |  | 21.9 |  | -- |  | 21.9
2009 |  | -- | 30.5 |  | -- |  | -- |  | 30.5 |  | -- |  | 30.5
2010 |  | -- | 12.2 |  | -- |  | -- |  | 12.2 |  | -- |  | 12.2
2011 |  | -- | 14 |  | -- |  | -- |  | 14 |  | -- |  | 14
2012 |  | -- | 10.8 |  | -- |  | -- |  | 10.8 |  | -- |  | 10.8
2013 |  | -- | 2.1 |  | -- |  | -- |  | 2.1 |  | -- |  | 2.1
2014 |  | -- | 2.8 |  | -- |  | -- |  | 2.8 |  | -- |  | 2.8
2015 |  | -- | 0.2 |  | -- |  | -- |  | 0.2 |  | -- |  | 0.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | 15.6 |  | -- |  | -- |  | 15.6 |  | -- |  | 15.6
2018 |  | -- | 14.3 |  | -- |  | -- |  | 14.3 |  | -- |  | 14.3
2019 |  | -- | 21.6 |  | -- |  | -- |  | 21.6 |  | -- |  | 21.6
2020 |  | -- | 5 |  | -- |  | -- |  | 5 |  | -- |  | 5
Subtotal |  | -- | 579.9 |  | -- |  | -- |  | 579.9 |  | -- |  | 579.9

## Table 31
Annual Funding 0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1990 |  | -- | 46.9 |  | -- |  | -- |  | 46.9 |  | -- |  | 46.9
1991 |  | -- | 10 |  | -- |  | -- |  | 10 |  | -- |  | 10
1992 |  | -- | 18.2 |  | -- |  | -- |  | 18.2 |  | -- |  | 18.2
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1994 |  | -- | 17.2 |  | -- |  | -- |  | 17.2 |  | -- |  | 17.2
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2000 |  | -- | 36 |  | -- |  | -- |  | 36 |  | -- |  | 36
2001 |  | -- | 42.5 |  | -- |  | -- |  | 42.5 |  | -- |  | 42.5
2002 |  | -- | 109.3 |  | -- |  | -- |  | 109.3 |  | -- |  | 109.3
2003 |  | -- | 33.3 |  | -- |  | -- |  | 33.3 |  | -- |  | 33.3
2004 |  | -- | 69.1 |  | -- |  | -- |  | 69.1 |  | -- |  | 69.1
2005 |  | -- | 52.1 |  | -- |  | -- |  | 52.1 |  | -- |  | 52.1
2006 |  | -- | 22.6 |  | -- |  | -- |  | 22.6 |  | -- |  | 22.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | 20 |  | -- |  | -- |  | 20 |  | -- |  | 20
2009 |  | -- | 27.5 |  | -- |  | -- |  | 27.5 |  | -- |  | 27.5
2010 |  | -- | 10.8 |  | -- |  | -- |  | 10.8 |  | -- |  | 10.8
2011 |  | -- | 12.2 |  | -- |  | -- |  | 12.2 |  | -- |  | 12.2
2012 |  | -- | 9.3 |  | -- |  | -- |  | 9.3 |  | -- |  | 9.3
2013 |  | -- | 1.8 |  | -- |  | -- |  | 1.8 |  | -- |  | 1.8
2014 |  | -- | 2.3 |  | -- |  | -- |  | 2.3 |  | -- |  | 2.3
2015 |  | -- | 0.2 |  | -- |  | -- |  | 0.2 |  | -- |  | 0.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2017 |  | -- | 12.4 |  | -- |  | -- |  | 12.4 |  | -- |  | 12.4
2018 |  | -- | 11.2 |  | -- |  | -- |  | 11.2 |  | -- |  | 11.2
2019 |  | -- | 16.6 |  | -- |  | -- |  | 16.6 |  | -- |  | 16.6
2020 |  | -- | 3.8 |  | -- |  | -- |  | 3.8 |  | -- |  | 3.8
Subtotal |  | -- | 585.3 |  | -- |  | -- |  | 585.3 |  | -- |  | 585.3

## Table 32
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | 231.4 |  | 231.4
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1996 |  | -- | 41.1 |  | -- |  | -- |  | 41.1 |  | -- |  | 41.1
1997 |  | 5 | 552.1 |  | -- |  | 25 |  | 577.1 |  | 132.3 |  | 709.4
1998 |  | 7 | 622.1 |  | -- |  | 20.4 |  | 642.5 |  | 66.2 |  | 708.7
1999 |  | 7 | 561.4 |  | -- |  | 18 |  | 579.4 |  | 104.1 |  | 683.5
2000 |  | 11 | 768.5 |  | -- |  | 31 |  | 799.5 |  | 187.8 |  | 987.3
2001 |  | 9 | 753.1 |  | -- |  | 99.2 |  | 852.3 |  | 157.9 |  | 1010.2
2002 |  | 9 | 660.6 |  | -- |  | 21.6 |  | 682.2 |  | 204.6 |  | 886.8
2003 |  | 11 | 844.2 |  | -- |  | 109.4 |  | 953.6 |  | 129.6 |  | 1083.2
2004 |  | 9 | 651.9 |  | -- |  | 59.9 |  | 711.8 |  | 167.5 |  | 879.3
2005 |  | 8 | 584.4 |  | -- |  | 115.8 |  | 700.2 |  | 321.8 |  | 1022
2006 |  | 12 | 868.2 |  | -- |  | 146.4 |  | 1014.6 |  | 367.1 |  | 1381.7
2007 |  | 14 | 1129.2 |  | -- |  | 222.8 |  | 1352 |  | 244.3 |  | 1596.3
2008 |  | 23 | 1651.9 |  | -- |  | 153.8 |  | 1805.7 |  | 308.1 |  | 2113.8
2009 |  | 30 | 1855.8 |  | -- |  | 70.6 |  | 1926.4 |  | 307.8 |  | 2234.2
2010 |  | 30 | 1847.9 |  | -- |  | 81.6 |  | 1929.5 |  | 317.4 |  | 2246.9
2011 |  | 30 | 1855.6 |  | -- |  | 30.5 |  | 1886.1 |  | 264.7 |  | 2150.8
2012 |  | 30 | 1921.3 |  | -- |  | 25.8 |  | 1947.1 |  | 264.3 |  | 2211.4
2013 |  | 18 | 1289.9 |  | -- |  | 29.1 |  | 1319 |  | 164.1 |  | 1483.1
2014 |  | 19 | 1230 |  | -- |  | 37.8 |  | 1267.8 |  | 144.5 |  | 1412.3
2015 |  | 19 | 1336.4 |  | -- |  | 16.3 |  | 1352.7 |  | 194.9 |  | 1547.6
2016 |  | 19 | 1342.8 |  | -- |  | 0.3 |  | 1343.1 |  | 97.6 |  | 1440.7
2017 |  | 16 | 1147.2 |  | -- |  | 9.3 |  | 1156.5 |  | 127.3 |  | 1283.8
2018 |  | 6 | 567.6 |  | -- |  | 4 |  | 571.6 |  | 92.1 |  | 663.7
2019 |  | 6 | 584.6 |  | -- |  | 7.8 |  | 592.4 |  | 138.6 |  | 731
2020 |  | 6 | 620.1 |  | -- |  | 0.5 |  | 620.6 |  | 43.5 |  | 664.1
2021 |  | 14 | 1334.5 |  | -- |  | 7.2 |  | 1341.7 |  | 190.8 |  | 1532.5
2022 |  | 14 | 1379.6 |  | -- |  | 10.7 |  | 1390.3 |  | 266.8 |  | 1657.1
2023 |  | 14 | 1393.5 |  | -- |  | 8.5 |  | 1402 |  | 209.3 |  | 1611.3
2024 |  | 6 | 681.2 |  | -- |  | 37.1 |  | 718.3 |  | 204.6 |  | 922.9
2025 |  | 6 | 677.2 |  | -- |  | 37.7 |  | 714.9 |  | 144.4 |  | 859.3
2026 |  | -- | -- |  | -- |  | 67.6 |  | 67.6 |  | -- |  | 67.6
Subtotal |  | 408 | 30753.9 |  | -- |  | 1505.7 |  | 32259.6 |  | 5795.4 |  | 38055

## Table 33
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | 299.8 |  | 299.8
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
1996 |  | -- | 45.8 |  | -- |  | -- |  | 45.8 |  | -- |  | 45.8
1997 |  | 5 | 609.6 |  | -- |  | 27.6 |  | 637.2 |  | 146.1 |  | 783.3
1998 |  | 7 | 679 |  | -- |  | 22.3 |  | 701.3 |  | 72.3 |  | 773.6
1999 |  | 7 | 605 |  | -- |  | 19.4 |  | 624.4 |  | 112.2 |  | 736.6
2000 |  | 11 | 817.4 |  | -- |  | 33 |  | 850.4 |  | 199.7 |  | 1050.1
2001 |  | 9 | 791.5 |  | -- |  | 104.3 |  | 895.8 |  | 166 |  | 1061.8
2002 |  | 9 | 685.6 |  | -- |  | 22.4 |  | 708 |  | 212.4 |  | 920.4
2003 |  | 11 | 859.1 |  | -- |  | 111.3 |  | 970.4 |  | 131.9 |  | 1102.3
2004 |  | 9 | 646.3 |  | -- |  | 59.4 |  | 705.7 |  | 166.1 |  | 871.8
2005 |  | 8 | 563.5 |  | -- |  | 111.7 |  | 675.2 |  | 310.3 |  | 985.5
2006 |  | 12 | 814.6 |  | -- |  | 137.4 |  | 952 |  | 344.4 |  | 1296.4
2007 |  | 14 | 1035.3 |  | -- |  | 204.3 |  | 1239.6 |  | 224 |  | 1463.6
2008 |  | 23 | 1492.2 |  | -- |  | 138.9 |  | 1631.1 |  | 278.3 |  | 1909.4
2009 |  | 30 | 1653.4 |  | -- |  | 62.9 |  | 1716.3 |  | 274.2 |  | 1990.5
2010 |  | 30 | 1612.6 |  | -- |  | 71.2 |  | 1683.8 |  | 277 |  | 1960.8
2011 |  | 30 | 1587.8 |  | -- |  | 26.1 |  | 1613.9 |  | 226.5 |  | 1840.4
2012 |  | 30 | 1620.8 |  | -- |  | 21.8 |  | 1642.6 |  | 223 |  | 1865.6
2013 |  | 18 | 1076.6 |  | -- |  | 24.3 |  | 1100.9 |  | 136.9 |  | 1237.8
2014 |  | 19 | 1013.4 |  | -- |  | 31.1 |  | 1044.5 |  | 119.1 |  | 1163.6
2015 |  | 19 | 1084.8 |  | -- |  | 13.2 |  | 1098 |  | 158.2 |  | 1256.2
2016 |  | 19 | 1071.4 |  | -- |  | 0.2 |  | 1071.6 |  | 77.9 |  | 1149.5
2017 |  | 16 | 898.3 |  | -- |  | 7.3 |  | 905.6 |  | 99.6 |  | 1005.2
2018 |  | 6 | 435.9 |  | -- |  | 3.1 |  | 439 |  | 70.7 |  | 509.7
2019 |  | 6 | 440.1 |  | -- |  | 5.9 |  | 446 |  | 104.4 |  | 550.4
2020 |  | 6 | 457.7 |  | -- |  | 0.4 |  | 458.1 |  | 32.1 |  | 490.2
2021 |  | 14 | 965.7 |  | -- |  | 5.2 |  | 970.9 |  | 138.1 |  | 1109
2022 |  | 14 | 978.8 |  | -- |  | 7.6 |  | 986.4 |  | 189.2 |  | 1175.6
2023 |  | 14 | 969.2 |  | -- |  | 5.9 |  | 975.1 |  | 145.6 |  | 1120.7
2024 |  | 6 | 464.5 |  | -- |  | 25.3 |  | 489.8 |  | 139.5 |  | 629.3
2025 |  | 6 | 452.7 |  | -- |  | 25.2 |  | 477.9 |  | 96.6 |  | 574.5
2026 |  | -- | -- |  | -- |  | 44.3 |  | 44.3 |  | -- |  | 44.3
Subtotal |  | 408 | 26428.6 |  | -- |  | 1373 |  | 27801.6 |  | 5172.1 |  | 32973.7

## Table 34
Cost Quantity Information 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2005 $M
1989 | -- | --
1990 | -- | --
1991 | -- | --
1992 | -- | --
1993 | -- | --
1994 | -- | --
1995 | -- | --
1996 | -- | --
1997 | 5 | 593.7
1998 | 7 | 675.2
1999 | 7 | 612.8
2000 | 11 | 800.2
2001 | 9 | 791.6
2002 | 9 | 722.8
2003 | 11 | 834.8
2004 | 9 | 670.4
2005 | 8 | 549.7
2006 | 12 | 803.9
2007 | 14 | 921
2008 | 23 | 1488.9
2009 | 30 | 1757
2010 | 30 | 1617.7
2011 | 30 | 1593
2012 | 30 | 1634.5
2013 | 18 | 1018.7
2014 | 19 | 1087.6
2015 | 19 | 1078.8
2016 | 19 | 1078.3
2017 | 16 | 917.9
2018 | 6 | 434
2019 | 6 | 441
2020 | 6 | 439.7
2021 | 14 | 965
2022 | 14 | 977.8
2023 | 14 | 988.2
2024 | 6 | 464.3
2025 | 6 | 470.1
2026 | -- | --
Subtotal | 408 | 26428.6

## Table 35
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | 21.9 |  | 21.9
2000 |  | -- | -- |  | -- |  | 19.5 |  | 19.5 |  | 21.3 |  | 40.8
2001 |  | -- | -- |  | -- |  | 26.7 |  | 26.7 |  | 22.6 |  | 49.3
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | 9.8 |  | -- |  | -- |  | 9.8 |  | 79.1 |  | 88.9
2004 |  | 2 | 147.6 |  | -- |  | -- |  | 147.6 |  | 42 |  | 189.6
2005 |  | 3 | 209.1 |  | -- |  | 7.2 |  | 216.3 |  | 113.9 |  | 330.2
2006 |  | 2 | 136.6 |  | -- |  | 18.6 |  | 155.2 |  | 94.1 |  | 249.3
2007 |  | 3 | 219.6 |  | -- |  | 9.3 |  | 228.9 |  | 156.2 |  | 385.1
2008 |  | 10 | 659.4 |  | -- |  | 7 |  | 666.4 |  | 272.4 |  | 938.8
2009 |  | 6 | 360.1 |  | -- |  | 16.4 |  | 376.5 |  | 103.4 |  | 479.9
2010 |  | 5 | 314.3 |  | -- |  | 18.8 |  | 333.1 |  | 237.9 |  | 571
2011 |  | 6 | 388.9 |  | -- |  | 15 |  | 403.9 |  | 166.3 |  | 570.2
2012 |  | 5 | 332 |  | -- |  | 4 |  | 336 |  | 62.6 |  | 398.6
2013 |  | 4 | 255 |  | -- |  | 0.5 |  | 255.5 |  | 61.8 |  | 317.3
2014 |  | 4 | 258.6 |  | -- |  | 3.2 |  | 261.8 |  | 36 |  | 297.8
2015 |  | -- | -- |  | -- |  | 15 |  | 15 |  | 3.7 |  | 18.7
2016 |  | 1 | 64.3 |  | -- |  | -- |  | 64.3 |  | 3 |  | 67.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.9 |  | 0.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.2 |  | 0.2
Subtotal |  | 51 | 3355.3 |  | -- |  | 161.2 |  | 3516.5 |  | 1499.3 |  | 5015.8

## Table 36
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | 23.6 |  | 23.6
2000 |  | -- | -- |  | -- |  | 20.7 |  | 20.7 |  | 22.7 |  | 43.4
2001 |  | -- | -- |  | -- |  | 28 |  | 28 |  | 23.8 |  | 51.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | -- | 10 |  | -- |  | -- |  | 10 |  | 81 |  | 91
2004 |  | 2 | 147.1 |  | -- |  | -- |  | 147.1 |  | 41.9 |  | 189
2005 |  | 3 | 202.2 |  | -- |  | 7 |  | 209.2 |  | 110.1 |  | 319.3
2006 |  | 2 | 128.8 |  | -- |  | 17.5 |  | 146.3 |  | 88.8 |  | 235.1
2007 |  | 3 | 201.7 |  | -- |  | 8.5 |  | 210.2 |  | 143.4 |  | 353.6
2008 |  | 10 | 595.9 |  | -- |  | 6.3 |  | 602.2 |  | 246.2 |  | 848.4
2009 |  | 6 | 320.1 |  | -- |  | 14.6 |  | 334.7 |  | 92 |  | 426.7
2010 |  | 5 | 274 |  | -- |  | 16.4 |  | 290.4 |  | 207.4 |  | 497.8
2011 |  | 6 | 333.8 |  | -- |  | 12.9 |  | 346.7 |  | 142.7 |  | 489.4
2012 |  | 5 | 280.7 |  | -- |  | 3.4 |  | 284.1 |  | 52.9 |  | 337
2013 |  | 4 | 211.2 |  | -- |  | 0.4 |  | 211.6 |  | 51.2 |  | 262.8
2014 |  | 4 | 211.3 |  | -- |  | 2.6 |  | 213.9 |  | 29.5 |  | 243.4
2015 |  | -- | -- |  | -- |  | 12.1 |  | 12.1 |  | 3 |  | 15.1
2016 |  | 1 | 50.9 |  | -- |  | -- |  | 50.9 |  | 2.4 |  | 53.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.7 |  | 0.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.2 |  | 0.2
Subtotal |  | 51 | 2967.7 |  | -- |  | 150.4 |  | 3118.1 |  | 1363.5 |  | 4481.6

## Table 37
Cost Quantity Information 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2005 $M
1999 | -- | --
2000 | -- | --
2001 | -- | --
2002 | -- | --
2003 | -- | --
2004 | 2 | 142.1
2005 | 3 | 206.7
2006 | 2 | 130.2
2007 | 3 | 185.2
2008 | 10 | 584.4
2009 | 6 | 344.5
2010 | 5 | 274.6
2011 | 6 | 334.2
2012 | 5 | 275.5
2013 | 4 | 215.7
2014 | 4 | 223.8
2015 | -- | --
2016 | 1 | 50.8
2017 | -- | --
2018 | -- | --
Subtotal | 51 | 2967.7

## Table 38
Annual Funding 0300 ¦ Procurement ¦ Procurement, Defense-Wide
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | 4 |  | 4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | 2 |  | 2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | 6.8 |  | 6.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | 15.9 |  | 15.9
2003 |  | -- | 5 |  | -- |  | -- |  | 5 |  | 36.9 |  | 41.9
2004 |  | -- | 41.9 |  | -- |  | -- |  | 41.9 |  | 35.5 |  | 77.4
2005 |  | -- | 54.5 |  | -- |  | 0.2 |  | 54.7 |  | 58.6 |  | 113.3
2006 |  | -- | 40.7 |  | -- |  | 1.9 |  | 42.6 |  | 55 |  | 97.6
2007 |  | -- | 113.9 |  | -- |  | -- |  | 113.9 |  | 79.9 |  | 193.8
2008 |  | -- | 177.5 |  | -- |  | 2.1 |  | 179.6 |  | 138.7 |  | 318.3
2009 |  | -- | 85.4 |  | -- |  | 11.6 |  | 97 |  | 29.8 |  | 126.8
2010 |  | -- | 56.1 |  | -- |  | 7.1 |  | 63.2 |  | 31.7 |  | 94.9
2011 |  | -- | 57.3 |  | -- |  | 9.1 |  | 66.4 |  | 37.2 |  | 103.6
2012 |  | -- | 57.1 |  | -- |  | 8.6 |  | 65.7 |  | 34 |  | 99.7
2013 |  | -- | 59.1 |  | -- |  | 3.8 |  | 62.9 |  | 30.3 |  | 93.2
2014 |  | -- | 61.6 |  | -- |  | 4.5 |  | 66.1 |  | 25.9 |  | 92
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 18 |  | -- |  | -- |  | 18 |  | -- |  | 18
Subtotal |  | -- | 828.1 |  | -- |  | 48.9 |  | 877 |  | 622.2 |  | 1499.2

## Table 39
Annual Funding 0300 ¦ Procurement ¦ Procurement, Defense-Wide
Fiscal Year | Quantity |  | BY 2005 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | 4.3 |  | 4.3
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | 2.1 |  | 2.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | 7.2 |  | 7.2
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | 16.5 |  | 16.5
2003 |  | -- | 5.1 |  | -- |  | -- |  | 5.1 |  | 37.6 |  | 42.7
2004 |  | -- | 41.5 |  | -- |  | -- |  | 41.5 |  | 35.2 |  | 76.7
2005 |  | -- | 52.5 |  | -- |  | 0.2 |  | 52.7 |  | 56.5 |  | 109.2
2006 |  | -- | 38.2 |  | -- |  | 1.8 |  | 40 |  | 51.7 |  | 91.7
2007 |  | -- | 104.8 |  | -- |  | -- |  | 104.8 |  | 73.6 |  | 178.4
2008 |  | -- | 160.9 |  | -- |  | 1.9 |  | 162.8 |  | 125.6 |  | 288.4
2009 |  | -- | 76.4 |  | -- |  | 10.4 |  | 86.8 |  | 26.6 |  | 113.4
2010 |  | -- | 49.3 |  | -- |  | 6.2 |  | 55.5 |  | 27.9 |  | 83.4
2011 |  | -- | 49.6 |  | -- |  | 7.9 |  | 57.5 |  | 32.1 |  | 89.6
2012 |  | -- | 48.6 |  | -- |  | 7.3 |  | 55.9 |  | 28.9 |  | 84.8
2013 |  | -- | 49.7 |  | -- |  | 3.2 |  | 52.9 |  | 25.4 |  | 78.3
2014 |  | -- | 51.1 |  | -- |  | 3.7 |  | 54.8 |  | 21.5 |  | 76.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | 14.5 |  | -- |  | -- |  | 14.5 |  | -- |  | 14.5
Subtotal |  | -- | 742.2 |  | -- |  | 42.6 |  | 784.8 |  | 572.7 |  | 1357.5

## Table 40
Cost Quantity Information 0300 ¦ Procurement ¦ Procurement, Defense-Wide
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2005 $M
1999 | -- | --
2000 | -- | --
2001 | -- | --
2002 | -- | --
2003 | -- | --
2004 | -- | 40
2005 | -- | 56.4
2006 | -- | 38.2
2007 | -- | 46.2
2008 | -- | 215
2009 | -- | 79.6
2010 | -- | 49.4
2011 | -- | 49.7
2012 | -- | 49.9
2013 | -- | 50.3
2014 | -- | 53
2015 | -- | --
2016 | -- | 14.5
Subtotal | -- | 742.2

## Table 41
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2003 0.8
2004 10.9
2005 14.5
2006 22.4
2007 --
2008 --
2009 --
2010 7.2
2011 --
2012 6.2
2013 --
2014 --
2015 --
2016 --
2017 12.4
Subtotal 74.4

## Table 42
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2005 $M
Total Program
2003 0.8
2004 10.8
2005 13.9
2006 21.0
2007 --
2008 --
2009 --
2010 6.2
2011 --
2012 5.2
2013 --
2014 --
2015 --
2016 --
2017 9.6
Subtotal 67.5

## Table 43
Annual Funding 0500 ¦ MILCON ¦ Military Construction, Defense-Wide
Fiscal Year | TY $M
Total Program
2000 | 0.2
2001 | 0.3
2002 | 8.5
2003 | 1.9
2004 | --
2005 | --
2006 | 1.8
2007 | 1.9
2008 | 0.7
2009 | 7.9
2010 | 11.6
2011 | --
2012 | --
2013 | 6.5
Subtotal | 41.3

## Table 44
Annual Funding 0500 ¦ MILCON ¦ Military Construction, Defense-Wide
Fiscal Year | BY 2005 $M
Total Program
2000 | 0.2
2001 | 0.3
2002 | 8.8
2003 | 1.9
2004 | --
2005 | --
2006 | 1.7
2007 | 1.7
2008 | 0.6
2009 | 7
2010 | 10
2011 | --
2012 | --
2013 | 5.4
Subtotal | 37.6

## Table 45
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1997-04-25 | 2002-05-06
Approved Quantity | 25 | 58
Reference | LRIP ADM | Program Restructure ADM
Start Year | 1997 | 1997
End Year | 2001 | 2009
The Current Total LRIP Quantity is more than 10% of the total production quantity due to a program restructure with the May 2002 ADM which authorized additional LRIP aircraft.

## Table 46
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Japan 6/12/2015 5 556.0 FMS Case JA-P-SCH: Procurement of five V-22 aircraft, unique Japan communications equipment, development, and associated logistics support for long lead requirements.
Japan 8/22/2014 1.0 FMS Case JA-P-FXQ: Studies and Analysis of the V
-22 Program to refine requirements for future aircraft procurement and conduct site assessments in Japan.
Israel 11/21/2013 1.3 FMS Case IS-P-GOY-A1: Studies and Analysis of the V-22 Program to refine requirements for future aircraft procurement and conduct site assessments in Israel.
Notes
Nuclear Costs
None

## Table 47
Unit Cost
Unit Cost Report
Item |  | BY 2005 $M | BY 2005 $M |  | % Change
|  | Current UCR Baseline (Oct 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 50250.4 |  |  | 51405
Quantity | 458 |  |  | 461
Unit Cost | 109.717 |  |  | 111.508 |  | 1.63
Average Procurement Unit Cost
Cost | 38562.8 |  |  | 38812.8
Quantity | 456 |  |  | 459
Unit Cost | 84.568 |  |  | 84.559 |  | -0.01
Item |  | BY 2005 $M | BY 2005 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Sep 2005 APB)
Program Acquisition Unit Cost
Cost | 50250.4 |  |  | 51405
Quantity | 458 |  |  | 461
Unit Cost | 109.717 |  |  | 111.508 |  | 1.63
Average Procurement Unit Cost
Cost | 38562.8 |  |  | 38812.8
Quantity | 456 |  |  | 459
Unit Cost | 84.568 |  |  | 84.559 |  | -0.01

## Table 48
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2005 $M | [7 empty] | TY $M
[12 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Feb 1988 | [6 empty] | 41.101 |  |  |  |  | 35.309 |  |  |  | 34.657 |  |  |  | 30.541
APB as of January 2006 |  |  |  |  | Sep 2005 | [6 empty] | 109.717 |  |  |  |  | 84.568 |  |  |  | 116.274 |  |  |  | 94.516
Revised Original APB |  |  |  |  | Sep 2005 | [6 empty] | 109.717 |  |  |  |  | 84.568 |  |  |  | 116.274 |  |  |  | 94.516
Prior APB |  |  |  |  | Feb 2008 | [6 empty] | 109.717 |  |  |  |  | 84.568 |  |  |  | 116.274 |  |  |  | 94.516
Current APB |  |  |  |  | Oct 2011 | [6 empty] | 109.717 |  |  |  |  | 84.568 |  |  |  | 116.274 |  |  |  | 94.516
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 110.059 |  |  |  |  | 83.28 |  |  |  | 119.039 |  |  |  | 95.207
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 111.508 |  |  |  |  | 84.559 |  |  |  | 121.176 |  |  |  | 97.102
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  |  |  | Spt |  | Total
40.180 -12.793 50.391 -4.762 8.157 30.121 0.000 4.980 76.094 116.274
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  |  | Oth |  |  | Spt |  |  | Total
116.274 -1.169 -0.280 5.513 1.913 -1.909 0.000 0.834 4.902 121.176

## Table 49
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [12 empty] | APUC Production Estimate
| Econ |  | Qty |  |  | Sch |  | Eng | Est | Oth | Spt | Total
36.641 -12.349 47.964 -4.862 5.134 16.986 0.000 5.002 57.875 94.516
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [12 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est | Oth | Spt |  | Total
94.516 -1.174 -0.140 5.537 0.466 -2.941 0.000 0.838 2.586 97.102
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  |  |  | Dec 1982 |  |  |  | Dec 1982 |  |  | Dec 1982 |  |  |  | Dec 1982
Milestone II |  |  |  | May 1985 |  |  |  | Apr 1986 |  |  | Apr 1986 |  |  |  | Apr 1986
Milestone III |  |  |  | Jul 1989 |  |  |  | N/A |  |  | Oct 2005 |  |  |  | Oct 2005
IOC |  |  |  | Dec 1991 |  |  |  | N/A |  |  | Mar 2007 |  |  |  | Jun 2007
Total Cost (TY $M) |  |  |  | 24467 |  |  |  | 29662.3 |  |  | 53253.4 |  |  |  | 55862.3
Total Quantity |  |  |  | 609 |  |  |  | 919 |  |  | 458 |  |  |  | 461
PAUC |  |  |  | 40.176 |  |  |  | 32.277 |  |  | 116.274 |  |  |  | 121.176

## Table 50
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 9891.7 | 43099.3 | 262.4 | 53253.4
Previous Changes
Economic | 6.7 | -417.8 | -0.1 | -411.2
Quantity | -- | 145.5 | -- | 145.5
Schedule | -- | 2222.1 | -- | 2222.1
Engineering | 639.2 | 213.4 | -- | 852.6
Estimating | 508.3 | -1551.7 | -155 | -1198.4
Other | -- | -- | -- | --
Support | -- | -106 | -- | -106
Subtotal | 1154.2 | 505.5 | -155.1 | 1504.6
Current Changes
Economic | -6.6 | -121.1 | -0.1 | -127.8
Quantity | -- | 74 | -- | 74
Schedule | -- | 319.6 | -- | 319.6
Engineering | 29 | 0.4 | -- | 29.4
Estimating | 108.3 | 201.7 | 8.5 | 318.5
Other | -- | -- | -- | --
Support | -- | 490.6 | -- | 490.6
Subtotal | 130.7 | 965.2 | 8.4 | 1104.3
Total Changes | 1284.9 | 1470.7 | -146.7 | 2608.9
CE - Cost Variance | 11176.6 | 44570 | 115.7 | 55862.3
CE - Cost & Funding | 11176.6 | 44570 | 115.7 | 55862.3

## Table 51
Summary BY 2005 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 11446.5 | 38562.8 | 241.1 | 50250.4
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | 118.6 | -- | 118.6
Schedule | -- | 1141.3 | -- | 1141.3
Engineering | 481 | 157.3 | -- | 638.3
Estimating | 458.8 | -1686.2 | -142.6 | -1370
Other | -- | -- | -- | --
Support | -- | -151.4 | -- | -151.4
Subtotal | 939.8 | -420.4 | -142.6 | 376.8
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | 58.6 | -- | 58.6
Schedule | -- | 143.7 | -- | 143.7
Engineering | 22.8 | 0.3 | -- | 23.1
Estimating | 78 | 141.6 | 6.6 | 226.2
Other | -- | -- | -- | --
Support | -- | 326.2 | -- | 326.2
Subtotal | 100.8 | 670.4 | 6.6 | 777.8
Total Changes | 1040.6 | 250 | -136 | 1154.6
CE - Cost Variance | 12487.1 | 38812.8 | 105.1 | 51405
CE - Cost & Funding | 12487.1 | 38812.8 | 105.1 | 51405
Previous Estimate: December 2014

## Table 52
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -6.6
Addition of V-22 Electrical System Re-Design (Navy). (Engineering) |  | 7.2 | 9.2
Addition of V-22 RBA recovery (Navy). (Engineering) |  | 15.6 | 19.8
Revised estimate for V-22 Aerial Refueling System development (Navy). (Estimating) |  | 15.7 | 19.8
Revised estimate for MV-22 Digital Interoperability (Navy). (Estimating) |  | 34.4 | 45
Revised estimate for Follow-On Test and Evaluation (FOT&E) (Navy). (Estimating) |  | 3.6 | 6.3
Revised estimate for FOT&E (Air Force). (Estimating) |  | 3.4 | 4.5
Revised estimate for Silent Night Radar (DoD). (Estimating) |  | 15.6 | 19.8
Revised estimate for Digital Interoperability (Air Force). (Estimating) |  | 29.6 | 43.1
Revised estimate to reflect actuals (Navy). (Estimating) |  | -16.5 | -20.4
Revised estimate to reflect actuals (Air Force). (Estimating) |  | -9.4 | -11.5
Adjustment for current and prior escalation. (Estimating) |  | 1.6 | 1.7
RDT&E Subtotal |  | 100.8 | 130.7
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -121.1
Total Quantity variance resulting from an increase of one aircraft from 50 to 51 (Air Force). (Subtotal)
Quantity variance resulting from an increase of one aircraft from 50 to 51 (Air Force). (Quantity)
+61.1 +77.2
(+58.6) (+74.0)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+3.4) (+4.3) Allocation to Engineering resulting from Quantity change. (Engineering) (QR) (+0.3) (+0.4) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-1.2) (-1.5)
Stretch-out of procurement buy profile from FY 2017-FY 2023 to FY 2017-FY 2025 (Navy). (Schedule)
Additional schedule variance due to the procurement buy profile from FY 2017-FY 2023 to FY 2017-FY 2025 (Navy). (Schedule)
0.0 +99.9
+140.3 +215.4
Revised estimate to reflect Multi-Year Procurement II contract prices (Navy). (Estimating) +17.3 +21.4
Increase due to FY 2018 Single-Year Procurement vice Multi-Year Procurement assumption (Navy). (Estimating)
+37.8 +49.2
Revised estimate for the C/MV-22 Navy variant unique items (Navy). (Estimating) +0.4 +5.2
Increase attributed to Government Furnished Equipment, Engine, Ancillary, and Non- Recurring cost estimate updates (Navy). (Estimating)
Adjustment for Annual Advanced Procurement due to estimating changes (Navy). (Estimating)
+60.8 +87.8
-6.4 -1.0
Additional variance resulting from an increase of one aircraft (Air Force). (Estimating) | -10.2 |  |  | -12.9
Additional variance resulting from an increase of one aircraft (DoD). (Estimating) | 14.5 |  |  | 18
Revised estimate to reflect actuals (Air Force). (Estimating) | -3.2 |  |  | -3.8
Adjustment for current and prior escalation. (Estimating) | 31.8 |  |  | 39.3
Adjustment for current and prior escalation. (Support) | 4.6 |  |  | 5.1
Increase in Other Support due to revised estimate of Support Equipment, Peculiar Training | 95.5 |  |  | 156.3

## Table 53
Equipment, Technical Publications, Production Engineering Support, and Other Integrated Logistics Support (Navy). (Support)
Increase in Other Support due to revised estimate of Production Engineering Support for an increase of one aircraft (Air Force). (Support)
+0.2 +0.3
Increase in Other Support to reflect actuals (DoD). (Support) 0.0 +0.1
Increase in Initial Spares due to revised spares requirement based on current projections for C/MV-22 Navy variant (Navy). (Support)
Increase in Initial Spares to reflect actuals and to update remaining Spares requirements based on current projections (Air Force). (Support)
+225.3 +328.2
+0.6 +0.7
Decrease in Initial Spares to reflect actuals (DoD). (Support) 0.0 -0.1
Procurement Subtotal +670.4 +965.2
(QR) Quantity Related
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -0.1
Revised estimate for LHD Pad Conversion and MV-22 LZ Improvements (Navy). (Estimating)
+6.5 +8.4
Adjustment for current and prior escalation. (Estimating) +0.1 +0.1
MILCON Subtotal +6.6 +8.4

## Table 54
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: V22 MYP2 Year 1 (FY13 Lot 17)
Contractor: Bell-Boeing JPO
Contractor Location: 401 Tiltrotor Drive
Amarillo, TX 79111
Contract Number: N00019-12-C-2001/1
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 29, 2011
Definitization Date: June 12, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
81.9 N/A 21 1411.3 1485.6 22 1174.0 1178.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the initial contract price reflecting the value of advance procurement funded items only. The current contract price reflects the full airframe value, as well as additional required Engineering Change Proposals.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) +9.4 -8.6
Previous Cumulative Variances -1.5 -67.4
Net Change +10.9 +58.8
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to favorable material costs and efficiencies on the production line.
The favorable net change in the schedule variance is due to production line schedule recovery.
Notes
The quantity increase is due to a Congressional add for combat-loss replacement aircraft.
Contract N0001912C2001 was initially awarded on December 29, 2012 with Lot 17 Advance Procurement Long Lead Items. Lot 17 aircraft were added and the Multi-Year Procurement was definitized with a modification to this contract on June 12, 2013.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 55
Contract Identification
Appropriation: Procurement
Contract Name: V22 MYP2 Year 2 (FY14 Lot 18)
Contractor: Bell-Boeing JPO
Contractor Location: 401 Tiltrotor Drive
Amarillo, TX 79111
Contract Number: N00019-12-C-2001/2
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 17, 2013
Definitization Date: December 17, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1000.6 N/A 22 1474.6 1552.2 23 1255.4 1240.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the initial contract price reflecting the value of advance procurement funded items only. The current contract price reflects the full airframe value, as well as additional required Engineering Change Proposals.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) -20.6 -82.9
Previous Cumulative Variances -2.2 -27.3
Net Change -18.4 -55.6
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to higher material cost associated with two work breakdown structure elements.
The unfavorable net change in the schedule variance is due to inventory being awarded but not issued to the production line because operations behind schedule.
Notes
CV-22 Option 0107 was exercised, adding one more aircraft to Lot 18.

## Table 56
Contract Identification
Appropriation: Procurement
Contract Name: V-22 AE 1107C Turboshaft Engine
Contractor: Rolls Royce
Contractor Location: 2355 S. Tibbs Avenue
Indianapolis, IN 46206-0420
Contract Number: N00019-12-C-0007
Contract Type: Firm Fixed Price (FFP)
Award Date: March 30, 2012
Definitization Date: March 30, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
150.9 N/A 70 404.5 N/A 182 404.5 404.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the initial contract price reflecting the value of the base year award. The current contract price represents the sum of the base year award plus the sum of the three options.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
The engine contract provides for a base year and four option years for procurement of engines for production install and spares FY 2012 through FY 2016 requirements for the MV-22 and CV-22 weapons systems. To date, the base year (FY 2012) was awarded and the first three options (FY 2013, FY 2014, and FY 2015) have been exercised. This contract is a Commercial Federal Acquisition Regulation Part 12 contract.

## Table 57
Contract Identification
Appropriation: Acq O&M
Contract Name: JPBL 1 Year 7
Contractor: Bell-Boeing JPO
Contractor Location: 401 Tilt Rotor Drive
Amarillo, TX 79111
Contract Number: N00019-09-D-0008/882 Contract Type: Cost Plus Incentive Fee (CPIF) Award Date: November 20, 2014
Definitization Date: November 20, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
119.0 N/A N/A 119.0 N/A N/A 100.7 105.6
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/7/2016) +3.5 -0.1
Previous Cumulative Variances -- --
Net Change +3.5 -0.1
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to actual logistics support requirements under predicted estimates resulting in a potential underrun.
The unfavorable cumulative schedule variance is due to a slight delay in completion of tasking.
Notes
This is the first time this contract is being reported.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 58
Contract Identification
Appropriation: Acq O&M
Contract Name: JPBL ll
Contractor: Bell-Boeing
Contractor Location: 404 Tilt Rotor Drive
Amarillo, TX 79111
Contract Number: N00019-09-D-0008/6
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: October 04, 2012
Definitization Date: October 04, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
193.3 N/A N/A 291.0 N/A N/A 421.0 257.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a contract modification to fund a cost overrun caused by increased Fleet demand for parts and blade repairs.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/7/2016) -46.8 +28.8
Previous Cumulative Variances -- --
Net Change -46.8 +28.8
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to the fact that Fleet demand for parts and blade repairs have been higher than the baseline plan.
The favorable cumulative schedule variance is due to completion of required tasking sooner than planned.
Notes
This is the first time this contract is being reported.

## Table 59
Contract Identification
Appropriation: Procurement
Contract Name: V-22 MYP2 Year 3 (FY15 Lot 19)
Contractor: Bell-Boeing JPO
Contractor Location: 401Tilt Rotor Drive
Amarillo, TX 79111
Contract Number: N00019-12-C-2001/19
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: December 22, 2014
Definitization Date: December 22, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1220.8 1285.1 19 1222.2 1286.5 19 1018.8 1072.1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications to incorporate required Engineering Change Proposals.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/7/2016) +0.9 -26.5
Previous Cumulative Variances -- --
Net Change +0.9 -26.5
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to lower material costs than planned.
The unfavorable cumulative schedule variance is due to inventory being available but not issued to the production line because of operations behind schedule.
Notes
This is the first time this contract is being reported.

## Table 60
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 2 | 2 | 2 | 100%
Production | 329 | 329 | 459 | 71.68%
Total Program Quantity Delivered | 331 | 331 | 461 | 71.8%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
55862.3
39962.1
71.54%
46
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
35
76.09%
44885.8
80.35%
The above data is current as of February 26, 2016.

## Table 61
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 12, 2016
Source of Estimate: POE
Quantity to Sustain: 452
Unit of Measure: Aircraft
Service Life per Unit: 25.00 Years
Fiscal Years in Service: FY 2001 - FY 2054
The O&S cost estimate does not include the 2 developmental aircraft, 4 HX-21 aircraft, and 2 test aircraft. The estimate also does not include the plus-up aircraft added in the FY 2017 PB.
| MV-22 | Navy MV-22 | CV-22
Aircraft Service Life (hrs) | 10000 | 10000 | 10000
Aircraft Attrition Rate | 0.6% | 1% | 0.6%
Aircraft Pipeline Rate | 13.3% | 10% | 8%
Total Aircraft Inventory (TAI) | 360 | 48 | 50
Primary Authorized Aircraft (PAA) | 276 | 36 | 50
Flight Hour per Month | 35 | 35 | 36
Flight Hours per Year | 420 | 420 | 432
Total Aircraft Operating Years | 7744 | 948 | 1082
Sustainment Strategy
The V-22 Program Office is executing a Joint Sustainment Strategy that provides the product support elements for the Marine Corps MV-22, Air Force CV-22 fleets and Navy CMV-22. The sustainment strategy addresses all three levels of maintenance (Organizational, Intermediate and Depot). The cornerstones of the Joint Sustainment Strategy are the Performance Based Agreements (PBA) between the Program Office and the war fighters. The PBAs clearly define the war fighter's product support requirements to be achieved through the execution of the V-22 Joint Sustainment Strategy. The Joint Sustainment Strategy is executed via a myriad of processes and organizations to include DoD organic activities and commercial contractors. Multiple Performance Based Logistics contracts are used to support the V-22 Program.

## Table 62
Antecedent Information
The V-22s antecedent aircraft are the CH-46E Sea Knight, CH-53D Sea Stallion, MH-53J/M Pave Low, and the C-2A Greyhound aircraft.
The CH-46E Sea Knight's O&S costs were used as the basis for the V-22 antecedent aircraft costs. The largest number of V-22s being procured (360 MV-22s) are being used to replace the CH-46E aircraft. The antecedent cost is based on the CH-46E's 3-year average (1999-2001) O&S cost data extracted from Visibility and Management of Operating and Support Costs (VAMOSC) database for the 229 aircraft reported on during that time. Since VAMOSC does not capture Indirect Support costs, the CH-46E Indirect Support cost is calculated by multiplying the CH-46E Unit-Level Manpower by the ratio of V-22 Indirect Support to V-22 Unit-Level Manpower. The data was normalized to BY05$M.
Annual O&S Costs BY2005 $M
Cost Element |  | V-22 Average Annual Cost Per Aircraft | [5 empty] | CH-46E (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  | 1.448 | [5 empty] | 0.449
Unit Operations |  | 0.298 | [5 empty] | 0.058
Maintenance |  | 4.488 | [5 empty] | 1.227
Sustaining Support |  | 0.533 | [5 empty] | 0.038
Continuing System Improvements |  | 0.655 | [5 empty] | 0.182
Indirect Support |  | 0.764 | [5 empty] | 0.22
Other |  | -- | [5 empty] | --
Total |  | 8.186 | [5 empty] | 2.174
Item | Total O&S Cost $M
| V-22 | [7 empty] | CH-46E (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 75022.5 |  |  | 82524.8 |  |  | 80032.1 |  | 20782.3
Then Year | 121543.7 |  |  | N/A |  |  | 125049.3 |  | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
Average Annual O&S Cost per Aircraft = Total O&S Cost / (MV-22 USMC operating years + MV-22 Navy operating years
+ CV-22 operating years)
O&S Cost Variance
Category |  |  | BY 2005 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 72098.9
2014 SAR

## Table 63
Programmatic/Planning Factors 2305.8 PB17 Flight Hours, updated CMV-22 delivery schedule,
updated CMV-22 squadron standup, additional MV-22 squadrons, manpower estimate update, attrition rate change.
Cost Estimating Methodology 0.0
Cost Data Update 6137.6 Updated reliabilities of Aviation Depot Level Repairables and Aviation Fleet Maintenance parts, FY 2016 pricing (24% APC), updated actuals, FY 2015 fuel consumption, indirect rates update.
Labor Rate -387.9 FY 2016 Labor Rates
Energy Rate -122.3 Fuel rate decrease
Technical Input 0.0
Other 0.0
Total Changes 7933.2
Current Estimate 80032.1
Disposal Estimate Details
Date of Estimate: January 12, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2005 $M): Total costs for disposal of all Aircraft are 98.4