## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-429
VH-92A Presidential Helicopter (VH-92A)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 21
Unit Cost 22
Cost Variance 25
Contracts 28
Deliveries and Expenditures 29
Operating and Support Cost 30

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
VH-92A Presidential Helicopter (VH-92A)
DoD Component
Navy
Responsible Office
Col Robert Pridgen
PMA274 Presidential Helicopters Program
Program Executive Office - Air, Anti-Submarine Warfare, Assault & Special Mission
48202 Bronson Road, Building 2805 Patuxent River, MD 20670-1547
robert.d.pridgen@navy.mil
Phone: 301-757-5782
Fax: 301-757-7999
DSN Phone: DSN Fax:
Date Assigned: July 2, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 17, 2014
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 17, 2014

## Table 6
Mission and Description
The VH-92A Presidential Helicopter (VH-92A) program mission is to provide safe, reliable, and timely transportation for the President, Vice President, Foreign Heads of State, and other official parties as directed by the Director of the White House Military Office. Presidential helicopter transportation requirements are executed by Marine Helicopter Squadron One (HMX-
1) and support the President worldwide and the Vice President primarily inside the National Capital Region. Mission tasking encompasses two (2) main types of missions, administrative lift (Mission Tasking 1) and contingency operations (Mission Tasking 2). The VH-92A platform will replace both In-Service aircraft (VH-3D and VH-60N) and is based on Sikorsky’s commercial S-92A helicopter. The acquisition strategy for the VH-92A program involves integration of mature government- defined mission systems and an executive interior into the existing S-92A air vehicle.

## Table 7
Executive Summary
The VH-92A program completed a Milestone B DAB review in March 2014. The MDA approved the VH-92A program to enter the EMD phase in an ADM dated April 17, 2014. On April 17, 2014, the USD(AT&L) certified (with one waiver) the provisions set forth in section 2366b of title 10, United States Code (USC). Provision (2) of that section was waived in accordance with subsection (d) of the statute. On January 29, 2016, the USD(AT&L) certified that the VH-92A program met the certification requirement for provision (2) pursuant to section 2366b of title 10, USC. There are no remaining 2366b waivers associated with this program.
A Fixed Price Incentive Firm contract was competitively awarded to Sikorsky Aircraft Corporation on May 7, 2014. A total quantity of 23 aircraft will be procured, consisting of 21 operational aircraft and 2 test aircraft. In August 2015, the VH-92A program conducted a System Level Preliminary Design Review (PDR). In September 2015, early risk reduction testing was completed at Lockheed Martin's facility in Owego, NY including co-site testing. Engineering Development Model (EDM) 1 and EDM 2 are currently in modification at Sikorsky's facility in Stratford, CT. Mission Communications System development and integration efforts continue at Naval Air Systems Command in St. Inigoes, MD and Lockheed Martin, Owego, NY. In addition, Live Fire Test and Evaluation efforts have commenced. The program conducted an In-Process Review with the MDA on March 7, 2016. System Level Critical Design Review is planned for 4th Quarter FY 2016.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Materiel Development Decision | Jun 2010 | Jun 2010 | Jun 2010 | Jun 2010
Pre-EMD | Mar 2013 | Mar 2013 | Mar 2013 | Mar 2013
Milestone B | Mar 2014 | Mar 2014 | Sep 2014 | Apr 2014
Critical Design Review | Jul 2016 | Jul 2016 | Jan 2017 | Jul 2016
Milestone C | Jan 2019 | Jan 2019 | Jul 2019 | Jan 2019
IOT&E Complete | Mar 2020 | Mar 2020 | Sep 2020 | Mar 2020
IOC | Jul 2020 | Jul 2020 | Jan 2021 | Jul 2020
FRP Decision | May 2021 | May 2021 | Nov 2021 | May 2021
Full Operational Capability | Jul 2022 | Jul 2022 | Jan 2023 | Jul 2022
Change Explanations
Acronyms and Abbreviations
IOT&E - Initial Operational Test & Evaluation

## Table 10
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Passenger Seating and Lift Capacity
(Objective= Threshold) MT-1: 14 passengers MT-2 | (Objective= Threshold) MT-1: 14 passengers MT-2 | MT-1: 12 passengers MT-2: 14 passengers | TBD | MT-1: 12 passengers MT-2: 14 passengers
Range (Operational Day)
MT-1 NCR, NCR Return: >100 NM MT-1 CONUS/OCONUS: >200 NM MT-2: >300 NM | MT-1 NCR, NCR Return: >100 NM MT-1 CONUS/OCONUS: >200 NM MT-2: >300 NM | MT-1 NCR, NCR Return: >50 NM MT-1 CONUS/OCONUS: >150 NM MT-2: >250 NM | TBD | MT-1 NCR, NCR Return: >50 NM MT-1 CONUS/OCONUS: >150 NM MT-2: >250 NM
Hover Performance
HOGE with mission payload and other required equipment (High Hot Day) | HOGE with mission payload and other required equipment (High Hot Day) | HOGE with mission payload and other required equipment (Operational Day) | TBD | HOGE with mission payload and other required equipment (Operational Day)
Transportability
(Objective= Threshold) MT-2: (1) MT-2 aircraft and all required equipment, personnel (29), and SE necessary to execute deployed maintenance and mission requirements shall be transportable using (1) C-17. | (Objective= Threshold) MT-2: (1) MT-2 aircraft and all required equipment, personnel (29), and SE necessary to execute deployed maintenance and mission requirements shall be transportable using (1) C-17. | MT-2: (1) MT-2 aircraft and all required equipment, personnel (29), and SE necessary to execute deployed maintenance and mission requirements shall be transportable using (1) C-17. | TBD | MT-2: (1) MT-2 aircraft and all required equipment, personnel (29), and SE necessary to execute deployed maintenance and mission requirements shall be transportable using (1) C-17.
Landing Zone Suitability
(Objective= Threshold) Maintain at least a 50 foot obstacle clearance during all phases of approach, landing, take- off, and departure from the existing White House South Lawn. | (Objective= Threshold) Maintain at least a 50 foot obstacle clearance during all phases of approach, landing, take- off, and departure from the existing White House South Lawn. | Maintain at least a 50 foot obstacle clearance during all phases of approach, landing, take -off, and departure from the existing White House South Lawn. | TBD | Maintain at least a 50 foot obstacle clearance during all phases of approach, landing, take -off, and departure from the existing White House South Lawn.
Sustainment: Materiel Availability - Am, Operational Availability -Ao
Am ≥ 59% MT-1: Ao ≥ 85% MT-2: Ao ≥ 85% | Am ≥ 59% MT-1: Ao ≥ 85% MT-2: Ao ≥ 85% | Am ≥ 57% MT-1: Ao ≥ 80% MT-2: Ao ≥ 83% | TBD | Am ≥ 57% MT-1: Ao ≥ 80% MT-2: Ao ≥ 83%
Training

## Table 11
(Objective= Threshold) Reduce the overall time to train for pilots and crew chiefs from current In-Service aircraft time to train utilizing a Systems Approach to Training. | (Objective= Threshold) Reduce the overall time to train for pilots and crew chiefs from current In-Service aircraft time to train utilizing a Systems Approach to Training. | Reduce the overall time to train for pilots and crew chiefs from current In-Service aircraft time to train utilizing a Systems Approach to Training. | TBD | Reduce the overall time to train for pilots and crew chiefs from current In-Service aircraft time to train utilizing a Systems Approach to Training.
Net-Ready
(Objective= Threshold) | (Objective= Threshold) | Support net-centric | TBD | Support net-centric
Support net-centric | Support net-centric | military operations |  | military operations
military operations Enter | military operations Enter | Enter and be managed |  | Enter and be managed
and be managed on the | and be managed on the | on the network |  | on the network
network Exchanges | network Exchanges | Exchanges information. |  | Exchanges information.
information. | information.
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Development Document (CDD) dated January 3, 2013
Change Explanations
None
Notes
With Joint Staff (J-4) concurrence and as documented in the CDD, the Energy KPP required by the Joint Capabilities Integration Development System Manual is not applicable to VH-92A.
Net Ready KPP Products are detailed in the CDD, Appendix A.
The VH-92A program was planned and budgeted to the performance threshold.
Acronyms and Abbreviations
Am - Materiel Availability Ao - Operational Availability
CONUS - Continental United States HOGE - Hover out of Ground Effect
MT-1 - Mission Tasking 1 (administrative lift)
MT-2 - Mission Tasking 2 (contingency operations) NCR - National Capital Region
NM - Nautical Mile
OCONUS - Outside the Continental United States SE - Support Equipment

## Table 12
Track to Budget
RDT&E
Appn | BA | PE
Navy 1319 05 0604273N
Project Name
3300 Presidential Helicopter (VH-92A) 3390 VH-92A Improvements
Procurement
Appn | BA | PE
Navy 1506 04 0901212M
Line Item Name
0455 VH-92A Executive Helo Navy 1506 06 0901212M
Line Item Name
0605 Spares for VXX

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2014 $M | [6 empty] | BY 2014 $M |  | TY $M
| SAR Baseline Development Estimate |  |  | Current APB Development Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Development Estimate |  |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 2606.1 |  |  | 2606.1 | 2866.7 |  |  | 2421.6 |  | 2805.7 |  |  | 2805.7 |  | 2571.8
Procurement |  | 2043.6 |  |  | 2043.6 | 2248 |  |  | 2205 |  | 2379 |  |  | 2379 |  | 2516.4
Flyaway |  | -- |  |  | -- | -- |  |  | 1501.3 |  | -- |  |  | -- |  | 1712.3
Recurring |  | -- |  |  | -- | -- |  |  | 1501.3 |  | -- |  |  | -- |  | 1712.3
Non Recurring |  | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
Support |  | -- |  |  | -- | -- |  |  | 703.7 |  | -- |  |  | -- |  | 804.1
Other Support |  | -- |  |  | -- | -- |  |  | 269.8 |  | -- |  |  | -- |  | 309.2
Initial Spares |  | -- |  |  | -- | -- |  |  | 433.9 |  | -- |  |  | -- |  | 494.9
MILCON |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 4649.7 |  |  | 4649.7 | N/A |  |  | 4626.6 |  | 5184.7 |  |  | 5184.7 |  | 5088.2
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current APB cost estimate provides sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk and external interference. It is consistent with average resource expenditures on historical efforts of similar size, scope, and complexity and represents a notional 50% confidence level.
Total Quantity
Quantity |  |  | SAR Baseline Development Estimate |  |  |  | Current APB Development |  |  |  |  | Current Estimate
RDT&E |  |  | 6 |  |  |  | 6 |  |  |  |  | 6
Procurement |  |  | 17 |  |  |  | 17 |  |  |  |  | 17
Total |  |  | 23 |  |  |  | 23 |  |  |  |  | 23

## Table 14
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 651.4 | 507.1 |  | 338.4 |  | 478.4 | 288.2 |  | 189.9 |  | 54.5 |  | 63.9 |  | 2571.8
Procurement | 0 | 0 |  | 0 |  | 0 | 845.8 |  | 854.8 |  | 815.8 |  | 0 |  | 2516.4
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 651.4 | 507.1 |  | 338.4 |  | 478.4 | 1134 |  | 1044.7 |  | 870.3 |  | 63.9 |  | 5088.2
PB 2016 Total | 662.9 | 507.1 |  | 589.7 |  | 481.7 | 1089 |  | 913.1 |  | 782 |  | 139 |  | 5164.5
Delta | -11.5 | 0 |  | -251.3 |  | -3.3 | 45 |  | 131.6 |  | 88.3 |  | -75.1 |  | -76.3
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 6 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 6
Production | 0 |  | 0 |  | 0 | 0 | 0 |  | 6 |  | 6 | 5 |  | 0 |  | 17
PB 2017 Total | 6 |  | 0 |  | 0 | 0 | 0 |  | 6 |  | 6 | 5 |  | 0 |  | 23
PB 2016 Total | 6 |  | 0 |  | 0 | 0 | 0 |  | 6 |  | 6 | 5 |  | 0 |  | 23
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 73.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 92.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 356.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 507.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 338.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 478.4
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 288.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 189.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.5
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.4
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.5
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.4
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.6
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.8
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.2
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.5
Subtotal |  | 6 | -- |  | -- |  | -- |  | -- |  | -- |  | 2571.8

## Table 16
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 76
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59.6
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 347.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 486.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 318.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 442.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 261.2
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.5
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.3
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.3
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2025 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2026 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.2
2027 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
2028 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
2029 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.6
2030 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4
Subtotal |  | 6 | -- |  | -- |  | -- |  | -- |  | -- |  | 2421.6

## Table 17
For RDT&E aircraft, the first 2 will support contractor and government led testing and will remain as test and evaluation assets. The remaining 4 will support the completion of government led testing and will be utilized for Initial Operational Test & Evaluation. These 4 aircraft will then transition to operational status.

## Table 18
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | 6 | 594.6 |  | -- |  | -- |  | 594.6 |  | 251.2 |  | 845.8
2020 |  | 6 | 596.7 |  | -- |  | -- |  | 596.7 |  | 258.1 |  | 854.8
2021 |  | 5 | 521 |  | -- |  | -- |  | 521 |  | 294.8 |  | 815.8
Subtotal |  | 17 | 1712.3 |  | -- |  | -- |  | 1712.3 |  | 804.1 |  | 2516.4

## Table 19
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2014 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2019 |  | 6 | 531.2 |  | -- |  | -- |  | 531.2 |  | 224.5 |  | 755.7
2020 |  | 6 | 522.7 |  | -- |  | -- |  | 522.7 |  | 226 |  | 748.7
2021 |  | 5 | 447.4 |  | -- |  | -- |  | 447.4 |  | 253.2 |  | 700.6
Subtotal |  | 17 | 1501.3 |  | -- |  | -- |  | 1501.3 |  | 703.7 |  | 2205

## Table 20
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2014-04-17 | 2014-04-17
Approved Quantity | 12 | 12
Reference | Milestone B ADM | Milestone B ADM
Start Year | 2019 | 2019
End Year | 2022 | 2022
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the requirement to have a minimum of 12 aircraft to establish an initial production base for the system. This LRIP quantity has been approved by the MDA as documented in the Milestone B ADM.

## Table 21
Foreign Military Sales
None
Nuclear Costs
None

## Table 22
Unit Cost
Unit Cost Report
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Current UCR Baseline (Apr 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 4649.7 |  |  | 4626.6
Quantity | 23 |  |  | 23
Unit Cost | 202.161 |  |  | 201.157 |  | -0.5
Average Procurement Unit Cost
Cost | 2043.6 |  |  | 2205
Quantity | 17 |  |  | 17
Unit Cost | 120.212 |  |  | 129.706 |  | 7.9
Item |  | BY 2014 $M | BY 2014 $M |  | % Change
|  | Original UCR Baseline (Apr 2014 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 4649.7 |  |  | 4626.6
Quantity | 23 |  |  | 23
Unit Cost | 202.161 |  |  | 201.157 |  | -0.5
Average Procurement Unit Cost
Cost | 2043.6 |  |  | 2205
Quantity | 17 |  |  | 17
Unit Cost | 120.212 |  |  | 129.706 |  | 7.9
The increase in Average Procurement Unit Cost is due to establishment of the Aircraft Procurement, Navy, initial spares funding line (APN-6).

## Table 23
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2014 $M | [6 empty] | TY $M
[8 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  | Apr 2014 |  |  |  |  | 202.161 |  |  |  | 120.212 |  |  |  | 225.422 |  |  | 139.941
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Current APB |  |  | Apr 2014 |  |  |  |  | 202.161 |  |  |  | 120.212 |  |  |  | 225.422 |  |  | 139.941
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 203.291 |  |  |  | 121.482 |  |  |  | 224.543 |  |  | 139.947
Current Estimate |  |  | Dec 2015 |  |  |  |  | 201.157 |  |  |  | 129.706 |  |  |  | 221.226 |  |  | 148.024
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Development Estimate | Changes | [15 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est |  | Oth |  |  | Spt | Total
225.422 -3.826 0.000 0.000 0.000 -7.383 0.000 7.013 -4.196 221.226
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Development Estimate | Changes | [15 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  |  | Eng |  | Est | Oth |  |  | Spt | Total
139.941 -2.624 0.000 0.000 0.000 1.218 0.000 9.488 8.082 148.024

## Table 24
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | Mar 2014 | N/A | Apr 2014
Milestone C | N/A | Jan 2019 | N/A | Jan 2019
IOC | N/A | Jul 2020 | N/A | Jul 2020
Total Cost (TY $M) | N/A | 5184.7 | N/A | 5088.2
Total Quantity | N/A | 23 | N/A | 23
PAUC | N/A | 225.422 | N/A | 221.226

## Table 25
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 2805.7 | 2379 | -- | 5184.7
Previous Changes
Economic | -29 | -24.6 | -- | -53.6
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 8.7 | 6.1 | -- | 14.8
Other | -- | -- | -- | --
Support | -- | 18.6 | -- | 18.6
Subtotal | -20.3 | 0.1 | -- | -20.2
Current Changes
Economic | -14.4 | -20 | -- | -34.4
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -199.2 | 14.6 | -- | -184.6
Other | -- | -- | -- | --
Support | -- | 142.7 | -- | 142.7
Subtotal | -213.6 | 137.3 | -- | -76.3
Total Changes | -233.9 | 137.4 | -- | -96.5
CE - Cost Variance | 2571.8 | 2516.4 | -- | 5088.2
CE - Cost & Funding | 2571.8 | 2516.4 | -- | 5088.2

## Table 26
Summary BY 2014 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 2606.1 | 2043.6 | -- | 4649.7
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 4.4 | 5.5 | -- | 9.9
Other | -- | -- | -- | --
Support | -- | 16.1 | -- | 16.1
Subtotal | 4.4 | 21.6 | -- | 26
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -188.9 | 12.8 | -- | -176.1
Other | -- | -- | -- | --
Support | -- | 127 | -- | 127
Subtotal | -188.9 | 139.8 | -- | -49.1
Total Changes | -184.5 | 161.4 | -- | -23.1
CE - Cost Variance | 2421.6 | 2205 | -- | 4626.6
CE - Cost & Funding | 2421.6 | 2205 | -- | 4626.6
Previous Estimate: December 2014

## Table 27
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -14.4
Adjustment for current and prior escalation. (Estimating) | 4.6 | 4.7
Revised estimate to reflect the application of new outyear inflation indices. (Estimating) | 9.1 | 9.8
Revised estimate to align with FY 2017 PB. (Estimating) | -4.5 | -3.6
Revised estimate due to realized efficiencies in FY 2016-2017. (Estimating) | -198.1 | -210.1
RDT&E Subtotal | -188.9 | -213.6
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -20.0
Revised estimate to reflect the application of new outyear inflation indices. (Estimating) +12.8 +14.6
Decrease in Other Support due revised labor estimates and the application of new outyear inflation indices. (Support)
Increase in Initial Spares due to establishment of Aircraft Procurement, Navy initial spares funding line and the application of new outyear inflation indices. (Support)
-40.1 -48.3
+167.1 +191.0
Procurement Subtotal +139.8 +137.3

## Table 28
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: Presidential Helicopter Replacement Program (EMD)
Contractor: Sikorsky Aircraft Corp.
Contractor Location: 6900 Main Street PO Box 9731
Stratford, CT 06615-9131
Contract Number: N00019-14-C-0050
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: May 07, 2014
Definitization Date: May 07, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
1244.7 1326.7 6 1211.1 1286.4 6 1230.2 1230.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a contract modification that moved test spares from a Fixed Price Incentive CLIN to a Firm Fixed Price CLIN which reduced the overall contract price.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2016) -3.7 -2.7
Previous Cumulative Variances -0.4 -0.7
Net Change -3.3 -2.0
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to additional work associated with the airstair door, cabin floor, and titanium airframe machining.
The unfavorable net change in the schedule variance is due to additional work associated with the airstair door, cabin floor, and Mission Communications System rack and console design. Key milestones are on plan to meet APB objectives.

## Table 29
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 6 | 0%
Production | 0 | 0 | 17 | 0%
Total Program Quantity Delivered | 0 | 0 | 23 | 0%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
5088.2
546.1
10.73%
21
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
7
33.33%
1158.5
22.77%
The above data is current as of February 09, 2016.

## Table 30
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 16, 2014
Source of Estimate: SCP
Quantity to Sustain: 21
Unit of Measure: Aircraft
Service Life per Unit: 40.00 Years
Fiscal Years in Service: FY 2021 - FY 2062
Aircraft Attrition: 1 aircraft over the life of the program Aircraft Pipeline Factor: 19% of Total Aircraft Inventory (TAI)
Squadrons: Marine Helicopter Squadron One (HMX-1) Helicopters per (active) squadron: 16 Monthly Flight Hours per Helicopter: 19.8
Total TAI Helicopter Years: 840
Total Primary Authorized Aircraft Helicopter Years: 648
Total program acquisition quantity of 23 aircraft is comprised of 2 test aircraft and 21 operational aircraft. The quantity to sustain encompasses the 21 operational aircraft.
Sustainment Strategy
The VH-92 program will utilize Organizational, limited Intermediate and Depot level maintenance capabilities. Contractor maintenance will be employed as support for depot level repairables. Aircraft rework will be performed via an organic depot level Integrated Maintenance Program. During sustainment, in-service engineering support will be provided by the Contractor.
Antecedent Information
The Antecedent VH-3D/VH-60N data is representative of FY 2012 to FY 2014 average of Naval Visibility And Management of Operating and Support Cost (VAMOSC) reported cost data.
Total O&S Costs = Average annual O&S Cost/aircraft * total aircraft operating years = $12.050M * 840 = $10,122.0M BY 2014.

## Table 31
Annual O&S Costs BY2014 $M
Cost Element |  | VH-92A Average Annual Cost Per Aircraft | [5 empty] | VH-3D/VH-60N (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  | 1.75 | [5 empty] | 1.75
Unit Operations |  | 0.36 | [5 empty] | 0.44
Maintenance |  | 5.98 | [5 empty] | 4.35
Sustaining Support |  | 0.81 | [5 empty] | 0.69
Continuing System Improvements |  | 2.19 | [5 empty] | 4.51
Indirect Support |  | 0.31 | [5 empty] | 0.31
Other |  | 0 | [5 empty] | 0
Total |  | 11.4 | [5 empty] | 12.05
.
Item | Total O&S Cost $M
| VH-92A | [7 empty] | VH-3D/VH-60N (Antecedent)
| Current Development APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 10140.4 |  |  | 11154.4 |  |  | 9573 |  | 10122
Then Year | 17674.3 |  |  | N/A |  |  | 16631.1 |  | N/A
For Total O&S Cost, the Current Estimate of $9,573.0M BY 2014 is the SCP established to support the Program's Navy Gate 5 and Milestone B Review held during the second quarter of FY 2014. The CAPE ICE of $10,140.4M BY 2014 was selected to establish the APB objective value. Differences between the numbers are primarily driven by Maintenance Concept and projected System Improvements for the platform.
Equation to Translate Annual Cost to Total Cost
Average annual O&S cost/aircraft = Total O&S costs / total aircraft operating years = $9,573.0M / 840 = $11.400M BY 2014
O&S Cost Variance
Category |  |  | BY 2014 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
9573
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0

## Table 32
Total Changes 0.0
Current Estimate 9573.0
Disposal Estimate Details
Date of Estimate: January 16, 2014
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2014 $M): Total costs for disposal of all Aircraft are 1.2
The estimate will be refined at Milestone C based on the System Disposal Plan Annex to the Life Cycle Sustainment Plan.