## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-442
AIM-9X Block II Sidewinder (AIM-9X Blk II)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 15
Cost and Funding 16
Low Rate Initial Production 26
Foreign Military Sales 27
Nuclear Costs 28
Unit Cost 29
Cost Variance 32
Contracts 35
Deliveries and Expenditures 42
Operating and Support Cost 43

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
AIM-9X Block II Sidewinder (AIM-9X Blk II)
DoD Component
Navy
Joint Participants
Air Force
Responsible Office
Capt James Stoneman 47123 Buse Road
Unit IPT, Suite 451
Patuxent River, MD 20670-1547
jim.stoneman@navy.mil
Phone: | 301-757-7311
Fax: | 301-757-6435
DSN Phone: | 757-7311
DSN Fax: | 757-6435
Date Assigned: | October 9, 2014
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated December 23, 2011
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated August 31, 2015

## Table 6
Mission and Description
The AIM-9X Block II Sidewinder (AIM-9X Blk II) short-range air-to-air missile is a long term evolution of the AIM-9 series of fielded missiles. The missile program provides a launch and leave, air combat munitions that uses passive Infrared (IR) energy for acquisition and tracking of enemy aircraft and complements the Advanced Medium Range Air-to-Air Missile. Air superiority in the short-range air-to-air missile arena is essential and includes first shot, first kill opportunity against enemy employing IR countermeasures. Anti-Tamper features have been incorporated to protect improvements inherent in this design.

## Table 7
Executive Summary
The AIM-9X Block II missile completed Initial Operational Test and Evaluation (IOT&E) in March 2015 and was found to be operationally effective and suitable. The United States Navy declared IOC in March 2015 and began fielding the AIM-9X Block II missiles later that month. The MDA approved the FRP decision in August 2015 and the program awarded the first full rate production contract in September 2015. The program awarded the System Improvement Program III (SIP III) contract in September 2015 to improve missile performance, address obsolescence and to implement cost reduction initiatives. The United States Air Force fielded the AIM-9X Block II Captive Air Training Missile for training in December 2015 and anticipates IOC in April 2016.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
(Ch-1)
(Ch-2)
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
MS C | Jun 2011 | Jun 2011 | Dec 2011 | Jun 2011
OT Start | Apr 2012 | Apr 2012 | Oct 2012 | May 2012
OT Complete | Apr 2013 | Sep 2014 | Mar 2015 | Jan 2015
IOC | Sep 2014 | Sep 2014 | Mar 2015 | Mar 2015
FRP Decision | Dec 2013 | Jun 2015 | Dec 2015 | Aug 2015
FOC | Oct 2015 | Apr 2016 | Oct 2016 | Oct 2016
Change Explanations
(Ch-1) The FRP Decision current estimate changed from June 2015 to August 2015 to reflect the actual date FRP was approved.
(Ch-2) The FOC current estimate changed from October 2015 to October 2016 to reflect the updated APB.
Acronyms and Abbreviations
MS - Milestone
OT - Operational Test

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
AIM-9X Day/Night Capability
Yes | Yes | Yes | Yes | Yes
AIM-9X Aircraft Interface/Interoperability Missile Weight (lbs.)
≤ 192 | ≤ 192 | ≤ 210 | 186.2 | ≤ 192
AIM-9X Aircraft Interface/Interoperability Missile Length (in.)
≤ 115 | ≤ 115 | ≤ 123 | 119.2 | ≤ 123
AIM-9X Aircraft Interface/Interoperability Missile Box Size (in.)
≤ 12.5 X 12.5 | ≤ 12.5 X 12.5 | ≤ 12.5 X 12.5 | 12.5 X 12.5 | ≤ 12.5 X 12.5
AIM-9X Aircraft Interface/Interoperability Missile Diameter (in.)
≤ 5 | ≤ 5 | ≤ 7 | ≤ 5 | ≤ 5
AIM-9X Aircraft Interface/Interoperability Interface
Mid body umbilical only | Mid body umbilical only | Digital. | Digital | Mid body umbilical only
AIM-9X High Off Boresight Capability Cueing/Verification
Interface with current/ planned aircraft radar systems and planned HMCS. | Interface with current/ planned aircraft radar systems and planned HMCS. | Interface with current/ planned aircraft radar systems and planned HMCS. | Yes | Interface with current/ planned aircraft radar systems and planned- HMCS
AIM-9X Captive Carry Reliability (MTBCCF) (hr.)
>.or.=900 | >.or.=900 | >.or.=500 | 794.16 | >.or.=900
AIM-9X Detect Non-Operational Missile (BIT) All Components (%)
>.or.=0.80 | >.or.=0.80 | >.or.=0.60 | TBD | >.or.=0.60
AIM-9X Detect Non-Operational Missile (BIT-able Components) (%)
>.or.=0.95 | >.or.=0.95 | >.or.=0.90 | 0.92 | >.or.=0.90
AIM-9X Mean Time Between False Alarms (hr.)
>.or.=25 | >.or.=25 | <.or.=16 | >.or.=18 | >.or.=16
AIM-9X BIT Time (sec.)
≤ 20 | ≤ 20 | ≤ 20 | ≤ 15 | ≤ 20
EMI Compatibility
Threshold= Objective | Threshold= Objective | Not incur damage to electrical components while in the electromagnetic | Yes | Threshold= Objective
(Ch-1)
(Ch-2)
(Ch-3)

## Table 11
environment of an aircraft carried. The AIM -9X Block II missile shall be compatible with representative threshold hose aircraft weapon and sensor load-outs with regard to RFI, EMI, and MIL-STD-1533 or MIL-STD-1760 data bus message throughput constraints.
Ao- AUR
No less than (.98) after 35,000 flight hours | No less than (.98) after 35,000 flight hours | No less than (.93) after 35,000 flight hours | TBD | No less than (.93) after 35,000 flight hours
Net Readiness
The capability, system, and/or service must fully support execution of joint critical operational activities and information exchanges identified in the DoD Enterprise Architecture and solution architectures based on integrated DoDAF content, and must satisfy the technical requirements for transition to Net- Centric military operations to include: 1) Solution architecture products complaint with DoD Enterprise Architecture based on integrated DoDAF content, including specified operationally effective information exchanges. 2) Compliant with Net- Centric Data Strategy and Net-Centric Services Strategy, and the principles and rules identified in the DoD IEA, excepting | The capability, system, and/or service must fully support execution of joint critical operational activities and information exchanges identified in the DoD Enterprise Architecture and solution architectures based on integrated DoDAF content, and must satisfy the technical requirements for transition to Net- Centric military operations to include: 1) Solution architecture products complaint with DoD Enterprise Architecture based on integrated DoDAF content, including specified operationally effective information exchanges. 2) Compliant with Net- Centric Data Strategy and Net-Centric Services Strategy, and the principles and rules identified in the DoD IEA, excepting | The capability, system, and/or service must fully support execution of all operational activities and information exchanges identified in DoD Enterprise Architecture and solution architectures based on integrated DoDAF content, and must satisfy the technical requirements for transition to Net-Centric military operations to include: 1) Solution architecture products compliant with DoD Enterprise Architecture based on integrated DoDAF content, including specified operationally effective information exchanges. 2) Compliant with Net- Centric Data Strategy and Net-Centric Services Strategy, and the principles and rules identified in the DoD IEA , excepting tactical and non-IP communica- tions. 3) Compliant with GIG Technical | TBD | The capability, system, and/or service must fully support execution of joint critical operational activities and information exchanges identified in the DoD Enterprise Architecture and solution architectures based on integrated DoDAF content, and must satisfy the technical requirements for transition to Net- Centric military operations to include: 1) Solution architecture products complaint with DoD Enterprise Architecture based on integrated DoDAF content, including specified operationally effective information exchanges. 2) Compliant with Net- Centric Data Strategy and Net- Centric Services
(Ch-1)

## Table 12
tactical and non-IP communica-tions. 3) Compliant with GIG Technical Guidance to include IT Standards identified in the TV-1 and implementation guidance of GIG GESPs necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views. 4) Information assurance requirements including availability, integrity, authenticat-ion, confident-iality, and non-repudiation, and issuance of an IATO or ATO by the DAA and 5) Supportabil-ity requirements to include SAASM Spectrum and JTRS requirements | tactical and non-IP communica-tions. 3) Compliant with GIG Technical Guidance to include IT Standards identified in the TV-1 and implementation guidance of GIG GESPs necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views. 4) Information assurance requirements including availability, integrity, authenticat-ion, confidential-ity, and non-repudiation, and issuance of an IATO or ATO by the DAA and 5) Supportabil-ity requirements to include SAASM Spectrum and JTRS requirements | Guidance to include IT Standards identified in the TV-1 and implementation guidance of GESPs, necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views. 4) Information assurance requirements including availability, integrity, authenticat-ion, confidential-ity, and non- repudiation, and issuance of an IATO or ATO by the DAA and 5) Supportabil-ity requirements to include SAASM, Spectrum and JTRS necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views |  | Strategy, and the principles and rules identified in the DoD IEA, excepting tactical and non-IP communica-tions. 3) Compliant with GIG Technical Guidance to include IT Standards identified in the TV-1 and implementa-tion guidance of GIG GESPs necessary to meet all operational requirements specified in the DoD Enterprise Architecture and solution architecture views. 4) Information assurance requirements including availability, integrity, authentica- tion, confidentiality and non-repudiation, and issuance of an IATO or ATO by the DAA and 5) Support- ability requirements to include SAASM Spectrum and JTRS requirements
Ao- CATM
No less than (.95) after 100,000 flight hours | No less than (.95) after 100,000 flight hours | No less than (.86) after 100,000 flight hours | TBD | No less than (.95) after 100,000 flight hours
Material Availability (Am)
Threshold= Objective | Threshold= Objective | No less than (.82) | TBD | Threshold= Objective
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
CPD dated May 20, 2011

## Table 13
Change Explanations
(Ch-1) The Current Estimate for AIM-9X Detect Non-Operational Missile (BIT) All Components (%) and Ao-AUR changed
due to an error in the previous SAR.
(Ch-2) The Current Estimate for AIM-9X Detect Non-Operational Missile (BIT-able Components ) (%) changed from
>.or.=0.95 to >.or.=0.92 based on amount of time the missile has been fielded; more data is required to analyze.
(Ch-3) The Current Estimate for AIM-9X Mean Time Between False Alarms (hr.)changed from >.or.=25 to >.or.=16 based on the amount of time the missile has been fielded; more data is required to analyze.
Notes
AIM-9X Day/Night Capability demonstrated performance changed from TBD to Yes. AIM-9X High Off Boresight Capability Cueing/Verification demonstrated performance changed from TBD to Yes. AIM-9X BIT Time (sec.) demonstrated performance TBD to ≤ 20. EMI Capability demonstrated performance changed from TBD to Yes. Capabilities were demonstrated during Developmental Test / Operational Test.
AIM-9X Aircraft Interface/Interoperability Missile Weight (lbs) demonstrated performance changed from TBD to 186.2. AIM- 9X Aircraft Interface/Interoperability Missile Length (in.) demonstrated performance changed from TBD to 119.2. AIM-9X Aircraft Interface/Interoperability Missile Box Size (in.) demonstrated performance changed from TBD to 12.5 X 12.5. AIM-9X Aircraft Interface/Interoperability Missile Diameter (in.) demonstrated performance changed from TBD to ≤ 5. AIM-9X Aircraft Interface/Interoperability Interface demonstrated performance changed from TBD to Digital. Characteristics were verified during AIM-9X Block II production.
AIM-9X Detect Non-Operational Missile (BIT) All Components (%) current estimated changed from >.or.=0.80 to >.or.=0.60. Ao-AUR current estimated changed from No less than (.98) after 35,000 flight hours to No less than (.93) after 35,000 flight hours.
AIM-9X Detect Non-Operational Missile (BIT-able Components ) (%) demonstrated performance changed from TBD to 0.92
due to capability demonstration to date.
AIM-9X Mean Time Between False Alarms (hr.) demonstrated performance changed from TBD to >.or.=18 due to capability demonstration during Operational Test.

## Table 14
Acronyms and Abbreviations
Ao - Operational Availability ATO - Authorization To Operate AUR - All Up Round
BIT - Built In Test
CATM - Captive Air Training Missile DAA - Designated Accrediting Authority
DoDAF - Department of Defense Architecture Framework EMI - Electromagnetic Interference
GESP - GIG Enterprise Service Profile GIG - Global Information Grid
HMCS - Helmet Mounted Cueing System hr - hour
IATO - Interim Authorization to Operate IEA - Information Enterprise Architecture in - Inches
IP - Internet Protocol
IT - Information Technology
JTRS - Joint Test Requirement System lbs - Pounds
Mid - Middle MIL - Military
MTBCCF - Mean Time Between Captive Carry Failure RFI - Radio Frequency Interference
SAASM - Selective Availability Anti-Spoofing Module sec - seconds
STD - Standard
TV - Technical View

## Table 15
Track to Budget
General Notes
Block III funding (Project Unit 0458) is not included in this Block II SAR.
RDT&E
Appn |  |  |  | BA | PE
Navy 1319 07 0207161N
Project Name
0457 AIM-9X
Air Force 3600 07 0207161F
Project Name
674132 AIM-9 Product Improvement
Procurement
Appn |  |  |  | BA | PE
Navy 1507 02 0206138M
Line Item | Name
2209 Sidewinder (Shared)
Notes: USMC funding received as WPN
Navy 1507 02 0204162N
|  | Line Item |  |  | Name
|  | 2209 |  |  | Sidewinder | (Shared)
Navy |  | 1507 | 6 |  | 0204162N
|  | Line Item |  |  | Name
|  | 6120 Notes: |  |  | Spares and Repair Parts Initial Spares | (Shared)
Air Force |  | 3020 04 |  |  | 0207161F
|  | Line Item |  |  | Name
|  | 000999 Notes: |  |  | Initial Spares/Repair Parts Initial Spares | (Shared)
Air Force |  | 3020 02 |  |  | 0207161F
|  | Line Item |  |  | Name
|  | M09HAI |  |  | Sidewinder (AIM-9X) | (Shared)

## Table 16
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2011 $M | [5 empty] | BY 2011 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 168.8 |  |  | 504.9 | 555.4 |  |  | 537.8 |  | 175.7 |  |  | 547.1 |  | 582.3
Procurement | 3798.5 |  |  | 2821.5 | 3103.7 |  |  | 2960.2 |  | 4680.4 |  |  | 3324.4 |  | 3517.2
Flyaway | -- |  |  | -- | -- |  |  | 2862.4 |  | -- |  |  | -- |  | 3404.6
Recurring | -- |  |  | -- | -- |  |  | 2716.7 |  | -- |  |  | -- |  | 3240.9
Non Recurring | -- |  |  | -- | -- |  |  | 145.7 |  | -- |  |  | -- |  | 163.7
Support | -- |  |  | -- | -- |  |  | 97.8 |  | -- |  |  | -- |  | 112.6
Other Support | -- |  |  | -- | -- |  |  | 42.5 |  | -- |  |  | -- |  | 47.6
Initial Spares | -- |  |  | -- | -- |  |  | 55.3 |  | -- |  |  | -- |  | 65
MILCON | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 3967.3 |  |  | 3326.4 | N/A |  |  | 3498 |  | 4856.1 |  |  | 3871.5 |  | 4099.5
Current APB Cost Estimate Reference
FRP Joint Component Cost Position dated August 03, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current APB cost estimate provided sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk and external interference. It was consistent with average resource expenditures on historical efforts of similar size, scope, and complexity and represents a notional 50% confidence level.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  | 6000 |  |  |  | 6000 |  |  |  |  | 6000
Total |  | 6000 |  |  |  | 6000 |  |  |  |  | 6000

## Table 17
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 201.7 | 114.4 |  |  | 109.2 | 81.3 | 48.1 |  | 13.7 |  | 13.9 |  |  | 0 |  | 582.3
Procurement | 829.1 | 292.7 |  |  | 206.2 | 200.5 | 207 |  | 213.1 |  | 211.2 |  |  | 1357.4 |  | 3517.2
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 1030.8 | 407.1 |  |  | 315.4 | 281.8 | 255.1 |  | 226.8 |  | 225.1 |  |  | 1357.4 |  | 4099.5
PB 2016 Total | 1033 | 418.6 |  |  | 432.3 | 366.8 | 241.1 |  | 211.1 |  | 210.2 |  |  | 840 |  | 3753.1
Delta | -2.2 | -11.5 |  |  | -116.9 | -85 | 14 |  | 15.7 |  | 14.9 |  |  | 517.4 |  | 346.4
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 1568 |  | 733 | 439 | 376 |  | 373 |  | 368 | 327 |  | 1816 |  | 6000
PB 2017 Total | 0 |  | 1568 |  | 733 | 439 | 376 |  | 373 |  | 368 | 327 |  | 1816 |  | 6000
PB 2016 Total | 0 |  | 1568 |  | 733 | 722 | 698 |  | 364 |  | 363 | 365 |  | 1187 |  | 6000
Delta | 0 |  | 0 |  | 0 | -283 | -322 |  | 9 |  | 5 | -38 |  | 629 |  | 0

## Table 18
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.4
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 71
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.3
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.6
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.3
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 303.4

## Table 19
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.6
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.3
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 279.7

## Table 20
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.9
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.6
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 278.9

## Table 21
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.7
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.7
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.7
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.9
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.4
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.4
Subtotal |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 258.1

## Table 22
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | -- | -- |  | -- |  | 0.9 |  | 0.9 |  | -- |  | 0.9
2010 |  | -- | -- |  | -- |  | 11.4 |  | 11.4 |  | -- |  | 11.4
2011 |  | 63 | 46.1 |  | -- |  | 3.1 |  | 49.2 |  | 1.2 |  | 50.4
2012 |  | 69 | 39.2 |  | -- |  | 7.6 |  | 46.8 |  | 1.7 |  | 48.5
2013 |  | 150 | 60.1 |  | -- |  | 3.6 |  | 63.7 |  | 6.8 |  | 70.5
2014 |  | 208 | 86.6 |  | -- |  | 5.1 |  | 91.7 |  | 6.6 |  | 98.3
2015 |  | 167 | 64.2 |  | -- |  | 2 |  | 66.2 |  | 3.2 |  | 69.4
2016 |  | 227 | 81.2 |  | -- |  | 7.1 |  | 88.3 |  | 5.6 |  | 93.9
2017 |  | 152 | 68.5 |  | -- |  | 0.9 |  | 69.4 |  | 1.6 |  | 71
2018 |  | 150 | 75.3 |  | -- |  | 2.8 |  | 78.1 |  | 2.6 |  | 80.7
2019 |  | 153 | 75.8 |  | -- |  | 1.6 |  | 77.4 |  | 3 |  | 80.4
2020 |  | 153 | 79.2 |  | -- |  | 1.6 |  | 80.8 |  | 2.6 |  | 83.4
2021 |  | 150 | 85.6 |  | -- |  | 2.7 |  | 88.3 |  | 2.6 |  | 90.9
2022 |  | 160 | 88.8 |  | -- |  | 1.1 |  | 89.9 |  | 2.8 |  | 92.7
2023 |  | 157 | 90.2 |  | -- |  | 1.6 |  | 91.8 |  | 2.8 |  | 94.6
2024 |  | 151 | 90 |  | -- |  | 3.7 |  | 93.7 |  | 2.8 |  | 96.5
2025 |  | 155 | 93.9 |  | -- |  | 1.7 |  | 95.6 |  | 2.9 |  | 98.5
2026 |  | 132 | 119.7 |  | -- |  | 2.2 |  | 121.9 |  | 3.1 |  | 125
2027 |  | 132 | 141.1 |  | -- |  | 4.3 |  | 145.4 |  | 3.2 |  | 148.6
2028 |  | 119 | 151.3 |  | -- |  | 2.3 |  | 153.6 |  | 1.5 |  | 155.1
Subtotal |  | 2648 | 1536.8 |  | -- |  | 67.3 |  | 1604.1 |  | 56.6 |  | 1660.7

## Table 23
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | -- | -- |  | -- |  | 0.9 |  | 0.9 |  | -- |  | 0.9
2010 |  | -- | -- |  | -- |  | 11.3 |  | 11.3 |  | -- |  | 11.3
2011 |  | 63 | 44.8 |  | -- |  | 3 |  | 47.8 |  | 1.2 |  | 49
2012 |  | 69 | 37.5 |  | -- |  | 7.2 |  | 44.7 |  | 1.7 |  | 46.4
2013 |  | 150 | 56.7 |  | -- |  | 3.4 |  | 60.1 |  | 6.5 |  | 66.6
2014 |  | 208 | 80.7 |  | -- |  | 4.7 |  | 85.4 |  | 6.2 |  | 91.6
2015 |  | 167 | 58.9 |  | -- |  | 1.9 |  | 60.8 |  | 2.9 |  | 63.7
2016 |  | 227 | 73.2 |  | -- |  | 6.4 |  | 79.6 |  | 5.1 |  | 84.7
2017 |  | 152 | 60.6 |  | -- |  | 0.8 |  | 61.4 |  | 1.4 |  | 62.8
2018 |  | 150 | 65.4 |  | -- |  | 2.4 |  | 67.8 |  | 2.2 |  | 70
2019 |  | 153 | 64.5 |  | -- |  | 1.3 |  | 65.8 |  | 2.6 |  | 68.4
2020 |  | 153 | 66.1 |  | -- |  | 1.3 |  | 67.4 |  | 2.2 |  | 69.6
2021 |  | 150 | 70 |  | -- |  | 2.1 |  | 72.1 |  | 2.2 |  | 74.3
2022 |  | 160 | 71.2 |  | -- |  | 0.9 |  | 72.1 |  | 2.2 |  | 74.3
2023 |  | 157 | 70.9 |  | -- |  | 1.3 |  | 72.2 |  | 2.2 |  | 74.4
2024 |  | 151 | 69.4 |  | -- |  | 2.8 |  | 72.2 |  | 2.2 |  | 74.4
2025 |  | 155 | 71 |  | -- |  | 1.2 |  | 72.2 |  | 2.2 |  | 74.4
2026 |  | 132 | 88.7 |  | -- |  | 1.6 |  | 90.3 |  | 2.3 |  | 92.6
2027 |  | 132 | 102.5 |  | -- |  | 3.1 |  | 105.6 |  | 2.3 |  | 107.9
2028 |  | 119 | 107.7 |  | -- |  | 1.6 |  | 109.3 |  | 1.1 |  | 110.4
Subtotal |  | 2648 | 1259.8 |  | -- |  | 59.2 |  | 1319 |  | 48.7 |  | 1367.7

## Table 24
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | -- | -- |  | -- |  | 1.9 |  | 1.9 |  | -- |  | 1.9
2010 |  | -- | -- |  | -- |  | 14.2 |  | 14.2 |  | -- |  | 14.2
2011 |  | 106 | 60.5 |  | -- |  | 3.7 |  | 64.2 |  | 1.4 |  | 65.6
2012 |  | 127 | 75.8 |  | -- |  | 9.1 |  | 84.9 |  | 1.7 |  | 86.6
2013 |  | 150 | 62.3 |  | -- |  | 4.2 |  | 66.5 |  | 7.3 |  | 73.8
2014 |  | 225 | 95.2 |  | -- |  | 5.5 |  | 100.7 |  | 6.1 |  | 106.8
2015 |  | 303 | 123.4 |  | -- |  | 3.4 |  | 126.8 |  | 4 |  | 130.8
2016 |  | 506 | 181.3 |  | -- |  | 16.6 |  | 197.9 |  | 0.9 |  | 198.8
2017 |  | 287 | 123.8 |  | -- |  | 3.4 |  | 127.2 |  | 8 |  | 135.2
2018 |  | 226 | 107.8 |  | -- |  | 6 |  | 113.8 |  | 6 |  | 119.8
2019 |  | 220 | 118.3 |  | -- |  | 3.7 |  | 122 |  | 4.6 |  | 126.6
2020 |  | 215 | 120.9 |  | -- |  | 4.4 |  | 125.3 |  | 4.4 |  | 129.7
2021 |  | 177 | 110.4 |  | -- |  | 7.9 |  | 118.3 |  | 2 |  | 120.3
2022 |  | 199 | 118.9 |  | -- |  | 1.9 |  | 120.8 |  | 2 |  | 122.8
2023 |  | 198 | 121.4 |  | -- |  | 2.1 |  | 123.5 |  | 2.1 |  | 125.6
2024 |  | 192 | 122.3 |  | -- |  | 4 |  | 126.3 |  | 2.1 |  | 128.4
2025 |  | 188 | 122.9 |  | -- |  | 2.2 |  | 125.1 |  | 2.2 |  | 127.3
2026 |  | 33 | 38.9 |  | -- |  | 2.2 |  | 41.1 |  | 1.2 |  | 42.3
Subtotal |  | 3352 | 1704.1 |  | -- |  | 96.4 |  | 1800.5 |  | 56 |  | 1856.5

## Table 25
Annual Funding 3020 ¦ Procurement ¦ Missile Procurement, Air Force
Fiscal Year | Quantity |  | BY 2011 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2009 |  | -- | -- |  | -- |  | 1.9 |  | 1.9 |  | -- |  | 1.9
2010 |  | -- | -- |  | -- |  | 14.2 |  | 14.2 |  | -- |  | 14.2
2011 |  | 106 | 59.3 |  | -- |  | 3.6 |  | 62.9 |  | 1.4 |  | 64.3
2012 |  | 127 | 73 |  | -- |  | 8.8 |  | 81.8 |  | 1.6 |  | 83.4
2013 |  | 150 | 58.7 |  | -- |  | 4 |  | 62.7 |  | 6.8 |  | 69.5
2014 |  | 225 | 88.3 |  | -- |  | 5.1 |  | 93.4 |  | 5.7 |  | 99.1
2015 |  | 303 | 113.2 |  | -- |  | 3.1 |  | 116.3 |  | 3.7 |  | 120
2016 |  | 506 | 163.4 |  | -- |  | 15 |  | 178.4 |  | 0.8 |  | 179.2
2017 |  | 287 | 109.5 |  | -- |  | 3 |  | 112.5 |  | 7.1 |  | 119.6
2018 |  | 226 | 93.5 |  | -- |  | 5.2 |  | 98.7 |  | 5.2 |  | 103.9
2019 |  | 220 | 100.6 |  | -- |  | 3.1 |  | 103.7 |  | 3.9 |  | 107.6
2020 |  | 215 | 100.8 |  | -- |  | 3.6 |  | 104.4 |  | 3.7 |  | 108.1
2021 |  | 177 | 90.2 |  | -- |  | 6.4 |  | 96.6 |  | 1.7 |  | 98.3
2022 |  | 199 | 95.2 |  | -- |  | 1.6 |  | 96.8 |  | 1.6 |  | 98.4
2023 |  | 198 | 95.4 |  | -- |  | 1.6 |  | 97 |  | 1.7 |  | 98.7
2024 |  | 192 | 94.2 |  | -- |  | 3.1 |  | 97.3 |  | 1.6 |  | 98.9
2025 |  | 188 | 92.8 |  | -- |  | 1.6 |  | 94.4 |  | 1.7 |  | 96.1
2026 |  | 33 | 28.8 |  | -- |  | 1.6 |  | 30.4 |  | 0.9 |  | 31.3
Subtotal |  | 3352 | 1456.9 |  | -- |  | 86.5 |  | 1543.4 |  | 49.1 |  | 1592.5

## Table 26
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2011-06-30 | 2014-06-05
Approved Quantity | 361 | 1140
Reference | Milestone C ADM | LRIP IV ADM
Start Year | 2011 | 2011
End Year | 2012 | 2014
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the need to maintain the production line.
The Initial LRIP Decision Approved Quantity was authorized for LRIP I and II per the Milestone C ADM dated June 30, 2011.

## Table 27
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Australia | 2015-12-22 |  | 12.6 | FMS Case AT-P-AYW. 14 Captive Air Training Missiles and a classified quantity of Tactical and Special Air Training Missiles.
Japan | 2015-12-11 | 10 | 4.5 | FMS Case JA-P-ASL. 4 Tactical Missiles and 6 Captive Air Training Missiles
Turkey | 2015-12-10 | 18 | 7 | FMS Case TK-P-AHX-A6. 18 Captive Air Training Missiles
South Korea | 2015-10-30 | 72 | 52.3 | FMS Case KS-P-ALE 62 Tactical Missiles and 10 Captive Air Training Missiles
Norway | 2015-10-28 | 120 | 65.8 | FMS Case NO-P-AHV. 90 Tactical Missiles and 30 Captive Air Training Missiles
Taiwan | 2015-09-10 | 80 | 50.3 | FMS Case TQ-D-QBZ. 40 Tactical Missiles and 40 Captive Air Training Missiles
Romania | 2015-03-30 | 18 | 7.2 | FMS Case RO-P-AAA 12 Tactical Missiles and 6 Captive Air Training Missiles
Australia | 2015-02-09 |  | 54.1 | FMS Case AT-P-AZT. 68 Captive Air Training Missiles and a classified quantity of Special Air Training Missiles.
Israel | 2014-12-17 | 10 | 3.7 | FMS Case IS-P-AUH 5 Tactical Missiles and 5 Captive Air Training Missiles
Japan | 2014-12-01 | 9 | 4.5 | FMS Case JA-P-LZB. 9 Tactical Missiles.
South Korea | 2014-08-27 | 78 | 54.1 | FMS Case KS-P-ALC 76 Tactical Missiles and 2 Captive Air Training Missiles
Belgium | 2014-01-06 | 60 | 24.6 | FMS Case BE-P-ACX. 30 Tactical Missiles and 30 Captive Air Training Missiles.
Singapore | 2013-12-18 | 28 | 9.7 | FMS Case SN-P-ADF. 20 Tactical Missiles and 8 Captive Air Training Missiles.
Netherlands | 2013-11-01 | 48 | 15.4 | FMS Case NE-P-AGE. 28 Tactical Missiles and 20 Captive Air Training Missiles.
Turkey | 2013-09-03 | 117 | 47 | FMS Case TK-P-AHX-A5. 117 Tactical Missiles.
Oman | 2013-03-11 | 74 | 20.7 | FMS Case MU-P-LAO. 50 Tactical Missiles and 24 Captive Air Training Missiles.
Kuwait | 2013-02-28 | 100 | 29.1 | FMS Case KU-P-ABI. 80 Tactical Missiles and 20 Captive Air Training Missiles.
Malaysia | 2012-05-29 | 28 | 8 | FMS Case MF-P-AAD. 20 Tactical Missiles and 8 Captive Air Training Missiles.
Morocco | 2012-03-29 | 32 | 8.4 | FMS Case MO-P-AAK. 20 Tactical Missiles and 12 Captive Air Training Missiles.
Saudi Arabia | 2011-12-25 | 154 | 85 | FMS Case SR-D-SAI. 120 Tactical Missiles and 34 Captive Air Training Missiles.
South Korea | 2011-12-20 | 19 | 9 | FMS Case KS-P-AKR. 19 Tactical Missiles.
Notes

## Table 28
All FMS missiles are the AIM-9X-2 Block II configuration and were procured under FMS procedures with waivers for nonrecurring cost and Yockey (USD (AT&L) approval to offer a weapon system under development. Effective August 2015, Yockey approval is no longer required for the AIM-9X Blk II because the missile system is in FRP.
All FMS missile procurements are on missile production contract(s) except for agreements accepted in 2015.
FMS Block II missile shipments have been on hold pending both United States Navy and United States Air Force Block II fielding. FMS Block II missile shipments to international partners are projected to begin in approximately 4th Quarter FY 2016.
Nuclear Costs
None

## Table 29
Unit Cost
Unit Cost Report
Item |  | BY 2011 $M | BY 2011 $M |  | % Change
|  | Current UCR Baseline (Aug 2015 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3326.4 |  |  | 3498
Quantity | 6000 |  |  | 6000
Unit Cost | 0.554 |  |  | 0.583 |  | 5.16
Average Procurement Unit Cost
Cost | 2821.5 |  |  | 2960.2
Quantity | 6000 |  |  | 6000
Unit Cost | 0.47 |  |  | 0.493 |  | 4.84
Item |  | BY 2011 $M | BY 2011 $M |  | % Change
|  | Original UCR Baseline (Dec 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3967.3 |  |  | 3498
Quantity | 6000 |  |  | 6000
Unit Cost | 0.661 |  |  | 0.583 |  | -11.83
Average Procurement Unit Cost
Cost | 3798.5 |  |  | 2960.2
Quantity | 6000 |  |  | 6000
Unit Cost | 0.633 |  |  | 0.493 |  | -22.13

## Table 30
Unit Cost History
Item |  |  |  |  | Date |  |  | BY 2011 $M | [5 empty] | TY $M
[8 empty] | PAUC |  |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  | Dec 2011 |  |  |  |  | 0.661 |  |  |  | 0.633 |  |  | 0.809 |  |  | 0.78
APB as of January 2006 |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Revised Original APB |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  | Dec 2011 |  |  |  |  | 0.661 |  |  |  | 0.633 |  |  | 0.809 |  |  | 0.78
Current APB |  |  | Aug 2015 |  |  |  |  | 0.554 |  |  |  | 0.47 |  |  | 0.645 |  |  | 0.554
Prior Annual SAR |  |  | Dec 2014 |  |  |  |  | 0.541 |  |  |  | 0.456 |  |  | 0.626 |  |  | 0.533
Current Estimate |  |  | Dec 2015 |  |  |  |  | 0.583 |  |  |  | 0.493 |  |  | 0.683 |  |  | 0.586
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [14 empty] | PAUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  |  | Total
0.809 0.017 0.000 -0.128 0.050 -0.048 0.000 -0.017 -0.126 0.683
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est |  | Oth | Spt |  |  | Total
0.780 0.018 0.000 -0.129 -0.001 -0.065 0.000 -0.017 -0.194 0.586

## Table 31
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | N/A | N/A
Milestone C | N/A | N/A | Jun 2011 | Jun 2011
IOC | N/A | N/A | Sep 2014 | Mar 2015
Total Cost (TY $M) | N/A | N/A | 4856.1 | 4099.5
Total Quantity | N/A | N/A | 6000 | 6000
PAUC | N/A | N/A | 0.809 | 0.683

## Table 32
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 175.7 | 4680.4 | -- | 4856.1
Previous Changes
Economic | -1.4 | 125.7 | -- | 124.3
Quantity | -- | -- | -- | --
Schedule | -- | -823.9 | -- | -823.9
Engineering | 307.8 | -7.8 | -- | 300
Estimating | 70.7 | -705.2 | -- | -634.5
Other | -- | -- | -- | --
Support | -- | -68.9 | -- | -68.9
Subtotal | 377.1 | -1480.1 | -- | -1103
Current Changes
Economic | -2.5 | -20.2 | -- | -22.7
Quantity | -- | -- | -- | --
Schedule | -- | 50.5 | -- | 50.5
Engineering | -- | -- | -- | --
Estimating | 32 | 316.9 | -- | 348.9
Other | -- | -- | -- | --
Support | -- | -30.3 | -- | -30.3
Subtotal | 29.5 | 316.9 | -- | 346.4
Total Changes | 406.6 | -1163.2 | -- | -756.6
CE - Cost Variance | 582.3 | 3517.2 | -- | 4099.5
CE - Cost & Funding | 582.3 | 3517.2 | -- | 4099.5

## Table 33
Summary BY 2011 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Production Estimate) | 168.8 | 3798.5 | -- | 3967.3
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -407.6 | -- | -407.6
Engineering | 274.3 | -7.4 | -- | 266.9
Estimating | 66.5 | -604.2 | -- | -537.7
Other | -- | -- | -- | --
Support | -- | -44.1 | -- | -44.1
Subtotal | 340.8 | -1063.3 | -- | -722.5
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 28.2 | 247.8 | -- | 276
Other | -- | -- | -- | --
Support | -- | -22.8 | -- | -22.8
Subtotal | 28.2 | 225 | -- | 253.2
Total Changes | 369 | -838.3 | -- | -469.3
CE - Cost Variance | 537.8 | 2960.2 | -- | 3498
CE - Cost & Funding | 537.8 | 2960.2 | -- | 3498
Previous Estimate: December 2014

## Table 34
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -2.5
Adjustment for current and prior escalation. (Estimating) |  | 1.1 | 1.1
Decrease due to FY 2017 PB reduction. (Navy) (Estimating) |  | -9.4 | -10.7
Decrease due to Targeted Balanced Budget Act (TBBA). (Navy) (Estimating) |  | -2 | -2.3
Revised estimate for software improvements and redesign of component hardware due to |  | 38.5 | 43.9
obsolescence. (Air Force) (Estimating)
RDT&E Subtotal +28.2 +29.5
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -20.2
Stretch-out of procurement buy profile of 149 missiles from FY 2017 through FY 2021 to FYDP, FY 2022 to FY 2028 (Navy). (Schedule)
Additional schedule variance due to economies of scale associated with stretch-out of procurement buy profile. (Navy) (Estimating)
Stretch-out of procurement buy profile of 490 missiles from FY 2017 through FY 2022 to FYDP, FY 2023 to FY 2026 (Air Force). (Schedule)
Additional schedule variance due to the stretch-out of the procurement buy profile. (Air Force) (Estimating)
0.0 +15.9
+11.5 +16.3
0.0 +34.6
+11.0 +12.8
Updated hardware estimates based on FRP Milestone data. (Navy) (Estimating) +79.4 +106.6 Updated hardware estimates based on the FRP Milestone data. (Air Force) (Estimating) +93.9 +116.3
Revised estimate for systems engineering and program management as a result of FRP Milestone data. (Navy) (Estimating)
Revised estimate for systems engineering and program management as a result of FRP Milestone data. (Air Force) (Estimating)
+31.6 +40.5
+16.4 +19.9
Adjustment for current and prior escalation. (Estimating) +4.0 +4.5
Adjustment for current and prior escalation. (Support) +0.7 +0.5
Decrease in Other Support due to reduction in requirements of Special Air Training Missiles (Navy). (Support)
Decrease in Other Support due to reduction in requirements of Special Air Training Missiles (Air Force). (Support)
-14.9 -18.5
-5.7 -7.5
Decrease in Initial Spares due to change in procurement profile (Navy). (Support) Increase in Initial Spares due to change in procurement profile (Air Force). (Support) | -9.6 +6.7 |  |  | -12.3 +7.5
Procurement Subtotal | 225 |  |  | 316.9

## Table 35
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: AIM-9X Block II System Improvement Program
Contractor: Raytheon Missiles Systems
Contractor Location: 1151 E Hermans Rd
Tucson, AZ 85756
Contract Number: N00019-11-C-0026
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: March 31, 2011
Definitization Date: March 31, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
19.9 N/A 1 90.7 N/A 1 90.7 90.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to additional effort for Active Optical Target Detector obsolescence, system development and integration, algorithm development, F-22 integration, as well as replacement of Aircraft Interface and Cryo-Cooler Circuit card assemblies which are being driven by obsolescence.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (CPFF) contract.
General Contract Variance Explanation
Earned Value Management (EVM) was only required on one CLIN in this contract. The CLIN Period of Performance ended in September 2014.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 36
Contract Identification
Appropriation: Procurement
Contract Name: AIM-9X Block II Production
Contractor: Raytheon Missile Systems
Contractor Location: 1151 E Hermans Road
Tucson, AZ 85756-9367
Contract Number: N00019-11-C-0001
Contract Type: Firm Fixed Price (FFP), Fixed Price Incentive(Firm Target) (FPIF)
Award Date: September 29, 2011
Definitization Date: September 29, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
61.9 61.9 120 540.9 108.4 1070 540.9 540.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to procurement of additional FY 2011 assets, the awards of Lot 12 and Lot 13 Contracts, addition of Programmable Advanced System Interface Simulator Test Set, increased Spares requirement, Inertial Measurement Unit investigation to include retrofits and upgrades, and AIM-9X Block II sectionalization support equipment in support of the United States Navy (USN) and several FMS customers. Additional Spares were authorized in December 2014 for USN, United States Air Force, and FMS.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP/FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract because an earned value management waiver was granted by the Office of the Assistant Secretary of the Navy (Research, Development and Acquisition) Deputy Assistant of the Navy (Acquisition and Procurement) on January 23, 2012 due to utilization of other methods (i.e., a Cost and Software Data Reporting requirement) to monitor contract performance. In addition, the contract includes FAR Clause 52.216-16 which requires quarterly limitation on payments reporting by the contractor after the first delivery.
Notes
The Contract Ceiling Price applies to only the FPIF CLINs of the contract.
This contract includes FMS and Other Customer Funds.

## Table 37
Contract Identification
Appropriation: Procurement
Contract Name: AIM-9X Obsolescence, S/W Development & Platform Integration
Contractor: Raytheon Company
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85756
Contract Number: N00019-12-C-2002/1
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: May 11, 2012
Definitization Date: May 11, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1.4 N/A N/A 55.6 N/A N/A 55.7 55.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the addition of the following efforts: Engineering Investigations and Missile Software Correction for F-16 Wing Twist, Flight Test Support, Production Software Support, Deficiency Analysis, Engineering Analysis of subsystem hardware, Engineering Change Proposal Preparation, AIM-9X EA-18G HERO and E3 Testing, Air Force Seek Eagle Phase II, AIM-9X Block II Prototype Development, Integration and Flight Test and associated contract fees.
The reduction in Current Contract Price, since the last SAR, is the result of a mathematical error in breaking out CLIN 0113 into a separate Effort (2) per the EVM reporting guidance. CLIN 0113 was completed in September 2015.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (CPFF) contract.
General Contract Variance Explanation
EVM requirements for this Effort (1) applied only to CLINs 103, 105 and 107. The Period of Performance for these CLINs has expired and EVM is no longer reported.

## Table 38
Contract Identification
Appropriation: Procurement
Contract Name: AIM-9X Block II Lot 14 Production
Contractor: Raytheon Company
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85756
Contract Number: N00019-14-C-0053
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 26, 2014
Definitization Date: June 26, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
223.1 229.7 677 227.6 234.5 689 227.6 227.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the procurement of additional AIM-9X Block II Guidance Unit covers in support of the United States Navy, United States Air Force (USAF) and FMS (Netherlands, Singapore, Turkey, and Morocco), as well as the procurement of additional AIM-9X Block II missiles and containers for USAF.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract because an earned value management waiver was granted by the Office of the Assistant Secretary of the Navy (Research, Development and Acquisition) Deputy Assistant of the Navy (Acquisition and Procurement) on June 20, 2014 due to the utilization of other methods (i.e., a Cost and Software Data Reporting requirement) to monitor contract performance. In addition, the contract includes Federal Acquisition Regulation Clause 52.216-16 which requires quarterly limitation on payments reporting by the contractor after the first delivery.

## Table 39
Contract Identification
Appropriation: RDT&E
Contract Name: AIM-9X Obsolescence, S/W Development & Platform Integration (CLIN 0113)
Contractor: Raytheon Missile Systems
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85756
Contract Number: N00019-12-C-2002/2
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: August 05, 2014
Definitization Date: August 05, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
43.8 N/A N/A 43.8 N/A N/A 43.8 43.8
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (8/23/2015) +3.1 -3.1
Previous Cumulative Variances +1.1 -2.1
Net Change +2.0 -1.0
Cost and Schedule Variance Explanations
The favorable net change in the cost variance is due to labor efficiencies in the program's supporting efforts.
The unfavorable net change in the schedule variance is due to delays of suppliers' material and release of Phase 2 software as a result of the technical complexity.
Notes
The Period of Performance for this Contract CLIN expired on September 30, 2015 and therefore ended EVM reporting.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 40
Contract Identification
Appropriation: RDT&E
Contract Name: AIM-9X Block II Lot 15 Production
Contractor: Raytheon
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85756
Contract Number: N00019-15-C-0092
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: March 26, 2015
Definitization Date: March 26, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
26.0 26.0 0 241.5 246.9 576 241.5 241.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to awarding the final Lot 15 contract for AIM-9X Block II Full Rate Production which includes missiles, containers and spare parts in support of the United States Navy, United States Air Force and several FMS customers.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FPIF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract because an earned value management waiver was granted by the Office of the Assistant Secretary of the Navy (Research, Development and Acquisition) Deputy Assistant of the Navy (Acquisition and Procurement) on May 26, 2015 due to the utilization of other methods (i.e., a Cost and Software Data Reporting requirement) to monitor contract performance. In addition, the contract includes Federal Acquisition Regulation Clause 52.216-16 which requires quarterly limitation on payments reporting by the contractor after the first delivery.
Notes
This is the first time this contract is being reported.

## Table 41
Contract Identification
Appropriation: RDT&E
Contract Name: AIM-9X Block II System Improvement Plan III
Contractor: Raytheon
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85756
Contract Number: N00019-15-C-0121/1
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: September 25, 2015
Definitization Date: September 25, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
264.8 N/A 0 264.8 N/A 0 264.8 264.8
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (1/31/2016) +1.2 -1.8
Previous Cumulative Variances -- --
Net Change +1.2 -1.8
Cost and Schedule Variance Explanations
The favorable cumulative cost variance is due to a delay in invoicing for performance taken in the Dome efforts, LOE being time-phased earlier than planned and labor efficiencies.
The unfavorable cumulative schedule variance is due to delays in Operational Flight Software (OFS) OFS.9.4 Algorithm and Software development as well as a late start in the Dome efforts.
Notes
This is the first time this contract is being reported.

## Table 42
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 915 | 915 | 6000 | 15.25%
Total Program Quantity Delivered | 915 | 915 | 6000 | 15.25%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
4099.5
690.6
16.85%
25
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
13
52%
1437.9
35.08%
The above data is current as of February 09, 2016.

## Table 43
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 11, 2016
Source of Estimate: POE
Quantity to Sustain: 6000
Unit of Measure: Total Quantity
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 2014 - FY 2049
The sustaining support consists of systems engineering, program management support, failure analysis, and Surveillance/quality/obsolescence evaluation program. The cost estimate considers a service life stated in the service life letter 8810 dated July 24, 2013 for the All Up Round (AUR) and letter dated September 15, 2010 for the Captive Air Training Missile (CATM). The estimate assumes operational utilization AURs and CATMs as indicated in the following table:
Type | Service | Yearly Qty In- Use | Yearly Flight Hours
CATM | USN | All | 310
| USAF | All | 297
AUR | USN | 188 | 226
| USAF | 225 | 33
Sustainment Strategy
The sustainment strategy for the AIM-9X-2 is essentially the same as the previous AIM-9X missile configurations. The key focus areas include maintenance of key performance requirements, decreasing life cycle costs and ensuring asset availability for warfighters. Specific sustainment initiatives include depot maintenance and repairs, sustaining/systems engineering, program management support, failure analysis and ordnance assessment and continuing system improvement, primarily software support. The cost estimate considers a 20-year sustainment period after delivery of the final production lot. The estimate assumes operational utilization of CATMs and AURs based on historical annual average flight hours for each Service's current total inventory of AIM-9X CATMs and AURs.
Antecedent Information
The AIM-9X Block I is the antecedent system to the AIM-9X Block II. Antecedent costs were derived based on historical data collected via the Visibility and Management of Operating and Support Costs database and estimated through the remainder of the life (FY 2032). A total of 3,097 AIM-9X Block I missiles were procured. The last year of procurement was FY 2010. There is a 20-year service life assumption for the AIM-9X Block I AUR and a 13-year service life assumption for the CATM. The AIM-9X Block I system included a warranty period that accounted for missile repair costs. The AIM-9X Block II system did not include a warranty and was estimated accordingly.

## Table 44
Annual O&S Costs BY2011 $M
Cost Element |  | AIM-9X Blk II Average Annual Cost Per Total Quantity | [5 empty] | AIM-9X (Antecedent) Average Annual Cost Per Total Quantity
Unit-Level Manpower |  | 0 | [5 empty] | 0
Unit Operations |  | 0 | [5 empty] | 2.2
Maintenance |  | 11.36 | [5 empty] | 5.3
Sustaining Support |  | 7.47 | [5 empty] | 5.8
Continuing System Improvements |  | 4.87 | [5 empty] | 5
Indirect Support |  | 0 | [5 empty] | 0.1
Other |  | 0 | [5 empty] | 0
Total |  | 23.7 | [5 empty] | 18.4
Item | Total O&S Cost $M
| AIM-9X Blk II | [7 empty] | AIM-9X (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 826.8 |  |  | 909.5 |  |  | 876.8 |  | 531.9
Then Year | 1274 |  |  | N/A |  |  | 1361.8 |  | N/A
The increase in sustainment cost for the AIM-9X Block II missile from the AIM-9X Block I missile is that the sustainment period went from 29 years for Navy only missile sustainment for Block I to 35 years for Block II. This was based on the quantity of 3,097 Navy missiles being sustained for the Block I program versus the remaining 6,000 Navy and Air Force missiles that will be sustained for the Block II program. The other reason for the increase is using a different Mean-Time- Between-Failure (MTBF) to calculate repair costs. The specification MTBF was used for Block II and the actual MTBF was used to calculate the Block I.
The current estimate has increased due FRP decision and the change in the production profile which pushed sustainment out an additional year.
Equation to Translate Annual Cost to Total Cost
Average Annual Cost is calculated using the total cost divided by the number of years for sustainment.
Total Cost $876.8M divided by 37 years for maintenance equals $23.7M average annual cost per total quantity.
O&S Cost Variance
Category |  |  | BY 2011 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
770.8
Programmatic/Planning Factors 50.0 Increase due to adjusted production profile.
Cost Estimating Methodology 0.0
Cost Data Update 56.0 Increase due to inclusion of initial Block II actuals.
Labor Rate 0.0

## Table 45
Energy Rate | 0
Technical Input | 0
Other | 0
Total Changes | 106
Current Estimate | 876.8
Disposal Estimate Details
Date of Estimate: Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2011 $M):
Disposal costs are not identified at this time.