## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-191
MH-60R Multi-Mission Helicopter (MH-60R)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 12
Cost and Funding 13
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 21
Unit Cost 22
Cost Variance 25
Contracts 28
Deliveries and Expenditures 32
Operating and Support Cost 33

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
MH-60R Multi-Mission Helicopter (MH-60R)
DoD Component
Navy
Responsible Office
CAPT Craig Grubb, PMA 299 Multi-Mission Helicopter Program Executive Office - Air, Anti-Submarine Warfare, Assault & Special Mission
47123 Buse Rd Unit IPT, Suite 156
Patuxent River, MD 20670-1547
craig.d.grubb@navy.mil
Phone: 301-757-5409
Fax: 301-757-5276
DSN Phone: 757-5409
DSN Fax: 757-5276
Date Assigned: December 19, 2014
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 22, 2006
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated November 29, 2010

## Table 6
Mission and Description
The MH-60R Multi-Mission Helicopter (MH-60R) primary mission areas include Anti-Submarine Warfare and Surface Warfare. Secondary mission areas include Search and Rescue, Vertical Replenishment, Naval Surface Fire Support, logistics support, personnel transport, Medical Evacuation, and Very High Frequency/Ultra High Frequency Link Communication Relay. The MH-60R is the central component of the 'Navy Helicopter Master Plan' and the Chief of Naval Operations approved Helicopter Concept of Operations that replaces the aging SH-60B and SH-60F helicopters. The avionics upgrades over the existing SH-60B/F include: a glass cockpit common with the MH-60S; Airborne Low Frequency Sonar (ALFS) as a long-range active dipping sonar; Electronic Support Measures with expanded frequency coverage and location detection; Multi-Mode Radar with long-range search, Automatic Radar Periscope Detection and Discrimination; imaging Inverse Synthetic Aperture Radar; Forward Looking Infra-Red for imaging and laser target designation; Commercial Off-The-Shelf Acoustic Processor for acoustic processing for ALFS and sonobuoys; Integrated Self Defense; Advanced Precision Kill Weapon System; and the Mission Planning System. MH-60R sensors and real-time exchange of tactical data with the host ship will bring a new dimension of battle space control to the Naval Commander.

## Table 7
Executive Summary
As of December 31, 2015, a total of 229 aircraft have been delivered; 216 domestic and 15 Royal Australian Navy. To date, seventeen MH-60R squadrons have been established. FRP deliveries to the fleet continue on schedule in support of squadron standups. FY 2016 Multi-Year 2 (MY2) contract Common Cockpit & Mission Systems and Multi-Year 8 (MY8) contract Airframe options have been awarded for the delivery of the final 29 of 280 MH-60R aircraft. Nineteen Common Data Link installations on Cruiser destroyer ships have been completed. Installation is complete on USS Curtis Wilbur (DDG-54) but awaiting acceptance which requires a successful live underway event with an MH-60R. Additionally, installations are underway on USS Milius (DDG-69), USS Sterett (DDG-104), USS Dewey (DDG-105) and the USS Cape St. George (CG-71).
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone II | Jul 1993 | Jul 1993 | Jan 1994 | Jul 1993
TECHEVAL
Start | Oct 2004 | Oct 2004 | Apr 2005 | Aug 2004
Complete | Feb 2005 | Feb 2005 | Aug 2005 | Feb 2005
OPEVAL
Start | May 2005 | May 2005 | Nov 2005 | May 2005
Complete | Sep 2005 | Sep 2005 | Mar 2006 | Sep 2005
IOC | Dec 2005 | Dec 2005 | Jun 2006 | Dec 2005
Milestone III | Jan 2006 | Jan 2006 | Jul 2006 | Mar 2006
Automatic Radar Periscope Detection and Discriminator (ARPDD)
ARPDD Interim Process Review (IPR) (System Design Development (SDD) Award) | N/A | Apr 2008 | Oct 2008 | Apr 2008
ARPDD Critical Design Review (CDR) | N/A | Jun 2009 | Dec 2009 | Apr 2009
Operational Test (OT) Start | N/A | May 2012 | Nov 2012 | Aug 2012
IOC | N/A | Jul 2013 | Jan 2014 | Jan 2014
Change Explanations
None
Acronyms and Abbreviations
OPEVAL - Operational Evaluation TECHEVAL - Technical Evaluation

## Table 11
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Availability (%): Mission Capable
82 | 82 | 70 | 82.3 | 73
Net Ready: All interfaces, services, policy-enforcement, controls, and data-sharing of the NCOW RM and GIG-KIPs will be satisfied to the requirements of the specific Joint integrated architecture products (including data correctness, data availability, and data processing), and information assurance accreditation specified in the threshold and objective values.
100% of requirements | 100% of requirements | 100% of enterprise - level or critical requirements | 100% of enterprise - level or critical requirements | 100% of enterprise - level or critical requirements
Crew Protection: Crashworthiness, Crew Restraint, and Egress
Crew Seating 35/25/20G, Passenger 20/20/20 | Crew Seating 35/25/20G, Passenger 20/20/20 | Crew Seating 20/20/20G, Passenger 14/13/12G | Crew Seating 20/20/20G, Passenger 14/13/12G | Crew Seating 20/20/20G, Passenger 14/13/12G
(Ch-1)
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Production Document (CPD) dated November 28, 2005
Change Explanations
(Ch-1) The decrease in the current estimate for Availability (%): Mission Capable from 78.9 to 73 does not indicate a negative trend. Since the MH-60R is resourced on a Ready For Tasking/Ready Basic Aircraft standard, a metric which changes monthly as units progress through the Fleet Readiness Training Plan, the corresponding Mission Capable rate also changes monthly, but is expected to remain above threshold.
Acronyms and Abbreviations
G - Gravitational Force
GIG - Global Information Grid KIPs - Key Interface Profiles
NCOW RM - Net-Centric Operational Warfare Reference Model

## Table 12
Track to Budget
RDT&E
Appn |  | BA | PE
Navy 1319 05 0604212N
Project | Name
2412 ASW & Other HELO Development/MH-60R Lamps
Navy 1319 05 0604216N
(Sunk)
Project | Name
1707 MH-60R Development
9215 Multi-Mission HELO Upgrade Development/MH- 60 PMLCC
(Sunk)
Notes
RDT&E funds in Project Element 0604216N Project Unit 1707 in FY 2018 and beyond do not affect MH-60R production and therefore are not related to the acquisition program.
Procurement
Appn |  | BA | PE
Navy 1506 01 0204243N
Line Item | Name
0182 MH-60R
Notes: MH-60R - Funding does not include initial spares
Navy 1506 06 0204243N
Line Item | Name
0605 Spares and Repair Parts (Sunk)

## Table 13
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2006 $M | [6 empty] | BY 2006 $M |  | TY $M
| SAR Baseline Production Estimate |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 1519 |  |  | 1718.9 | 1890.8 |  |  | 1853 |  | 1375.7 |  |  | 1570.4 |  | 1720.8
Procurement |  | 9108 |  |  | 11360.2 | 12495.9 |  |  | 10384.4 |  | 10049 |  |  | 12573.5 |  | 11487.1
Flyaway |  | -- |  |  | -- | -- |  |  | 8625.5 |  | -- |  |  | -- |  | 9570.2
Recurring |  | -- |  |  | -- | -- |  |  | 7454.3 |  | -- |  |  | -- |  | 8292.5
Non Recurring |  | -- |  |  | -- | -- |  |  | 1171.2 |  | -- |  |  | -- |  | 1277.7
Support |  | -- |  |  | -- | -- |  |  | 1758.9 |  | -- |  |  | -- |  | 1916.9
Other Support |  | -- |  |  | -- | -- |  |  | 1474.6 |  | -- |  |  | -- |  | 1617.4
Initial Spares |  | -- |  |  | -- | -- |  |  | 284.3 |  | -- |  |  | -- |  | 299.5
MILCON |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M |  | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total |  | 10627 |  |  | 13079.1 | N/A |  |  | 12237.4 |  | 11424.7 |  |  | 14143.9 |  | 13207.9
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The current APB cost estimate provided sufficient resources to execute the program under normal conditions, encountering average levels of technical, schedule and programmatic risk and external interference. It was consistent with average resource expenditures on historical efforts of similar size, scope, and complexity and represents a notional 50% confidence level.
Total Quantity
Quantity |  |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  |  | 2 |  |  |  | 2 |  |  |  |  | 2
Procurement |  |  | 252 |  |  |  | 298 |  |  |  |  | 278
Total |  |  | 254 |  |  |  | 300 |  |  |  |  | 280

## Table 14
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 1696.6 | 18.9 |  | 5.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1720.8
Procurement | 10483.5 | 942.4 |  | 61.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 11487.1
MILCON | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 12180.1 | 961.3 |  | 66.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 13207.9
PB 2016 Total | 12217.7 | 991.5 |  | 75.3 |  | 5.7 |  | 2.6 |  | 2.7 |  | 0 |  | 0 |  | 13295.5
Delta | -37.6 | -30.2 |  | -8.8 |  | -5.7 |  | -2.6 |  | -2.7 |  | 0 |  | 0 |  | -87.6
Funding Notes
Prior Year Procurement amount differs from FY 2017 PB Submission due to $40 Million FY 2014 rescission reflected in the FY 2016 Appropriations Bill. The $40 Million has been removed from the SAR submittal. In the PB 2017 submittal the rescission was noted but the funding was not removed.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2
Production | 0 |  | 249 |  | 29 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 278
PB 2017 Total | 2 |  | 249 |  | 29 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 280
PB 2016 Total | 2 |  | 249 |  | 29 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 280
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 15
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.2
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.5
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.7
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 70.7
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 70
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 65.1
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.2
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.3
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 209
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 110.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.8
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 133.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 81.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 78.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 74.1
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.4
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.7
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.9
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.3
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 1720.8

## Table 16
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2006 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.7
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.8
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.6
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.2
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.2
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 82.7
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 75.7
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63.4
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 97.1
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 235.3
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 122.1
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 144.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 85.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 79.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.4
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.5
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 1853

## Table 17
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | 5 | 175.9 |  | -- |  | 25.8 |  | 201.7 |  | 35.3 |  | 237
2001 |  | -- | -- |  | -- |  | 44.7 |  | 44.7 |  | 7.3 |  | 52
2002 |  | -- | -- |  | -- |  | 11.2 |  | 11.2 |  | 3.8 |  | 15
2003 |  | -- | 32.5 |  | -- |  | 36.5 |  | 69 |  | 52.4 |  | 121.4
2004 |  | 4 | 168.4 |  | -- |  | 68.4 |  | 236.8 |  | 108.7 |  | 345.5
2005 |  | 6 | 204 |  | -- |  | 71.4 |  | 275.4 |  | 155.4 |  | 430.8
2006 |  | 12 | 394.8 |  | -- |  | 58.2 |  | 453 |  | 204 |  | 657
2007 |  | 25 | 714.6 |  | -- |  | 71.9 |  | 786.5 |  | 131.3 |  | 917.8
2008 |  | 28 | 868.8 |  | -- |  | 95.2 |  | 964 |  | 115.6 |  | 1079.6
2009 |  | 30 | 924.7 |  | -- |  | 121.7 |  | 1046.4 |  | 146.4 |  | 1192.8
2010 |  | 24 | 668.9 |  | -- |  | 95.5 |  | 764.4 |  | 186.8 |  | 951.2
2011 |  | 24 | 734 |  | -- |  | 110.4 |  | 844.4 |  | 220.4 |  | 1064.8
2012 |  | 24 | 730.5 |  | -- |  | 138.1 |  | 868.6 |  | 83.8 |  | 952.4
2013 |  | 19 | 609.6 |  | -- |  | 70.6 |  | 680.2 |  | 62.4 |  | 742.6
2014 |  | 19 | 614.5 |  | -- |  | 62.5 |  | 677 |  | 63 |  | 740
2015 |  | 29 | 785.9 |  | -- |  | 22.2 |  | 808.1 |  | 175.5 |  | 983.6
2016 |  | 29 | 665.4 |  | -- |  | 173.4 |  | 838.8 |  | 103.6 |  | 942.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | 61.2 |  | 61.2
Subtotal |  | 278 | 8292.5 |  | -- |  | 1277.7 |  | 9570.2 |  | 1916.9 |  | 11487.1

## Table 18
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2006 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | 5 | 192.9 |  | -- |  | 28.3 |  | 221.2 |  | 38.7 |  | 259.9
2001 |  | -- | -- |  | -- |  | 48.4 |  | 48.4 |  | 7.9 |  | 56.3
2002 |  | -- | -- |  | -- |  | 12 |  | 12 |  | 4.1 |  | 16.1
2003 |  | -- | 34.1 |  | -- |  | 38.3 |  | 72.4 |  | 55 |  | 127.4
2004 |  | 4 | 172.1 |  | -- |  | 69.9 |  | 242 |  | 111.2 |  | 353.2
2005 |  | 6 | 202.8 |  | -- |  | 71 |  | 273.8 |  | 154.5 |  | 428.3
2006 |  | 12 | 381.9 |  | -- |  | 56.3 |  | 438.2 |  | 197.3 |  | 635.5
2007 |  | 25 | 675.5 |  | -- |  | 68 |  | 743.5 |  | 124.1 |  | 867.6
2008 |  | 28 | 809.1 |  | -- |  | 88.7 |  | 897.8 |  | 107.7 |  | 1005.5
2009 |  | 30 | 849.4 |  | -- |  | 111.8 |  | 961.2 |  | 134.4 |  | 1095.6
2010 |  | 24 | 601.8 |  | -- |  | 85.9 |  | 687.7 |  | 168.1 |  | 855.8
2011 |  | 24 | 647.6 |  | -- |  | 97.4 |  | 745 |  | 194.4 |  | 939.4
2012 |  | 24 | 635.4 |  | -- |  | 120.1 |  | 755.5 |  | 72.9 |  | 828.4
2013 |  | 19 | 524.6 |  | -- |  | 60.7 |  | 585.3 |  | 53.7 |  | 639
2014 |  | 19 | 522 |  | -- |  | 53.1 |  | 575.1 |  | 53.5 |  | 628.6
2015 |  | 29 | 657.7 |  | -- |  | 18.6 |  | 676.3 |  | 146.8 |  | 823.1
2016 |  | 29 | 547.4 |  | -- |  | 142.7 |  | 690.1 |  | 85.2 |  | 775.3
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | 49.4 |  | 49.4
Subtotal |  | 278 | 7454.3 |  | -- |  | 1171.2 |  | 8625.5 |  | 1758.9 |  | 10384.4

## Table 19
Cost Quantity Information 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2006 $M
2000 | 5 | 192.9
2001 | -- | --
2002 | -- | --
2003 | -- | --
2004 | 4 | 169.2
2005 | 6 | 170.6
2006 | 12 | 326.7
2007 | 25 | 686.6
2008 | 28 | 781.6
2009 | 30 | 857.9
2010 | 24 | 627.9
2011 | 24 | 624.6
2012 | 24 | 614.2
2013 | 19 | 538
2014 | 19 | 478.3
2015 | 29 | 739.8
2016 | 29 | 646
2017 | -- | --
Subtotal | 278 | 7454.3

## Table 20
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1999-05-10 | 2005-04-05
Approved Quantity | 21 | 15
Reference | Navy Program Decision Meeting ADM | Navy Program Review ADM
Start Year | 2002 | 2002
End Year | 2007 | 2007
In May 1999 the Assistant Secretary of the Navy (Research, Development and Acquisition) approved a total LRIP quantity of
21. In April 2005, the LRIP quantity was further reduced from 21 to 15 due to revised acquisition strategy.

## Table 21
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Saudi Arabia | 2015-07-20 | 10 | 1079 | Total cost based on Letter of Offer and Acceptance signed July 20, 2015. FMS Case SR-P-SBU includes initial sustainment (spares, support equipment, pubs, training, tech support) and Tactical Operational Flight Trainer.
Denmark | 2012-12-06 | 0 | 308.7 | Total Cost based on Letter of Offer and Acceptance signed December 6, 2012 for Sustainment Support to include Aircraft Spares, Support Equipment, Repair of Repairables, Publications, Technical Data, Technical Support and Training. FMS Case DE-P-GBP.
Denmark | 2012-12-06 | 9 | 640 | Total Cost based on Letter of Offer and Acceptance signed December 6, 2012. FMS Case DE-P-SAE includes initial sustainment (spares, support equipment, pubs, training, tech support) and Mission Operational Flight Trainer.
Australia | 2011-06-06 | 0 | 755 | Total Cost based on Letter of Offer and Acceptance signed June 6, 2011 for ten years Through Life Support, Spares, Support Equipment, Publications, Technical Support and Training. FMS Cases AT-P- GTC and AT-P-GXO.
Australia | 2011-06-06 | 24 | 2052.7 | Total Cost based on Letter of Offer and Acceptance signed June 6, 2011. FMS Case AT-P-SCF includes initial sustainment (spares, support equipment, pubs, training, tech support) and Tactical Operational Flight Trainer.
Notes
Nuclear Costs
None

## Table 22
Unit Cost
Unit Cost Report
Item |  | BY 2006 $M | BY 2006 $M |  | % Change
|  | Current UCR Baseline (Nov 2010 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 13079.1 |  |  | 12237.4
Quantity | 300 |  |  | 280
Unit Cost | 43.597 |  |  | 43.705 |  | 0.25
Average Procurement Unit Cost
Cost | 11360.2 |  |  | 10384.4
Quantity | 298 |  |  | 278
Unit Cost | 38.121 |  |  | 37.354 |  | -2.01
Item |  | BY 2006 $M | BY 2006 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(May 2004 APB)
Program Acquisition Unit Cost
Cost | 9894.9 |  |  | 12237.4
Quantity | 243 |  |  | 280
Unit Cost | 40.72 |  |  | 43.705 |  | 7.33
Average Procurement Unit Cost
Cost | 8361.1 |  |  | 10384.4
Quantity | 241 |  |  | 278
Unit Cost | 34.693 |  |  | 37.354 |  | 7.67

## Table 23
Unit Cost History
Item | [7 empty] | Date |  |  | BY 2006 $M | [7 empty] | TY $M
[11 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Jun 1995 | [5 empty] | 26.155 |  |  |  |  | 22.846 |  |  |  | 29.981 |  |  |  | 27.062
APB as of January 2006 |  |  |  |  | May 2004 | [5 empty] | 40.208 |  |  |  |  | 34.255 |  |  |  | 41.427 |  |  |  | 36.09
Revised Original APB |  |  |  |  | May 2004 | [5 empty] | 40.208 |  |  |  |  | 34.255 |  |  |  | 41.427 |  |  |  | 36.09
Prior APB |  |  |  |  | Sep 2008 | [5 empty] | 42.626 |  |  |  |  | 36.143 |  |  |  | 45.746 |  |  |  | 39.877
Current APB |  |  |  |  | Nov 2010 | [5 empty] | 43.597 |  |  |  |  | 38.121 |  |  |  | 47.146 |  |  |  | 42.193
Prior Annual SAR |  |  |  |  | Dec 2014 | [5 empty] | 43.894 |  |  |  |  | 37.503 |  |  |  | 47.484 |  |  |  | 41.583
Current Estimate |  |  |  |  | Dec 2015 | [5 empty] | 43.705 |  |  |  |  | 37.354 |  |  |  | 47.171 |  |  |  | 41.321
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  |  | Oth |  |  |  | Spt |  | Total
44.979 -1.370 -18.295 0.747 3.963 11.669 0.000 3.286 0.000 44.979
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  | Oth |  |  | Spt |  |  | Total
44.979 -0.282 -0.852 0.465 1.405 1.248 0.000 0.208 2.192 47.171

## Table 24
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [11 empty] | APUC Production Estimate
| Econ | Qty |  |  | Sch | Eng | Est |  | Oth |  | Spt | Total
39.877 -1.249 -15.767 0.753 3.098 10.132 0.000 3.033 0.000 39.877
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [11 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng | Est | Oth |  | Spt |  | Total
39.877 -0.249 -0.381 0.468 0.449 0.947 0.000 0.210 1.444 41.321
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  |  | Current Estimate
Milestone I |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Milestone II |  |  | N/A |  |  | Jul 1993 |  |  |  | Jul 1993 |  |  |  | Jul 1993
Milestone III |  |  | N/A |  |  | Oct 2001 |  |  |  | N/A |  |  |  | Mar 2006
IOC |  |  | N/A |  |  | Mar 2001 |  |  |  | Dec 2005 |  |  |  | Dec 2005
Total Cost (TY $M) |  |  | N/A |  |  | 11424.7 |  |  |  | 11424.7 |  |  |  | 13207.9
Total Quantity |  |  | N/A |  |  | 254 |  |  |  | 254 |  |  |  | 280
PAUC |  |  | N/A |  |  | 44.979 |  |  |  | 44.979 |  |  |  | 47.171

## Table 25
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1375.7 10049.0 -- 11424.7
Economic |  | -9.4 |  | -46.2 |  | -- |  | -55.6
Quantity |  | -- |  | 931.1 |  | -- |  | 931.1
Schedule |  | -- |  | 130.1 |  | -- |  | 130.1
Engineering |  | 268.7 |  | 147.8 |  | -- |  | 416.5
Estimating |  | 100.4 |  | 273.7 |  | -- |  | 374.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 74.6 |  | -- |  | 74.6
Subtotal |  | 359.7 |  | 1511.1 |  | -- |  | 1870.8
Current Changes Economic |  | -0.3 |  | -23.1 |  | -- |  | -23.4
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -23.1 |  | -- |  | -23.1
Estimating |  | -14.3 |  | -10.5 |  | -- |  | -24.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -16.3 |  | -- |  | -16.3
Subtotal |  | -14.6 |  | -73 |  | -- |  | -87.6
Total Changes |  | 345.1 |  | 1438.1 |  | -- |  | 1783.2
CE - Cost Variance |  | 1720.8 |  | 11487.1 |  | -- |  | 13207.9
CE - Cost & Funding |  | 1720.8 |  | 11487.1 |  | -- |  | 13207.9

## Table 26
Summary BY 2006 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
1519.0 9108.0 -- 10627.0
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 793.7 |  | -- |  | 793.7
Schedule |  | -- |  | 52.5 |  | -- |  | 52.5
Engineering |  | 238.4 |  | 120.3 |  | -- |  | 358.7
Estimating |  | 107 |  | 300.9 |  | -- |  | 407.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 50.5 |  | -- |  | 50.5
Subtotal |  | 345.4 |  | 1317.9 |  | -- |  | 1663.3
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -18.9 |  | -- |  | -18.9
Estimating |  | -11.4 |  | -9.3 |  | -- |  | -20.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -13.3 |  | -- |  | -13.3
Subtotal |  | -11.4 |  | -41.5 |  | -- |  | -52.9
Total Changes |  | 334 |  | 1276.4 |  | -- |  | 1610.4
CE - Cost Variance |  | 1853 |  | 10384.4 |  | -- |  | 12237.4
CE - Cost & Funding |  | 1853 |  | 10384.4 |  | -- |  | 12237.4
Previous Estimate: December 2014

## Table 27
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -0.3
Adjustment for current and prior escalation. (Estimating) +0.2 +0.2
Removal of funds in FY 2018 and beyond that are not related to this acquisition program. (Estimating)
Revised estimate due to FMS cost sharing of Very High Frequency Omni Ranging/Instrument Landing System development and testing costs. (Estimating)
-8.7 -11.0
-2.0 -2.5
Revised estimate to reflect prior year actuals. (Estimating) | -0.9 |  |  | -1
RDT&E Subtotal | -11.4 |  |  | -14.6
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -23.1
Adjustment for current and prior escalation. (Estimating) +16.5 +19.7
Congressional reduction resulting in program de-scope in acquisition program closeout and production line shutdown activities. (Engineering)
-18.9 -23.1
Revised estimate to reflect actual cost of Government Furnished Equipment. (Estimating) |  | -5.1 |  | -5.8
Revised estimate to reflect actual cost of Airborne Low Frequency Sonar. (Estimating) |  | -20.7 |  | -24.4
Adjustment for current and prior escalation. (Support) |  | 2.4 |  | 2.8
Decrease in Other Support due to refined labor cost estimate. (Support) |  | -15.7 |  | -19
Decrease in Initial Spares due to refined cost estimate. (Support) |  | 0 |  | -0.1
Procurement Subtotal |  | -41.5 |  | -73

## Table 28
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: Raytheon Integrated Defense Systems ALFS Lot 9
Contractor: Raytheon Integrated Defense Systems
Contractor Location: 1847 W. Main Rd
Portsmouth, RI 02871-1087
Contract Number: N00019-11-C-0077
Contract Type: Firm Fixed Price (FFP)
Award Date: September 27, 2011
Definitization Date: September 27, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
81.7 N/A 24 162.8 N/A 49 162.8 162.8
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a contract modification awarded in December 2011 for additional scope for procurement of the 25 Royal Australian Navy Airborne Low Frequency Sonar systems and a contract modification awarded January 2014 for system reliability improvements .
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 29
Contract Identification
Appropriation: Procurement
Contract Name: MH-60R Airframe (Lots 10-14)
Contractor: Sikorsky Aircraft Corporation (SAC)
Contractor Location: 6900 Main Street
Stratford, CT 06614-1385
Contract Number: W58RGZ-12-C-0008
Contract Type: Firm Fixed Price (FFP)
Award Date: July 06, 2012
Definitization Date: July 06, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1934.7 N/A 131 1819.5 N/A 120 1819.5 1819.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the FY 2014 PB reduction of 11 aircraft.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 30
Contract Identification
Appropriation: Procurement
Contract Name: Raytheon Integrated Defense Systems ALFS Lot 10 & 11
Contractor: Raytheon Integrated Defense Systems
Contractor Location: 1847 W. Main Rd
Portsmouth, RI 02871-1087
Contract Number: N00019-13-C-0012
Contract Type: Firm Fixed Price (FFP)
Award Date: December 20, 2012
Definitization Date: December 20, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
158.6 N/A 48 258.4 N/A 80 258.4 258.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications, award of $33M for Lot XII in August 2015, award of $65.8M for Lot XIII in November 2015, and $1M in miscellaneous contract modifications.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 31
Contract Identification
Appropriation: Procurement
Contract Name: MH-60R Common Cockpit & Mission Systems (Lots 10-14)
Contractor: Lockheed Martin Mission Systems and Sensors (LM MS2)
Contractor Location: 1801 State Route 17C
Owego, NY 13827-3998
Contract Number: N00019-11-C-0020
Contract Type: Firm Fixed Price (FFP)
Award Date: April 05, 2012
Definitization Date: April 05, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1107.7 N/A 131 1038.0 N/A 120 1038.0 1038.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the FY 2014 PB reduction of 11 aircraft.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.

## Table 32
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 2 | 2 | 2 | 100%
Production | 170 | 215 | 278 | 77.34%
Total Program Quantity Delivered | 172 | 217 | 280 | 77.5%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
13207.9
10617.4
80.39%
28
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
27
96.43%
13141.4
99.5%
The above data is current as of February 09, 2016.
A total of 231 aircraft have been delivered; of that 217 were domestic and are included in the MH-60R deliveries data above, the remaining 16 are for the Royal Australian Navy.

## Table 33
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 20, 2016
Source of Estimate: POE
Quantity to Sustain: 280
Unit of Measure: Aircraft
Service Life per Unit: 24.60 Years
Fiscal Years in Service: FY 2002 - FY 2042
O&S Cost uses FY 2016 PB Escalation Indices.
Actual aircraft flight hour data used to calculate the 10,000 hour service life. Maintenance Costs consisting of Aviation Depot Level Repairable and Consumables are now estimated using a bottoms up model, utilizing both historical costs and reliability performance to date for the MH-60R which includes the cost savings of new I-level capabilities, instead of the observed historical cost ratios from other similar H-60s. In addition, a MH-60R specific manning document and sundown plan is now being utilized instead of the legacy manning documents for other H-60 platforms. A phased approach estimate includes the ramp-up of aircraft as they are introduced to the fleet through the retirement of MH-60R aircraft from service.
Aircraft Attrition Rate = 0.2% of Total Active Inventory (TAI) per Year Aircraft Pipeline Rate = 17.6% of TAI per year
Average Flight Hours per Month per Aircraft = 33.9 Total Operating Aircraft Years = 5,666
Sustainment Strategy
Organizational, Intermediate, and Depot level maintenance capabilities. Organizational and Intermediate level military maintenance support.
Depot level government and contractor mixed maintenance support. Performance Based Logistics Contract: Seahawk 2015 (+1,700 parts).
Antecedent Information
The antecedent system is the SH-60B/F aircraft. All costs are from the FY 2015 Naval Visibility and Management of Operating and Support Costs (VAMOSC) Aviation Type Model Series Report database (data from 2009 through 2014) and the FY 2015 Aircraft Planning Data File Primary Aircraft Authorization. Indirect Support is a function of Unit Level Manpower costs.
Legacy systems have experienced and continue to experience service life adjustments and system modifications that make the compilation of Total O&S cost by assuming a static service life (e.g. 25 years) not credible.
In addition, the capture of O&S data in available reporting systems has changed significantly over time. VAMOSC, the Navy's official system for collecting and reporting O&S cost, provides cost from 1997 - 2014. The cost data for platforms in existence prior to 1997 is either unavailable or incomplete. In summary, sufficient historical data and resources do not exist to create a comparable, credible Total O&S cost.

## Table 34
For comparison purposes, the BY Antecedent Total O&S Costs is the product of the Antecedent’s Average Annual Cost per Aircraft and the Operational Aircraft Years of the MH-60R.
Annual O&S Costs BY2006 $M
Cost Element |  | MH-60R Average Annual Cost Per Aircraft | [5 empty] | SH-60B/F (Antecedent) Average Annual Cost Per Aircraft
Unit-Level Manpower |  | 1.801 | [5 empty] | 1.85
Unit Operations |  | 0.233 | [5 empty] | 0.21
Maintenance |  | 1.848 | [5 empty] | 2.123
Sustaining Support |  | 0.121 | [5 empty] | 0.105
Continuing System Improvements |  | 0.276 | [5 empty] | 0.224
Indirect Support |  | 0.789 | [5 empty] | 0.848
Other |  | 0 | [5 empty] | 0
Total |  | 5.068 | [5 empty] | 5.36
.
Item | Total O&S Cost $M
| MH-60R | [7 empty] | SH-60B/F (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year | 36067.5 |  |  | 39674.3 |  |  | 28716.6 |  | 30369.8
Then Year | 49181.1 |  |  | N/A |  |  | 41878.2 |  | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Equation to Translate Annual Cost to Total Cost
The Average Annual Cost per Aircraft for the MH-60R is calculated by dividing the Total O&S Cost by the Total Operating Aircraft Years for the program.
Total O&S Cost ($28,716.6M) / Total Operating Aircraft Years (5,666) = Average Annual Cost per Aircraft ($ 5.068M)
O&S Cost Variance
Category |  |  | BY 2006 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
28360.7
Programmatic/Planning Factors 298.4 Aircraft Planning Data File and Depot Schedule Update Cost Estimating Methodology -134.8 Updated In-Service training munitions using actual costs
vice legacy data
Cost Data Update 22.0 Updated historical cost information
Labor Rate -252.4 Composite Labor Rates update
Energy Rate -47.2 Fuel rate update
Technical Input 469.9 Increased consumable material cost estimate to reflect historical performance

## Table 35
Other 0.0
Total Changes 355.9
Current Estimate 28716.6
Disposal Estimate Details
Date of Estimate: January 20, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2006 $M): Total costs for disposal of all Aircraft are 70.0
The Rough Order of Magnitude estimate will be refined as the System Disposal Plan Annex to the Life Cycle Sustainment Plan is developed.