## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-345
Mobile User Objective System (MUOS)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 15
Cost and Funding 16
Low Rate Initial Production 29
Foreign Military Sales 30
Nuclear Costs 30
Unit Cost 31
Cost Variance 34
Contracts 37
Deliveries and Expenditures 42
Operating and Support Cost 43

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Mobile User Objective System (MUOS)
DoD Component
Navy
Responsible Office
CAPT Joseph Kan
Program Executive Office (Space Systems) 4301 Pacific Highway
San Diego, CA 92110-3127
joseph.kan@navy.mil
Phone: | 619-524-7756
Fax: | 619-524-7861
DSN Phone: | 524-7756
DSN Fax: Date Assigned: | December 13, 2013
References
SAR Baseline (Production Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated March 15, 2008
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated July 24, 2012

## Table 6
Mission and Description
The Mobile User Objective System (MUOS) is a narrowband Military Satellite Communications (MILSATCOM) system that supports a worldwide, multi-Service population of mobile and fixed-site terminal users in the Ultra High Frequency (UHF) band, providing increased communications capabilities to smaller terminal users while still supporting interoperability to legacy terminals.
MUOS adapts a commercial third generation Wideband Code Division Multiple Access (WCDMA) cellular phone network architecture and combines it with geosynchronous satellites (in place of cell towers) to provide a new and more capable UHF MILSATCOM system. The constellation of four operational satellites and ground network control will provide greater than ten times the system capacity of the current UHF Follow-On (UFO) constellation.
MUOS includes the satellite constellation, a ground control and network management system, and a new waveform for user terminals. The space segment is comprised of a constellation of four geosynchronous satellites, plus one on-orbit spare.
The ground system includes the ground transport, network management, satellite control, and associated infrastructure to both fly the satellites and manage the users’ communications. MUOS is designed to support users that require greater mobility, higher data rates, and improved operational availability. The new waveform is termed the MUOS Common Air Interface (CAI), a Software Communications Architecture compliant modulation technique for the Joint Tactical Radio System terminals.
The flow of information between users when MUOS is operational will be much different than today’s systems. Users will communicate with the satellite via UHF WCDMA links and the satellites will relay this to one of four interconnected ground sites located in Wahiawa (Hawaii), Chesapeake (Virginia), Niscemi (Italy), and Geraldton (Australia) via a Ka-band feeder link. These facilities identify the destination of the communications, and route the information to the appropriate ground site for Ka-band uplink to the satellite and UHF WCDMA downlink to the correct users. A network management facility, located at Wahiawa, will feature a government-controlled, priority-based resource management capability that will be adaptable and responsive to changing operational communications requirements. Additionally, MUOS will provide access to select Defense Information System Network services, providing a voice and data capability that has not been available to UHF MILSATCOM users on prior systems. For satellite telemetry, tracking, and commanding, MUOS will use existing control centers operated by the Naval Satellite Operations Center Headquarters at Point Mugu, California, and their detachment at Schriever Air Force Base, Colorado Springs, Colorado.
When MUOS is fielded, it will serve a mixed terminal population. Some users will have terminals only able to support the legacy waveforms while other users will have newer terminals able to support the MUOS CAI. Each MUOS satellite carries a legacy payload similar to that flown on UFO-11. These legacy payloads will continue to support legacy terminals, allowing for a more gradual transition to the MUOS WCDMA waveform.

## Table 7
Executive Summary
The program office continues to make significant progress toward fielding the complete MUOS constellation and capability. MUOS Information Assurance (IA) accreditations are in place, net-centric capabilities have been validated, and MUOS-1, MUOS-2, and MUOS-3 are providing reliable legacy ultra-high frequency satellite communications capability to the warfighter. MUOS-3 was conditionally accepted by the Navy in June 2015, and legacy operations capability commenced January 2016. MUOS-4 successfully launched in September 2015, completed initial on-orbit testing, and was accepted by the Navy in November 2015. MUOS-4 legacy operations capability is planned to commence by April 2016. Three of four MUOS ground sites are operational. MUOS-5 met the MUOS APB milestone "5th Satellite Ready to Ship", and will support Initial Launch Capability in May 2016. The program continues to work with the State Department and the Secretary of Defense regarding the Italian court-issued Niscemi work sequestration.
The program entered Multi-Service Operational Test and Evaluation which consists of two separate and distinct tests. The first test was completed on November 20, 2015 and evaluated the Wideband Code Division Multiple Access capability. The second test is focused on the cyber security aspects of operational assessment and is on schedule for April 2016. The subsequent operational evaluation report is anticipated by July 2016. Deficiencies discovered during testing are being addressed via incremental software releases.
The annual MUOS Gate 6 Sufficiency Review/Configuration Steering Board (CSB) was presented to the Principal Military Deputy to the Assistant Secretary of the Navy for Research, Development and Acquisition in August 2015. The PM identified significant growth in the MUOS O&S cost which resulted in an APB breach for which the PM submitted a Program Deviation Report dated November 6, 2015. The principal O&S breach cost driver is hardware/software obsolescence. The program’s resource sponsor identified $188M that was applied across the FYDP for addressing operations and sustainment, obsolescence, and cyber/IA issues. The remaining funding shortfalls are being addressed by the program office via the budget process.
The MUOS constellation consists of five on-orbit satellites, four of which are active, and one that is an on-orbit spare. The MUOS APB reflects a sixth satellite for replenishment. The current estimate for this replenishment satellite is $1.4B (TY), primarily due to parts obsolescence and the non-recurring engineering cost of re-establishing the satellite production line. Due to the estimated high cost of the sixth satellite and lack of available funding, the CSB determined that the procurement is impractical and unaffordable. The CSB recommended a reduction of the MUOS satellite quantity in the APB from six to five satellites. Pending approval of the revised MUOS cost estimate by the OSD CAPE, the cost/quantity changes will be incorporated into a revised APB and in subsequent SAR submissions.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
The schedule breach was previously reported in the December 2013 SAR. The "3rd Satellite Ready to Ship" milestone was met when the satellite was shipped in November 2014 and subsequently launched in January 2015.
Increases due to hardware and software obsolescence, Information Assurance/cybersecurity existing/emerging vulnerabilities, and new scope attribute to waveform support, End-to-End implementation and Electro-Magnetic Interference mitigation were incorporated into the MUOS O&S cost estimate, which resulted in an APB O&S threshold cost breach.
A Program Deviation Report was submitted November 6, 2015 to the Navy. The MUOS PM will continue to work with the Navy Resource Sponsor via the budget process to fund the total program sustainment requirements. The MUOS PM will incorporate a revised cost estimate into the APB.
Nunn-McCurdy Breaches

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Key Decision Point B | Sep 2004 | Sep 2004 | Mar 2005 | Sep 2004
Key Decision Point C | Oct 2006 | Oct 2006 | Apr 2007 | Aug 2006
Build Approval | Oct 2007 | Oct 2007 | Apr 2008 | Feb 2008
Follow-On Buy | Oct 2008 | Oct 2008 | Apr 2009 | Oct 2008
MUOS On-Orbit Capability | Mar 2010 | N/A | N/A | N/A
MUOS Waveform Certification | Apr 2010 | N/A | N/A | N/A
2nd Satellite Operational | Mar 2011 | N/A | N/A | N/A
MUOS Ready to Ship | N/A | Dec 2011 | May 2012 | Dec 2011
3rd Satellite Operational | Mar 2012 | N/A | N/A | N/A
4th Satellite Operational | Mar 2013 | N/A | N/A | N/A
2nd Satellite Ready to Ship | N/A | Sep 2012 | Jun 2013 | May 2013
3rd Satellite Ready to Ship | N/A | Sep 2013 | Jun 2014 | Nov 20141
4th Satellite Ready to Ship | N/A | Sep 2014 | Jun 2015 | May 2015
5th Satellite Ready to Ship | N/A | Sep 2015 | Jun 2016 | Feb 2016
MUOS Full Operational Capability | Mar 2014 | Oct 2016 | Jul 2017 | Jan 2017
(Ch-1)
1 APB Breach
Change Explanations
(Ch-1) The current estimate for "5th Satellite Ready to Ship" is updated from August 2015 to February 2016 and reflects the actual satellite availability to support the Initial Launch Capability assigned by the Air Force's Current Launch Schedule Review Board.

## Table 11
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Coverage
24 hours/day | 24 hours/day | 24 hours/day | Coverage | 24 hours/day
communications | communications | communications | threshold | communications
services at all latitudes | services at all latitudes | services from 65 | requirement | services from 65
and longitudes | and longitudes | degrees North to 65 | verified by | degrees North to 65
|  | degrees South latitude | analyses using | degrees South latitude
|  | at all longitudes | the Satellite Tool | at all longitudes
Kit (a
performance
model). Recent
exercises
demonstrated
coverage to 75
degrees North
with limited
coverage above
75 degrees North
Capacity
300% worldwide | 300% worldwide | 1,997 worldwide | Capacity | 1,997 worldwide
simultaneous | simultaneous | simultaneous | threshold | simultaneous
accesses (5,991 at | accesses (5,991 at | accesses (39.2 Mbps) | requirement | accesses (39.2 Mbps)
117.6 Mbps) | 117.6 Mbps) | with 502 simultaneous | verified by | with 502 simultaneous
associated with the | associated with the | theater accesses (3 | analyses using | theater accesses (3
CMTW scenario | CMTW scenario | Mbps) | the MPM | Mbps)
Access and Control
Resources planned, | Resources planned, | Resources planned, | Automated | Resources planned,
allocated, prioritized, | allocated, prioritized, | allocated, prioritized, | functionality for | allocated, prioritized,
and dynamically | and dynamically | and dynamically | resource planning, | and dynamically
configured or | configured or | configured or | allocation and | configured or
reconfigured in less | reconfigured in less | reconfigured within 15 | prioritization were | reconfigured in less
than 5 minutes for all | than 5 minutes for all | minutes and for | demonstrated via | than 5 minutes for all
networks; and priority- | networks; and priority- | selected high priority | test; network | networks; and priority-
based access is | based access is | networks within 5 | configuration/ | based access is
provided or the request | provided or the request | minutes; and priority- | reconfiguration | provided or the request
is queued and | is queued and | based access is | was | is queued and
feedback provided to | feedback provided to | provided or the request | demonstrated via | feedback provided to
the user within 3 | the user within 3 | is queued and | PM's capabilities | the user within 6
seconds 90% of the | seconds 90% of the | feedback provided to | assessment. | seconds 90% of the
time and 6 seconds | time and 6 seconds | the user within 6 | Priority-based | time and 10 seconds
99% of the time | 99% of the time | seconds 90% of the | access was | 99% of the time
|  | time and 10 seconds | demonstrated via
|  | 99% of the time | PM's capabilities
assessment and

## Table 12
developmental scenario-based testing
Net Ready
Fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability, integrity, authentication, confidentiality, and nonrepudiation, and issuance of an ATO by the DAA, and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views | Fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net- Centric military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability, integrity, authentication, confidentiality, and nonrepudiation, and issuance of an ATO by the DAA, and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views | Fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for transition to Net- Centric military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability, integrity, authentication, confidentiality, and nonrepudiation, and issuance of an IATO by the DAA, and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views | JITC Memorandum “Mobile User Objective System (MUOS) Net Ready Key Performance Parameter (NR KPP) Interim Status Letter” of May 2, 2013 summarized the interim evaluation of MUOS NR KPP compliance. For the final assessment, JITC will use Information Exchange performance data from both the MUOS second Technical Evaluation and second Multi- service Operational Test and Evaluation events | Fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for transition to Net- Centric military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1; 2) DISR mandated GIG KIPs identified in the KIP declaration table; 3) NCOW RM Enterprise Services; 4) Information assurance requirements including availability, integrity, authentication, confidentiality, and nonrepudiation, and issuance of an IATO by the DAA; and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views
Types of Service
Support synchronous and asynchronous broadcast, point-to- | Threshold plus support an asymmetrical multicast | Support synchronous and asynchronous broadcast, point-to- | Transmission of both voice and data via | Support synchronous and asynchronous broadcast, point-to-

## Table 13
point, and netted communicat-ions topologies plus support an asymmetrical multicast communications topology | communications topology | point, and netted communications topologies | broadcast, point- to-point and netted topologies. Services were tested during the PM’s capabilities assessment and developmental scenario-based testing | point, and netted communications topologies
Communications on the Move
Support | Support | Support | Analysis that | Support
communications on | communications on | communications on | service | communications on
the move when and | the move when and | the move when and | requirements can | the move when and
where needed in all | where needed in all | where needed in all | be met in all | where needed in all
environments while | environments while | environments while | required | environments while
engaged in combat | engaged in combat | engaged in combat | environments | engaged in combat
operations | operations | operations | based on | operations
expected user
radio
performance.
Developmental
testing during
terminal
integration phase
demonstrated
Handheld,
Manpack, and
Small Form Fit
terminals with
various antennas
in urban and
forested
environments
Availability
Provide an operational | Provide an operational | Provide an operational | Link availability | Provide an operational
link availability of at | link availability of at | link availability of at | analysis predicted | link availability of at
least 99% averaged | least 99% averaged | least 97% averaged | that all MUOS | least 97% averaged
over any year of | over any year of | over any year of | users will have at | over any year of
operation and a | operation and a | operation and a | least 97% link | operation and a
constellation | constellation | constellation availability | availability | constellation availability
availability over the | availability over the | over the required | averaged over a | over the required
required length of | required length of | length of service of at | year. Constellation | length of service of at
service of at least 90% | service of at least 90% | least 70% | availability | least 70%
analysis predicted
that the probability
of 4 operational
satellites on orbit
over the required
length of service
is 87%

## Table 14
Requirements Reference
Capability Production Document (CPD) dated January 15, 2008
Change Explanations
None
Acronyms and Abbreviations
ATO - Approval to Operate
CMTW - Combined Major Theater War DAA - Designated Approval Authority
DISR - DOD Informational Technology Standards Region GIG - Global Information Grid
IATO - Interim Approval to Operate IT - Information Technology
JITC - Joint Interoperability Test Command KIPs - Key Interface Profiles
Mbps - megabits per second MPM - MUOS Performance Model
NCOW RM - Net-Centric Operations and Warfare Reference Model NR - Net Ready
TV-1 - Technical View 1

## Table 15
Track to Budget
RDT&E
Appn |  | BA | PE
Navy 1319 07 0303109N
Project | Name
2472 Mobile User Objective System (MUOS)
Procurement
Appn |  | BA | PE
Navy 1507 02 0303109N
Line Item | Name
2433 Fleet Satellite Communications Follow-On
MILCON
Appn |  | BA | PE
Navy 1205 01 0301376N
Project | Name
P131 Facilities Restoration & Mod - Communication (Shared) (Sunk)
Acq O&M
Appn |  | BA | PE
Navy 1804 04 0303109N
Project | Name
4A6M Servicewide Communications (Shared) (Sunk)

## Table 16
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2004 $M |  |  |  |  | BY 2004 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E |  | 3245.2 |  | 3684 | 4052.4 |  | 3604.9 |  | 3636.2 |  | 4138.2 |  | 4057.9
Procurement |  | 2460.3 |  | 2354.2 | 2589.6 |  | 2165.4 |  | 3104.1 |  | 2896.3 |  | 2719.9
Flyaway |  | -- |  | -- | -- |  | 2165.4 |  | -- |  | -- |  | 2719.9
Recurring |  | -- |  | -- | -- |  | 2165.4 |  | -- |  | -- |  | 2719.9
Non Recurring |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Other Support |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON |  | 30.7 |  | 30.8 | 33.9 |  | 30.8 |  | 34.5 |  | 34.6 |  | 34.6
Acq O&M |  | 32.7 |  | 25.2 | 27.7 |  | 25.2 |  | 35.8 |  | 26.8 |  | 26.8
Total |  | 5768.9 |  | 6094.2 | N/A |  | 5826.3 |  | 6810.6 |  | 7095.9 |  | 6839.2
Confidence Level
Confidence Level of cost estimate for current APB: 50%
This cost estimate incorporates the 2011 Director, Cost Assessment and Program Evaluation (D,CAPE) Research, Development, Test and Evaulation (RDT&E) estimate (April 2011) which, like all CAPE estimates, carries a confidence level of 50%. The development estimate presented by the CAPE in April 2011, as a result of Acquisition Decision Memorandum (ADM) direction January 2011, like all life-cycle cost estimates previously performed by the CAPE, is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described. The program office's estimate for Procurement and Sustainment activities (December 2011), like the RDT&E estimate, was completed with a 50% confidence level.

## Table 17
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 2 | 2 | 2
Procurement | 4 | 4 | 4
Total | 6 | 6 | 6
Quantity Notes
The units of measure for the MUOS program consist of six satellites, six launch vehicles, the entire ground system, and the associated support.

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY 2016 |  | FY 2017 |  | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
RDT&E | 3971.6 | 3.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 83.2 |  | 4057.9
Procurement | 2009.4 | 2.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 707.9 |  | 2719.9
MILCON | 34.6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 34.6
Acq O&M | 26.8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 26.8
PB 2017 Total | 6042.4 | 5.7 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 791.1 |  | 6839.2
PB 2016 Total | 6064.4 | 56.1 |  | 21.7 |  | 22.6 |  | 23.3 |  | 23.8 |  | 58.3 |  | 1012.6 |  | 7282.8
Delta | -22 | -50.4 |  | -21.7 |  | -22.6 |  | -23.3 |  | -23.8 |  | -58.3 |  | -221.5 |  | -443.6
Funding Notes
Funds for sustainment were identified within acquisition costs in prior SAR submissions. The funding profile within this SAR submission accurately categorizes O&S costs. The total amount moved from acquisition to O&S costs is $562.4M
(TY) (RDT&E: $218.4M TY, Weapons Procurement, Navy (WPN): $344M TY). However, the Total Appropriation
Summary Delta of $443.6M (TY) does not match the O&S cost of $562.4M (TY) because total WPN increased by $118.8M (TY) in FY 2017 PB, all of which is O&S costs.
Quantity Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Quantity | Undistributed |  | Prior |  | FY 2016 | FY 2017 | FY 2018 |  | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complete |  | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2
Production | 0 |  | 3 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | 4
PB 2017 Total | 2 |  | 3 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | 6
PB 2016 Total | 2 |  | 3 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | 6
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.6
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 84.4
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 375.2
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 449.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 637.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 591.3
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 497
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 398.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 391.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 224.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 141.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.9
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.8
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.5
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.7
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 4057.9

## Table 20
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2004 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67.5
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 82.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 358.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 416.3
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 576
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 524.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 435.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 344
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 330.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 186
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 115.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.3
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.4
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.5
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.8
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 3604.9

## Table 21
FY 2017 PB RDT&E Controls (TY): $4276.3M
Total RDT&E Acquisition (TY): $4,057.9M
RDT&E O&S (TY): FY 2016 - $13.0M FY 2017 - $13.9M FY 2018 - $13.9M FY 2019 - $13.2M FY 2020 - $13.0M FY 2021 - $13.2M FY 2022 - $33.9M FY 2023 - $32.6M FY 2024 - $21.0M FY 2025 - $21.4M FY 2026 - $21.8M FY 2027 - $7.5M
Total RDT&E O&S (TY): $218.4M
Total RDT&E O&S (BY 2004): $153.5M

## Table 22
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | 203.7 |  | -- |  | -- |  | 203.7 |  | -- |  | 203.7
2009 |  | 1 | 339.5 |  | -- |  | -- |  | 339.5 |  | -- |  | 339.5
2010 |  | 1 | 509.9 |  | -- |  | -- |  | 509.9 |  | -- |  | 509.9
2011 |  | 1 | 494.7 |  | -- |  | -- |  | 494.7 |  | -- |  | 494.7
2012 |  | -- | 238.2 |  | -- |  | -- |  | 238.2 |  | -- |  | 238.2
2013 |  | -- | 21.4 |  | -- |  | -- |  | 21.4 |  | -- |  | 21.4
2014 |  | -- | 13.8 |  | -- |  | -- |  | 13.8 |  | -- |  | 13.8
2015 |  | -- | 188.2 |  | -- |  | -- |  | 188.2 |  | -- |  | 188.2
2016 |  | -- | 2.6 |  | -- |  | -- |  | 2.6 |  | -- |  | 2.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2023 |  | -- | 49 |  | -- |  | -- |  | 49 |  | -- |  | 49
2024 |  | 1 | 658.9 |  | -- |  | -- |  | 658.9 |  | -- |  | 658.9
Subtotal |  | 4 | 2719.9 |  | -- |  | -- |  | 2719.9 |  | -- |  | 2719.9

## Table 23
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 2004 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2008 |  | -- | 179 |  | -- |  | -- |  | 179 |  | -- |  | 179
2009 |  | 1 | 294.1 |  | -- |  | -- |  | 294.1 |  | -- |  | 294.1
2010 |  | 1 | 434.3 |  | -- |  | -- |  | 434.3 |  | -- |  | 434.3
2011 |  | 1 | 413.4 |  | -- |  | -- |  | 413.4 |  | -- |  | 413.4
2012 |  | -- | 196.1 |  | -- |  | -- |  | 196.1 |  | -- |  | 196.1
2013 |  | -- | 17.4 |  | -- |  | -- |  | 17.4 |  | -- |  | 17.4
2014 |  | -- | 11 |  | -- |  | -- |  | 11 |  | -- |  | 11
2015 |  | -- | 148.4 |  | -- |  | -- |  | 148.4 |  | -- |  | 148.4
2016 |  | -- | 2 |  | -- |  | -- |  | 2 |  | -- |  | 2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2023 |  | -- | 33.1 |  | -- |  | -- |  | 33.1 |  | -- |  | 33.1
2024 |  | 1 | 436.6 |  | -- |  | -- |  | 436.6 |  | -- |  | 436.6
Subtotal |  | 4 | 2165.4 |  | -- |  | -- |  | 2165.4 |  | -- |  | 2165.4

## Table 24
FY 2017 PB WPN Controls (TY): $3063.9M
Total WPN Acquisition (TY): $2719.9M
Procurement O&S (TY): FY 2014 - $3.1M
FY 2015 - $18.5M FY 2016 - $31.7M FY 2017 - $36.7M FY 2018 - $46.1M FY 2019 - $41.9M FY 2020 - $40.3M FY 2021 - $37.5M FY 2022 - $12.4M FY 2023 - $14.5M FY 2024 - $21.2M FY 2025 - $13.4M FY 2026 - $13.7M FY 2027 - $13.0M
Total Procurement O&S (TY): $344.0M
Total Procurement O&S (BY 2004): $247.9M
Cost Quantity Information 1507 ¦ Procurement ¦ Weapons Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2004 $M
2008 | -- | --
2009 | 1 | 446.5
2010 | 1 | 433.4
2011 | 1 | 437.5
2012 | -- | --
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
2022 | -- | --
2023 | -- | --
2024 | 1 | 848
Subtotal | 4 | 2165.4

## Table 25
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
2007 | 26.1
2008 | 8.5
Subtotal | 34.6

## Table 26
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 2004 $M
Total Program
2007 | 23.3
2008 | 7.5
Subtotal | 30.8

## Table 27
Annual Funding 1804 ¦ Acq O&M ¦ Operation and Maintenance, Navy
Fiscal Year | TY $M
Total Program
2002 4.2
2003 4.6
2004 4.5
2005 --
2006 --
2007 --
2008 4.6
2009 5.0
2010 3.9
Subtotal 26.8

## Table 28
Annual Funding 1804 ¦ Acq O&M ¦ Operation and Maintenance, Navy
Fiscal Year | BY 2004 $M
Total Program
2002 4.3
2003 4.6
2004 4.4
2005 --
2006 --
2007 --
2008 4.1
2009 4.4
2010 3.4
Subtotal 25.2

## Table 29
Low Rate Initial Production
There is no LRIP for this program.

## Table 30
Foreign Military Sales
None
Nuclear Costs
None

## Table 31
Unit Cost
Unit Cost Report
Item |  |  | BY 2004 $M | BY 2004 $M |  |  |  | % Change
|  |  | Current UCR Baseline (Jul 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 6094.2 |  |  |  |  | 5826.3
Quantity | 6 |  |  |  |  | 6
Unit Cost | 1015.7 |  |  |  |  | 971.05 |  |  | -4.4
Average Procurement Unit Cost
Cost | 2354.2 |  |  |  |  | 2165.4
Quantity | 4 |  |  |  |  | 4
Unit Cost | 588.55 |  |  |  |  | 541.35 |  |  | -8.02
Item |  |  | BY 2004 $M |  | BY 2004 $M |  |  | % Change
|  |  | Original UCR Baseline (Dec 2004 APB) |  | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost |  | 5738 |  |  |  |  | 5826.3
Quantity |  | 6 |  |  |  |  | 6
Unit Cost |  | 956.333 |  |  |  |  | 971.05 |  | 1.54
Average Procurement Unit Cost
Cost |  | 2591 |  |  |  |  | 2165.4
Quantity |  | 4 |  |  |  |  | 4
Unit Cost |  | 647.75 |  |  |  |  | 541.35 |  | -16.43
PAUC reflects the sum of six satellites, six launch vehicles, the entire ground segment, and the associated support, divided by the total quantity of six. APUC reflects the sum of four satellites and six launch vehicles, divided by a procurement quantity of four.

## Table 32
Unit Cost History
Item |  |  |  |  | Date |  |  |  | BY 2004 $M | [8 empty] | TY $M
[9 empty] | PAUC |  |  |  |  | APUC |  |  |  | PAUC |  |  |  |  | APUC
Original APB |  |  |  | Dec 2004 |  |  |  |  | 956.333 | [5 empty] | 647.75 |  |  |  |  | 1080.183 |  |  |  | 776.025
APB as of January 2006 |  |  |  | Dec 2004 |  |  |  |  | 956.333 | [5 empty] | 647.75 |  |  |  |  | 1080.183 |  |  |  | 776.025
Revised Original APB |  |  |  | N/A |  |  |  |  | N/A | [5 empty] | N/A |  |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  | Mar 2008 |  |  |  |  | 961.483 | [5 empty] | 615.075 |  |  |  |  | 1135.1 |  |  |  | 776.025
Current APB |  |  |  | Jul 2012 |  |  |  |  | 1015.7 | [5 empty] | 588.55 |  |  |  |  | 1182.65 |  |  |  | 724.075
Prior Annual SAR |  |  |  | Dec 2014 |  |  |  |  | 1023.6 | [5 empty] | 582.025 |  |  |  |  | 1213.8 |  |  |  | 736.275
Current Estimate |  |  |  | Dec 2015 |  |  |  |  | 971.05 | [5 empty] | 541.35 |  |  |  |  | 1139.867 |  |  |  | 679.975
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  | Sch |  | Eng |  |  | Est |  | Oth |  |  |  | Spt |  |  | Total
1080.183 49.000 0.000 2.750 0.000 3.167 0.000 0.000 54.917 1135.100
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  | Sch |  | Eng |  |  | Est |  | Oth |  |  |  | Spt | Total
1135.100 -16.567 0.000 11.683 34.451 -24.800 0.000 0.000 4.767 1139.867

## Table 33
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [12 empty] | APUC Production Estimate
| Econ | Qty |  | Sch | Eng |  |  | Est | Oth |  | Spt |  | Total
776.025 39.100 0.000 4.125 0.000 -43.225 0.000 0.000 0.000 776.025
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [12 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  | Est | Oth | Spt |  | Total
776.025 -20.875 0.000 17.150 0.000 -92.325 0.000 0.000 -96.050 679.975
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  |  |  | Current Estimate
Milestone A |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  |  |  | N/A
Milestone B |  |  | N/A |  |  |  | Sep 2004 |  |  | Sep 2004 |  |  |  |  | Sep 2004
Milestone C |  |  | N/A |  |  |  | Oct 2006 |  |  | Oct 2006 |  |  |  |  | Aug 2006
IOC |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  |  |  | N/A
Total Cost (TY $M) |  |  | N/A |  |  |  | 6481.1 |  |  | 6810.6 |  |  |  |  | 6839.2
Total Quantity |  |  | N/A |  |  |  | 6 |  |  | 6 |  |  |  |  | 6
PAUC |  |  | N/A |  |  |  | 1080.183 |  |  | 1135.1 |  |  |  |  | 1139.867
Milestone (MS) B and C dates reflect National Security Space Acquisition Policy 03-01 dates for Key Decision Point B and C, not MS B and C as specified in DoD 5000.02.
Build Approval was authorized February 2008.
IOC is synonymous with the term On-Orbit Capability, which is referenced by the MUOS Program.

## Table 34
Cost Variance
Summary TY $M
Item | RDT&E | Procurement | MILCON | Acq O&M | Total
SAR Baseline (Production Estimate) | 3636.2 | 3104.1 | 34.5 | 35.8 | 6810.6
Previous Changes
Economic | -13.2 | -74.5 | 0.1 | 0.1 | -87.5
Quantity | -- | -- | -- | -- | --
Schedule | 1.5 | 47.8 | -- | -- | 49.3
Engineering | 206.7 | -- | -- | -- | 206.7
Estimating | 445.1 | -132.3 | -- | -9.1 | 303.7
Other | -- | -- | -- | -- | --
Support | -- | -- | -- | -- | --
Subtotal | 640.1 | -159 | 0.1 | -9 | 472.2
Current Changes
Economic | -2.9 | -9 | -- | -- | -11.9
Quantity | -- | -- | -- | -- | --
Schedule | -- | 20.8 | -- | -- | 20.8
Engineering | -- | -- | -- | -- | --
Estimating | -215.5 | -237 | -- | -- | -452.5
Other | -- | -- | -- | -- | --
Support | -- | -- | -- | -- | --
Subtotal | -218.4 | -225.2 | -- | -- | -443.6
Total Changes | 421.7 | -384.2 | 0.1 | -9 | 28.6
CE - Cost Variance | 4057.9 | 2719.9 | 34.6 | 26.8 | 6839.2
CE - Cost & Funding | 4057.9 | 2719.9 | 34.6 | 26.8 | 6839.2

## Table 35
Summary BY 2004 $M
Item | RDT&E | Procurement | MILCON | Acq O&M | Total
SAR Baseline (Production Estimate) | 3245.2 | 2460.3 | 30.7 | 32.7 | 5768.9
Previous Changes
Economic | -- | -- | -- | -- | --
Quantity | -- | -- | -- | -- | --
Schedule | -0.4 | 2.5 | -- | -- | 2.1
Engineering | 144.9 | -- | -- | -- | 144.9
Estimating | 367.8 | -134.7 | 0.1 | -7.5 | 225.7
Other | -- | -- | -- | -- | --
Support | -- | -- | -- | -- | --
Subtotal | 512.3 | -132.2 | 0.1 | -7.5 | 372.7
Current Changes
Economic | -- | -- | -- | -- | --
Quantity | -- | -- | -- | -- | --
Schedule | -1.5 | -- | -- | -- | -1.5
Engineering | -- | -- | -- | -- | --
Estimating | -151.1 | -162.7 | -- | -- | -313.8
Other | -- | -- | -- | -- | --
Support | -- | -- | -- | -- | --
Subtotal | -152.6 | -162.7 | -- | -- | -315.3
Total Changes | 359.7 | -294.9 | 0.1 | -7.5 | 57.4
CE - Cost Variance | 3604.9 | 2165.4 | 30.8 | 25.2 | 5826.3
CE - Cost & Funding | 3604.9 | 2165.4 | 30.8 | 25.2 | 5826.3
Previous Estimate: December 2014

## Table 36
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -2.9
Adjustment for current and prior escalation. (Estimating) +1.0 +1.1
Stretch-out of procurement buy-profile from FY 2021 - FY 2022 to FY 2022 - FY 2023 in support of procurement of sixth satellite. (Schedule)
Removal of previously identified acquisition cost to program sustainment efforts. (Estimating)
Revised estimate for miscellaneous budget adjustments from FY 2015 through FY 2027. (Estimating)
-1.5 0.0
-153.5 -218.4
+1.4 +1.8
RDT&E Subtotal -152.6 -218.4
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -9.0
Adjustment for current and prior escalation. (Estimating) +1.8 +2.2
Stretch-out of procurement buy-profile from FY 2023 to FY 2024 for advance procurement of sixth satellite. (Schedule)
0.0 +20.8
Revised estimate due to Congressional plus ups. (Estimating) +87.6 +118.8
Removal of previously identified acquisition cost to program sustainment efforts. (Estimating)
Revised estimate for miscellaneous budget adjustments from FY 2016 through FY 2027. (Estimating)
-247.9 -344.0
-4.2 -14.0
Procurement Subtotal -162.7 -225.2

## Table 37
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: MUOS RRDD AOS Contract - CLIN 3
Contractor: Lockheed Martin (LMSSC)
Contractor Location: 1111 Lockheed Martin Way
Sunnyvale, CA 94089-1212
Contract Number: N00039-04-C-2009/3
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: September 24, 2004
Definitization Date: September 24, 2004
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
279.0 298.5 1 282.5 332.5 1 332.6 332.5
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the inclusion of a contract Engineering Change Proposal.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (5/31/2015) -10.4 -19.1
Previous Cumulative Variances -6.1 -22.8
Net Change -4.3 +3.7
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to the continued cost impact of the Output Multiplexer (OMUX) failure, repair and replacement, and re-testing, as well as level of effort tasks performed beyond baseline completion.
The favorable net change in the schedule variance is due to sustained recovery to the baseline plan with the restart of Single Line Flow after the replacement OMUX was installed on the satellite.

## Table 38
Notes
The final Cost Performance Report for CLIN 0003 was submitted June 25, 2015 for month end May 2015 contract and EVM data. Per contract modification P00236 dated August 12, 2015 further submittals of EVM contract deliverables for CLIN 0003 are no longer required as of July 10, 2015.
CLIN 0003 supports the milestone "5th Satellite Ready to Ship".
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 39
Contract Identification
Appropriation: Procurement
Contract Name: MUOS RRDD AOS Contract – CLIN 5
Contractor: Lockheed Martin (LMSSC)
Contractor Location: 1111 Lockheed Martin Way
Sunnyvale, CA 94089-1212
Contract Number: N00039-04-C-2009/5
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: September 24, 2004
Definitization Date: September 24, 2004
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
287.7 307.7 1 277.8 324.7 1 325.2 324.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the change in methodology to align the target price to the Contract Performance Report data reported by the Prime Contractor, which excludes $9.9M Mission Success Fee. In previous SAR submissions, the Mission Success Fee was included in the target price. In accordance with guidance, the Original Target Price remains unchanged, and continues to include the $9.9M of Fee.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (5/31/2015) -7.4 -4.2
Previous Cumulative Variances +1.1 -10.7
Net Change -8.5 +6.5
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to increased efforts for on orbit observation analysis, as well as the incurrence of Launch Operations, Program Support, and System Engineering, Integration, and Test level of effort tasks performed beyond baseline completion.
The favorable net change in the schedule variance is due to the recovery to the baseline plan as late tasks driven by the overall launch schedule delays were completed

## Table 40
Notes
The final Cost Performance Report for CLIN 0005 was submitted June 25, 2015 for month end May 2015 contract and EVM data. Per contract modification P00236 dated August 12, 2015 further submittals of EVM contract deliverables for CLIN 0005 are no longer required as of July 10, 2015.
CLIN 0005 supported the "3rd Satellite Ready to Ship" milestone.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 41
Contract Identification
Appropriation: Procurement
Contract Name: MUOS RRDD AOS Contract – CLIN 7
Contractor: Lockheed Martin (LMSSC)
Contractor Location: 1111 Lockheed Martin Way
Sunnyvale, CA 94089-1212
Contract Number: N00039-04-C-2009/7
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: September 24, 2004
Definitization Date: September 24, 2004
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
288.5 339.6 1 288.5 339.6 1 333.0 339.6
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (5/31/2015) +15.7 -13.6
Previous Cumulative Variances +20.1 -12.1
Net Change -4.4 -1.5
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to the Assembly, Integration, and Test Single Line Flow extension for technical issues associated with several components including Solar Array trim tabs and Uplink/Downlink Unit.
The unfavorable net change in the schedule variance is due to the delay of on orbit testing efforts performed by System Engineering, Integration, and Test.
Notes
The final Cost Performance Report for CLIN 0007 was submitted June 25, 2015 for month end May 2015 contract and EVM data. Per contract modification P00236 dated August 12, 2015 further submittals of EVM contract deliverables for CLIN 0007 are no longer required as of July 10, 2015.
CLIN 0007 supported the "4th Satellite Ready to Ship" milestone.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 42
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 2 | 2 | 2 | 100%
Production | 3 | 2 | 4 | 50%
Total Program Quantity Delivered | 5 | 4 | 6 | 66.67%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
6839.2
5826
85.19%
25
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
17
68%
6048.1
88.43%
The above data is current as of February 29, 2016.

## Table 43
Operating and Support Cost
Cost Estimate Details
Date of Estimate: October 15, 2015
Source of Estimate: POE
Quantity to Sustain: 6
Unit of Measure: Ground Station
Service Life per Unit: 17.00 Years
Fiscal Years in Service: FY 2011 - FY 2027
The MUOS constellation consists of five satellites, four operational and one on-orbit spare. In addition, the APB includes procurement of a sixth satellite to replace the first satellite at end-of-life. MUOS O&S costs include sustainment of all satellites and six ground sites located in Wahiawa (Hawaii), Chesapeake (Virginia), Niscemi (Italy), Geraldton (Australia), and MUOS Ground System hardware and software at Naval Satellite Operations Center (NAVSOC) Point Mugu (California) and NAVSOC Detachment Delta. O&S reflects primary sustainment of ground stations.
Sustainment Strategy
The MUOS sustainment strategy is based on a Performance Based Logistics plan to optimize total system availability while minimizing cost and logistics footprint. The majority of sustainment work is focused on the sustainment of the MUOS Ground System (hardware and software) from handover of the Ground System in FY 2010 through the program lifecycle (end FY 2027).
Antecedent Information
The antecedent system to MUOS was the Ultra High Frequency (UHF) Follow-on (UFO) satellite communications program. Comparisons of O&S costs for UFO are not provided. Although the MUOS system continues to support UHF capabilities, the infrastructure of MUOS and its sustainment are not comparable to UFO.
Annual O&S Costs BY2004 $M
Cost Element | MUOS Average Annual Cost Per Ground Station | UFO (Antecedent) Cost Per Ground Station Per Year
Unit-Level Manpower | 0 | 0
Unit Operations | 0 | 0
Maintenance | 0.333 | 0
Sustaining Support | 10.123 | 0
Continuing System Improvements | 0 | 0
Indirect Support | 0.715 | 0
Other | 0 | 0
Total | 11.171 | --
Changes to unitized costs from prior year SAR are due to FY 2015 update of the O&S estimate.

## Table 44
Item | Total O&S Cost $M
| MUOS | [6 empty] | UFO (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year |  | 379.9 |  | 417.9 |  |  | 1139.41 |  | 0
Then Year 1 APB O&S Cost Breach |  | 508.2 |  | N/A |  |  | 1577.8 |  | N/A
Funds for sustainment were identified within acquisition cost in prior SAR submissions. The funding profile within this SAR submission accurately categorizes sustainment costs and aligns them within the O&S estimate. Total O&S costs are comprised of RDT&E, Weapons Procurement, Navy (WPN), and O&M Navy.
Equation to Translate Annual Cost to Total Cost
The unitized annual costs reflect the total O&S cost divided by six ground stations and sustainment of the MUOS Ground System over 17 years (FY 2011 through FY 2027).
O&S Cost Variance
Category |  |  | BY 2004 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
387.5
Programmatic/Planning Factors 0.0
Cost Estimating Methodology 0.0
Cost Data Update 751.9 Studies/test results identified a higher level of Ground System obsolescence than originally projected, resulting in an increase in O&S costs.
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 751.9
Current Estimate 1139.4
The $751.9M of O&S Cost Variance includes the correct categorization of $401.4M (BY 2004) O&S costs that were previously identified as acquisition costs in prior SAR submissions.
Disposal Estimate Details
Date of Estimate: October 15, 2015
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2004 $M): Total costs for disposal of all Ground Station are 0.0
Satellites will be disposed on-orbit using on-board fuel paid for during the procurement phase of the program. Ground stations will not be disposed of and will be utilized and sustained by follow on program.