## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-290
Navy Multiband Terminal (NMT)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 10
Track to Budget 15
Cost and Funding 16
Low Rate Initial Production 24
Foreign Military Sales 25
Nuclear Costs 25
Unit Cost 26
Cost Variance 29
Contracts 32
Deliveries and Expenditures 34
Operating and Support Cost 35

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Navy Multiband Terminal (NMT)
DoD Component
Navy
Responsible Office
CAPT Mark Glover
4301 Pacific Coast Highway San Diego, CA 92110-3127
mark.glover@navy.mil
Phone: 619-524-7930
Fax: 619-524-3501
DSN Phone: 524-7930
DSN Fax:
Date Assigned: September 10, 2013
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated October 4, 2010
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated March 11, 2016

## Table 6
Mission and Description
The Navy Multiband Terminal (NMT) Program is the next generation maritime military satellite communications
terminal. The NMT Program is the required Navy component to the Advanced Extremely High Frequency (AEHF) Program for enhancing protected and survivable satellite communications for Naval forces. NMT multiband capabilities will communicate via two way Ka-Band on Wideband Global Satellite Communication (SATCOM) (WGS) and via X-Band on the Defense Satellite Communications System and WGS. NMT will operate in the Extremely High Frequency (EHF)/AEHF Low Data Rate, Medium Data Rate, and Extended Data Rate communication modes. NMT will sustain the Military SATCOM architecture by providing connectivity across the spectrum of mission areas to include land, air, and naval warfare, special operations, strategic nuclear operations, strategic defense, theater missile defense, and space operations and intelligence. The NMT system will replenish and improve on the capabilities of both the MILSTAR system and WGS system by equipping the warfighters with the assured, jam resistant, secure communications as described in the ORD for the joint AEHF Satellite Communications (AFSPC ORD 004-99, October 2000) and WGS System (Wideband Gapfiller System ORD, May 3, 2000), and the NMT CPD (NMT CPD 769-6F-08, November 18, 2008). The AEHF system will provide crosslinks within the constellation as well as between AEHF satellites and MILSTAR satellites in the backwards-compatible mode. Mission requirements specific to Navy operations, including threat levels and scenarios, are contained in the AEHF ORD. NMT will be a FORCEnet enabler by providing critical protected bandwidth for warfighter information services.

## Table 7
Executive Summary
NMT held a successful Gate 6/Configuration Steering Board (CSB) review on November 30, 2015. The purpose of the review was to add the Wideband Anti-Jam Modem System (WAMS) capability to the NMT program baseline in support of Anti-Access/Area Denial initiatives. The Assistant Secretary of the Navy for Research, Development, and Acquisition (ASN (RDA)) approved WAMS pre-acquisition activities and the program has initiated these efforts in the first quarter of FY 2016.
In support of the Gate 6/CSB and updated APB, the program office worked with the Naval Center for Cost Analysis to develop a revised Component Cost Position (CCP). The CCP was approved on December 18, 2015. The updated APB, which was signed on March 11, 2016, adds Adaptive Coding (AC) and WAMS to the program baseline. AC was approved by ASN (RDA) at the June 2014 CSB and provides the Fleet with optimized communication throughput in dynamic environments.
On December 29, 2015, NMT awarded the Follow-On Full Deployment production contract to Raytheon. The contract, valued at $466M, will allow the program office to procure remaining terminals to meet the inventory objective and will support NMT procurements for Other Customer Funded (OCF) requirements. At the time of the award, the program exercised the Production Year 6 option for a buy of 12 NMT program of record terminals and 21 OCF terminals.
As of December 30, 2015, NMT has fielded 101 of the 250 terminals in the current inventory objective.
NMT continues to prepare for a Follow-on Operational Test and Evaluation, scheduled for the third quarter of FY 2016. There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 9
Schedule
None
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | Oct 2003 | Oct 2003 | Oct 2003 | Oct 2003
System Development & Demonstration Contract Award | Oct 2003 | Oct 2003 | Oct 2003 | Oct 2003
Critical Design Review | May 2005 | May 2005 | May 2005 | May 2005
Operational Assessment | Sep 2009 | Mar 2010 | Mar 2010 | Mar 2010
Milestone C | Feb 2010 | Aug 2010 | Aug 2010 | Aug 2010
Initial Operational Test and Evaluation (Start) | Apr 2012 | Jul 2011 | Jul 2011 | Jul 2011
Full Rate Production Decision Review | Sep 2012 | Nov 2012 | Nov 2012 | Nov 2012
IOC | Sep 2012 | Dec 2012 | Dec 2012 | Dec 2012
Change Explanations

## Table 10
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
NMT Antenna Control Coverage
The NMT shall be capable of pointing and tracking satellites with elevation angles of 0 deg (20 deg for the mast) above the horizon and 360 deg in azimuth with full platform dynamics. In the absence of sea state or submarine dynamics, the antenna shall have the capability to point at satellites down to 0 deg relative to the horizon. | The NMT shall be capable of pointing and tracking satellites with elevation angles of 0 deg (20 deg for the mast) above the horizon and 360 deg in azimuth with full platform dynamics. In the absence of sea state or submarine dynamics, the antenna shall have the capability to point at satellites down to 0 deg relative to the horizon. | The NMT shall be capable of pointing and tracking satellites with elevation angles of 10 deg (20 deg for the mast) above the horizon and 360 deg in azimuth with full platform dynamics. | Demonstrat-ed capability to acquire and track Milstar, WGS, and DSCS satellites. | The NMT shall be capable of pointing and tracking satellites with elevation angles of 0 deg (20 deg for the mast) above the horizon and 360 deg in azimuth with full platform dynamics. In the absence of sea state or submarine dynamics, the antenna shall have the capability to point at satellites down to 0 deg relative to the horizon.
Sustainment
Materiel Availability
>= 0.95 | >= 0.95 | >= 0.75 | Ship: 0.98, Sub: 0.99, Shore: 0.99 | >= 0.95
Operational Availability (Ao)
>0.999 (sub) > 0.999 (ship/shore) | >0.999 (sub) > 0.999 (ship/shore) | > 0.940 (sub) > 0.900 (ship/shore) | Ship: 0.98, Sub: 0.99, Shore: 0.99 | >0.999 (sub) > 0.999 (ship/shore)
Reliability
Materiel Reliability – Mean Time Between Failure (MTBF)
>= 2200 hrs | >= 2200 hrs | >= 1100 hrs | Ship: 14,211 hrs, Sub: 9,275 hrs, Shore: >= 2,200 hrs | >= 2200 hrs
Materiel Reliability - Mean Time Between Critical Failure (MTBCF)
>= 4200 hrs | >= 4200 hrs | >= 1400 hrs | Ship: 14,211 hrs, Sub: 9,275 hrs, Shore: >= 4,200 hrs | >= 4200 hrs
Maintainability
Mean Time to Repair (MTTR)
<= 1 hr | <= 1 hr | <= 3 hrs | Ship: 1.18 hrs | <= 1 hr
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)

## Table 11
(10/15/2012) Shore: 1.25 hrs (11/14/2011) Sub: 4.3 hrs (11/14/2011)
Cost
Ownership Cost
<= $298M | <= $253M | <= $278M | $253.0M | <= $328M
Survivability
Survive an EMP (AEHF Only)
NMT AEHF/EHF | NMT AEHF/EHF | NMT AEHF/EHF | TBD | NMT AEHF/EHF
functionality shall be | functionality shall be | functionality shall be |  | functionality shall be
capable of surviving | capable of surviving | capable of surviving |  | capable of surviving
indirect nuclear | indirect nuclear | indirect nuclear |  | indirect nuclear
detonation EMP and | detonation EMP and | detonation EMP and |  | detonation EMP and
thermal blast effects | thermal blast effects | thermal blast effects |  | thermal blast effects
as defined in ELEX- | as defined in ELEX- | as defined in ELEX- |  | as defined in ELEX-
S-488G and SR- | S-488G and SR- | S-488G and SR- |  | S-488G and SR-
3000 Appendix B-8.4 | 3000 Appendix B-8.4 | 3000 Appendix B-8.4 |  | 3000 Appendix B-8.4
NMT Multiband Terminal Operations
NMT shall provide | NMT shall provide | NMT shall provide | TBD | NMT shall provide
AEHF/EHF capability | AEHF/EHF capability | AEHF/EHF capability |  | AEHF/EHF capability
with two-way military | with two-way military | with two-way military |  | with two-way military
Ka-band (ship only), | Ka-band (ship only), | Ka-band (ship only), |  | Ka-band (ship only),
GBS (sub/ship) and | GBS (sub/ship) and | GBS (sub/ship) and |  | GBS (sub/ship) and
X-band (ship /subs) | X-band (ship /subs) | X-band (ship/subs). |  | X-band (ship /subs)
simultan-eously. The | simultan-eously. The | The NMT shall |  | simultaneou-sly. The
NMT shall operate in | NMT shall operate in | operate in the |  | NMT shall operate in
the EHF/AEHF LDR, | the EHF/AEHF LDR, | EHF/AEHF LDR, |  | the EHF/AEHF LDR,
MDR, and XDR | MDR, and XDR | MDR, and XDR |  | MDR, and XDR
communica-tion | communica-tion | communica-tion |  | communicat-ion
modes. | modes. | modes. |  | modes.
Net-Ready
The system must | The system must | The system must | Interoperabil-ity: NMT | The system must
fully support | fully support | fully support | is capable of | fully support
execution of all | execution of all | execution of joint | supporting operations | execution of all
operational activities | operational activities | critical operational | in the joint operations | operational activities
identified in the | identified in the | activities identified in | environment. The | identified in the
applicable joint and | applicable joint and | the applicable joint | NMT interfaced and | applicable joint and
system integrated | system integrated | and system | operated with other | system integrated
architectures and the | architectures and the | integrated | communicat-ions | architectures and the
system must satisfy | system must satisfy | architectures and the | systems over Milstar, | system must satisfy
the technical | the technical | system must satisfy | WGS, and DSCS | the technical
requirements for | requirements for | the technical | satellite systems. The | requirements for
transition to Net- | transition to Net- | requirements for Net | NMTs conducted end- | transition to Net-
Centric military | Centric military | -Centric military | to-end communicat- | Centric military
operations to | operations to | operations to | ions with other NMTs | operations to
include: 1) DISR | include: 1) DISR | include: 1) DISR | and legacy EHF and | include: 1) DISR
mandated GIG IT | mandated GIG IT | mandated GIG IT | SHF terminals. | mandated GIG IT
standards and | standards and | standards and | During testing and | standards and
profiles identified in | profiles identified in | profiles identified in | ongoing operations, | profiles identified in
(Ch-2)

## Table 12
the TV-1 2) DISR mandated GIG KIPs identified in the KIP declaration table 3) NCOW RM Enterprise Services 4) Information assurance requirements resulting in issuance of an ATO by the DAA, and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views. | the TV-1 2) DISR mandated GIG KIPs identified in the KIP declaration table 3) NCOW RM Enterprise Services 4) Information assurance requirements resulting in issuance of an ATO by the DAA, and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views. | the TV-1 2) DISR mandated GIG KIPs identified in the KIP declaration table 3) NCOW RM Enterprise Services 4) Information assurance requirements resulting in issuance of an ATO by the DAA, and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views. | the Navy sent a large number of e-mails through the Secure Internet Protocol Router Network (SIPRNET) as their preferred mode of communicat-ions. Information Assurance: The Navy Information Operations Command performed information assurance testing during the integrated test period. | the TV-1 2) DISR mandated GIG KIPs identified in the KIP declaration table 3) NCOW RM Enterprise Services 4) Information assurance requirements resulting in issuance of an ATO by the DAA, and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views.
Sustainment - WAMS
Materiel Availability - WAM
N/A | >= 0.75 | (T=O) >= 0.75 | TBD | >= 0.75
Materiel Availability - Mini-Hub
N/A | >= 0.75 | (T=O) >= 0.75 | TBD | >= 0.75
Ao - WAM
N/A | >= 0.96 | (T=O) >= 0.96 | TBD | >= 0.96
Ao - Mini-Hub
N/A | >= 0.96 | (T=O) >= 0.96 | TBD | >= 0.96
Reliability
MTBF - WAM
N/A | >= 30,000 hrs | (T=O) >= 30,000 hrs | TBD | >= 30,000 hrs
MTBF - Mini-Hub
N/A | >= 8,900 hrs | (T=O) >= 8,900 hrs | TBD | >= 8,900 hrs
Maintainability
MTTR - WAM
N/A | < 1 hour | (T=O) < 1 hour | TBD | < 1 hour
MTTR - Mini-Hub
N/A | < 1 hour | (T=O) < 1 hour | TBD | < 1 hour
(Ch-3)
(Ch-3)
(Ch-3)
(Ch-3)
(Ch-3)
(Ch-3)
(Ch-3)
(Ch-3)

## Table 13
Benign Data Rates - WAMS
Ship X-band large X/Ka antenna
N/A | >=13.7 Mbps | (T=O) >=13.7 Mbps | TBD | >=13.7 Mbps
| (measured on the | (measured on the |  | (measured on the
| return link from the | return link from the |  | return link from the
| ship WAM to shore | ship WAM to shore |  | ship WAM to shore
| hub); >=15.9 Mbps | hub); >=15.9 Mbps |  | hub); >=15.9 Mbps
| (measured on the | (measured on the |  | (measured on the
| forward link from | forward link from |  | forward link from
| shore hub to ship | shore hub to ship |  | shore hub to ship
| WAM) | WAM) |  | WAM)
Ship X-band small X/Ka antenna
N/A | >=4.1 Mbps | (T=O) >=4.1 Mbps | TBD | >=4.1 Mbps
| (measured on the | (measured on the |  | (measured on the
| return link from ship | return link from ship |  | return link from ship
| WAM to shore hub); | WAM to shore hub); |  | WAM to shore hub);
| >=3.2 Mbps | >=3.2 Mbps |  | >=3.2 Mbps
| (measured on the | (measured on the |  | (measured on the
| forward link from | forward link from |  | forward link from
| shore hub to ship | shore hub to ship |  | shore hub to ship
| WAM) | WAM) |  | WAM)
Submarine X-band
N/A | >=300 Kbps | (T=O) >=300 Kbps | TBD | >=300 Kbps
| (measured on the | (measured on the |  | (measured on the
| return link from the | return link from the |  | return link from the
| submarine WAM to | submarine WAM to |  | submarine WAM to
| the shore hub); | the shore hub); |  | the shore hub);
| >=300 Kbps | >=300 Kbps |  | >=300 Kbps
| (measured on the | (measured on the |  | (measured on the
| forward link from | forward link from |  | forward link from
| shore hub to | shore hub to |  | shore hub to
| submarine WAM) | submarine WAM) |  | submarine WAM)
(Ch-3)
(Ch-3)
(Ch-3)
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
The requirements are referenced in two documents, the NMT Capability Production Document (CPD) dated November 18, 2008 and the draft NMT CPD Increment 1 for Wideband Anti-Jam Modem System (WAMS).
Change Explanations
(Ch-1) Demonstrated Performance metrics for Material Availability, Operational Availability, MTBF, and MTBCF on Ship/Sub platforms reflect Naval Sea Warfare Center Corona data as of December 31, 2015; Shore metrics reflect data provided by the vendor.
(Ch-2) Cost estimate changed from $223.5M to $253.0M to reflect the December 18, 2015 Component Cost Position. (Ch-3) Performance Characteristic was added in the NMT CPD Increment 1 for WAMS.

## Table 14
Notes
Demonstrated Performance metrics for MTTR reflect the results of the IOT&E and Verification of Correction of Deficiencies
Acronyms and Abbreviations
AEHF - Advanced Extremely High Frequency ATO - Approval to Operate
DAA - Designated Approval Authority deg - degree
DISR - DoD Information Standards Registry DSCS - Defense Satellite Communication System EHF - Extremely High Frequency
EMP - Electro Magnetic Pulse GBS - Global Broadcast Service GIG - Global Information Grid hrs - hours
IOT&E - Initial Operational Test and Evaluation IT - Information Technology
KIP - Key Interface Profile LDR - Low Data Rate MDR - Medium Data Rate
MTBCF - Mean Time Between Critical Failure MTBF - Mean Time Between Failure
MTTR - Mean Time to Repair
NCOW RM - Net-Centric Operational Warfare Reference Model SHF - Super High Frequency
sub - submarine
TV - Technical View
WGS - Wideband Global SATCOM XDR - Extended Data Rate

## Table 15
Track to Budget
RDT&E
Appn |  | BA | PE
Navy | 1319 07 |  | 0303109N
| Project |  | Name
| 728 |  | Navy Multiband Terminal | (Shared)
| 9889 |  | Navy Multiband Terminal | (Shared) (Sunk)
Procurement
Appn |  | BA | PE
Navy | 1810 02 |  | 0303109N
| Line Item |  | Name
| 3216 |  | Navy Multiband Terminal
Notes
Line item 9020 is a shared control number and is not included in the NMT APB. As a result, it is not shown in the above Track to Budget.

## Table 16
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2002 $M |  |  |  | BY 2002 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 555.9 |  | 729.8 | 802.8 |  | 728.1 |  | 631.3 |  | 868.6 |  | 868.6
Procurement | 962 |  | 1041.6 | 1145.8 |  | 1039.5 |  | 1221.7 |  | 1368.4 |  | 1368.4
Flyaway | -- |  | -- | -- |  | 1039.5 |  | -- |  | -- |  | 1368.4
Recurring | -- |  | -- | -- |  | 539.2 |  | -- |  | -- |  | 703.3
Non Recurring | -- |  | -- | -- |  | 500.3 |  | -- |  | -- |  | 665.1
Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Other Support | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Initial Spares | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 1517.9 |  | 1771.4 | N/A |  | 1767.6 |  | 1853 |  | 2237 |  | 2237
Current APB Cost Estimate Reference
The NMT Cost Section is based on the Naval Center for Cost Analysis (NCCA) Component Cost Position (CCP) memo dated December 18, 2015
Confidence Level
Confidence Level of cost estimate for current APB: 53%
The estimate was developed at the Risk Adjusted Mean.

## Table 17
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 28 | 28 | 28
Procurement | 276 | 250 | 250
Total | 304 | 278 | 278
Quantity Notes
The original NMT inventory objective was 276 but the quantity has been reduced to 250 due to revised Navy requirements.
The NMT unit of measure is defined as a single terminal, to include the Communication Group, Antennas, and Radomes.
Procurement costs in FY 2023 - 2028 are for the Wideband Anti-Jam Modem System (WAMS). Because WAMS is not an NMT end item, there are no quantities associated with the costs.

## Table 18
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 671.6 | 28 |  |  | 21.1 | 32.1 | 34.8 |  | 30.8 |  | 10.3 |  |  | 39.9 | 868.6
Procurement | 853.4 | 118.1 |  |  | 38.4 | 68.1 | 95 |  | 71.4 |  | 11.1 |  |  | 112.9 | 1368.4
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 | 0
PB 2017 Total | 1525 | 146.1 |  |  | 59.5 | 100.2 | 129.8 |  | 102.2 |  | 21.4 |  |  | 152.8 | 2237
PB 2016 Total | 1546 | 144.1 |  |  | 70 | 69.1 | 88.6 |  | 76.9 |  | 42.8 |  |  | 23.6 | 2061.1
Delta | -21 | 2 |  |  | -10.5 | 31.1 | 41.2 |  | 25.3 |  | -21.4 |  |  | 129.2 | 175.9
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 28 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 28
Production | 0 |  | 205 |  | 12 | 2 | 8 |  | 10 |  | 13 | 0 |  | 0 |  | 250
PB 2017 Total | 28 |  | 205 |  | 12 | 2 | 8 |  | 10 |  | 13 | 0 |  | 0 |  | 278
PB 2016 Total | 28 |  | 205 |  | 12 | 3 | 3 |  | 17 |  | 6 | 4 |  | 0 |  | 278
Delta | 0 |  | 0 |  | 0 | -1 | 5 |  | -7 |  | 7 | -4 |  | 0 |  | 0

## Table 19
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.6
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.4
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 64.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 87.7
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 108.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 78.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.5
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.1
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 34.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.3
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.2
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.7
Subtotal |  | 28 | -- |  | -- |  | -- |  | -- |  | -- |  | 868.6

## Table 20
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.5
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 68.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 75.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 92.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.4
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.8
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.6
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.1
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.8
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.1
2022 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.1
2023 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.8
2024 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.6
Subtotal |  | 28 | -- |  | -- |  | -- |  | -- |  | -- |  | 728.1

## Table 21
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | 33 | 52.9 |  | -- |  | 8.7 |  | 61.6 |  | -- |  | 61.6
2011 |  | 54 | 87.4 |  | -- |  | 24.1 |  | 111.5 |  | -- |  | 111.5
2012 |  | 26 | 56.7 |  | -- |  | 50.6 |  | 107.3 |  | -- |  | 107.3
2013 |  | 34 | 100.3 |  | -- |  | 55.9 |  | 156.2 |  | -- |  | 156.2
2014 |  | 41 | 100 |  | -- |  | 83.6 |  | 183.6 |  | -- |  | 183.6
2015 |  | 17 | 88.3 |  | -- |  | 144.9 |  | 233.2 |  | -- |  | 233.2
2016 |  | 12 | 48.2 |  | -- |  | 69.9 |  | 118.1 |  | -- |  | 118.1
2017 |  | 2 | 3.5 |  | -- |  | 34.9 |  | 38.4 |  | -- |  | 38.4
2018 |  | 8 | 23.3 |  | -- |  | 44.8 |  | 68.1 |  | -- |  | 68.1
2019 |  | 10 | 55.2 |  | -- |  | 39.8 |  | 95 |  | -- |  | 95
2020 |  | 13 | 35.2 |  | -- |  | 36.2 |  | 71.4 |  | -- |  | 71.4
2021 |  | -- | -- |  | -- |  | 11.1 |  | 11.1 |  | -- |  | 11.1
2022 |  | -- | -- |  | -- |  | 25.5 |  | 25.5 |  | -- |  | 25.5
2023 |  | -- | 12.1 |  | -- |  | 2.3 |  | 14.4 |  | -- |  | 14.4
2024 |  | -- | 11.2 |  | -- |  | 9.5 |  | 20.7 |  | -- |  | 20.7
2025 |  | -- | 10.2 |  | -- |  | 7.2 |  | 17.4 |  | -- |  | 17.4
2026 |  | -- | 8.4 |  | -- |  | 6.3 |  | 14.7 |  | -- |  | 14.7
2027 |  | -- | 7.6 |  | -- |  | 5.1 |  | 12.7 |  | -- |  | 12.7
2028 |  | -- | 2.8 |  | -- |  | 4.7 |  | 7.5 |  | -- |  | 7.5
Subtotal |  | 250 | 703.3 |  | -- |  | 665.1 |  | 1368.4 |  | -- |  | 1368.4

## Table 22
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2002 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2010 |  | 33 | 43.7 |  | -- |  | 7.2 |  | 50.9 |  | -- |  | 50.9
2011 |  | 54 | 71.2 |  | -- |  | 19.6 |  | 90.8 |  | -- |  | 90.8
2012 |  | 26 | 45.5 |  | -- |  | 40.5 |  | 86 |  | -- |  | 86
2013 |  | 34 | 79.3 |  | -- |  | 44.3 |  | 123.6 |  | -- |  | 123.6
2014 |  | 41 | 78.1 |  | -- |  | 65.2 |  | 143.3 |  | -- |  | 143.3
2015 |  | 17 | 68 |  | -- |  | 111.5 |  | 179.5 |  | -- |  | 179.5
2016 |  | 12 | 36.5 |  | -- |  | 52.9 |  | 89.4 |  | -- |  | 89.4
2017 |  | 2 | 2.6 |  | -- |  | 25.9 |  | 28.5 |  | -- |  | 28.5
2018 |  | 8 | 17 |  | -- |  | 32.6 |  | 49.6 |  | -- |  | 49.6
2019 |  | 10 | 39.4 |  | -- |  | 28.5 |  | 67.9 |  | -- |  | 67.9
2020 |  | 13 | 24.7 |  | -- |  | 25.3 |  | 50 |  | -- |  | 50
2021 |  | -- | -- |  | -- |  | 7.6 |  | 7.6 |  | -- |  | 7.6
2022 |  | -- | -- |  | -- |  | 17.2 |  | 17.2 |  | -- |  | 17.2
2023 |  | -- | 8 |  | -- |  | 1.5 |  | 9.5 |  | -- |  | 9.5
2024 |  | -- | 7.2 |  | -- |  | 6.2 |  | 13.4 |  | -- |  | 13.4
2025 |  | -- | 6.5 |  | -- |  | 4.5 |  | 11 |  | -- |  | 11
2026 |  | -- | 5.2 |  | -- |  | 3.9 |  | 9.1 |  | -- |  | 9.1
2027 |  | -- | 4.6 |  | -- |  | 3.1 |  | 7.7 |  | -- |  | 7.7
2028 |  | -- | 1.7 |  | -- |  | 2.8 |  | 4.5 |  | -- |  | 4.5
Subtotal |  | 250 | 539.2 |  | -- |  | 500.3 |  | 1039.5 |  | -- |  | 1039.5

## Table 23
Cost Quantity Information 1810 ¦ Procurement ¦ Other Procurement, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 2002 $M
2010 | 33 | 47.7
2011 | 54 | 74.2
2012 | 26 | 48.5
2013 | 34 | 82.5
2014 | 41 | 80.1
2015 | 17 | 72
2016 | 12 | 38.5
2017 | 2 | 5.6
2018 | 8 | 19
2019 | 10 | 43.4
2020 | 13 | 27.7
2021 | -- | --
2022 | -- | --
2023 | -- | --
2024 | -- | --
2025 | -- | --
2026 | -- | --
2027 | -- | --
2028 | -- | --
Subtotal | 250 | 539.2

## Table 24
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2003-07-21 | 2012-02-28
Approved Quantity | 90 | 113
Reference | Milestone B Acquisition Strategy | Extended LRIP ADM
Start Year | 2010 | 2010
End Year | 2011 | 2012
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the strong technical performance of NMT during Operational Assessment.
The Total LRIP is also more than 10% in order to ensure a smooth and consistent establishment of production capacity, as well as to take advantage of the significant operational benefits from providing the NMT capability aligned with the satellites with which it operates.
A Gate-6/FRP Decision Review was conducted on November 8, 2012 and approved via an ADM on November 30, 2012. This ADM authorized full production and installation for the NMT Program of Record and Other Customers.
Approved quantity reflects the U.S. Navy fleet modernization buy, and does not include Other Customer Funded quantities.

## Table 25
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
United Kingdom | 2007-04-18 | 16 | 96.1 | FMS Case UK-P-LTN and UK-P-LVA
Netherlands | 2006-07-26 | 5 | 37.9 | FMS Case NE-P-LGR
Canada | 2006-03-30 | 23 | 89 | FMS Case CN-P-LHL
Notes
Nuclear Costs
None

## Table 26
Unit Cost
Unit Cost Report
Item |  | BY 2002 $M | BY 2002 $M |  | % Change
|  | Current UCR Baseline (Mar 2016 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1771.4 |  |  | 1767.6
Quantity | 278 |  |  | 278
Unit Cost | 6.372 |  |  | 6.358 |  |  | -0.22
Average Procurement Unit Cost
Cost | 1041.6 |  |  | 1039.5
Quantity | 250 |  |  | 250
Unit Cost | 4.166 |  |  | 4.158 |  |  | -0.19
Item |  | BY 2002 $M | BY 2002 $M |  | % Change
|  | Original UCR Baseline (Dec 2006 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1923.4 |  |  | 1767.6
Quantity | 333 |  |  | 278
Unit Cost | 5.776 |  |  | 6.358 |  | 10.08
Average Procurement Unit Cost
Cost | 1345.6 |  |  | 1039.5
Quantity | 305 |  |  | 250
Unit Cost | 4.412 |  |  | 4.158 |  | -5.76

## Table 27
Unit Cost History
Item | [7 empty] | Date |  |  |  |  | BY 2002 $M | [5 empty] | TY $M
[13 empty] | PAUC |  | APUC |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Dec 2006 | [7 empty] | 5.776 |  |  | 4.412 |  |  |  | 6.97 |  |  |  | 5.544
APB as of January 2006 |  |  |  |  | N/A | [7 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Revised Original APB |  |  |  |  | N/A | [7 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Apr 2013 | [7 empty] | 5.498 |  |  | 3.857 |  |  |  | 6.823 |  |  |  | 5.017
Current APB |  |  |  |  | Mar 2016 | [7 empty] | 6.372 |  |  | 4.166 |  |  |  | 8.047 |  |  |  | 5.474
Prior Annual SAR |  |  |  |  | Dec 2014 | [7 empty] | 5.924 |  |  | 3.91 |  |  |  | 7.414 |  |  |  | 5.108
Current Estimate |  |  |  |  | Dec 2015 | [7 empty] | 6.358 |  |  | 4.158 |  |  |  | 8.047 |  |  |  | 5.474
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [20 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth | Spt |  |  | Total
6.970 0.082 0.637 0.034 0.000 -1.210 0.000 -0.418 -0.875 6.095
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [18 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth | Spt |  | Total
6.095 0.008 0.297 0.033 0.762 0.852 0.000 0.000 1.952 8.047

## Table 28
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [14 empty] | APUC Production Estimate
| Econ | Qty |  | Sch |  | Eng |  |  | Est |  | Oth |  | Spt |  | Total
5.544 0.047 0.553 0.038 0.000 -1.295 0.000 -0.461 -1.118 4.426
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  |  | Est |  | Oth |  | Spt | Total
4.426 0.009 0.156 0.037 0.350 0.496 0.000 0.000 1.048 5.474
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  |  | SAR Development Estimate | [5 empty] | SAR Production Estimate |  |  | Current Estimate
Milestone A |  |  | N/A |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A
Milestone B |  |  | N/A |  |  |  |  | Oct 2003 | [5 empty] | Oct 2003 |  |  | Oct 2003
Milestone C |  |  | N/A |  |  |  |  | Feb 2010 | [5 empty] | Feb 2010 |  |  | Aug 2010
IOC |  |  | N/A |  |  |  |  | Sep 2012 | [5 empty] | Sep 2012 |  |  | Dec 2012
Total Cost (TY $M) |  |  | N/A |  |  |  |  | 2321.1 | [5 empty] | 1853 |  |  | 2237
Total Quantity |  |  | N/A |  |  |  |  | 333 | [5 empty] | 304 |  |  | 278
PAUC |  |  | N/A |  |  |  |  | 6.97 | [5 empty] | 6.095 |  |  | 8.047

## Table 29
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
631.3 1221.7 -- 1853.0
Economic |  | 0.7 |  | 7.9 |  | -- |  | 8.6
Quantity |  | -- |  | -76.3 |  | -- |  | -76.3
Schedule |  | -- |  | 9.6 |  | -- |  | 9.6
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 152.1 |  | 114.1 |  | -- |  | 266.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 152.8 |  | 55.3 |  | -- |  | 208.1
Current Changes Economic |  | -0.7 |  | -5.6 |  | -- |  | -6.3
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -0.3 |  | -- |  | -0.3
Engineering |  | 124.5 |  | 87.4 |  | -- |  | 211.9
Estimating |  | -39.3 |  | 9.9 |  | -- |  | -29.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 84.5 |  | 91.4 |  | -- |  | 175.9
Total Changes |  | 237.3 |  | 146.7 |  | -- |  | 384
CE - Cost Variance |  | 868.6 |  | 1368.4 |  | -- |  | 2237
CE - Cost & Funding |  | 868.6 |  | 1368.4 |  | -- |  | 2237

## Table 30
Summary BY 2002 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
555.9 962.0 -- 1517.9
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -55.9 |  | -- |  | -55.9
Schedule |  | -- |  | -0.7 |  | -- |  | -0.7
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 113.3 |  | 72.2 |  | -- |  | 185.5
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 113.3 |  | 15.6 |  | -- |  | 128.9
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | 88.9 |  | 55.2 |  | -- |  | 144.1
Estimating |  | -30 |  | 6.7 |  | -- |  | -23.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 58.9 |  | 61.9 |  | -- |  | 120.8
Total Changes |  | 172.2 |  | 77.5 |  | -- |  | 249.7
CE - Cost Variance |  | 728.1 |  | 1039.5 |  | -- |  | 1767.6
CE - Cost & Funding |  | 728.1 |  | 1039.5 |  | -- |  | 1767.6
Previous Estimate: December 2014

## Table 31
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -0.7
Revised estimate to reflect the addition of the Wideband Anti-Jam Modem System (WAMS). (Engineering)
Revised estimate to reflect cost estimating methodology changes to align with the updated SCP. (Estimating)
Revised estimate due to funding reductions, such as the RDT&E Underexecution Mark, and WAMS IOC rephasing. (Estimating)
+88.9 +124.5
-17.2 -22.5
-13.2 -17.3
Adjustment for current and prior escalation. (Estimating) +0.4 +0.5
RDT&E Subtotal +58.9 +84.5
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -5.6
Acceleration of procurement buy profile caused by FY 2018 - FY 2020 Other Procurement, Navy (OPN) funding realignments. (Schedule)
Revised estimate to reflect the addition of the Wideband Anti-Jam Modem System. (Engineering)
Revised estimate to reflect cost estimating methodology changes to align with the updated SCP. (Estimating)
Revised estimate due to funding reductions, such as the OPN Underexecution Mark, and WAMS IOC rephasing. (Estimating)
0.0 -0.3
+55.2 +87.4
+2.8 +4.3
+1.2 +2.1
Adjustment for current and prior escalation. (Estimating) +2.7 +3.5
Procurement Subtotal +61.9 +91.4

## Table 32
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: NMT Production & Deployment
Contractor: Raytheon
Contractor Location: 1001 Boston Post Road
Marlboro, MA 01752
Contract Number: N00039-04-C-0012/3
Contract Type: Firm Fixed Price (FFP)
Award Date: September 07, 2010
Definitization Date: September 07, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
641.5 N/A 276 394.2 N/A 205 394.2 394.2
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a reduction in inventory objective and the extension of the NMT fielding plan, both of which reduced the number of terminals procured on the contract. In response to a change in Navy requirements, the inventory objective was reduced from 276 to 250.
Furthermore, fact of life changes such as funding reductions have moved the procurement of 45 terminals onto the Follow- On Full Deployment contract, which was awarded December 29, 2015.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 33
Contract Identification
Appropriation: Procurement
Contract Name: NMT Follow-On Full Deployment
Contractor: Raytheon
Contractor Location: 1001 Boston Post Road
Marlboro, MA 01752
Contract Number: N00039-16-C-0050/1
Contract Type: Firm Fixed Price (FFP)
Award Date: December 29, 2015
Definitization Date: December 29, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
203.7 N/A 45 203.7 N/A 45 203.7 203.7
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
This is the first time this contract is being reported.

## Table 34
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 28 | 28 | 28 | 100%
Production | 179 | 172 | 250 | 68.8%
Total Program Quantity Delivered | 207 | 200 | 278 | 71.94%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
2237
1240.1
55.44%
28
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
16
57.14%
1671.1
74.7%
The above data is current as of February 09, 2016.
Production Deliveries to Date reflect U.S. Navy fleet modernization buys, and do not include Other Customer Funds quantities.

## Table 35
Operating and Support Cost
Cost Estimate Details
Date of Estimate: December 18, 2015
Source of Estimate: SCP
Quantity to Sustain: 250
Unit of Measure: System
Service Life per Unit: 21.00 Years
Fiscal Years in Service: FY 2012 - FY 2032
The NMT unit of measure is defined as a single terminal, to include the Communication Group, Antennas, and Radomes. Total O&S reflects the sum of all costs resulting from the operation, maintenance, and support of NMT terminals after acceptance into the Navy Inventory. Efforts include depot maintenance, sustaining support, In Service Engineering Activity, program management, system engineering, system test & evaluation, software maintenance and facilities costs. The 28 RDT&E funded Engineering Development Model assets are not included in the NMT sustainment plan because they are not part of the fielded inventory objective.
Sustainment Strategy
The NMT sustainment strategy includes the maintenance of both the hardware and software. The hardware maintenance employs a three level concept – Organizational, Intermediate, and Depot. The Intermediate maintenance will be performed by the Regional Maintenance Centers and further supported by the In Service Engineering Agent Atlantic and Pacific, and include efforts such as the help desk, Fleet assistance, and life cycle testing. The Depot maintenance includes any repairs to the Antenna Systems (organic) and Communication Group (commercial). The Sparing concept includes both On Board Repair Parts, which support each fielded platform, and Supply System Stock, which are secondary items required for full life cycle support as managed through Naval Supply Systems Command Weapon Systems Support. Additionally, the program will provide major combatants with added allowance items that include parts identified as single points of failure. The Original Equipment Manufacturer is the assigned Software Support Activity.
Software Maintenance will include a combination of refresh and maintenance, to include updates, fixes, and patches. The software refreshes will occur approximately every 18 months through the end of the system life.
Antecedent Information
The Navy Extremely High Frequency Satellite Program (NESP) and WSC-6 Super High Frequency (SHF) programs are antecedent programs to NMT, but program costs are not readily available.
Annual O&S Costs BY2002 $K
Cost Element | NMT Average Annual Cost Per System | No Antecedent (Antecedent) N/A
Unit-Level Manpower | 39.4 | 0
Unit Operations | 0 | 0
Maintenance | 2.3 | 0
Sustaining Support | 21.9 | 0
Continuing System Improvements | 0 | 0
Indirect Support | 24 | 0
Other | 0 | 0
Total | 87.6 | --

## Table 36
Item | Total O&S Cost $M
| NMT | [5 empty] | No Antecedent (Antecedent)
| Current Production APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 253 |  | 278.3 |  |  | 253 | N/A
Then Year | 377.5 |  | N/A |  |  | 377.5 | N/A
Disposal Cost is included in the Operating and Support Cost of the current APB objective and threshold for this program.
Unit-Level Manpower costs are not included in the NMT APB nor in the current estimate.
Equation to Translate Annual Cost to Total Cost
Total O&S = (Average Annual Cost per System - Unit-Level Manpower Cost) * Total Number of NMT Systems * NMT System Life
$253.0M = ($87.6K - $39.4K) * 250 * 21
O&S Cost Variance
Category |  | BY 2002 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
169.3
Programmatic/Planning Factors 25.3 Revised estimate to reflect the addition of the Wideband Anti-Jam Modem System.
Cost Estimating Methodology 58.4 Revised estimate to reflect cost estimating methodology changes in the updated SCP. Changes include revised Cost Estimating Relationships and underlying assumptions used to estimate Software Maintenance costs as well as the addition of code maintenance associated with Adaptive Coding (AC) and Advanced Time Division Multiple Access Interface Processor (ATIP). AC and ATIP were not included in the previous estimate.
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 83.7
Current Estimate 253.0
Disposal Estimate Details
Date of Estimate: December 18, 2015
Source of Estimate: SCP
Disposal/Demilitarization Total Cost (BY 2002 $M): Total costs for disposal of all System are 0.5

## Table 37
Costs include equipment removal; packaging, handling, storage and distribution; and disposition services.