## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-286
Remote Minehunting System (RMS)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 11
Track to Budget 13
Cost and Funding 15
Low Rate Initial Production 22
Foreign Military Sales 23
Nuclear Costs 23
Unit Cost 24
Cost Variance 28
Contracts 31
Deliveries and Expenditures 33
Operating and Support Cost 34

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Remote Minehunting System (RMS)
DoD Component
Navy
Responsible Office
CAPT William Guarini
1333 Isaac Hull Avenue, S.E. Washington Navy Yard, Bldg. 197 Washington, DC 20376
William.Guarini@navy.mil
Phone: | 202-781-4103
Fax: | 202-781-4576
DSN Phone: | 326-4103
DSN Fax: Date Assigned: | March 6, 2014
References
SAR Baseline (Development Estimate)
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 7, 2010
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated October 23, 2012

## Table 6
Mission and Description
The Remote Minehunting System (RMS) is a mine reconnaissance system designed for the detection, classification, identification, and localization of bottom and moored mines in shallow and deep water. The RMS is a fully integrated system consisting of a semi-submersible Remote Multi-Mission Vehicle (RMMV) with a tethered, towed variable depth sensor, the AN/AQS-20. The RMMV is a high-endurance, semi-autonomous, low-observable, unmanned vehicle. The AN/AQS-20, a separate Acquisition Category II program, incorporates five separate sonars/sensors (side-look sonar, forward-look sonar, volume search sonar, gap fill sonar, and electro-optical identification sensor) in a compact, lightweight, and hydrodynamically stable towed body. The AN/AQS-20 localizes mine-like objects and provides the operator with a visual image and a contact data list. All mission data is recorded by the Littoral Combat Ship (LCS) for post-mission analysis. Line
-of-Sight and Over-the-Horizon communication provides vehicle Command and Control and mine reconnaissance sensor data transmission. The RMS will provide the Navy the capability to keep ships and Sailors out of the minefield and will be deployed from the LCS as part of the Mine Countermeasures Mission Package (MCM MP).

## Table 7
Executive Summary
This is the final SAR submission for the Remote Minehunting System (RMS) program, because the program has been cancelled.
The RMS is a fully integrated system consisting of the Remote Multi-Mission Vehicle (RMMV) and AN/AQS-20 minehunting sonar system. On June 1, 2010, following critical Nunn McCurdy unit cost breaches, the Under Secretary of Defense for Acquisition, Technology, and Logistics (USD(AT&L)) restructured the RMS program as an Acquisition Category ID program and, as required by 10 U.S.C. §2433a, rescinded Milestone (MS) C for the program. USD(AT&L) has not approved the RMS program re-entry into the MS C phase.
The RMMV supported the Littoral Combat Ship (LCS) Mine Countermeasures (MCM) Mission Package (MP) Technical Evaluation (TECHEVAL) from March 2015 through August 2015. The v6.0 RMMVs (1, 7, 9, & 10) were tested from an LCS with 22 launches and 380 hours operating time. The RMMV successfully demonstrated its minehunting performance requirements, but failed to meet the reliability requirement. Subsequently, as a result of the RMMVs unsatisfactory demonstrated reliability, the Assistant Secretary of the Navy, Research, Development, and Acquisition (ASN( RD&A) and the Chief of Naval Operations (CNO) chartered an RMS Independent Review Team (IRT) to assess RMMV technical performance and reliability, requirements, and program management structure and conduct an Analysis of Alternatives of unmanned systems to achieve the Navy’s LCS minehunting requirements.
The Navy’s budget exhibits in support of the FY 2017 PB were prepared prior to the RMS IRT report being finalized, and
those budget exhibits reflected anticipated changes to the RMS program. In the FY 2016 PB, the RMS program received a
$34.5M reduction in the Other Procurement, Navy (OPN) line and a $2.5M reduction in the RD&TE line. The FY 2017 PB zeroes OPN beginning in FY 2017 and RDT&E beginning in FY 2018. The FY 2016 PB showed 2 units to be procured in FY 2016 and stated that a total quantity of 54 RMS units would be procured at program completion. FY 2017 PB shows 1 unit to be procured in FY 2016 and states that a total quantity of 11 RMS units would be procured at program completion.
On February 24, 2016, the ASN(RD&A) and the CNO concurred with the RMS IRT report’s recommendations, one of which was to halt procurement of additional RMS units. In March 2016, USD(AT&L) issued an ADM that cancelled the RMS program. The ADM reduced the RMS program’s total procurement quantity to the 10 units delivered. The ADM directed that RMS production activities shall cease in an orderly manner and that the 10 units delivered shall be sustained until they are transitioned to another acquisition program to serve as test and integration assets.
The RMS program’s cancellation will result in critical Nunn McCurdy unit cost breaches. Specifically, the Navy calculates that the reduction in the total quantity of RMS units from 54 to 10 will cause: (a) the PAUC to increase 211.91% in relationship to the PAUC baseline in the current APB; and, (b) the APUC to increase by 24.95% in relationship to the APUC baseline in the current APB. Accordingly, the information required by 10 U.S.C. §2433(g)(1) (A) - (F) is included in this report.
In accordance with 10 U.S.C. §2433(g)(2), the Secretary of Defense certification is not required to be submitted for the RMS program. In accordance with 10 U.S.C. §2433(d)(3), this report notifies Congress of the Secretary of the Navy’s determination that the PAUC and APUC for the RMS program have increased by a percentage greater than the critical unit cost growth threshold, and these increases are attributed above to the program’s cancellation.
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
The impact of the FY 2017 PB reductions will cause Nunn McCurdy unit cost breaches and multiple APB breaches to
schedule. The March 2016 ADM issued by USD(AT&L) truncates the RMS program to the 10 units already delivered.
The O&S Cost reported in this SAR are based on the Program Life Cycle Cost Estimate dated August 2014. This was based upon an inventory of 54 units, which has been dramatically reduced following FY 2017 PB, which results in an O&S breach.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC Critical APUC Significant
Original UCR Baseline
PAUC Critical
APUC None

## Table 9
Schedule
(Ch-1)
(Ch-1)
(Ch-2)
(Ch-1)
(Ch-1)
(Ch-1)
(Ch-1)
Schedule Events
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Milestone II | Dec 1999 | Dec 1999 | Jun 2000 | Dec 1999
OA (Shallow) | Apr 2005 | Apr 2005 | Oct 2005 | Apr 2005
Milestone C/LRIP | Jul 2005 | Jul 2005 | Jan 2006 | Jul 2005
Operational Assessment | Aug 2006 | Aug 2006 | Feb 2007 | Aug 2006
Second LRIP Decision | Sep 2006 | Sep 2006 | Mar 2007 | Sep 2006
DT/OA Increment 1 | Feb 2014 | Feb 2014 | Aug 2014 | Dec 2013
Milestone C | May 2014 | May 2014 | Nov 2014 | N/A1
LRIP Contract Award w/Options for FRP | Sep 2014 | Sep 2014 | Mar 2015 | N/A1
Initial Operational Capability | Jan 2015 | Jan 2015 | Jul 2015 | Aug 20181
TECHEVAL | Mar 2017 | Mar 2017 | Sep 2017 | N/A1
OPEVAL | Jun 2017 | Jun 2017 | Dec 2017 | N/A1
Full Rate Production | Jul 2017 | Jul 2017 | Jan 2018 | N/A1
Excercise FRP Contract Options under LRIP Contract | Oct 2017 | Oct 2017 | Apr 2018 | N/A1
1 APB Breach

## Table 10
Change Explanations
(Ch-1) The current estimates for the following schedule events have changed to N/A because the Navy will procure no additional RMS units:
-Milestone C
-LRIP Contract Award w/Options for FRP
-TECHEVAL
-OPEVAL
-Full Rate Production
-Exercise FRP Contract Options under LRIP Contract
(Ch-2) The current estimate for IOC has changed from February 2016 to Aug 2018 because only LRIP 1 will proceed to support deployments.
Acronyms and Abbreviations
DT - Developmental Testing MCM - Mine Countermeasures OA - Operational Assessment OPEVAL - Operational Evaluation
RMMV - Remote Multi-Mission Vehicle TECHEVAL - Technical Evaluation

## Table 11
Performance
Performance Characteristics
SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Demonstrated Performance | Current Estimate
Operational Availability
0.85 | 0.85 | 0.8 | TBD | 0.6
Material Availability
N/A | 0.75 | 0.59 | TBD | 0.59
Net Ready
N/A | yes | yes | TBD | yes
Transit Speed (kts)
20 | N/A | N/A | N/A | N/A
Water Depth -Shallow
Mine Type
Bottom, CCT, CT, IV | N/A | N/A | N/A | N/A
Water Depth - Deep
Mine Type
CCT, CT, IV | N/A | N/A | N/A | N/A
(Ch-1)
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Capability Development Document (CDD) dated May 31, 2011
Change Explanations
(Ch-1) Based upon the performance of the Remote Multi Mission Vehicle (RMMV) during the Littoral Combat Ship Mine Countermeasures Mission Package (LCS MCM MP) Technical Evaluation (TECHEVAL), the current estimate has been revised from 0.80 to 0.60.
Notes
The RMS CPD was approved on March 28, 2014. There are no changes to the KPPs based on the CPD. A Milestone C is no longer planned for the program, therefore an update to the APB is unnecessary.

## Table 12
Acronyms and Abbreviations
CCT - Close-Close Tethered CT - Close Tethered
IV - In-Volume kts - knots
MS - Milestone

## Table 13
Track to Budget
RDT&E
Appn |  | BA | PE
Navy | 1319 04 |  | 0603502N
| Project |  | Name
| 260 |  | Surface and Shallow Water (Shared) (Sunk) Mine Countermeasures
| Notes: |  | Active through FY 2014
| 9999 |  | Remote Minehunting Systems (Shared) (Sunk)
| Notes: |  | Congressional Add to continue development of RMS during the RMS reliability growth program.
Navy | 1319 04 |  | 0603581N
| Project |  | Name
| 3129 |  | LCS Mission Package (Shared) (Sunk) Development
| Notes: |  | Funding is provided to research and study methods to employ mine warfare mission modules independently of the Littoral Combat Ship (LCS) platform.
Navy | 1319 04 |  | 0604122N
| Project |  | Name
| 260 |  | Remote Minehunting Systems
| Notes: |  | Active beginning in FY 2015.
Procurement
Appn |  | BA | PE
Navy | 1810 01 |  | 0204230N
| Line Item |  | Name
| 1601 |  | LCS MCM Mission Modules (Shared) (Sunk)
| Notes: |  | The RMS budget is only the Remote Multi-Mission Vehicle (RMMV) element of cost under the Cost Code LM001.
| 1605 |  | Remote Minehunting Systems (RMS)
| Notes: |  | Includes Remote Multi Mission Vehicles (RMMV), RMMV Cradles and Production Engineering.
Navy | 1810 02 |  | 0204302N
| Line Item |  | Name
| 2622 |  | Minesweeping System (Shared) (Sunk) Replacement
| Notes: |  | The RMS budget is comprised of all the elements of cost listed under Cost Code LV064, RMS.
Navy | 1810 08 |  | 0204228N

## Table 14
Line Item Name
9020 Spares and Repair Parts (Shared) (Sunk)

## Table 15
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2006 $M |  |  |  |  | BY 2006 $M |  | TY $M
| SAR Baseline Development Estimate |  | Current APB Development Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Development Estimate |  | Current APB Development Objective |  | Current Estimate
RDT&E |  | 649.6 |  | 649.6 | 714.2 |  | 618 |  | 654.4 |  | 654.4 |  | 617.3
Procurement |  | 630 |  | 630 | 693 |  | 121.1 |  | 795 |  | 795 |  | 127.3
Flyaway |  | -- |  | -- | -- |  | 101.9 |  | -- |  | -- |  | 107.2
Recurring |  | -- |  | -- | -- |  | 101.9 |  | -- |  | -- |  | 107.2
Non Recurring |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
Support |  | -- |  | -- | -- |  | 19.2 |  | -- |  | -- |  | 20.1
Other Support |  | -- |  | -- | -- |  | 19.2 |  | -- |  | -- |  | 20.1
Initial Spares |  | -- |  | -- | -- |  | 0 |  | -- |  | -- |  | 0
MILCON |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total |  | 1279.6 |  | 1279.6 | N/A |  | 739.1 |  | 1449.4 |  | 1449.4 |  | 744.6
Confidence Level
Confidence Level of cost estimate for current APB: 50%
The Independent Cost Estimate to support the RMS Nunn-McCurdy certification, like all life-cycle cost estimates previously performed by the Cost Assessment and Program Evaluation (CAPE), is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Derpartment has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs (MDAPs). Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.

## Table 16
Total Quantity
Quantity | SAR Baseline Development Estimate | Current APB Development | Current Estimate
RDT&E | 2 | 2 | 2
Procurement | 52 | 52 | 8
Total | 54 | 54 | 10
Quantity Notes
Of the $53.1M in the FY 2016 Other Procurement Navy (OPN) budget, it is expected the Navy will only release $18M for the program to fund the v6.0 upgrades. The Independent Review Team (IRT) report eliminated the Quantity 1 procurement of LRIP 2 in FY 2016.

## Table 17
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 596.7 | 17.6 |  | 3 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 617.3
Procurement | 109.3 | 18 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 127.3
MILCON | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 706 | 35.6 |  | 3 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 744.6
PB 2016 Total | 706 | 107.7 |  | 96.4 |  | 66.7 | 68 |  | 46 |  | 60.2 |  |  | 388.6 |  | 1539.6
Delta | 0 | -72.1 |  | -93.4 |  | -66.7 | -68 |  | -46 |  | -60.2 |  |  | -388.6 |  | -795
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 2 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 2
Production | 0 |  | 8 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 8
PB 2017 Total | 2 |  | 8 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 10
PB 2016 Total | 2 |  | 8 |  | 2 | 4 | 4 |  | 4 | 2 |  | 4 |  | 24 |  | 54
Delta | 0 |  | 0 |  | -2 | -4 | -4 |  | -4 | -2 |  | -4 |  | -24 |  | -44

## Table 18
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.9
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.6
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.4
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.5
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.9
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 55.4
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 59
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 56.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.3
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.7
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.5
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 50.3
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.6
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 617.3

## Table 19
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2006 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.8
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.2
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.7
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.6
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.7
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 46.9
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.5
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 44.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 32.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.9
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
Subtotal |  | 2 | -- |  | -- |  | -- |  | -- |  | -- |  | 618

## Table 20
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | 3 | 32.1 |  | -- |  | -- |  | 32.1 |  | 2.1 |  | 34.2
2006 |  | 4 | 46.3 |  | -- |  | -- |  | 46.3 |  | 11.7 |  | 58
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | 1 | 10.8 |  | -- |  | -- |  | 10.8 |  | 3.6 |  | 14.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | 2.7 |  | 2.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | 18 |  | -- |  | 18 |  | -- |  | 18
Subtotal |  | 8 | 89.2 |  | 18 |  | -- |  | 107.2 |  | 20.1 |  | 127.3

## Table 21
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2006 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2005 |  | 3 | 32.1 |  | -- |  | -- |  | 32.1 |  | 2.1 |  | 34.2
2006 |  | 4 | 44.8 |  | -- |  | -- |  | 44.8 |  | 11.3 |  | 56.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | 1 | 10.1 |  | -- |  | -- |  | 10.1 |  | 3.3 |  | 13.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | 2.5 |  | 2.5
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | -- | -- |  | 14.9 |  | -- |  | 14.9 |  | -- |  | 14.9
Subtotal |  | 8 | 87 |  | 14.9 |  | -- |  | 101.9 |  | 19.2 |  | 121.1

## Table 22
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2005-07-01 | 2010-06-01
Approved Quantity | 3 | 18
Reference | Milestone C ADM | Nunn-McCurdy ADM
Start Year | 2005 | 2005
End Year | 2007 | 2016
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the elimination of the Remote Multi- Mission Vehicles (RMMVs) for the Anti-Submarine Warfare Mission Package for the Littoral Combat Ship in the FY 2010 PB, which reduced the number of RMMV production units from 106 to 52.
In July 2005, the initial approval of three RMMV LRIP 1 units was authorized. The Assistant Secretary of the Navy for Research, Development, and Acquisition approved an additional four RMMV LRIP 1 units in September 2006 and one more RMMV LRIP 1 unit in April 2008. USD(AT&L) authorized ten additional RMMV LRIP 2 units in June 2010.
Eighteen RMMV LRIP units have been authorized to date and eight RMMV LRIP 1 units have been delivered. On August 25, 2014, USD(AT&L) issued an ADM that authorized the release of the LRIP 2 contract.
USD(AT&L) is the Milestone Decision Authority for the RMS program. The March 2016 ADM truncates the RMS program to the 10 units already delivered and directs the Navy to develop a transition plan to shut-down RMS production in an orderly fashion and sustain the 10 RMS units in the Navy’s inventory as test and integration assets.

## Table 23
Foreign Military Sales
None
Nuclear Costs
None

## Table 24
Unit Cost
Unit Cost Report
Item |  | BY 2006 $M | BY 2006 $M |  | % Change
|  | Current UCR Baseline (Oct 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1279.6 |  |  | 739.1
Quantity | 54 |  |  | 10
Unit Cost | 23.696 |  |  | 73.91 |  | +211.911
Average Procurement Unit Cost
Cost | 630 |  |  | 121.1
Quantity | 52 |  |  | 8
Unit Cost | 12.115 |  |  | 15.138 |  | +24.951
Item |  | BY 2006 $M | BY 2006 $M |  | % Change
Revised
|  | Original UCR | Current Estimate
|  | Baseline | (Dec 2015 SAR)
(Oct 2010 APB)
Program Acquisition Unit Cost
Cost | 1279.6 |  |  | 739.1
Quantity | 54 |  |  | 10
Unit Cost | 23.696 |  |  | 73.91 |  | +211.911
Average Procurement Unit Cost
Cost | 630 |  |  | 121.1
Quantity | 52 |  |  | 8
Unit Cost | 12.115 |  |  | 15.138 |  | 24.95
Item |  | TY $M |  |  | TY % Change
|  | Current UCR Baseline (Oct 2012 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost (PAUC)
Cost | 1449.4 |  |  | 744.6
Unit Cost | 26.841 |  |  | 74.46 |  | 177.41
Average Procurement Unit Cost (APUC)
Cost | 795 |  |  | 127.3
Unit Cost | 15.288 |  |  | 15.912 |  | 4.08

## Table 25
Item |  | TY $M | [6 empty] | TY % Change
|  | Revised Original UCR Baseline (Oct 2010 APB) |  | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost (PAUC)
Cost | 1449.4 |  |  |  |  | 744.6
Unit Cost | 26.841 |  |  |  |  | 74.46 |  |  |  | 177.41
Average Procurement Unit Cost (APUC)
Cost | 795 |  |  |  |  | 127.3
Unit Cost | 15.288 |  |  |  |  | 15.912 |  |  |  | 4.08
1
Nunn-McCurdy Breach
The impact of the FY 2017 PB reductions caused a Nunn-McCurdy unit cost breach. The March 2016 ADM issued by USD (AT&L) truncates the RMS program to the 10 units already delivered. The Unit Cost Report is reflective of Quantity 10 units vice the Quantity 11 provided in FY 2017 PB.
Unit Cost Breach Data
Changes From Previous SAR |  |  | $M/Qty. |  |  |  | Per | cent
PAUC (BY $M) |  |  |  |  | 49.323 |  |  | 200.61
APUC (BY $M) |  |  |  |  | 2.313 |  |  | 18.04
PAUC Quantity |  |  |  |  | -44 |  |  | 0
PAUC (TY $M) |  |  |  |  | 45.949 |  |  | 161.16
APUC (TY $M) |  |  |  |  | -0.78 |  |  | -4.67
Initial SAR Information - Dec 2006 |  |  | BY2006 $M |  |  |  | TY | $M
Program Acquisition Cost |  |  | 1298.2 |  |  |  | 1411.7
Unit Cost PAUC Changes
The impact of the FY 2017 PB reductions caused a Nunn-McCurdy unit cost breach. The March 2016 ADM issued by USD (AT&L) truncates the RMS program to the 10 units already delivered. The Unit Cost Report is reflective of Quantity 10 units vice the Quantity 11 provided in FY 2017 PB.
Unit Cost APUC Changes
The impact of the FY 2017 PB reductions caused a Nunn-McCurdy unit cost breach. The March 2016 ADM issued by USD (AT&L) truncates the RMS program to the 10 units already delivered. The Unit Cost Report is reflective of Quantity 10 units vice the Quantity 11 provided in FY 2017 PB.

## Table 26
Unit Cost History
Item | [7 empty] | Date |  |  |  | BY 2006 $M | [8 empty] | TY $M
[12 empty] | PAUC |  |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Oct 2006 | [6 empty] | 12.08 | [5 empty] | 8.364 |  |  |  | 12.957 |  |  |  | 9.572
APB as of January 2006 |  |  |  |  | N/A | [6 empty] | N/A | [5 empty] | N/A |  |  |  | N/A |  |  |  | N/A
Revised Original APB |  |  |  |  | Oct 2010 | [6 empty] | 23.696 | [5 empty] | 12.115 |  |  |  | 26.841 |  |  |  | 15.288
Prior APB |  |  |  |  | Oct 2010 | [6 empty] | 23.696 | [5 empty] | 12.115 |  |  |  | 26.841 |  |  |  | 15.288
Current APB |  |  |  |  | Oct 2012 | [6 empty] | 23.696 | [5 empty] | 12.115 |  |  |  | 26.841 |  |  |  | 15.288
Prior Annual SAR |  |  |  |  | Dec 2014 | [6 empty] | 24.587 | [5 empty] | 12.825 |  |  |  | 28.511 |  |  |  | 16.692
Current Estimate |  |  |  |  | Dec 2015 | [6 empty] | 73.91 | [5 empty] | 15.138 |  |  |  | 74.46 |  |  |  | 15.912
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Production Estimate | Changes | [22 empty] | PAUC Development Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  |  | Spt |  |  | Total
12.957 -0.752 3.262 2.950 0.454 6.344 0.000 1.626 13.884 26.841
Current SAR Baseline to Current Estimate (TY $M)
PAUC Development Estimate |  | Changes | [20 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  |  | Oth |  | Spt |  |  |  | Total
26.841 1.010 66.349 5.300 0.000 -12.520 0.000 -12.520 47.619 74.460

## Table 27
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Production Estimate | Changes | [14 empty] | APUC Development Estimate
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt | Total
9.572 -0.783 -0.129 3.238 0.000 1.702 0.000 1.688 5.716 15.288
Current SAR Baseline to Current Estimate (TY $M)
APUC Development Estimate | Changes | [14 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est |  | Oth |  | Spt |  | Total
15.288 0.838 19.399 6.625 0.000 -10.588 0.000 -15.650 0.624 15.912
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate | [5 empty] | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  |  | N/A | [5 empty] | N/A |  |  | N/A
Milestone II |  |  |  | N/A |  |  |  | N/A | [5 empty] | Dec 1999 |  |  | Dec 1999
Milestone C |  |  |  | N/A |  |  |  | May 2014 | [5 empty] | Jul 2005 |  |  | Jul 2005
IOC |  |  |  | N/A |  |  |  | Jan 2015 | [5 empty] | Sep 2007 |  |  | Aug 2018
Total Cost (TY $M) |  |  |  | N/A |  |  |  | 1449.4 | [5 empty] | 1399.4 |  |  | 744.6
Total Quantity |  |  |  | N/A |  |  |  | 54 | [5 empty] | 108 |  |  | 10
PAUC |  |  |  | N/A |  |  |  | 26.841 | [5 empty] | 12.957 |  |  | 74.46

## Table 28
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Development Estimate)
Previous Changes
654.4 795.0 -- 1449.4
Economic |  | 4.2 |  | 12.5 |  | -- |  | 16.7
Quantity |  | -- |  | -- |  | -- |  | --
Schedule |  | -- |  | 103.6 |  | -- |  | 103.6
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | 13 |  | -9.3 |  | -- |  | 3.7
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -33.8 |  | -- |  | -33.8
Subtotal |  | 17.2 |  | 73 |  | -- |  | 90.2
Current Changes Economic |  | -0.8 |  | -5.8 |  | -- |  | -6.6
Quantity |  | -- |  | -517.5 |  | -- |  | -517.5
Schedule |  | -- |  | -50.6 |  | -- |  | -50.6
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -53.5 |  | -75.4 |  | -- |  | -128.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -91.4 |  | -- |  | -91.4
Subtotal |  | -54.3 |  | -740.7 |  | -- |  | -795
Total Changes |  | -37.1 |  | -667.7 |  | -- |  | -704.8
CE - Cost Variance |  | 617.3 |  | 127.3 |  | -- |  | 744.6
CE - Cost & Funding |  | 617.3 |  | 127.3 |  | -- |  | 744.6

## Table 29
Summary BY 2006 $M
Item | RDT&E | Procurement | MILCON | Total
SAR Baseline (Development Estimate) | 649.6 | 630 | -- | 1279.6
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | 71.9 | -- | 71.9
Engineering | -- | -- | -- | --
Estimating | 11.2 | -10 | -- | 1.2
Other | -- | -- | -- | --
Support | -- | -25 | -- | -25
Subtotal | 11.2 | 36.9 | -- | 48.1
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -382.1 | -- | -382.1
Schedule | -- | -38 | -- | -38
Engineering | -- | -- | -- | --
Estimating | -42.8 | -58.7 | -- | -101.5
Other | -- | -- | -- | --
Support | -- | -67 | -- | -67
Subtotal | -42.8 | -545.8 | -- | -588.6
Total Changes | -31.6 | -508.9 | -- | -540.5
CE - Cost Variance | 618 | 121.1 | -- | 739.1
CE - Cost & Funding | 618 | 121.1 | -- | 739.1
Previous Estimate: December 2014
Cost Variance Notes
All variances are related to the impact of the FY 2017 PB and Independent Review Team (IRT) Report.

## Table 30
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -0.8
Adjustment for current and prior escalation. (Estimating) | 0.5 | 0.5
Revised Estimate to align to FY 2017 PB (Estimating) | -43.3 | -54
RDT&E Subtotal | -42.8 | -54.3
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -5.8
Adjustment for current and prior escalation. (Estimating) +0.5 +0.6
Quantity variance resulting from a decrease of 44 Remote Multi Mission Vehicles (RMMVs) from 52 to 8. (Subtotal)
-416.6 -563.2
Quantity variance resulting from a decrease of 44 RMMVs from 52 to 8. (Quantity) | -382.1 |  | -517.5
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -38 |  | -50.6
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -3.5 |  | -4.9
Revised Estimate to align to FY 2017 PB (Estimating) (QR) | -62.7 |  | -80.9
Decrease in Other Support due to a change in RMMV quantities. (Support) (QR) | -35.3 |  | -48.2
Decrease in Initial Spares due to the resulting decrease in RMMV quantities. (Support) (QR) | -31.7 |  | -43.2
Procurement Subtotal (QR) Quantity Related | -545.8 |  | -740.7

## Table 31
Contracts
Contract Identification
Appropriation: RDT&E
Contract Name: Remote Multi Mission Vehicle (RMMV) LRIP 1 Support BOA DO-1 TECHEVAL and IOT&E Support
Contractor: Lockheed Martin Corporation
Contractor Location: 100 East 17th Street
Riviera Beach, FL 33404
Contract Number: N00024-15-G-6315
Contract Type: Cost Plus Fixed Fee (CPFF)
Award Date: December 22, 2014
Definitization Date: December 22, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
85.5 N/A 0 14.7 N/A 0 14.7 14.7
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the ceiling price is the total value of the Basic Ordering Agreement (BOA), and the BOA will be comprised of multiple Delivery Orders (DOs). The Target Price is the total value of the first DO (DO-1).
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (CPFF) contract.
General Contract Variance Explanation
Cost and schedule variances are not reported for this contract, because the cost or incentive portion does not meet the threshold requirements for earned value management reporting.
Notes
Cost and schedule variances are not reported for this contract, because the cost or incentive portion does not meet the threshold requirements for earned value management reporting. The Delivery Order does not meet the threshold cost ($14.7).The Ceiling value of the Basic Ordering Agreement (BOA) is $85.5M. The BOA will be comprised of multiple Delivery Orders (DOs).

## Table 32
Contract Identification
Appropriation: RDT&E
Contract Name: Remote Minehunting System (RMS)/Littoral Combat Ship (LCS) Integration Contract
Contractor: Lockheed Martin Corporation
Contractor Location: 100 East 17th Street
Riviera Beach, FL 33404
Contract Number: N00024-13-C-6300/1
Contract Type: Cost Plus Fixed Fee (CPFF), Firm Fixed Price (FFP)
Award Date: May 21, 2013
Definitization Date: April 07, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
62.8 N/A 0 87.2 N/A 0 92.3 92.3
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to Increase in cost due to award of modification to upgrade of Remote Multi Mission Vehicles (RMMVs) 2, 5, and 6 to a v6.0 configuration via Firm- Fixed Price with an option.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (4/16/2015) |  |  |  | -1.9 |  |  |  | -0.3
Previous Cumulative Variances |  |  |  | -1.7 |  |  |  | -0.5
Net Change |  |  |  | -0.2 |  |  |  | 0.2
Percent Variance Percent Complete |  |  |  | -4.70% +91.04% |  |  |  | -0.6%
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to increased complexity to integrate with the AN/AQS-20 Pre Planned Product Improvement.
The favorable net change in the schedule variance is due to aging purchase requisitions.
Notes
Integrated Baseline Review was held on November 19, 2013 and contract was definitized on April 7, 2014.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 33
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 2 | 2 | 2 | 100%
Production | 8 | 8 | 8 | 100%
Total Program Quantity Delivered | 10 | 10 | 10 | 100%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
744.6
692.8
93.04%
22
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
21
95.45%
741.6
99.6%
The above data is current as of February 09, 2016.

## Table 34
Operating and Support Cost
Cost Estimate Details
Date of Estimate: March 16, 2016
Source of Estimate: POE
Quantity to Sustain: 10
Unit of Measure: Vehicle
Service Life per Unit: 10.00 Years
Fiscal Years in Service: FY 2015 - FY 2026
The Navy anticipates that the ADM issued will in effect truncate the RMS program to the 10 units already delivered and direct the Navy to develop a transition plan to shut-down RMS production in an orderly fashion and sustain the 10 RMS units in the Navy’s inventory as test and integration assets.
Sustainment Strategy
RMS currently plans to execute an "organic/industry " three level maintenance strategy. Afloat, Ashore and Depot maintenance approaches are defined as follows: Afloat - critical corrective maintenance with Mission Package Detachment trained in corrective maintenance procedures. Intermediate maintenance will be done by the Mission Package Support Facility or their representative such as the In-service Engineering Agent or other shore support activities. Depot – Analysis was completed and the Original Equipment Manufacturer (OEM) was selected based on the number of vehicles and the repair capabilities identified. The first ten units will be under the OEM Depot Source of Repair. The RMS program is following the Independent Review Team Recommendations to deploy RMS as part of the Littoral Combat Ship Mine Countermeasures Mission Package (LCS MCM MP) in FY 2018. Based upon its performance and that of the other Minehunting alternatives an assessment will be made by the Navy on what solution will continue forward. If RMS is not selected, it will likely be phased out through FY 2026. If RMS is selected, the program will be reinstated.
Antecedent Information
No Antecedent.
Annual O&S Costs BY2006 $K
Cost Element | RMS Average Annual Cost Per Vehicle | No Antecedent System (Antecedent) No Antecedent System
Unit-Level Manpower | 0 | --
Unit Operations | 4.605 | --
Maintenance | 507.662 | --
Sustaining Support | 45.649 | --
Continuing System Improvements | 123.884 | --
Indirect Support | 0 | --
Other | 17.251 | --
Total | 699.051 | --
The Unit-Level Manpower is a Littoral Combat Ship (LCS) Mission Module cost. RMS will still be deployed with the LCS Mine Countermeasure Mission Package (MCM MP) in FY 2018 per the Independent Review Team (IRT) recommendations.

## Table 35
Item | Total O&S Cost $M
| RMS | [5 empty] | No Antecedent System (Antecedent)
| Current Development APB Objective/Threshold |  |  |  | Current Estimate
Base Year | 649 |  | 713.9 |  |  | 69.9 | 0
Then Year | 1109 |  | N/A |  |  | 119.4 | N/A
The Current Estimate reflects the Program’s truncation to the 10 units already delivered along with the reduced service life of 10 years.
Equation to Translate Annual Cost to Total Cost
Total O&S Costs = Average Annual Cost Per Vehicle x # Remote Multi Mission Vehicle (RMMV) Units x Service Life;
$699.051K x 10 x 10 = $69,905K
O&S Cost Variance
Category |  | BY 2006 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
755
Programmatic/Planning Factors -685.1 Reflects change in POR inventory from 54 to 10 and the
reduction of service life from 20 to 10 years.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes -685.1
Current Estimate 69.9
Disposal Estimate Details
Date of Estimate: March 16, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 2006 $M): Total costs for disposal of all Vehicle are 0.8
The per unit disposal cost is $6.53 per pound (lb.) in BY 2006 and was derived from an analogy to the AN/SLQ-32 Program. The weight is 12,850 lbs. as identified in the Remote Multi-Mission Vehicle CARD. Phase-out and disposal of the system begins in FY 2019 and ends in FY 2026.