## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-554
Multifunctional Information Distribution System (MIDS)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 10
Schedule 11
Performance 14
Track to Budget 29
Cost and Funding 34
Low Rate Initial Production 66
Foreign Military Sales 67
Nuclear Costs 69
Unit Cost 70
Cost Variance 73
Contracts 77
Deliveries and Expenditures 84
Operating and Support Cost 85

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Multifunctional Information Distribution System (MIDS)
DoD Component
Navy
Joint Participants
Air Force; Army
Navy is the lead Component as specified in the Under Secretary of Defense for Acquisition, Technology, and Logistics (USD (AT&L)) Navy Program Delegation Decisions Acquisition Decision Memorandum (ADM) dated July 24, 2012
Responsible Office
CAPT Robert Croxson MIDS Program Office 33050 Nixie Way
Bldg 17A, Suite 422
San Diego, CA 92147-5416
robert.d.croxson@navy.mil
Phone: | 619-524-1549
Fax: | 619-524-1639
DSN Phone: | 524-1549
DSN Fax: | 524-1639
Date Assigned: | May 19, 2015
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated March 22, 2006
Approved APB
Assistant Secretary of the Navy (Research, Development & Acquisition) (ASN(RDA)) Approved Acquisition Program Baseline (APB) dated November 12, 2013

## Table 6
Mission and Description
The Multifunctional Information Distribution System (MIDS) program consists of two products, MIDS Low Volume Terminal (MIDS-LVT) and MIDS Joint Tactical Radio System (MIDS JTRS).
The MIDS-LVT is the product of the MIDS International Program Office (IPO), a multinational (U.S., France (FRA), Germany (DEU), Italy (ITA), and Spain (ESP)) cooperative development program with joint service participation (U.S. Navy (USN),
U.S. Army (USA), and U.S. Air Force (USAF)). The DoD established the program to design, develop and deliver low volume, lightweight tactical information system terminals for U.S. and Allied fighter aircraft, bombers, helicopters, ships, and ground sites. MIDS-LVT provides interoperability with North Atlantic Treaty Organization (NATO) and non-NATO users, significantly increasing force effectiveness and minimizing hostile actions and friend-on-friend engagements.
Three principal configurations of the terminal are in production and use an open system, modular architecture. MIDS-LVT
(1) includes voice, Tactical Air Navigation (TACAN) and variable power transmission and provides a Link 16 capability to the F/A-18, which was previously unable to use Joint Tactical Information Distribution System (JTIDS) due to space and weight limitations. MIDS-LVT(2) is an Army variant of MIDS-LVT tailored as a functional replacement for the JTIDS Class 2M terminal. MIDS-LVT(3), also referred to, as MIDS Fighter Data Link (FDL), is a reduced function terminal for the Air Force (no voice, no TACAN). MIDS-LVT contracted for Block Upgrade 2 (BU2) to incorporate Cryptographic (Crypto) Modernization (CM), Enhanced Throughput (ET), and Frequency Remapping (FR) in the MIDS-LVT terminal.
MIDS JTRS is designed as a U.S. Only Pre-Planned Product Improvement (P3I), executed as an Engineering Change Proposal (ECP) to the production MIDS-LVT configuration, and is fully compatible with MIDS-LVT. MIDS JTRS completed qualification in first quarter of FY 2010. It facilitated the Joint Program Executive Office (JPEO) JTRS incremental approach for fielding advanced JTRS transformational networking capability and transformed the MIDS-LVT into a four channel, Software Communications Architecture (SCA) compliant, Joint Tactical Radio. A form-fit-function replacement to MIDS- LVT, MIDS JTRS also adds three programmable 2 Megahertz (MHz) to 2 Gigahertz (GHz) channels capable of hosting the JTRS legacy and networking Waveforms (WFs). In addition to the Link 16, TACAN, and voice functionality found in MIDS- LVT, and MIDS-LVT BU2, MIDS JTRS adds capabilities such as CM, ET, FR, software programmability, Four Net Concurrent Multi-Netting with Concurrent Contention Receive (CMN-4), and Tactical Targeting Network Technology (TTNT). CMN-4 and TTNT are integral components of Naval Integrated Fire Control – Counter Air (NIFC-CA) and link together aircraft carrier strike group E-2Ds and EA-18s, and the aircraft carrier itself.

## Table 7
Executive Summary
Program Highlights Since Last Report:
The Multifunctional Information Distribution System (MIDS) Program Office (MPO) consists of two products, the MIDS Low Volume Terminal (MIDS-LVT) and the MIDS Joint Tactical Radio System (MIDS JTRS). The MIDS Program Manager (PM) continues implementation of an acquisition strategy that maintains continuous competition between the two U.S. production contractors, Datalink Solutions (DLS) and ViaSat, a software contract with BAE Systems, and directed procurements to EuroMIDS for MIDS-LVT. DLS is a consortium between BAE Systems and Rockwell Collins. EuroMIDS is a consortium among Airbus Defense & Space, Indra, Finmeccanica, and Thales.
MIDS-LVT Block Upgrade 2 (BU2) is a 39-month Engineering Change Proposal (ECP) awarded November 2013 to bring National Security Agency (NSA) mandated Crypto Modernization (CM) and National Telecommunications and Information Agency and Federal Aviation Agency mandated Frequency Remapping (FR) capability to the terminal.
MIDS-LVT is continuing development efforts and working to mitigate software integration issues and a potential schedule delay and funding shortfall. MIDS-LVT conducted multiple Hardware (HW)/Software (SW) Critical Design Reviews (CDRs) with vendors in February and March 2015 in support of the MIDS-LVT and BU2 efforts to successfully demonstrate design maturity in the areas of system, software, hardware, and security:
- DLS Hardware CDR was conducted in Wayne, NJ, on February 9-10, 2015.
- The Joint BAE, Thales, and Warner Robins Air Logistics Complex Centralized Software Support Activity (CSSA) Software
CDR was held in at Wayne, NJ, on February 11-13, 2015.
- The EuroMIDS BU2 Hardware CDR was conducted in Rome, ITA, on March 4-5, 2015.
- The ViaSat Hardware CDR was held at Carlsbad, CA, on March 25-26, 2015.
The MIDS Steering Committee #54 was hosted by Germany in Berlin, on March 17-19, 2015. Key agreements were obtained on the approval of the MIDS Program Management Plan (PMP) for the MIDS International Program Office (IPO) and concurrence on financial procedures for FY 2016. The next MIDS Steering Committee #55 was held in Rome, Italy on September 22-24, 2015. The meeting was chaired by Program Executive Officer for Tactical Aircraft Programs PEO(T) and focused on the status of the cooperative development of MIDS-LVT BU2.
The MIDS International Review Board (MIRB) #23 met in Brussels, Belgium, May 4-8, 2015, with 310 participants from 29 countries to discuss North Atlantic Treaty Organization’s (NATO's) integration of MIDS and MIDS-LVT BU2. MIRB #24 was held in Washington, DC on November 16-20, 2015, with 335 attendees from 28 Nations/Agencies. Topics included keynote addresses by PEO(T) and Air Force Headquarters Air Combat Command Deputy Director of Plans, Programs and Requirements, and updates on MIDS Products, Software, and Platforms.
As a follow-on to the MIDS JTRS Core terminal, MIDS JTRS Four Net Concurrent Multi-Netting with Concurrent Contention Receive (CMN-4) is being implemented as an ECP, and is considered a low risk enhancement to Link 16 while providing a significant upgraded capability for the Fleet. The MIDS Program Office (MPO) has coordinated all platform integration and test efforts with F/A-18 Program Management Air (PMA-265) throughout all MIDS efforts. This close relationship continues with the MIDS JTRS CMN-4 enhancement. Coordination involves over 3,500 hours of laboratory testing with no hardware failures, completion of the first MIDS JTRS CMN-4 flight in March 2015 and the completion of Government First Article Qualification Testing (GFAQT) in May 2015. MIDS JTRS CMN-4 Problem Reports (PRs) are being addressed as they are identified in Developmental Test (DT). Full MIDS JTRS CMN-4 functionality has been demonstrated successfully in the laboratory and inflight testing. MIDS JTRS is also enhancing the MIDS JTRS CMN-4 capability as MIDS Modernization Increments (MMI). MMI 1 development delivery orders were awarded to DLS and ViaSat in June 2015. The U.S. Air Force has also recognized the value of the MIDS JTRS CMN-4 capability and has begun development efforts to support migrating F-15, F-16 and F-22 squadrons to MIDS JTRS CMN-4.
The MIDS JTRS Tactical Targeting Network Technology (TTNT) L-Band development continued with a CDR on July 21-22, 2015. As a result of the Middle Class Tax Relief and Job Creation Act of 2012 and resulting spectrum sell-off, the MIDS

## Table 8
JTRS TTNT spectrum use will now include S-Band. Compensation for the sell-off and S-Band transition is being provided to the Services. The program office worked with Department of Navy Chief Information Officer (DoN CIO) and Office of the Chief of Naval Operations (OPNAV) for Information Dominance (N2/N6) on the appropriate use of the Spectrum Relocation Funds (SRF) and guidelines for spending and accounting of SRF dollars. The program office then led a SRF Planning Meeting on August 19, 2015 to plan the path forward for S-band integration into MIDS JTRS TTNT, the cost distribution between SRF and DoD funds, and the underlying assumptions for building the cost estimate for the L&S-Bands MIDS JTRS TTNT development. Expansion to S-Band impacts MIDS JTRS TTNT baseline, requiring redesign of the MIDS JTRS TTNT Transceiver (XCVR), MIDS JTRS TTNT External Power Amplifier (TEPA) and High Power Amplifier (HPA).
A successful L-Band MIDS JTRS TTNT XCVR risk reduction demonstration and early waveform porting was completed, which saved approximately five months of design and integration on the MIDS JTRS TTNT development effort. L-Band development continues and the award for the L&S-Bands MIDS JTRS TTNT design and development is anticipated in late FY 2016.
MIDS completed a review of PM Joint Tactical Network (JTN) processes for management of Software Defined Radio (SDR) waveforms in preparation for the transition of Link 16 waveform responsibilities to PMA/Program Management Warfare (PMW)-101. On June 4, 2015, all responsibilities of Link 16 waveform were transferred to PMA/PMW-101. Subsequently, PMA/PMW-101 participated in a Link 16 Evolution Kickoff Summit in Washington, DC on July 14, 2015. The meeting was chaired by Under Secretary of Defense for Acquisition, Acquisition, Technology, and Logistics (USD(AT&L)) Command, Control, and Communications (C3), Cyber and Business Systems (C3CB) and focused on ensuring DoD is evolving/modernizing Link 16 to increase future capabilities, and is fostering communication across DoD stakeholders.
MIDS-LVT Lot 16 delivery orders were awarded to DLS and ViaSat on August 31, 2015, 113 terminals and 8 receivers/transmitters units for $21M. MIDS JTRS Lot 4 production was awarded to DLS and ViaSat on September 18, 2015, 209 terminals for $70.8M.
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation:
April 1990: Joint Requirements Oversight Council Memorandum (JROCM 031-90) approved the Mission Need Statement (MNS) for MIDS-LVT.
December 1993: At MS II, USD(AT&L) authorized MIDS to proceed with MIDS-LVT EMD.
September 2001: USD(AT&L) directed the MIDS Program to update the Acquisition Strategy to include a JTRS Compliance Migration Strategy.
September 2003: At MS III, ASN(RDA) authorized Full Rate Production for MIDS-LVT.
July 2004: ASN(RDA) approved the Acquisition Strategy to develop MIDS JTRS via an Engineering Change Proposal.
February 2005: USD(AT&L) authorized the establishment of the Joint Program Executive Office (JPEO) Joint Tactical Radio System (JTRS) for authority over all JTRS products, including MIDS.
May 2008: JROCM 112-08 approved MIDS JTRS Capability Production Document.
December 2009: MIDS JTRS completed Contractor First Article Qualification Test and Government First Article Qualification Test (GFAQT). USD(AT&L) approved the Limited Production & Fielding of MIDS JTRS.
April 2011: MIDS JTRS completed Initial Operational Test & Evaluation including Verification of the Correction of Deficiencies(VCD), COMOPTEVFOR (Naval Command Operational Test and Evaluation Force) and Director of Operational Test & Evaluation Reports.

## Table 9
April 2012: USD(AT&L) approved the Full Production and Fielding of MIDS JTRS.
July 2012: USD(AT&L) directed the JPEO JTRS reorganization and realignment to transfer MIDS to Navy MDA alignment and designated MIDS as an ACAT IC program.
November 2012: ASN(RDA) approved MIDS JTRS IOC.
January 2013: ASN(RDA) designated MIDS as the Program Manager Air/Program Manager Warfare-101.
January 2013: ASN(RDA) authorized development of MIDS JTRS TTNT and MIDS JTRS CMN-4 capabilities to be managed as ECPs to the MIDS ACAT IC Program.
January 2013: PEO(Tactical Aircraft) assigned MIDS as the Naval Integrated Fire Control – Counter Air From the Air Advanced Tactical Data Link (ATDL) lead to coordinate with F/A-18, E-2D, EA-18G and other platform offices.
May 2013: Procurement, and Operating and Sustainment (O&S) breaches were realized due to increased procurement quantities of MIDS terminals by F/A-18. Program Deviation Report was submitted by the MIDS PM and approved by ASN (RD&A).
July 2013: MIDS JTRS CMN-4 Cooperative Development delivery orders were awarded to ViaSat and DLS.
November 2013: Due to the May Program Deviation Report, a revised Acquisition Program Baseline (APB) was approved by ASN(RD&A).
November 2013: MIDS-LVT Block Upgrade 2 (BU2) Award. MIDS-LVT BU2 development contracts were awarded to DLS, EuroMIDS and ViaSat. MIDS-LVT BU2 is a 39-month ECP to bring National Security Agency mandated Crypto Modernization and National Telecommunications and Information Agency and Federal Aviation Administration mandated Frequency Remapping capabilities to the MIDS-LVT Link-16 product line.
August 2014: MIDS JTRS TTNT L-Band Full Development Contract was awarded to DLS and ViaSat.
November 2014: MIDS JTRS TTNT waveform development was completed. The next step is early porting and demonstration of the waveform.
March 2015: Conducted the first MIDS JTRS CMN-4 flight on F/A-18 aircraft at China Lake.
May-June 2015: MIDS Modernization Increment 1 (MMI 1) demonstration testing was conducted, and development delivery orders were awarded to DLS and ViaSat.
June 2015: Responsibilities for the Link-16 waveform were transferred to MIDS program office from Joint Tactical Networking Center (JTNC).
August-September 2015: MIDS-LVT Lot 16 and MIDS JTRS Lot 4 production delivery orders were awarded to DLS and ViaSat.

## Table 10
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
The Procurement and O&S breaches occurred when the U.S. Air Force received the Resource Management Decision (RMD) funding for 1497 Concurrent Multi-Netting (CMN-4) and Tactical Targeting Network Technology (TTNT) MIDS Joint Tactical Radio System (JTRS) terminals in addition to the Navy 385 terminals. Additionally the services purchased 267 Low Volume Terminals (LVT). The PAUC and APUC overall continue below thresholds.
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
A Program Deviation Report (PDR) was signed by the MIDS PM on February 16, 2016. The PDR was submitted to PEO(T) for review and forwarding to the Assistant Secretary of the Navy for Research, Development, and Acquisition (ASN RD&A). A revised APB is in process.
Nunn-McCurdy Breaches

## Table 11
Schedule

## Table 12
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone II (DAB) | Dec 1993 | Dec 1993 | Jun 1994 | Dec 1993
Development Contract Award
LVT Contract Award | Mar 1994 | Mar 1994 | Sep 1994 | Mar 1994
LVT(2) Modifcation | Aug 1995 | Aug 1995 | Feb 1996 | Aug 1995
LVT(3) Qual Contract Award | Sep 1996 | Sep 1996 | Mar 1997 | Sep 1996
Critical Design Review (MIDS Terminal) | N/A
LVT | Nov 1995 | Nov 1995 | May 1996 | Nov 1995
LVT(2) | Feb 1997 | Feb 1997 | Aug 1997 | Feb 1997
First EMD Terminal Delivery
LVT | Dec 1997 | Dec 1997 | Jun 1998 | Dec 1997
LVT(3) | Feb 1998 | Feb 1998 | Aug 1998 | Feb 1998
LVT(2) | May 1998 | May 1998 | Nov 1998 | May 1998
Initial Carrier Suitability | Nov 1998 | Nov 1998 | May 1999 | Nov 1998
IOT&E Complete
LVT(3) | Jul 1999 | Jul 1999 | Jan 2000 | Jul 1999
LVT(2) | Feb 2002 | Feb 2002 | Aug 2002 | Feb 2002
LVT | Jan 2003 | Jan 2003 | Jul 2003 | Jan 2003
Milestone III
LVT (3) | Dec 1999 | Dec 1999 | Jun 2000 | Dec 1999
LVT (Air Force) | Sep 2003 | Sep 2003 | Mar 2004 | Sep 2003
LVT (Navy) | Apr 2004 | Apr 2004 | Oct 2004 | Apr 2004
Program Review DAB for LRIP | Feb 2000 | Feb 2000 | Aug 2000 | Feb 2000
LRIP Production Contract Award | Mar 2000 | Mar 2000 | Sep 2000 | Mar 2000
IOC
LVT(3) | Jan 2001 | Jan 2001 | Jul 2001 | Jan 2001
LVT(2) | Jun 2002 | Jun 2002 | Dec 2002 | Jun 2002
LVT | May 2003 | May 2003 | Nov 2003 | May 2003
Full Rate Production - LVT(2) | May 2003 | May 2003 | Nov 2003 | May 2003
FOT&E
LVT (F/A-18) Start | Mar 2004 | Mar 2004 | Sep 2004 | Mar 2004
LVT (F/A-18) Complete | Nov 2005 | Nov 2005 | May 2006 | Nov 2005
FOC
LVT(3) | Mar 2004 | Mar 2004 | Sep 2004 | Mar 2004
LVT (F/A-18) | Mar 2012 | Mar 2012 | Sep 2012 | Mar 2012

## Table 13
MSD
LVT (F/A-18) | Jun 2005 | Jun 2005 | Dec 2005 | Jun 2005
MIDS JTRS (Core Terminal)
LP&F | N/A | Dec 2009 | Jun 2010 | Dec 2009
FP&F | N/A | Mar 2012 | Sep 2012 | Mar 2012
IOC | N/A | May 2012 | Nov 2012 | May 2012
Change Explanations
None
Notes
An OSD decision was made in December 2009 that MIDS Joint Tactical Radio System (MIDS JTRS) (Core TerminaI) did not require a Milestone (MS) C decision since the MIDS Program had a MS C decision in September 2003.
Acronyms and Abbreviations
FOT&E - Follow-On Test and Evaluation FP&F - Full Production and Fielding
IOT&E - Initial Operational Test and Evaluation JTRS - Joint Tactical Radio System
LP&F - Limited Production and Fielding LVT - Low Volume Terminal
MSD - Material Support Date Qual - Qualification

## Table 14
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Interoperability
All top level IERs in SMORD | All top level IERs in SMORD | All critical top level IERs in SMORD | 100% Demonstrat- ed | All top level IERs in SMORD
Waveform Compatibility
STANAG 4175 & JTIDS SSS | STANAG 4175 & JTIDS SSS | STANAG 4175 & JTIDS SSS | JITC Certified | STANAG 4175 & JTIDS SSS
Message Standard
STANAG 5516 (& 5616 for Data Fwds) & MIL-STD- 6016B | STANAG 5516 (& 5616 for Data Fwds) & MIL-STD- 6016B | STANAG 5516 (& 5616 for Data Fwds) & MIL-STD-6016B | JITC Certified | STANAG 5516 (& 5616 for Data Fwds) & MIL- STD-6016B
Maximum Power Transmission (w)
LVT
Multiple selectable levels | Multiple selectable levels | >=200 with IF for 1000 | 200 with IF | Multiple selectable levels
LVT(2)
Multiple selectable levels | Multiple selectable levels | >=200 or 25 selectable | 200/25 | Multiple selectable levels
LVT(3)
Multiple selectable levels | Multiple selectable levels | >=50 | 50 | Multiple selectable levels
IER (Kbps)
1000 | >=1000 | 28.8 -115.2 | 1100 kbps | >=1000
Paired Time Slot Relay Capability
Integral and automated | Integral and automated | Integral and automated | Integral and automated | Integral and automated
Repromulgation Relay (nm) MIDS-LVT(2)
4 hop | 4 hops | 3 hops | 4 hops | 4 hops
Paired Time Slot Relay Range (nm) (USN Only)

## Table 15
1200 | >=1200 | >=500 | 520 | >=1200
Communication Range
LVT (USN: C2 to C2)
300 | >=300 | >=300 | 350 | >=300
LVT (USN: Non-C2 to C2)
240 | >=240 | >=220 | 240 | >=240
LVT (USN: Non-C2 to Non-C2)
200 | >=200 | >=180 | 220 | >=200
LVT (USN: Surface Platforms)
LOS up to 300 | LOS >=300 | LOS >=300 | 300 | LOS >=300
LVT (F-16: Non-C2 to C2)
300 | >=300 | >=200 | 200 | >=300
LVT (F-16: Non-C2 to Non-C2)
150 | >=150 | >=100 | 150 | >=150
LVT(2)
Up to 300 with LOS at 200 w | Up to 300 with LOS at 200 w | Up to 300 with LOS at 200 w | 300 | Up to 300 with LOS at 200 w
LVT(3) (Non-C2 to C2)
300 | >=300 | >=200 | 300 | >=300
LVT(3) (Non-C2 to Non-C2)
150 | >=150 | >=100 | 170 | >=150
Voice Channels: LVT (USN)
Capable of 2 | Capable of 2 | 1 | 2 | Capable of 2
Coded Message Error Probability (%)
LVT
1 | <=1 | <=2 | Passed | <=1
LVT(3)
< 1 detected | <= 1 detected | <=2 | Passed | <= 1 detected
LVT(2)
1 | <=1 | <=2 | Passed | <=1
Jam Resistance
LVT (USN) (db)
MJCS-194 - 89 | MJCS-194-89 | MJCS-194-89 | Compliant | MJCS-194-89
LVT (F-16) (%)
< 1 detected error | <=1 detected error | <= 1 detected error | Passed | <=1 detected error

## Table 16
LVT(2) (%)
< 1 detected error | <= 1 detected error | <= 5 | Passed | <= 1 detected error
LVT(3) (%)
< 1 detected error | <= 1 detected error | <= 1 detected error | Passed | <= 1 detected error
Ao
LVT
0.9 | >=.90 | >=.90 | 0.91 | >=.90
LVT(2) (Terminal)
0.94 | >=.94 | >=.90 | 0.94 | >=.94
LVT(3)
0.97 | >=.97 | >=.95 | 0.965 | >=.97
MTBF (hr)(lab)
USN
1000 | >=1000 | >=1000 | 1850 | >=1000
USA
1800 | >=1800 | >=1000 | 1850 | >=1800
USAF
1500 | >=1500 | >=1000 | 1850 | >=1500
MFHBOMF/MTBOMF (hr)
System
25 | >=25 | >=25 | 32 | >=25
LVT (Aircraft) (Terminal)
300 | >=300 | >=220 | 240 | >=300
LVT (Ships) (Terminal)
350 | >=350 | >=257 | 275 | >=350
LVT(2) (Terminal)
393 | >=393 | >=393 | 425 | >=393
MTTR (O-level) (min)
LVT(2) (Terminal)
30 | <=30 | <=30 | 25 | <=30
MCMTOMF
LVT (USN Aircraft)
60 | <=60 | <=90 | 75 | <=60
LVT (USN Ships)
60 | <=60 | <=90 | 80 | <=60
LVT (USAF)

## Table 17
MRT < 20 | MRT < 20 | MRT < 30 | 25 | MRT < 20
LVT(3)
MRT < 20 | MRT < 20 | MRT < 30 | 28 | MRT < 20
Volume (Cubic Feet)
LVT
< .6 | <= .6 | <= .6 | 0.58 | <= .6
LVT(2)
< 1.4 | <=1.4 | <=1.4 | 1.32 | <=1.4
LVT(3)
< .6 | <= .6 | <= .6 | 0.56 | <= .6
Weight (lbs)
LVT
< 65 | <=65 | <=65 | 63.8 | <=65
LVT(2)
< 88 | <=88 | <=88 | 87.9 | <=88
LVT(3)
< 65 | <=65 | <=65 | 63.8 | <=65
MIDS-LVT Enhancement ECPs
Message Standards
N/A | STANAG 5516 (& 5616 for Data Fwds) & MIL-STD- 6016C | STANAG 5516 (& 5516 for Data Fwds) & MIL-STD-6016B | To Be Determined (TBD) until Block Upgrade 2 (BU2) Enhanced Throughput (ET) is implemented | STANAG 5516 (& 5616 for Data Fwds) & MIL- STD-6016C
Communications Range
N/A | see note 12c through 17c | see note 12c through 17c | TBD until MIDS- LVT BU2 ET is implemented | TBD until MIDS- LVT BU2 is implemented
Information Exchange Rate (Kbps)
LET 0
N/A | >=358 | >=107 | TBD until MIDS- LVT BU2 ET is implemented | >=358
LET 1
N/A | >=546 | >=358 | TBD until MIDS- LVT BU2 ET is implemented | >=546
LET 2
N/A | >=833 | >=546 | TBD until MIDS- LVT BU2 ET is | >=833

## Table 18
implemented
LET 3
N/A | >=968 | >=833 | TBD until MIDS- LVT BU2 ET is implemented | >=968
LET 4
N/A | >=1100 | >=968 | TBD until MIDS- LVT BU2 ET is implemented | >=1100
Coded Message Error Probability (%)
LET 0
N/A | <=1% | <=2% | TBD until MIDS- LVT BU2 ET is implemented | <=1%
LET 1
N/A | <=1% | <=2% | TBD until MIDS- LVT BU2 ET is implemented | <=1%
LET 2
N/A | <=1% | <=2% | TBD until MIDS- LVT BU2 ET is implemented | <=1%
LET 3
N/A | <=1% | <=2% | TBD until MIDS- LVT BU2 ET is implemented | <=1%
LET 4
N/A | <=1% | <=2% | TBD until MIDS- LVT BU2 ET is implemented | <=1%
Jam Resistance
N/A | MJCS-194-89 | MJCS-194-89 | TBD until MIDS- LVT BU2 ET is implemented | MJCS-194-89
MIDS JTRS Performance Parameters
Link-16 Waveform compatibility
N/A | STANAG 4175 and MIDS LVT SSS | STANAG 4175 and MIDS LVT SSS | Passed JITC waveform conformance test. | Passed JITC waveform conformance test.
Link-16 Message Standard
N/A | MIL-STD-6016C and STANAG 5516 | MIL-STD-6016C and STANAG 5516 | Passed JITC waveform conformance test. | Passed JITC waveform conformance

## Table 19
test.
Link-16 IER
Normal Operations with JTRS
N/A | >=1100 Kbps | >=28-115.2 Kbps | 128 | 128
LET 0
N/A | >=358 | >=107 | 107 | 107
LET 1
N/A | >=546 | >=358 | 358 | 358
LET 2
N/A | >=833 | >=546 | 546 | 546
LET 3
N/A | >=968 | >=833 | 837 | 837
LET 4
N/A | >=1100 | >=968 | 968 | 968
Interoperability: All top level IERs will be satisfied to the standards specified in the threshold (T) and objective (O) values.
N/A | All top-level Information exchange Requirements (IERs) are met. | All top-level Information Exchange Requirements (IERs) are met. | All top-level IERs transferred. | All top-level IERs transferred.
Link-16 Coded Message Error Probability (CMEP)
LET 0
N/A | <=1% | <=2% | <=2% | <=1%
LET 1
N/A | <=1% | <=2% | <=2% | <=1%
LET 2
N/A | <=1% | <=2% | <=2% | <=1%
LET 3
N/A | <=1% | <=2% | <=2% | <=1%
LET 4
N/A | <=1% | <=2% | <=2% | <=1%
Weight/Volume
N/A | <=65 lbs, <=.6 cu.ft. | <=65 lbs, <=.6 cu.ft. | Measured 54.7 lbs; measured .573 cu. ft. | <=65 lbs, <=.6 cu.ft.
Link-16 Jam Resistance
JTRS (USN) (db)
N/A | MJCS-194-89 | MJCS-194-89 | Exceeds threshold by 1-3 db in 95% of all cases. | Exceeds threshold by 1-3 db in 95% of all cases.

## Table 20
All Others
N/A | <=1% Detected message error rate | <=1% Detected message error rate | 0.98% | 0.98%
Link-16 J-Voice Channels
N/A | 2 | 2 | 2 | 2
Link-16 Communications Range Data
N/A | ≥300 nm (C2-C2 w/HPA); ≥240 nm (C2-non-C2); ≥200 nm (non-C2-non- C2) | ≥300 nm (C2-C2 w/HPA); ≥220 nm (C2-non-C2); ≥180 nm (non- C2-non-C2) | >=250 nm | >=250 nm.
Link-16 Communications Range J-Voice
N/A | >=220nm (C2-C2 w/HPA); >=140nm (C2-non-C2); >=90nm (non-C2- nonC2/non C2-C2) | >=220nm (C2-C2 w/HPA); >=140nm (C2-non-C2); >=90nm (non-C2-nonC2/non C2-C2) | >=220nm (C2-C2 w/HPA) - Not Tested; >=140nm (C2-non-C2 - Not tested; >=90nm (non-C2- nonC2/non C2-C2) - 150. | >=220nm (C2- C2 w/HPA) - Terminal not installed in C2 platform yet; >=140nm (C2- non-C2 - Terminal not installed in C2 platform yet; >=90nm (non-C2 -nonC2/non C2- C2) - 150.
Link-16 Relay
N/A | >=1200nm | >=500nm | Not tested yet. | >=500 nm
Multi-Channels/Networks
N/A | 4 Channels simultaneously with TACAN/multi-net (single network) Link-16 fixed operation on Channel 1 | 4 Channels simultaneously with TACAN/multi-net (single network) Link-16 fixed operation on Channel 1 | 4 Channels passed. | 4 Channels passed.
Scan Frequencies
N/A | Scan a minimum of 10 frequencies or presets | Scan a minimum of 10 frequencies or presets | FOT&E: No MIDS JTRS waveforms require presets. | FOT&E: No MIDS JTRS waveforms require presets.
Terminal Start-up/Restart (Link-16 only)
N/A | <=2.0 min | <=3.5 minutes | 3.2 min | 3.2 min
IBIT Performance (Link-16 only)
N/A | <=30seconds | <=70 seconds | 29 seconds | 29 seconds
Link-16 Net Entry/Synchronization
N/A | <=30 seconds | Not to exceed 4 min from time that coarse sync is initiated | 30 sec - 2.5 min | 30 sec - 2.5 min
Crypto-Rekeying
N/A | Over the Air Rekeying | At O-level | Not implemented in | Not implemented

## Table 21
| (OTAR) through electronic media, or common reprogramming hardware / software |  | Core Terminal. | in Core Terminal.
Link-16 Transmission of Unit Position and Status Reports
N/A | <=100 ft accuracy | <=300 ft accuracy | 78 ft | 78 ft
TACAN Performance Start-up/Restart
N/A | <=14 seconds | <=30 seconds | 15 seconds | 15 seconds
MFHBOMF (System/Single Channel)
N/A | >=36 hrs (Other Platforms) | >=25 hrs (F/A-18E/F, EA-18G, TACAIR) | 36.5 hrs. | 36.5 hrs
MTBF Lab (Ch. 1(Link-16))
N/A | >=1800 hrs | >= 1200 hrs | 1285 hrs | 1285 hrs
MTBF Lab (Ch. 2, 3 & 4)
N/A | >=1800 hrs | >=1550 hrs | 1550 hrs | 1550 hrs
MFHBOMF (Terminal/Single Channel))
N/A | >=300 hrs | >=220 hrs | 724 (includes lab data) | 220 hrs
MCMTOMF (Single Channel)
N/A | <= 60 min | <=120 min; <= 90 min (F/A-18 E/F, EA-18G, NAVAIR) | 60 min | 60 min (Single channel)
MRT
N/A | <= 20 min | <= 45 min | 20 min | 45 min
BIT PCD
N/A | PCD>= 98% | PCD>= 95% | 97% | 97%
BIT MFHBFA
N/A | MFHBFA: >= 451 hrs | MFHBFA: >= 113 hrs | 80 hrs | 120 hrs
Start-Up (Terminal/Single Channel)
N/A | <=2min (OE, crypto and waveform); <=2min (fine sync) | <=3.5min (OE, Crypto and waveform); <=4min (fine sync) | 3.2 min | 3.2 min
Start-Up (Waveform/Link-16 only)
N/A | <=2min (OE, crypto, and waveform); <=2min (fine sync) | <=3.5min (OE, crypto, and waveform); <=4min (fine sync) | .5 - 2.5 min | .5 - 2.5 min
Restart < 50 milliseconds (Core configuration only)
N/A | Operates through | Operates through | Operates through | Operates through
Restart <10 seconds (Terminal)
N/A | <=2min | <=3.5min | 2.5 min | 2.5 min
Restart <10 seconds (Link-16 waveform)

## Table 22
N/A | <=10sec | <=10sec | 9 sec | 9 sec
Restart >=10 seconds and <2min (Terminal)
N/A | <=2min | <=3.5min | 3.2 min | 3.2 min
Restart >=10 seconds and <2min (Link-16)
N/A | <=2min | <=4min | 3.2 min | 3.2 min
Restart >= 2 min (Terminal)
N/A | <=2min | <=3.5min | 3.2 min | 3.2 min
Restart >=2 min (Link-16 Waveform)
N/A | <=2min | <=4min | 3.2 min | 3.2 min
TACAN Start-up/Restart
N/A | <=14sec | <=30sec | 15 sec | 15 sec
IBIT Performance
N/A | <=30sec | <=70sec | 30 sec | 30 sec
Terminal Operating Frequency Range
N/A | Operate 2-2000 MHz | Operate 2-2000 MHz | Operation within 2- 2000 MHz | Operate 2-2000 MHz
MIDS JTRS Capability
N/A | F3I for MIDS-LVT (1) and shall meet the performance measures in MIDS JTRS Core Terminal in Table 6 of the CPD in addition to TACAN and J- Voice. | F3I for MIDS-LVT (1) and shall meet the performance measures in MIDS JTRS Core Terminal in Table 6 of the CPD in addition to TACAN and J-Voice. | 11 of 11 Performance measures have been achieved in a Developmental Test period. | 11 of 11 Performance measures have been achieved in a Developmental Test period.
Functionality
N/A | MIDS JTRS Core Terminal will meet connectivity requirements of ALL Airborne (MIDS JTRS) Domain Waveforms. | The MIDS JTRS Core Terminal shall be capable of supporting secure and non-secure voice, video, and data communications by porting narrowband and wideband JTRS developed waveforms in compliance with the Software Communications Architecture. Where a MIDS JTRS Core Terminal replaces the WF/radio function(s) of one or more legacy radios and continued interoperability with legacy radios is required, software WFs will be ported and JTRS radio shall perform the same WF/radio function(s) and mission(s) supported by the legacy radios. JTRS Core Terminal will meet connectivity requirements of ported Waveforms. | 15 of 15 Performance measures have been achieved. | 15 of 15 Performance measures have been achieved.

## Table 23
Number of Channels
N/A | Threshold same as Objective (One TACAN/Link-16 plus three additional channels for JTRS Waveforms). | One TACAN/Link-16 plus three additional channels for JTRS Waveforms. Navy Initial Implementation - TACAN/Link-16 plus 3 additional channels ((2MHz - 2 GHz transceivers) as capability for future JTRS WFs) for F/A-18E/F. USAF Initial Implementation - Link-16 for B-1. | 1 of 1 Performance measures have been achieved. | 1 of 1 Performance measures have been achieved.
Net Ready
N/A | The system must fully support execution of joint critical operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for transition to Net- Centric military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration (Table 31), 3) NCOW RM Enterprise Services 4) IA requirements including availability, integrity, authentication, confidentiality, and non- repudiation, and issuance of an IATO by the DAA, and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture reviews. | The MIDS JTRS Core Terminal will support Net-Centric military operations via a gateway. The system must be able to enter and be managed in the network, and exchange data in a secure manner to enhance mission effectiveness. The systems must have the ability to provide survivable, interoperable, secure and operationally effective information exchanges to enable a Net-centric military capability. The system must fully support execution of all operational activities identified in the applicable joint and system integrated architectures and the system must satisfy the technical requirements for Net-Centric military operations to include 1) DISR mandated GIG IT standards and profiles identified in the TV-1, 2) DISR mandated GIG KIPs identified in the KIP declaration (Table 31), 3) NCOW RM Enterprise Services 4) IA requirements including availability, integrity, authentication, confidentiality, and non- repudiation, and issuance of an ATO by the DAA, and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture reviews. | 5 of 5 Performance measures have been achieved. System certified by NSA in March 2010 | 5 of 5 Performance measures have been achieved. System certified by NSA in March 2010.

## Table 24
Operational Availability (Ao)
N/A | Each MIDS JTRS Core Terminal shall demonstrate an Ao of >0.99 for all channels. | Each MIDS JTRS Core Terminal shall demonstrate an Ao of >0.90 for Link-16 / TACAN Channel and >0.96 for the remaining channels. | 96.8%. | 96.8%
Software Configurable
N/A | Each MIDS JTRS Core Terminal shall provide any designated operator with the ability to load and reconfigure its modes/ capabilities via software while in the operational environment | Each MIDS JTRS Core Terminal shall provide any designated operator with the ability to load and reconfigure its modes/ capabilities via software while in the operational environment | 1 of 1 Performance measures have been achieved. | 1 of 1 Performance measures have been achieved.
Growth
N/A | MIDS JTRS Core Terminal shall provide an internal growth capability through an open systems architecture approach, and shall be modular, scaleable and flexible as designed to suit specific operational requirements. | MIDS JTRS Core Terminal shall provide an internal growth capability through an open systems architecture approach, and shall be modular, scaleable and flexible as designed to suit specific operational requirements. | 2 of 2 Performance measures achieved. | 2 of 2 Performance measures achieved.
Navigation – Link-16 Position (PPLI)
N/A | ≤100 feet | ≤300 feet | Operation at ≤100 feet | ≤100 feet
Tactical Air Navigation (TACAN)
N/A | Capabilities equivalent to LVT | Capabilities equivalent to LVT | Capabilities equivalent to LVT | Capabilities equivalent to LVT
Spectrum Certification
N/A | Meets DD-1494 Stage 4 | Meets DD-1494 Stage 4 | DD-1494 Stage 4 issued. | Meets DD-1494 Stage 4
Memory/Processor Reserve
N/A | Provide growth memory and processor reserve to allow for an increased capability or functionality of each set and with each generation of radios | Provide growth memory and processor reserve to allow for an increased capability or functionality of each set and with each generation of radios | Met with no issues. | Provide growth memory and processor reserve to allow for an increased capability or functionality of each set and with each generation of radios
Operational Communications
Passive Syncronization

## Table 25
N/A | Fine Sync achieved passively | Fine Sync achieved passively | Achieved Fine Sync passively | Fine Sync achieved passively
Automatic Message Acknowledgement
N/A | IAW Mil-STD 6016C | IAW Mil-STD 6016C | Automatic Message Acknowledgement IAW Mil-STD 6016C | IAW Mil-STD 6016C
Crypto Control (CTP-11)
N/A | Proper O-level control of NSA approved crypto device | Proper O-level control of NSA approved crypto device | Proper O-level control of NSA approved crypto device | Proper O-level control of NSA approved crypto device
Multi-Net (CTP-10)/8d
N/A | 2 simultaneous nets | 2 simultaneous nets | Performance of two simultaneous nets | 2 simultaneous nets
GIG Requirements
N/A | DISR mandated GIG requirements specified in TV-1 of ISP | DISR mandated GIG requirements specified in TV-1 of ISP | Met DISR mandated GIG requirements specified in TV-1 of ISP | DISR mandated GIG requirements specified in TV-1 of ISP
Key Information Profile (KIP)
N/A | DISA mandated GIG KIPs are identified in ISP in the KIP Declaration Table | DISA mandated GIG KIPs are identified in ISP in the KIP Declaration Table | The DISA mandated GIG KIPs are identified in the ISP in the KIP Declaration Table | DISA mandated GIG KIPs are identified in ISP in the KIP Declaration Table
Design per NCOW RM
N/A | NCOW RM Enterprise Services are met | NCOW RM Enterprise Services are met | The NCOW RM Enterprise Services are met | NCOW RM Enterprise Services are met
Information Exchange Requirements met
N/A | Operationally Effective exchanges of all messages IAW ISP | Operationally Effective exchanges of all messages IAW ISP | Showed Operationally Effective exchange of all messages IAW ISP | Operationally Effective exchanges of all messages IAW ISP
Enable CMN/CCR Reception
N/A | Receive on 4 net numbers (CMN); 4 receptions within a timeslot (CCR) | Receive on 4 net numbers (CMN); 4 receptions within a timeslot (CCR) | TBD | Receive 4 net numbers (CMN); 4 receptions within a timeslot (CCR)

## Table 26
Requirements Reference
MIDS Operational Requirements Document (ORD) (MIDS-LVT) dated July 25, 2004 and MIDS JTRS Capability Production Document (CPD) dated July 16, 2013
Change Explanations
None
Notes
1. For LET 0 there is a 5 db loss in jam resistance and 44% loss in range over PAC4 Single Pulse. The 1% error rate will be calculated based on the decrease in jamming resistance.
2. For LET 1 there is a 7 db loss in jam resistance and 56% loss in range over PAC4 Single Pulse. The 1% error rate will be calculated based on the decrease in jamming resistance.
3. For LET 2 there is a 9 db loss in jam resistance and 65% loss in range over PAC4 Single Pulse. The 1% error rate will be calculated based on the decrease in jamming resistance.
4. For LET 3 there is a 10 db loss in jam resistance and 67% loss in range over PAC4 Single Pulse. The 1% error rate will be calculated based on the decrease in jamming resistance.
5. For LET 4 there is an 11 db loss in jam resistance and 72% loss in range over PAC4 Single Pulse. The 1% error rate will be calculated based on the decrease in jamming resistance.
6. For Frequency Remap, there will be a db loss for the number of frequencies remapped based on the formula 10 log (51/51-NR) where NR = the number of frequencies remapped. There is a corresponding decrease in range of approximately 1% for each frequency that is remapped.

## Table 27
Acronyms and Abbreviations
Ao - Operational Availability ATO - Authority to Operate BIT - Built in Test
BU2 - Block Upgrade 2
C2 - Command and Control
CFAQT - Contractor First Article Qualification Testing CMEP - Coded Message Error Probability
CMN/CCR - Concurrent Multi-Netting/Concurrent Contention Receive cu. ft. - cubic feet
DAA - Designated Approving Authority db - decibel(s)
DISR - Defense Information Standards Registry ECP - Engineering Change Proposal
ET - Enhanced Throughput
F3I - Form, Fit, Function and interface FDL - Fighter Data Link
FOT&E - Follow-on Test and Evaluation
GFAQT - Government First Article Qualification Testing GIG IT - Global Information Grid Information Technology HPA - High Power Amplifier
hr - hour(s)
IATO - Interim Authority to Operate IBIT - Initialization Built in Test
IER - Information Exchange Requirements IF - Interface
JITC - Joint Interoperability Test Command
JTIDS - Joint Tactical Information Distribution System kbps - kilobits per second
KIPs - Key Interface Profiles lbs - Pounds
LET - Link 16 Enhanced Throughput LOS - Line of sight
LVT - Low Volume Terminal
MCMTOMF - Mean Corrective Maintenance Time for Operational Mission Failures MFHBFA - Mean Flight Hours Between False Alarms
MFHBOMF - Mean Flight Hours Between Operational Mission Failures MHz - Megahertz
MIDS - Multifunctional Information Distribution System Mil-Std - Military Standard
min - minute(s)
MJCS - Memorandum Joint Chiefs of Staff MRT - Mean Repair Time
MTBF - Mean Time Between Failure
MTBOMF - Mean Time Between Operational Mission Failures MTTR - Mean Time to Repair
NCOW RM - Net-Centric Operations and Warfare Reference Model nm, nmi - Nautical mile
NSA - National Security Agency OE - Operational Environment O-Level - Organization Level OTAR - Over the Air Re-keying PAC4 - Packed-4

## Table 28
PCD - Percent Correct Detect sec - second(s)
SINCGARS - Single Channel Ground and Airborne Radio System SMORD - Single MIDS ORD
SSS - System Segment Specification STANAG - Standardization Agreement TACAN - Tactical Air Navigation
TV - Technical View w - watt(s)

## Table 29
Track to Budget
General Notes
The current RDT&E increased to fully fund MIDS Joint Tactical Radio System (JTRS) Tactical targeting Network technology (TTNT) development.
The current production terminal procurement estimate increased by a total of 2,149 terminals due to the large procurement order from the U.S. Air Force (Platforms: F-15, F-16, F-22).
RDT&E
Appn |  | BA | PE
Navy 1319 05 0205604N
Project | Name
2126 Tactical Data Links (Shared) (Sunk)
Notes: ATDLS Integration
Navy 1319 07 0205604N
Project | Name
2126 Tactical Data Links (Shared)
Notes: ATDLS Integration
3020 Tactical Data Links (Shared)
Notes: MIDS/JTRS
Navy 1319 05 0604234N
Project | Name
3051 Advanced Hawkeye (Shared)
Navy 1319 05 0604270N
Project | Name
E0556 Navy EA-6B Integration/EA-6B (Shared) (Sunk) E2781 Navy EA-6B Integration/EA-6B (Shared) (Sunk)
Navy 1319 05 0604280N
Project | Name
3020 Joint Tactical Radio System (JTRS)
Notes: MIDS/JTRS
3073 Joint Tactical Radio System (JTRS)
Notes: AMF/JTRS
Army 2040 05 0603713A
(Shared) (Sunk)
(Shared) (Sunk)
Project | Name
D370 (Shared) (Sunk)
Notes: Army MIDS/Army MIDS
Army 2040 05 0604280A
Project | Name
162 Joint Tactical Radio System (Shared) (Sunk)

## Table 30
(JTRS)
Notes: Network Enterprise Domain (NED)
Air Force 3600 07 0101126F
| Project |  | Name
| 675344 |  | B-1B Squadrons | (Shared)
Air Force | 3600 | 7 | 0101127F
| Project |  | Name
| 675345 |  | B-2 Squadrons (Shared)
Air Force | 3600 | 5 | 0207130F
| Project |  | Name
| F15 |  | Air Force MIDS/F-15C/D | (Shared) | (Sunk)
Air Force | 3600 07 |  | 0207133F
| Project |  | Name
| 672671 |  | F-16 Squadrons (Shared)
Air Force | 3600 | 5 | 0207133F
| Project |  | Name
| 672671 |  | Air Force MIDS/F-16 | (Shared) | (Sunk)
Air Force | 3600 05 |  | 0207134F
| Project |  | Name
| 674703 |  | Air Force MIDS/F-15E | (Shared) | (Sunk)
Air Force | 3600 07 |  | 0207134F
| Project |  | Name
| 676020 |  | F-15 Squadrons | (Shared)
Air Force | 3600 07 |  | 0207138F
| Project |  | Name
| 674788 |  | F-22 Squadrons | (Shared)
Air Force | 3600 07 |  | 0207417F
| Project |  | Name
| 67411L |  | Airborne Warning and Control System (AWACS) | (Shared)
Air Force | 3600 07 |  | 0207448F
| Project |  | Name
| 675045 |  | C2ISR Tactical Data Link | (Shared)
Air Force | 3600 07 |  | 0208006F
| Project |  | Name
| 675380 |  | Mission Planning Systems | (Shared)
Air Force | 3600 07 |  | 0305207F
| Project |  | Name
| 674754 |  | Manned Reconnaissance Systems | (Shared)
Air Force | 3600 05 |  | 0604240F
| Project |  | Name
| 11B002 |  | Air Force MIDS | (Shared) | (Sunk)

## Table 31
Air Force 3600 05 0604280F
Project Name
655068 Joint Tactical Radio System
(JTRS)
Air Force 3600 05 0604281F
(Shared) (Sunk)
Project | Name
655050 Tactical Data Networks Enterprise
Defense-Wide 0400 05 0603883C
(Shared)
|  | Project |  | Name
|  | 10 |  | DOD | (Shared) | (Sunk)
Defense-Wide |  | 0400 05 |  | 0604771D
|  | Project |  | Name
|  | P771 |  | OSD, DA/JTRS | (Shared) | (Sunk)
|  | P773 |  | OSD, DA/Multifunctional Information Distribution System | (Shared) | (Sunk)
Procurement
Appn |  |  | BA | PE
Navy |  | 1506 01 |  | 0204136N
|  | Line Item |  | Name
|  | 145 |  | F-18 Series | (Shared) | (Sunk)
Navy |  | 1506 05 |  | 0204154N
|  | Line Item |  | Name
|  | 511 |  | EA-6 Series | (Shared)
Navy |  | 1506 | 5 | 0204136N
|  | Line Item |  | Name
|  | 525 |  | F-18 Series | (Shared)
Navy |  | 1506 | 5 | 0204152N
|  | Line Item |  | Name
0544 EW Development (Shared) (Sunk)
Notes: EA-6 Series
Sunk FY16
Navy 1611 02 0204112N
Line Item | Name
2001 Carrier Replacement Program (Shared)
2086 Multi-Purpose CVNs (Shared) (Sunk)
Navy 1611 02 0204222N
Line Item | Name
2122 DDG (Shared)
Navy 1611 02 0204230N
Line Item | Name
2127 Littoral Combat Ship (Shared)

## Table 32
Navy |  | 1611 | 3 | 0204411N
|  | Line | Item | Name
|  | 3035 |  | Amphibious Assault Ships | (Shared) (Sunk)
|  | 3036 |  | LPD-17 | (Shared)
Navy |  | 1611 | 5 | 0204411N
|  | Line | Item | Name
|  | 5110 |  | Outfitting | (Shared)
Navy |  | 1810 | 2 | 0205604N
|  | Line Item |  | Name
2614 Advanced Tactical Data Link System
Army 2035 02 0214400A
(Shared)
Line Item | Name
B22603 Radio Terminal Set, MIDS-LVT
-2
Air Force 3010 05 0604281F
(Shared)
Line Item | Name
655262 Tactical Data Networks Enterprise
Air Force 3010 05 0207446F
(Shared)
Line Item | Name
B00200 ABL (Shared)
Air Force 3010 07 0207132F
Line Item | Name
F01500 F-15 (Shared)
Air Force 3010 05 0207130F
Line Item | Name
F01500 F-15 (Shared) (Sunk)
Air Force 3010 05 0207133F
Line Item | Name
F01600 F-16 (Shared)
Air Force 3010 07 0207133F
Line Item | Name
F0160P F-16 (Shared) (Sunk)
Air Force 3010 05 0207423F
Line Item | Name
MN9860 Joint Tactical Radio System (Shared)
Air Force 3010 05 0207133F
Line Item | Name
OTHACF Other Aircraft (Shared)
Notes: Battlefield ABN Comm Node (BACN)
Air Force 3080 03 0207448F
Line Item | Name

## Table 33
831010 Comsec Equipment (Shared)
834010 General Information
Technology
Air Force 3080 03 0401840F
(Shared)
Line Item | Name
834070 AMC Command and Control
System
Air Force 3080 03 0201131F
(Shared)
Line Item | Name
835140 Air Combat Command
Communications
Notes: AFCENT
Air Force 3080 02 0207133F
(Shared)
Line Item | Name
F01600 F-16 (Shared) (Sunk)
Defense-Wide 0300 02
Line Item | Name
10 DOD (Shared) (Sunk)
Defense-Wide 0300 02 0208865C
Line Item | Name
2257 DA, Patriot (Shared) (Sunk)
Defense-Wide 0300 02 0208861C
Line Item | Name
2260 DA, THAAD (Shared) (Sunk)
Defense-Wide 0300 02
Line Item | Name
30 GAPO (Shared) (Sunk)

## Table 34
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 2003 $M |  |  |  | BY 2003 $M |  | TY $M
| SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Production Estimate |  | Current APB Production Objective |  | Current Estimate
RDT&E | 869.4 |  | 1637.5 | 1801.3 |  | 1738.8 |  | 825.8 |  | 1750.6 |  | 1877
Procurement | 955.4 |  | 1393.5 | 1532.9 |  | 2133.51 |  | 993.1 |  | 1585.6 |  | 2615.7
Flyaway | -- |  | -- | -- |  | 1946.3 |  | -- |  | -- |  | 2407.1
Recurring | -- |  | -- | -- |  | 1873.8 |  | -- |  | -- |  | 2335.7
Non Recurring | -- |  | -- | -- |  | 72.5 |  | -- |  | -- |  | 71.4
Support | -- |  | -- | -- |  | 187.2 |  | -- |  | -- |  | 208.6
Other Support | -- |  | -- | -- |  | 39.8 |  | -- |  | -- |  | 44.8
Initial Spares | -- |  | -- | -- |  | 147.4 |  | -- |  | -- |  | 163.8
MILCON | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 |  | 0 | -- |  | 0 |  | 0 |  | 0 |  | 0
Total | 1824.8 |  | 3031 | N/A |  | 3872.3 |  | 1818.9 |  | 3336.2 |  | 4492.7
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 47%
The MIDS cost model is built using Microsoft Excel 2010. Total Life Cycle Cost Estimate (LCCE) for MIDS is at the 47% confidence level on the generated Sigmoid (S)-Curve. The generated point estimate is based on the developed Cost Estimating Relationships (CERs) and inputted sunk costs rather than an estimate at a chosen confidence level. MIDS has incorporated the actual costs of our most recent development of MIDS Joint Tactical Radio System (MIDS JTRS) Phase 2B to build in more confidence and validate the confidence level.
Cost Notes
RDT&E costs include the MIDS Low Volume Terminal (MIDS-LVT) and MIDS Joint Tactical Radio System (MIDS JTRS) terminal development, terminal acquisition, integration and test on the United States Navy platforms for all current MIDS Program Managment Office enhancement efforts.
Procurement costs are for MIDS-LVT and MIDS JTRS terminals purchased by the platforms.
The costs of platform installation and platform kits, and United States Air Force and United States Army platform integration and testing of MIDS-LVT and MIDS JTRS are to be included in the respective budgets and baseline agreements of the various platforms implementing MIDS.
The current production terminal procurement estimate increased by a total of 2,149 terminals due to the procurement order from the U.S. Air Force (Platforms: F-15, F-16, F-22).

## Table 35
Total Quantity
Quantity | SAR Baseline Production Estimate | Current APB Production | Current Estimate
RDT&E | 143 | 488 | 604
Procurement | 2821 | 5745 | 8000
Total | 2964 | 6233 | 8604
Quantity Notes
The unit of measure is terminals.
Procurement quantities include MIDS terminals for United States Navy, United States Air Force, and United States Army platforms. The current estimate includes MIDS Joint Tactical Radio System (MIDS JTRS) procurement quantities for the Phase 2B Core terminals, Four Net Concurrent Multi-Netting with Concurrent Contention Receive (CMN-4), and Tactical Targeting Network Technology (TTNT).
Procurement budgets include funding to upgrade terminals, e.g. make a Core terminal CMN-4 capable, CMN-4 to TTNT, and MIDS-LVT to BU2. However, these terminals are not included in future quantity counts as they have already been accounted for when they were initially procured.
The current production terminal procurement estimate increased by a total of 2,149 terminals due to the procurement order from the U.S. Air Force (Platforms: F-15, F-16, F-22) and the U.S. Navy.

## Table 36
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 1670.4 | 73.7 |  |  | 57.4 | 21.1 | 17.8 |  | 18.1 |  | 18.5 |  |  | 0 |  | 1877
Procurement | 1403.8 | 100.9 |  |  | 155.2 | 223.4 | 252 |  | 195.3 |  | 115.1 |  |  | 170 |  | 2615.7
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0
PB 2017 Total | 3074.2 | 174.6 |  |  | 212.6 | 244.5 | 269.8 |  | 213.4 |  | 133.6 |  |  | 170 |  | 4492.7
PB 2016 Total | 2999.2 | 137.4 |  |  | 137.6 | 119.5 | 80.8 |  | 71.6 |  | 0 |  |  | 0 |  | 3546.1
Delta | 75 | 37.2 |  |  | 75 | 125 | 189 |  | 141.8 |  | 133.6 |  |  | 170 |  | 946.6
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 604 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 604
Production | 0 |  | 5063 |  | 320 | 438 | 688 |  | 744 |  | 432 | 133 |  | 182 |  | 8000
PB 2017 Total | 604 |  | 5063 |  | 320 | 438 | 688 |  | 744 |  | 432 | 133 |  | 182 |  | 8604
PB 2016 Total | 548 |  | 4941 |  | 203 | 176 | 232 |  | 157 |  | 142 | 0 |  | 0 |  | 6399
Delta | 56 |  | 122 |  | 117 | 262 | 456 |  | 587 |  | 290 | 133 |  | 182 |  | 2205

## Table 37
Cost and Funding
Annual Funding By Appropriation
Annual Funding 0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.5
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.9
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23.3
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.6
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.7
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.9
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.2
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.9
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
Subtotal |  | 70 | -- |  | -- |  | -- |  | -- |  | -- |  | 372.7

## Table 38
Annual Funding 0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.1
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.9
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.1
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.2
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.3
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.9
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.2
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.6
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 29
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 40
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.9
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
Subtotal |  | 70 | -- |  | -- |  | -- |  | -- |  | -- |  | 397.6

## Table 39
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.7
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.4
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.4
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 31
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.2
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 39.8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 45.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.3
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.7
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.2
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.8
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.4
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 27.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 98.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 162.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 77.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.6
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.2
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 120.7
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.5
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 70.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.1
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 17.8
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.1
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.5
Subtotal |  | 202 | -- |  | -- |  | -- |  | -- |  | -- |  | 1366

## Table 40
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.6
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.6
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.1
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.6
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.1
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 33.3
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 30
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.9
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.3
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63.9
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38.2
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 26.3
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 21.5
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 25.8
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.2
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 144
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 67.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.7
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 82
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 38
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 95.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63.1
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 54.1
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.5
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 15.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 12.9
2021 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13
Subtotal |  | 202 | -- |  | -- |  | -- |  | -- |  | -- |  | 1213.5

## Table 41
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.2
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.9
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.4
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
Subtotal |  | 78 | -- |  | -- |  | -- |  | -- |  | -- |  | 27.1

## Table 42
Annual Funding 2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.5
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.5
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.1
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.6
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.8
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
Subtotal |  | 78 | -- |  | -- |  | -- |  | -- |  | -- |  | 25.9

## Table 43
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.3
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.6
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.5
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.5
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.2
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.6
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.6
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.5
Subtotal |  | 254 | -- |  | -- |  | -- |  | -- |  | -- |  | 111.2

## Table 44
Annual Funding 3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.4
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 0.2
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 6.5
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.9
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 13.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.1
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.2
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.3
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.1
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.3
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.7
Subtotal |  | 254 | -- |  | -- |  | -- |  | -- |  | -- |  | 101.8

## Table 45
Annual Funding 0300 ¦ Procurement ¦ Procurement, Defense-Wide
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | 11 | 2.7 |  | 0.1 |  | 4.5 |  | 7.3 |  | 0.6 |  | 7.9
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | 19 | 4.8 |  | 0.1 |  | -- |  | 4.9 |  | 1 |  | 5.9
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.3 |  | 0.3
2003 |  | 10 | 2.5 |  | -- |  | -- |  | 2.5 |  | 0.1 |  | 2.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | 4 | 1 |  | -- |  | -- |  | 1 |  | -- |  | 1
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | 7 | 1.5 |  | -- |  | -- |  | 1.5 |  | -- |  | 1.5
2011 |  | 5 | 1.1 |  | -- |  | -- |  | 1.1 |  | -- |  | 1.1
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | 2 | 0.5 |  | -- |  | -- |  | 0.5 |  | -- |  | 0.5
Subtotal |  | 58 | 14.1 |  | 0.2 |  | 4.5 |  | 18.8 |  | 2 |  | 20.8

## Table 46
Annual Funding 0300 ¦ Procurement ¦ Procurement, Defense-Wide
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | 11 | 2.8 |  | 0.1 |  | 4.7 |  | 7.6 |  | 0.6 |  | 8.2
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | 19 | 4.8 |  | 0.1 |  | -- |  | 4.9 |  | 1 |  | 5.9
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.3 |  | 0.3
2003 |  | 10 | 2.4 |  | -- |  | -- |  | 2.4 |  | 0.1 |  | 2.5
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | 4 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | 7 | 1.3 |  | -- |  | -- |  | 1.3 |  | -- |  | 1.3
2011 |  | 5 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | 2 | 0.4 |  | -- |  | -- |  | 0.4 |  | -- |  | 0.4
Subtotal |  | 58 | 13.5 |  | 0.2 |  | 4.7 |  | 18.4 |  | 2 |  | 20.4

## Table 47
This appropriation provides for the procurement of the Army unique MIDS Low Volume Terminal (MIDS-LVT) (2) and MIDS- LVT (11) variants for the Patriot Air Defense System, THAAD and GAPO. There was an overall decrease in this appropriation due to the Army GAPO de-obligating 2 terminals since the previous SAR.

## Table 48
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | 16 | 5.9 |  | 1.3 |  | 0.5 |  | 7.7 |  | 0.3 |  | 8
2000 |  | 58 | 15.1 |  | 1.8 |  | 35.5 |  | 52.4 |  | 8.3 |  | 60.7
2001 |  | 64 | 20.2 |  | 3.7 |  | 0.2 |  | 24.1 |  | 2.5 |  | 26.6
2002 |  | 103 | 23.9 |  | 0.5 |  | -- |  | 24.4 |  | 10.6 |  | 35
2003 |  | 116 | 22.7 |  | 3.6 |  | -- |  | 26.3 |  | 10.4 |  | 36.7
2004 |  | 138 | 27.8 |  | 3.2 |  | -- |  | 31 |  | 8.4 |  | 39.4
2005 |  | 130 | 25.7 |  | 2.9 |  | -- |  | 28.6 |  | 13.8 |  | 42.4
2006 |  | 169 | 31 |  | 2.9 |  | 0.1 |  | 34 |  | 1.8 |  | 35.8
2007 |  | 169 | 35.2 |  | 3 |  | -- |  | 38.2 |  | 5.2 |  | 43.4
2008 |  | 202 | 40.4 |  | 2.9 |  | -- |  | 43.3 |  | 9.4 |  | 52.7
2009 |  | 127 | 28.5 |  | 2.9 |  | -- |  | 31.4 |  | 1 |  | 32.4
2010 |  | 174 | 29.9 |  | 0.2 |  | -- |  | 30.1 |  | 3.9 |  | 34
2011 |  | 147 | 29.1 |  | 0.2 |  | -- |  | 29.3 |  | 3.9 |  | 33.2
2012 |  | 128 | 31.6 |  | 0.2 |  | -- |  | 31.8 |  | 7.5 |  | 39.3
2013 |  | 262 | 74.8 |  | 0.2 |  | -- |  | 75 |  | -- |  | 75
2014 |  | 176 | 48.5 |  | 0.2 |  | -- |  | 48.7 |  | 2.5 |  | 51.2
2015 |  | 62 | 13.6 |  | 0.2 |  | -- |  | 13.8 |  | 7.2 |  | 21
2016 |  | 215 | 57.3 |  | 0.2 |  | -- |  | 57.5 |  | 5.7 |  | 63.2
2017 |  | 235 | 65.1 |  | 0.2 |  | -- |  | 65.3 |  | 7.1 |  | 72.4
2018 |  | 268 | 76.6 |  | 0.2 |  | -- |  | 76.8 |  | 4.1 |  | 80.9
2019 |  | 190 | 63.6 |  | 0.2 |  | -- |  | 63.8 |  | 2.7 |  | 66.5
2020 |  | 154 | 93.2 |  | 0.2 |  | -- |  | 93.4 |  | 2.9 |  | 96.3
2021 |  | 86 | 86.8 |  | 0.2 |  | -- |  | 87 |  | 1.6 |  | 88.6
2022 |  | 78 | 78.5 |  | 0.2 |  | -- |  | 78.7 |  | -- |  | 78.7
2023 |  | 43 | 63.8 |  | -- |  | -- |  | 63.8 |  | -- |  | 63.8
Subtotal |  | 3510 | 1088.8 |  | 31.3 |  | 36.3 |  | 1156.4 |  | 120.8 |  | 1277.2

## Table 49
Annual Funding 1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | 16 | 6.1 |  | 1.3 |  | 0.5 |  | 7.9 |  | 0.3 |  | 8.2
2000 |  | 58 | 15.3 |  | 1.8 |  | 36.1 |  | 53.2 |  | 8.4 |  | 61.6
2001 |  | 64 | 20.2 |  | 3.8 |  | 0.2 |  | 24.2 |  | 2.5 |  | 26.7
2002 |  | 103 | 23.7 |  | 0.5 |  | -- |  | 24.2 |  | 10.4 |  | 34.6
2003 |  | 116 | 22 |  | 3.5 |  | -- |  | 25.5 |  | 10.1 |  | 35.6
2004 |  | 138 | 26.3 |  | 3 |  | -- |  | 29.3 |  | 8 |  | 37.3
2005 |  | 130 | 23.6 |  | 2.7 |  | -- |  | 26.3 |  | 12.7 |  | 39
2006 |  | 169 | 27.7 |  | 2.6 |  | 0.1 |  | 30.4 |  | 1.6 |  | 32
2007 |  | 169 | 30.8 |  | 2.6 |  | -- |  | 33.4 |  | 4.5 |  | 37.9
2008 |  | 202 | 34.8 |  | 2.5 |  | -- |  | 37.3 |  | 8.1 |  | 45.4
2009 |  | 127 | 24.2 |  | 2.5 |  | -- |  | 26.7 |  | 0.8 |  | 27.5
2010 |  | 174 | 24.9 |  | 0.2 |  | -- |  | 25.1 |  | 3.2 |  | 28.3
2011 |  | 147 | 23.7 |  | 0.2 |  | -- |  | 23.9 |  | 3.2 |  | 27.1
2012 |  | 128 | 25.4 |  | 0.2 |  | -- |  | 25.6 |  | 6 |  | 31.6
2013 |  | 262 | 59.5 |  | 0.2 |  | -- |  | 59.7 |  | -- |  | 59.7
2014 |  | 176 | 38.1 |  | 0.2 |  | -- |  | 38.3 |  | 1.9 |  | 40.2
2015 |  | 62 | 10.5 |  | 0.2 |  | -- |  | 10.7 |  | 5.6 |  | 16.3
2016 |  | 215 | 43.6 |  | 0.2 |  | -- |  | 43.8 |  | 4.3 |  | 48.1
2017 |  | 235 | 48.6 |  | 0.1 |  | -- |  | 48.7 |  | 5.4 |  | 54.1
2018 |  | 268 | 56.1 |  | 0.1 |  | -- |  | 56.2 |  | 3 |  | 59.2
2019 |  | 190 | 45.7 |  | 0.1 |  | -- |  | 45.8 |  | 1.9 |  | 47.7
2020 |  | 154 | 65.6 |  | 0.1 |  | -- |  | 65.7 |  | 2.1 |  | 67.8
2021 |  | 86 | 59.9 |  | 0.1 |  | -- |  | 60 |  | 1.1 |  | 61.1
2022 |  | 78 | 53.1 |  | 0.1 |  | -- |  | 53.2 |  | -- |  | 53.2
2023 |  | 43 | 42.3 |  | -- |  | -- |  | 42.3 |  | -- |  | 42.3
Subtotal |  | 3510 | 851.7 |  | 28.8 |  | 36.9 |  | 917.4 |  | 105.1 |  | 1022.5

## Table 50
This appropriation identifies the MIDS Low Volume Terminal (MIDS-LVT) and MIDS Joint Tactical Radio System (MIDS JTRS) core, CMN4 and TTNT that are planned for the Navy F/A-18C/D/E/F, E/A-18G, E-2D, P-3, P-8, KC-130, EP-3E, MH- 60R/S, the EA-6B.
This appropriation increased by 72 MIDS-LVT terminals and 403 MIDS JTRS terminals since the previous SAR.

## Table 51
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | 1 | 0.4 |  | -- |  | -- |  | 0.4 |  | -- |  | 0.4
2002 |  | 2 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2003 |  | 5 | 2.1 |  | -- |  | -- |  | 2.1 |  | -- |  | 2.1
2004 |  | 5 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2005 |  | 3 | 0.7 |  | -- |  | -- |  | 0.7 |  | -- |  | 0.7
2006 |  | 4 | 0.7 |  | -- |  | -- |  | 0.7 |  | -- |  | 0.7
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | 2 | 0.4 |  | -- |  | -- |  | 0.4 |  | -- |  | 0.4
2009 |  | 2 | 0.4 |  | -- |  | -- |  | 0.4 |  | -- |  | 0.4
2010 |  | 4 | 0.7 |  | -- |  | -- |  | 0.7 |  | -- |  | 0.7
2011 |  | 8 | 1.4 |  | -- |  | -- |  | 1.4 |  | -- |  | 1.4
2012 |  | 7 | 1.3 |  | -- |  | -- |  | 1.3 |  | -- |  | 1.3
2013 |  | 5 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2014 |  | 5 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2015 |  | 3 | 0.5 |  | -- |  | -- |  | 0.5 |  | -- |  | 0.5
2016 |  | 3 | 0.7 |  | -- |  | -- |  | 0.7 |  | -- |  | 0.7
2017 |  | 8 | 2.3 |  | -- |  | -- |  | 2.3 |  | -- |  | 2.3
2018 |  | 3 | 1.1 |  | -- |  | -- |  | 1.1 |  | -- |  | 1.1
2019 |  | 4 | 2.8 |  | -- |  | -- |  | 2.8 |  | -- |  | 2.8
2020 |  | 5 | 5.3 |  | -- |  | -- |  | 5.3 |  | -- |  | 5.3
2021 |  | 4 | 4.3 |  | -- |  | -- |  | 4.3 |  | -- |  | 4.3
2022 |  | 1 | 2.6 |  | -- |  | -- |  | 2.6 |  | -- |  | 2.6
2023 |  | 1 | 2.2 |  | -- |  | -- |  | 2.2 |  | -- |  | 2.2
Subtotal |  | 85 | 33.5 |  | -- |  | -- |  | 33.5 |  | -- |  | 33.5

## Table 52
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | 1 | 0.4 |  | -- |  | -- |  | 0.4 |  | -- |  | 0.4
2002 |  | 2 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2003 |  | 5 | 1.9 |  | -- |  | -- |  | 1.9 |  | -- |  | 1.9
2004 |  | 5 | 0.8 |  | -- |  | -- |  | 0.8 |  | -- |  | 0.8
2005 |  | 3 | 0.6 |  | -- |  | -- |  | 0.6 |  | -- |  | 0.6
2006 |  | 4 | 0.6 |  | -- |  | -- |  | 0.6 |  | -- |  | 0.6
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | 2 | 0.3 |  | -- |  | -- |  | 0.3 |  | -- |  | 0.3
2009 |  | 2 | 0.3 |  | -- |  | -- |  | 0.3 |  | -- |  | 0.3
2010 |  | 4 | 0.5 |  | -- |  | -- |  | 0.5 |  | -- |  | 0.5
2011 |  | 8 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2012 |  | 7 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2013 |  | 5 | 0.6 |  | -- |  | -- |  | 0.6 |  | -- |  | 0.6
2014 |  | 5 | 0.6 |  | -- |  | -- |  | 0.6 |  | -- |  | 0.6
2015 |  | 3 | 0.3 |  | -- |  | -- |  | 0.3 |  | -- |  | 0.3
2016 |  | 3 | 0.4 |  | -- |  | -- |  | 0.4 |  | -- |  | 0.4
2017 |  | 8 | 1.4 |  | -- |  | -- |  | 1.4 |  | -- |  | 1.4
2018 |  | 3 | 0.7 |  | -- |  | -- |  | 0.7 |  | -- |  | 0.7
2019 |  | 4 | 1.6 |  | -- |  | -- |  | 1.6 |  | -- |  | 1.6
2020 |  | 5 | 3 |  | -- |  | -- |  | 3 |  | -- |  | 3
2021 |  | 4 | 2.4 |  | -- |  | -- |  | 2.4 |  | -- |  | 2.4
2022 |  | 1 | 1.4 |  | -- |  | -- |  | 1.4 |  | -- |  | 1.4
2023 |  | 1 | 1.2 |  | -- |  | -- |  | 1.2 |  | -- |  | 1.2
Subtotal |  | 85 | 21.7 |  | -- |  | -- |  | 21.7 |  | -- |  | 21.7

## Table 53
This appropriation identifies the MIDS on Ship variant for new construction surface ships. This appropriation increased by 6 MIDS-LVT terminals and 26 MIDS JTRS terminals since the previous SAR.

## Table 54
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | 3 | 1.1 |  | -- |  | -- |  | 1.1 |  | -- |  | 1.1
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | 2 | 0.5 |  | -- |  | -- |  | 0.5 |  | -- |  | 0.5
2003 |  | 6 | 1.7 |  | -- |  | -- |  | 1.7 |  | -- |  | 1.7
2004 |  | 8 | 1.8 |  | -- |  | -- |  | 1.8 |  | -- |  | 1.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.1 |  | 0.1
2006 |  | 8 | 1.9 |  | -- |  | 0.1 |  | 2 |  | -- |  | 2
2007 |  | 17 | 3.8 |  | -- |  | -- |  | 3.8 |  | 0.6 |  | 4.4
2008 |  | 26 | 6.6 |  | -- |  | -- |  | 6.6 |  | -- |  | 6.6
2009 |  | 6 | 1.2 |  | -- |  | -- |  | 1.2 |  | -- |  | 1.2
2010 |  | 12 | 2.5 |  | -- |  | -- |  | 2.5 |  | -- |  | 2.5
2011 |  | 44 | 9.8 |  | -- |  | -- |  | 9.8 |  | -- |  | 9.8
2012 |  | 6 | 1.2 |  | -- |  | -- |  | 1.2 |  | -- |  | 1.2
2013 |  | 26 | 7 |  | -- |  | -- |  | 7 |  | -- |  | 7
2014 |  | 6 | 1.3 |  | -- |  | -- |  | 1.3 |  | -- |  | 1.3
2015 |  | 15 | 2.8 |  | -- |  | -- |  | 2.8 |  | -- |  | 2.8
2016 |  | 30 | 8 |  | -- |  | -- |  | 8 |  | -- |  | 8
2017 |  | 35 | 9.3 |  | -- |  | -- |  | 9.3 |  | -- |  | 9.3
2018 |  | 27 | 9.3 |  | -- |  | -- |  | 9.3 |  | -- |  | 9.3
2019 |  | 15 | 11.4 |  | -- |  | -- |  | 11.4 |  | -- |  | 11.4
2020 |  | 15 | 9.5 |  | -- |  | -- |  | 9.5 |  | -- |  | 9.5
2021 |  | 5 | 4.2 |  | -- |  | -- |  | 4.2 |  | -- |  | 4.2
2022 |  | 1 | 4.9 |  | -- |  | -- |  | 4.9 |  | -- |  | 4.9
Subtotal |  | 313 | 99.8 |  | -- |  | 0.1 |  | 99.9 |  | 0.7 |  | 100.6

## Table 55
Annual Funding 1810 ¦ Procurement ¦ Other Procurement, Navy
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1999 |  | 3 | 1.1 |  | -- |  | -- |  | 1.1 |  | -- |  | 1.1
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2002 |  | 2 | 0.5 |  | -- |  | -- |  | 0.5 |  | -- |  | 0.5
2003 |  | 6 | 1.7 |  | -- |  | -- |  | 1.7 |  | -- |  | 1.7
2004 |  | 8 | 1.7 |  | -- |  | -- |  | 1.7 |  | -- |  | 1.7
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | 0.1 |  | 0.1
2006 |  | 8 | 1.7 |  | -- |  | 0.1 |  | 1.8 |  | -- |  | 1.8
2007 |  | 17 | 3.3 |  | -- |  | -- |  | 3.3 |  | 0.6 |  | 3.9
2008 |  | 26 | 5.7 |  | -- |  | -- |  | 5.7 |  | -- |  | 5.7
2009 |  | 6 | 1 |  | -- |  | -- |  | 1 |  | -- |  | 1
2010 |  | 12 | 2.1 |  | -- |  | -- |  | 2.1 |  | -- |  | 2.1
2011 |  | 44 | 8.1 |  | -- |  | -- |  | 8.1 |  | -- |  | 8.1
2012 |  | 6 | 1 |  | -- |  | -- |  | 1 |  | -- |  | 1
2013 |  | 26 | 5.6 |  | -- |  | -- |  | 5.6 |  | -- |  | 5.6
2014 |  | 6 | 1 |  | -- |  | -- |  | 1 |  | -- |  | 1
2015 |  | 15 | 2.2 |  | -- |  | -- |  | 2.2 |  | -- |  | 2.2
2016 |  | 30 | 6.1 |  | -- |  | -- |  | 6.1 |  | -- |  | 6.1
2017 |  | 35 | 7 |  | -- |  | -- |  | 7 |  | -- |  | 7
2018 |  | 27 | 6.8 |  | -- |  | -- |  | 6.8 |  | -- |  | 6.8
2019 |  | 15 | 8.2 |  | -- |  | -- |  | 8.2 |  | -- |  | 8.2
2020 |  | 15 | 6.7 |  | -- |  | -- |  | 6.7 |  | -- |  | 6.7
2021 |  | 5 | 2.9 |  | -- |  | -- |  | 2.9 |  | -- |  | 2.9
2022 |  | 1 | 3.3 |  | -- |  | -- |  | 3.3 |  | -- |  | 3.3
Subtotal |  | 313 | 77.7 |  | -- |  | 0.1 |  | 77.8 |  | 0.7 |  | 78.5

## Table 56
This appropriation increased by 57 MIDS-Low Volume Terminal (MIDS-LVT) terminals and 107 MIDS Joint Tactical Radio System (JTRS) terminals since the previous SAR.

## Table 57
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | 1 | 0.3 |  | -- |  | -- |  | 0.3 |  | -- |  | 0.3
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | 4 | 1 |  | -- |  | -- |  | 1 |  | 0.4 |  | 1.4
2004 |  | 5 | 1.3 |  | -- |  | -- |  | 1.3 |  | 0.4 |  | 1.7
2005 |  | 62 | 15.7 |  | -- |  | -- |  | 15.7 |  | 1.2 |  | 16.9
2006 |  | 67 | 16.3 |  | -- |  | -- |  | 16.3 |  | 0.1 |  | 16.4
2007 |  | 40 | 9.4 |  | -- |  | -- |  | 9.4 |  | 1.1 |  | 10.5
2008 |  | 144 | 33.5 |  | -- |  | -- |  | 33.5 |  | -- |  | 33.5
2009 |  | 29 | 6.4 |  | -- |  | -- |  | 6.4 |  | 2.2 |  | 8.6
2010 |  | 30 | 7 |  | -- |  | -- |  | 7 |  | 1.6 |  | 8.6
2011 |  | 22 | 4.8 |  | -- |  | -- |  | 4.8 |  | 1 |  | 5.8
2012 |  | 9 | 2 |  | -- |  | -- |  | 2 |  | 0.1 |  | 2.1
2013 |  | 5 | 3.3 |  | -- |  | -- |  | 3.3 |  | 0.4 |  | 3.7
2014 |  | 1 | 1.1 |  | -- |  | -- |  | 1.1 |  | 0.1 |  | 1.2
2015 |  | 2 | 0.1 |  | -- |  | -- |  | 0.1 |  | 3.9 |  | 4
2016 |  | 1 | 9.4 |  | -- |  | -- |  | 9.4 |  | -- |  | 9.4
2017 |  | 1 | 12.4 |  | -- |  | -- |  | 12.4 |  | -- |  | 12.4
2018 |  | 1 | 12.4 |  | -- |  | -- |  | 12.4 |  | -- |  | 12.4
2019 |  | 1 | 11.4 |  | -- |  | -- |  | 11.4 |  | -- |  | 11.4
2020 |  | 1 | 5.5 |  | -- |  | -- |  | 5.5 |  | -- |  | 5.5
2021 |  | 1 | 6.5 |  | -- |  | -- |  | 6.5 |  | -- |  | 6.5
Subtotal |  | 427 | 159.8 |  | -- |  | -- |  | 159.8 |  | 12.5 |  | 172.3

## Table 58
Annual Funding 2035 ¦ Procurement ¦ Other Procurement, Army
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | 1 | 0.3 |  | -- |  | -- |  | 0.3 |  | -- |  | 0.3
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2003 |  | 4 | 1 |  | -- |  | -- |  | 1 |  | 0.4 |  | 1.4
2004 |  | 5 | 1.2 |  | -- |  | -- |  | 1.2 |  | 0.4 |  | 1.6
2005 |  | 62 | 14.5 |  | -- |  | -- |  | 14.5 |  | 1.1 |  | 15.6
2006 |  | 67 | 14.7 |  | -- |  | -- |  | 14.7 |  | 0.1 |  | 14.8
2007 |  | 40 | 8.3 |  | -- |  | -- |  | 8.3 |  | 0.9 |  | 9.2
2008 |  | 144 | 29 |  | -- |  | -- |  | 29 |  | -- |  | 29
2009 |  | 29 | 5.5 |  | -- |  | -- |  | 5.5 |  | 1.8 |  | 7.3
2010 |  | 30 | 5.9 |  | -- |  | -- |  | 5.9 |  | 1.3 |  | 7.2
2011 |  | 22 | 4 |  | -- |  | -- |  | 4 |  | 0.8 |  | 4.8
2012 |  | 9 | 1.6 |  | -- |  | -- |  | 1.6 |  | 0.1 |  | 1.7
2013 |  | 5 | 2.6 |  | -- |  | -- |  | 2.6 |  | 0.3 |  | 2.9
2014 |  | 1 | 0.9 |  | -- |  | -- |  | 0.9 |  | -- |  | 0.9
2015 |  | 2 | 0.1 |  | -- |  | -- |  | 0.1 |  | 3 |  | 3.1
2016 |  | 1 | 7.2 |  | -- |  | -- |  | 7.2 |  | -- |  | 7.2
2017 |  | 1 | 9.3 |  | -- |  | -- |  | 9.3 |  | -- |  | 9.3
2018 |  | 1 | 9.1 |  | -- |  | -- |  | 9.1 |  | -- |  | 9.1
2019 |  | 1 | 8.2 |  | -- |  | -- |  | 8.2 |  | -- |  | 8.2
2020 |  | 1 | 3.9 |  | -- |  | -- |  | 3.9 |  | -- |  | 3.9
2021 |  | 1 | 4.5 |  | -- |  | -- |  | 4.5 |  | -- |  | 4.5
Subtotal |  | 427 | 131.8 |  | -- |  | -- |  | 131.8 |  | 10.2 |  | 142

## Table 59
This appropriation provides for the procurement of the Army unique MIDS Low Volume Terminal (MIDS-LVT) (2) and MIDS- LVT (11) variants. This appropriation increased by 2 MIDS-LVT terminals since the previous SAR.

## Table 60
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | 52 | 8.5 |  | -- |  | 4.4 |  | 12.9 |  | 6.9 |  | 19.8
2002 |  | 150 | 32.5 |  | -- |  | -- |  | 32.5 |  | 10.2 |  | 42.7
2003 |  | 180 | 36.8 |  | -- |  | -- |  | 36.8 |  | 10.5 |  | 47.3
2004 |  | 137 | 24.3 |  | -- |  | -- |  | 24.3 |  | 13.8 |  | 38.1
2005 |  | 164 | 35.5 |  | -- |  | 0.1 |  | 35.6 |  | 4.3 |  | 39.9
2006 |  | 129 | 25.1 |  | -- |  | -- |  | 25.1 |  | 1.7 |  | 26.8
2007 |  | 152 | 31.1 |  | -- |  | -- |  | 31.1 |  | 3.4 |  | 34.5
2008 |  | 52 | 14.7 |  | -- |  | -- |  | 14.7 |  | 4.4 |  | 19.1
2009 |  | 15 | 5 |  | -- |  | -- |  | 5 |  | 1.6 |  | 6.6
2010 |  | 51 | 13 |  | -- |  | -- |  | 13 |  | 2.4 |  | 15.4
2011 |  | 34 | 9.5 |  | -- |  | -- |  | 9.5 |  | 0.2 |  | 9.7
2012 |  | 83 | 25.8 |  | -- |  | -- |  | 25.8 |  | -- |  | 25.8
2013 |  | 43 | 11.3 |  | -- |  | -- |  | 11.3 |  | -- |  | 11.3
2014 |  | 34 | 11.7 |  | -- |  | -- |  | 11.7 |  | -- |  | 11.7
2015 |  | 1 | 5.8 |  | -- |  | -- |  | 5.8 |  | -- |  | 5.8
2016 |  | 65 | 17.8 |  | -- |  | -- |  | 17.8 |  | -- |  | 17.8
2017 |  | 148 | 46.4 |  | -- |  | -- |  | 46.4 |  | -- |  | 46.4
2018 |  | 377 | 109.4 |  | -- |  | -- |  | 109.4 |  | -- |  | 109.4
2019 |  | 522 | 153.3 |  | -- |  | -- |  | 153.3 |  | -- |  | 153.3
2020 |  | 233 | 72.7 |  | -- |  | -- |  | 72.7 |  | -- |  | 72.7
2021 |  | 37 | 11.5 |  | -- |  | -- |  | 11.5 |  | -- |  | 11.5
2022 |  | 23 | 7 |  | -- |  | -- |  | 7 |  | -- |  | 7
2023 |  | 13 | 3.9 |  | -- |  | -- |  | 3.9 |  | -- |  | 3.9
2024 |  | 22 | 6.9 |  | -- |  | -- |  | 6.9 |  | -- |  | 6.9
Subtotal |  | 2717 | 719.5 |  | -- |  | 4.5 |  | 724 |  | 59.4 |  | 783.4

## Table 61
Annual Funding 3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2001 |  | 52 | 8.5 |  | -- |  | 4.4 |  | 12.9 |  | 6.9 |  | 19.8
2002 |  | 150 | 32.2 |  | -- |  | -- |  | 32.2 |  | 10.1 |  | 42.3
2003 |  | 180 | 35.9 |  | -- |  | -- |  | 35.9 |  | 10.2 |  | 46.1
2004 |  | 137 | 23.1 |  | -- |  | -- |  | 23.1 |  | 13.1 |  | 36.2
2005 |  | 164 | 32.7 |  | -- |  | 0.1 |  | 32.8 |  | 4 |  | 36.8
2006 |  | 129 | 22.6 |  | -- |  | -- |  | 22.6 |  | 1.5 |  | 24.1
2007 |  | 152 | 27.2 |  | -- |  | -- |  | 27.2 |  | 3 |  | 30.2
2008 |  | 52 | 12.7 |  | -- |  | -- |  | 12.7 |  | 3.7 |  | 16.4
2009 |  | 15 | 4.2 |  | -- |  | -- |  | 4.2 |  | 1.4 |  | 5.6
2010 |  | 51 | 10.8 |  | -- |  | -- |  | 10.8 |  | 2 |  | 12.8
2011 |  | 34 | 7.8 |  | -- |  | -- |  | 7.8 |  | 0.1 |  | 7.9
2012 |  | 83 | 20.8 |  | -- |  | -- |  | 20.8 |  | -- |  | 20.8
2013 |  | 43 | 8.9 |  | -- |  | -- |  | 8.9 |  | -- |  | 8.9
2014 |  | 34 | 9.1 |  | -- |  | -- |  | 9.1 |  | -- |  | 9.1
2015 |  | 1 | 4.5 |  | -- |  | -- |  | 4.5 |  | -- |  | 4.5
2016 |  | 65 | 13.4 |  | -- |  | -- |  | 13.4 |  | -- |  | 13.4
2017 |  | 148 | 34.3 |  | -- |  | -- |  | 34.3 |  | -- |  | 34.3
2018 |  | 377 | 79.4 |  | -- |  | -- |  | 79.4 |  | -- |  | 79.4
2019 |  | 522 | 109.1 |  | -- |  | -- |  | 109.1 |  | -- |  | 109.1
2020 |  | 233 | 50.7 |  | -- |  | -- |  | 50.7 |  | -- |  | 50.7
2021 |  | 37 | 7.9 |  | -- |  | -- |  | 7.9 |  | -- |  | 7.9
2022 |  | 23 | 4.7 |  | -- |  | -- |  | 4.7 |  | -- |  | 4.7
2023 |  | 13 | 2.6 |  | -- |  | -- |  | 2.6 |  | -- |  | 2.6
2024 |  | 22 | 4.4 |  | -- |  | -- |  | 4.4 |  | -- |  | 4.4
Subtotal |  | 2717 | 567.5 |  | -- |  | 4.5 |  | 572 |  | 56 |  | 628

## Table 62
This appropriation identifies the MIDS Low Volume Terminal (MIDS-LVT) and MIDS Joint Tactical Radio System (MIDS JTRS) terminals that are planned for the F-15, F-22, F-16, AC-130, RC-135, EC130E/H, B-1, E-8C, the Airborne Laser and United States Air Force shore sites. This appropriation increased by 67 MIDS-LVT terminals and 1346 MIDS JTRS terminals since the previous SAR.

## Table 63
Annual Funding 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | 6 | 3 |  | -- |  | -- |  | 3 |  | -- |  | 3
1997 |  | -- | -- |  | -- |  | 0.3 |  | 0.3 |  | -- |  | 0.3
1998 |  | 77 | 18.5 |  | -- |  | 15.2 |  | 33.7 |  | 1 |  | 34.7
1999 |  | 173 | 33 |  | 0.3 |  | -- |  | 33.3 |  | 2.1 |  | 35.4
2000 |  | 294 | 49.8 |  | 0.7 |  | 0.5 |  | 51 |  | 3.8 |  | 54.8
2001 |  | 148 | 26.7 |  | 0.6 |  | 4.4 |  | 31.7 |  | 1 |  | 32.7
2002 |  | 97 | 18.6 |  | -- |  | 5.6 |  | 24.2 |  | -- |  | 24.2
2003 |  | 30 | 0.4 |  | -- |  | -- |  | 0.4 |  | 5.3 |  | 5.7
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | 6 | 1.8 |  | -- |  | -- |  | 1.8 |  | -- |  | 1.8
2017 |  | 11 | 12.4 |  | -- |  | -- |  | 12.4 |  | -- |  | 12.4
2018 |  | 12 | 10.3 |  | -- |  | -- |  | 10.3 |  | -- |  | 10.3
2019 |  | 12 | 6.6 |  | -- |  | -- |  | 6.6 |  | -- |  | 6.6
2020 |  | 24 | 6 |  | -- |  | -- |  | 6 |  | -- |  | 6
Subtotal |  | 890 | 187.1 |  | 1.6 |  | 26 |  | 214.7 |  | 13.2 |  | 227.9

## Table 64
Annual Funding 3080 ¦ Procurement ¦ Other Procurement, Air Force
Fiscal Year | Quantity |  | BY 2003 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1996 |  | 6 | 3.2 |  | -- |  | -- |  | 3.2 |  | -- |  | 3.2
1997 |  | -- | -- |  | -- |  | 0.3 |  | 0.3 |  | -- |  | 0.3
1998 |  | 77 | 19.2 |  | -- |  | 15.7 |  | 34.9 |  | 1 |  | 35.9
1999 |  | 173 | 33.8 |  | 0.3 |  | -- |  | 34.1 |  | 2.2 |  | 36.3
2000 |  | 294 | 50.3 |  | 0.7 |  | 0.5 |  | 51.5 |  | 3.8 |  | 55.3
2001 |  | 148 | 26.5 |  | 0.6 |  | 4.4 |  | 31.5 |  | 1 |  | 32.5
2002 |  | 97 | 18.2 |  | -- |  | 5.4 |  | 23.6 |  | -- |  | 23.6
2003 |  | 30 | 0.4 |  | -- |  | -- |  | 0.4 |  | 5.2 |  | 5.6
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2016 |  | 6 | 1.4 |  | -- |  | -- |  | 1.4 |  | -- |  | 1.4
2017 |  | 11 | 9.5 |  | -- |  | -- |  | 9.5 |  | -- |  | 9.5
2018 |  | 12 | 7.7 |  | -- |  | -- |  | 7.7 |  | -- |  | 7.7
2019 |  | 12 | 4.8 |  | -- |  | -- |  | 4.8 |  | -- |  | 4.8
2020 |  | 24 | 4.3 |  | -- |  | -- |  | 4.3 |  | -- |  | 4.3
Subtotal |  | 890 | 179.3 |  | 1.6 |  | 26.3 |  | 207.2 |  | 13.2 |  | 220.4

## Table 65
This appropriation identifies the MIDS Fighter Data Link (FDL) terminals for the F-15C/D/E that are being procured on a separate contract. The FY 1996 funding (TY $3.0M) reports the United States Air Force funds contributed to the qualification and build of six FDL terminals. Additional funds in excess of $8.0M were contributed by the contractor, Data Link Solutions L.L.C., for completion of the full qualification program requirements.
This appropriation also includes the MIDS-Low Volume Terminal (MIDS-LVT) procurement for the Air Force. This appropriation increased by 65 MIDS-LVT terminals since the previous SAR.

## Table 66
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2000-05-11 | 2003-12-08
Approved Quantity | 70 | 544
Reference | Milestone II ADM | Milestone C ADM
Start Year | 2000 | 2000
End Year | 2001 | 2003
The MDA authorized LRIP on May 11, 2000 for 70 MIDS Low Volume Terminal (MIDS-LVT). Three additional LRIP decisions were authorized for a cumulative total of 544 MIDS-LVT and MIDS-LVT(2) variants (about 25 percent of the then planned procurement of 2,145 terminals). Based on a Milestone C decision in 2003 for the MIDS program, USD (AT&L) General Counsel and senior staff changed the title of the 2009 DAB decision for MIDS JTRS to Limited Production and Fielding (LP&F). A follow-on decision for the MIDS JTRS variant was made for Full Production and Fielding (FP&F), and not FRP. On December 23, 2009 an ADM approved the award of the limited production of 41 MIDS JTRS variant terminals to support the F/A-18E/F production schedule and Joint Surveillance Target Attack Radar System (JSTARS) integration and testing requirements. On January 31, 2011, an ADM approved an award of a second limited production for 42 MIDS JTRS variant terminals to support F/A-18E/F production, RC-135 Rivet Joint, EC-130H Compass Call, and other Service requirements.

## Table 67
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Kuwait | 2015-09-24 | 4 | 0.9 | Date of sale listed is the most current buy on FMS case KU-B-UMG.
Netherlands | 2015-09-24 | 10 | 5.4 | Total Costs are cumulative over multiple years and FMS cases (NE-P-LFT; NE-P-LGT). Date of sale listed is the most current buy.
Australia | 2015-09-18 | 271 | 60.4 | Total Costs are cumulative over multiple years and FMS cases (AT-D-QCI; AT-P-GOV; AT-P-LAB; AT- P-LCE; AT-P-LCK; AT-P-LCQ; AT-P-LDN; AT-P- LER; AT-P-LET; AT-P-SAF; AT-P-SCF; AT-P-SCI; AT-P-LFA). Date of sale listed is the most current buy.
United Kingdom | 2015-09-18 | 10 | 3.2 | Total Costs are cumulative over multiple years and FMS cases (UK-D-SAO; UK-P-LVE). Date of sale listed is the most current buy.
Oman | 2015-08-31 | 72 | 13.7 | Total Costs are cumulative over multiple years and FMS cases (MU-D-SAB; MU-P-LAP). Date of sale listed is the most current buy.
Romania | 2015-08-31 | 15 | 2.7 | Total Cost is cumulative over multiple years. Date of sale listed is the most current buy on FMS case RO-D-QAH.
Thailand | 2015-08-31 | 24 | 4.5 | Total Costs are cumulative over multiple years and FMS cases (TH-D-QCZ; TH-P-LFA). Date of sale listed is the most current buy.
Singapore | 2015-03-06 | 61 | 7.5 | Total Costs are cumulative over multiple years and FMS cases (SN-D-SAA; SN-D-SAC; SN-D-BAA; SN-D-QAT). Date of sale listed is the most current buy.
Japan | 2015-03-05 | 149 | 32.8 | Total Costs are cumulative over multiple years and FMS cases (JA-P-LTY; JA-P-LTD; JA-P-LTV; JA-P- LUD; JA-P-LVM; JA-P-LVY; JA-P-LUO; JA-P-LUP; JA-P-LVE; JA-P-LWC; JA-P-LWJ; JA-P-LWO; JA-P -LXB; JA-P-LXC; JA-P-LXD; JA-P-LXE; JA-P-LXF; JA-P-LXM; JA-P-LXN; JA-P-LXO; JA-P-LYC; JA-P- LYL; JA-P-LYQ; JA-P-LYP; JA-P-LYT; JA-P-LYV; JA -P-LYX; JA-P-LZG; JA-P-NAF). Date of sale listed is the most current buy.
Saudi Arabia | 2015-02-20 | 241 | 18.6 | Total Costs are cumulative over multiple years and FMS cases (SR-D-QAB; SR-D-SAI, SR-P-LCO; SR-D-QBP). Date of sale listed is the most current buy. *Not all cost data is available. 165 terminals without pricing.*
Belgium | 2015-01-20 | 84 | 18.2 | Total Costs are cumulative over multiple years and FMS cases (BE-D-DZV; BE-D-QAT, BE-P-LBB). Date of sale listed is the most current buy.
Canada | 2015-01-20 | 144 | 31.3 | Total Costs are cumulative over multiple years and FMS cases (CN-P-LHF; CN-P-LHS; CN-P-LIC; CN-

## Table 68
Poland | 2015-01-20 | 78 | 16.6 | P-LIQ; CN-P-LJC, CN-P-LJR). Date of sale listed is the most current buy. Total Costs are cumulative over multiple years and
FMS cases (PL-D-SAC; PL-P-LAM). Date of sale listed is the most current buy.
South Korea | 2014-12-29 | 34 | 9 | Total Costs are cumulative over multiple years and FMS cases (KS-P-BTV; KS-P-GOL; KS-P-LPN; KS -P-QDW; KS-P-BVB). Date of sale listed is the most current buy.
Finland | 2014-09-30 | 120 | 23.2 | Total Costs are cumulative over multiple years and FMS cases (FI-P-LBC; FI-P-LBD; FI-P-LBH; FI-P- LBJ). Date of sale listed is the most current buy.
New Zealand | 2014-09-30 | 9 | 1.6 | Date of sale listed is the most current buy on FMS case (NZ-P-LAJ; NZ-P-LAZ; NZ-P-LAU).
Chile | 2014-08-07 | 25 | 3.7 | Date of sale listed is the most current buy on FMS case CI-P-LCW.
Jordan | 2014-08-07 | 34 | 5.6 | Total Costs are cumulative over multiple years and FMS cases (JO-P-LAZ; JO-P-LBG; JO-D-QBK) Date of sale listed is the most current buy.
Portugal | 2014-08-07 | 46 | 8.5 | Date of sale listed is the most current buy on FMS case PT-D-NAE; PT-P-LDH.
Switzerland | 2013-08-05 | 60 | 14.6 | Date of sale listed is the most current buy on FMS case SZ-P-LAC; SZ-P-LAH.
United Arab Emirates | 2013-08-05 | 19 | 3.3 | Total Costs are cumulative over multiple years and FMS cases (AE-P-LAA; AE-B-UAF; AE-B-ZUG). Date of sale listed is the most current buy.
Taiwan | 2013-06-04 | 196 | 59.4 | Total Costs are cumulative over multiple years and FMS cases (TW-P-GNU; TW-B-YYV; TW-P-GMK; TW-P-LEJ; TW-P-SEG; TW-P-GMG). Date of sale listed is the most current buy.
Turkey | 2012-09-21 | 314 | 61.1 | Total Costs are cumulative over multiple years and FMS cases (TK-D-NCU; TK-P-LKT; TK-D-SMB). Date of sale listed is the most current buy.
Hungary | 2010-09-16 | 22 | 4.1 | Date of sale listed is the most current buy on FMS case HU-P-LAD.
Pakistan | 2010-09-16 | 68 | 16.1 | Total Costs are cumulative over multiple years and FMS cases (PK-D-NAP; PK-D-SAF). Date of sale listed is the most current buy.
Morocco | 2010-05-14 | 30 | 4.8 | Date of sale listed is the most current buy on FMS case MO-D-SAY.
Norway | 2009-06-23 | 77 | 22.9 | Total Costs are cumulative over multiple years and FMS cases (NO-D-OAF; NO-D-OAG; NO-P-LBE; NO-P-LBO). Date of sale listed is the most current buy.
Greece | 2008-12-22 | 40 | 6.9 | Total Costs are cumulative over multiple years and FMS cases (GR-B-XJU; GR-D-SNY). Date of sale listed is the most current buy.
Austria | 2008-05-12 | 24 | 0 | FMS total costs not releasable for Austria. AU-P- LAD.
Sweden | 2006-08-28 | 28 | 4.9 | Date of sale listed is the most current buy on FMS case SW-P-LAO.
Germany | 2004-02-20 | 10 | 6.4 | Date of sale listed is the most current buy on FMS

## Table 69
case GY-P-LGI.
Denmark 5/16/2002 3 0.9 Date of sale listed is the most current buy on FMS
case DE-D-OAB.
Notes
The above FMS cases, with the exception of United Kingdom (UK-D-SAO; UK-P-LVE) and Australia (AT-P-SCI; AT-P- LFA) for MIDS Joint Tactical Radio System (MIDS JTRS) terminals, are for MIDS Low Volume Terminals (MIDS-LVT).
Direct Commercial Sales (DCS) totaling 968 MIDS-LVT terminals have been implemented to date with Australia (16), Belgium (2), Denmark (77), Greece (6), Iceland (3), Japan (2), Korea (183), North Atlantic Treaty Organization (NATO) Air Command and Control System (ACCS) Management Agency (NACMA) (72), Netherlands (149), NATO EuroFighter 2000 and Tornado Management Agency (36), Norway (31), Poland (2), Singapore (7), Sweden (140), Turkey (15) and United Kingdom (227). (Cost information for direct commercial sales is not available nor is date of sale). Per CJCSI 6510.0C, DCS sales for MIDS-LVT and MIDS JTRS are no longer sanctioned, except for a case-by-case basis with Australia, Canada, New Zealand, and the United Kingdom, or a one-time waiver has already been obtained.
Other foreign sales for 42 MIDS-LVT terminals at a cost of 12.2$M were implemented through February 2015 with the European Participating Air Force (3) and German competitive buys (39).
Nuclear Costs
None

## Table 70
Unit Cost
Unit Cost Report
Item |  | BY 2003 $M | BY 2003 $M |  | % Change
|  | Current UCR Baseline (Nov 2013 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 3031 |  |  | 3872.3
Quantity | 6233 |  |  | 8604
Unit Cost | 0.486 |  |  | 0.45 |  | -7.41
Average Procurement Unit Cost
Cost | 1393.5 |  |  | 2133.5
Quantity | 5745 |  |  | 8000
Unit Cost | 0.243 |  |  | 0.267 |  | 9.88
Item |  | BY 2003 $M | BY 2003 $M |  | % Change
|  | Original UCR Baseline (Mar 1994 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1091.4 |  |  | 3872.3
Quantity | 672 |  |  | 8604
Unit Cost | 1.624 |  |  | 0.45 |  | -72.29
Average Procurement Unit Cost
Cost | 523.7 |  |  | 2133.5
Quantity | 630 |  |  | 8000
Unit Cost | 0.831 |  |  | 0.267 |  | -67.87

## Table 71
Unit Cost History
Item | [7 empty] | Date |  |  |  |  | BY 2003 $M | [7 empty] | TY $M
[13 empty] | PAUC |  |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Mar 1994 | [7 empty] | 1.625 |  |  |  |  | 0.831 |  |  |  | 1.666 |  |  |  | 0.931
APB as of January 2006 |  |  |  |  | Jun 2004 | [7 empty] | 0.616 |  |  |  |  | 0.339 |  |  |  | 0.614 |  |  |  | 0.352
Revised Original APB |  |  |  |  | N/A | [7 empty] | N/A |  |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Apr 2012 | [7 empty] | 0.533 |  |  |  |  | 0.255 |  |  |  | 0.573 |  |  |  | 0.28
Current APB |  |  |  |  | Nov 2013 | [7 empty] | 0.486 |  |  |  |  | 0.243 |  |  |  | 0.535 |  |  |  | 0.276
Prior Annual SAR |  |  |  |  | Dec 2014 | [7 empty] | 0.5 |  |  |  |  | 0.258 |  |  |  | 0.554 |  |  |  | 0.296
Current Estimate |  |  |  |  | Dec 2015 | [7 empty] | 0.45 |  |  |  |  | 0.267 |  |  |  | 0.522 |  |  |  | 0.327
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [22 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  |  | Est |  |  | Oth |  | Spt |  |  | Total
1.670 -0.023 -1.090 0.015 -0.017 0.058 0.000 0.001 -1.056 0.614
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [20 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng | Est |  |  | Oth |  | Spt |  |  | Total
0.614 0.002 -0.159 -0.007 0.068 -0.003 0.000 0.007 -0.092 0.522

## Table 72
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [11 empty] | APUC Production Estimate
| Econ |  | Qty |  |  | Sch | Eng |  | Est | Oth | Spt | Total
0.931 -0.019 -0.520 0.016 -0.036 -0.021 0.000 0.001 -0.579 0.352
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [11 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch |  | Eng |  | Est | Oth | Spt | Total
0.352 0.001 0.021 -0.007 -0.015 -0.032 0.000 0.007 -0.025 0.327
SAR Baseline History
Item |  |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | N/A
Milestone II |  |  |  | N/A |  |  |  | Dec 1993 |  |  | Dec 1993 |  |  | Dec 1993
Milestone III |  |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  | Dec 1999
IOC |  |  |  | N/A |  |  |  | Dec 2000 |  |  | N/A |  |  | Jan 2001
Total Cost (TY $M) |  |  |  | N/A |  |  |  | 1119.5 |  |  | 1818.9 |  |  | 4492.7
Total Quantity |  |  |  | N/A |  |  |  | 672 |  |  | 2964 |  |  | 8604
PAUC |  |  |  | N/A |  |  |  | 1.666 |  |  | 0.614 |  |  | 0.522
The baseline includes separate Milestone (MS) III decisions for the MIDS Low Volume Terminal (MIDS-LVT) Variant (1) and MIDS-LVT Variant (3) and a separate IOC for each MIDS variant. A MS III decision was originally planned for the United States Army unique MIDS-LVT Variant (2) but it was replaced by an FRP decision approved by the Assistant Secretary of the Navy (Research, Development and Acquisition) in an ADM dated December 8, 2003.

## Table 73
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
825.8 993.1 -- 1818.9
Economic |  | 7.1 |  | 14.5 |  | -- |  | 21.6
Quantity |  | 92.4 |  | 1089.2 |  | -- |  | 1181.6
Schedule |  | -0.2 |  | -31.5 |  | -- |  | -31.7
Engineering |  | 705.6 |  | -69.2 |  | -- |  | 636.4
Estimating |  | 178 |  | -319 |  | -- |  | -141
Other |  | -- |  | -- |  | -- |  | --
Support |  | 3.7 |  | 56.6 |  | -- |  | 60.3
Subtotal |  | 986.6 |  | 740.6 |  | -- |  | 1727.2
Current Changes Economic |  | -1.6 |  | -3 |  | -- |  | -4.6
Quantity |  | 13.9 |  | 894.9 |  | -- |  | 908.8
Schedule |  | -- |  | -26 |  | -- |  | -26
Engineering |  | -- |  | -47.4 |  | -- |  | -47.4
Estimating |  | 52.3 |  | 61.7 |  | -- |  | 114
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 1.8 |  | -- |  | 1.8
Subtotal |  | 64.6 |  | 882 |  | -- |  | 946.6
Total Changes |  | 1051.2 |  | 1622.6 |  | -- |  | 2673.8
CE - Cost Variance |  | 1877 |  | 2615.7 |  | -- |  | 4492.7
CE - Cost & Funding |  | 1877 |  | 2615.7 |  | -- |  | 4492.7

## Table 74
Summary BY 2003 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
869.4 955.4 -- 1824.8
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | 84.3 |  | 850.4 |  | -- |  | 934.7
Schedule |  | -0.4 |  | -9 |  | -- |  | -9.4
Engineering |  | 592.9 |  | -53.9 |  | -- |  | 539
Estimating |  | 138.7 |  | -278.6 |  | -- |  | -139.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | 3.2 |  | 44.3 |  | -- |  | 47.5
Subtotal |  | 818.7 |  | 553.2 |  | -- |  | 1371.9
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | 10.9 |  | 636 |  | -- |  | 646.9
Schedule |  | -- |  | -15 |  | -- |  | -15
Engineering |  | -- |  | -33.4 |  | -- |  | -33.4
Estimating |  | 39.8 |  | 35.8 |  | -- |  | 75.6
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 1.5 |  | -- |  | 1.5
Subtotal |  | 50.7 |  | 624.9 |  | -- |  | 675.6
Total Changes |  | 869.4 |  | 1178.1 |  | -- |  | 2047.5
CE - Cost Variance |  | 1738.8 |  | 2133.5 |  | -- |  | 3872.3
CE - Cost & Funding |  | 1738.8 |  | 2133.5 |  | -- |  | 3872.3
Previous Estimate: December 2014

## Table 75
RDT&E |  |  | $M
Current Change Explanations |  |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1.6
Quantity variance resulting from an increase of 35 MIDS Joint Tactical Radio System (JTRS) terminals (Air Force). (Quantity)
Quantity variance resulting from an increase of 11 MIDS-Low Volume Terminal (LVT) terminals and 6 MIDS JTRS terminals (Navy). (Quantity)
Revised estimate to align with FY 2017 PB to fully fund MIDS JTRS Tactical Targeting Network Technology (TTNT) (Navy). (Estimating)
+8.4 +10.7
+2.5 +3.2
+13.0 +18.5
Revised estimate for rate adjustments (Navy). (Estimating) -1.7 -2.3
Congressional Reduction in FY 2017 (Navy). (Estimating) -1.3 -1.8
Revised estimate for purchase of 4 MIDS-LVT Block Upgrade 2 retrofit kits for risk reduction terminals (Air Force). (Estimating)
FY 2014 - FY 2015 New funding for Investigation Reports for implementation of MIDS JTRS to Air Force Platforms (Air Force). (Estimating)
Additional Funding in FY 2015 for MIDS Modernization and MIDS JTRS TTNT (Navy). (Estimating)
Revised estimate for MIDS JTRS TTNT High Powered Amplifier technical development (Navy). (Estimating)
+1.3 +1.6
+8.5 +10.8
+17.2 +21.9
+2.0 +2.6
Adjustment for current and prior escalation. (Estimating) +0.8 +1.0
RDT&E Subtotal +50.7 +64.6
Procurement |  |  | $M
Current Change Explanations |  |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -3.0
Acceleration of procurement buy profile (Navy) F-18 earlier buy from FY 2015 to FY 2013 (Schedule)
Quantity variance resulting from an increase of 65 MIDS-LVT terminals from 825 to 890 (Air Force). (Other Procurement, Air Force - OPAF) (Subtotal)
Quantity variance resulting from an increase of 65 MIDS-LVT terminals from 825 to 890 (Air Force). (OPAF) (Quantity)
0.0 -4.8
+13.0 +17.6
(+19.2) (+26.0)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) |  | -0.5 |  |  | -0.6
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) |  | -1.1 |  |  | -1.6
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) |  | -4.6 |  |  | -6.2
Quantity variance resulting from an increase of 67 MIDS-LVT terminals and 1346 MIDS |  | 285.2 |  |  | 399.5
JTRS terminals (Air Force). (Aircraft Procurement, Air Force - APAF) (Subtotal) Quantity variance resulting from an increase of 67 MIDS-LVT terminals and 1346
MIDS JTRS terminals (Air Force). (APAF) (Quantity)
(+417.8) (+585.3)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -10 |  |  | -14.1
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) | -21.9 |  |  | -30.8
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -100.7 |  |  | -140.9
Quantity variance resulting from an increase of 2 MIDS-LVT terminals from 425 to 427 | 0.4 |  |  | 0.6
(Army). (Other Procurement, Army - OPA) (Subtotal)
Quantity variance resulting from an increase of 2 MIDS-LVT terminals from 425 to 427 (Army). (OPA) (Quantity)
(+0.6) (+0.8)

## Table 76
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (-0.2) (-0.2)
Quantity variance resulting from an increase of 57 MIDS-LVT terminals and 107 MIDS JTRS terminals (Navy). (Other Procurement, Navy - OPN) (Subtotal)
Quantity variance resulting from an increase of 57 MIDS-LVT terminals and 107 MIDS JTRS terminals (Navy). (OPN) (Quantity)
+33.4 +44.6
(+48.2) (+64.5)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -1 |  | -1.3
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) | -2.3 |  | -3.1
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -11.5 |  | -15.5
Quantity variance resulting from an increase of 6 MIDS-LVT terminals and 26 MIDS JTRS | 6.4 |  | 11
terminals (Navy). (Shipbuilding and Conversion, Navy - SCN) (Subtotal)
Quantity variance resulting from an increase of 6 MIDS-LVT terminals and 26 MIDS JTRS terminals (Navy). (SCN) (Quantity)
(+9.5) (+16.1)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) |  | -0.1 | -0.2
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) |  | -0.4 | -0.8
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) |  | -2.6 | -4.1
Quantity variance resulting from an increase of 72 MIDS LVT terminals and 403 MIDS JTRS |  | 95.2 | 136.8
(Navy). (Aircraft Procurement, Navy - APN) (Subtotal)
Quantity variance resulting from an increase of 72 MIDS LVT terminals and 403 MIDS JTRS(Navy). (APN) (Quantity)
(+141.3) (+203.0)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -3.4 |  | -5
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) | -7.7 |  | -11.1
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -35 |  | -50.1
Quantity variance resulting from a decrease of 2 MIDS-LVT terminals from 60 to 58 (DoD). | -0.4 |  | -0.5
(Procurement Defense Agency - PDA) (Subtotal)
Quantity variance resulting from a decrease of 2 MIDS-LVT terminals from 60 to 58 (DoD). (PDA) (Quantity)
(-0.6) (-0.8)
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (+0.2) (+0.3) Revised estimation due to quantity change and retrofit inclusion (OPAF) (Estimating) (QR) +14.6 +19.5 Revised estimation due to quantity change and retrofit inclusion (OPN) (Estimating) (QR) +14.6 +20.9 Revised estimation due to quantity change and retrofit inclusion (APAF) (Estimating) (QR) +18.8 +26.3 Revised estimation due to quantity change and retrofit inclusion (APN) (Estimating) (QR) +134.9 +198.0 Revised estimation due to quantity change and retrofit inclusion (OPA). (Estimating) (QR) +0.8 +2.2 Revised estimation due to quantity change and retrofit inclusion (SCN) (Estimating) (QR) +6.0 +10.8 Adjustment for current and prior escalation. (Estimating) +0.5 +0.7
Adjustment for current and prior escalation. (Support) -0.2 -0.2
Decrease in other support for MIDS JTRS and MIDS-LVT due to change in estimation of support necessary for MIDS retrofit kits and repairs (Navy). (APN) (Support)
-1.8 -2.2
Increase in initial spares due to estimation change (Navy). (APN) (Support) +1.6 +1.7
FY 2015 Increased support due to additional procurement of MIDS-LVT retrofit kits (Army). (OPA) (Support)
FY 2015 Increased quantity of spares resulting from additional procurement of MIDS-LVT spares (Army). (OPA) (Support)
FY 2015 Decrease in other support due to an estimating correction (Air Force)(APAF) (Support)
+0.7 +0.9
+2.7 +3.5
-1.5 -1.9
Procurement Subtotal +624.9 +882.0
(QR) Quantity Related

## Table 77
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: MIDS Production Contract
Contractor: BAE Systems/Rockwell Collins Data Link Solutions L.L.C. (DLS)
Contractor Location: 350 Collins Rd NE
Cedar Rapids, IA 52498
Contract Number: N00039-10-D-0031
Contract Type: Indefinite Delivery Indefinite Quantity (IDIQ), Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF)
Award Date: March 10, 2010
Definitization Date: March 10, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
134.8 N/A 59 216.4 N/A 619 485.6 485.6
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to exercising options on the IDIQ contract for award of more Delivery Orders (non-Earned Value (EV)).
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (IDIQ/FFP/CPFF) contract.
General Contract Variance Explanation
Cost variance and Schedule variance is not reported for this contract because the contract includes only the production portion, which is FFP and level of effort. The Delivery Orders with EVM are not reported in this Contract value.

## Table 78
Notes
The Production for MIDS-Low Volume Terminal (MIDS-LVT) and MIDS Joint Tactical Radio System (MIDS JTRS) terminals are on new contracts which have been added to the report.
The original value of the contract when awarded was $134.8M in 2010. Since then more IDIQ orders have been awarded and options exercised increasing the value of the contract to $485.6M (although only $216.4M has been obligated).
This production contract includes nonrecurring engineering, supportability, and the manufacture of MIDS-LVT terminals, MIDS JTRS terminals, and associated spares. FMS are not included in the supplemental contract cost information.
This is a Multiple Award Firm Fixed Price IDIQ contract. Delivery Orders are competed between two vendors, ViaSat and DLS. Current Contract Target Price reflects orders awarded to this vendor except for EV efforts which are accounted for separately.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 79
Contract Identification
Appropriation: Procurement
Contract Name: MIDS Production Contract
Contractor: ViaSat, INC
Contractor Location: 6155 El Camino Real
Carlsbad, CA 92009
Contract Number: N00039-10-D-0032
Contract Type: Indefinite Delivery Indefinite Quantity (IDIQ), Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF)
Award Date: March 10, 2010
Definitization Date: March 10, 2010
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
134.8 N/A 76 258.0 N/A 781 527.4 527.4
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to delivery orders not yet awarded.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (IDIQ/FFP/CPFF) contract.
General Contract Variance Explanation
Cost variance and Schedule variance is not reported for this contract because the contract includes only the production portion, which is FFP and level of effort. The Delivery Orders with EVM are not reported in this Contract value.
Notes
The Production for MIDS-Low Volume Terminals (MIDS-LVT) and MIDS Joint Tactical Radio System (MIDS JTRS) terminals are on new contracts which have been added to the report.
The original value of the contract when awarded was $134.8M in 2010. Since then more IDIQ orders have been awarded and options exercised increasing the value of the contract to $527.4M (although only $258M has been obligated).
This production contract includes nonrecurring engineering, supportability, and the manufacture of MIDS-LVT terminals, MIDS JTRS terminals, and associated spares. FMS are not included in the supplemental contract cost information.
This is a Multiple Award Firm Fixed Price IDIQ contract. Delivery Orders are competed between two vendors, ViaSat and Data Link Solutions L.L.C.. Current Contract Target Price reflects orders awarded to this vendor except for Earned Value efforts which are accounted for separately.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 80
Contract Identification
Appropriation: Procurement
Contract Name: MIDS JTRS Production Contract
Contractor: BAE Systems/Rockwell Collins Data Link Solutions L.L.C. (DLS)
Contractor Location: 350 Collins Rd NE
Cedar Rapids, IA 52498
Contract Number: N00039-15-D-0007
Contract Type: Indefinite Delivery Indefinite Quantity (IDIQ), Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF)
Award Date: June 17, 2015
Definitization Date: June 17, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
50.1 N/A 153 50.1 N/A 153 478.6 478.6
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (IDIQ/FFP/CPFF) contract.
General Contract Variance Explanation
Cost and Schedule variance is not reported for this contract, because thus far no delivery order requiring EVM has been awarded.
Notes
This is the first time this contract is being reported.
The overall value with all Options included of this contract is $478.6M. In the future, more IDIQ orders will be awarded and options exercised increasing the current of the contract.
This production contract includes nonrecurring engineering, supportability, and the manufacture of MIDS Joint Tactical Radio terminals. FMS are not included in the supplemental contract cost information.
This is a Multiple Award Firm Fixed Price IDIQ contract. Delivery Orders are competed between two vendors, ViaSat and DLS. Current Contract Target Price reflects orders awarded to this vendor.

## Table 81
Contract Identification
Appropriation: Procurement
Contract Name: MIDS Production Contract
Contractor: ViaSat, INC
Contractor Location: 6155 El Camino Real
Carlsbad, CA 92009
Contract Number: N00039-15-D-0008
Contract Type: Indefinite Delivery Indefinite Quantity (IDIQ), Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF)
Award Date: May 28, 2015
Definitization Date: May 28, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
19.6 N/A 42 19.6 N/A 42 478.6 478.6
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (IDIQ/FFP/CPFF) contract.
General Contract Variance Explanation
Cost and Schedule variance is not reported for this contract, because thus far no delivery order requiring EVM has been awarded.
Notes
This is the first time this contract is being reported.
The overall value with all Options included of this contract is $478.6M. In the future, more IDIQ orders will be awarded and options exercised increasing the current of the contract.
This production contract includes nonrecurring engineering, supportability, and the manufacture of MIDS Joint Tactical Radio System terminal. FMS are not included in the supplemental contract cost information.
This is a Multiple Award Firm Fixed Price IDIQ contract. Delivery Orders are competed between two vendors, ViaSat and DLS. Current Contract Target Price reflects orders awarded to this vendor.

## Table 82
Contract Identification
Appropriation: Procurement
Contract Name: MIDS-LVT Production Contract
Contractor: BAE Systems/Rockwell Collins Data Link Solutions L.L.C. (DLS)
Contractor Location: 350 Collins Rd NE
Cedar Rapids, IA 52498
Contract Number: N00039-15-D-0042
Contract Type: Indefinite Delivery Indefinite Quantity (IDIQ), Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF)
Award Date: August 27, 2015
Definitization Date: August 27, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
14.6 N/A 57 14.6 N/A 57 538.5 538.5
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (IDIQ/FFP/CPFF) contract.
General Contract Variance Explanation
Cost and Schedule variance is not reported for this contract, because thus far no delivery order requiring EVM has been awarded.
Notes
This is the first time this contract is being reported.
The overall value with all Options included of this contract is $538.5M. In the future, more IDIQ orders will be awarded and options exercised increasing the current of the contract.
This production contract includes nonrecurring engineering, supportability, and the manufacture of MIDS-Low Volume Terminal (MIDS-LVT). FMS are not included in the supplemental contract cost information.
This is a Multiple Award Firm Fixed Price IDIQ contract. Delivery Orders are competed between two vendors, ViaSat and DLS. Current Contract Target Price reflects orders awarded to this vendor.

## Table 83
Contract Identification
Appropriation: Procurement
Contract Name: MIDS Production Contract
Contractor: ViaSat, INC
Contractor Location: 6155 El Camino Real
Carlsbad, CA 92009
Contract Number: N00039-15-D-0043
Contract Type: Indefinite Delivery Indefinite Quantity (IDIQ), Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF)
Award Date: August 21, 2015
Definitization Date: August 21, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
5.1 N/A 26 5.1 N/A 26 514.3 514.3
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (IDIQ/FFP/CPFF) contract.
General Contract Variance Explanation
Cost and Schedule variance is not reported for this contract, because thus far no delivery order requiring EVM has been awarded.
Notes
This is the first time this contract is being reported.
The overall value with all Options included of this contract is $514.3M. In the future, more IDIQ orders will be awarded and options exercised increasing the current of the contract.
This production contract includes nonrecurring engineering, supportability, and the manufacture of MIDS-Low Volume Terminal (MIDS-LVT). FMS are not included in the supplemental contract cost information.
This is a Multiple Award Firm Fixed Price IDIQ contract. Delivery Orders are competed between two vendors, ViaSat and DLS. Current Contract Target Price reflects orders awarded to this vendor.

## Table 84
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 520 | 520 | 604 | 86.09%
Production | 4420 | 4440 | 8000 | 55.5%
Total Program Quantity Delivered | 4940 | 4960 | 8604 | 57.65%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
4492.7
3090.3
68.78%
35
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
27
77.14%
3248.8
72.31%
The above data is current as of February 09, 2016.
Total deliveries listed above do not contain EuroMIDS (non-U.S. vendor) terminals (which are not reported in the SAR).

## Table 85
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 26, 2016
Source of Estimate: POE
Quantity to Sustain: 8000
Unit of Measure: Terminal
Service Life per Unit: 20.00 Years
Fiscal Years in Service: FY 1996 - FY 2044
The O&S costs are based on the POE (dated February 26, 2016), which was evaluated by the Air Force Cost Analysis Agency and Naval Center for Cost Analysis in support of the MIDS Joint Tactical Radio System (MIDS JTRS) Full Production & Fielding (FP&F) decision. The quantity of 8,000 includes U.S. only terminals currently fielded and on contract plus known requirements for FY 2015 through FY 2044. This period includes a phase-in, steady state, and phase
-down profile. Development units have no sustainment costs.
The current production terminal procurement estimate increased by a total of 2,149 terminals due to the procurement order from the U.S. Air Force (Platforms: F-15, F-16, F-22).
Sustainment Strategy
The annual operating hours per aircraft for peacetime deployment are estimated to be approximately 400. The annual operating hours per ship for peacetime deployment are estimated to be 3,977. The annual operating hours per Army Ground Air Defense station are estimated to be 2,212.
For Navy aircraft and Army platforms, maintenance is a three-level structure (i.e. Organizational, Intermediate/Direct Support and Depot). For Navy ships and Air Force aircraft platforms it is a two-level structure (i.e. Organizational and Depot). Navy aircraft support costs assume the use of the Consolidated Automated Support System at the Intermediate level of maintenance. The terminal reliability and maintainability characteristics used are consistent with the requirements contained in the ORD.
Antecedent Information
No Antecedent. The MIDS Low Volume Terminal (MIDS-LVT) does not replace an existing DoD system because it provides Link 16 capability to platforms that were unable to employ analogous systems due to space and weight constraints. The MIDS JTRS terminal is a form, fit, and function replacement and upgrade for MIDS-LVT in selected DoD systems.

## Table 86
Annual O&S Costs BY2003 $K
Cost Element |  |  | MIDS Average Annual Cost Per Terminal | [5 empty] | N/A (Antecedent)
Unit-Level Manpower |  |  | 0.25 | [5 empty] | --
Unit Operations |  |  | 0 | [5 empty] | --
Maintenance |  |  | 0.44 | [5 empty] | --
Sustaining Support |  |  | 4.12 | [5 empty] | --
Continuing System Improvements |  |  | 5.43 | [5 empty] | --
Indirect Support |  |  | 0 | [5 empty] | --
Other |  |  | 0 | [5 empty] | --
Total |  |  | 10.24 | [5 empty] | --
Item | Total O&S Cost $M
| MIDS | [8 empty] | N/A (Antecedent)
| Current Production APB Objective/Threshold | [5 empty] | Current Estimate
Base Year |  | 1176.6 |  |  | 1294.3 |  |  | 1638.41 |  |  | N/A
Then Year 1 APB O&S Cost Breach |  | 1573.7 |  |  | N/A |  |  | 2184.5 |  |  | N/A
Equation to Translate Annual Cost to Total Cost
The calculation of total O&S costs is based on total quantities of 8000 multiplied by an economic life of 20 years multiplied by a unit cost of $10.24K per year.
O&S Cost Variance
Category |  |  |  | BY 2003 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
1198.3
Programmatic/Planning Factors 440.1 Increased quantity Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 440.1
Current Estimate 1638.4
Disposal Estimate Details
Date of Estimate:

## Table 87
Source of Estimate:
Disposal/Demilitarization Total Cost (BY 2003 $M):
Disposal costs are not identified at this time.