## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-289
Tactical Tomahawk RGM-109E/UGM-109E Missile (TACTOM)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 9
Schedule 10
Performance 12
Track to Budget 13
Cost and Funding 14
Low Rate Initial Production 20
Foreign Military Sales 21
Nuclear Costs 21
Unit Cost 22
Cost Variance 25
Contracts 29
Deliveries and Expenditures 31
Operating and Support Cost 32

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
Tactical Tomahawk RGM-109E/UGM-109E Missile (TACTOM)
DoD Component
Navy
Responsible Office
CAPT Mark Johnson Program Executive Office
Unmanned Aviation and Strike Weapons 47123 Buse Rd., Bldg. 2272, Rm. 247
Patuxent River, MD 20670-1547
mark.e.johnson@navy.mil
Phone: 301-757-6408
Fax: 301-757-6412
DSN Phone: 757-6408
DSN Fax:
Date Assigned: September 18, 2015
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated August 3, 2004
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated April 11, 2011

## Table 6
Mission and Description
The Tactical Tomahawk RGM-109E/UGM-109E Missile (TACTOM) counters threats against United States Forces by destroying fixed and mobile targets, which include command, control and logistic systems, industrial and other high value targets, and fixed and mobile defense systems. The Tomahawk Weapons System (TWS) consists of the TACTOM missile, the Tomahawk Mission Planning Center (TMPC), and the Tactical Tomahawk Weapons Control System
(TTWCS). TACTOM is an ACAT IC program, TMPC is an ACAT II program, and TTWCS is an ACAT III program. TACTOM provides major modernization to the existing Tomahawk technology by increasing responsiveness and flexibility at a more affordable production unit cost.
Key elements of the TACTOM design are an improved navigation and guidance computer, improved anti-jam Global Positioning System capability, improved responsiveness and flexibility through two-way satellite communications for in-flight re-targeting, a loiter capability, and the ability to send a single-frame Battle Damage Indication Image of over-flown areas prior to impact. Modern manufacturing techniques and Commercial Off-the-Shelf/Government Off-the-Shelf hardware provide this improved capability. Additionally, the life cycle costs are significantly reduced by extending the recertification interval from eight years for the currently fielded Block III Tomahawk to 15 years for TACTOM. TACTOM will maximize the use of existing TWS program and logistic support.

## Table 7
Executive Summary
Program Highlights Since Last Report:
TACTOM has exercised 12 FRP contracts to date, the most recent occurring in FY 2015. The FY 2015 FRP 12 was awarded for a total of 214, which includes 196 surface FY 2015 All-Up-Round (AUR) missiles and 18 surface FY 2014 Buy- to-Budget AUR missiles.
As of February 9, 2016, a total of 3,636 TACTOM missiles have been delivered, which includes 79 FMS missiles for the United Kingdom (UK).
The FY 2015 Overseas Contingency Operations (OCO) supplemental funds appropriated by Congress to replenish 47 TACTOM missiles, fired during Operation Inherent Resolve (OIR), will be procured with the FY 2016 production contract (due to maximum quantity constraints on the FY 2015 contract).
TACTOM deliveries by Raytheon Missile Systems (RMS), Tucson, Arizona, are consistently ahead of contract delivery schedule. As of February 9, 2016, RMS achieved 79 consecutive months of meeting or exceeding the contracted TACTOM missile delivery requirements. The current combined Block III Tomahawk and TACTOM fleet inventory is sufficient to satisfy projected calendar year 2016 U.S. Navy operational load-outs.
Procurement of new missiles has been suspended beginning in FY 2018, three years earlier than the APB dated April 11, 2011. The Department of the Navy will continue to reassess production throughout the FYDP.
The program continues to focus on hardware obsolescence, product improvement and modernization opportunities to meet existing requirements, ensure continued weapons system viability, and keep pace with evolving threats. Initial modernization efforts would be associated with communication upgrades to enable missile communications in non-permissive environments.
There are no significant software-related issues with this program at this time.
History of Significant Developments Since Program Initiation:
June 1998: Milestone II development Contract Award.
August 2002: First Development Flight Test successfully completed. October 3, 2002: LRIP-1 contract awarded for 25 missiles.
January 14, 2003: LRIP-2 contract awarded for 167 missiles. October 2003: Technical Evaluation completed.
March 2004: Successful Operational Evaluation (OPEVAL) completed. OPEVAL included two surface and two underwater test launches, numerous mission planning exercises and a complete 96-hour end-to-end operational scenario.
March 4, 2004: LRIP-3 contract awarded for 210 missiles. Late in FY 2003, a Congressional plus-up provided for an LRIP- 3 procurement to accelerate the replenishment of inventory lost during Operation Iraqi Freedom.
May 2004: IOC achieved.
August 3, 2004: Entered the Production and Deployment Phase based on Milestone III ADM issued by the Assistant Secretary of the Navy (Research, Development, and Acquisition).

## Table 8
August 11, 2004: Operational Requirements Document for Tomahawk Weapons Systems Baseline IV signed. TACTOM is authorized in Chapter 2 of this system level document.
August 18, 2004: FRP contract awarded. A Multi-Year Procurement contract (FY 2004-FY 2008) was signed with Raytheon Missile Systems for a base plus four options, for up to 2200 Block IV Tactical Tomahawk AUR missiles.
September 16, 2004: An in depth Production Verification Test of randomly selected Block IV Tactical Tomahawk AUR LRIP missile was successfully completed at the Naval Surface Weapons Center, Indian Head Division.
March 31, 2009: FRP Contract awarded for base year plus two options, for up to 1050 Block IV Tactical Tomahawk AUR missiles.
September 13, 2011: Additional FY 2011 funding was received through OMNIBUS reprograming action to replenish the 221 Tomahawk missile expenditures during Operation Odyssey Dawn.
June 7, 2012: FRP Contract awarded for base year plus one option to procure up to 740 Block IV Tactical Tomahawk AUR missiles.
September 2014: During Operation Inherent Resolve (OIR), the U.S. Navy fired 47 TACTOM missiles from aboard the USS Arleigh Burke and USS Philippine Sea. Additional FY 2015 OCO supplemental funds were appropriated by Congress for the replenishment of those combat expenditures.
September 24, 2014: FRP contract award for 231 Block IV Tactical Tomahawk AUR missiles. The FY 2014 procurement includes 196 surface and subsurface launched AURs, 20 Torpedo Tube Launched AURs as part of the UK FMS Case, and 15 surface AURs (FY 2013 funded through Buy-to-Budget). The FY 2015 option includes 96 surface AURs and ten surface AURs (FY 2014 funded through Buy-to-Budget).
September 24, 2014: Contract awarded for FRP-11 (231 missiles), and FRP-12 (214 missiles). All deliveries are scheduled from November 2015 to August 2017.

## Table 9
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
The TACTOM RDT&E increases are associated with the revised funding estimates for the Anti-Access/Area Denial software development, hardware development, systems engineering, integration, system testing, and transition documentation to incorporate baseline improvements during mid-life recertification commencing in FY 2019.
A Program Deviation Letter (PDR) was submitted to ASN(RDA) on February 10, 2016. An updated ABP will be submitted within 90 days.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 10
Schedule
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Milestone II Development Contract Award | Jun 1998 | Jun 1998 | Dec 1998 | Jun 1998
LRIP Authorization | Sep 2002 | Sep 2002 | Mar 2003 | Sep 2002
LRIP 2 | Jan 2003 | Jan 2003 | Jul 2003 | Jan 2003
Operational Assessment | Jan 2003 | Jan 2003 | Jul 2003 | Jan 2003
TECHEVAL
Start | Mar 2003 | Mar 2003 | Sep 2003 | Mar 2003
Complete | Oct 2003 | Oct 2003 | Apr 2004 | Oct 2003
OPEVAL
Start | Dec 2003 | Dec 2003 | Jun 2004 | Dec 2003
Complete | Mar 2004 | Mar 2004 | Sep 2004 | Mar 2004
Initial Operational Capability | Mar 2004 | Mar 2004 | Sep 2004 | May 2004
Milestone III | May 2004 | May 2004 | Nov 2004 | Aug 2004
FRP Contract Award | May 2004 | May 2004 | Nov 2004 | Aug 2004

## Table 11
Change Explanations
None
Acronyms and Abbreviations
OPEVAL - Operational Evaluation TECHEVAL - Technical Evaluation

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
MR (%)
0.9 | 0.9 | 0.86 | 0.92 | 0.92
CR (%)
0.96 | 0.96 | 0.94 | 0.97 | 0.97
(Ch-1)
(Ch-1)
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
Operational Requirements Document (ORD) #641-76-04 dated August 11, 2004
Change Explanations
(Ch-1) MR decreased from .93 to .92 from the previous 2014 SAR due to the inclusion of results from Operation Inherent Resolve (OIR). CR decreased from .99 to .97 from the previous 2014 SAR due to the inclusion of results from OIR.
Notes
The data set for Cruise Reliability (CR) and Mission Reliability (MR) includes TACTOM Flight Tests, combat expenditures, and accounting for corrective actions in the missile inventory. Test events include Operational Evaluation, Technical Evaluation, TACTOM Penetrating Vehicle flights, contractor flights, ground tests, and combat expenditures. Corrected failures that meet all of the following criteria have been removed from the data set: root cause of a failure is known, the failure mode is eliminated by hardware or software modification, the modification has been appropriately verified by test, and the modification has been implemented throughout the entire missile population.
Acronyms and Abbreviations
CR - Cruise Reliability MR - Mission Reliability
OIR - Operation Inherent Resolve

## Table 13
Track to Budget
RDT&E
Appn |  | BA | PE
Navy 1319 07 0204229N
Project | Name
0545 Tomahawk Mssn Planning Ctr (Shared)
Notes: Current Estimate includes RDT&E funding for modernization efforts in FY 2014 - FY 2020 to mitigate navigation and communication obsolescence.
2658 Tomahawk Mssn Planning Ctr (Sunk) 2659 Tomahawk Mssn Planning Ctr (Sunk)
Notes
RDT&E funding for TACTOM modernization is a subset of the total RDT&E funding within PE 0204229N.
Procurement
Appn |  | BA | PE
Navy 1507 02 0204229N
Line Item | Name
2101 TOMAHAWK (Shared)
Notes: TACTOM

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 1999 $M | [5 empty] | BY 1999 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 564.9 |  |  | 564.9 | 621.4 |  |  | 623.71 |  | 581 |  |  | 581.9 |  | 663.1
Procurement | 2412.4 |  |  | 4962.6 | 5458.8 |  |  | 4501.1 |  | 2709.3 |  |  | 6303.5 |  | 5727.3
Flyaway | -- |  |  | -- | -- |  |  | 4412.8 |  | -- |  |  | -- |  | 5616.3
Recurring | -- |  |  | -- | -- |  |  | 3956 |  | -- |  |  | -- |  | 4880.9
Non Recurring | -- |  |  | -- | -- |  |  | 456.8 |  | -- |  |  | -- |  | 735.4
Support | -- |  |  | -- | -- |  |  | 88.3 |  | -- |  |  | -- |  | 111
Other Support | -- |  |  | -- | -- |  |  | 88.3 |  | -- |  |  | -- |  | 111
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- |  | 0
MILCON | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Acq O&M | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 |  | 0
Total | 2977.3 |  |  | 5527.5 | N/A |  |  | 5124.8 |  | 3290.3 |  |  | 6885.4 |  | 6390.4
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 51%
The estimate to support this program, like most cost estimates, is built upon a product-oriented work breakdown structure based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which we have been successful.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 10 |  |  |  | 10 |  |  |  |  | 10
Procurement |  | 2780 |  |  |  | 4730 |  |  |  |  | 4215
Total |  | 2790 |  |  |  | 4740 |  |  |  |  | 4225

## Table 15
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2 | 20 | FY | 2021 | To Complete |  |  | Total
RDT&E | 594.5 | 20.2 |  |  | 22.7 | 16.6 | 4.9 |  | 4.2 |  | 0 |  | 0 |  | 663.1
Procurement | 4633.2 | 202.3 |  |  | 186.9 | 37.7 | 37 |  | 38 |  | 38.8 |  | 553.4 |  | 5727.3
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 5227.7 | 222.5 |  |  | 209.6 | 54.3 | 41.9 |  | 42.2 |  | 38.8 |  | 553.4 |  | 6390.4
PB 2016 Total | 5225.8 | 197.4 |  |  | 45.5 | 56.8 | 44.5 |  | 44.7 |  | 0 |  | 0 |  | 5614.7
Delta | 1.9 | 25.1 |  |  | 164.1 | -2.5 | -2.6 |  | -2.5 |  | 38.8 |  | 553.4 |  | 775.7
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 10 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 10
Production | 0 |  | 3966 |  | 149 | 100 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 4215
PB 2017 Total | 10 |  | 3966 |  | 149 | 100 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 4225
PB 2016 Total | 10 |  | 3958 |  | 100 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 4068
Delta | 0 |  | 8 |  | 49 | 100 | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 157

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.8
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 122.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 164.2
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 105.4
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 63
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 57.3
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 19.8
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.2
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 20.2
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 22.7
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.6
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.9
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 4.2
Subtotal |  | 10 | -- |  | -- |  | -- |  | -- |  | -- |  | 663.1

## Table 17
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 1999 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 49.9
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 121.3
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 160.3
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 101.5
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 60.1
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 53.9
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 18.1
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | --
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 1.8
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 7.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14.8
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.4
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 11.7
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 3.4
2020 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 2.9
Subtotal |  | 10 | -- |  | -- |  | -- |  | -- |  | -- |  | 623.7

## Table 18
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | 25 | 45.7 |  | -- |  | 24 |  | 69.7 |  | 2.4 |  | 72.1
2003 |  | 377 | 420.5 |  | -- |  | 13.7 |  | 434.2 |  | 2.9 |  | 437.1
2004 |  | 322 | 344.5 |  | -- |  | -- |  | 344.5 |  | 7.4 |  | 351.9
2005 |  | 298 | 268.5 |  | -- |  | -- |  | 268.5 |  | 8.7 |  | 277.2
2006 |  | 409 | 362.7 |  | -- |  | -- |  | 362.7 |  | 9.9 |  | 372.6
2007 |  | 355 | 343.3 |  | -- |  | -- |  | 343.3 |  | 7.7 |  | 351
2008 |  | 496 | 469.1 |  | -- |  | -- |  | 469.1 |  | 5 |  | 474.1
2009 |  | 207 | 274.5 |  | -- |  | -- |  | 274.5 |  | 5 |  | 279.5
2010 |  | 196 | 268 |  | -- |  | -- |  | 268 |  | 6.3 |  | 274.3
2011 |  | 417 | 541.3 |  | -- |  | -- |  | 541.3 |  | 7.1 |  | 548.4
2012 |  | 196 | 266.5 |  | -- |  | -- |  | 266.5 |  | 9.9 |  | 276.4
2013 |  | 211 | 287.8 |  | -- |  | -- |  | 287.8 |  | 5.8 |  | 293.6
2014 |  | 214 | 301.4 |  | -- |  | -- |  | 301.4 |  | 6.1 |  | 307.5
2015 |  | 243 | 310.9 |  | -- |  | -- |  | 310.9 |  | 6.6 |  | 317.5
2016 |  | 149 | 195.5 |  | -- |  | -- |  | 195.5 |  | 6.8 |  | 202.3
2017 |  | 100 | 180.7 |  | -- |  | -- |  | 180.7 |  | 6.2 |  | 186.9
2018 |  | -- | -- |  | -- |  | 34.7 |  | 34.7 |  | 3 |  | 37.7
2019 |  | -- | -- |  | -- |  | 36 |  | 36 |  | 1 |  | 37
2020 |  | -- | -- |  | -- |  | 36.4 |  | 36.4 |  | 1.6 |  | 38
2021 |  | -- | -- |  | -- |  | 37.2 |  | 37.2 |  | 1.6 |  | 38.8
2022 |  | -- | -- |  | -- |  | 55.6 |  | 55.6 |  | -- |  | 55.6
2023 |  | -- | -- |  | -- |  | 56.4 |  | 56.4 |  | -- |  | 56.4
2024 |  | -- | -- |  | -- |  | 57.2 |  | 57.2 |  | -- |  | 57.2
2025 |  | -- | -- |  | -- |  | 58.1 |  | 58.1 |  | -- |  | 58.1
2026 |  | -- | -- |  | -- |  | 49.8 |  | 49.8 |  | -- |  | 49.8
2027 |  | -- | -- |  | -- |  | 41 |  | 41 |  | -- |  | 41
2028 |  | -- | -- |  | -- |  | 43.9 |  | 43.9 |  | -- |  | 43.9
2029 |  | -- | -- |  | -- |  | 42.7 |  | 42.7 |  | -- |  | 42.7
2030 |  | -- | -- |  | -- |  | 45.2 |  | 45.2 |  | -- |  | 45.2
2031 |  | -- | -- |  | -- |  | 44.4 |  | 44.4 |  | -- |  | 44.4
2032 |  | -- | -- |  | -- |  | 33.1 |  | 33.1 |  | -- |  | 33.1
2033 |  | -- | -- |  | -- |  | 22.3 |  | 22.3 |  | -- |  | 22.3
2034 |  | -- | -- |  | -- |  | 3.7 |  | 3.7 |  | -- |  | 3.7
Subtotal |  | 4215 | 4880.9 |  | -- |  | 735.4 |  | 5616.3 |  | 111 |  | 5727.3

## Table 19
Annual Funding 1507 ¦ Procurement ¦ Weapons Procurement, Navy
Fiscal Year | Quantity |  | BY 1999 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
2002 |  | 25 | 43 |  | -- |  | 22.6 |  | 65.6 |  | 2.3 |  | 67.9
2003 |  | 377 | 388.1 |  | -- |  | 12.6 |  | 400.7 |  | 2.7 |  | 403.4
2004 |  | 322 | 308.8 |  | -- |  | -- |  | 308.8 |  | 6.6 |  | 315.4
2005 |  | 298 | 234.2 |  | -- |  | -- |  | 234.2 |  | 7.6 |  | 241.8
2006 |  | 409 | 308.6 |  | -- |  | -- |  | 308.6 |  | 8.4 |  | 317
2007 |  | 355 | 285.9 |  | -- |  | -- |  | 285.9 |  | 6.4 |  | 292.3
2008 |  | 496 | 384.5 |  | -- |  | -- |  | 384.5 |  | 4.1 |  | 388.6
2009 |  | 207 | 221.8 |  | -- |  | -- |  | 221.8 |  | 4.1 |  | 225.9
2010 |  | 196 | 212.9 |  | -- |  | -- |  | 212.9 |  | 5 |  | 217.9
2011 |  | 417 | 422 |  | -- |  | -- |  | 422 |  | 5.5 |  | 427.5
2012 |  | 196 | 204.7 |  | -- |  | -- |  | 204.7 |  | 7.6 |  | 212.3
2013 |  | 211 | 217.9 |  | -- |  | -- |  | 217.9 |  | 4.4 |  | 222.3
2014 |  | 214 | 225.1 |  | -- |  | -- |  | 225.1 |  | 4.6 |  | 229.7
2015 |  | 243 | 228.8 |  | -- |  | -- |  | 228.8 |  | 4.8 |  | 233.6
2016 |  | 149 | 141.4 |  | -- |  | -- |  | 141.4 |  | 4.9 |  | 146.3
2017 |  | 100 | 128.3 |  | -- |  | -- |  | 128.3 |  | 4.4 |  | 132.7
2018 |  | -- | -- |  | -- |  | 24.1 |  | 24.1 |  | 2.1 |  | 26.2
2019 |  | -- | -- |  | -- |  | 24.6 |  | 24.6 |  | 0.7 |  | 25.3
2020 |  | -- | -- |  | -- |  | 24.3 |  | 24.3 |  | 1.1 |  | 25.4
2021 |  | -- | -- |  | -- |  | 24.5 |  | 24.5 |  | 1 |  | 25.5
2022 |  | -- | -- |  | -- |  | 35.8 |  | 35.8 |  | -- |  | 35.8
2023 |  | -- | -- |  | -- |  | 35.6 |  | 35.6 |  | -- |  | 35.6
2024 |  | -- | -- |  | -- |  | 35.4 |  | 35.4 |  | -- |  | 35.4
2025 |  | -- | -- |  | -- |  | 35.2 |  | 35.2 |  | -- |  | 35.2
2026 |  | -- | -- |  | -- |  | 29.6 |  | 29.6 |  | -- |  | 29.6
2027 |  | -- | -- |  | -- |  | 23.9 |  | 23.9 |  | -- |  | 23.9
2028 |  | -- | -- |  | -- |  | 25.1 |  | 25.1 |  | -- |  | 25.1
2029 |  | -- | -- |  | -- |  | 23.9 |  | 23.9 |  | -- |  | 23.9
2030 |  | -- | -- |  | -- |  | 24.8 |  | 24.8 |  | -- |  | 24.8
2031 |  | -- | -- |  | -- |  | 23.9 |  | 23.9 |  | -- |  | 23.9
2032 |  | -- | -- |  | -- |  | 17.5 |  | 17.5 |  | -- |  | 17.5
2033 |  | -- | -- |  | -- |  | 11.5 |  | 11.5 |  | -- |  | 11.5
2034 |  | -- | -- |  | -- |  | 1.9 |  | 1.9 |  | -- |  | 1.9
Subtotal |  | 4215 | 3956 |  | -- |  | 456.8 |  | 4412.8 |  | 88.3 |  | 4501.1

## Table 20
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 2001-04-12 | 2003-08-26
Approved Quantity | 25 | 402
Reference | LRIP ADM | LRIP III Acquisition Strategy Report/Acquisition Plan (ASR/AP)
Start Year | 2002 | 2002
End Year | 2005 | 2007
Authority to act on LRIP-3 was granted by the Assistant Secretary of the Navy for Research, Development, and Acquisition on August 26, 2003, by way of a signed ASR/AP, vice an ADM. This ASR/AP served to support the FY 2003 Emergency Supplemental funding for 210 TACTOM All-Up-Round LRIP missiles to increase the total LRIP quantity to 402 missiles.
Urgency was due to Operation Iraqi Freedom and the expenditure of a large number of Block III Tomahawk Missiles.

## Table 21
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
United Kingdom | 2014-09-24 | 20 | 26.6 | Torpedo Tube Launch (TTL) TACTOM missiles were purchased in FY 2014; cost includes missiles and ancillary equipment. All United Kingdom (UK) missiles are scheduled to be delivered by 2nd Quarter 2016.
United Kingdom | 2013-03-11 | 4 | 5.7 | TTL TACTOM missiles were purchased in FY 2013; cost includes missiles and ancillary equipment. All UK missiles on contract have been delivered.
United Kingdom | 2006-02-10 | 65 | 64 | TTL TACTOM missiles were purchased in FY 2006; cost includes missiles and ancillary equipment. All UK missiles on contract have been delivered.
Notes
In October 2014, the UK submitted a Letter of Request (LOR) to procure 65 TACTOM TTL All-Up-Rounds (AUR) from United States Navy (USN) stock starting in FY 2015. A Letter of Offer and Acceptance (LOA) for 20 of the 65 AURs was signed by the UK in March 2015. Ownership of the 20 AURs has been transferred to the UK. PMA-280 has worked with the Comptroller and other Naval Air Systems Command (NAVAIR) competencies to establish a Replacement Program. The FMS funds associated with the 20 assets that have been sold to the UK have been reprogrammed to Weapon Procurement Navy (WPN). The WPN funds will be utilized for a USN TACTOM missile procurement starting in FY 2016.
Acronyms and Abbreviations
AUR - All-Up-Round
LOA - Letter of Acceptance LOR - Letter of Request
NAVAIR - Naval Systems Air Command TTL - Torpedo Tube Launch
UK - United Kingdom USN - United States Navy
WPN - Weapon Procurement Navy
Nuclear Costs
None

## Table 22
Unit Cost
Unit Cost Report
Item |  | BY 1999 $M | BY 1999 $M |  | % Change
|  | Current UCR Baseline (Apr 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 5527.5 |  |  | 5124.8
Quantity | 4740 |  |  | 4225
Unit Cost | 1.166 |  |  | 1.213 |  | 4.03
Average Procurement Unit Cost
Cost | 4962.6 |  |  | 4501.1
Quantity | 4730 |  |  | 4215
Unit Cost | 1.049 |  |  | 1.068 |  | 1.81
Item |  | BY 1999 $M | BY 1999 $M |  | % Change
|  | Original UCR Baseline (Sep 1999 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 1683.7 |  |  | 5124.8
Quantity | 1365 |  |  | 4225
Unit Cost | 1.233 |  |  | 1.213 |  | -1.62
Average Procurement Unit Cost
Cost | 1158.4 |  |  | 4501.1
Quantity | 1353 |  |  | 4215
Unit Cost | 0.856 |  |  | 1.068 |  | 24.77

## Table 23
Unit Cost History
Item | [7 empty] | Date |  |  |  |  | BY 1999 $M | [6 empty] | TY $M
[13 empty] | PAUC |  | APUC |  |  |  |  | PAUC |  |  |  | APUC
Original APB |  |  |  |  | Sep 1999 | [7 empty] | 1.233 |  |  |  | 0.856 |  |  |  | 1.365 |  |  |  | 0.984
APB as of January 2006 |  |  |  |  | Apr 2005 | [7 empty] | 1.076 |  |  |  | 0.913 |  |  |  | 1.237 |  |  |  | 1.069
Revised Original APB |  |  |  |  | N/A | [7 empty] | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | N/A
Prior APB |  |  |  |  | Apr 2005 | [7 empty] | 1.076 |  |  |  | 0.913 |  |  |  | 1.237 |  |  |  | 1.069
Current APB |  |  |  |  | Apr 2011 | [7 empty] | 1.166 |  |  |  | 1.049 |  |  |  | 1.453 |  |  |  | 1.333
Prior Annual SAR |  |  |  |  | Dec 2014 | [7 empty] | 1.14 |  |  |  | 0.991 |  |  |  | 1.38 |  |  |  | 1.222
Current Estimate |  |  |  |  | Dec 2015 | [7 empty] | 1.213 |  |  |  | 1.068 |  |  |  | 1.513 |  |  |  | 1.359
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Development Estimate | Changes | [21 empty] | PAUC Production Estimate
| Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  |  | Oth |  | Spt |  |  | Total
1.365 -0.015 0.324 0.117 0.000 -0.716 0.000 0.104 -0.186 1.179
Current SAR Baseline to Current Estimate (TY $M)
PAUC Production Estimate |  | Changes | [19 empty] | PAUC Current Estimate
|  | Econ |  | Qty |  |  | Sch |  |  | Eng |  | Est |  | Oth | Spt |  |  | Total
1.179 0.025 -0.173 0.062 0.016 0.388 0.000 0.016 0.334 1.513

## Table 24
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Development Estimate | Changes | [11 empty] | APUC Production Estimate
| Econ | Qty |  | Sch | Eng |  |  | Est |  | Oth | Spt | Total
0.984 -0.015 0.325 0.097 0.000 -0.520 0.000 0.104 -0.009 0.975
Current SAR Baseline to Current Estimate (TY $M)
APUC Production Estimate | Changes | [11 empty] | APUC Current Estimate
| Econ | Qty |  | Sch |  | Eng |  |  | Est | Oth | Spt | Total
0.975 0.025 -0.104 0.062 0.016 0.369 0.000 0.016 0.384 1.359
SAR Baseline History
Item |  |  | SAR Planning Estimate |  |  |  | SAR Development Estimate |  |  |  | SAR Production Estimate |  |  | Current Estimate
Milestone I |  |  | N/A |  |  |  | N/A |  |  |  | N/A |  |  | N/A
Milestone II |  |  | N/A |  |  |  | Jun 1998 |  |  |  | Jun 1998 |  |  | Jun 1998
Milestone III |  |  | N/A |  |  |  | Jun 2003 |  |  |  | May 2004 |  |  | Aug 2004
IOC |  |  | N/A |  |  |  | Apr 2003 |  |  |  | Mar 2004 |  |  | May 2004
Total Cost (TY $M) |  |  | N/A |  |  |  | 1863.4 |  |  |  | 3290.3 |  |  | 6390.4
Total Quantity |  |  | N/A |  |  |  | 1365 |  |  |  | 2790 |  |  | 4225
PAUC |  |  | N/A |  |  |  | 1.365 |  |  |  | 1.179 |  |  | 1.513

## Table 25
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
581.0 2709.3 -- 3290.3
Economic |  | -- |  | 112.3 |  | -- |  | 112.3
Quantity |  | -- |  | 853.1 |  | -- |  | 853.1
Schedule |  | -- |  | 251.1 |  | -- |  | 251.1
Engineering |  | -- |  | 63.2 |  | -- |  | 63.2
Estimating |  | 73.6 |  | 913.7 |  | -- |  | 987.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 57.4 |  | -- |  | 57.4
Subtotal |  | 73.6 |  | 2250.8 |  | -- |  | 2324.4
Current Changes Economic |  | -0.1 |  | -7.6 |  | -- |  | -7.7
Quantity |  | -- |  | 105.5 |  | -- |  | 105.5
Schedule |  | -- |  | 11.8 |  | -- |  | 11.8
Engineering |  | -- |  | 3.1 |  | -- |  | 3.1
Estimating |  | 8.6 |  | 643.7 |  | -- |  | 652.3
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 10.7 |  | -- |  | 10.7
Subtotal |  | 8.5 |  | 767.2 |  | -- |  | 775.7
Total Changes |  | 82.1 |  | 3018 |  | -- |  | 3100.1
CE - Cost Variance |  | 663.1 |  | 5727.3 |  | -- |  | 6390.4
CE - Cost & Funding |  | 663.1 |  | 5727.3 |  | -- |  | 6390.4

## Table 26
Summary BY 1999 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
564.9 2412.4 -- 2977.3
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 630.8 |  | -- |  | 630.8
Schedule |  | -- |  | 205.1 |  | -- |  | 205.1
Engineering |  | -- |  | 46.1 |  | -- |  | 46.1
Estimating |  | 52.3 |  | 680.1 |  | -- |  | 732.4
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 47 |  | -- |  | 47
Subtotal |  | 52.3 |  | 1609.1 |  | -- |  | 1661.4
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 74.6 |  | -- |  | 74.6
Schedule |  | -- |  | 8.5 |  | -- |  | 8.5
Engineering |  | -- |  | 2.2 |  | -- |  | 2.2
Estimating |  | 6.5 |  | 386.6 |  | -- |  | 393.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 7.7 |  | -- |  | 7.7
Subtotal |  | 6.5 |  | 479.6 |  | -- |  | 486.1
Total Changes |  | 58.8 |  | 2088.7 |  | -- |  | 2147.5
CE - Cost Variance |  | 623.7 |  | 4501.1 |  | -- |  | 5124.8
CE - Cost & Funding |  | 623.7 |  | 4501.1 |  | -- |  | 5124.8
Previous Estimate: December 2014

## Table 27
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -0.1
Revised estimate to reflect updated Anti-Access/Area Denial estimates which include: software development, hardware development, systems engineering, integration, system testing, and transition documentation. (Estimating)
+6.5 +8.6
RDT&E Subtotal +6.5 +8.5
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -7.6
Quantity variance resulting from an increase of 157 TACTOM missiles from 4,058 to 4,215. (Subtotal)
Quantity variance resulting from an increase of 157 TACTOM missiles from 4,058 to 4,215. (Quantity)
+146.6 +205.1
(+105.4) (+147.5)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) (+8.4) (+11.7) Allocation to Engineering resulting from Quantity change. (Engineering) (QR) (+2.2) (+3.1) Allocation to Estimating resulting from Quantity change. (Estimating) (QR) (+30.6) (+42.8)
Additional Quantity Variance due to the procurement of 49 additional missiles in FY 2016 and 100 additional TACTOM missiles in FY 2017. (Quantity)
Schedule Variance resulting from an increase of 8 TACTOM missiles in FY 2014 and 49 TACTOM missiles in FY 2016. (Schedule)
Additional Schedule Variance resulting from an increase of 8 TACTOM missiles in FY 2014 added through Buy-to-Budget authority. (Schedule)
Additional Schedule Variance resulting from addition of 49 TACTOM missiles in FY 2016, returning program to Minimum Sustaining Rate. (Schedule)
Increase due to revised obsolescence activities in FY 2015 and FY 2016 due to production restoral in FY 2017. (Estimating)
Reduction to obsolescence to account for increased MK14 canister procurement in FY 2014 due to increased Buy-to-Budget quantities. (Estimating)
-30.8 -42.0
0.0 -0.4
-7.4 -9.9
+7.5 +10.4
+5.8 +7.9
-0.7 -1.0
Increase due to the inclusion of modernization kits FY 2021 - FY 2034. (Estimating) +348.6 +590.6
Revised estimate of production line shutdown costs FY 2016 - FY 2019 due to the inclusion of TACTOM missile production in FY 2017. (Estimating)
Increase due to revised cost estimate of MK14 canisters associated with additional TACTOM missiles in FY 2016 and FY 2017. (Estimating)
-5.1 -6.4
+10.1 +14.1
Revised estimate to reflect actuals. (Estimating) -0.4 -0.5
Increase due to production support costs associated with production of TACTOM missiles in FY 2017. (Estimating) (QR)
Decrease due to FY 2016 Congressional reduction for production support funding carryover. (Estimating)
Revised estimate of modernization kits in FY 2018 and FY 2019 to account for the inclusion of production in FY 2017. Revised estimate of modernization kits in FY 2020 due to Navy Working Capital Fund rate change. (Estimating)
+14.5 +20.5
-1.5 -2.1
-17.9 -25.8
Decrease due to reduction in negotiated TACTOM missile hardware cost. (Estimating) -2.6 -3.6 Increase due to revised cost estimate of MK14 canisters associated with 8 additional +0.6 +1.0

## Table 28
TACTOM missiles in FY 2014 obtained through Buy-to-Budget authority. (Estimating)
Increase in Other Support due to the addition of Range Safety System kits in Support Costs in FY 2016 - FY 2018. (Subtotal)
+7.6 +10.5
Increase in Other Support due to the inclusion of 157 TACTOM Missiles. (Support) (+1.2) (+1.6)
Increase in Other Support due to the addition of Range Safety System kits in Support Costs in FY 2016 - FY 2018. (Support)
(+6.4) (+8.9)
Adjustment for current and prior escalation. (Estimating) Adjustment for current and prior escalation. (Support) | +4.6 +0.1 | +6.2 +0.2
Procurement Subtotal (QR) Quantity Related | 479.6 | 767.2

## Table 29
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: BLK IV TACTOM FRP FY14-15
Contractor: Raytheon Missile Systems
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85747
Contract Number: N00019-14-C-0075
Contract Type: Firm Fixed Price (FFP)
Award Date: September 24, 2014
Definitization Date: September 24, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
251.1 N/A 231 512.3 N/A 331 539.0 539.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the award of the Composite Capsule Launching System (CCLS), and an option exercise for 100 surface launched All-Up-Rounds.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
The FY 2014 base contract was awarded for the procurement of 231 missiles at a price of $251.1M. The FY 2014 procurement includes 196 surface and subsurface launched All-Up-Rounds (AUR), 20 torpedo tube launched AURs as part of the United Kingdom Foreign Military Sales case, and 15 surface AURs (FY 2013 funded through Buy-to-Budget).
The FY 2015 option exercise for 100 surface AURs was awarded on January 29, 2015. A modification to this option was issued on February 26, 2015, which included 114 additional surface AURs. These missiles were funded by a mix of FY 2014 Buy-to-Budget and FY 2015 funds. This modification increased the contract by $90,601,839.46 to $506,979,383.46 (when awarded in February).
Current contract price includes United States Navy missiles and subsurface variant capsules.

## Table 30
Contract Identification
Appropriation: Procurement
Contract Name: BLK IV TACTOM FRP FY12-13
Contractor: Raytheon Missile Systems
Contractor Location: 1151 East Hermans Road
Tucson, AZ 85747
Contract Number: N00019-12-C-2000
Contract Type: Firm Fixed Price (FFP)
Award Date: June 07, 2012
Definitization Date: June 07, 2012
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
337.8 N/A 361 706.0 N/A 617 710.0 710.0
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the FY 2013 procurement option being exercised for an additional 252 United States Navy (USN) missiles and four United Kingdom missiles.
Cost and Schedule Variance Explanations
Cost and Schedule Variance reporting is not required on this (FFP) contract.
Notes
The FY 2012 base contract was awarded for the procurement of 361 missiles at a price of $337.8M The FY 2013 contract option for USN missiles was exercised in December 2012. An additional option was also exercised in March 2013 to procure four FMS missiles resulting in an increase of the total contract procurement quantity to 617 missiles (USN and FMS).
Operation Odyssey Dawn replenishment missiles were procured utilizing the FY 2012 procurement contract.
This contract is more than 90% complete; therefore, this is the final report for this contract.

## Table 31
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 10 | 10 | 10 | 100%
Production | 3549 | 3557 | 4215 | 84.39%
Total Program Quantity Delivered | 3559 | 3567 | 4225 | 84.43%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
6390.4
4697.7
73.51%
37
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
19
51.35%
5450.2
85.29%
The above data is current as of February 09, 2016.
As of February 9, 2016 a total of 3636 TACTOM missiles have been delivered, which includes 79 FMS missiles for the United Kingdom.

## Table 32
Operating and Support Cost
Cost Estimate Details
Date of Estimate: January 20, 2016
Source of Estimate: POE
Quantity to Sustain: 3779
Unit of Measure: Total Quantity
Service Life per Unit: 30.00 Years
Fiscal Years in Service: FY 2004 - FY 2049
In January 2016, the TACTOM O&S cost estimate was re-estimated to account for reduced O&M funding in the PB 2017 FYDP and data received through TACTOM missile recertification studies conducted in FY 2015.
The current cost estimate includes actual and projected cost for operation and sustainment of all 4,215 procured missiles, beginning in FY 2004, with cost estimate projections extending to FY 2049. The total service life of a TACTOM is anticipated to be 30 years, which includes the initial 15 years of warranty coverage after delivery and an additional 15 years of service life following recertification. The "Quantity to Sustain" (3,779 shown above) is the forecasted inventory anticipated to sustain beyond recertification for the second 15 years of life, which includes reductions across the life cycle for actual and projected missile expenditures. This quantity is increased from FY 2014 due to the addition of 157 missiles added in the FY 2017 PB through Congressional add and Buy-to-Budget authority. Actual O&S costs were utilized from FY 2004 through FY 2015, and revised budget estimate covers FY 2016 through FY 2049.
The average annual O&S requirement in the PB 2017 FYDP decreased from previous years, causing a decrease in the projected O&M Core requirements funding through the end of the TACTOM life cycle. The revised missile recertification quantity profile shifts recertification costs later than previous estimates, resulting in an increase in the the TY costs due to inflation.
Sustainment Strategy
The sustainment strategy includes maintenance and recertification costs of the All-Up-Round (AUR) and an Operational flight test program to track Tomahawk Weapon System performance. TACTOM Sustainment Strategy is based on the original Tomahawk Program "Wooden Round" concept, which relies upon a 15 year missile warranty, and features limited missile maintenance outside of that provided by the Original Equipment Manufacturer (OEM). The total service life of a TACTOM is anticipated to be 30 years, which includes the initial 15 years of warranty coverage after delivery and an additional 15 years of service life following recertification. The OEM operates a TACTOM depot activity and is responsible for conducting the majority of the maintenance for TACTOM, of which efforts are largely covered by the 15 year warranty. The TACTOM recertification program is scheduled to begin inducting missiles in FY 2019 (per FY 2016 PB submission). The TACTOM recertification program will continue until 3,779 missiles are recertified or expended. Organizational level maintenance is limited to visual inspections, missile inventory checks (surface only), Mode 7 alignment confidence checks (submarine only) and minor unscheduled maintenance (i.e. corrosion control). Intermediate level maintenance is limited to missile identification checks, receipt and transfer inspections, electrical continuity, and nitrogen pressure checks.
Antecedent Information
Block III Tomahawk is the antecedent system of TACTOM. Antecedent costs were derived from average annual actual cost spanning 24 years. The source of this data is the Block III Tomahawk budget. Peak inventory for Block III was 1,296 missiles. The Block III Tomahawk service life was also 30 years.

## Table 33
Annual O&S Costs BY1999 $M
Cost Element |  | TACTOM Average Annual Cost Per Total Quantity |  |  |  | Tomahawk Block III (Antecedent) Average Annual Cost Per Total Quantity
Unit-Level Manpower |  | 0 |  |  |  | 0
Unit Operations |  | 0 |  |  |  | 0
Maintenance |  | 0 |  |  |  | 0
Sustaining Support |  | 32.666 |  |  |  | 36.6
Continuing System Improvements |  | 0 |  |  |  | 0
Indirect Support |  | 0 |  |  |  | 0
Other |  | 21.011 |  |  |  | 65.4
Total |  | 53.677 |  |  |  | 102
Missile recertification cost (shown as "other" in the unitized cost summary above) is the estimated contract cost for the OEM to recertify the inventory, divided by 45 years. The recertification program, however, is only scheduled to last for approximately 17 of the 45 years, so the unitized recertification cost (“other”) understates the expected annual cost
to recertify TACTOM missiles.
In December 2015, the TACTOM recertification estimate was re-estimated to reflect data received from recertification studies conducted in 2015, and revised quantity phasing to meet budget constraints. The revision also incorporated the recertification cost of the MK45 Capsule, which was not part of the previous estimate. The total O&S cost estimate increase therefore reflects an improved understanding of the scope of the TACTOM recertification effort.
The actual number of recertifications per year may not match the procurement profile. While missiles should be returned for recertification not later than 15 years following delivery, the estimate recognizes historical budget constraints. This anticipated annual limit will cause schedule variances between optimal recertification dates and actual recertification dates, resulting in a total recertification program that will extend beyond 15 years.
Item | Total O&S Cost $M
| TACTOM | [5 empty] | Tomahawk Block III (Antecedent)
| Current Production APB Objective/Threshold |  |  | Current Estimate
Base Year | N/A |  | N/A |  | 2415.5 |  | 3058.4
Then Year | N/A |  | N/A |  | 4145.7 |  | N/A
Equation to Translate Annual Cost to Total Cost
Average Annual Cost Per Total Quantity = Total O&S Cost / Inventory Service Life
$53.677M = $2,415.5M / 45
The unitized costs shown above are the Base Year O&S totals shown above, divided by the expected 45 years of inventory service life (FY 2004 - FY 2049).
O&S Cost Variance

## Table 34
Category | BY 1999 $M | Change Explanations
Prior SAR Total O&S Estimates - Dec 2014 SAR
2522.9
Programmatic/Planning Factors -107.4 The total O&M funding in the PB 2017 FYDP is, on
average, less than annual funding levels in previous years. This decreased the projected O&M funding levels through the remainder of the TACTOM life cycle, resulting in a decrease.
Cost Estimating Methodology 0.0
Cost Data Update 0.0
Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes -107.4
Current Estimate 2415.5
Disposal Estimate Details
Date of Estimate: January 20, 2016
Source of Estimate: POE
Disposal/Demilitarization Total Cost (BY 1999 $M): Total costs for disposal of all Total Quantity are 50.1
The U.S. Army has responsibility for disposal of all ordnance.