## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-180
DDG 51 Arleigh Burke Class Guided Missile Destroyer (DDG 51)
As of FY 2017 President's Budget
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Common Acronyms and Abbreviations for MDAP Programs 3
Program Information 5
Responsible Office 5
References 5
Mission and Description 6
Executive Summary 7
Threshold Breaches 8
Schedule 9
Performance 12
Track to Budget 15
Cost and Funding 16
Low Rate Initial Production 30
Foreign Military Sales 31
Nuclear Costs 31
Unit Cost 32
Cost Variance 35
Contracts 38
Deliveries and Expenditures 46
Operating and Support Cost 47

## Table 3
Common Acronyms and Abbreviations for MDAP Programs
Acq O&M - Acquisition-Related Operations and Maintenance ACAT - Acquisition Category
ADM - Acquisition Decision Memorandum APB - Acquisition Program Baseline APPN - Appropriation
APUC - Average Procurement Unit Cost
$B - Billions of Dollars
BA - Budget Authority/Budget Activity Blk - Block
BY - Base Year
CAPE - Cost Assessment and Program Evaluation CARD - Cost Analysis Requirements Description CDD - Capability Development Document
CLIN - Contract Line Item Number CPD - Capability Production Document CY - Calendar Year
DAB - Defense Acquisition Board DAE - Defense Acquisition Executive
DAMIR - Defense Acquisition Management Information Retrieval DoD - Department of Defense
DSN - Defense Switched Network
EMD - Engineering and Manufacturing Development EVM - Earned Value Management
FOC - Full Operational Capability FMS - Foreign Military Sales FRP - Full Rate Production
FY - Fiscal Year
FYDP - Future Years Defense Program ICE - Independent Cost Estimate
IOC - Initial Operational Capability Inc - Increment
JROC - Joint Requirements Oversight Council
$K - Thousands of Dollars
KPP - Key Performance Parameter LRIP - Low Rate Initial Production
$M - Millions of Dollars
MDA - Milestone Decision Authority
MDAP - Major Defense Acquisition Program MILCON - Military Construction
N/A - Not Applicable
O&M - Operations and Maintenance
ORD - Operational Requirements Document OSD - Office of the Secretary of Defense O&S - Operating and Support
PAUC - Program Acquisition Unit Cost

## Table 4
PB - President’s Budget PE - Program Element
PEO - Program Executive Officer PM - Program Manager
POE - Program Office Estimate
RDT&E - Research, Development, Test, and Evaluation SAR - Selected Acquisition Report
SCP - Service Cost Position TBD - To Be Determined TY - Then Year
UCR - Unit Cost Reporting
U.S. - United States
USD(AT&L) - Under Secretary of Defense (Acquisition, Technology and Logistics)

## Table 5
Program Information
Program Name
DDG 51 Arleigh Burke Class Guided Missile Destroyer (DDG 51)
DoD Component
Navy
Responsible Office
CAPT Mark R. Vandroff, USN
Program Executive Office Ships (PEO Ships) 1333 Isaac Hull Avenue SE
Washington, DC 20376-2301
mark.vandroff@navy.mil
Phone: | 202-781-2177
Fax: | 202-781-0021
DSN Phone: | 336-2177
DSN Fax: Date Assigned: | May 23, 2011
References
SAR Baseline (Production Estimate)
Decision Coordinating Paper #1337 Revision 1, Change 1 of August 22, 1986
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated May 10, 2011

## Table 6
Mission and Description
The DDG 51 Arleigh Burke Class Guided Missile Destroyer (DDG 51) is a multi-mission guided missile destroyer designed to operate offensively and defensively, independently, or as units of Carrier Strike Groups, Expeditionary Strike Groups, and Missile Defense Action Groups in multi-threat environments that include air, surface, and subsurface threats. These ships will respond to Low Intensity Conflict/Coastal and Littoral Offshore Warfare scenarios as well as open ocean conflict providing or augmenting power projection, forward presence requirements, and escort operations at sea. Flight IIA ships have introduced new capabilities, Cooperative Engagement Capability (CEC) and a MK-45 Gun that will provide improved air and anti-missile defense and improved land attack.
The DDG 51 Class ships provide outstanding combat capability and survivability characteristics while considering procurement and lifetime support costs. They feature extraordinary seakeeping and low observability characteristics.
The DDG 51 features the AEGIS Weapon System (AWS), which has quick reaction time, high firepower, and improved Electronic Countermeasures capability in Anti-Air Warfare (AAW). The ships' Anti-Submarine Warfare (ASW) System provides superior long range multi-target detection and engagement capability with two embarked Light Airborne Multi- Purpose System MK-III helicopters (Flight IIA, DDG 79 and follow-on ships). DDG 91 and follow-on ships employ the littoral variant SPY-1D(V). The Advanced Tomahawk Weapon Control System (DDGs 79-95) and the Tactical Tomahawk Weapons Control System (DDG 96 and follow-on ships) allow employment of multiple variants of Tomahawk missiles for strike warfare. The MK-45 gun weapon system provides significant capability for surface warfare, land attack, and air defense. The CEC is being installed on DDG 51 Class Ships to promote Network Centric Warfare capability. The AWS is the heart of an integrated combat system that provides area coverage and command/control focus in all dimensions of Naval Warfighting and Joint Military Operations: AAW; ASW; Anti-Surface Warfare; Command, Control, Communications, Computers & Intelligence; and Strike Warfare. DDG 113 and follow ships will provide Integrated Air and Missile Defense and work with other Ballistic Missile Defense assets.
Structural features are an all steel hull and deckhouse with vital spaces protected and located within the hull. The ship employs a gas turbine propulsion system with Controllable Pitch Propellers similar to the CG 47 class.
The DDG 51 Destroyer is being produced to fulfill a surface combatant requirement to provide air dominance, integrated air and missile defense, maritime dominance and land attack capability.

## Table 7
Executive Summary
The DDG 51 Program has successfully delivered 62 ships (DDG 51 – 112) since program inception in 1985. Subsequent to the restart of the program in 2009, annual, annual with option, or multi-year procurement contracts for 14 additional ships between FY 2010 – FY 2017 have been awarded.
The Navy has instituted several initiatives to reduce cost associated with FY 2010 and follow DDG 51 Class ships including the increased the use of competitive contracts in lieu of sole source contracts. Other cost savings initiatives include the use of Multi-Year Procurements (MYP) with Profit Related to Offer (PRO) concept, refurbished assets from retiring Navy ships and leveraging Government Furnished Equipment (GFE) contracts across multiple ship classes to obtain better prices across the Navy.
The Navy is currently developing the next baseline upgrade referred to as Flight III which will provide enhanced surface combatant Integrated Air Missile Defense (IAMD) capability. The upgrade will primarily consist of the integration of the SPY- 6 radar, being developed by Raytheon, along with the necessary electrical power and cooling and ship stability modifications. Flight III will be introduced on a FY 2016 ship. Congress provided an additional $1B in FY 2016 to support incremental funding for an additional DDG 51 Class ship.
The FY 2017 PB submission requests $3,211.3M Full Funding for two ships in FY 2017, and $16M Cost to Complete for the Government responsible portion for the shipbuilding construction contract overrun for DDG 115.
The DDG 51 Class Program has achieved the following significant production milestones since the last report:
• DDG 119 (DELBERT BLACK) Start Fabrication completed on July 6, 2015 in Pascagoula, MS.
• DDG 118 (DANIEL INOUYE) Start Fabrication completed on August 2, 2015 in Bath, ME.
• DDG 113 (JOHN FINN) AEGIS Light Off conducted on September 7, 2015 in Pascagoula, MS.
• DDG 117 (PAUL IGNATIUS) Lay Keel completed on September 11, 2015 in Pascagoula, MS.
• DDG 115 (RAFAEL PERALTA) Launch completed on November 1, 2015 in Bath, ME.
• DDG 116 (THOMAS HUDNER) Lay Keel completed on November 6, 2015 in Bath, ME.
• DDG 114 (RALPH JOHNSON) Launch completed on December 12, 2015 in Pascagoula, MS.
• DDG 115 (RAFAEL PERALTA) AEGIS Light Off conducted on December 17, 2015 in Bath, ME.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for contracts included in this SAR are For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).
There are no significant software-related issues with this program at this time.

## Table 8
Threshold Breaches
APB Breaches
Explanation of Breach
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None
RDT&E Cost Breach is due to increased development and integration costs associated with the introduction of new Standard Missile-6 Block (BLK) IA and Naval Integrated Fire Control - Counter Air (NIFCCA) 2019 warfighting capabilities into AEGIS Advanced Capability Build (ACB) 16, and development and integration of NIFC- CA 2019, Ballistic Missile Defense improved threat set, Surface Electronic Warfare Improvement Program BLK II, and Combat ID warfighting capabilities into AEGIS ACB 20.
Procurement Cost Breach is due to the increase in ship quantities from approved APB to current estimate (86 ships vice 75 ships). The 2015 SAR adds 4 additional ships (2 in FY 2021 and 2 in FY 2022).
O&S Cost Breach due to increase in ship quantity from last approved APB to current estimate (86 vice 75 ships) and corrected service life per unit calculations for FLT IIA and FLT III (increase of 5 years from 35 to 40 for FLT IIA/FLT III ships). The 2012 SAR added 2 ships (FY 2018), the 2013 SAR added 3 ships (1 in FY 2016 and 2 in FY 2019),
the 2014 SAR added 2 ships (FY 2020), and the 2015 SAR adds 4 additional ships (FY 2021 and FY 2022).
Updated Program Deviation Report and APB are in process.
Nunn-McCurdy Breaches

## Table 9
Schedule

## Table 10
Schedule Events
Events | SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Current Estimate
Complete Concept Design | N/A | Dec 1980 | Jun 1981 | Dec 1980
DNSARC I | Jun 1981 | Jun 1981 | Dec 1981 | Jun 1981
Complete Preliminary Design | N/A | Mar 1983 | Sep 1983 | Mar 1983
DSARC II | Dec 1983 | Dec 1983 | Jun 1984 | Dec 1983
Complete Contract Design | N/A | Jun 1984 | Dec 1984 | Jun 1984
DDG 51 Contract Award | Apr 1985 | Apr 1985 | Oct 1985 | Apr 1985
Milestone IIIA | Oct 1986 | Oct 1986 | Apr 1987 | Oct 1986
DDG 52 Contract Award | Jan 1987 | May 1987 | Nov 1987 | May 1987
DDG 53 Contract Award | N/A | Sep 1987 | Mar 1988 | Sep 1987
Lay Keel DDG 51 | N/A | Dec 1988 | Jun 1989 | Dec 1988
Launch DDG 51 | N/A | Sep 1989 | Mar 1990 | Sep 1989
DDG 51 Delivery | N/A | Apr 1991 | Oct 1991 | Apr 1991
Launch DDG 52 | N/A | Mar 1991 | Sep 1991 | May 1991
Organic Support Available | N/A | Jul 1991 | Jan 1992 | Jul 1991
Depot Support Available | N/A | Jul 1991 | Jan 1992 | Jul 1991
OPEVAL | N/A | Feb 1992 | Aug 1992 | Feb 1992
DDG 52 Delivery | N/A | May 1992 | Nov 1992 | Oct 1992
DDG 51 IOC | Oct 1990 | Feb 1993 | Aug 1993 | Feb 1993
DDG 53 Delivery | N/A | Feb 1993 | Aug 1993 | Aug 1993
Milestone IV | N/A | Apr 1993 | Oct 1993 | Oct 1993
DDG 51 Flight IIA Contract Award | N/A | Mar 1994 | Sep 1994 | Jul 1994
Complete ESSM COEA | N/A | Nov 1994 | May 1995 | Nov 1994
ESSM Milestone IV | N/A | Nov 1994 | May 1995 | Nov 1994
SH-60B Hellfire IOC | N/A | Dec 1997 | Jan 1999 | Dec 1997
DDG 51 Flight IIA Delivery | N/A | May 2000 | Nov 2000 | May 2000
DDG 51 Flight IIA IOC | N/A | Oct 2001 | Apr 2002 | Oct 2001
ESSM IOC | N/A | Jan 2004 | Jul 2004 | Feb 2004
Change Explanations
None

## Table 11
Acronyms and Abbreviations
COEA - Cost and Operational Effectiveness Analysis
DNSARC - Department of the Navy System Acquisition Review Council DSARC - Defense System Acquisition Review Council
ESSM - Evolved Sea Sparrow Missile OPEVAL - Operational Evaluation

## Table 12
Performance
Performance Characteristics
SAR Baseline Production Estimate | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
SHIP:
Length (ft)
466 | N/A | N/A | Baseline Dependent | Baseline Dependent
Beam (ft)
59 | N/A | N/A | 59 | 59
Navigational Draft (ft)
30.6 | N/A | N/A | 31 | 31
Displacement (long tons)
8300 | N/A | N/A | 9300 | 9300
Propulsion LM (Gas Turbine)
2500 | N/A | N/A | 2500 | 2500
Accommodations
341 | N/A | N/A | 314 | 314
MOBILITY:
Speed (knots)
30 | 30 | 30 | 30 | 30
Armament
Anti-Submarine Warfare
ASW System
AN/SQQ-89 | N/A | N/A | AN/SQQ-89 | AN/SQQ-89
ASROC
VLA | N/A | N/A | VLA | VLA
Helo
SEAHAWK; LAMPS | 2 EMBARKEDHELOS | 2 EMBARKEDHELOS | 2 Embarked Helos | 2 Embarked Helos
Anti-Air Warfare
Launchers
MK 41 VLS | N/A | N/A | MK 41 VLS | MK 41 VLS
Missiles
SM-2 MR | N/A | N/A | SM-2 MR/SM-3/ESSM | SM-2 MR/SM-3/ESSM
Missile Fire Control System
3 MK 99 | N/A | N/A | 3 MK 99 | 3 MK 99
(Ch-1)

## Table 13
Guns
2 PHALANX | N/A | N/A | 2 PHALANX | 2 PHALANX
Anti-Surface/Strike Warfare
Guns
1 5"/54 | N/A | N/A | 1 5"/62 | 1 5"/62
Gunfire Control System
MK 160 | N/A | N/A | MK 160 | MK 160
Anti-Ship Cruise Missile
HARPOON | N/A | N/A | N/A | N/A
Cruise Missile
TOMAHAWK | N/A | N/A | TOMAHAWK | TOMAHAWK
Electronic Warfare
SLQ-32 SRBOC | N/A | N/A | SLQ-32, SRBOC, Combat DF | SLQ-32, SRBOC, Combat DF
Radars
Surface
SPS-67 | N/A | N/A | SPS-67 | SPS-67/SPQ-9B
3D
SPY-1D | N/A | N/A | SPY-1D (V) | SPY-1D (V)/SPY-6
MINE WARFARE:
Detection Range of Moored/Floating Mine (YDS)
N/A | 1000 | 800 | 1400 | 1400
Classified Performance information is provided in the classified annex to this submission.
Requirements Reference
ORD dated April 15, 1994
Change Explanations
(Ch-1) The current estimate for Length has changed from "see change explanations" to "Baseline Dependent". As noted in the 2014 SAR, the production estimate, demonstrated performance, and current estimate for length at waterline for FLT I and FLT II are 466. Demonstrated performance and current estimate for length at waterline for FLT IIA and FLT III is 471.
Demonstrated performance and current estimate for FLT IIA length overall is 509. Current estimate for FLT III length overall is 509.
Notes
Demonstrated Performance and Current Estimate are for the FLT IIA configuration except for Radars that have inputs for FLT IIA and FLT III ships. Production Estimates are from the FLT II configuration. Demonstrated Performance characteristics reflect testing through the TEMP 801-OT-IIIH report dated July 20, 2006. SM-3 Block IA Demonstrated Performance is reflected in FTM-15, approved April 14, 2011.

## Table 14
Acronyms and Abbreviations
ASROC - Anti-Submarine Rocket ASW - Anti-Submarine Warfare DF - Direction Finding
ESSM - Evolved Sea Sparrow Missile FLT - Flight
ft - Feet
FTM - Flight Test Mission HELO - Helicopter
MK - Mark
MR - Medium Range
SM-2 - Standard Missile 2 SM-3 - Standard Missile 3
SRBOC - Super Rapid Blooming Off-Board Chaff TEMP - Test & Evaluation Master Plan
VLA - Vertical Launching ASROC (Anti-Submarine Rocket) VLS - Vertical Launching System
YDS - Yards

## Table 15
Track to Budget
RDT&E
Appn BA PE
Navy 1319 04 0603564N
Project Name
0409 DDG-51 Flt III Concept Development Navy 1319 05 0604303N
Project Name
1776 AEGIS Weapon System Mods (Sunk) Navy 1319 05 0604307N
Project Name
1447 Surf Combatant Combat System Imp (Shared)
Procurement
Appn BA PE
Navy 1611 02 0204222N
Line Item Name
2122 DDG-51
Navy 1611 05 0204222N
Line Item Name
5110 Outfitting (Shared)
5300 Completion of PY Shipbuilding Programs (Shared)
MILCON
Appn BA PE
Navy 1205 0204228N
Project Name
263 AEGIS Computer Center Building Addition (Sunk) Navy 1205 0605896N
Project Name
261 Battle Force Combatant Education Facility (Sunk)

## Table 16
Cost and Funding
Cost Summary
Total Acquisition Cost
Appropriation | BY 1987 $M | [5 empty] | BY 1987 $M |  | TY $M
| SAR Baseline Production Estimate |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate |  | SAR Baseline Production Estimate |  |  | Current APB Production Objective |  | Current Estimate
RDT&E | 979.8 |  |  | 3031.8 | 3335 |  |  | 3493.61 |  | 916.6 |  |  | 3954.6 | 4890.8
Procurement | 15948.3 |  |  | 57095.5 | 62805.1 |  |  | 63309.71 |  | 19173.1 |  |  | 84417.5 | 101911.2
Flyaway | -- |  |  | -- | -- |  |  | 63309.7 |  | -- |  |  | -- | 101911.2
Recurring | -- |  |  | -- | -- |  |  | 61761.9 |  | -- |  |  | -- | 99362
Non Recurring | -- |  |  | -- | -- |  |  | 1547.8 |  | -- |  |  | -- | 2549.2
Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- | 0
Other Support | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- | 0
Initial Spares | -- |  |  | -- | -- |  |  | 0 |  | -- |  |  | -- | 0
MILCON | 25.6 |  |  | 34.8 | 38.3 |  |  | 37.6 |  | 27.8 |  |  | 41 | 44.5
Acq O&M | 0 |  |  | 0 | -- |  |  | 0 |  | 0 |  |  | 0 | 0
Total | 16953.7 |  |  | 60162.1 | N/A |  |  | 66840.9 |  | 20117.5 |  |  | 88413.1 | 106846.5
1 APB Breach
Confidence Level
Confidence Level of cost estimate for current APB: 84%
Eighty One percent (81%) of the ships are complete with a confidence level of 100%. Remaining future ships are budgeted at a 50% confidence level as reflected in Navy cost estimating curves.
Total Quantity
Quantity |  | SAR Baseline Production Estimate |  |  |  | Current APB Production |  |  |  |  | Current Estimate
RDT&E |  | 0 |  |  |  | 0 |  |  |  |  | 0
Procurement |  | 23 |  |  |  | 75 |  |  |  |  | 86
Total |  | 23 |  |  |  | 75 |  |  |  |  | 86

## Table 17
Cost and Funding
Funding Summary
Appropriation Summary
FY 2017 President's Budget / December 2015 SAR (TY$ M)
Appropriation | Prior | FY | 2016 | FY 2017 |  | FY 2018 | FY 2019 |  | FY 2020 |  | FY | 2021 | To Complete |  |  | Total
RDT&E | 3498.3 | 243.5 |  |  | 175.5 | 195.1 | 195 |  | 174.4 |  | 158.1 |  | 250.9 |  | 4890.8
Procurement | 75249.4 | 4266.8 |  |  | 3348.9 | 3636.6 | 3633.2 |  | 3712 |  | 3784 |  | 4280.3 |  | 101911.2
MILCON | 44.5 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 44.5
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2017 Total | 78792.2 | 4510.3 |  |  | 3524.4 | 3831.7 | 3828.2 |  | 3886.4 |  | 3942.1 |  | 4531.2 |  | 106846.5
PB 2016 Total | 78789.7 | 3556.1 |  |  | 3686.4 | 3781.7 | 3827.2 |  | 3927.1 |  | 183.4 |  | 575.9 |  | 98327.5
Delta | 2.5 | 954.2 |  |  | -162 | 50 | 1 |  | -40.7 |  | 3758.7 |  | 3955.3 |  | 8519
Quantity Summary
FY 2017 President's Budget / December 2015 SA | [9 empty] | R (TY$ M)
Quantity | Undistribu | ted | Prior |  | FY 2016 | FY 2017 | FY 2018 | FY 2019 |  | FY 2020 |  | FY 2021 |  | To Complet | e | Total
Development | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Production | 0 |  | 72 |  | 2 | 2 | 2 |  | 2 |  | 2 | 2 |  | 2 |  | 86
PB 2017 Total | 0 |  | 72 |  | 2 | 2 | 2 |  | 2 |  | 2 | 2 |  | 2 |  | 86
PB 2016 Total | 0 |  | 72 |  | 2 | 2 | 2 |  | 2 |  | 2 | 0 |  | 0 |  | 82
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 2 |  | 2 |  | 4

## Table 18
Cost and Funding
Annual Funding By Appropriation
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1980 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.5
1981 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.3
1982 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102
1983 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 150.7
1984 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 121.1
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.8
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 93.5
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100.4
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 93.4
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 52.3
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 41.2
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 87.5
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 87.2
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 110.6
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.7
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 89.6
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 87.3
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 82.5
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 78.3
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 155.4
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 232.6
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 143.5
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 230.7
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 199
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 135.3
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 126
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 113.4
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.2
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 37.4
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 8.7
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 16.8
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 42.5
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.8
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 62.1
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 86.3

## Table 19
2015 | -- | -- | -- | -- | -- | -- | 125.7
2016 | -- | -- | -- | -- | -- | -- | 243.5
2017 | -- | -- | -- | -- | -- | -- | 175.5
2018 | -- | -- | -- | -- | -- | -- | 195.1
2019 | -- | -- | -- | -- | -- | -- | 195
2020 | -- | -- | -- | -- | -- | -- | 174.4
2021 | -- | -- | -- | -- | -- | -- | 158.1
2022 | -- | -- | -- | -- | -- | -- | 200.5
2023 | -- | -- | -- | -- | -- | -- | 44.6
2024 | -- | -- | -- | -- | -- | -- | 5.8
Subtotal | -- | -- | -- | -- | -- | -- | 4890.8

## Table 20
Annual Funding 1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity |  | BY 1987 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1980 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 14
1981 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.1
1982 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 118.3
1983 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 167.3
1984 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 129.8
1985 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 144.2
1986 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 94.4
1987 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 98.5
1988 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.7
1989 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 47.6
1990 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 36.1
1991 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 73.9
1992 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 71.6
1993 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 88.7
1994 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 80.9
1995 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.2
1996 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 66.3
1997 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 61.9
1998 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 58.3
1999 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 114.3
2000 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 168.7
2001 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.7
2002 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 163.4
2003 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 138.9
2004 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 91.9
2005 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 83.4
2006 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 72.8
2007 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 43.3
2008 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 23
2009 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 5.3
2010 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 10.1
2011 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 24.8
2012 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 28.1
2013 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 35.3
2014 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 48.4
2015 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 69.6
2016 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 132.7
2017 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 93.9
2018 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 102.4
2019 |  | -- | -- |  | -- |  | -- |  | -- |  | -- |  | 100.4

## Table 21
2020 | -- | -- | -- | -- | -- | -- | 88
2021 | -- | -- | -- | -- | -- | -- | 78.2
2022 | -- | -- | -- | -- | -- | -- | 97.3
2023 | -- | -- | -- | -- | -- | -- | 21.2
2024 | -- | -- | -- | -- | -- | -- | 2.7
Subtotal | -- | -- | -- | -- | -- | -- | 3493.6

## Table 22
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | TY $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1984 |  | -- | 78.5 |  | -- |  | -- |  | 78.5 |  | -- |  | 78.5
1985 |  | 1 | 846.6 |  | -- |  | 299.2 |  | 1145.8 |  | -- |  | 1145.8
1986 |  | -- | 98.1 |  | -- |  | -- |  | 98.1 |  | -- |  | 98.1
1987 |  | 3 | 2326.7 |  | -- |  | 158.2 |  | 2484.9 |  | -- |  | 2484.9
1988 |  | -- | 9.6 |  | -- |  | -- |  | 9.6 |  | -- |  | 9.6
1989 |  | 4 | 2876.5 |  | -- |  | -- |  | 2876.5 |  | -- |  | 2876.5
1990 |  | 5 | 3569.5 |  | -- |  | 13.5 |  | 3583 |  | -- |  | 3583
1991 |  | 4 | 3145.1 |  | -- |  | 3.6 |  | 3148.7 |  | -- |  | 3148.7
1992 |  | 5 | 3982.8 |  | -- |  | 38.3 |  | 4021.1 |  | -- |  | 4021.1
1993 |  | 4 | 3379.3 |  | -- |  | 7.9 |  | 3387.2 |  | -- |  | 3387.2
1994 |  | 3 | 2703.3 |  | -- |  | 86.9 |  | 2790.2 |  | -- |  | 2790.2
1995 |  | 3 | 2779.7 |  | -- |  | 37.8 |  | 2817.5 |  | -- |  | 2817.5
1996 |  | 2 | 2289.5 |  | -- |  | 61.7 |  | 2351.2 |  | -- |  | 2351.2
1997 |  | 4 | 3541.9 |  | -- |  | 38.8 |  | 3580.7 |  | -- |  | 3580.7
1998 |  | 4 | 3424.3 |  | -- |  | 110.5 |  | 3534.8 |  | -- |  | 3534.8
1999 |  | 3 | 2674.1 |  | -- |  | 44.2 |  | 2718.3 |  | -- |  | 2718.3
2000 |  | 3 | 2651.1 |  | -- |  | 30.1 |  | 2681.2 |  | -- |  | 2681.2
2001 |  | 3 | 3231.3 |  | -- |  | -- |  | 3231.3 |  | -- |  | 3231.3
2002 |  | 3 | 3293.7 |  | -- |  | 14.4 |  | 3308.1 |  | -- |  | 3308.1
2003 |  | 2 | 2657.2 |  | -- |  | 63.1 |  | 2720.3 |  | -- |  | 2720.3
2004 |  | 3 | 3345.3 |  | -- |  | 4.7 |  | 3350 |  | -- |  | 3350
2005 |  | 3 | 3653.5 |  | -- |  | 8.9 |  | 3662.4 |  | -- |  | 3662.4
2006 |  | -- | 508.6 |  | -- |  | -- |  | 508.6 |  | -- |  | 508.6
2007 |  | -- | 289.3 |  | -- |  | -- |  | 289.3 |  | -- |  | 289.3
2008 |  | -- | 94.9 |  | -- |  | -- |  | 94.9 |  | -- |  | 94.9
2009 |  | -- | 331.2 |  | -- |  | -- |  | 331.2 |  | -- |  | 331.2
2010 |  | 1 | 2306.7 |  | -- |  | 121.8 |  | 2428.5 |  | -- |  | 2428.5
2011 |  | 2 | 2584.2 |  | -- |  | 11.6 |  | 2595.8 |  | -- |  | 2595.8
2012 |  | 1 | 1780.8 |  | -- |  | 120.2 |  | 1901 |  | -- |  | 1901
2013 |  | 3 | 4471.5 |  | -- |  | 29.8 |  | 4501.3 |  | -- |  | 4501.3
2014 |  | 1 | 2086.5 |  | -- |  | -- |  | 2086.5 |  | -- |  | 2086.5
2015 |  | 2 | 2932.9 |  | -- |  | -- |  | 2932.9 |  | -- |  | 2932.9
2016 |  | 2 | 3032.8 |  | -- |  | 1234 |  | 4266.8 |  | -- |  | 4266.8
2017 |  | 2 | 3338.9 |  | -- |  | 10 |  | 3348.9 |  | -- |  | 3348.9
2018 |  | 2 | 3636.6 |  | -- |  | -- |  | 3636.6 |  | -- |  | 3636.6
2019 |  | 2 | 3633.2 |  | -- |  | -- |  | 3633.2 |  | -- |  | 3633.2
2020 |  | 2 | 3712 |  | -- |  | -- |  | 3712 |  | -- |  | 3712
2021 |  | 2 | 3784 |  | -- |  | -- |  | 3784 |  | -- |  | 3784
2022 |  | 2 | 3950 |  | -- |  | -- |  | 3950 |  | -- |  | 3950
2023 |  | -- | 229.8 |  | -- |  | -- |  | 229.8 |  | -- |  | 229.8

## Table 23
2024 | -- | 20.1 | -- | -- | 20.1 | -- | 20.1
2025 | -- | 20.1 | -- | -- | 20.1 | -- | 20.1
2026 | -- | 20.1 | -- | -- | 20.1 | -- | 20.1
2027 | -- | 20.1 | -- | -- | 20.1 | -- | 20.1
2028 | -- | 20.1 | -- | -- | 20.1 | -- | 20.1
Subtotal | 86 | 99362 | -- | 2549.2 | 101911.2 | -- | 101911.2

## Table 24
Annual Funding 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
Fiscal Year | Quantity |  | BY 1987 $M
|  |  | End Item Recurring Flyaway | Non End Item Recurring Flyaway |  | Non Recurring Flyaway |  | Total Flyaway |  | Total Support |  | Total Program
1984 |  | -- | 78.5 |  | -- |  | -- |  | 78.5 |  | -- |  | 78.5
1985 |  | 1 | 829.8 |  | -- |  | 293.3 |  | 1123.1 |  | -- |  | 1123.1
1986 |  | -- | 94 |  | -- |  | -- |  | 94 |  | -- |  | 94
1987 |  | 3 | 2179.7 |  | -- |  | 148.2 |  | 2327.9 |  | -- |  | 2327.9
1988 |  | -- | 8.7 |  | -- |  | -- |  | 8.7 |  | -- |  | 8.7
1989 |  | 4 | 2540.5 |  | -- |  | -- |  | 2540.5 |  | -- |  | 2540.5
1990 |  | 5 | 3064.1 |  | -- |  | 11.6 |  | 3075.7 |  | -- |  | 3075.7
1991 |  | 4 | 2626.4 |  | -- |  | 3.1 |  | 2629.5 |  | -- |  | 2629.5
1992 |  | 5 | 3242.3 |  | -- |  | 31.1 |  | 3273.4 |  | -- |  | 3273.4
1993 |  | 4 | 2723.5 |  | -- |  | 6.3 |  | 2729.8 |  | -- |  | 2729.8
1994 |  | 3 | 2127.5 |  | -- |  | 68.3 |  | 2195.8 |  | -- |  | 2195.8
1995 |  | 3 | 2163.3 |  | -- |  | 29.4 |  | 2192.7 |  | -- |  | 2192.7
1996 |  | 2 | 1762.8 |  | -- |  | 47.5 |  | 1810.3 |  | -- |  | 1810.3
1997 |  | 4 | 2686.1 |  | -- |  | 29.4 |  | 2715.5 |  | -- |  | 2715.5
1998 |  | 4 | 2539.8 |  | -- |  | 81.9 |  | 2621.7 |  | -- |  | 2621.7
1999 |  | 3 | 1952.3 |  | -- |  | 32.3 |  | 1984.6 |  | -- |  | 1984.6
2000 |  | 3 | 1887.5 |  | -- |  | 21.5 |  | 1909 |  | -- |  | 1909
2001 |  | 3 | 2224.1 |  | -- |  | -- |  | 2224.1 |  | -- |  | 2224.1
2002 |  | 3 | 2254.2 |  | -- |  | 9.9 |  | 2264.1 |  | -- |  | 2264.1
2003 |  | 2 | 1719.2 |  | -- |  | 40.8 |  | 1760 |  | -- |  | 1760
2004 |  | 3 | 2088.6 |  | -- |  | 2.9 |  | 2091.5 |  | -- |  | 2091.5
2005 |  | 3 | 2184.2 |  | -- |  | 5.3 |  | 2189.5 |  | -- |  | 2189.5
2006 |  | -- | 293.7 |  | -- |  | -- |  | 293.7 |  | -- |  | 293.7
2007 |  | -- | 159.7 |  | -- |  | -- |  | 159.7 |  | -- |  | 159.7
2008 |  | -- | 50.7 |  | -- |  | -- |  | 50.7 |  | -- |  | 50.7
2009 |  | -- | 171.6 |  | -- |  | -- |  | 171.6 |  | -- |  | 171.6
2010 |  | 1 | 1154.3 |  | -- |  | 61 |  | 1215.3 |  | -- |  | 1215.3
2011 |  | 2 | 1252.3 |  | -- |  | 5.6 |  | 1257.9 |  | -- |  | 1257.9
2012 |  | 1 | 843.9 |  | -- |  | 57 |  | 900.9 |  | -- |  | 900.9
2013 |  | 3 | 2077.4 |  | -- |  | 13.9 |  | 2091.3 |  | -- |  | 2091.3
2014 |  | 1 | 951.6 |  | -- |  | -- |  | 951.6 |  | -- |  | 951.6
2015 |  | 2 | 1314.7 |  | -- |  | -- |  | 1314.7 |  | -- |  | 1314.7
2016 |  | 2 | 1334.9 |  | -- |  | 543.2 |  | 1878.1 |  | -- |  | 1878.1
2017 |  | 2 | 1441.8 |  | -- |  | 4.3 |  | 1446.1 |  | -- |  | 1446.1
2018 |  | 2 | 1539.8 |  | -- |  | -- |  | 1539.8 |  | -- |  | 1539.8
2019 |  | 2 | 1508.2 |  | -- |  | -- |  | 1508.2 |  | -- |  | 1508.2
2020 |  | 2 | 1510.7 |  | -- |  | -- |  | 1510.7 |  | -- |  | 1510.7
2021 |  | 2 | 1509.8 |  | -- |  | -- |  | 1509.8 |  | -- |  | 1509.8
2022 |  | 2 | 1545.2 |  | -- |  | -- |  | 1545.2 |  | -- |  | 1545.2
2023 |  | -- | 88.1 |  | -- |  | -- |  | 88.1 |  | -- |  | 88.1

## Table 25
2024 | -- | 7.6 | -- | -- | 7.6 | -- | 7.6
2025 | -- | 7.4 | -- | -- | 7.4 | -- | 7.4
2026 | -- | 7.3 | -- | -- | 7.3 | -- | 7.3
2027 | -- | 7.1 | -- | -- | 7.1 | -- | 7.1
2028 | -- | 7 | -- | -- | 7 | -- | 7
Subtotal | 86 | 61761.9 | -- | 1547.8 | 63309.7 | -- | 63309.7

## Table 26
Cost Quantity Information 1611 ¦ Procurement ¦ Shipbuilding and Conversion, Navy
End Item
Recurring
Fiscal Year | Quantity | Flyaway (Aligned With
Quantity)
BY 1987 $M
1984 | -- | --
1985 | 1 | 934.7
1986 | -- | --
1987 | 3 | 2344.3
1988 | -- | --
1989 | 4 | 2630.9
1990 | 5 | 3159.7
1991 | 4 | 2666.6
1992 | 5 | 3305.4
1993 | 4 | 2672.1
1994 | 3 | 2117.9
1995 | 3 | 2157.2
1996 | 2 | 1560.9
1997 | 4 | 2631.7
1998 | 4 | 2805.6
1999 | 3 | 2159.1
2000 | 3 | 2063.4
2001 | 3 | 2107.8
2002 | 3 | 2335.7
2003 | 2 | 1576.2
2004 | 3 | 2159.9
2005 | 3 | 2210.6
2006 | -- | --
2007 | -- | --
2008 | -- | --
2009 | -- | --
2010 | 1 | 1039.8
2011 | 2 | 1560.8
2012 | 1 | 866.4
2013 | 3 | 2056.1
2014 | 1 | 815
2015 | 2 | 1383.7
2016 | 2 | 1494.7
2017 | 2 | 1533.2
2018 | 2 | 1518.3
2019 | 2 | 1488.5
2020 | 2 | 1474.7
2021 | 2 | 1465.9
2022 | 2 | 1465.1

## Table 27
2023 | -- | --
2024 | -- | --
2025 | -- | --
2026 | -- | --
2027 | -- | --
2028 | -- | --
Subtotal | 86 | 61761.9

## Table 28
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | TY $M
Total Program
1986 4.6
1987 --
1988 14.7
1989 8.5
1990 --
1991 --
1992 --
1993 --
1994 --
1995 --
1996 --
1997 --
1998 13.2
1999 --
2000 --
2001 3.5
Subtotal 44.5

## Table 29
Annual Funding 1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | BY 1987 $M
Total Program
1986 4.5
1987 --
1988 13.4
1989 7.5
1990 --
1991 --
1992 --
1993 --
1994 --
1995 --
1996 --
1997 --
1998 9.7
1999 --
2000 --
2001 2.5
Subtotal 37.6

## Table 30
Low Rate Initial Production
Item | Initial LRIP Decision | Current Total LRIP
Approval Date | 1986-10-30 | 1986-10-30
Approved Quantity | 9 | 9
Reference | Milestone IIIA Review Decision Memorandum | Milestone IIIA Review Decision Memorandum
Start Year | 1985 | 1985
End Year | 1989 | 1989
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the Milestone IIIA Review Decision Memorandum dated October 30, 1986, approving 9 LRIP ships which is standard for ship building programs.

## Table 31
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Description
Japan | 2015-10-30 | 121 | 5856 | Date cited is date of last case sale.
South Korea | 2015-10-27 | 14 | 2994 | Date cited is date of last case sale.
Australia | 2014-05-22 | 6 | 1225 | Date cited is date of last case sale.
Norway | 2012-07-18 | 10 | 344 | Date cited is date of last case sale.
Spain | 2006-08-11 | 7 | 1285 | Date cited is date of last case sale.
Notes
Quantity numbers above reflect FMS cases, rather than ships. Cases are agreements between the United States and an eligible foreign country to provide defense articles, training, and/or services for purchase. Cases can be related to procurements (e.g., Ordalt or standard missile), training (e.g., AEGIS shipboard training or replacement crew training), and program management support (e.g., Combat System Ship Qualification Test). Case quantity numbers reflect all cases; open and closed.
Nuclear Costs
None

## Table 32
Unit Cost
Unit Cost Report
Item |  | BY 1987 $M | BY 1987 $M |  | % Change
|  | Current UCR Baseline (May 2011 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 60162.1 |  |  | 66840.9
Quantity | 75 |  |  | 86
Unit Cost | 802.161 |  |  | 777.22 |  | -3.11
Average Procurement Unit Cost
Cost | 57095.5 |  |  | 63309.7
Quantity | 75 |  |  | 86
Unit Cost | 761.273 |  |  | 736.159 |  | -3.3
Item |  | BY 1987 $M | BY 1987 $M |  | % Change
|  | Original UCR Baseline (Feb 1988 APB) | Current Estimate (Dec 2015 SAR)
Program Acquisition Unit Cost
Cost | 16723.8 |  |  | 66840.9
Quantity | 23 |  |  | 86
Unit Cost | 727.122 |  |  | 777.22 |  | 6.89
Average Procurement Unit Cost
Cost | 15745.3 |  |  | 63309.7
Quantity | 23 |  |  | 86
Unit Cost | 684.578 |  |  | 736.159 |  | 7.53

## Table 33
Unit Cost History
Item |  |  |  | Date |  |  | BY 1987 $M |  |  |  |  | TY $M
[7 empty] | PAUC |  | APUC |  |  | PAUC |  |  |  | APUC
Original APB |  |  | Feb 1988 |  |  |  | 727.122 |  |  | 684.578 |  |  |  | 883.152 |  |  | 843.209
APB as of January 2006 |  |  | Aug 2002 |  |  |  | 766.675 |  |  | 725.342 |  |  |  | 1031.612 |  |  | 981.022
Revised Original APB |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  | Mar 2010 |  |  |  | 796.555 |  |  | 759.297 |  |  |  | 1131.565 |  |  | 1085.962
Current APB |  |  | May 2011 |  |  |  | 802.161 |  |  | 761.273 |  |  |  | 1178.841 |  |  | 1125.567
Prior Annual SAR |  |  | Dec 2014 |  |  |  | 773.601 |  |  | 732.151 |  |  |  | 1199.116 |  |  | 1142.216
Current Estimate |  |  | Dec 2015 |  |  |  | 777.22 |  |  | 736.159 |  |  |  | 1242.401 |  |  | 1185.014
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Production Estimate | Changes | [13 empty] | PAUC Current Estimate
| Econ | Qty |  |  | Sch | Eng |  | Est | Oth |  | Spt |  | Total
874.674 -38.084 105.995 22.766 92.433 184.617 0.000 0.000 367.727 1242.401
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Production Estimate | Changes | [13 empty] | APUC Current Estimate
| Econ | Qty |  |  | Sch | Eng |  | Est | Oth |  | Spt |  | Total
833.613 -36.674 136.075 21.081 74.631 156.288 0.000 0.000 351.401 1185.014

## Table 34
SAR Baseline History
Item | SAR Planning Estimate | SAR Development Estimate | SAR Production Estimate | Current Estimate
Milestone I | Jun 1981 | Jun 1981 | Jun 1981 | Jun 1981
Milestone II | May 1983 | Dec 1983 | Dec 1983 | Dec 1983
Milestone III | Aug 1986 | Aug 1986 | N/A | N/A
IOC | N/A | N/A | Oct 1990 | Feb 1993
Total Cost (TY $M) | 10953.5 | 14910.6 | 20117.5 | 106846.5
Total Quantity | 9 | 14 | 23 | 86
PAUC | 1217.056 | 1065.043 | 874.674 | 1242.401

## Table 35
Cost Variance
Summary TY $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
916.6 19173.1 27.8 20117.5
Economic |  | -113.3 |  | -3219.4 |  | 0.1 |  | -3332.6
Quantity |  | -- |  | 59210 |  | -- |  | 59210
Schedule |  | 144.9 |  | 1605.4 |  | -- |  | 1750.3
Engineering |  | 1581 |  | 5683.4 |  | 16.7 |  | 7281.1
Estimating |  | 2092.1 |  | 11209.2 |  | -0.1 |  | 13301.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 3704.7 |  | 74488.6 |  | 16.7 |  | 78210
Current Changes Economic |  | -8 |  | 65.4 |  | -- |  | 57.4
Quantity |  | -- |  | 5010 |  | -- |  | 5010
Schedule |  | -- |  | 207.6 |  | -- |  | 207.6
Engineering |  | -66.8 |  | 734.9 |  | -- |  | 668.1
Estimating |  | 344.3 |  | 2231.6 |  | -- |  | 2575.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 269.5 |  | 8249.5 |  | -- |  | 8519
Total Changes |  | 3974.2 |  | 82738.1 |  | 16.7 |  | 86729
Current Estimate |  | 4890.8 |  | 101911.2 |  | 44.5 |  | 106846.5

## Table 36
Summary BY 1987 $M
Item | RDT&E |  | Procurement |  | MILCON |  | Total
SAR Baseline (Production Estimate)
Previous Changes
979.8 15948.3 25.6 16953.7
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 35040.3 |  | -- |  | 35040.3
Schedule |  | 89.1 |  | 421 |  | -- |  | 510.1
Engineering |  | 883.1 |  | 3028.1 |  | 11.9 |  | 3923.1
Estimating |  | 1409.3 |  | 5598.7 |  | 0.1 |  | 7008.1
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 2381.5 |  | 44088.1 |  | 12 |  | 46481.6
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 1979.4 |  | -- |  | 1979.4
Schedule |  | -- |  | 82 |  | -- |  | 82
Engineering |  | -35.3 |  | 290.3 |  | -- |  | 255
Estimating |  | 167.6 |  | 921.6 |  | -- |  | 1089.2
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | -- |  | -- |  | --
Subtotal |  | 132.3 |  | 3273.3 |  | -- |  | 3405.6
Total Changes |  | 2513.8 |  | 47361.4 |  | 12 |  | 49887.2
Current Estimate |  | 3493.6 |  | 63309.7 |  | 37.6 |  | 66840.9
Previous Estimate: December 2014

## Table 37
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -8
Adjustment for current and prior escalation. (Estimating) | 1.5 | 2.8
Realignment of Cyber Security Task Force to another RDT&E Project Unit. (Engineering) | -35.3 | -66.8
Revised estimates to reflect application of new outyear escalation indices. (Estimating) | 2.7 | 5.2
Congressional Reduction associated with AEGIS Advanced Capability Build (ACB) 16. | -15.2 | -28
(Estimating)
Revised estimate to reflect refinement of AEGIS ACB 16/AEGIS ACB 20 development including ACB 20 certification, test, and evaluation. (Estimating)
+178.6 +364.3
RDT&E Subtotal +132.3 +269.5
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 65.4
Adjustment for current and prior escalation. (Estimating) | -17.6 | -38.4
Total Quantity variance resulting from an increase of 4 ships from 82 to 86. (Subtotal) | 2967.4 | 7511.4
Quantity variance resulting from an increase of 4 ships from 82 to 86. (Quantity) | -2022.7 | -5120
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -82 | -207.6
Allocation to Engineering resulting from Quantity change. (Engineering) (QR) | -290.3 | -734.9
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -572.4 | -1448.9
Additional Quantity variance reflects actual funding adjustments associated with the | -43.3 | -110
increase of 2 ships in FY 2021 and estimates for 2 additional ships in FY 2022. (Quantity)
Revised estimates to reflect application of new outyear escalation indices. (Estimating) | -11.2 | -27
Congressional Reductions to FY 2016 for shipbuilder and SPQ-9B. (Estimating) | -7.5 | -17.1
Congressional Plus-Up for an additional ship not in the SAR profile. (Estimating) | 440.1 | 1000
Adjustment for impact of Congressional Plus-Up without increase to profile. (Estimating) | -40.1 | -91
Revised estimate to reflect program efficiencies. (Estimating) | -54.2 | -130.8
Revised estimate to reflect refinement of FY 2012, FY 2013, and FY 2015 shipbuilding | 44.2 | 105.2
estimates. (Estimating)
Revised estimate to reflect refinement of outfitting and post delivery estimates. (Estimating) | -4.5 | -18.2
Procurement Subtotal | 3273.3 | 8249.5
(QR) Quantity Related

## Table 38
Contracts
Contract Identification
Appropriation: Procurement
Contract Name: DDG 113 Guided Missile Destroyer
Contractor: Huntington Ingalls Industries (HII)
Contractor Location: 1000 Access Road
Pascagoula, MS 39567
Contract Number: N00024-11-C-2309/113
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 15, 2011
Definitization Date: June 15, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
773.6 852.5 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to negotiated changes to the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to an increase in manufacturing hours caused by a loss of learning from the production gap and new management in the hull shops. Hull shops are complete and cost performance continues to improve across the rest of the manufacturing pool. Performance has improved across manufacturing and is forecasted to continue until delivery.
The unfavorable net change in the schedule variance is due to hull shops loss of learning and additional re-work associated with coatings. DDG 113 has improved on its schedule overall and plans to deliver DDG 113 by the contract delivery date.
Notes
DDG 113 (FY 2010 ship) was a sole source annual procurement awarded to HII on June 15, 2011.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).

## Table 39
Contract Identification
Appropriation: Procurement
Contract Name: DDG 114 Guided Missile Destroyer
Contractor: Huntington Ingalls Industries (HII)
Contractor Location: 1000 Access Road
Pascagoula, MS 39567
Contract Number: N00024-11-C-2307/114
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: September 26, 2011
Definitization Date: September 26, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
687.6 787.6 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to negotiated changes to the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to an increase in manufacturing hours caused by a loss of learning from the production gap, new management in the hull shops, and a Performance Measurement Baseline (PMB) with a lower Target Cost than the previous DDG (DDG 113). Hull shops are now 100% complete and cost performance continues to improve across the rest of the manufacturing pool. Despite the poor cost performance, significant learning can be seen from DDG 113. Performance has improved across manufacturing and is forecasted to continue until delivery.
The unfavorable net change in the schedule variance is due to electrical hookup falling behind from pulling class-4 cable. HII plans to deliver DDG 114 one month before the contract delivery date.
Notes
The DDG 114 (one of two FY 2011 ships) was a competitively bid annual procurement awarded to Ingalls on September 26, 2011.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).

## Table 40
Contract Identification
Appropriation: Procurement
Contract Name: DDG 115 Guided Missile Destroyer
Contractor: General Dynamics (GD), Bath Iron Works (BIW)
Contractor Location: 700 Washington Street
Bath, ME 04530
Contract Number: N00024-11-C-2305/115
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: September 26, 2011
Definitization Date: September 26, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
669.6 749.3 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to negotiated changes to the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to increased manufacturing hours due to a less experienced staff that was hired for the DDG 51 Program restart and the reassignment of experienced staff to the DDG 1000.
The unfavorable net change in the schedule variance is due to increased manufacturing hours due to a less experienced staff that was hired in response to the DDG 51 Program restart and the reassignment of experienced staff to the DDG 1000. All future contract and planning dates are under Navy review.
Notes
The DDG 115 (one of two FY 2011 ships) was a competitively bid annual procurement awarded to BIW on September 26, 2011.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).

## Table 41
Contract Identification
Appropriation: Procurement
Contract Name: DDG 116 Guided Missile Destroyer
Contractor: General Dynamics (GD), Bath Iron Works (BIW)
Contractor Location: 700 Washington Street
Bath, ME 04530
Contract Number: N00024-11-C-2305/116
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: February 28, 2012
Definitization Date: September 26, 2011
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
655.0 718.6 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to negotiated changes to the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to increased manufacturing hours due to a less experienced staff that was hired the DDG 51 Program restart and the reassignment of experienced staff to the DDG 1000.
The favorable net change in the schedule variance is due to a schedule changes and over manning. All future contract and planning dates are under Navy review.
Notes
The DDG 116 (FY 2012 ship) was awarded as an option to BIW on September 26, 2011. Option was exercised on February 28, 2012.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).

## Table 42
Contract Identification
Appropriation: Procurement
Contract Name: DDG 117 Guided Missile Destroyer
Contractor: Huntington Ingalls Industries (HII)
Contractor Location: 1000 Access Road
Pascagoula, MS 39567
Contract Number: N00024-13-C-2307
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 03, 2013
Definitization Date: June 03, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
626.9 715.3 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to negotiated changes to the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to an increase in manufacturing hours caused by a loss of learning from the production gap and new management in the hull shops. DDG 117's cost performance continues to be better than DDG 114.
The unfavorable net change in the schedule variance is due to loss of learning causing late products affecting the schedule. DDG 117's planned Launch date is January 17, 2017. DDG 117 is planned to deliver before the contract date.
Notes
DDG 117 (one of three FY 2013 ships) is part of the FY 2013 - FY 2017 Multi Year Procurement awarded on June 3, 2013.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).

## Table 43
Contract Identification
Appropriation: Procurement
Contract Name: DDG 118 Guided Missile Destroyer
Contractor: General Dynamics (GD), Bath Iron Works (BIW)
Contractor Location: 700 Washington Street
Bath, ME 04530
Contract Number: N00024-13-C-2305
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 03, 2013
Definitization Date: June 03, 2013
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
650.4 748.3 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to negotiated changes to the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to delayed products coming out of fabrication shops.
The unfavorable net change in the schedule variance is due to the late start of construction, more than 10 months beyond the Performance Measurement Baseline (PMB) date. The late start of construction is attributed to the impacts of yard-wide workload and manning.
Notes
DDG 118 (one of three FY 2013 ships) is part of the FY 2013 - FY 2017 Multi Year Procurement awarded on June 3, 2013.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).

## Table 44
Contract Identification
Appropriation: Procurement
Contract Name: DDG 119 Guided Missile Destroyer
Contractor: Huntington Ingalls Industries (HII)
Contractor Location: 1000 Access Road
Pascagoula, MS
Contract Number: N00024-13-C-2307/119
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 03, 2013
Definitization Date: June 03, 2014
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
643.6 706.1 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to negotiated changes to the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to hull shop performance not meeting planned targets, though trends show improvement from previous hulls under construction.
The favorable net change in the schedule variance is due to material budget time-phasing at this early stage of production. DDG 119's planned Lay Keel date of May 6, 2016 is achievable and DDG 119 is expected to deliver prior to contract delivery date.
Notes
DDG 119 (FY 2014 ship) is part of the FY 2013 - 2017 Multiyear Procurement awarded on June 3, 2013.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).

## Table 45
Contract Identification
Appropriation: Procurement
Contract Name: DDG 121 Guided Missile Destroyer
Contractor: Huntington Ingalls Industries (HII)
Contractor Location: 1000 Access Road
Pascagoula, MS
Contract Number: N00024-13-C-2307/121
Contract Type: Fixed Price Incentive(Firm Target) (FPIF)
Award Date: June 03, 2013
Definitization Date: March 27, 2015
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target |  | Ceiling | Qty | Contractor |  | Program Manager
657.1 749.8 1 1
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to negotiated changes to the contract.
Contract Variance
Item |  |  |  | Cost Variance |  |  |  | Schedule Variance
Cumulative Variances To Date (12/31/2015) Previous Cumulative Variances
Net Change
Cost and Schedule Variance Explanations
The unfavorable cumulative cost variance is due to material budget time-phasing at this early stage of production.
The unfavorable cumulative schedule variance is due to material budget time-phasing at this early stage of production.
Notes
DDG 121 (FY 2015 ship) is part of the FY 2013 - 2017 Multiyear Procurement awarded on June 3, 2013.
Current Contract Price ($M), Estimated Price at Completion ($M) and Cost and Schedule Variance for this contract is For Official Use Only - Exempt from FOIA release under 5 U.S.C. 552(b)(4).

## Table 46
Deliveries and Expenditures
Deliveries
Delivered to Date | Planned to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 62 | 62 | 86 | 72.09%
Total Program Quantity Delivered | 62 | 62 | 86 | 72.09%
Expended and Appropriated (TY $M)
Total Acquisition Cost Expended to Date Percent Expended Total Funding Years
106846.5
65832.6
61.61%
49
Years Appropriated
Percent Years Appropriated Appropriated to Date Percent Appropriated
37
75.51%
83302.5
77.96%
The above data is current as of February 09, 2016.

## Table 47
Operating and Support Cost
Cost Estimate Details
Date of Estimate: February 03, 2016
Source of Estimate: POE
Quantity to Sustain: 86
Unit of Measure: Ship
Service Life per Unit: 40.00 Years
Fiscal Years in Service: FY 1992 - FY 2068
The total ship quantity is 86 ships. Estimates are based on a service life of 35 years for the 28 Flight I and Flight II ships and 40 years for the 58 Flight IIA and Flight III ships.
Sustainment Strategy
DDG 51 Hull, Mechanical & Electrical equipment sustainment approach is by use of Multi Ship/Multi Option contracting strategy for repairs and overhauls. The program provides Integrated Logistics Support oversight and guidance to Participating Acquisition Resource Managers that develop various sustainment approaches for combat systems and Communications, Command, Control, Computers, and Intelligence.
Manpower optimization initiatives have been sought to leverage new technology and reduce costs. Reductions have been achieved across all DDG 51 Class Flights. For example, initial Flight IIA Billet Allotment was 333 officers and enlisted personnel. Policies have been implemented and new technologies deployed to reduce billets by 35 to 298, as reflected in the Ship Manpower Document, dated September 2011, for Flight IIA (DDG 103-110).
Antecedent Information
The Antecedent System is the CG 47 class of ships. The CG 47 class was used since it is the only other ship class with the AEGIS Weapon System installed. The CG 47 estimates were derived using the Naval Visibility And Management of Operating and Support Costs (VAMOSC) database. CG 47 estimates are based on 27 ships, 22 with a service life of 35 years and five with service life between 18-21 years. The years of data used for the CG 47 class are FY 2010 - FY 2015.
Annual O&S Costs BY1987 $M
Cost Element | DDG 51 Average Annual Cost Per Ship | CG 47 (Antecedent) Average Annual Cost Per Ship
Unit-Level Manpower | 12.896 | 11.48
Unit Operations | 7.016 | 4.747
Maintenance | 3.491 | 11.686
Sustaining Support | 0.93 | 0.945
Continuing System Improvements | 2.87 | 3.248
Indirect Support | 5.844 | 9.778
Other | 0 | 0
Total | 33.047 | 41.884

## Table 48
Item | Total O&S Cost $M
| DDG 51 | [6 empty] | CG 47 (Antecedent)
| Current Production APB Objective/Threshold |  |  |  |  | Current Estimate
Base Year |  | 84945 |  | 93439.5 |  |  | 109032.01 |  | 34865.8
Then Year 1 APB O&S Cost Breach |  | 177651 |  | N/A |  |  | 314558.3 |  | N/A
O&S Cost Breach is due to the increase in ship quantity from last approved APB to current estimate (75 ships vice 86 ships) and corrected service life per unit calculations for Flight IIA and Flight III (increase of 5 years from 35 to 40 for Flight IIA/Flight III ships). Change from last APB is a total of 11 ships (2 ships added in 2012 SAR, 3 ships in 2013 SAR, 2 ships in 2014 SAR, and 4 new ships in 2015 SAR).
Equation to Translate Annual Cost to Total Cost
DDG 51
($33.047M x 28 ships x 35 years) + ($33.047M x 58 ships x 40 years) = $109,032M
CG 47
($41.884M x 22 ships x 35 years) + ($41.884M x 1 ship x 21 years) + ($41.884M x 2 ships x 20 years) + ($41.884M x 1 ship x 19 years) + ($41.884M x 1 ship x 18 years) = $34,865.8M
O&S Cost Variance
Category |  |  | BY 1987 $M |  | Change Explanations
Prior SAR Total O&S Estimates - Dec 2015 SAR
98162.7
Programmatic/Planning Factors 5286.4 Addition of four ships Cost Estimating Methodology 0.0
Cost Data Update 5582.9 Additional costs from updated data within VAMOSC Labor Rate 0.0
Energy Rate 0.0
Technical Input 0.0
Other 0.0
Total Changes 10869.3
Current Estimate 109032.0
Disposal Estimate Details
Date of Estimate: February 03, 2016
Source of Estimate: NAVSEA 05C
Disposal/Demilitarization Total Cost (BY 1987 $M): Total costs for disposal of all Ship are 452.4
The DDG 51 Class remains in full rate production and continues to be updgraded in new construction. The oldest of the class are approaching mid service life now and many are being upgraded with newer technologies which will inevitably change the cost of inactivation and disposal for the class.