## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-298
C-130 AMP
As of December 31, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 4
Threshold Breaches |  | 5
Schedule |  | 6
Performance |  | 7
Track To Budget |  | 13
Cost and Funding |  | 14
Low Rate Initial Production |  | 21
Nuclear Cost |  | 22
Foreign Military Sales |  | 22
Unit Cost |  | 23
Cost Variance |  | 27
Contracts |  | 30
Deliveries and Expenditures |  | 31
Operating and Support Cost |  | 32

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
C-130 Avionics Modernization Program (C-130 AMP)
DoD Component
Air Force
Responsible Office
Responsible Office
Mr. Edwin P. McDermott | Phone | 937-255-1571
Bldg 16 | Fax | 937-255-3207
2275 D Street | DSN Phone | 785-1571
Room 149 WPAFB, OH 45433 | DSN Fax | 785-3207
Edwin.McDermott@wpafb.af.mil | Date Assigned | April 1, 2011
References
SAR Baseline (Production Estimate)
Defense Acquisiton Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 18, 2010
Approved APB
Defense Acquisition Executive (DAE) Approved Acquisition Program Baseline (APB) dated April 18, 2010

## Table 4
Mission and Description
The C-130 Avionics Modernization Program (AMP) consolidates and installs the mandated Air Force Navigation/Safety modifications, the Communications Navigation Surveillance/Air Traffic Management (CNS/ATM) capabilities, and the C-130 Broad Area Review requirements on 221 of the Air Force's Combat Delivery C-130s. These mandated modifications are incorporated with various other Reliability, Maintainability, and Sustainability upgrades to include: installation of fleet-wide radars, aircrew displays, dual autopilots, dual flight management systems and HF/UHF/VHF radios/data links. AMP will allow this fleet complete access to the CNS/ATM-mandated national and international air space for the foreseeable future.
This fleet consists of three (3) different mission design series (MDS) aircraft to be modified by the AMP (C-130 H2, H2.5, and H3). Within each of these MDSs multiple variants exist among the aircraft that will be modified with AMP. Today, these different models and cockpit configurations create significant logistics support and aircrew training inefficiencies. Also, these differences greatly complicate aircrew and aircraft scheduling and interoperability at forward operating locations. C-130 AMP standardizes the cockpit configurations and avionics suites for these different variants into a single cockpit configuration by installing a core avionics package with a common cockpit layout, thus eliminating many of these significant logistics, interoperability, and training problems.
Executive Summary
The C-130 AMP was canceled in the FY 2013 President's Budget, which results in the program being greater than 90 percent expended and delivered. Therefore, pursuant to section 2432 of Title 10, United State Code, this will be the final SAR for the program. Program cancellation also requires Congressional Nunn-McCurdy notification.
As a result of the cancellation of the C-130 AMP, the Program Acquisition Unit Cost (PAUC) increased 851% and Average Procurement Unit Cost (APUC) increased 292% resulting in a critical Nunn-McCurdy breach.
Dedicated Operational Test and Evaluation (OT&E) Status - C-130 IOT&E has been indefinitely delayed due to pending cancellation.
- Operational Test and Evaluation Certificate signed December 2011; Military Flight Release signed January 2012.
- LRIP 1 (AMP #4) completed installation at Warner-Robins Air Logistics Center and delivered to Little Rock, AFB January 3, 2012; LRIP 2's (AMP #5) estimated delivery is March 2012
Source Familiarization Phase (SFP) source selection process expired December 2011.
There are no software-related issues with the program at this time.

## Table 5
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Explanation of Breach
The Schedule Breach was reported in December 2010 SAR.
The FY 2013 President's Budget canceled C-130 AMP. This results in both PAUC and APUC Unit Cost APB breaches, as well as critical Nunn-McCurdy breaches.
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC Critical
APUC Critical
Original UCR Baseline
PAUC Critical
APUC Critical

## Table 6
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B Complete | JUL 2001 | JUL 2001 | JAN 2002 | JUL 2001
Critical Design Review (CDR) | NOV 2005 | NOV 2005 | MAY 2006 | AUG 2005
Milestone C LRIP | MAR 2010 | MAR 2010 | SEP 2010 | JUN 2010
Operational Test Complete | JUL 2012 | JUL 2012 | JAN 2013 | N/A 1
Full Rate Production Decision | FEB 2013 | FEB 2013 | AUG 2013 | N/A 1
LRIP Installs Complete | DEC 2014 | DEC 2014 | JUN 2015 | N/A 1
1APB Breach
(Ch-1)
(Ch-1)
(Ch-1)
Change Explanations
(Ch-1) Program cancellation negates the need for Current Estimates for Operational Test Complete, Full Rate Production Decision, and LRIP Installs Complete milestones.

## Table 7
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
CNS/ATM & Nav- | Meet | Meet | Meet | Navigation | Meet
Safety Compliance | technical | technical | technical | system | technical
| performance | performance | performance | Accuracy | performance
| based | based | based | Criteria: | based
| standards | standards | standards | Cross track | standards
| for RNP and | for RNP and | for RNP and | and along- | for RNP and
| RNAV | RNAV | RNAV | track error of | RNAV
| airspace | airspace | airspace | <1 nautical | airspace
| IAW 2005 | IAW 2005 | IAW 2005 | miles 95% of | IAW 2005
| world- wide | world- wide | world- wide | the time, | world-wide
| CNS/ATM | CNS/ATM | CNS/ATM | meets RNP- | CNS/ATM
| standards as | standards as | standards as | 1, Basic | standards as
| they apply to | they apply to | they apply to | RNAV, and | they apply to
| C-130 | C-130 | C-130 | precision | C-130
| operations. | operations. | operations. | area | operations.
| Comply with | Comply with | Comply with | navigation | Comply with
| Air Force | Air Force | Air Force | operations. | Air Force
| Nav- Safety | Nav- Safety | Nav- Safety | Result: | Nav-Safety
| Master Plan | Master Plan | Master Plan | Parameters | Master Plan
| require- | require- | require- | met on the | require-
| ments. | ments. | ments. | ground. Ref: | ments.
2008-05-02
AFOTEC
OA Report
Baseline Cockpit | The cockpit | The cockpit | The cockpit | Percentage | The cockpit
Configuration | avionics | avionics | avionics | of | avionics
| architecture | architecture | architecture | Successful | architecture
| on all | on all | on all | Arrivals | on all
| combat | combat | combat | Criteria: > or | combat
| delivery | delivery | delivery | = to 90% of | delivery
| aircraft shall | aircraft shall | aircraft shall | missons | aircraft shall
| be optimized | be optimized | be optimized | meet AMC | be optimized
| to ensure the | to ensure the | to ensure the | Instruction | to ensure the
| aircraft can | aircraft can | aircraft can | 10-202, Vol | aircraft can
| effectively | effectively | effectively | 6 | effectively
| execute | execute | execute | requirements | execute
| current | current | current | and | current
| missions | missions | missions | applicable | missions
| throughout | throughout | throughout | AF | throughout
| the world | the world | the world | Instructions. | the world
| with a basic | with a basic | with a basic | Result: 85% | with a basic
| cockpit crew | cockpit crew | cockpit crew | successful. | cockpit crew
| of no greater | of no greater | of no greater | Ref: 2 May | of no greater
| than two | than two | than two | 08 AFOTEC | than two
| pilots and | pilots and | pilots and | OA report. | pilots and
| one flight | one flight | one flight | Human | one flight
| engineer | engineer | engineer | factor | engineer

## Table 8
| from their | from their | from their | workload | from their
| respective | respective | respective | assess- | respective
| crew | crew | crew | ments; | crew
| positions. | positions. | positions. | Integrated | positions.
System
Evaluation
Jul - Aug 09
Boeing final
human
factors test
complete -
Aug 09 Final
Air Force
Flight Test
Center
Human
Factors
complete -
Dec 09
Net Ready | The system | The system | The system | TBD | The system
| must fully | must fully | must fully |  | must fully
| support | support | support |  | support
| execution of | execution of | execution of |  | execution of
| all | all | joint critical |  | all
| operational | operational | operational |  | operational
| activities | activities | activities |  | activities
| identified in | identified in | identified in |  | identified in
| the | the | the |  | the
| applicable | applicable | applicable |  | applicable
| joint and | joint and | joint and |  | joint and
| system | system | system |  | system
| integrated | integrated | integrated |  | integrated
| architectures | architectures | architectures |  | architectures
| and the | and the | and the |  | and the
| system must | system must | system must |  | system must
| satisfy the | satisfy the | satisfy the |  | satisfy the
| technical | technical | technical |  | technical
| requirements | requirements | requirements |  | requirements
| for Net- | for Net- | for transition |  | for Net-
| Centric | Centric | to Net- |  | Centric
| military | military | Centric |  | military
| operations | operations | military |  | operations
| to include 1) | to include 1) | operations |  | to include 1)
| DISR | DISR | to include 1) |  | DISR
| mandated | mandated | DISR |  | mandated
| GIG IT | GIG IT | mandated |  | GIG IT
| standards | standards | GIG IT |  | standards
| and profiles | and profiles | standards |  | and profiles
| identified in | identified in | and profiles |  | identified in
| the TV-1, 2) | the TV-1, 2) | identified in |  | the TV-1, 2)
| DISR | DISR | the TV-1, 2) |  | DISR
| mandated | mandated | DISR |  | mandated
| GIG KIPs | GIG KIPs | mandated |  | GIG KIPs
| identified in | identified in | GIG KIPs |  | identified in

## Table 9
| the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability, integrity, authen- tication, confiden- tiality, and non- repudiation, and issuance of an ATO by the DAA and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views. | the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability, integrity, authen- tication, confiden- tiality, and non- repudiation, and issuance of an ATO by the DAA and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views. | identified in the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability, integrity, authen- tication, confiden- tiality, and non- repudiation, and issuance of an IATO by the DAA and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views. |  | the KIP declaration table, 3) NCOW RM Enterprise Services 4) Information assurance requirements including availability, integrity, authen- tication, confiden- tiality, and non- repudiation, and issuance of an ATO by the DAA and 5) Operationally effective information exchanges; and mission critical performance and information assurance attributes, data correctness, data availability, and consistent data processing specified in the applicable joint and system integrated architecture views.
Integrated Defensive System Situational Awareness | Use inputs from the AAR-47 | Use inputs from the AAR-47 | Use inputs from the AAR-47 | Initial ground and range flight testing | Use inputs from the AAR-47

## Table 10
| MWS, ALE- | MWS, ALE- | MWS, ALE- | completed. | MWS, ALE-
| 47 CMDS, | 47 CMDS, | 47 CMDS, |  | 47 CMDS,
| and ALR-69 | and ALR-69 | and ALR-69 |  | and ALR-69
| RWR to | RWR to | RWR to |  | RWR to
| generate an | generate an | generate an |  | generate an
| integrated | integrated | integrated |  | integrated
| defensive | defensive | defensive |  | defensive
| systems | systems | systems |  | systems
| capability | capability | capability |  | capability
| that displays | that displays | that displays |  | that displays
| proper | proper | proper |  | proper
| signal | signal | signal |  | signal
| detection, | detection, | detection, |  | detection,
| provides | provides | provides |  | provides
| appropriate | appropriate | appropriate |  | appropriate
| audio tones | audio tones | audio tones |  | audio tones
| and advisory | and advisory | and advisory |  | and advisory
| messages, | messages, | messages, |  | messages,
| triggers the | triggers the | triggers the |  | triggers the
| correct | correct | correct |  | correct
| automatic | automatic | automatic |  | automatic
| dispense | dispense | dispense |  | dispense
| responses, | responses, | responses, |  | responses,
| and provides | and provides | and provides |  | and provides
| a centralized | a centralized | a centralized |  | a centralized
| defensive | defensive | defensive |  | defensive
| systems | systems | systems |  | systems
| resource | resource | resource |  | resource
| status. | status. | status. |  | status.
Operations in a | Aircraft | Aircraft | Aircraft | Chem/Bio | Aircraft
Chemical/Biological | controls and | controls and | controls and | gear test | controls and
Environment | systems | systems | systems | accom- | systems
| modified by | modified by | modified by | plished | modified by
| AMP shall | AMP shall | AMP shall | successfully | AMP shall
| be operable | be operable | be operable | (per | be operable
| without | without | without | AFOTEC). | without
| degradation | degradation | degradation | Ref: 4 | degradation
| or | or | or | December | or
| operational | operational | operational | 2008 test on | operational
| constraints | constraints | constraints | AMP 1 at | constraints
| in a | in a | in a | EAFB. | in a
| chemical/ | chemical/ | chemical/ |  | chemical /
| biological | biological | biological |  | biological
| environment | environment | environment |  | environment
| with aircrew | with aircrew | with aircrew |  | with aircrew
| Chemical/ | Chemical/ | Chemical/ |  | Chemical /
| Biological | Biological | Biological |  | Biological
| protective | protective | protective |  | protective
| clothing | clothing | clothing |  | clothing.
Material Availability | AMP | AMP | AMP | AFOTEC | AMP
| NMCAMP | NMCAMP | NMCAMP | assessment | NMCAMP
| rate shall be | rate shall be | rate shall be | exceeds | rate shall be
| less than or | less than or | less than or | requirement; | less than or
| equal to 2.2 | equal to 2.2 | equal to 2.2 | 1.4% | equal to 2.2

## Table 11
| percent for | percent for | percent for | preliminary | percent for
| C-130 | C-130 | C-130 | verification | C-130
| H2/H2.5/ H3 | H2/H2.5/ H3 | H2/H2.5/ H3 | by AFOTEC. | H2/H2.5/H3
| fleet avionics | fleet avionics | fleet avionics |  | fleet avionics
| work unit | work unit | work unit |  | work unit
| codes. | codes. | codes. |  | codes.
Requirements Source: Capability Production Document (CPD) for C-130 AMP Initial Increment (V 3.1) March 4, 2008 (Joint Requirements Oversight Council Memo 051-08)
Acronyms And Abbreviations
AFI - Air Force Instruction
AFOTEC - Air Force Operational Test & Evaluation Center
AFROCC - Air Force Requirements for Operational Capability Council AMC - Air Mobility Command
ASACM - Advanced Situational Awareness and Countermeasures ATO - Approval to Operate
CJCSI - Chairman Joint Chief of Staff Instruction CMDS - Countermeasures Dispenser System
CNS/ATM - Communications, Navigation Surveillance/Air Traffic Management CPD - Capabilities Production Document
DAA - Designated Approval Authority
DISR - DOD Information Technology Standards and Profile Registry EAFB - Edwards Air Force Base
GIG - Global Information Grid
IATO - Interim Approval to Operate IAW - In Accordance With
IER - Information Exchange Requirement IP - Internet Protocol
IT - Information Technology
JITC - Joint Interoperability Test Command JTRS - Joint Tactical Radio System
KIP - Key Interface Profiles
KPP - Key Performance Parameter
NCOW RM - Net Centric Operations and Warfare Reference Model NMCAMP - Not Mission Capable AMP
OA - Operational Assessment RNAV - Area Navigation
RNP - Required Navigation Performance RWR - Radar Warning Receiver
TBD - To Be Determined USAF - United States Air Force
Change Explanations
None
Memo
OSD (AT&L) Acquisition Decision Memorandum (June 4, 2007) directed restructure of C-130 AMP to modernize C-130H2, C-130H2.5 and C-130H3 Mission Design Series only, eliminating Special Mission aircraft requirements. As a result, Performance Characteristics specifically related to Special Mission requirements have been deleted.

## Table 12
AMC's Capability Production Document (CPD) for C-130 AMP [Capability Production Document for C-130 AMP Initial Increment (V 3.1)], prepared for Milestone C Decision, identifies six Key Performance Parameters (KPPs) essential to mission accomplishment (Ref Table 6.1 in CPD) and are updates to existing KPPs. The existing Acquisition Performance Baseline Performance Characteristics have been deleted and replaced with the six KPPs identified in the CPD.
Time and Accuracy Standards defined in AFI 11-2C-130, Vol 2; cockpits shall meet the requirements of the USAF flight instrumentation endorsement process outlined in AFI 11-202 Vol. III, April 5, 2006.
Net Ready KPP: Defined in CJCSI 6212.01D, March 8, 2006. C-130 AMP will not meet the full intent of the Net- Ready KPP until an IP-enabled radio (e.g. JTRS) is developed, validated and integrated into the architecture.
However, 85-90% of the requirement can be met with the AMP design. In addition, the architecture has been designed to accommodate JTRS integration in the future. The incremental approach to satisfying this requirement has been coordinated with JITC, AFOTEC, the Joint Staff, and AMC.
Material Availability KPP: Not Mission Capable rate is calculated for the AMP work unit codes as described in AMC Supplement 1 to AFI 21-101 using the following formula: Not Mission Capable AMP (NMCAMP) is equal to the NMCAMP-Maintenance hours plus NMCAMP-both basic plus maintenance hours plus NMCAMP-supply hours divided by possessed hours times 100. AFOTEC assessment exceeds requirement; 1.4% preliminary verification.

## Table 13
Track To Budget
RDT&E
APPN 3600 BA 07 PE 0401115F (Air Force)
Project 4885 Air Force/Avionics
Modernization Program (AMP)
2012 is final year of 3600
(Sunk)
APPN 0400 | BA 07 Project F100CA | PE 0406404D DoD (SOF) | (DoD) | (Sunk)
2006 was final year of 0400.
Procurement
APPN 3010 | BA 05 | PE 0401115F | (Air Force)
| ICN C13000 ICN C1300A | Air Force Air Force | (Shared) | (Sunk) (Sunk)

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
| BY2010 $M |  |  |  |  | BY2010 $M |  | TY $M
Appropriation | SAR Baseline Prod Est |  | Current APB Production Objective/Threshold |  |  | Current Estimate |  | SAR Baseline Prod Est | Current APB Production Objective | Current Estimate
RDT&E | 1874.9 |  | 1874.9 |  | 2062.4 | 1859.3 |  | 1753.3 | 1753.3 | 1741.5
Procurement | 4055.3 |  | 4055.3 |  | 4460.8 | 437.3 |  | 4547 | 4547 | 458.1
Flyaway | 3602.3 |  | -- |  | -- | 80.3 |  | 4043.4 | -- | 81.2
Recurring | 3602.3 |  | -- |  | -- | 80.3 |  | 4043.4 | -- | 81.2
Non Recurring | 0 |  | -- |  | -- | 0 |  | 0 | -- | 0
Support | 453 |  | -- |  | -- | 357 |  | 503.6 | -- | 376.9
Other Support | 362.9 |  | -- |  | -- | 354 |  | 402.4 | -- | 373.9
Initial Spares | 90.1 |  | -- |  | -- | 3 |  | 101.2 | -- | 3
MILCON | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Acq O&M | 0 |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Total | 5930.2 |  | 5930.2 |  | N/A | 2296.6 |  | 6300.3 | 6300.3 | 2199.6
Confidence Levels for Current Acquisition Program Baseline Cost: The Independent Cost Estimate to support the C-130 AMP Milestone C decision in March 2010, like all life-cycle cost estimates previously performed by the Cost Assessment and Program Evaluation, is built upon a product-oriented work breakdown structure, based on historical actual cost information to the maximum extent possible, and, most importantly, based on conservative assumptions that are consistent with actual demonstrated contractor and government performance for a series of acquisition programs in which the Department has been successful.
It is difficult to calculate mathematically the precise confidence levels associated with life-cycle cost estimates prepared for Major Defense Acquisition Programs. Based on the rigor in methods used in building estimates, the strong adherence to the collection and use of historical cost information, and the review of applied assumptions, we project that it is about equally likely that the estimate will prove too low or too high for execution of the program described.
In December 2011, the Program Office Estimate assessed both the development and production programs as relatively low risk: the C-130 AMP has entered Low Rate Initial Production with little technology risk, all technology readiness ratings seven or higher, and the requirements well defined.
Quantity |  | SAR Baseline Prod Est |  | Current APB Production |  |  | Current Estimate
RDT&E |  | 3 |  | 3 |  |  | 3
Procurement |  | 218 |  | 218 |  |  | 6
Total |  | 221 |  | 221 |  |  | 9
The unit of measure is a modified aircraft.

## Table 15
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2013 President's Budget / December 2011 SAR (TY$ M)
The FY 2013 President's Budget cancelled C-130 AMP.
Appropriation |  | Prior | FY2012 |  | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
RDT&E |  | 1735 | 6.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1741.5
Procurement |  | 250 | 208.1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 458.1
MILCON |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2013 Total |  | 1985 | 214.6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2199.6
PB 2012 Total |  | 2100.8 | 260.1 |  | 267.1 |  | 372.8 |  | 557.2 |  | 699.5 |  | 739.1 |  | 1459.1 |  | 6455.7
Delta |  | -115.8 | -45.5 |  | -267.1 |  | -372.8 |  | -557.2 |  | -699.5 |  | -739.1 |  | -1459.1 |  | -4256.1
Quantity | Undistributed |  |  | Prior |  | FY2012 |  | FY2013 | FY2014 | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
Development | 3 |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 3
Production | 0 |  |  | 6 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 6
PB 2013 Total | 3 |  |  | 6 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 9
PB 2012 Total | 3 |  |  | 10 |  | 8 |  | 8 | 20 | 32 |  | 39 |  | 39 |  | 62 |  | 221
Delta | 0 |  |  | -4 |  | -8 |  | -8 | -20 | -32 |  | -39 |  | -39 |  | -62 |  | -212

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2001 | -- | -- | -- | -- | -- | -- | 6.7
2002 | -- | -- | -- | -- | -- | -- | 13
2003 | -- | -- | -- | -- | -- | -- | 49.1
2004 | -- | -- | -- | -- | -- | -- | 62.4
2005 | -- | -- | -- | -- | -- | -- | 65.3
2006 | -- | -- | -- | -- | -- | -- | 61.4
Subtotal | -- | -- | -- | -- | -- | -- | 257.9

## Table 17
Annual Funding BY$
0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2010 $M | Non End Item Recurring Flyaway BY 2010 $M | Non Recurring Flyaway BY 2010 $M | Total Flyaway BY 2010 $M | Total Support BY 2010 $M | Total Program BY 2010 $M
2001 | -- | -- | -- | -- | -- | -- | 7.9
2002 | -- | -- | -- | -- | -- | -- | 15.1
2003 | -- | -- | -- | -- | -- | -- | 56.3
2004 | -- | -- | -- | -- | -- | -- | 69.9
2005 | -- | -- | -- | -- | -- | -- | 71.1
2006 | -- | -- | -- | -- | -- | -- | 64.9
Subtotal | -- | -- | -- | -- | -- | -- | 285.2

## Table 18
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1999 | -- | -- | -- | -- | -- | -- | 1.7
2000 | -- | -- | -- | -- | -- | -- | 8.6
2001 | -- | -- | -- | -- | -- | -- | 60.3
2002 | -- | -- | -- | -- | -- | -- | 49.2
2003 | -- | -- | -- | -- | -- | -- | 122.7
2004 | -- | -- | -- | -- | -- | -- | 111.8
2005 | -- | -- | -- | -- | -- | -- | 155.9
2006 | -- | -- | -- | -- | -- | -- | 248.5
2007 | -- | -- | -- | -- | -- | -- | 182.4
2008 | -- | -- | -- | -- | -- | -- | 229.8
2009 | -- | -- | -- | -- | -- | -- | 161.8
2010 | -- | -- | -- | -- | -- | -- | 102.3
2011 | -- | -- | -- | -- | -- | -- | 42.1
2012 | -- | -- | -- | -- | -- | -- | 6.5
Subtotal | 3 | -- | -- | -- | -- | -- | 1483.6

## Table 19
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2010 $M | Non End Item Recurring Flyaway BY 2010 $M | Non Recurring Flyaway BY 2010 $M | Total Flyaway BY 2010 $M | Total Support BY 2010 $M | Total Program BY 2010 $M
1999 | -- | -- | -- | -- | -- | -- | 2.1
2000 | -- | -- | -- | -- | -- | -- | 10.3
2001 | -- | -- | -- | -- | -- | -- | 71.1
2002 | -- | -- | -- | -- | -- | -- | 57.4
2003 | -- | -- | -- | -- | -- | -- | 141.1
2004 | -- | -- | -- | -- | -- | -- | 125.5
2005 | -- | -- | -- | -- | -- | -- | 170.6
2006 | -- | -- | -- | -- | -- | -- | 264
2007 | -- | -- | -- | -- | -- | -- | 188.8
2008 | -- | -- | -- | -- | -- | -- | 233.1
2009 | -- | -- | -- | -- | -- | -- | 162
2010 | -- | -- | -- | -- | -- | -- | 101.1
2011 | -- | -- | -- | -- | -- | -- | 40.8
2012 | -- | -- | -- | -- | -- | -- | 6.2
Subtotal | 3 | -- | -- | -- | -- | -- | 1574.1

## Table 20
Annual Funding TY$
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2008 | 2 | 19.3 | -- | -- | 19.3 | 1.9 | 21.2
2009 | 4 | 61.9 | -- | -- | 61.9 | 69.7 | 131.6
2010 | -- | -- | -- | -- | -- | -- | --
2011 | -- | -- | -- | -- | -- | 97.2 | 97.2
2012 | -- | -- | -- | -- | -- | 208.1 | 208.1
Subtotal | 6 | 81.2 | -- | -- | 81.2 | 376.9 | 458.1

## Table 21
Annual Funding BY$
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2010 $M |  | Non End Item Recurring Flyaway BY 2010 $M | Non Recurring Flyaway BY 2010 $M |  | Total Flyaway BY 2010 $M | Total Support BY 2010 $M | Total Program BY 2010 $M
2008 | 2 | 19.3 |  | -- | -- |  | 19.3 | 1.9 | 21.2
2009 | 4 | 61 |  | -- | -- |  | 61 | 68.6 | 129.6
2010 | -- | -- |  | -- | -- |  | -- | -- | --
2011 | -- | -- |  | -- | -- |  | -- | 92.3 | 92.3
2012 | -- | -- |  | -- | -- |  | -- | 194.2 | 194.2
Subtotal | 6 | 80.3 |  | -- | -- |  | 80.3 | 357 | 437.3
Low Rate Initial Production
|  |  | Initial LRIP Decision |  |  | Current Total LRIP
Approval Date |  |  | 7/27/2001 2/13/2012 50 2 M/S B ADM 2013 President's Budget 2005 2008 2014 2012
Approved Quantity
Reference
Start Year
End Year
The first of two current Lot 1 LRIP aircraft (AMP #4) completed installation at Robins Air Force Base and delivered to Little Rock Air Force Base for Initial Operational Test & Evaluation (IOT&E) start in January 2012. The second (AMP
#5) is scheduled for installation completion and delivery in March 2012. C-130 AMP IOT&E has been indefinitely postponed.
Quantity of 2 Current Total LRIP Approved exceeds 10% of total production quantity of 6 due to decrease of 212 aircraft from 218 in the FY 2013 President's Budget .

## Table 22
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Memo
Sweden 1/31/2005 8 99.9 On July 1, 2009 Sweden’s Defense Materiel
Administration sent an informal notification to the Assistant Secretary of the Air Force for International Affairs (SAF/IA) that the program had been canceled. The Program Office telephoned Boeing Long Beach in July 2009 to alert them of informal notification. The Program Office received a formal letter via SAF/IA in July 2009 and issued the termination letter to Boeing Long Beach in August 2009. Boeing issued a Termination Settlement Proposal in June 2010 in amount of $25M. Settlement negotiations are still ongoing.
Nuclear Cost
None

## Table 23
Unit Cost
Unit Cost Report
|  | BY2010 $M | BY2010 $M
Unit Cost |  | Current UCR Baseline (APR 2010 APB) | Current Estimate (DEC 2011 SAR) |  |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 5930.2 |  |  | 2296.6
Quantity | 221 |  |  | 9
Unit Cost | 26.833 |  |  | 255.178 |  |  | +850.99 1
Average Procurement Unit Cost (APUC)
Cost | 4055.3 |  |  | 437.3
Quantity | 218 |  |  | 6
Unit Cost | 18.602 |  |  | 72.883 |  |  | +291.80 1
|  | BY2010 $M | BY2010 $M
Unit Cost |  | Revised Original UCR Baseline (FEB 2008 APB) | Current Estimate (DEC 2011 SAR) |  |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 5610.8 |  |  | 2296.6
Quantity | 222 |  |  | 9
Unit Cost | 25.274 |  |  | 255.178 |  |  | +909.65 1
Average Procurement Unit Cost (APUC)
Cost | 3510.2 |  |  | 437.3
Quantity | 219 |  |  | 6
Unit Cost | 16.028 |  |  | 72.883 |  |  | +354.72 1
TY $M
Unit Cost |  | Current UCR Baseline (APR 2010 APB) | Current Estimate (DEC 2011 SAR) |  | TY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 6300.3 |  |  | 2199.6
Unit Cost | 28.508 |  |  | 244.4 |  |  | 757.3
Average Procurement Unit Cost (APUC)
Cost | 4547 |  |  | 458.1
Unit Cost | 20.858 |  |  | 76.35 |  |  | 266.05

## Table 24
TY $M
Unit Cost |  |  | Revised Original UCR Baseline (FEB 2008 APB) |  |  | Current Estimate (DEC 2011 SAR) |  |  |  | TY % Change
Program Acquisition Unit Cost (PAUC)
Cost |  | 5910.1 |  |  |  |  | 2199.6
Unit Cost |  | 26.622 |  |  |  |  | 244.4 |  |  |  | 818.04
Average Procurement Unit Cost (APUC)
Cost |  | 3982.7 |  |  |  |  | 458.1
Unit Cost |  | 18.186 |  |  |  |  | 76.35 |  |  |  | 319.83
1 Nunn-McCurdy Breach
The FY 2013 President's Budget cancelled C-130 AMP. The program is currently developing its cancellation plan.
Unit Cost Breach Data
PAUC (BY $M) |  |  |  |  | 255.178 |  |  |  | 833.69
APUC (BY $M) |  |  |  |  | 72.883 |  |  |  | 283.47
PAUC Quantity |  |  |  |  | 9 |  |  |  | 0
PAUC (TY $M) |  |  |  |  | 244.4 |  |  |  | 736.67
APUC (TY $M) |  |  |  |  | 76.35 |  |  |  | 255.93
Initial SAR Information DEC 2001 |  |  |  |  | BY2000 $M |  |  |  | TY $M
Program Acquisition Cost |  |  |  |  | 3333.9 |  |  |  | 3965.4
Changes from Previous SAR |  |  |  | $M/Qty. |  |  |  | Percent
Unit Cost PAUC Changes
The FY 2013 President's Budget cancelled C-130 AMP.
Unit Cost APUC Changes
The FY 2013 President's Budget cancelled C-130 AMP.

## Table 25
Unit Cost History
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
[12 empty] | BY2010 $M | [6 empty] | TY $M
[5 empty] | Date | [6 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  |  |  | JUL 2001 | [6 empty] | 7.767 |  |  | 6.497 |  |  |  | 7.64 |  |  | 6.538
APB as of January 2006 |  |  |  |  | MAR 2003 | [6 empty] | 9.662 |  |  | 7.201 |  |  |  | 9.376 |  |  | 7.208
Revised Original APB |  |  |  |  | FEB 2008 | [6 empty] | 25.274 |  |  | 16.028 |  |  |  | 26.622 |  |  | 18.186
Prior APB |  |  |  |  | FEB 2008 | [6 empty] | 25.274 |  |  | 16.028 |  |  |  | 26.622 |  |  | 18.186
Current APB |  |  |  |  | APR 2010 | [6 empty] | 26.833 |  |  | 18.602 |  |  |  | 28.508 |  |  | 20.858
Prior Annual SAR |  |  |  |  | DEC 2010 | [6 empty] | 27.33 |  |  | 19.006 |  |  |  | 29.211 |  |  | 21.451
Current Estimate |  |  |  |  | DEC 2011 | [6 empty] | 255.178 |  |  | 72.883 |  |  |  | 244.4 |  |  | 76.35
Initial PAUC Dev Est | Changes | [19 empty] | PAUC Prod Est
| Econ |  | Qty |  |  | Sch |  | Eng |  |  | Est |  |  | Oth |  | Spt |  | Total
7.640 -1.393 5.276 1.385 0.351 13.620 0.000 1.629 20.868 28.508
Current SAR Baseline to Current Estimate (TY $M)
PAUC Prod Est |  | Changes | [17 empty] | PAUC Current Est
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  |  | Oth |  | Spt |  | Total
28.508 7.744 238.670 -5.989 0.722 -10.433 0.000 -14.822 215.892 244.400

## Table 26
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Dev Est | Changes | [12 empty] | APUC Prod Est
| Econ | Qty |  | Sch | Eng |  | Est |  | Oth | Spt |  | Total
6.538 -1.455 3.351 0.858 0.000 9.915 0.000 1.651 14.320 20.858
Current SAR Baseline to Current Estimate (TY $M)
APUC Prod Est | Changes | [12 empty] | APUC Current Est
| Econ | Qty |  | Sch |  | Eng |  | Est | Oth | Spt |  |  | Total
20.858 10.800 87.692 -12.233 0.000 -8.533 0.000 -22.233 55.492 76.350
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  |  |  | SAR Development Estimate (DE) |  |  | SAR Production Estimate (PdE) |  |  |  | Current Estimate
Milestone A |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  |  | N/A
Milestone B |  |  | N/A |  |  |  |  | N/A |  |  | JUL 2001 |  |  |  | JUL 2001
Milestone C |  |  | N/A |  |  |  |  | JAN 2007 |  |  | MAR 2010 |  |  |  | JUN 2010
IOC |  |  | N/A |  |  |  |  | N/A |  |  | N/A |  |  |  | N/A
Total Cost (TY $M) |  |  | N/A |  |  |  |  | 3965.4 |  |  | 6300.3 |  |  |  | 2199.6
Total Quantity |  |  | N/A |  |  |  |  | 519 |  |  | 221 |  |  |  | 9
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  |  |  | 7.64 |  |  | 28.508 |  |  |  | 244.4

## Table 27
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Prod Est) | 1753.3 | 4547 | -- | 6300.3
Previous Changes
Economic | 3.1 | -5.2 | -- | -2.1
Quantity | -- | -- | -- | --
Schedule | 19.5 | 60.9 | -- | 80.4
Engineering | 6.5 | -- | -- | 6.5
Estimating | -3.1 | 40.2 | -- | 37.1
Other | -- | -- | -- | --
Support | -- | 33.5 | -- | 33.5
Subtotal | 26 | 129.4 | -- | 155.4
Current Changes
Economic | 1.8 | 70 | -- | 71.8
Quantity | -- | -3895.7 | -- | -3895.7
Schedule | -- | -134.3 | -- | -134.3
Engineering | -- | -- | -- | --
Estimating | -39.6 | -91.4 | -- | -131
Other | -- | -- | -- | --
Support | -- | -166.9 | -- | -166.9
Subtotal | -37.8 | -4218.3 | -- | -4256.1
Total Changes | -11.8 | -4088.9 | -- | -4100.7
CE - Cost Variance | 1741.5 | 458.1 | -- | 2199.6
CE - Cost & Funding | 1741.5 | 458.1 | -- | 2199.6

## Table 28
Summary Base Year 2010 $M
| RDT&E |  | Proc | MILCON | Total
SAR Baseline (Prod Est) Previous Changes |  | 1874.9 | 4055.3 | -- | 5930.2
Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | 18.4 | 17.7 | -- | 36.1
Engineering |  | 6.5 | -- | -- | 6.5
Estimating |  | -3.1 | 34.8 | -- | 31.7
Other |  | -- | -- | -- | --
Support |  | -- | 35.4 | -- | 35.4
Subtotal |  | 21.8 | 87.9 | -- | 109.7
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -3384.5 | -- | -3384.5
Schedule |  | -- | -112.1 | -- | -112.1
Engineering |  | -- | -- | -- | --
Estimating |  | -37.4 | -77.9 | -- | -115.3
Other |  | -- | -- | -- | --
Support |  | -- | -131.4 | -- | -131.4
Subtotal |  | -37.4 | -3705.9 | -- | -3743.3
Total Changes |  | -15.6 | -3618 | -- | -3633.6
CE - Cost Variance |  | 1859.3 | 437.3 | -- | 2296.6
CE - Cost & Funding |  | 1859.3 | 437.3 | -- | 2296.6
Previous Estimate: December 2010

## Table 29
RDT&E |  | $M
Current Change Explanations |  | Base Year |  | Then Year
Revised escalation indices. (Economic) |  | N/A |  | 1.8
Decrease due to Air Force withholds for higher priority programs. (Estimating) |  | -18.4 |  | -19.4
Decrease due to program cancellation of funding in FY 2013 President's Budget. (Estimating) |  | -17.5 |  | -18.7
Adjustment for current and prior escalation. (Estimating) |  | -1.5 |  | -1.5
RDT&E Subtotal |  | -37.4 |  | -37.8
Procurement |  | $M
Current Change Explanations |  | Base Year |  | Then Year
Revised escalation indices. (Economic) N/A +70.0
Total Quantity variance resulting from a decrease of 212 aircraft from 218 to 6. (Subtotal)
Quantity variance resulting from a decrease of 212 aircraft from 218 to 6. (Quantity)
-3734.9 -4305.7
(-3548.8) (-4085.5)
Allocation to Schedule resulting from Quantity change. (Schedule) (QR) | -112.1 |  | -132.8
Allocation to Estimating resulting from Quantity change. (Estimating) (QR) | -74 |  | -87.4
Additional Quantity variance resulting from Quantity change due to cancellation. (Quantity)
Decrease in Schedule variance due to rephasing of Low Rate Initial Production (LRIP) procurement. (Schedule) (QR)
+164.3 +189.8
0.0 -1.5
Adjustment for current and prior escalation. (Estimating) |  | -3.9 |  |  | -4
Decrease in Other Support due to rephasing of LRIP procurement. (Support) (QR) |  | -26.5 |  |  | -46.2
Adjustment for current and prior escalation. (Support) |  | -1.5 |  |  | -1.7
Decrease in Initial Spares resulting from Quantity change due to cancellation. (Support) |  | -103.4 |  |  | -119
Procurement Subtotal |  | -3705.9 |  |  | -4218.3
(QR) Quantity Related

## Table 30
Contracts
Appropriation: RDT&E
Contract Name C-130 AMP (LRIP)
Contractor THE BOEING COMPANY
Contractor Location 2401 E. WARDLOW RD
LONG BEACH, CA 90807-5309
Contract Number, Type FA8625-08-C-6481, FFP
Award Date September 30, 2008
Definitization Date March 02, 2010
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
36.7 N/A 2 172.3 N/A 6 172.3 172.3
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
The difference between the initial contract price target and the current contract price target is due to Contract modifications
Delivered Quantity under Contract Deliveries means AMP kits from Boeing. The first Low Rate Initial Production aircraft (AMP #4) delivered to Little Rock Air Force Base on January 3, 2012. The second (AMP #5) is completing its installation modification at Warner Robins Air Logistics Center with an estimated delivery during March 2012.

## Table 31
Deliveries and Expenditures
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 3 |  | 3 |  | 3 | 100%
Production | 2 |  | 1 |  | 6 | 16.67%
Total Program Quantities Delivered | 5 |  | 4 |  | 9 | 44.44%
Expenditures and |  | Appropriations (TY $M)
Total Acquisition Cost | 2199.6 | Years Appropriated |  |  | 14
Expenditures To Date | 1733.4 | Percent Years Appropriated |  |  | 100%
Percent Expended | 78.81% | Appropriated to Date |  |  | 2199.6
Total Funding Years | 14 | Percent Appropriated |  |  | 100%

## Table 32
Operating and Support Cost
Assumptions And Ground Rules
The Table below does not include Unit-Level Manpower since it represents a savings for C-130 AMP of $172.6K (Base Year 2010) per aircraft per year. Therefore, the Total Unitized O&S Cost (Base Year 2010) equals $71.6K for a steady state period. Total O&S costs also include ramp up and ramp down costs that would not be in the steady state per unit cost. Therefore, the product of per unit aircraft cost, number of aircraft, and steady state period will not equal the total O&S costs Costs shown are deltas to the existing O&S costs for the C-130 Combat Delivery fleet of 221 aircraft.
C-130 AMP O&S Program Office Estimate provided December 2011 by Aeronautical Systems Center Financial Management.
Unit Cost Breakout (BY)
The Table below does not include Unit-Level Manpower since it represents a savings for C-130 AMP of $172.6K (Base Year 2010$) per aircraft per year. Therefore, the Total Unitized O&S Cost (Base Year 2010$) equals
$71.6K.
Each aircraft in inventory 20 years; total Life Cycle FY 2010 - FY 2042
There is no antecedent system for this modernization.
Costs BY2010 $K
Cost Element | C-130 AMP Annual Cost Per Aircraft | No Antecedent
Unit-Level Manpower | -- | --
Unit Operations | 172.2 | --
Maintenance | -- | --
Sustaining Support | 70.9 | --
Continuing System Improvements | -- | --
Indirect Support | 1.2 | --
Other | -- | --
Total Unitized Cost (Base Year 2010 $) | 244.3 | --
Total O&S Costs $M | C-130 AMP | No Antecedent
Base Year | 496.5 | --
Then Year | 561.9 | --
C-130 AMP O&S estimate update provided December 2011 by Aeronautical System Center Financial Management.