## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-549
F/A-18E/F Super Hornet Aircraft (F/A-18E/F)
As of December 31, 2012
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 4
Executive Summary |  | 5
Threshold Breaches |  | 6
Schedule |  | 7
Performance |  | 10
Track To Budget |  | 13
Cost and Funding |  | 14
Low Rate Initial Production |  | 21
Foreign Military Sales |  | 22
Nuclear Cost |  | 22
Unit Cost |  | 23
Cost Variance |  | 26
Contracts |  | 29
Deliveries and Expenditures |  | 33
Operating and Support Cost |  | 34

## Table 3
Program Information
Program Name
F/A-18E/F Super Hornet Aircraft (F/A-18E/F)
DoD Component
Navy
Responsible Office
Responsible Office
CAPT Frank Morley, USN | Phone | 301-757-7669
Program Executive Officer (PMA265) | Fax | 301-757-7520
Bldg 2272, Suite 445 NAVAIRSYSCOMHQ | DSN Phone | 757-7669
47123 Buse Road, Unit IPT Patuxent River, MD 20670-1547 | DSN Fax | 757-7520
francis.morley@navy.mil | Date Assigned | July 14, 2011
References
SAR Baseline (Production Estimate)
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated September 17, 2000
Approved APB
Navy Acquisition Executive (NAE) Approved Acquisition Program Baseline (APB) dated February 15, 2011

## Table 4
Mission and Description
The F/A-18E/F Super Hornet is the second major model upgrade since the inception of the F/A-18 aircraft program. The single-seat F/A-18E and the two-seat F/A-18F are high performance, twin-engine, mid-wing, and multi-mission tactical aircraft designed to replace the F/A-18C (single-seat) and F/A-18D (two-seat) aircraft as they reach the end of their service lives and retire. The F/A-18E/F is designed to meet current Navy fighter escort and interdiction mission requirements, to maintain F/A-18 fleet air defense and close air support roles, as well as an increasing range of missions, including Forward Air Controller (Airborne) and Aerial Tanking, as the F/A-18E/F has proven capability to replace the S-3 as an aerial tanker. F/A-18E/F enhancements include increased range and improved carrier suitability required for the F/A-18 to continue its key strike fighter role against the advanced threats of the 21st century.

## Table 5
Executive Summary
The program continues to excel. Cost, schedule, and performance were superb during this reporting period, and the program continues to deliver aircraft ahead of schedule. As of March 27, 2013, the program has delivered 506 aircraft to the fleet (62 Low Rate Initial Production (LRIP) and 444 Full Rate Production (FRP)). This report solely reflects the domestic Program of Record (PoR) quantities.
As of January 30, 2013, Super Hornet aircraft have flown over 1,131,122 hours.
The F/A-18E/F and EA-18G are software-intensive systems that share a common Operational Flight Program (OFP). The current OFP is the H6E System Configuration Set (SCS), which was released to the fleet in October 2011. The H8E SCS represents the latest software upgrade that will replace the H6E SCS following Operational Test (OT). The program office delayed H8E entry into OT by four months to correct weapon integration and interoperability issues. The issues were resolved, and OT began in June 2012. H8E fleet release is scheduled for July 2013. Therefore, there are no significant software-related issues with this program at this time.
Because the program is more than 90 percent delivered, this is the final SAR submission for the F/A-18E/F Super Hornet Aircraft program (pursuant to section 2432 of title 10, United States Code).

## Table 6
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
O&S Cost
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 7
Schedule

## Table 8
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone IV/II | MAR 1992 | MAR 1992 | SEP 1992 | MAY 1992
First Engine to Test | APR 1993 | APR 1993 | OCT 1993 | MAY 1993
Preliminary Design Review (Airframe) | APR 1993 | APR 1993 | OCT 1993 | JUN 1993
Critical Design Review (Airframe) | JAN 1994 | JAN 1994 | JUL 1994 | JUL 1994
Production Readiness Review (Airframe) | APR 1995 | APR 1995 | OCT 1995 | AUG 1995
Preliminary Flight Qualification (Engine) | MAR 1995 | MAR 1995 | SEP 1995 | SEP 1995
First Flight | OCT 1995 | OCT 1995 | APR 1996 | NOV 1995
Long Lead Release for LRIP | DEC 1995 | DEC 1995 | JUN 1996 | MAR 1996
LRIP Decision Milestone | MAR 1997 | MAR 1997 | SEP 1997 | MAR 1997
Limited Production Qualification (Engine) | MAR 1997 | MAR 1997 | SEP 1997 | APR 1997
LRIP Contract Award | JAN 1997 | JAN 1997 | JUL 1997 | MAY 1997
Full Production Qualification (Engine) | AUG 1998 | AUG 1998 | FEB 1999 | DEC 1998
LRIP First Delivery | DEC 1998 | DEC 1998 | JUN 1999 | DEC 1998
Milestone III | JAN 2000 | JAN 2000 | JUL 2000 | JUN 2000
Full Rate Production Contract Award | JAN 2000 | JAN 2000 | JUL 2000 | JUN 2000
DT&E
DT-IIA | OCT 1995 | OCT 1995 | APR 1996 | NOV 1995
DT-IIB | NOV 1996 | NOV 1996 | MAY 1997 | DEC 1996
DT-IIC | NOV 1997 | NOV 1997 | MAY 1998 | DEC 1997
DT-IID | JUL 1998 | JUL 1998 | JAN 1999 | OCT 1998
DT-IIE | OCT 1998 | OCT 1998 | APR 1999 | APR 1999
IOT&E
OT-IIA | NOV 1997 | NOV 1997 | MAY 1998 | NOV 1997
OT-IIB | DEC 1997 | DEC 1997 | JUN 1998 | JUN 1998
OT-IIC | MAR 1999 | MAR 1999 | SEP 1999 | MAY 1999
O-Level Maintenance Capability (OPEVAL) | MAR 1999 | MAR 1999 | SEP 1999 | MAY 1999
IOC | JUN 2001 | JUN 2001 | DEC 2001 | SEP 2001
I-Level Maintenance Capability
WRA TPS and Modified TPSs (IOC) | SEP 2000 | SEP 2000 | MAR 2001 | SEP 2000
New SRA TPS (IOC + one year) | SEP 2001 | SEP 2001 | MAR 2002 | SEP 2001
Material Support Date | OCT 2002 | OCT 2002 | APR 2003 | APR 2003
Navy Support Date | OCT 2003 | OCT 2003 | APR 2004 | MAR 2004
D-Level Maintenance Capability | OCT 2003 | OCT 2003 | APR 2004 | MAR 2004

## Table 9
Acronyms And Abbreviations
DT - Developmental Testing
DT&E - Developmental Test and Evaluation IOC - Initial Operational Capability
IOT&E - Initial Operational Test and Evaluation LRIP - Low Rate Initial Production
OPEVAL - Operational Evaluation OT - Operational Testing
SRA - Shop Replaceable Assembly TPS - Test Program Set
WRA - Weapon Replaceable Assembly
Change Explanations
None

## Table 10
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Interoperability of the F/A-18E/F Communications & Data Link Suite | Achieve all IERs | Achieve all IERs | Achieve all Critical IERs | Achieve all Critical IERs | Achieve all Critical IERs
Deck Spot Factor (F/A- 18A/B/C/D =1.2) | <= 1.4 | <= 1.4 | <1.5 | 1.46 | 1.46
Fighter Escort Radius (F/A-18E)(internal fuel) (Nm) | >=425 | >=425 | >=410 | 462 | 434
Interdiction Mission Radius (Nm)
2 external tanks (retained) | >=400 | >=400 | >=390 | 444 | 419
3 external tanks (retained) | >=450 | >=450 | >=430 | 489 | 463
Combat Ceiling (max thrust) (ft) | >50000 | >50000 | >=50000 | 52300 | 51948
Launch: Catapult WOD (C-13-1 Catapult MAXTOGW (kts)) | <=25 | <=25 | <=30 | 19 | 19
Recovery: WOD (MK- 7MOD 3) (kts) | <=10 | <=10 | <=15 | 8 | 8
Recovery Payload (lbs) | >9000 | >9000 | >=9000 | 9494 | 9327
Usable Load Factor (Subsonic; Nz) (G's) | >= +7.5 | >= +7.5 | >= +7.5 | 7.5 | 7.5
Specific Excess Power (Max Thrust, .9M, 1G, 10kft) (fps) | >=650 | >=650 | >600 | 648 | 631
Acceleration (.8M to 1.2M at 35kft) (sec) | <=60 | <=60 | <70 | 65 | 69
Additional Internal Fuel Capacity (lbs) (greater than C/D) | >=3000 | >=3000 | >=3000 | 4090 | 4090
Mean Time Between Operational Mission Failure (MTBOMF) (Replaces MFHBF) | >=3.2 | >=3.2 | >=2.6 | 10 | 9.3
Direct Maintenance Manhours per Flight Hour (DMMH/FH) (Replaces MH/FH) | <=5.0 | <=5.0 | <=9.0 | 6.4 | 5.9

## Table 11
Speed (Mach) Fighter Escort Mission Configuration @10,000 ft with Intermediate Rated Thrust | 0.98 | 0.98 | 0.96 | 0.96 | 0.96
Empty Weight (lbs) | 29950 | 29950 | 31950 | 30801 | 30968
Built-In Test (All Avionics)
Fault Detection (%) | 75 | 75 | 65 | 94.5 | 98.9
Fault Isolation (%) | 90 | 90 | 85 | 90.5 | 97.6
False Alarm Rate (%) | 30 | 30 | 45 | 33.5 | 39.6
Approach Speed (kts) | <=140 | <=140 | <=150 | 142 | 142
Requirements Source: Operational Requirements Document (ORD) dated March 22, 2000
Acronyms And Abbreviations
fps - feet per second Ft - Feet
G - Gravitational Acceleration
IER - Information Exchange Requirement kft - Thousand Feet
kts - knots lbs - pounds
M - Mach Number
MAX TOGW - Maximum Take Off Gross Weight MFHBF - Mean Flight Hours Between Failure MH/FH - Maintenance Hours per Flight Hour Nm - Nautical Mile/s
Nz - Normal Load Factor, Normal Acceleration sec - second
WOD - Wind Over Deck
Change Explanations
None
Memo
Interdiction Mission Radius, Recovery Payload, Specific Excess Power, Additional Internal Fuel Capacity, Launch Wind Over Deck and Acceleration Time are estimates based on the F/A-18E aircraft.
Interdiction Mission Radius Nautical Miles payload with:
a. 2 external tanks + 2 Airborne Intercept Missile (AIM) -9 + 4 MK 83 Low Drag (LD) on Low Drag Pylons + Forward Looking Infrared Radar/Navigation Forward Looking Infrared Radar (FLIR/NAVFLIR).
b. 3 external tanks + 2 AIM-9 + 4 MK 83 LD on Low Drag Pylons + Forward Looking Infrared Radar/Navigation Forward Looking Infrared Radar (FLIR/NAVFLIR).
MK is part of a serial number; it is not an acronym or an abbreviation.

## Table 12
Current estimated performance is based on Lot 35 Full Rate Production (FRP) 12 configuration as of January 2013.
Recovery Payload: F/A-18F: 44,000 Carrier Landing Design Gross Weight (CLDGW). The F/A-18E/F at Initial Operating Capability (IOC) provided for a threshold/objective of 9,000 pounds of recovery payload.
Specific Excess Power: F/A-18E: (2) AIM-9 + (2) AIM-120 + Gun and Ammo with 60% internal fuel; and the equivalent design gross weight for the F/A-18F.

## Table 13
Track To Budget
RDT&E
APPN 1319 | BA 07 | PE 0204136N | (Navy)
| Project E2130 | (E2130) F/A-18 Squadrons/Follow-on Variant | (Sunk)
Procurement
APPN 1506 | BA 01 | PE 0204136N | (Navy)
| ICN 0145 | APN 1 F/A-18E/F (Fighter) Hornet (MYP)
APPN 1506 | BA 06 | PE 0204136N | (Navy)
| ICN 0605 | APN 6 Spares | (Shared)

## Table 14
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
|  | BY2000 $M | [6 empty] | BY2000 $M
Appropriation |  | SAR Baseline Prod Est |  |  | Current APB Production Objective/Threshold |  |  |  | Current Estimate
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  |  | Current Estimate
RDT&E |  | 5889.4 |  |  |  | 5895.2 |  | 6484.7 |  | 5895.2 |  | 5574 | 5557.6 | 5557.6
Procurement |  | 32995.3 |  |  |  | 41460.3 |  | 45606.3 |  | 39880.5 |  | 36063.3 | 46347.3 | 44501
Flyaway |  | 27850.7 |  |  |  | -- |  | -- |  | 32673.3 |  | 30453.8 | -- | 36368
Recurring |  | 27001.3 |  |  |  | -- |  | -- |  | 31211.1 |  | 29575.6 | -- | 34773.6
Non Recurring |  | 849.4 |  |  |  | -- |  | -- |  | 1462.2 |  | 878.2 | -- | 1594.4
Support |  | 5144.6 |  |  |  | -- |  | -- |  | 7207.2 |  | 5609.5 | -- | 8133
Other Support |  | 4304.8 |  |  |  | -- |  | -- |  | 6091.1 |  | 4709.4 | -- | 6920.3
Initial Spares |  | 839.8 |  |  |  | -- |  | -- |  | 1116.1 |  | 900.1 | -- | 1212.7
MILCON |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Acq O&M |  | 0 |  |  |  | 0 |  | -- |  | 0 |  | 0 | 0 | 0
Total |  | 38884.7 |  |  |  | 47355.5 |  | N/A |  | 45775.7 |  | 41637.3 | 51904.9 | 50058.6
Confidence Level for Current APB Cost 50% - The Program of Record&nbsp;(PoR) decreased from 565 to 552 due to a reduction in procurement quantities in President's Budget (PB) Congress added an additional 11 F/A- 18E aircraft to the program profile. These additional aircraft will be incorporated into the PoR with the next budget submission.
Quantity |  |  | SAR Baseline Prod Est |  |  |  | Current APB Production |  |  |  | Current Estimate
RDT&E |  |  | 0 |  |  |  | 0 |  |  |  | 0
Procurement |  |  | 458 |  |  |  | 565 |  |  |  | 552
Total |  |  | 458 |  |  |  | 565 |  |  |  | 552
The Program of Record (PoR) decreased from 565 to 552 due to a reduction in procurement quantities in President's Budget (PB) 2014.
Congress added an additional 11 F/A-18E aircraft to the program profile. These additional aircraft will be incorporated into the PoR with the next budget submission.

## Table 15
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2014 President's Budget / December 2012 SAR (TY$ M)
RDT&E | 5557.6 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5557.6
Procurement | 42173 |  |  | 2083.7 |  |  | 244.3 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 44501
MILCON | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
Acq O&M | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
PB 2014 Total | 47730.6 |  |  | 2083.7 |  |  | 244.3 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 50058.6
PB 2013 Total | 47761 |  |  | 2083.7 |  |  | 1154 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 50998.7
Delta | -30.4 |  |  | 0 |  |  | -909.7 |  |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | -940.1
Program funding and production quantities listed in this SAR are consistent with the FY 2014 President's Budget (PB). The FY 2014 PB did not reflect the enacted DoD appropriation for FY 2013, nor sequestration; it reflected the President's requested amounts for FY 2013.
Appropriation |  | Prior | FY2013 |  |  | FY2014 |  |  | FY2015 |  |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  |  | To Complete |  | Total
Quantity | Undistributed |  |  |  | Prior |  |  | FY2013 |  | FY2014 |  | FY2015 |  | FY2016 |  |  | FY2017 |  |  | FY2018 |  | To Complete |  | Total
Development | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0
Production | 0 |  |  |  | 526 |  |  | 26 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 552
PB 2014 Total | 0 |  |  |  | 526 |  |  | 26 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 552
PB 2013 Total | 0 |  |  |  | 526 |  |  | 26 |  | 13 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 565
Delta | 0 |  |  |  | 0 |  |  | 0 |  | -13 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | -13

## Table 16
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1992 | -- | -- | -- | -- | -- | -- | 349.5
1993 | -- | -- | -- | -- | -- | -- | 842.1
1994 | -- | -- | -- | -- | -- | -- | 1396.2
1995 | -- | -- | -- | -- | -- | -- | 1246
1996 | -- | -- | -- | -- | -- | -- | 801.1
1997 | -- | -- | -- | -- | -- | -- | 345.4
1998 | -- | -- | -- | -- | -- | -- | 234.6
1999 | -- | -- | -- | -- | -- | -- | 195.6
2000 | -- | -- | -- | -- | -- | -- | 132.1
2001 | -- | -- | -- | -- | -- | -- | 13.9
2002 | -- | -- | -- | -- | -- | -- | 1.1
Subtotal | -- | -- | -- | -- | -- | -- | 5557.6

## Table 17
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
1992 | -- | -- | -- | -- | -- | -- | 391.7
1993 | -- | -- | -- | -- | -- | -- | 922.4
1994 | -- | -- | -- | -- | -- | -- | 1501.2
1995 | -- | -- | -- | -- | -- | -- | 1314.4
1996 | -- | -- | -- | -- | -- | -- | 831
1997 | -- | -- | -- | -- | -- | -- | 354
1998 | -- | -- | -- | -- | -- | -- | 238.5
1999 | -- | -- | -- | -- | -- | -- | 196.5
2000 | -- | -- | -- | -- | -- | -- | 130.8
2001 | -- | -- | -- | -- | -- | -- | 13.6
2002 | -- | -- | -- | -- | -- | -- | 1.1
Subtotal | -- | -- | -- | -- | -- | -- | 5895.2

## Table 18
Annual Funding TY$
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | 233.5 | -- | -- | 233.5 | -- | 233.5
1997 | 12 | 1471.5 | -- | 200 | 1671.5 | 436.8 | 2108.3
1998 | 20 | 1678.7 | -- | 163.4 | 1842.1 | 331 | 2173.1
1999 | 30 | 2237.9 | -- | 195.5 | 2433.4 | 451.3 | 2884.7
2000 | 36 | 2230.9 | -- | 85.9 | 2316.8 | 580.3 | 2897.1
2001 | 39 | 2377.2 | -- | 63.4 | 2440.6 | 524 | 2964.6
2002 | 48 | 2651.8 | -- | 72.7 | 2724.5 | 531.2 | 3255.7
2003 | 45 | 2684.5 | -- | 71 | 2755.5 | 482.1 | 3237.6
2004 | 42 | 2529.2 | -- | 168 | 2697.2 | 503.6 | 3200.8
2005 | 42 | 2560.9 | -- | 75.8 | 2636.7 | 401.1 | 3037.8
2006 | 38 | 2209.2 | -- | 44.6 | 2253.8 | 514.2 | 2768
2007 | 37 | 2175.7 | -- | 39.8 | 2215.5 | 474.8 | 2690.3
2008 | 37 | 2190.6 | -- | 56.7 | 2247.3 | 537.5 | 2784.8
2009 | 23 | 1396.5 | -- | 88.6 | 1485.1 | 404 | 1889.1
2010 | 18 | 1043.9 | -- | 36.2 | 1080.1 | 399.6 | 1479.7
2011 | 31 | 1703.4 | -- | 70.5 | 1773.9 | 467 | 2240.9
2012 | 28 | 1859.3 | -- | 67.3 | 1926.6 | 400.4 | 2327
2013 | 26 | 1538.9 | -- | 95 | 1633.9 | 449.8 | 2083.7
2014 | -- | -- | -- | -- | -- | 244.3 | 244.3
Subtotal | 552 | 34773.6 | -- | 1594.4 | 36368 | 8133 | 44501

## Table 19
Annual Funding BY$
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
1996 | -- | 239.3 | -- | -- | 239.3 | -- | 239.3
1997 | 12 | 1495.2 | -- | 203.2 | 1698.4 | 443.8 | 2142.2
1998 | 20 | 1686.1 | -- | 164.1 | 1850.2 | 332.5 | 2182.7
1999 | 30 | 2219.3 | -- | 193.9 | 2413.2 | 447.5 | 2860.7
2000 | 36 | 2183.4 | -- | 84.1 | 2267.5 | 567.9 | 2835.4
2001 | 39 | 2299.1 | -- | 61.3 | 2360.4 | 506.8 | 2867.2
2002 | 48 | 2532.7 | -- | 69.4 | 2602.1 | 507.4 | 3109.5
2003 | 45 | 2513.7 | -- | 66.5 | 2580.2 | 451.4 | 3031.6
2004 | 42 | 2307.4 | -- | 153.3 | 2460.7 | 459.4 | 2920.1
2005 | 42 | 2272.3 | -- | 67.3 | 2339.6 | 355.9 | 2695.5
2006 | 38 | 1907.4 | -- | 38.5 | 1945.9 | 443.9 | 2389.8
2007 | 37 | 1835.6 | -- | 33.6 | 1869.2 | 400.6 | 2269.8
2008 | 37 | 1820.7 | -- | 47.1 | 1867.8 | 446.8 | 2314.6
2009 | 23 | 1144.3 | -- | 72.6 | 1216.9 | 331.1 | 1548
2010 | 18 | 836.3 | -- | 29 | 865.3 | 320.2 | 1185.5
2011 | 31 | 1332.7 | -- | 55.2 | 1387.9 | 365.4 | 1753.3
2012 | 28 | 1426.9 | -- | 51.6 | 1478.5 | 307.4 | 1785.9
2013 | 26 | 1158.7 | -- | 71.5 | 1230.2 | 338.7 | 1568.9
2014 | -- | -- | -- | -- | -- | 180.5 | 180.5
Subtotal | 552 | 31211.1 | -- | 1462.2 | 32673.3 | 7207.2 | 39880.5

## Table 20
Cost Quantity Information
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
End Item
Recurring
Flyaway
Fiscal Year | Quantity | (Aligned with
Quantity)
BY 2000
$M
1996 | -- | --
1997 | 12 | 1493.4
1998 | 20 | 1839.1
1999 | 30 | 2200.2
2000 | 36 | 2132.9
2001 | 39 | 2359.9
2002 | 48 | 2545.6
2003 | 45 | 2516.7
2004 | 42 | 2311.8
2005 | 42 | 2274.7
2006 | 38 | 1908.2
2007 | 37 | 1864.4
2008 | 37 | 1826.4
2009 | 23 | 1141.1
2010 | 18 | 837.4
2011 | 31 | 1372.3
2012 | 28 | 1379.6
2013 | 26 | 1207.4
2014 | -- | --
Subtotal | 552 | 31211.1

## Table 21
Low Rate Initial Production
The Current Total LRIP Quantity is more than 10% of the total production quantity due to the Quadrennial Defense Review (QDR). As a result of the QDR, the total procurement quantity for the program was reduced to a range of 548 to 785 aircraft, but there was not a change to the LRIP quantity. The LRIP quantity was approved during the LRIP Defense Acquisition Board (DAB) in March 1997.
| Initial LRIP Decision | Current Total LRIP
Approval Date | 3/26/1997 3/26/1997 62 62 Milestone II ADM Milestone II ADM 1997 1997 1999 1999
Approved Quantity
Reference
Start Year
End Year

## Table 22
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Memo
Australia | 2011-04-14 |  | 357.9 | This case was implemented for the sustainment of 24 F/A-18F aircraft.
Australia | 2007-05-02 | 24 | 2474 | The Program Office has a Foreign Military Sales case with Australia for 24 F/A-18F aircraft. This case was implemented for acquisition and initial support.
Nuclear Cost
None

## Table 23
Unit Cost
Unit Cost Report
|  | BY2000 $M | BY2000 $M
Unit Cost |  | Current UCR Baseline (FEB 2011 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 47355.5 |  |  | 45775.7
Quantity | 565 |  |  | 552
Unit Cost | 83.815 |  |  | 82.927 |  |  | -1.06
Average Procurement Unit Cost (APUC)
Cost | 41460.3 |  |  | 39880.5
Quantity | 565 |  |  | 552
Unit Cost | 73.381 |  |  | 72.247 |  |  | -1.55
|  | BY2000 $M | BY2000 $M
Unit Cost |  | Original UCR Baseline (JUN 1992 APB) | Current Estimate (DEC 2012 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 65944.7 |  |  | 45775.7
Quantity | 1000 |  |  | 552
Unit Cost | 65.945 |  |  | 82.927 |  | 25.75
Average Procurement Unit Cost (APUC)
Cost | 59976.8 |  |  | 39880.5
Quantity | 1000 |  |  | 552
Unit Cost | 59.977 |  |  | 72.247 |  | 20.46

## Table 24
Unit Cost History
[10 empty] | BY2000 $M |  |  |  |  | TY $M
[5 empty] | Date |  |  |  |  | PAUC |  | APUC |  |  | PAUC |  |  | APUC
Original APB |  |  |  |  | JUN 1992 |  |  |  |  | 65.942 |  | 59.97 |  |  | 94.583 |  |  | 88.75
APB as of January 2006 |  |  |  |  | JUL 2003 |  |  |  |  | 86.175 |  | 75.505 |  |  | 91.968 |  |  | 81.871
Revised Original APB |  |  |  |  | N/A |  |  |  |  | N/A |  | N/A |  |  | N/A |  |  | N/A
Prior APB |  |  |  |  | JUL 2003 |  |  |  |  | 86.175 |  | 75.505 |  |  | 91.968 |  |  | 81.871
Current APB |  |  |  |  | FEB 2011 |  |  |  |  | 83.815 |  | 73.381 |  |  | 91.867 |  |  | 82.031
Prior Annual SAR |  |  |  |  | DEC 2011 |  |  |  |  | 82.395 |  | 71.961 |  |  | 90.263 |  |  | 80.427
Current Estimate |  |  |  |  | DEC 2012 |  |  |  |  | 82.927 |  | 72.247 |  |  | 90.686 |  |  | 80.618
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial PAUC Dev Est | Changes | [15 empty] | PAUC Prod Est
| Econ |  | Qty |  |  | Sch | Eng |  | Est |  | Oth |  | Spt |  | Total
94.583 -16.460 25.278 1.930 -2.510 0.670 0.000 -12.580 -3.672 90.911
Current SAR Baseline to Current Estimate (TY $M)
PAUC Prod Est |  | Changes | [13 empty] | PAUC Current Est
|  | Econ |  | Qty |  | Sch | Eng | Est |  |  | Oth |  | Spt | Total
90.911 0.460 -4.853 2.010 0.468 -2.520 0.000 4.210 -0.225 90.686

## Table 25
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Dev Est | Changes | [14 empty] | APUC Prod Est
| Econ |  | Qty |  |  | Sch | Eng | Est | Oth |  | Spt |  |  | Total
88.750 -16.090 18.461 2.200 -2.510 0.510 0.000 -12.580 -10.009 78.741
Current SAR Baseline to Current Estimate (TY $M)
APUC Prod Est | Changes | [14 empty] | APUC Current Est
| Econ | Qty |  |  | Sch |  | Eng | Est |  | Oth |  | Spt |  |  | Total
78.741 0.503 -2.781 2.010 0.468 -2.533 0.000 4.210 1.877 80.618
SAR Baseline History
Item/Event |  |  |  | SAR Planning Estimate (PE) |  |  |  | SAR Development Estimate (DE) |  |  |  |  | SAR Production Estimate (PdE) |  |  |  | Current Estimate
Milestone I |  |  |  | N/A |  |  |  | N/A |  |  |  |  | N/A |  |  |  | N/A
Milestone II |  |  |  | DEC 1991 |  |  |  | MAR 1992 |  |  |  |  | MAR 1992 |  |  |  | MAY 1992
Milestone III |  |  |  | DEC 1998 |  |  |  | JAN 2000 |  |  |  |  | JAN 2000 |  |  |  | JUN 2000
IOC |  |  |  | N/A |  |  |  | SEP 2000 |  |  |  |  | JUN 2001 |  |  |  | SEP 2001
Total Cost (TY $M) |  |  |  | 3974.4 |  |  |  | 94583 |  |  |  |  | 41637.3 |  |  |  | 50058.6
Total Quantity |  |  |  | N/A |  |  |  | 1000 |  |  |  |  | 458 |  |  |  | 552
Prog. Acq. Unit Cost (PAUC) |  |  |  | N/A |  |  |  | 94.583 |  |  |  |  | 90.911 |  |  |  | 90.686

## Table 26
Cost Variance
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Prod Est) | 5574 | 36063.3 | -- | 41637.3
Previous Changes
Economic | -23.7 | 170.6 | -- | 146.9
Quantity | -- | 6942.6 | -- | 6942.6
Schedule | -- | 1109.4 | -- | 1109.4
Engineering | -- | 258.3 | -- | 258.3
Estimating | 7.3 | -1299.4 | -- | -1292.1
Other | -- | -- | -- | --
Support | -- | 2196.3 | -- | 2196.3
Subtotal | -16.4 | 9377.8 | -- | 9361.4
Current Changes
Economic | -- | 107 | -- | 107
Quantity | -- | -1076.1 | -- | -1076.1
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -98.8 | -- | -98.8
Other | -- | -- | -- | --
Support | -- | 127.8 | -- | 127.8
Subtotal | -- | -940.1 | -- | -940.1
Total Changes | -16.4 | 8437.7 | -- | 8421.3
CE - Cost Variance | 5557.6 | 44501 | -- | 50058.6
CE - Cost & Funding | 5557.6 | 44501 | -- | 50058.6

## Table 27
Summary Base Year 2000 $M
| RDT&E |  | Proc |  | MILCON |  | Total
SAR Baseline (Prod Est) 5889.4 32995.3 -- 38884.7
Previous Changes
Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | 5421.9 |  | -- |  | 5421.9
Schedule |  | -- |  | 998.1 |  | -- |  | 998.1
Engineering |  | -- |  | 227.2 |  | -- |  | 227.2
Estimating |  | 5.8 |  | -953.7 |  | -- |  | -947.9
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 1968.9 |  | -- |  | 1968.9
Subtotal |  | 5.8 |  | 7662.4 |  | -- |  | 7668.2
Current Changes Economic |  | -- |  | -- |  | -- |  | --
Quantity |  | -- |  | -795.1 |  | -- |  | -795.1
Schedule |  | -- |  | -- |  | -- |  | --
Engineering |  | -- |  | -- |  | -- |  | --
Estimating |  | -- |  | -75.8 |  | -- |  | -75.8
Other |  | -- |  | -- |  | -- |  | --
Support |  | -- |  | 93.7 |  | -- |  | 93.7
Subtotal |  | -- |  | -777.2 |  | -- |  | -777.2
Total Changes |  | 5.8 |  | 6885.2 |  | -- |  | 6891
CE - Cost Variance |  | 5895.2 |  | 39880.5 |  | -- |  | 45775.7
CE - Cost & Funding |  | 5895.2 |  | 39880.5 |  | -- |  | 45775.7
Previous Estimate: December 2011

## Table 28
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A +107.0
Quantity variance resulting from a decrease of 13 FA-18E/F from 565 to 552. (Quantity) -609.4 -824.7
Additional quantity variance due to loss of 13 F/A-18E/F. (Quantity) (QR) | -185.7 |  |  | -251.4
Adjustment for current and prior escalation. (Estimating) | -54.5 |  |  | -70.9
Revised estimate to reflect actuals. (Estimating) | -22.1 |  |  | -29.4
Revised estimate to reflect budget controls. (Estimating) | 0.8 |  |  | 1.5
Adjustment for current and prior escalation. (Support) | -13.7 |  |  | -17.8
Increase in Other Support costs due to additional Sustaining Engineering costs. (Support) | 110.7 |  |  | 148.8
Decrease in Initial Spares. (Support) (QR) | -3.3 |  |  | -3.2
Procurement Subtotal (QR) Quantity Related | -777.2 |  |  | -940.1
(QR)

## Table 29
Contracts
Appropriation: Procurement
Contract Name Airframe Multi-Year Procurement III (MYP III)
Contractor The Boeing Company
Contractor Location 6200 JS McDonnell Blvd St. Louis, MO 63134
Contract Number, Type N00019-09-C-0019, FPIF
Award Date December 04, 2008
Definitization Date September 28, 2010
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
2770.5 2945.6 66 4506.6 4621.2 103 4506.6 4506.6
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FPIF contract.
General Contract Variance Explanation
In accordance with Defense Federal Acquisition Regulation Supplement Subpart 234.2, Earned Value Management System, a waiver was obtained and approved on June 10, 2010, by the Deputy Assistant Secretary of the Navy (Acquisition and Logistics Management), to omit Earned Value Management requirements.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to multiple funded modifications and the incorporation of Engineering Change Proposals (ECPs).
The MYP III contract value and quantities represent only the F/A-18E/F portion of the contract and do not include the EA-18G portion.

## Table 30
Appropriation: Procurement
Contract Name F414 Engine Production Lots 11-15
Contractor GE Aircraft Engines
Contractor Location 1000 Western Ave.
Lynn, MA 01905-2655
Contract Number, Type N00019-06-C-0088, FPEPA
Award Date April 26, 2006
Definitization Date September 26, 2007
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
255.9 N/A 224 1308.5 N/A 305 1308.5 1308.5
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FPEPA contract.
General Contract Variance Explanation
There is no contract performance reporting required on this Fixed Price Economic Price Adjustment (FPEPA) contract.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to exercising contract options, incorporation of Engine Program Descriptions (EPDs) in support of the F414 Component Improvement Program (CIP), and procurement of long lead material in support of FY 2010 and FY 2011 engines.
This contract is more than 90% complete; therefore, this is the final report for this contract.
The original quantity of 224 represents the total potential F/A-18E/F engine quantity. This quantity is based upon the base contract (68) and all option year (156) engines to be procured. This report solely reflects the domestic Program of Record (PoR) quantities.

## Table 31
Appropriation: Procurement
Contract Name F414 Engine Production Lots 16-17
Contractor GE Aircraft Engines
Contractor Location 1000 Western Ave.
Lynn, MA 01905-2655
Contract Number, Type N00019-11-C-0045, FFP
Award Date April 20, 2011
Definitization Date September 26, 2012
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
6.6 N/A 0 440.0 N/A 110 440.0 440.0
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP contract.
Contract Comments
This is the first time this contract is being reported.
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to the FY 2012 procurement of 56 engines and devices, two spare engines, one spare module as well as the FY 2013 procurement of long lead material, 52 engines and devices. This report solely reflects the domestic Program of Record (PoR) quantities.
The original contract value only reflects the procurement of FY 2013 F414 logistics and engineering support.

## Table 32
Appropriation: Procurement
Contract Name System Configuration Sets (SCS) Contract
Contractor The Boeing Company
Contractor Location 6200 JS McDonnell Blvd St. Louis, MO 63166
Contract Number, Type N68936-09-D-0002, IDIQ/CPIF/CPFF
Award Date December 19, 2008
Definitization Date December 19, 2008
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
905.3 N/A 80 899.9 N/A 67 899.9 899.9
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this IDIQ/CPIF/CPFF contract.
General Contract Variance Explanation
In accordance with a contract addendum to Federal Acquisition Regulation Clause 52.234-4, Earned Value Management (EVM) will be implemented on individual orders. As stated in the contract, EVM is not applicable at the basic contract level.
Contract Comments
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a contract modification realigning certain efforts from a Cost Plus Incentive Fee Contract Line Item Number (CLIN) to a Cost Plus Fixed Fee Level of Effort CLIN.
The initial contract price target for the basic contract reflects the total negotiated value at contract award. The current contract price target for the basic contract reflects the revised contract value.
The value, quantities, and funding for each delivery or task order, issued under this Indefinite-Delivery, Indefinite- Quantity contract, are individually negotiated.
This contract includes shared costs and quantities for the F/A-18E/F and EA-18G platforms; therefore, all data is duplicated in the EA-18G SAR.

## Table 33
Deliveries and Expenditures
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 0 |  | 0 |  | 0 | --
Production | 506 |  | 506 |  | 552 | 91.67%
Total Program Quantities Delivered | 506 |  | 506 |  | 552 | 91.67%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 50058.6 | Years Appropriated |  |  | 22
Expenditures To Date | 42116.9 | Percent Years Appropriated |  |  | 95.65%
Percent Expended | 84.14% | Appropriated to Date |  |  | 49814.3
Total Funding Years | 23 | Percent Appropriated |  |  | 99.51%
The above data is current as of 3/26/2013.

## Table 34
Operating and Support Cost
F/A-18E/F
Assumptions and Ground Rules
Cost Estimate Reference: Current Program: F/A-18 E/F
Flight Hours per aircraft per month: 28.2
Number of 12 Primary Authorized Aircraft (PAA) F/A-18E/F Squadrons in FY 2016: 19 Number of 10 PAA F/A-18E/F Squadrons in FY 2016: 11
Fleet Readiness Squadron (FRS) at 12-14 E & 29-31 F: 2 Consumption rate, gallons per hour: 1,291
Petroleum, Oil, and Lubricant (POL) Cost, JP-5 per Gallon FY 2000 $: 0.73 Number of Aircraft Operating Years: 9,128
Operational Service Life (OSL): 6,000 Flight Hours Date of Estimate: February 2013
Source: Air-4.2 Operating & Support (O&S) Cost Estimate
Sustainment Strategy:
The F/A-18E/F support strategy is based on the following basing and utilization plans. The current Program of Record (PoR) consists of 19 - 12 PAA F/A-18E/F squadrons and 11 - 10 PAA Carrier Air Wing (CVW) deployable squadrons stationed at either Naval Air Station (NAS) Lemoore, CA, or NAS Oceana, VA. Two Fleet Replacement Squadrons (FRS) - NAS Lemoore and NAS Oceana - are comprised of 85 aircraft. Twenty-two additional aircraft are either currently stationed, or will be stationed at various test and training units throughout the Continental United States (CONUS). Additionally, four fleet squadrons are forward deployed to Atsugi, Japan. The majority of the airframe and engine components are supported via three-level maintenance plans. Avionics components, on the other hand, are predominantly supported by two-level maintenance plans.
The total F/A-18E/F aircraft procurement quantity is 552, which have a service life of 20 years. Two of the aircraft were used as EA-18G System Development and Demonstration (SDD) assets. Eight of the aircraft have been lost through attrition as Category 1 strikes.
Antecedent Information: Antecedent Program: F/A-18C/D
Consumption Rate, Gallons per Hour: 1,127
Number of Aircraft Operating Years: 9,128 (See Total O&S Cost Comments below) Flight Hours per Aircraft per Month: 23.5
POL Cost, JP-5 per gallon FY 2000 $: 0.73
The variable components of the cost estimate, such as the Flying Hour Program (FHP), are based on the number of aircraft operational years available and flight hours. Some elements, such as personnel and associated indirect and training costs, are dependent on the number of squadrons and manning requirements. Other elements which are fixed in nature, such as sustaining engineering, are based on a cost-per-aircraft. Modification, airframe, support equipment and depot maintenance are estimated as the total requirement and applied on a cost-per- aircraft basis.
O&S Cost Variance Explanation
Variance Category Causal Factor Impact

## Table 35
Cost Estimating Methodologies N/A N/A
Aviation Type/Model/Series Report
Cost Data Updates
Rates
Technical Inputs
Programmatics
(ATMSR) weapons training expendable stores and temporary additional duty rates rose significantly. The 2013 composite rates were lower than the 2012 rates, primarily due to a
$1,880 reduction in the Medicare Eligible Retiree Health Care (MERHC) accrual rate.
The Aviation Depot Level Repairable (AVDLR) pricing for components previously managed Eligible Retiree Health Care (MERHC) accrual rate under F/A-18E/F Integrated Readiness Support Teaming (FIRST) rose significantly in 2013. This was offset by a $663M reduction in modifications during the FYDP.
The President's Budget (PB) 2014 removed 13 pipeline and attrition aircraft, resulting in a loss of 40 aircraft operating years.
1.3%
-0.1%
-0.6%
-0.1%
Estimated Technical & Programmatic Updates
• Aircraft inventory updated to remove 13 aircraft
– 11 during the Office of the Secretary of Defense (OSD) 2014 Bill Payer
– Two during President's Budget (PB) 2014 as an End Game Offset
• Program of Record (PoR) life cycle end year changed to 2035
• Number of aircraft operating years decreased
Unitized O&S Costs BY2000 $K
Cost Element | F/A-18E/F Average Annual Cost per Aircraft | F/A-18C/D (Antecedent) Average Annual Cost per Aircraft
Unit-Level Manpower | 1.122 | 0.983
Unit Operations | 0.497 | 0.289
Maintenance | 1.76 | 2.097
Sustaining Support | 0.084 | 0.078
Continuing System Improvements | 0.518 | 0.524
Indirect Support | 0.227 | 0.204
Other | 0 | 0
Total | 4.208 | 4.175
Unitized Cost Comments:
The Average Annual Cost Per Unit for the F/A-18E/F is calculated by dividing the total O&S cost by the total operational aircraft years for the program.

## Table 36
Total O&S Cost $M
| Current Production APB Objective/Threshold | Current Estimate
| F/A-18E/F | F/A-18E/F | F/A-18C/D (Antecedent)
Base Year | 36961.7 40657.9 38410.0 38112.0
Then Year | 65103.8 N/A 67505.0 N/A
Total O&S Costs Comments:
For comparison purposes, the base year antecedent total O&S costs are the product of the antecedent’s average annual cost per aircraft and the operational aircraft years of the new F/A-18E/F aircraft.
Disposal Costs
While disposal costs are not part of the Cost Assessment and Program Evaluation (CAPE) 2007 O&S Cost Element Structure (CES) and are not included in the totals above, the Life Cycle Cost (LCC) impact of disposal costs has been estimated at $58.9M in Base Year (BY) 2000 dollars and $99.5M in Then Year (TY) dollars.