## Table 1
Selected Acquisition Report (SAR)
RCS: DD-A&T(Q&A)823-367
HIMARS
As of December 31, 2011
Defense Acquisition Management Information Retrieval
(DAMIR)

## Table 2
Table of Contents
Program Information |  | 3
Responsible Office |  | 3
References |  | 3
Mission and Description |  | 3
Executive Summary |  | 4
Threshold Breaches |  | 5
Schedule |  | 6
Performance |  | 7
Track To Budget |  | 9
Cost and Funding |  | 10
Low Rate Initial Production |  | 16
Nuclear Cost |  | 17
Foreign Military Sales |  | 17
Unit Cost |  | 18
Cost Variance |  | 21
Contracts |  | 24
Deliveries and Expenditures |  | 30
Operating and Support Cost |  | 31

## Table 3
Program Information
Designation And Nomenclature (Popular Name)
High Mobility Artillery Rocket System (HIMARS)
DoD Component
Army
Responsible Office
Responsible Office
COL Gary Stephens | Phone | 256-876-1195
Project Manager | Fax | 256-955-7958
Precision Fires Rocket & Missile Sys | DSN Phone | 746-1195
ATTN: SFAE-MSLS-PF Redstone Arsenal, AL 35898-8000 | DSN Fax | 645-8820
gary.stephens1@us.army.mil | Date Assigned | July 25, 2011
References
SAR Baseline (Production Estimate)
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated August 17, 2005
Approved APB
Army Acquisition Executive (AAE) Approved Acquisition Program Baseline (APB) dated August 17, 2005
Mission and Description
The High Mobility Artillery Rocket System (HIMARS) fully supports the joint early-entry expeditionary forces, contingency forces, and Modular Fires Brigades. HIMARS is a C-130 transportable (combat loaded), wheeled, indirect fire launcher system that is capable of firing all rockets and missiles in the current and future Multiple Launch Rocket System (MLRS) Family of Munitions (MFOM) to include Guided Multiple Launch Rocket System (GMLRS) (Dual Purpose Improved Conventional Munition (DPICM) and Unitary) and Army Tactical Missile System (ATACMS) (Block I, II, and Unitary). The HIMARS launcher is mounted on a modified Family of Medium Tactical Vehicles (FMTV) 6X6 all-wheel drive 5-ton truck chassis. HIMARS provides rocket/missile capability to joint, current and future forces through a lighter weight, more deployable system in both early and forced entry scenarios. The HIMARS mission, as part of the MLRS fleet of launchers, is to provide field artillery medium and long-range rocket and long- range missile fires in support of Brigade Combat Teams. HIMARS, as part of the Modular Fires Brigade, provides fires that shape the battlefield, and shield the force. HIMARS will replace select MLRS M270 launcher units, as well as selected M198 Howitzer units. The United States Marine Corps will procure two battalions of HIMARS.

## Table 4
Executive Summary
The Sixth and Final Full Rate Production (FRP VI) contract was awarded on December 23, 2010, for 44 launchers for the US Army. The objective armored cab design, known as the Increased Crew Protection (ICP), was cut into production in FY 2009 (FRP III) and was applied via a modificaiton program to the remainder of the fleet. 13 HIMARS battalions have been fielded to date and the four remaining future fieldings are on track to be complete by the end of FY13. On August 17, 2011, the U.S. Army accepted formal delivery of the 300th HIMARS launcher, from Lockheed Martin at their production facility in Camden, AR and this milestone denotes that the Army has attained 80% of its Army Procurement Objective of 375 platforms. The 375th HIMARS chasis was delivered to the US Army on December 14, 2011 and denotes that the Army will be able to attain 100% of its Army Aquisition Objective of 375 platforms. In FY 2011, the Army successfully demonstrated the new HIMARS "Hot Panel" capability. This enables the HIMARS launcher's fire control system to remain initialized during air transport. It also allows HIMARS to monitor its position via a C-130's/ C-17's aircraft's Global Positioning System (GPS) while in flight and execute a fire mission immediately after disembarkation, thus reducing mission time on the ground. This capability was demonstrated and verified during a joint tactical scenario conducted on April 27, 2011. The M142 HIMARS has been successfully and continuously employed in combat operations by both US Army and Marine Corps units in the Southwest Asia Theater since 2003. HIMARS launchers have greatly contributed to the war efforts in both Iraq and Afghanistan. The HIMARS program won the William J. Perry Precision Strike Award for outstanding combat effectiveness in 2008 and the Secretary of Defense Performance-Based Logistics Award for the second time in 2009 for its Life Cycle Contractor Support (LCCS) program, the only program in the Defense Department to do so.
There are no significant software-related issues with this program at this time.

## Table 5
Threshold Breaches
APB Breaches
Schedule Performance
Cost RDT&E Procurement MILCON
Acq O&M
Unit Cost PAUC APUC
Nunn-McCurdy Breaches
Current UCR Baseline
PAUC None
APUC None
Original UCR Baseline
PAUC None
APUC None

## Table 6
Schedule
Milestones | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Current Estimate
Milestone B | DEC 1999 | DEC 1999 | JUN 2000 | DEC 1999
Milestone C | MAR 2003 | MAR 2003 | SEP 2003 | MAR 2003
LRIP Contract Award | APR 2003 | APR 2003 | OCT 2003 | APR 2003
IOTE
Start | SEP 2004 | SEP 2004 | MAR 2005 | SEP 2004
Finish | DEC 2004 | DEC 2004 | JUN 2005 | NOV 2004
FRP IPR | JUN 2005 | JUN 2005 | DEC 2005 | JUN 2005
FUE | MAR 2005 | MAR 2005 | SEP 2005 | MAR 2005
Acronyms And Abbreviations
FRP - Full Rate Production FUE - First Unit Equipped
IOTE - Initial Operational Test and Evaluation IPR - Interim Program Review
LRIP - Low Rate Initial Production
Change Explanations
None

## Table 7
Performance
Characteristics | SAR Baseline Prod Est | Current APB Production Objective/Threshold |  | Demonstrated Performance | Current Estimate
Reaction Time Total Mission Cycle (Rockets) (Min) | 9 | 9 | 13 | 12:59 | 12:59
Transportability (fully combat loaded)
C130 Load (min) | 25 | N/A | N/A | N/A | N/A
C130 Off-Load (min) | 5 | N/A | N/A | N/A | N/A
Fire All Current and Future MFOM | No degradation in MFOM effectiveness | No degradation in MFOM effectiveness | No degradation in MFOM effectiveness | Effectiveness equivalent to M270/ M270A1 demonstrate d performance | No degradation in MFOM effectiveness
Interoperability w/FA Voice and Digital Systems | Use AFATDS | N/A | N/A | N/A | N/A
Reload Cycle Time (min) | 4 | 4 | 7 | 5:35 | 5:35
Block II Enhanced C2 | Perform technical and tactical fire control using JVMF operating on the T1 | Perform technical and tactical fire control using JVMF operating on the T1 | Receive and execute fire mission digitally from FA Sensor | Successfully used digital communicati ons | Must be able to receive and execute fire missions digitally from field artillery sensors.
Block II Increased Crew Protection | Cab survives direct hit by Artillery: 155 frag @ 60m; Ammo: 7.62 mm x51 AP, 7.65mm x 54R API | Cab survives direct hit by Artillery: 155 frag @ 60m; Ammo: 7.62mm x51 AP, 7.65mm x 54R API | Cab survives direct hit by Artillery: 155 frag @ 80m; Ammo: 7.62mm x39 API | Successfully qualified ICP cab to required protection level except for multiple glass hits. Working on new glass recipe. | Cab survives direct hit by Artillery: 155 frag @ 60m; Ammo: 7.62mm x 51 AP, 7.65mm x 54R API
Block II Improved Initialization | Transition from power- onto an operational ready state in 5.5 mins | Transition from power- onto an operational ready state in 5.5 mins | Transition from power- onto an operational ready state in 4 mins | Successfully completed three hot panel exercises that | Transition from power- onto an operational ready state in 5.5 mins

## Table 8
| given a stored heading, valid location and valid GPS keys | given a stored heading, valid location and valid GPS keys | given a stored heading, valid location and valid GPS keys | demonstrate d reduced power-on to operational readiness time | given a stored heading, valid location and valid GPS keys
Block II Reliability
Mean Time Between Essential Function Failures (MTBEFF) (hrs) | 45 | 45 | 34 | 152 | >41
Mean Time Between System Aborts (MTBSA) (hrs) | 81 | 81 | 58 | 259 | >70
Requirements Source: Operational Requirements Document (ORD), dated January 5, 2004
Acronyms And Abbreviations
@ - At
AFATDS - Advanced Field Artillery Tactical Data System APB - Aquisition Program Baseline
API - Armor Piercing Incindeary FA - Field Artillery
frag - Fragments
GPS - Global Positioning System Hrs - Hours
ICP - Increased Crew Protection
JVMF - Joint Variable Message Format KPP - Key Performance Parameter
m - Meters
MFOM - Multiple Launch Rocket System (MLRS) Family of Munitions min - Minutes
mm - Millimeters
MTBEFF - Mean Time Between Essential Function Failures MTBSA - Mean Time Between System Aborts
Change Explanations
None
Memo
Demonstrated performance values were collected during System Development and Demonstration (SDD) testing, Production Qualification Testing (PQT) II, and the joint HIMARS/GMLRS IOT&E (Guided Multiple Launch Rocket System Initial Operational Test and Evaluation). Demonstrated performance met Acquisition Program Baseline threshold requirements. Block II reliability requirements were demonstrated during continued reliability testing through November 14, 2006.

## Table 9
Track To Budget
RDT&E
APPN 2040 | BA 07 Project 090 |  | PE 0603778A MLRS HIMARS |  | (Army) (Shared)
The HIMARS Program of Record will complete production in FY 2013. RDT&E funds FY 2013 and beyond apply to post production modifications and are not reflected in this report. The current program schedule shows HIMARS will be 90% delivered in the 3rd quarter of FY 2012.
Procurement
APPN 2032 |  | BA 02 |  | PE 0603778A |  | (Army)
|  | ICN C03000 ICN C03001 ICN CA0250 |  | HIMARS Launcher HIMARS Training Devices Initial Spares, HIMARS |  | (Sunk)
C02901 is the parent line.

## Table 10
Cost and Funding
Cost Summary
Total Acquisition Cost and Quantity
TY $M
SAR Baseline Prod Est | Current APB Production Objective |  |  | Current Estimate
|  | BY2003 $M | [5 empty] | BY2003 $M
Appropriation |  | SAR Baseline Prod Est |  |  | Current APB Production Objective/Threshold |  |  | Current Estimate
RDT&E |  | 206.3 |  |  | 235.7 |  | 259.3 | 242 |  | 206.4 | 239.6 | 248.8
Procurement |  | 3421.1 |  |  | 1856.1 |  | 2041.7 | 1516.9 |  | 4074.9 | 2129.7 | 1742
Flyaway |  | 3047.1 |  |  | -- |  | -- | 1251.2 |  | 3626.3 | -- | 1435.2
Recurring |  | 3024.1 |  |  | -- |  | -- | 1232.1 |  | 3601.6 | -- | 1413.4
Non Recurring |  | 23 |  |  | -- |  | -- | 19.1 |  | 24.7 | -- | 21.8
Support |  | 374 |  |  | -- |  | -- | 265.7 |  | 448.6 | -- | 306.8
Other Support |  | 228.6 |  |  | -- |  | -- | 201.9 |  | 273 | -- | 232.7
Initial Spares |  | 145.4 |  |  | -- |  | -- | 63.8 |  | 175.6 | -- | 74.1
MILCON |  | 84.2 |  |  | 0 |  | -- | 0 |  | 107.1 | 0 | 0
Acq O&M |  | 0 |  |  | 0 |  | -- | 0 |  | 0 | 0 | 0
Total |  | 3711.6 |  |  | 2091.8 |  | N/A | 1758.9 |  | 4388.4 | 2369.3 | 1990.8
Quantity |  |  | SAR Baseline Prod Est |  |  | Current APB Production |  |  | Current Estimate
RDT&E |  |  | 6 |  |  | 6 |  |  | 6
Procurement |  |  | 888 |  |  | 450 |  |  | 375
Total |  |  | 894 |  |  | 456 |  |  | 381

## Table 11
Cost and Funding
Funding Summary
Appropriation and Quantity Summary FY2013 President's Budget / December 2011 SAR (TY$ M)
Appropriation | Prior | FY2012 |  | FY2013 |  | FY2014 | FY2015 |  | FY2016 |  | FY2 | 17 | To Complete |  | T | otal
RDT&E | 242.7 | 6.1 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 248.8
Procurement | 1697.3 | 32.6 |  |  | 12.1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1742
MILCON | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acq O&M | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
PB 2013 Total | 1940 | 38.7 |  |  | 12.1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1990.8
PB 2012 Total | 1948.4 | 38.7 |  |  | 21.4 | 1.6 | 1.6 |  | 1.6 |  | 0 |  | 0 |  | 2013.3
Delta | -8.4 | 0 |  |  | -9.3 | -1.6 | -1.6 |  | -1.6 |  | 0 |  | 0 |  | -22.5
Quantity | ndistributed |  | Prior |  | FY2012 | FY2013 | FY2014 | FY2015 |  | FY2016 |  | FY2017 |  | To Complete |  | Total
Development | 6 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 6
Production | 0 |  | 375 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 375
PB 2013 Total | 6 |  | 375 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 381
PB 2012 Total | 6 |  | 375 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 381
Delta | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
U

## Table 12
Cost and Funding
Annual Funding By Appropriation
Annual Funding TY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1999 | -- | -- | -- | -- | -- | -- | 5
2000 | -- | -- | -- | -- | -- | -- | 34.8
2001 | -- | -- | -- | -- | -- | -- | 47.4
2002 | -- | -- | -- | -- | -- | -- | 55.6
2003 | -- | -- | -- | -- | -- | -- | 28.8
2004 | -- | -- | -- | -- | -- | -- | 18.6
2005 | -- | -- | -- | -- | -- | -- | 9.2
2006 | -- | -- | -- | -- | -- | -- | 12.1
2007 | -- | -- | -- | -- | -- | -- | 18.1
2008 | -- | -- | -- | -- | -- | -- | 4.3
2009 | -- | -- | -- | -- | -- | -- | 3.7
2010 | -- | -- | -- | -- | -- | -- | 1.9
2011 | -- | -- | -- | -- | -- | -- | 3.2
2012 | -- | -- | -- | -- | -- | -- | 6.1
Subtotal | 6 | -- | -- | -- | -- | -- | 248.8

## Table 13
Annual Funding BY$
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2003 $M | Non End Item Recurring Flyaway BY 2003 $M | Non Recurring Flyaway BY 2003 $M | Total Flyaway BY 2003 $M | Total Support BY 2003 $M | Total Program BY 2003 $M
1999 | -- | -- | -- | -- | -- | -- | 5.2
2000 | -- | -- | -- | -- | -- | -- | 35.6
2001 | -- | -- | -- | -- | -- | -- | 47.9
2002 | -- | -- | -- | -- | -- | -- | 55.6
2003 | -- | -- | -- | -- | -- | -- | 28.2
2004 | -- | -- | -- | -- | -- | -- | 17.8
2005 | -- | -- | -- | -- | -- | -- | 8.6
2006 | -- | -- | -- | -- | -- | -- | 11
2007 | -- | -- | -- | -- | -- | -- | 16
2008 | -- | -- | -- | -- | -- | -- | 3.7
2009 | -- | -- | -- | -- | -- | -- | 3.2
2010 | -- | -- | -- | -- | -- | -- | 1.6
2011 | -- | -- | -- | -- | -- | -- | 2.6
2012 | -- | -- | -- | -- | -- | -- | 5
Subtotal | 6 | -- | -- | -- | -- | -- | 242

## Table 14
Annual Funding TY$
2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2003 | 28 | 119.2 | -- | -- | 119.2 | 13.3 | 132.5
2004 | 24 | 95.6 | -- | -- | 95.6 | 28.4 | 124
2005 | 37 | 154.4 | -- | -- | 154.4 | 14.7 | 169.1
2006 | 38 | 135.2 | -- | 7.7 | 142.9 | 18.3 | 161.2
2007 | 44 | 142.8 | -- | 8.3 | 151.1 | 47.1 | 198.2
2008 | 57 | 190.5 | -- | 5.8 | 196.3 | 44.4 | 240.7
2009 | 57 | 187.7 | -- | -- | 187.7 | 52.7 | 240.4
2010 | 46 | 168.7 | -- | -- | 168.7 | 49.5 | 218.2
2011 | 44 | 175.5 | -- | -- | 175.5 | 37.5 | 213
2012 | -- | -- | 31.7 | -- | 31.7 | 0.9 | 32.6
2013 | -- | -- | 12.1 | -- | 12.1 | -- | 12.1
Subtotal | 375 | 1369.6 | 43.8 | 21.8 | 1435.2 | 306.8 | 1742

## Table 15
Annual Funding BY$
2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2003 $M | Non End Item Recurring Flyaway BY 2003 $M | Non Recurring Flyaway BY 2003 $M | Total Flyaway BY 2003 $M | Total Support BY 2003 $M | Total Program BY 2003 $M
2003 | 28 | 114.5 | -- | -- | 114.5 | 12.8 | 127.3
2004 | 24 | 89.4 | -- | -- | 89.4 | 26.6 | 116
2005 | 37 | 140.5 | -- | -- | 140.5 | 13.4 | 153.9
2006 | 38 | 120.4 | -- | 6.9 | 127.3 | 16.2 | 143.5
2007 | 44 | 124.7 | -- | 7.2 | 131.9 | 41.2 | 173.1
2008 | 57 | 163.8 | -- | 5 | 168.8 | 38.2 | 207
2009 | 57 | 159.4 | -- | -- | 159.4 | 44.7 | 204.1
2010 | 46 | 140.7 | -- | -- | 140.7 | 41.3 | 182
2011 | 44 | 143.7 | -- | -- | 143.7 | 30.6 | 174.3
2012 | -- | -- | 25.5 | -- | 25.5 | 0.7 | 26.2
2013 | -- | -- | 9.5 | -- | 9.5 | -- | 9.5
Subtotal | 375 | 1197.1 | 35 | 19.1 | 1251.2 | 265.7 | 1516.9

## Table 16
Cost Quantity Information
2032 ¦ Procurement ¦ Missile Procurement, Army
End Item
Recurring
Flyaway
Fiscal Year | Quantity | (Aligned with
Quantity)
BY 2003
$M
2003 | 28 | 114.5
2004 | 24 | 89.4
2005 | 37 | 140.5
2006 | 38 | 120.4
2007 | 44 | 124.8
2008 | 57 | 164
2009 | 57 | 160
2010 | 46 | 141.9
2011 | 44 | 141.6
2012 | -- | --
2013 | -- | --
Subtotal | 375 | 1197.1
Low Rate Initial Production
|  | Initial LRIP Decision | Current Total LRIP
Approval Date |  | 12/1/1999 12/1/1999 89 89 MS B MS B 2003 2003 2007 2007
Approved Quantity
Reference
Start Year
End Year
The Current Total LRIP quantity is more than 10% of the total production quantity due to a reduction in the total quantities from the original baseline; at time of LRIP approval total production quantity was 10%. HIMARS had three Low Rate Initial Production (LRIP) contracts beginning in 2003, with the last deliveries from LRIP III taking place in February 2007.

## Table 17
Foreign Military Sales
As part of the Third Full Rate Production (FRP) contract signed December 28, 2007, in addition to the 57 HIMARS launchers contracted for the US Army, there were 20 launchers for the United Arab Emirates and 18 for Singapore. The United Kingdom also procured 15 fire control systems for $10.1M as part of the Third Low Rate Initial Production (LRIP) contract signed December 23, 2004. As part of the Fifth FRP contract signed January 27, 2010, Jordan contracted for 12 launchers.
Country | Date of Sale | Quantity | Total Cost $M | Memo
Jordan | 2010-01-27 | 12 | 53.3
Singapore | 2007-12-28 | 18 | 52.8
United Arab Emirates | 2007-12-28 | 20 | 62.6
United Kingdom | 2004-12-23 | 15 | 10.1
Nuclear Cost
None

## Table 18
Unit Cost
Unit Cost Report
|  | BY2003 $M | BY2003 $M
Unit Cost |  | Current UCR Baseline (AUG 2005 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 2091.8 |  |  | 1758.9
Quantity | 456 |  |  | 381
Unit Cost | 4.587 |  |  | 4.617 |  |  | 0.65
Average Procurement Unit Cost (APUC)
Cost | 1856.1 |  |  | 1516.9
Quantity | 450 |  |  | 375
Unit Cost | 4.125 |  |  | 4.045 |  |  | -1.94
|  | BY2003 $M | BY2003 $M
Unit Cost |  | Original UCR Baseline (MAR 2003 APB) | Current Estimate (DEC 2011 SAR) |  | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 3711.6 |  |  | 1758.9
Quantity | 894 |  |  | 381
Unit Cost | 4.152 |  |  | 4.617 |  | 11.2
Average Procurement Unit Cost (APUC)
Cost | 3421.1 |  |  | 1516.9
Quantity | 888 |  |  | 375
Unit Cost | 3.853 |  |  | 4.045 |  | 4.98

## Table 19
Unit Cost History
SAR Unit Cost History
Initial SAR Baseline to Current SAR Baseline (TY $M)
[11 empty] | BY2003 $M | [6 empty] | TY $M
[5 empty] | Date | [5 empty] | PAUC |  |  | APUC |  |  |  | PAUC |  |  | APUC
Original APB |  |  |  |  | MAR 2003 | [5 empty] | 4.152 |  |  | 3.853 |  |  |  | 4.909 |  |  | 4.589
APB as of January 2006 |  |  |  |  | AUG 2005 | [5 empty] | 4.587 |  |  | 4.125 |  |  |  | 5.196 |  |  | 4.733
Revised Original APB |  |  |  |  | N/A | [5 empty] | N/A |  |  | N/A |  |  |  | N/A |  |  | N/A
Prior APB |  |  |  |  | MAR 2003 | [5 empty] | 4.152 |  |  | 3.853 |  |  |  | 4.909 |  |  | 4.589
Current APB |  |  |  |  | AUG 2005 | [5 empty] | 4.587 |  |  | 4.125 |  |  |  | 5.196 |  |  | 4.733
Prior Annual SAR |  |  |  |  | DEC 2010 | [5 empty] | 4.678 |  |  | 4.107 |  |  |  | 5.284 |  |  | 4.705
Current Estimate |  |  |  |  | DEC 2011 | [5 empty] | 4.617 |  |  | 4.045 |  |  |  | 5.225 |  |  | 4.645
Initial PAUC Dev Est | Changes | [18 empty] | PAUC Prod Est
| Econ |  | Qty |  |  | Sch |  | Eng |  | Est |  |  | Oth |  |  | Spt |  | Total
4.824 0.000 0.000 0.000 0.000 -0.014 0.000 0.099 0.085 4.909
Current SAR Baseline to Current Estimate (TY $M)
PAUC Prod Est |  | Changes | [16 empty] | PAUC Current Est
|  | Econ |  | Qty |  |  | Sch |  | Eng | Est |  | Oth |  |  | Spt |  | Total
4.909 0.620 0.486 -0.045 0.104 -0.410 0.000 -0.439 0.316 5.225

## Table 20
Initial SAR Baseline to Current SAR Baseline (TY $M)
Initial APUC Dev Est | Changes | [11 empty] | APUC Prod Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth | Spt |  | Total
4.630 0.000 0.000 0.000 0.000 -0.141 0.000 0.100 -0.041 4.589
Current SAR Baseline to Current Estimate (TY $M)
APUC Prod Est | Changes | [11 empty] | APUC Current Est
| Econ | Qty |  | Sch | Eng | Est |  | Oth | Spt |  |  | Total
4.589 0.641 0.057 -0.046 0.000 -0.150 0.000 -0.446 0.056 4.645
SAR Baseline History
Item/Event |  |  | SAR Planning Estimate (PE) |  |  |  | SAR Development Estimate (DE) |  |  | SAR Production Estimate (PdE) |  |  |  | Current Estimate
Milestone I |  |  | N/A |  |  |  | N/A |  |  | N/A |  |  |  | N/A
Milestone B |  |  | N/A |  |  |  | DEC 1999 |  |  | DEC 1999 |  |  |  | DEC 1999
Milestone C |  |  | N/A |  |  |  | MAR 2003 |  |  | MAR 2003 |  |  |  | MAR 2003
FUE |  |  | N/A |  |  |  | MAR 2005 |  |  | MAR 2005 |  |  |  | MAR 2005
Total Cost (TY $M) |  |  | N/A |  |  |  | 4312.9 |  |  | 4388.4 |  |  |  | 1990.8
Total Quantity |  |  | N/A |  |  |  | 894 |  |  | 894 |  |  |  | 381
Prog. Acq. Unit Cost (PAUC) |  |  | N/A |  |  |  | 4.824 |  |  | 4.909 |  |  |  | 5.225

## Table 21
Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Prod Est) | 206.4 | 4074.9 | 107.1 | 4388.4
Previous Changes
Economic | 1.1 | 233.6 | -5.4 | 229.3
Quantity | -- | -2332.3 | -- | -2332.3
Schedule | -- | -17.3 | -- | -17.3
Engineering | 39.6 | -- | -- | 39.6
Estimating | 1.9 | -50.8 | -101.7 | -150.6
Other | -- | -- | -- | --
Support | -- | -143.8 | -- | -143.8
Subtotal | 42.6 | -2310.6 | -107.1 | -2375.1
Current Changes
Economic | -- | 6.8 | -- | 6.8
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -0.2 | -5.5 | -- | -5.7
Other | -- | -- | -- | --
Support | -- | -23.6 | -- | -23.6
Subtotal | -0.2 | -22.3 | -- | -22.5
Total Changes | 42.4 | -2332.9 | -107.1 | -2397.6
CE - Cost Variance | 248.8 | 1742 | -- | 1990.8
CE - Cost & Funding | 248.8 | 1742 | -- | 1990.8

## Table 22
Summary Base Year 2003 $M
| RDT | &E | Proc | MILCON | Total
SAR Baseline (Prod Est) Previous Changes |  | 206.3 | 3421.1 | 84.2 | 3711.6
Economic |  | -- | -- | -- | --
Quantity |  | -- | -1689.8 | -- | -1689.8
Schedule |  | -- | -16.6 | -- | -16.6
Engineering |  | 35.5 | -- | -- | 35.5
Estimating |  | 0.4 | -85.5 | -84.2 | -169.3
Other |  | -- | -- | -- | --
Support |  | -- | -89 | -- | -89
Subtotal |  | 35.9 | -1880.9 | -84.2 | -1929.2
Current Changes Economic |  | -- | -- | -- | --
Quantity |  | -- | -- | -- | --
Schedule |  | -- | -- | -- | --
Engineering |  | -- | -- | -- | --
Estimating |  | -0.2 | -4 | -- | -4.2
Other |  | -- | -- | -- | --
Support |  | -- | -19.3 | -- | -19.3
Subtotal |  | -0.2 | -23.3 | -- | -23.5
Total Changes |  | 35.7 | -1904.2 | -84.2 | -1952.7
CE - Cost Variance |  | 242 | 1516.9 | -- | 1758.9
CE - Cost & Funding |  | 242 | 1516.9 | -- | 1758.9
Previous Estimate: December 2010

## Table 23
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Program funding reduction to accommodate higher priorities. (Estimating) |  | -0.2 | -0.2
RDT&E Subtotal |  | -0.2 | -0.2
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | 6.8
Adjustment for current and prior escalation. (Estimating) |  | -4.1 | -4.5
Program funding reduction to accommodate higher priorities for MLRS updates. (Estimating)
Revised estimate to reflect advance procurement realized savings on vehicle chassis in FY 2010. (Estimating)
-7.2 -10.0
+7.3 +9.0
Adjustment for current and prior escalation. (Support) | -1.1 |  |  | -1.7
Decrease in Other Support to accommodate higher priorities. (Support) | -14.1 |  |  | -16.9
Decrease in Initial Spares to align with end of production line. (Support) | -4.1 |  |  | -5
Procurement Subtotal | -23.3 |  |  | -22.3

## Table 24
Contracts
Appropriation: Procurement
Contract Name LRIP III
Contractor Lockheed Martin
Contractor Location Dallas, TX 75051
Contract Number, Type DAAH01-03-C-0005/38, FFP/CPFF
Award Date December 23, 2004
Definitization Date December 23, 2004
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
109.2 N/A 37 113.7 N/A 37 113.7 113.7
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP/CPFF contract.
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.
The difference between the initial contract price target and the current contract price target is due to a change order executed to perform system level qualification, a final configuration aduit for the replacement of the gunner's display unit.
The current contract target price for this contract is $126.4M for 38 units (37 for the US Army and one for the USMC). The Army portion is $113.7M, the USMC portion is $2.6M, and there is an additional $10.1M for 15 fire control systems for the United Kingdom.
Cost and Schedule reporting is not required on the FFP portion of this contract. The value of the CPFF portion of the contract is below the $20M threshold for Earned Value Management (EVM) reporting. In lieu of EVM, the Program Management Office is using a Performance Cost Report to monitor contract expenditures against the budget. The Cost Plus Fixed Fee (CPFF) portion of this contract had a total value of $15,140,240.
This contract was completed on November 30, 2010.

## Table 25
Appropriation: Procurement
Contract Name FRP II
Contractor Lockheed Martin
Contractor Location Dallas, TX 75051
Contract Number, Type W31P4Q-06-C-0001/10, FFP/CPFF
Award Date December 28, 2006
Definitization Date December 28, 2006
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
123.9 N/A 44 130.3 N/A 44 130.3 130.3
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP/CPFF contract.
Contract Comments
The difference between the initial contract price target and the current contract price target is due to a change order executed to procure Line Replaceable Units for the new universal fire control system.
The total quantity of 60 launchers on this contract includes 44 for the US Army at $130.3M and 16 for United States Marine Corps at $43.5M.
Cost and Schedule reporting is not required on the FFP portion of this contract. The value of the CPFF portion of the contract is below the $20M threshold for Earned Value Management (EVM) reporting. In lieu of EVM, the Program Management Office is using a Performance Cost Report to monitor contract expenditures against the budget. The Cost Plus Fixed Fee (CPFF) portion of this contract had a total value of $4,740,439.

## Table 26
Appropriation: Procurement
Contract Name FRP III
Contractor Lockheed Martin
Contractor Location Dallas, TX 75051
Contract Number, Type W31P4Q-08-C-0001/1, FFP/CPFF
Award Date December 28, 2007
Definitization Date December 28, 2007
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
150.7 N/A 57 157.6 N/A 57 157.6 157.6
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP/CPFF contract.
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.
The difference between the initial contract price target and the current contract price target is due to a change order executed for effort required to qualify the new universal positioning navigational units.
The total quantity of 95 launchers on this contract includes 57 for the US Army at $157.6M, 20 for the United Arab Emirates, and 18 for Singapore.
Cost and Schedule reporting is not required on the FFP portion of this contract. The value of the CPFF portion of the contract is below the $20M threshold for Earned Value Management (EVM) reporting. In lieu of EVM, the Program Management Office is using a Performance Cost Report to monitor contract expenditures against the budget. The Cost Plus Fixed Fee (CPFF) portion of this contract had a total value of $15,281,190.

## Table 27
Appropriation: Procurement
Contract Name FRP IV
Contractor Lockheed Martin
Contractor Location Dallas, TX 75051
Contract Number, Type W31P4Q-08-C-0001/2, FFP/CPFF
Award Date December 28, 2008
Definitization Date December 28, 2008
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
161.0 N/A 57 161.0 N/A 57 161.0 161.0
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP/CPFF contract.
Contract Comments
This contract is more than 90% complete; therefore, this is the final report for this contract.
This contract is for 64 units comprised of 57 for the US Army ($161.0M) and 7 for the USMC ($19.0M).
Cost and Schedule reporting is not required on the FFP portion of this contract. The value of the CPFF portion of the contract is below the $20M threshold for Earned Value Management (EVM) reporting. In lieu of EVM, the Program Management Office is using a Performance Cost Report to monitor contract expenditures against the budget. The Cost Plus Fixed Fee (CPFF) portion of this contract had a total value of $2,100,000.

## Table 28
Appropriation: Procurement
Contract Name FRP V
Contractor Lockheed Martin
Contractor Location Dallas, TX 75051
Contract Number, Type W31P4Q-08-C-0001/3, FFP/CPFF
Award Date December 22, 2009
Definitization Date December 22, 2009
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
143.5 N/A 46 143.5 N/A 46 143.5 143.5
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP/CPFF contract.
Contract Comments
The current unit total is 58 launchers on the contract comprised of 46 for the US Army ($143.5M) and 12 for Jordan ($34.8M).
Cost and Schedule reporting is not required on the FFP portion of this contract. The value of the CPFF portion of the contract is below the $20M threshold for Earned Value Management (EVM) reporting. In lieu of EVM, the Program Management Office is using a Performance Cost Report to monitor contract expenditures against the budget. The CPFF portion of this contract had a total value of $4,275,998.

## Table 29
Appropriation: Procurement
Contract Name FRP VI
Contractor Lockheed Martin Corporation
Contractor Location Dallas, TX 75051
Contract Number, Type W31P4Q-11-C-0101, FFP/CPFF
Award Date December 23, 2010
Definitization Date December 23, 2010
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
139.6 N/A 44 139.6 N/A 44 139.6 139.6
Cost And Schedule Variance Explanations
Cost and Schedule variance reporting is not required on this FFP/CPFF contract.
Contract Comments
This contract is for 44 units for the US Army.
Cost and Schedule reporting is not required on the FFP portion of this contract. The value of the CPFF portion of the contract is below the $20M threshold for Earned Value Management (EVM) reporting. In lieu of EVM, the Program Management Office is using a Performance Cost Report to monitor contract expenditures against the budget.
TheCPFF portion of this contract had a total value of $3,300,225.

## Table 30
Deliveries and Expenditures
Deliveries To Date | Plan To Date |  | Actual To Date | Total Quantity |  | Percent Delivered
Development | 6 |  | 6 |  | 6 | 100%
Production | 325 |  | 325 |  | 375 | 86.67%
Total Program Quantities Delivered | 331 |  | 331 |  | 381 | 86.88%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 1990.8 | Years Appropriated |  |  | 14
Expenditures To Date | 1768.9 | Percent Years Appropriated |  |  | 93.33%
Percent Expended | 88.85% | Appropriated to Date |  |  | 1978.7
Total Funding Years | 15 | Percent Appropriated |  |  | 99.39%
The data above is through January 31, 2012. The HIMARS Program of Record will complete production in FY 2013. RDT&E funds for FY 2013 and beyond apply to post production modifications and are not reflected in this report. The current program schedule shows HIMARS will be 90% delivered in the 3rd quarter of FY 2012.

## Table 31
Operating and Support Cost
Assumptions And Ground Rules
The unit for tracking Operating and Support (O&S) costs is a Battalion (BN). Each BN consists of three firing batteries of six launchers for a total of 19 launchers. The estimated cost assumes 19 BNs and a HIMARS service life of 20 years. The reflected O&S costs were estimated in the March 2003 Army Cost Position (ACP). The ACP includes operating tempo, reliability/maintainability, maintenance concept, manning and logistics policies. The O&S costs are based on the Level of Repair Analysis and the ACP. Life Cycle Contractor Support is being executed for HIMARS. The M270 Basic Launcher was the antecedent system for the HIMARS.
Costs BY2003 $M
Cost Element | HIMARS Avg Annual Cost Per Battalion | MLRS M270 Avg Annual Cost Per Battalion
Unit-Level Manpower | 1.3 | 17.7
Unit Operations | 0.2 | 0.3
Maintenance | 0.1 | 1.8
Sustaining Support | 0.1 | --
Continuing System Improvements | -- | --
Indirect Support | 0.1 | 1.2
Other | -- | --
Total Unitized Cost (Base Year 2003 $) | 1.8 | 21
Total O&S Costs $M | HIMARS | MLRS M270
Base Year | 684 | 29201
Then Year | 932.8 | 44339.8
The O&S Costs were overstated in the prior SAR; estimates have been revised to reflect a reduction in Unit Level Manpower.
Disposal costs were not included.